## RBS
Randomised Branch Sampling
Step 1: Break your project down into epics and number them sequentially, starting from 1 | [6 empty] | Types
Story Points
Number of epics |  | 20 |  | <-- Record the total number of epics in the project |  |  | Tasks
Estimate project size in |  | Tasks |  | <-- Select the type of estimate to use |  |  | Scenarios
Step 2: Randomly sample 7 epics
| Random epic | Chosen epic |  | <-- Re-calculate the sheet (F9) to get a new set of samples. It is OK if you get any duplicates.
1 | 11 | 19 |  | <-- To "save" your chose samples, copy them from column C to column D. Otherwise, the random numbers will keep changing!
2 | 4 | 2
3 | 9 | 19
4 | 2 | 13
5 | 15 | 13
6 | 15 | 12
7 | 18 | 8
Step 3: Break each of the sampled epics into stories. Number the stories of each epic sequantially, starting from 1.
| Epic # | Num stories |  | <-- Record the total number of stories for each epic.
1 | 19 | 19
2 | 2 | 5
3 | 19 | 8
4 | 13 | 15
5 | 13 | 7
6 | 12 | 9
7 | 8 | 20
INTERM: Estimate the total number of stories in the project |  |  |  |  | 237.1429 | Stories
| Epic # | Num Stories | Project estimate
1 | 19 | 19 | 380
2 | 2 | 5 | 100
3 | 19 | 8 | 160
4 | 13 | 15 | 300
5 | 13 | 7 | 140
6 | 12 | 9 | 180
7 | 8 | 20 | 400
Step 4: Randomly sample one story from each epic
| Epic # | Random story | Chosen story |  | <-- To "save" your chose samples, copy them from column D to column E. Otherwise, the random numbers will keep changing!
1 | 19 | 15 | 9 |  | NOTE: The chosen story number is the number of the story *within its epic*
2 | 2 | 5 | 18
3 | 19 | 8 | 24
4 | 13 | 12 | 5
5 | 13 | 5 | 34
6 | 12 | 9 | 25
7 | 8 | 1 | 3
Step 5: Estimate the size of each of the sampled stories in Tasks
| Epic # | Story # | Tasks |  | <-- Record the estimate for each sampled story
1 | 19 | 9 | 1
2 | 2 | 18 | 1
3 | 19 | 24 | 3
4 | 13 | 5 | 3
5 | 13 | 34 | 5
6 | 12 | 25 | 5
7 | 8 | 3 | 8
OUTPUT: Estimate the total number of Tasks in the project is |  |  |  |  | 951.4286 | Tasks
| Epic # | Num Stories | Story # | Tasks | Project estimate
1 | 19 | 19 | 9 | 1 | 380
2 | 2 | 5 | 18 | 1 | 100
3 | 19 | 8 | 24 | 3 | 480
4 | 13 | 15 | 5 | 3 | 900
5 | 13 | 7 | 34 | 5 | 700
6 | 12 | 9 | 25 | 5 | 900
7 | 8 | 20 | 3 | 8 | 3200
Each number represents one possible estimate for the total size of the project based on the sampled story.
All the possible estimates are aggregated into a single best guess estimate
Each number represents one possible estimate for the total number of stories in the project based on the sampled epic
All the possible estimates are aggregated into a single best guess estimate