## Data
User Story | Day in | Day Done | Type
1 | 1 | 1 | C
2 | 2 | 5 | A
3 | 3 | 5 | O
4 | 1 | 3 | C
5 | 2 | 2 | A
6 | 1 | 3 | A
7 | 1 | 2 | C
8 | 2 | 3 | A
9 | 1 | 2 | O
10 | 1 | 3 | C
11 | 3 | 4 | A

## Calc
Day | Count Done | Count Done C | Count Done A | Count Done O | Resample Done | Re:Count Done C | Re:Count Done A | Re:Count Done O
1 | 1 | 1 | 0 | 0 | 4 | 2 | 1 | 0
2 | 3 | 1 | 1 | 1 | 2 | 1 | 0 | 0
3 | 4 | 2 | 2 | 0 | 2 | 1 | 0 | 0
4 | 1 | 0 | 1 | 0 | 1 | 2 | 1 | 1
5 | 2 | 0 | 1 | 1 | 3 | 0 | 1 | 1

## Delovery Time
Project Delivery time PLAN | Project Delivery time ACTUAL
19.8491 | 16.6667
Number of user stories | Number of user stories
19 | 11

## Type C
| Plan |  | Actual
Type | C
Count | 5 |  | 4
Avg TH L1 | 0.43519 | Resampled TH C | 1.2
Delivery time L1 | 11.4894 | Delivery time C | 3.3333

## Type A
| Plan |  | Actual
Type | A
Count | 8 |  | 5
Avg TH L2 | 2.9492 | Resampled TH A | 0.6
Delivery time L2 | 2.7126 | Delivery time A | 8.3333

## Type O
| Plan |  | Actual
Type | O
Count | 6 |  | 2
Avg TH L3 | 1.0625 | Resampled TH O | 0.4
Delivery time L3 | 5.6471 | Delivery time O | 5

## Project_Type_1
PM_Trials | 10000
PM_Lib_Provenance | FVR
|  | Meta Data | Index
Click [+] to show data
|  | Avg_TH_Leg_1 | Avg_TH_Leg_2 | Avg_TH_Leg_3 | Average_LT
| 1 | 0.43519 | 2.9492 | 1.0625 | 1.9538
| 2 | 0.42593 | 2.5932 | 0.875 | 2.2689
| 3 | 0.44444 | 2.8475 | 1.75 | 2.1176
| 4 | 0.49074 | 2.4915 | 1.5312 | 2.3992
| 5 | 0.4537 | 4.0508 | 1.4062 | 2.0756
| 6 | 0.34259 | 2.1186 | 1.8125 | 2.0966
| 7 | 0.64815 | 2.1864 | 1.0938 | 2.1218
| 8 | 0.37963 | 2.2712 | 1.0938 | 2.1891
| 9 | 0.32407 | 3.0339 | 0.96875 | 1.979
| 10 | 0.33333 | 3.5424 | 0.90625 | 2.105
| 11 | 0.37963 | 2.7458 | 1.4062 | 2.0882
| 12 | 0.48148 | 2.5254 | 1.375 | 1.8235
| 13 | 0.35185 | 2.4407 | 1.1875 | 1.9244
| 14 | 0.2963 | 3.0508 | 1.4688 | 2.1303
| 15 | 0.30556 | 3.4746 | 1.5312 | 2.4412
| 16 | 0.30556 | 2.8305 | 0.875 | 1.8571
| 17 | 0.52778 | 2.8305 | 1.0312 | 2
| 18 | 0.25 | 2.3051 | 2.4688 | 1.9076
| 19 | 0.35185 | 2.1525 | 2.2188 | 1.8908
| 20 | 0.40741 | 2.1864 | 0.96875 | 2.021
| 21 | 0.40741 | 2.9153 | 1.0625 | 2.1471
| 22 | 0.25926 | 2.678 | 1.4688 | 1.9496
| 23 | 0.38889 | 3.1695 | 1.0312 | 2.1345
| 24 | 0.46296 | 2.4068 | 0.71875 | 1.7983
| 25 | 0.36111 | 2.8644 | 0.96875 | 2.3193
| 26 | 0.53704 | 3.3051 | 1.3438 | 2.2983
| 27 | 0.44444 | 3.1186 | 0.90625 | 1.9076
| 28 | 0.52778 | 2.8983 | 0.875 | 2.2059
| 29 | 0.35185 | 2.9322 | 1.25 | 2.1555
| 30 | 0.46296 | 2.4068 | 0.9375 | 2.2647
| 31 | 0.34259 | 3.339 | 0.375 | 2.0546
| 32 | 0.39815 | 2.9153 | 1.6875 | 2.416
| 33 | 0.5463 | 2.4237 | 1.5312 | 2.3824
| 34 | 0.43519 | 2.7627 | 1.9375 | 2.042
| 35 | 0.46296 | 2.2373 | 2.5 | 2.1975
| 36 | 0.44444 | 2.5424 | 1.5 | 2.0714
| 37 | 0.36111 | 2.2881 | 1.125 | 2.1681
| 38 | 0.44444 | 2.2034 | 2.0312 | 2.2227
| 39 | 0.40741 | 3.5593 | 1.4688 | 2.0546
| 40 | 0.43519 | 2.7458 | 0.59375 | 2.042
| 41 | 0.57407 | 2.4237 | 1.5 | 2.1639
| 42 | 0.23148 | 2.5085 | 1.1875 | 1.6849
| 43 | 0.36111 | 2.5763 | 0.84375 | 2.1975
| 44 | 0.4537 | 2.8136 | 1.0625 | 2.1471
| 45 | 0.51852 | 2.5424 | 1.7812 | 2.2395
| 46 | 0.49074 | 2.5932 | 1.875 | 2.0798
| 47 | 0.39815 | 2.2542 | 1.5938 | 1.9202
| 48 | 0.46296 | 2.3051 | 1.5625 | 2.3277
| 49 | 0.52778 | 2.1864 | 1.5938 | 2.3824
| 50 | 0.55556 | 3.4746 | 1.25 | 2.0546
| 51 | 0.27778 | 2.3051 | 0.90625 | 2.4664
| 52 | 0.27778 | 1.7797 | 1.2812 | 1.8529
| 53 | 0.47222 | 3.0678 | 1.1562 | 1.9748
| 54 | 0.42593 | 3.1525 | 1.7812 | 2.0168
| 55 | 0.30556 | 1.8644 | 1.1875 | 1.958
| 56 | 0.48148 | 3.0508 | 1.0312 | 2.0252
| 57 | 0.35185 | 1.9153 | 1.25 | 2.1092
| 58 | 0.44444 | 2.5593 | 1.4062 | 1.8992
| 59 | 0.41667 | 2.0678 | 1.7188 | 2.1092
| 60 | 0.32407 | 2.2542 | 1.5625 | 2.1387
| 61 | 0.40741 | 3.8644 | 1.125 | 2.1597
| 62 | 0.41667 | 2.4746 | 1.375 | 2.1723
| 63 | 0.56481 | 2.1017 | 1.6562 | 2.2899
| 64 | 0.26852 | 2.2373 | 1.1562 | 1.979
| 65 | 0.50926 | 2.0339 | 1.0312 | 1.8824
| 66 | 0.52778 | 2.5593 | 1.125 | 2.5504
| 67 | 0.37963 | 2.9153 | 1 | 2.0042
| 68 | 0.36111 | 2.3898 | 1.25 | 2.2437
| 69 | 0.46296 | 2.5763 | 1.4062 | 2.1975
| 70 | 0.46296 | 3.1695 | 1.0938 | 1.9748
| 71 | 0.41667 | 2.4746 | 1.3438 | 1.895
| 72 | 0.36111 | 2.4915 | 1 | 2.0042
| 73 | 0.36111 | 2.5254 | 0.96875 | 1.7773
| 74 | 0.49074 | 2.5593 | 1.1875 | 2.3109
| 75 | 0.2963 | 1.8305 | 0.96875 | 2.0504
| 76 | 0.50926 | 3.3898 | 1.5625 | 2.0798
| 77 | 0.30556 | 2.1356 | 1.3438 | 2.1597
| 78 | 0.44444 | 2.5593 | 1.9062 | 1.7983
| 79 | 0.42593 | 3.1017 | 1.2812 | 2.3361
| 80 | 0.27778 | 2.4237 | 2.75 | 2.4412
| 81 | 0.30556 | 2.661 | 0.9375 | 1.7941
| 82 | 0.35185 | 2.6271 | 1.7188 | 2.0966
| 83 | 0.40741 | 2.4407 | 1.625 | 1.9538
| 84 | 0.37037 | 2.5763 | 1.875 | 2.2395
| 85 | 0.31481 | 2.6441 | 1.4375 | 2.1303
| 86 | 0.47222 | 2.7288 | 1.0938 | 2.2311
| 87 | 0.26852 | 2.0508 | 1.0938 | 1.8361
| 88 | 0.4537 | 3.2542 | 1.125 | 2.3487
| 89 | 0.33333 | 2.7458 | 1 | 1.9286
| 90 | 0.42593 | 2.4237 | 1.4688 | 2.1975
| 91 | 0.38889 | 2.7119 | 1.7812 | 2.0882
| 92 | 0.35185 | 2.1017 | 1.0625 | 1.9664
| 93 | 0.5463 | 2.1864 | 1.1562 | 1.9412
| 94 | 0.27778 | 1.4576 | 1.375 | 2.1345
| 95 | 0.37963 | 1.8814 | 2.7812 | 2.3655
| 96 | 0.34259 | 2.9661 | 1.25 | 2.1597
| 97 | 0.42593 | 2.0169 | 1.2812 | 2.1134
| 98 | 0.31481 | 2.8136 | 0.875 | 2.2647
| 99 | 0.63889 | 2.2542 | 1.3438 | 1.9916
| 100 | 0.42593 | 2.7458 | 1.0312 | 1.8067
| 101 | 0.48148 | 2.0847 | 0.84375 | 1.9748
| 102 | 0.50926 | 2.1186 | 1.4688 | 2.1387
| 103 | 0.39815 | 2.0508 | 1.625 | 2.2311
| 104 | 0.38889 | 2.5932 | 1.5625 | 2.2185
| 105 | 0.44444 | 2.5932 | 0.9375 | 2.4118
| 106 | 0.41667 | 2.8305 | 1.125 | 2.1639
| 107 | 0.30556 | 2.4915 | 1.1875 | 1.9202
| 108 | 0.31481 | 2.7288 | 1.0938 | 1.8613
| 109 | 0.57407 | 3.0339 | 1.0938 | 1.9118
| 110 | 0.37963 | 2.678 | 1.2188 | 2.3109
| 111 | 0.40741 | 2 | 1.375 | 2.2479
| 112 | 0.44444 | 2.4407 | 1.3438 | 2.437
| 113 | 0.33333 | 1.9661 | 1.5312 | 2.4034
| 114 | 0.52778 | 3.3051 | 1.4375 | 2.084
| 115 | 0.37037 | 2.2712 | 1.5 | 2.3235
| 116 | 0.38889 | 3.0847 | 1.0312 | 2.2899
| 117 | 0.44444 | 2.661 | 1.4688 | 2.0798
| 118 | 0.43519 | 2.5763 | 0.8125 | 2.1555
| 119 | 0.44444 | 2.7797 | 1.0312 | 2.2563
| 120 | 0.19444 | 3.0339 | 1.5 | 2.0126
| 121 | 0.53704 | 2.9322 | 1.75 | 2.521
| 122 | 0.33333 | 2.9661 | 1.9062 | 2.0084
| 123 | 0.36111 | 3.0678 | 0.96875 | 2.1176
| 124 | 0.33333 | 2.4915 | 1.25 | 1.7731
| 125 | 0.37037 | 2.3559 | 1.9062 | 2.0252
| 126 | 0.28704 | 1.9492 | 1.9688 | 1.7857
| 127 | 0.42593 | 2.6271 | 1.6562 | 2.1597
| 128 | 0.43519 | 2.7797 | 1.2188 | 1.9664
| 129 | 0.28704 | 2.6441 | 1.7188 | 1.8025
| 130 | 0.5 | 1.7627 | 2.2812 | 2.063
| 131 | 0.49074 | 3.1356 | 1.0625 | 1.8782
| 132 | 0.51852 | 2.6271 | 1.3125 | 1.7983
| 133 | 0.40741 | 2.9322 | 1.25 | 2.1723
| 134 | 0.48148 | 2.6271 | 1.625 | 1.979
| 135 | 0.46296 | 3.2373 | 1.2188 | 2.0168
| 136 | 0.41667 | 1.5763 | 1.3438 | 2.4622
| 137 | 0.41667 | 2.339 | 1.125 | 1.9538
| 138 | 0.43519 | 3 | 1.7188 | 2.1975
| 139 | 0.42593 | 2.661 | 1.125 | 2
| 140 | 0.25926 | 2.5254 | 1.75 | 2.1891
| 141 | 0.38889 | 2.8305 | 1.9062 | 1.8067
| 142 | 0.35185 | 2.4576 | 1.5625 | 2.1429
| 143 | 0.5 | 2.4068 | 1.0938 | 1.8866
| 144 | 0.40741 | 2.5254 | 1.1562 | 2.1639
| 145 | 0.33333 | 2.9831 | 1.5938 | 2.0924
| 146 | 0.49074 | 2.4746 | 1.4375 | 2.2269
| 147 | 0.37037 | 2.7119 | 1.2812 | 2.2983
| 148 | 0.5 | 2.5254 | 1.4688 | 2.1134
| 149 | 0.5 | 2.7627 | 1.5312 | 2.042
| 150 | 0.48148 | 2.7797 | 1.25 | 1.6849
| 151 | 0.50926 | 3.678 | 1.5 | 2.0462
| 152 | 0.22222 | 2.6271 | 2.0312 | 2.2059
| 153 | 0.32407 | 2.9492 | 0.875 | 2.1723
| 154 | 0.36111 | 3.1356 | 1.4062 | 2.2563
| 155 | 0.39815 | 2.3051 | 1.5625 | 2.4874
| 156 | 0.51852 | 2.3729 | 1.7188 | 1.8487
| 157 | 0.31481 | 2.5763 | 1.6562 | 2.0504
| 158 | 0.39815 | 3.7797 | 1.7812 | 2.0252
| 159 | 0.4537 | 2 | 1.1562 | 2.1218
| 160 | 0.37963 | 2.7458 | 1.4062 | 2.1008
| 161 | 0.39815 | 3.3898 | 1.0625 | 2.1975
| 162 | 0.44444 | 3.0508 | 0.84375 | 2.2521
| 163 | 0.37963 | 2.9322 | 1.125 | 2.1261
| 164 | 0.23148 | 2.6441 | 1.6875 | 2.3193
| 165 | 0.55556 | 1.7797 | 1.6562 | 2.1429
| 166 | 0.5 | 2.4915 | 2.3438 | 2.0924
| 167 | 0.34259 | 2.9322 | 1.6562 | 1.9538
| 168 | 0.52778 | 2.4237 | 1.1875 | 1.9916
| 169 | 0.50926 | 3.0678 | 1.5938 | 1.8697
| 170 | 0.5 | 2.6271 | 1.3438 | 2.2143
| 171 | 0.39815 | 2.4068 | 1.0938 | 2.1513
| 172 | 0.51852 | 2.8983 | 2.375 | 2.1597
| 173 | 0.41667 | 2.7797 | 0.75 | 2.0084
| 174 | 0.39815 | 3.2542 | 3 | 2.4874
| 175 | 0.34259 | 2.4746 | 1.4688 | 2.2101
| 176 | 0.48148 | 1.9492 | 1.3438 | 2.1176
| 177 | 0.37037 | 2.2712 | 1.5 | 2.1513
| 178 | 0.55556 | 2.4407 | 1.75 | 2.3193
| 179 | 0.37963 | 2.8644 | 0.875 | 2.6555
| 180 | 0.34259 | 3.6102 | 1.25 | 2.1134
| 181 | 0.34259 | 2.1525 | 2.0625 | 2.2101
| 182 | 0.30556 | 3.0339 | 1.1875 | 2.0336
| 183 | 0.56481 | 2.6441 | 2.4062 | 2.0966
| 184 | 0.48148 | 2.8305 | 2.25 | 2.0126
| 185 | 0.37963 | 3.3559 | 1.6562 | 2.2521
| 186 | 0.37963 | 3.0508 | 0.8125 | 2.0882
| 187 | 0.39815 | 2.9492 | 1.5938 | 1.7605
| 188 | 0.28704 | 3.1864 | 1.4062 | 1.9118
| 189 | 0.21296 | 2.7966 | 1.5312 | 1.8529
| 190 | 0.34259 | 2.3559 | 2.2812 | 2.105
| 191 | 0.46296 | 2.8814 | 1.1875 | 1.9244
| 192 | 0.37037 | 2.7288 | 2.0312 | 1.8445
| 193 | 0.41667 | 2.6102 | 1.9062 | 2.1681
| 194 | 0.27778 | 2.7119 | 1.75 | 2.4664
| 195 | 0.37037 | 2.3559 | 2.0625 | 2.3319
| 196 | 0.40741 | 2.3898 | 1.2812 | 2.4118
| 197 | 0.41667 | 3.2712 | 0.96875 | 2.0924
| 198 | 0.64815 | 2.8136 | 1.1562 | 1.937
| 199 | 0.38889 | 3.3898 | 0.75 | 2.084
| 200 | 0.47222 | 3.322 | 1.5 | 2.0042
| 201 | 0.62963 | 2.8475 | 0.96875 | 1.8655
| 202 | 0.60185 | 3.1017 | 1.5312 | 2.0084
| 203 | 0.40741 | 1.8136 | 1.9062 | 2.1429
| 204 | 0.40741 | 1.8814 | 1.4062 | 1.8992
| 205 | 0.44444 | 2.7288 | 1.1562 | 1.9076
| 206 | 0.38889 | 2.8305 | 1.25 | 2.0378
| 207 | 0.59259 | 2.4237 | 1.75 | 2.0882
| 208 | 0.25 | 2.4915 | 1.875 | 1.9076
| 209 | 0.50926 | 1.9492 | 2.1875 | 1.9034
| 210 | 0.59259 | 2 | 1.1562 | 1.9748
| 211 | 0.39815 | 3.5085 | 1.4688 | 1.8697
| 212 | 0.69444 | 2.6949 | 0.9375 | 2.2815
| 213 | 0.42593 | 3.1356 | 1.1562 | 2.3361
| 214 | 0.32407 | 2.1864 | 1.9688 | 2.0294
| 215 | 0.41667 | 2.8305 | 1.8125 | 2.3193
| 216 | 0.46296 | 2.2712 | 1.5938 | 2.2017
| 217 | 0.42593 | 3.339 | 1.9062 | 1.9076
| 218 | 0.57407 | 2.7966 | 1.7812 | 2.0714
| 219 | 0.52778 | 2.9492 | 1.375 | 1.6681
| 220 | 0.35185 | 2.6949 | 1.8438 | 2.1261
| 221 | 0.44444 | 2.6949 | 1 | 2.0084
| 222 | 0.34259 | 2.2034 | 1.0312 | 2.1092
| 223 | 0.51852 | 3.1186 | 1.8125 | 2.105
| 224 | 0.43519 | 2.8475 | 2.0625 | 2.1134
| 225 | 0.34259 | 3.5593 | 1.4688 | 2.1176
| 226 | 0.42593 | 1.678 | 0.5625 | 2.1639
| 227 | 0.33333 | 2.5932 | 1.9375 | 1.9412
| 228 | 0.32407 | 2.339 | 1.8125 | 2.2983
| 229 | 0.37037 | 2.0847 | 1.5 | 2.0714
| 230 | 0.50926 | 2.9153 | 1.625 | 2.1849
| 231 | 0.44444 | 2.5085 | 1.25 | 2.3655
| 232 | 0.30556 | 2.9153 | 1.5312 | 1.9832
| 233 | 0.31481 | 2.9661 | 0.96875 | 2.3319
| 234 | 0.43519 | 2.8644 | 1.0625 | 1.7731
| 235 | 0.62037 | 3.2881 | 1.3125 | 1.8025
| 236 | 0.58333 | 3.1186 | 1.375 | 2.0966
| 237 | 0.34259 | 2.4915 | 1.5 | 1.8151
| 238 | 0.4537 | 2.8983 | 0.90625 | 2.1092
| 239 | 0.37037 | 3.1017 | 1.4062 | 1.895
| 240 | 0.28704 | 2.6102 | 0.9375 | 2.084
| 241 | 0.40741 | 2.4068 | 1.0625 | 2.2941
| 242 | 0.25926 | 2.6271 | 1.25 | 2.1008
| 243 | 0.37037 | 2.339 | 0.8125 | 2.0336
| 244 | 0.35185 | 2.6949 | 1.1875 | 2.084
| 245 | 0.26852 | 2.8475 | 1.625 | 1.7521
| 246 | 0.33333 | 2.8305 | 1.4062 | 2.2311
| 247 | 0.38889 | 2.661 | 1.6875 | 2.1849
| 248 | 0.2963 | 2.4068 | 1.875 | 2.3487
| 249 | 0.32407 | 3.322 | 1.6875 | 1.7773
| 250 | 0.56481 | 2.0847 | 1.5312 | 2.1387
| 251 | 0.41667 | 3.3051 | 1.3438 | 2.2857
| 252 | 0.32407 | 2.7119 | 1.0312 | 2.2689
| 253 | 0.27778 | 2.6102 | 1.2812 | 2.2647
| 254 | 0.40741 | 2.8305 | 1.5625 | 1.8529
| 255 | 0.2963 | 2.8814 | 1.9062 | 1.9748
| 256 | 0.39815 | 2.4576 | 1.625 | 2.1387
| 257 | 0.46296 | 2.6441 | 1.4688 | 2.3025
| 258 | 0.46296 | 2.7797 | 1.3438 | 2.2185
| 259 | 0.47222 | 2.2712 | 0.96875 | 1.9076
| 260 | 0.33333 | 2.8983 | 1.6875 | 2.458
| 261 | 0.39815 | 2.4407 | 1.1875 | 2.2311
| 262 | 0.55556 | 3.0339 | 1.375 | 1.9916
| 263 | 0.41667 | 2.5254 | 1.1562 | 2.0252
| 264 | 0.38889 | 2.7119 | 1.9375 | 1.9454
| 265 | 0.30556 | 3.0339 | 1.4375 | 2.021
| 266 | 0.37963 | 2.6102 | 2 | 2.2101
| 267 | 0.68519 | 2.7119 | 0.96875 | 1.8361
| 268 | 0.48148 | 2.5593 | 0.8125 | 2.0294
| 269 | 0.35185 | 3.0678 | 1.375 | 2.4454
| 270 | 0.52778 | 2.5593 | 0.96875 | 2.0168
| 271 | 0.46296 | 3.0508 | 2.0312 | 2.042
| 272 | 0.33333 | 2.8644 | 1.1562 | 1.9286
| 273 | 0.31481 | 2.9492 | 0.9375 | 2.1933
| 274 | 0.43519 | 3.2034 | 1.3438 | 2
| 275 | 0.46296 | 2.5085 | 2.4375 | 2.1513
| 276 | 0.32407 | 3.1356 | 1.8438 | 2.3824
| 277 | 0.32407 | 1.8475 | 1.6875 | 2.1429
| 278 | 0.36111 | 2.7797 | 2.25 | 2.0924
| 279 | 0.30556 | 2.322 | 2 | 1.937
| 280 | 0.32407 | 2.339 | 1.4062 | 1.9874
| 281 | 0.5 | 3.0847 | 1.4062 | 2.0336
| 282 | 0.34259 | 2.6102 | 1.4688 | 1.8824
| 283 | 0.48148 | 3.1356 | 0.8125 | 2.0126
| 284 | 0.42593 | 2.3729 | 1.1562 | 2.1429
| 285 | 0.27778 | 2.3898 | 1.4062 | 1.8487
| 286 | 0.37037 | 2.9492 | 1.4375 | 1.9832
| 287 | 0.28704 | 2.7627 | 0.84375 | 2.0126
| 288 | 0.4537 | 2.1864 | 1.4375 | 1.8487
| 289 | 0.32407 | 2.7966 | 1.9375 | 1.8571
| 290 | 0.39815 | 1.678 | 1.625 | 1.8697
| 291 | 0.36111 | 2.7288 | 1.75 | 1.8529
| 292 | 0.5 | 2.8136 | 1.2812 | 1.9832
| 293 | 0.57407 | 2.2881 | 2.4062 | 2.2563
| 294 | 0.42593 | 2.7627 | 1.0312 | 2.3193
| 295 | 0.44444 | 2.5424 | 1.6875 | 2.1639
| 296 | 0.37963 | 1.8983 | 1.4062 | 2.1681
| 297 | 0.5 | 3.4068 | 2.0938 | 2.3992
| 298 | 0.2963 | 2.6441 | 1.4688 | 2.3445
| 299 | 0.37037 | 3.1017 | 1.2188 | 2.0546
| 300 | 0.51852 | 3.3898 | 0.75 | 2.2311
| 301 | 0.38889 | 2.6271 | 1.75 | 2.2395
| 302 | 0.27778 | 2.4068 | 0.78125 | 2.021
| 303 | 0.61111 | 2.5085 | 1.9688 | 1.9034
| 304 | 0.43519 | 2.8475 | 1.125 | 2.4286
| 305 | 0.30556 | 1.7966 | 1.2188 | 1.9832
| 306 | 0.4537 | 2.678 | 1.8125 | 1.8403
| 307 | 0.62963 | 2.8475 | 1.1562 | 1.7521
| 308 | 0.31481 | 3.1356 | 0.90625 | 2.5168
| 309 | 0.40741 | 2.6949 | 1.2812 | 2.1723
| 310 | 0.33333 | 2.6102 | 1.4688 | 2.1639
| 311 | 0.37963 | 2.7119 | 0.90625 | 1.937
| 312 | 0.61111 | 3.2712 | 1.0312 | 1.8487
| 313 | 0.39815 | 2.2542 | 1.375 | 2.1387
| 314 | 0.32407 | 2.5424 | 2.6875 | 2.4832
| 315 | 0.2963 | 2.5932 | 1.3125 | 2.4412
| 316 | 0.5 | 2.1525 | 1.8125 | 1.9034
| 317 | 0.37963 | 2.4237 | 1.25 | 2.4622
| 318 | 0.47222 | 2.7966 | 2.0938 | 2.2773
| 319 | 0.37037 | 2.8136 | 1.3438 | 2.458
| 320 | 0.35185 | 3.2034 | 1.5312 | 1.7857
| 321 | 0.39815 | 1.678 | 0.875 | 2.1807
| 322 | 0.61111 | 3.4407 | 1.4375 | 2.2059
| 323 | 0.34259 | 3.0339 | 1.3438 | 1.9622
| 324 | 0.38889 | 2.8983 | 0.78125 | 2.3067
| 325 | 0.39815 | 2.339 | 1.2188 | 1.9538
| 326 | 0.37037 | 2.5085 | 1.0625 | 1.8824
| 327 | 0.49074 | 3.0678 | 1.9688 | 2.0084
| 328 | 0.37963 | 3.322 | 1.75 | 2.1639
| 329 | 0.50926 | 2.9661 | 1.75 | 2.3403
| 330 | 0.44444 | 2.8983 | 1.25 | 1.7941
| 331 | 0.31481 | 1.8475 | 0.65625 | 2.0546
| 332 | 0.52778 | 2.2373 | 1.5 | 1.9538
| 333 | 0.33333 | 2.5085 | 1.6562 | 1.8025
| 334 | 0.33333 | 2.5254 | 1.1875 | 1.7899
| 335 | 0.46296 | 2.7288 | 1.0312 | 2.1849
| 336 | 0.36111 | 2.6949 | 1.1875 | 2.0126
| 337 | 0.4537 | 2.4407 | 1.7812 | 2.2269
| 338 | 0.32407 | 2.8305 | 1.3125 | 2.0294
| 339 | 0.4537 | 2.9492 | 1.4062 | 2.2101
| 340 | 0.56481 | 2.1695 | 1.5312 | 2.2185
| 341 | 0.33333 | 4.3559 | 1.0938 | 2.084
| 342 | 0.49074 | 2.5932 | 0.90625 | 2.0966
| 343 | 0.32407 | 2.661 | 1.9688 | 2.0756
| 344 | 0.26852 | 2.1356 | 2.7188 | 1.9874
| 345 | 0.35185 | 2.9661 | 1.9688 | 1.9664
| 346 | 0.49074 | 2.6441 | 1.0938 | 1.6555
| 347 | 0.33333 | 2.2881 | 1.5625 | 1.8613
| 348 | 0.27778 | 3.1695 | 0.96875 | 2.0588
| 349 | 0.49074 | 2.8136 | 1 | 2.1765
| 350 | 0.32407 | 3 | 0.75 | 2.2227
| 351 | 0.42593 | 2.661 | 1.625 | 1.8697
| 352 | 0.5 | 2.2881 | 1.5312 | 2.1008
| 353 | 0.41667 | 2.7797 | 2.8438 | 2.2521
| 354 | 0.37963 | 2.3051 | 1.4375 | 2.1723
| 355 | 0.37037 | 2.4407 | 0.78125 | 2.4916
| 356 | 0.37963 | 3.1695 | 1.7188 | 2.1387
| 357 | 0.42593 | 2.4746 | 0.90625 | 2.1597
| 358 | 0.35185 | 2.5932 | 1.3438 | 2.084
| 359 | 0.32407 | 2.1186 | 1.9062 | 1.8319
| 360 | 0.37037 | 3.3898 | 1.4375 | 2.5462
| 361 | 0.33333 | 2.3559 | 1.0938 | 2.2101
| 362 | 0.34259 | 1.7966 | 1.9375 | 1.6345
| 363 | 0.37963 | 3.4237 | 1.8438 | 2.2899
| 364 | 0.51852 | 2.2373 | 1.3125 | 2.0336
| 365 | 0.39815 | 2.1017 | 1.375 | 1.8655
| 366 | 0.66667 | 2.7288 | 1.5625 | 2.1008
| 367 | 0.50926 | 2.6271 | 1.4375 | 2.0714
| 368 | 0.4537 | 2.6271 | 1.0938 | 2.2605
| 369 | 0.39815 | 2.7966 | 1.8438 | 2.5042
| 370 | 0.42593 | 2.3898 | 1.9062 | 1.9664
| 371 | 0.30556 | 2.7458 | 1.8438 | 1.8697
| 372 | 0.36111 | 2.8305 | 1.6562 | 2.0966
| 373 | 0.50926 | 3.5593 | 1.2812 | 1.7857
| 374 | 0.43519 | 3 | 1.4688 | 2.3151
| 375 | 0.4537 | 2.0508 | 1.4375 | 2.395
| 376 | 0.4537 | 2.1864 | 0.65625 | 1.9244
| 377 | 0.37963 | 3.2542 | 0.90625 | 2.0378
| 378 | 0.48148 | 2.8644 | 1.9375 | 2.479
| 379 | 0.31481 | 2.7627 | 1.9688 | 2.2101
| 380 | 0.41667 | 1.7797 | 1.875 | 2.0882
| 381 | 0.37963 | 2.7966 | 1.5625 | 2.3445
| 382 | 0.50926 | 2.322 | 1.4062 | 2.4244
| 383 | 0.41667 | 2.3051 | 0.84375 | 1.979
| 384 | 0.38889 | 2.7966 | 0.875 | 1.8613
| 385 | 0.40741 | 2.9661 | 2.5 | 1.9202
| 386 | 0.55556 | 2.8983 | 1.75 | 1.9454
| 387 | 0.62037 | 3.1356 | 1.5 | 2.0336
| 388 | 0.41667 | 2.4746 | 2 | 2.2143
| 389 | 0.42593 | 2.8305 | 1.4375 | 1.9034
| 390 | 0.43519 | 2.5085 | 1.375 | 1.7563
| 391 | 0.41667 | 3.4746 | 0.9375 | 2.2395
| 392 | 0.40741 | 2.3898 | 1.4375 | 1.937
| 393 | 0.32407 | 3.4068 | 0.9375 | 2.1975
| 394 | 0.42593 | 2.6102 | 1.125 | 1.8487
| 395 | 0.35185 | 2.661 | 1.125 | 2.0882
| 396 | 0.47222 | 3.5254 | 0.78125 | 2.2353
| 397 | 0.37037 | 2.661 | 1.6875 | 2.0042
| 398 | 0.32407 | 2.8305 | 1.375 | 1.9412
| 399 | 0.39815 | 2.4407 | 1.125 | 1.9748
| 400 | 0.39815 | 2.6102 | 1.4062 | 2.4412
| 401 | 0.37963 | 2.4407 | 1.4688 | 1.8151
| 402 | 0.41667 | 2.7119 | 1.1875 | 2.1387
| 403 | 0.44444 | 2.7966 | 0.8125 | 1.7941
| 404 | 0.34259 | 2.339 | 1.5312 | 1.8992
| 405 | 0.40741 | 3.1356 | 1.6562 | 2.2017
| 406 | 0.56481 | 2.5763 | 1.4688 | 2.2983
| 407 | 0.36111 | 2.0508 | 1.3125 | 2.1681
| 408 | 0.33333 | 2.2034 | 1.5625 | 2.2437
| 409 | 0.57407 | 2.7119 | 1.25 | 2.7773
| 410 | 0.46296 | 3.1525 | 1 | 1.9412
| 411 | 0.47222 | 3.2542 | 1.7188 | 2.2983
| 412 | 0.43519 | 2.5763 | 1.2812 | 2.021
| 413 | 0.32407 | 3.1017 | 1.625 | 2.0168
| 414 | 0.47222 | 3.4237 | 1.2188 | 2.3992
| 415 | 0.34259 | 3.9492 | 1.1562 | 1.9832
| 416 | 0.46296 | 2.8475 | 0.65625 | 1.7227
| 417 | 0.44444 | 2.8644 | 1.6875 | 2.042
| 418 | 0.31481 | 3.2542 | 2.5625 | 2.3445
| 419 | 0.47222 | 3.339 | 1.1562 | 2.0126
| 420 | 0.38889 | 2.7458 | 0.75 | 2.4664
| 421 | 0.35185 | 2.9661 | 1.5625 | 2.0882
| 422 | 0.44444 | 3 | 1.4375 | 1.9328
| 423 | 0.30556 | 2.4407 | 1.0938 | 2.4412
| 424 | 0.41667 | 2.6441 | 1.3125 | 1.9496
| 425 | 0.57407 | 2.7458 | 1.0312 | 2.3277
| 426 | 0.30556 | 3.3898 | 1.4062 | 2.479
| 427 | 0.33333 | 3.4237 | 2.4375 | 2.1555
| 428 | 0.38889 | 2.5424 | 1 | 2.1092
| 429 | 0.61111 | 2.5085 | 1.7188 | 2.1345
| 430 | 0.52778 | 3.0339 | 1.4375 | 2.2353
| 431 | 0.38889 | 3.0847 | 1.2812 | 2.1429
| 432 | 0.50926 | 2.2712 | 1.5938 | 2.1765
| 433 | 0.42593 | 3.1864 | 0.90625 | 1.8866
| 434 | 0.58333 | 2.7119 | 0.9375 | 1.9034
| 435 | 0.18519 | 3.0678 | 1.0938 | 1.895
| 436 | 0.36111 | 2.4746 | 1.2188 | 2.0462
| 437 | 0.38889 | 2.3898 | 1.7188 | 2.2941
| 438 | 0.37963 | 3.0339 | 1.4062 | 2.2311
| 439 | 0.2963 | 2.2712 | 1.1875 | 2.563
| 440 | 0.41667 | 2.0508 | 1.375 | 1.895
| 441 | 0.37963 | 2.7458 | 2.4375 | 2.6218
| 442 | 0.49074 | 2.5932 | 1.5312 | 2.2143
| 443 | 0.36111 | 3.0339 | 1.1875 | 1.9412
| 444 | 0.43519 | 3.2203 | 1.4688 | 2.0294
| 445 | 0.62037 | 2.9153 | 1.3438 | 2
| 446 | 0.49074 | 2.5763 | 2.25 | 1.8235
| 447 | 0.37037 | 3.1525 | 0.96875 | 2.0294
| 448 | 0.34259 | 3 | 1.0625 | 2.0546
| 449 | 0.32407 | 2.7797 | 1.5625 | 2.2983
| 450 | 0.33333 | 2.4407 | 1.2188 | 1.8487
| 451 | 0.5 | 2.7627 | 1.7812 | 2.1303
| 452 | 0.42593 | 2.2373 | 2.2188 | 1.7983
| 453 | 0.37963 | 2.5085 | 1.0938 | 1.7101
| 454 | 0.2963 | 3.1356 | 1.2812 | 1.937
| 455 | 0.49074 | 3.2542 | 1.8125 | 2.3529
| 456 | 0.52778 | 2.6102 | 1.25 | 2.1891
| 457 | 0.43519 | 2.5593 | 1.8125 | 2.0882
| 458 | 0.37963 | 2.7119 | 1.5625 | 2.3361
| 459 | 0.4537 | 2.3898 | 1.9062 | 2.0924
| 460 | 0.36111 | 3.4068 | 1.6875 | 2.1471
| 461 | 0.5 | 2.7627 | 1.6562 | 2.2563
| 462 | 0.42593 | 2.4407 | 1.2188 | 2.0462
| 463 | 0.47222 | 2.1525 | 1.375 | 1.9118
| 464 | 0.2963 | 2.4068 | 1.0938 | 2.0462
| 465 | 0.32407 | 2.9153 | 0.75 | 1.9958
| 466 | 0.50926 | 2.3729 | 1.5625 | 2.3739
| 467 | 0.30556 | 2.7966 | 1.4688 | 2.1429
| 468 | 0.38889 | 2.6441 | 0.875 | 2.084
| 469 | 0.46296 | 3.2712 | 1.1875 | 2.2479
| 470 | 0.5 | 2.5593 | 1.375 | 2.0168
| 471 | 0.35185 | 2.2034 | 1.75 | 2.2731
| 472 | 0.5 | 3.3898 | 0.96875 | 1.9076
| 473 | 0.44444 | 3.0847 | 0.9375 | 2.1933
| 474 | 0.38889 | 3.1356 | 1.9062 | 1.7815
| 475 | 0.42593 | 2.5254 | 2.3125 | 2.1218
| 476 | 0.37963 | 2.7797 | 1.9688 | 1.8571
| 477 | 0.35185 | 2.6949 | 1.2812 | 1.9328
| 478 | 0.4537 | 2.2373 | 1.4375 | 2.2941
| 479 | 0.62963 | 2.3559 | 0.78125 | 1.8361
| 480 | 0.2963 | 3.1017 | 0.875 | 1.8319
| 481 | 0.53704 | 2.7458 | 0.8125 | 2.1176
| 482 | 0.39815 | 2.7966 | 1.2188 | 1.9538
| 483 | 0.42593 | 2.5763 | 1.0938 | 1.7059
| 484 | 0.38889 | 2.4746 | 1.875 | 2.2269
| 485 | 0.41667 | 2.661 | 1.3125 | 2.0294
| 486 | 0.44444 | 2.7627 | 2.0625 | 1.9076
| 487 | 0.25926 | 3.4068 | 1.4688 | 2.1891
| 488 | 0.5 | 2.3051 | 0.59375 | 1.9496
| 489 | 0.38889 | 2.8983 | 1.0938 | 2.3151
| 490 | 0.46296 | 3.1864 | 1.75 | 2.2983
| 491 | 0.37963 | 2.7288 | 1.7812 | 1.9454
| 492 | 0.34259 | 3.2712 | 1.4062 | 2.4034
| 493 | 0.31481 | 2.0508 | 1.3438 | 2.3782
| 494 | 0.39815 | 1.9661 | 1.5625 | 1.8361
| 495 | 0.58333 | 3.0847 | 0.71875 | 1.7269
| 496 | 0.59259 | 2.3729 | 1 | 2.0588
| 497 | 0.28704 | 2.0169 | 1.0625 | 2.084
| 498 | 0.35185 | 3.1695 | 2.1875 | 2.1261
| 499 | 0.31481 | 2.4407 | 0.75 | 2.0378
| 500 | 0.7037 | 2.9831 | 1.4688 | 2.1765
| 501 | 0.61111 | 2.0169 | 1.4375 | 2.0588
| 502 | 0.40741 | 3.1017 | 0.8125 | 1.7311
| 503 | 0.2963 | 3.1864 | 1.75 | 1.9706
| 504 | 0.27778 | 2.9153 | 1.9062 | 1.895
| 505 | 0.44444 | 3.2712 | 1.0625 | 1.9916
| 506 | 0.4537 | 2.7458 | 1.4062 | 2.021
| 507 | 0.37037 | 2.7966 | 1.3125 | 2.0126
| 508 | 0.46296 | 3.5763 | 1.4688 | 2.2773
| 509 | 0.31481 | 2.7288 | 1.6875 | 2.0378
| 510 | 0.32407 | 3.0169 | 1.3438 | 2.1261
| 511 | 0.38889 | 2.678 | 1.0938 | 1.9958
| 512 | 0.47222 | 2.5254 | 0.9375 | 1.8193
| 513 | 0.51852 | 2.9831 | 1.1875 | 2.4538
| 514 | 0.47222 | 3.0847 | 2 | 2.2311
| 515 | 0.43519 | 2.8983 | 1.3125 | 1.9454
| 516 | 0.35185 | 3.3559 | 1.5 | 1.7311
| 517 | 0.50926 | 2.678 | 1.25 | 2.2395
| 518 | 0.44444 | 3.2542 | 0.71875 | 2.0084
| 519 | 0.41667 | 2.9661 | 1.0938 | 2.0252
| 520 | 0.31481 | 2.7966 | 1.7188 | 2.2143
| 521 | 0.47222 | 3.1695 | 1.9375 | 2.2101
| 522 | 0.34259 | 3.5763 | 1.375 | 2.0672
| 523 | 0.42593 | 3.6271 | 1.3438 | 1.7815
| 524 | 0.55556 | 2.4576 | 1.6562 | 1.9706
| 525 | 0.42593 | 3.1017 | 0.875 | 1.8487
| 526 | 0.47222 | 2.339 | 2.0625 | 1.8403
| 527 | 0.4537 | 2.2542 | 1.625 | 2.2773
| 528 | 0.5 | 3.2034 | 2 | 2.1975
| 529 | 0.35185 | 2.7966 | 1.9688 | 2.021
| 530 | 0.24074 | 2.6949 | 1.1562 | 1.979
| 531 | 0.2963 | 3.2203 | 1.6562 | 2.458
| 532 | 0.5 | 3.0169 | 1.8125 | 2.0462
| 533 | 0.34259 | 2.9153 | 1.0625 | 1.937
| 534 | 0.48148 | 3.1864 | 1.0312 | 2.105
| 535 | 0.39815 | 2.7627 | 1.2188 | 2
| 536 | 0.28704 | 2.3898 | 1.0312 | 2.2101
| 537 | 0.37963 | 2.8475 | 1.375 | 2.0042
| 538 | 0.37037 | 2.4576 | 2.5 | 2.1261
| 539 | 0.30556 | 2.5593 | 1.0938 | 2.1639
| 540 | 0.36111 | 2.9322 | 1.8125 | 2.2941
| 541 | 0.35185 | 2.5085 | 1.5938 | 2.1218
| 542 | 0.4537 | 2.9661 | 1.8438 | 2.2731
| 543 | 0.42593 | 2.1695 | 1.3125 | 1.958
| 544 | 0.48148 | 2.5593 | 1.7812 | 1.7479
| 545 | 0.48148 | 2.322 | 0.9375 | 1.7059
| 546 | 0.44444 | 2.5593 | 1.0938 | 2.2479
| 547 | 0.38889 | 2.4915 | 1.75 | 1.9118
| 548 | 0.43519 | 2.9153 | 1.4062 | 2.3613
| 549 | 0.30556 | 2.9831 | 1.4375 | 1.9034
| 550 | 0.50926 | 2.5085 | 0.59375 | 1.9916
| 551 | 0.27778 | 2.9322 | 1.6875 | 2.0798
| 552 | 0.5 | 2.1864 | 1.1875 | 2.3109
| 553 | 0.32407 | 2.4576 | 0.875 | 2.0168
| 554 | 0.48148 | 2.7627 | 1.375 | 2.1765
| 555 | 0.55556 | 2.6271 | 0.84375 | 2.2731
| 556 | 0.4537 | 3.2203 | 1.0938 | 2.3613
| 557 | 0.40741 | 2.9661 | 1.125 | 2.1387
| 558 | 0.5 | 2.1525 | 1.4062 | 2.1345
| 559 | 0.34259 | 3.0339 | 1.5 | 2.1134
| 560 | 0.43519 | 3.2034 | 1.5 | 2.0546
| 561 | 0.34259 | 1.9322 | 1.2188 | 2.5672
| 562 | 0.41667 | 3.5763 | 2.3438 | 2.1681
| 563 | 0.53704 | 2.2712 | 1.0938 | 2.1092
| 564 | 0.34259 | 2.2034 | 2.2812 | 1.9454
| 565 | 0.40741 | 2.7119 | 1.1562 | 1.9706
| 566 | 0.56481 | 2.8305 | 1.5 | 2.063
| 567 | 0.46296 | 2.7797 | 1.0938 | 2.2773
| 568 | 0.60185 | 2.6441 | 1.5625 | 2.1555
| 569 | 0.31481 | 1.9661 | 1.1875 | 2.1765
| 570 | 0.37037 | 2.6441 | 1.0312 | 2.1975
| 571 | 0.34259 | 2.3559 | 1.5938 | 2.3319
| 572 | 0.49074 | 2.7119 | 1.6875 | 1.9118
| 573 | 0.5463 | 3.339 | 1.1562 | 2.3361
| 574 | 0.48148 | 2.2542 | 1.375 | 2.1891
| 575 | 0.36111 | 3.0339 | 1.4062 | 2.1134
| 576 | 0.42593 | 3.0169 | 1.6562 | 2.2815
| 577 | 0.30556 | 2.1695 | 2.125 | 2.042
| 578 | 0.55556 | 2.6102 | 2.3438 | 2.0966
| 579 | 0.30556 | 2.2712 | 0.96875 | 1.7647
| 580 | 0.31481 | 2.5593 | 0.96875 | 2.2101
| 581 | 0.47222 | 3.4407 | 1.3438 | 1.979
| 582 | 0.25 | 3.0508 | 1.25 | 2.1723
| 583 | 0.38889 | 3.1864 | 1.8438 | 2.4412
| 584 | 0.41667 | 2.661 | 1.8125 | 2.0084
| 585 | 0.5463 | 2.6102 | 1.7188 | 2.1681
| 586 | 0.53704 | 2.0339 | 1.1562 | 1.9916
| 587 | 0.34259 | 2.8475 | 1.75 | 1.9496
| 588 | 0.47222 | 2.5932 | 1.0938 | 2.0378
| 589 | 0.32407 | 2.8305 | 1.0938 | 2.2017
| 590 | 0.42593 | 2.2712 | 1.9062 | 1.9118
| 591 | 0.57407 | 2.4407 | 1 | 2.4664
| 592 | 0.33333 | 2.7458 | 1.125 | 2.0378
| 593 | 0.48148 | 2.7966 | 1.25 | 2.0294
| 594 | 0.25 | 2.339 | 1.5625 | 1.9958
| 595 | 0.31481 | 2.8305 | 1.6562 | 2.5378
| 596 | 0.47222 | 2.5932 | 1.375 | 2.2857
| 597 | 0.37037 | 2.2542 | 1.4375 | 2.1261
| 598 | 0.42593 | 2.7797 | 1.5625 | 1.979
| 599 | 0.40741 | 3.339 | 1.2812 | 1.9874
| 600 | 0.46296 | 2.2203 | 1.2188 | 2.4622
| 601 | 0.5 | 3.2542 | 2.0625 | 2.105
| 602 | 0.31481 | 3.0339 | 0.96875 | 2
| 603 | 0.23148 | 3.3729 | 1.9688 | 2.0546
| 604 | 0.42593 | 2.7288 | 1.4688 | 2.1597
| 605 | 0.48148 | 2.6949 | 1.875 | 2.0966
| 606 | 0.46296 | 2.7966 | 1.1562 | 1.7605
| 607 | 0.37963 | 2.5254 | 1.1875 | 2.2857
| 608 | 0.38889 | 2.6102 | 0.8125 | 2.2689
| 609 | 0.53704 | 2.5254 | 1.2188 | 1.7899
| 610 | 0.50926 | 1.9831 | 1.1875 | 2.0378
| 611 | 0.42593 | 2.7288 | 1.5938 | 2.1681
| 612 | 0.50926 | 2.7627 | 1.4688 | 1.958
| 613 | 0.44444 | 2.8983 | 1.375 | 1.8739
| 614 | 0.43519 | 3.1525 | 1.0625 | 2.0672
| 615 | 0.41667 | 2.7119 | 0.96875 | 1.6933
| 616 | 0.37963 | 2.5424 | 2.4375 | 2.3655
| 617 | 0.33333 | 2.8305 | 1.2188 | 2.105
| 618 | 0.36111 | 2.9153 | 1.9375 | 2.0882
| 619 | 0.43519 | 3 | 1.4062 | 2.0336
| 620 | 0.55556 | 2.8644 | 1.5938 | 1.9244
| 621 | 0.42593 | 2.5763 | 1.1562 | 2.2479
| 622 | 0.62963 | 2.9661 | 2.0312 | 2.3067
| 623 | 0.27778 | 2.1017 | 1.125 | 2.1471
| 624 | 0.31481 | 2.3898 | 1.2812 | 1.9412
| 625 | 0.42593 | 3.0678 | 1.4375 | 2.2563
| 626 | 0.42593 | 2.9661 | 1.5625 | 2.3361
| 627 | 0.44444 | 3.2034 | 1.125 | 1.9748
| 628 | 0.49074 | 2.5424 | 0.875 | 1.9622
| 629 | 0.48148 | 2.5085 | 1.9688 | 2.2437
| 630 | 0.43519 | 2.1864 | 1.1875 | 2.084
| 631 | 0.47222 | 1.9153 | 0.9375 | 2.0504
| 632 | 0.47222 | 2.4237 | 0.875 | 1.9832
| 633 | 0.52778 | 3.4576 | 1.4375 | 2.063
| 634 | 0.44444 | 3.1695 | 2.4062 | 2.1471
| 635 | 0.37963 | 3.0847 | 1.1875 | 2.0924
| 636 | 0.50926 | 2.7627 | 1.2812 | 2.0378
| 637 | 0.37037 | 1.8814 | 1.5312 | 2.042
| 638 | 0.55556 | 2.8814 | 2.0312 | 2.2563
| 639 | 0.38889 | 2.6441 | 0.65625 | 2.4832
| 640 | 0.49074 | 2.8305 | 0.75 | 2.042
| 641 | 0.36111 | 2.7288 | 1.0625 | 2.1723
| 642 | 0.39815 | 2.8305 | 1.4062 | 2.0294
| 643 | 0.44444 | 2 | 1.375 | 1.958
| 644 | 0.47222 | 2.7627 | 1.625 | 2.1681
| 645 | 0.34259 | 2.9153 | 1.7188 | 2.1639
| 646 | 0.42593 | 1.8475 | 0.9375 | 1.8824
| 647 | 0.51852 | 2.5424 | 1.7812 | 2.3908
| 648 | 0.35185 | 3 | 0.96875 | 1.7731
| 649 | 0.46296 | 2.7288 | 1.8125 | 2.3529
| 650 | 0.52778 | 2.2542 | 1.1562 | 2.3782
| 651 | 0.26852 | 2.678 | 1.7188 | 2.1303
| 652 | 0.52778 | 2.7119 | 1.75 | 2.1303
| 653 | 0.42593 | 2.8136 | 1.375 | 2.0588
| 654 | 0.47222 | 2.2034 | 0.65625 | 2.2647
| 655 | 0.43519 | 2.3051 | 1.6875 | 1.916
| 656 | 0.34259 | 3.0678 | 1.4688 | 2.2899
| 657 | 0.49074 | 2.661 | 1.3125 | 2.0504
| 658 | 0.42593 | 2.7458 | 2.0625 | 2.458
| 659 | 0.33333 | 2.4068 | 1.25 | 1.8109
| 660 | 0.42593 | 1.8983 | 0.96875 | 2.1303
| 661 | 0.38889 | 2.6441 | 1.375 | 1.8697
| 662 | 0.52778 | 2.6102 | 0.875 | 2
| 663 | 0.35185 | 2.6271 | 1.0938 | 1.8613
| 664 | 0.44444 | 1.9661 | 1.8438 | 2.2521
| 665 | 0.38889 | 2.322 | 1.9375 | 2.1008
| 666 | 0.41667 | 2.1017 | 1.4688 | 1.8908
| 667 | 0.40741 | 2.6441 | 1.4375 | 2.3109
| 668 | 0.49074 | 2.4915 | 1.0312 | 2.042
| 669 | 0.43519 | 3.2034 | 1.5625 | 1.9454
| 670 | 0.44444 | 3.0508 | 1.2188 | 1.9076
| 671 | 0.36111 | 3.2712 | 1.5625 | 1.8487
| 672 | 0.35185 | 3.1695 | 1.5312 | 2.3866
| 673 | 0.26852 | 2.7797 | 1.4062 | 2.2899
| 674 | 0.37037 | 2.4237 | 1.875 | 2.3529
| 675 | 0.37963 | 3.5424 | 1.6562 | 2.0084
| 676 | 0.30556 | 2.8475 | 1.2812 | 1.8067
| 677 | 0.31481 | 2.6102 | 0.78125 | 2.3025
| 678 | 0.27778 | 2.7627 | 0.84375 | 2.0042
| 679 | 0.62963 | 2.8644 | 2.2812 | 2.0756
| 680 | 0.12963 | 2.9492 | 1.9062 | 1.9412
| 681 | 0.34259 | 2.2203 | 0.96875 | 2.1513
| 682 | 0.53704 | 2.4746 | 1.1562 | 2.4076
| 683 | 0.57407 | 2.5424 | 1.0625 | 1.9916
| 684 | 0.37963 | 2.0678 | 1.8438 | 2.0126
| 685 | 0.43519 | 2.3559 | 1.2188 | 2.0294
| 686 | 0.40741 | 2.8983 | 1.9375 | 2.2941
| 687 | 0.38889 | 2.6271 | 1.4062 | 1.8361
| 688 | 0.59259 | 3.1017 | 2.3125 | 2.1933
| 689 | 0.30556 | 3.5593 | 1.1875 | 2.1933
| 690 | 0.25 | 2.4237 | 1.25 | 2.1134
| 691 | 0.31481 | 2.7119 | 1.4062 | 2.0126
| 692 | 0.37963 | 2.3559 | 2.0312 | 2.0714
| 693 | 0.43519 | 2.7119 | 1.0938 | 2.0168
| 694 | 0.53704 | 2.5085 | 1.0938 | 2.1891
| 695 | 0.37037 | 2.5254 | 1.3125 | 2.1092
| 696 | 0.44444 | 2.5593 | 1.5312 | 2.0462
| 697 | 0.43519 | 3.339 | 1.5 | 2.0672
| 698 | 0.37037 | 2.3898 | 0.78125 | 2.0756
| 699 | 0.39815 | 2.3051 | 1.25 | 1.9076
| 700 | 0.56481 | 2.7119 | 1.3125 | 1.7689
| 701 | 0.42593 | 2.8644 | 1.5625 | 2.3319
| 702 | 0.35185 | 2.8983 | 1.3125 | 2.2143
| 703 | 0.40741 | 2.6271 | 2 | 1.9748
| 704 | 0.32407 | 2.7797 | 1.2812 | 2.1849
| 705 | 0.36111 | 3.3729 | 0.625 | 1.8697
| 706 | 0.46296 | 2.4068 | 1.375 | 2.2437
| 707 | 0.40741 | 2.3559 | 2.875 | 2.0756
| 708 | 0.50926 | 2.7458 | 1.875 | 2.2815
| 709 | 0.38889 | 2.4407 | 1.4375 | 2.2143
| 710 | 0.41667 | 2.4576 | 1.9062 | 1.9328
| 711 | 0.30556 | 2.4068 | 1.9688 | 1.8782
| 712 | 0.2963 | 2.322 | 0.75 | 1.9328
| 713 | 0.37037 | 2.9661 | 1.375 | 2.2353
| 714 | 0.4537 | 2 | 0.90625 | 2.1765
| 715 | 0.32407 | 1.9661 | 1.6562 | 2.2479
| 716 | 0.51852 | 2.9322 | 1.6875 | 2.2101
| 717 | 0.35185 | 3.4237 | 1.375 | 2.416
| 718 | 0.36111 | 2.339 | 1.25 | 2.1555
| 719 | 0.36111 | 2.7627 | 1.3438 | 2.2479
| 720 | 0.44444 | 2.5932 | 1.375 | 2.1092
| 721 | 0.39815 | 2.9153 | 1.4062 | 1.8361
| 722 | 0.5 | 2.661 | 1.4688 | 2.0714
| 723 | 0.33333 | 3.3898 | 1.4375 | 2.3193
| 724 | 0.48148 | 2.4237 | 1.1562 | 2.563
| 725 | 0.32407 | 2.3559 | 1.0625 | 2.0924
| 726 | 0.37963 | 3.0339 | 1.625 | 1.9748
| 727 | 0.40741 | 2.6102 | 1 | 2.1429
| 728 | 0.37037 | 2.5763 | 1.2188 | 2.2899
| 729 | 0.61111 | 1.9831 | 1.8125 | 2.0966
| 730 | 0.27778 | 2.7797 | 0.78125 | 2.1639
| 731 | 0.38889 | 2.8983 | 1.9688 | 2.1218
| 732 | 0.35185 | 2.7458 | 1.125 | 1.9118
| 733 | 0.2963 | 3.0339 | 1.3125 | 1.937
| 734 | 0.37963 | 2.4915 | 1.25 | 2.2857
| 735 | 0.56481 | 1.8814 | 1.1562 | 1.9118
| 736 | 0.34259 | 2.4915 | 1.3125 | 2.2941
| 737 | 0.4537 | 2.5593 | 1.3438 | 2.3235
| 738 | 0.5463 | 1.8305 | 1.2812 | 2.2899
| 739 | 0.5 | 2.4576 | 0.96875 | 1.8866
| 740 | 0.41667 | 3 | 2.5312 | 1.9958
| 741 | 0.38889 | 2.8814 | 1.0312 | 2.0672
| 742 | 0.34259 | 3.3051 | 1.2812 | 2.2353
| 743 | 0.42593 | 2.7797 | 1.1875 | 1.9958
| 744 | 0.49074 | 2.2203 | 1.5938 | 1.8908
| 745 | 0.42593 | 1.9492 | 0.8125 | 2.1218
| 746 | 0.31481 | 2.5593 | 1.25 | 2.2311
| 747 | 0.35185 | 2.9831 | 1.5312 | 2.1975
| 748 | 0.42593 | 2.9661 | 1.5625 | 2.2101
| 749 | 0.37037 | 3.1186 | 1.0938 | 2.0336
| 750 | 0.37963 | 3.2881 | 2.0312 | 1.9454
| 751 | 0.47222 | 2.7966 | 2.1562 | 1.8824
| 752 | 0.37037 | 2.1525 | 0.9375 | 1.6681
| 753 | 0.37963 | 2.9831 | 0.625 | 2.0546
| 754 | 0.40741 | 2.8305 | 1.2188 | 2.0252
| 755 | 0.43519 | 2.661 | 2.0625 | 2.1933
| 756 | 0.46296 | 2.5085 | 1.4375 | 1.8109
| 757 | 0.5 | 2.5254 | 1.375 | 2.3866
| 758 | 0.63889 | 2.9661 | 1.25 | 1.9496
| 759 | 0.43519 | 3.2881 | 1.5938 | 2.542
| 760 | 0.43519 | 1.9322 | 0.8125 | 2.0588
| 761 | 0.35185 | 2.2881 | 1.4062 | 2.0336
| 762 | 0.31481 | 2.9661 | 1.7188 | 2.1597
| 763 | 0.26852 | 2.2034 | 1.0938 | 1.9706
| 764 | 0.57407 | 2.8644 | 1.4688 | 2.0924
| 765 | 0.35185 | 2.7797 | 1.2812 | 2.4496
| 766 | 0.36111 | 2.678 | 2.1875 | 2.2101
| 767 | 0.55556 | 2.7288 | 1.2188 | 2.1345
| 768 | 0.30556 | 2.7458 | 0.5625 | 1.9664
| 769 | 0.34259 | 2.2542 | 1.8125 | 2.1891
| 770 | 0.41667 | 2.8136 | 1.3125 | 2.3739
| 771 | 0.41667 | 3.6949 | 1.25 | 2.2353
| 772 | 0.42593 | 2.2034 | 0.96875 | 1.7941
| 773 | 0.25926 | 2.2542 | 0.75 | 2.1261
| 774 | 0.51852 | 3.0169 | 0.78125 | 2.1597
| 775 | 0.38889 | 2.4407 | 1.3125 | 1.8739
| 776 | 0.42593 | 3.2203 | 1.125 | 1.937
| 777 | 0.37037 | 2.4915 | 1.5 | 2.2983
| 778 | 0.36111 | 2.4576 | 0.90625 | 2.0882
| 779 | 0.34259 | 3.2712 | 1.125 | 2.2311
| 780 | 0.47222 | 3.0339 | 1.0625 | 2.6765
| 781 | 0.4537 | 2.3051 | 0.96875 | 2.042
| 782 | 0.5 | 3.3898 | 2.125 | 2.0546
| 783 | 0.39815 | 2.3559 | 1.3125 | 1.8739
| 784 | 0.37037 | 1.8983 | 1.5625 | 2.1849
| 785 | 0.40741 | 3.322 | 1.2812 | 1.8403
| 786 | 0.41667 | 1.9492 | 1.125 | 2.3613
| 787 | 0.41667 | 2.7288 | 1.6875 | 2.3109
| 788 | 0.43519 | 2.4915 | 1.75 | 1.6975
| 789 | 0.44444 | 3.0847 | 0.53125 | 2.1134
| 790 | 0.55556 | 1.7627 | 1.5625 | 2.042
| 791 | 0.35185 | 3.8983 | 1.8125 | 2.0462
| 792 | 0.39815 | 3.4915 | 1.7812 | 2.2899
| 793 | 0.38889 | 2.0169 | 1.3125 | 2.1555
| 794 | 0.34259 | 2.3898 | 1.375 | 2.0252
| 795 | 0.40741 | 2.6271 | 1.4688 | 2.2689
| 796 | 0.38889 | 2.5763 | 0.78125 | 2.3782
| 797 | 0.38889 | 3.4746 | 1.5 | 2.0924
| 798 | 0.47222 | 2.2712 | 1.0938 | 2.4202
| 799 | 0.51852 | 2.5085 | 0.90625 | 2.3361
| 800 | 0.27778 | 2.7966 | 1.8438 | 1.937
| 801 | 0.34259 | 2.5763 | 1.2812 | 2.4202
| 802 | 0.31481 | 3.3559 | 1.2188 | 2.4412
| 803 | 0.42593 | 2.6441 | 1.3125 | 2.0588
| 804 | 0.34259 | 2.1017 | 1.5312 | 2.0252
| 805 | 0.34259 | 2.4915 | 1.4062 | 1.8908
| 806 | 0.35185 | 2.7797 | 2.0938 | 1.9916
| 807 | 0.41667 | 2.5424 | 1.1562 | 1.7353
| 808 | 0.36111 | 3.1017 | 1.25 | 1.9538
| 809 | 0.41667 | 2.7458 | 2.1562 | 2.3824
| 810 | 0.37963 | 2.3898 | 1.625 | 1.9202
| 811 | 0.36111 | 2.6949 | 1.2812 | 2.437
| 812 | 0.32407 | 2.8305 | 0.625 | 2.0126
| 813 | 0.4537 | 2.2373 | 1.375 | 2.2059
| 814 | 0.37963 | 3.5763 | 1.5625 | 1.8445
| 815 | 0.37037 | 2.6271 | 2.4375 | 1.7185
| 816 | 0.56481 | 2.2712 | 0.96875 | 2.3782
| 817 | 0.41667 | 2.4915 | 1.2188 | 2.1261
| 818 | 0.2963 | 3.322 | 2.625 | 2.2983
| 819 | 0.33333 | 2.1864 | 1.3438 | 2.2437
| 820 | 0.36111 | 3.4068 | 1.3438 | 1.9664
| 821 | 0.37037 | 2.4576 | 0.9375 | 2.0168
| 822 | 0.52778 | 2.5424 | 1.6875 | 1.8235
| 823 | 0.47222 | 2 | 1.8438 | 2.1597
| 824 | 0.55556 | 1.9831 | 1.7188 | 2.3025
| 825 | 0.40741 | 2.5254 | 1.0312 | 2.5546
| 826 | 0.4537 | 2.5593 | 0.84375 | 1.9328
| 827 | 0.46296 | 1.8644 | 1.5938 | 1.7899
| 828 | 0.37963 | 2.9322 | 1 | 2.2353
| 829 | 0.27778 | 2.6271 | 1.1875 | 2.2437
| 830 | 0.44444 | 2.1695 | 0.90625 | 2.2227
| 831 | 0.36111 | 2.4407 | 1.1875 | 2.2563
| 832 | 0.34259 | 2.9492 | 1.6562 | 2.1723
| 833 | 0.44444 | 2.1356 | 1.4375 | 2.3193
| 834 | 0.60185 | 2.0508 | 0.84375 | 2.2983
| 835 | 0.28704 | 2.2881 | 2.6562 | 2.1891
| 836 | 0.41667 | 2.2542 | 1.75 | 1.7521
| 837 | 0.42593 | 3.5085 | 0.53125 | 1.8571
| 838 | 0.49074 | 2.5932 | 0.9375 | 2.0714
| 839 | 0.44444 | 3.1695 | 1.375 | 1.9706
| 840 | 0.26852 | 2.4068 | 1.9062 | 1.916
| 841 | 0.37037 | 3.3729 | 1 | 2.2311
| 842 | 0.40741 | 3.0847 | 1.5 | 2.1345
| 843 | 0.37963 | 2.1864 | 1.25 | 2.1134
| 844 | 0.48148 | 2.9661 | 0.84375 | 2.063
| 845 | 0.46296 | 2.0169 | 1.5 | 2.4664
| 846 | 0.49074 | 2.2203 | 1.5938 | 2.063
| 847 | 0.40741 | 2.6441 | 1.5312 | 2.021
| 848 | 0.41667 | 2.1017 | 1.625 | 2
| 849 | 0.47222 | 2.5424 | 0.71875 | 2.0042
| 850 | 0.2963 | 2.6271 | 2.1875 | 1.8866
| 851 | 0.59259 | 2.1695 | 1.5 | 2.6639
| 852 | 0.5 | 3.5085 | 0.90625 | 2.1429
| 853 | 0.44444 | 3.4068 | 1.125 | 2.4118
| 854 | 0.40741 | 2.7288 | 0.96875 | 2.1597
| 855 | 0.53704 | 2.6102 | 1.3125 | 1.7941
| 856 | 0.44444 | 2.6949 | 1.3438 | 2.2311
| 857 | 0.41667 | 3.4237 | 1.2812 | 2.4706
| 858 | 0.61111 | 2.6949 | 1.5938 | 1.9244
| 859 | 0.51852 | 2.7288 | 0.71875 | 2.0546
| 860 | 0.49074 | 2.6949 | 1.375 | 1.7983
| 861 | 0.38889 | 2.6271 | 1.5938 | 2.1218
| 862 | 0.30556 | 2.5424 | 2.75 | 1.9706
| 863 | 0.36111 | 2.8136 | 1.3125 | 1.8824
| 864 | 0.40741 | 2.9322 | 0.9375 | 1.8824
| 865 | 0.27778 | 2.5424 | 1.2188 | 2.0126
| 866 | 0.40741 | 2.2203 | 1.4062 | 1.9076
| 867 | 0.57407 | 2.9661 | 1.5625 | 2.1513
| 868 | 0.30556 | 3 | 1.25 | 2.063
| 869 | 0.2963 | 3.2203 | 2.1562 | 2.4202
| 870 | 0.37963 | 2.6949 | 1.5 | 2.1261
| 871 | 0.4537 | 3.2712 | 1.125 | 1.9916
| 872 | 0.32407 | 2.9492 | 1.25 | 2.0336
| 873 | 0.40741 | 2.2881 | 1.9688 | 2.1639
| 874 | 0.36111 | 3.1017 | 0.75 | 2.1134
| 875 | 0.35185 | 2.9492 | 1.6562 | 1.7563
| 876 | 0.5 | 3.2881 | 1.5312 | 2.1513
| 877 | 0.5463 | 3.3729 | 1.4688 | 2.0714
| 878 | 0.37963 | 2.4915 | 0.96875 | 2.1555
| 879 | 0.50926 | 2.4068 | 1.5938 | 1.8361
| 880 | 0.39815 | 2.5254 | 1.75 | 2.1218
| 881 | 0.33333 | 2.5254 | 2.2188 | 2.063
| 882 | 0.44444 | 2.3729 | 1.0938 | 2.2899
| 883 | 0.40741 | 2.9322 | 0.8125 | 1.8361
| 884 | 0.37963 | 2.2034 | 0.6875 | 2.0336
| 885 | 0.43519 | 2.1525 | 0.90625 | 1.9706
| 886 | 0.38889 | 2.8305 | 1.375 | 2.1723
| 887 | 0.26852 | 2.2881 | 0.78125 | 2.0042
| 888 | 0.5 | 2.5763 | 0.875 | 2.2731
| 889 | 0.44444 | 2.7627 | 0.6875 | 2.1933
| 890 | 0.36111 | 2.339 | 1.5312 | 2.2143
| 891 | 0.37037 | 2.4068 | 1.0938 | 2.1471
| 892 | 0.42593 | 2.4915 | 0.96875 | 2.2437
| 893 | 0.38889 | 2.7627 | 1.0312 | 1.9874
| 894 | 0.55556 | 2.5593 | 1.375 | 1.7101
| 895 | 0.38889 | 2.3559 | 1.6875 | 1.9496
| 896 | 0.43519 | 3.2881 | 0.90625 | 2
| 897 | 0.27778 | 2.1017 | 1.7188 | 2.2269
| 898 | 0.57407 | 2.7458 | 1.625 | 2.1933
| 899 | 0.32407 | 2.2542 | 1.3438 | 2.6429
| 900 | 0.33333 | 3.0678 | 1.625 | 1.9202
| 901 | 0.49074 | 3.8305 | 1.7188 | 1.9034
| 902 | 0.40741 | 2.322 | 2 | 1.9328
| 903 | 0.33333 | 2.7627 | 1.375 | 1.6513
| 904 | 0.33333 | 2.9322 | 1.4062 | 1.8235
| 905 | 0.38889 | 1.6949 | 0.84375 | 2.0504
| 906 | 0.36111 | 2.8475 | 1.375 | 1.9412
| 907 | 0.46296 | 3.1017 | 1.125 | 2.084
| 908 | 0.5463 | 2.0508 | 1.7812 | 2.2185
| 909 | 0.2963 | 2.7627 | 1.0625 | 1.9538
| 910 | 0.42593 | 3.4915 | 1.0938 | 2.479
| 911 | 0.50926 | 2.6441 | 1.5 | 2.1303
| 912 | 0.43519 | 2.6441 | 1.5938 | 2.3824
| 913 | 0.4537 | 2.6271 | 1.4688 | 2.2563
| 914 | 0.42593 | 3.4746 | 1.0938 | 2.6471
| 915 | 0.39815 | 3.2034 | 2.375 | 1.9496
| 916 | 0.48148 | 3.0339 | 2.0938 | 2.2437
| 917 | 0.36111 | 2.5254 | 1.1562 | 2.3403
| 918 | 0.32407 | 2.8136 | 1.6875 | 1.9328
| 919 | 0.32407 | 3.3729 | 1.2812 | 2.3697
| 920 | 0.4537 | 2.322 | 1.125 | 2.042
| 921 | 0.26852 | 2.8136 | 1.7188 | 1.9748
| 922 | 0.5 | 1.6949 | 1.375 | 2.084
| 923 | 0.30556 | 1.7458 | 1.3125 | 2.0924
| 924 | 0.55556 | 2.9492 | 1.6562 | 1.9454
| 925 | 0.39815 | 2.8814 | 2.2812 | 2.2563
| 926 | 0.5 | 2.8814 | 1.2812 | 2.1723
| 927 | 0.48148 | 2.9153 | 1.8438 | 1.7899
| 928 | 0.5 | 2.6102 | 2.0938 | 2.1891
| 929 | 0.34259 | 2.8644 | 1.0312 | 2.021
| 930 | 0.37963 | 2.6949 | 0.65625 | 2.3445
| 931 | 0.38889 | 2.7288 | 1.0312 | 2.1723
| 932 | 0.36111 | 3.4576 | 1.4375 | 2.1849
| 933 | 0.32407 | 2.9492 | 2.2188 | 2.0336
| 934 | 0.35185 | 3.0339 | 0.625 | 1.6807
| 935 | 0.52778 | 2.8136 | 1.4375 | 2.2857
| 936 | 0.35185 | 2.0847 | 1.5312 | 1.9622
| 937 | 0.53704 | 2.5763 | 1.4375 | 2.4874
| 938 | 0.41667 | 2.4068 | 1.4062 | 2.1134
| 939 | 0.36111 | 3 | 0.65625 | 2.0966
| 940 | 0.57407 | 2.6441 | 1.3438 | 1.9706
| 941 | 0.60185 | 3.1186 | 1.3438 | 2.3824
| 942 | 0.47222 | 2.7288 | 1.5312 | 2.2983
| 943 | 0.47222 | 2.4746 | 1.6875 | 2.2941
| 944 | 0.46296 | 2.6271 | 2.0312 | 1.9958
| 945 | 0.38889 | 3.1864 | 0.875 | 1.9496
| 946 | 0.50926 | 2.2712 | 1.2188 | 2.0882
| 947 | 0.41667 | 2.7797 | 1.875 | 2.0714
| 948 | 0.50926 | 3.322 | 1.0938 | 2.2185
| 949 | 0.39815 | 3.0847 | 1.0312 | 2.0084
| 950 | 0.4537 | 3.1017 | 2.2812 | 2.437
| 951 | 0.41667 | 2.8475 | 1 | 2.3782
| 952 | 0.27778 | 2.8983 | 1.25 | 2.3487
| 953 | 0.44444 | 2.8475 | 1.9375 | 2.0966
| 954 | 0.60185 | 2.5932 | 1.8438 | 2.1639
| 955 | 0.38889 | 2.2712 | 1.5312 | 1.8109
| 956 | 0.31481 | 2.7458 | 1.2188 | 2.0336
| 957 | 0.38889 | 2.5254 | 1.2188 | 1.9874
| 958 | 0.25926 | 2.7627 | 1.375 | 2.3782
| 959 | 0.61111 | 2.5254 | 1.125 | 1.9328
| 960 | 0.42593 | 2.5085 | 0.71875 | 2.6303
| 961 | 0.39815 | 2.7288 | 2.2812 | 2.4034
| 962 | 0.48148 | 2.3898 | 1.0938 | 2.0126
| 963 | 0.35185 | 2.7119 | 1.4062 | 1.8529
| 964 | 0.43519 | 2.7458 | 0.875 | 1.9538
| 965 | 0.37037 | 2.9322 | 1.2812 | 2.3655
| 966 | 0.32407 | 2.3559 | 1.3438 | 1.9454
| 967 | 0.56481 | 2.3729 | 1.375 | 1.7941
| 968 | 0.49074 | 2.5932 | 1.5625 | 2.2773
| 969 | 0.5463 | 1.9153 | 1.1875 | 2.0462
| 970 | 0.40741 | 3.2034 | 1 | 1.9244
| 971 | 0.42593 | 2.2712 | 1.3125 | 1.8235
| 972 | 0.50926 | 2.4068 | 1.5625 | 2.416
| 973 | 0.47222 | 2.5254 | 1.0938 | 1.7479
| 974 | 0.40741 | 2.7797 | 1.375 | 2.1681
| 975 | 0.35185 | 2.322 | 0.75 | 1.9538
| 976 | 0.2963 | 2.6441 | 0.8125 | 2.0588
| 977 | 0.62963 | 2.4915 | 1.5 | 2.0378
| 978 | 0.34259 | 2.7458 | 1.5 | 2.2143
| 979 | 0.5463 | 2.7119 | 1.0312 | 2.084
| 980 | 0.40741 | 3.0678 | 1.7812 | 2.0042
| 981 | 0.47222 | 2.4915 | 0.84375 | 2.0672
| 982 | 0.38889 | 2.5085 | 1.3438 | 2.1723
| 983 | 0.41667 | 2.7288 | 1.1562 | 1.9412
| 984 | 0.32407 | 2.5424 | 1.125 | 2.0504
| 985 | 0.28704 | 2.6441 | 0.96875 | 2.1555
| 986 | 0.24074 | 2.3559 | 1.625 | 2.4244
| 987 | 0.57407 | 2.6949 | 1.0938 | 2.0588
| 988 | 0.4537 | 3 | 1.5625 | 1.8782
| 989 | 0.55556 | 2.339 | 1.6875 | 2.2395
| 990 | 0.37963 | 2.2203 | 1 | 2.1597
| 991 | 0.39815 | 3.1017 | 2.875 | 2.2689
| 992 | 0.49074 | 2.9322 | 0.875 | 1.7521
| 993 | 0.33333 | 3.2373 | 1.5938 | 2.4244
| 994 | 0.46296 | 3.678 | 1.9375 | 2.2185
| 995 | 0.36111 | 2.4237 | 1 | 2.3571
| 996 | 0.31481 | 3.2542 | 1.4688 | 2.0462
| 997 | 0.38889 | 2.5254 | 1.0312 | 1.958
| 998 | 0.31481 | 3.2373 | 1.5312 | 2.1513
| 999 | 0.47222 | 2.2712 | 1.1875 | 1.9076
| 1000 | 0.34259 | 2.6102 | 2.125 | 1.9832
| 1001 | 0.34259 | 2.7627 | 1.6562 | 1.9286
| 1002 | 0.34259 | 3.3051 | 1.5938 | 1.9244
| 1003 | 0.19444 | 2.5932 | 1.6875 | 1.7563
| 1004 | 0.36111 | 3.0339 | 1.5625 | 1.7479
| 1005 | 0.31481 | 2.5085 | 0.8125 | 2.2731
| 1006 | 0.28704 | 2.4068 | 0.84375 | 2.0504
| 1007 | 0.35185 | 3.7627 | 1.8438 | 1.916
| 1008 | 0.46296 | 2.4237 | 1.0625 | 2.2479
| 1009 | 0.41667 | 2.678 | 1.6562 | 1.9496
| 1010 | 0.39815 | 2.7966 | 1.75 | 2.0546
| 1011 | 0.5463 | 2.5424 | 1.7188 | 1.8613
| 1012 | 0.51852 | 2.5763 | 1.3125 | 1.8445
| 1013 | 0.33333 | 2.6949 | 1.9375 | 2.2773
| 1014 | 0.34259 | 2.5932 | 0.96875 | 2.1176
| 1015 | 0.26852 | 2.8475 | 1.0312 | 2.395
| 1016 | 0.39815 | 2.7458 | 1.875 | 1.9622
| 1017 | 0.35185 | 3.1356 | 1.375 | 2.1639
| 1018 | 0.46296 | 2.6441 | 1.375 | 1.9622
| 1019 | 0.39815 | 2.2881 | 1.4062 | 1.895
| 1020 | 0.34259 | 1.4915 | 2.2812 | 1.8739
| 1021 | 0.51852 | 3.339 | 1.7812 | 2.2773
| 1022 | 0.40741 | 2.5763 | 2.625 | 2.4034
| 1023 | 0.37037 | 2.4915 | 1.6562 | 1.9832
| 1024 | 0.31481 | 2.5254 | 1.8125 | 2.2605
| 1025 | 0.51852 | 1.9661 | 1.2812 | 2.6345
| 1026 | 0.38889 | 2.1695 | 1.3438 | 2.1387
| 1027 | 0.41667 | 2.2712 | 1.4062 | 2.2563
| 1028 | 0.38889 | 2.8305 | 1.3438 | 1.9034
| 1029 | 0.23148 | 2.5932 | 1.9375 | 1.8445
| 1030 | 0.48148 | 2.4068 | 1.2812 | 2.1849
| 1031 | 0.40741 | 2.5763 | 1.0625 | 2.1639
| 1032 | 0.40741 | 2.2203 | 0.78125 | 2.2437
| 1033 | 0.47222 | 2.9661 | 0.65625 | 2.1387
| 1034 | 0.46296 | 3.0508 | 0.96875 | 2.3067
| 1035 | 0.37037 | 2.8983 | 1.7188 | 1.9244
| 1036 | 0.44444 | 2.3051 | 1.5 | 1.9286
| 1037 | 0.36111 | 2.1017 | 1.125 | 2.1261
| 1038 | 0.36111 | 3.2373 | 1.1562 | 2.1429
| 1039 | 0.4537 | 3.1017 | 1.3438 | 1.916
| 1040 | 0.58333 | 2.6441 | 1.7812 | 2.2731
| 1041 | 0.41667 | 2.1864 | 1.4688 | 2.3151
| 1042 | 0.43519 | 2.8475 | 0.84375 | 1.9916
| 1043 | 0.47222 | 3.9322 | 1.2188 | 2.4412
| 1044 | 0.30556 | 2.6102 | 1.25 | 1.9202
| 1045 | 0.40741 | 2.8983 | 1.2188 | 2.1639
| 1046 | 0.61111 | 3.1864 | 1.5312 | 2.1176
| 1047 | 0.40741 | 2.661 | 1.375 | 1.8655
| 1048 | 0.46296 | 2.6271 | 1.2812 | 2.1303
| 1049 | 0.37037 | 1.9831 | 1.1562 | 1.9244
| 1050 | 0.36111 | 2.1525 | 1.5 | 1.9538
| 1051 | 0.40741 | 2.7288 | 1.1875 | 1.9202
| 1052 | 0.35185 | 3.1186 | 1.2188 | 2.0336
| 1053 | 0.38889 | 2.7288 | 1.5938 | 2.1681
| 1054 | 0.39815 | 1.9153 | 1.4688 | 2.2731
| 1055 | 0.53704 | 3.1186 | 2.0625 | 2.1261
| 1056 | 0.37037 | 3.0678 | 1.2188 | 1.9874
| 1057 | 0.33333 | 2.2373 | 1.6875 | 2.3361
| 1058 | 0.33333 | 2.1864 | 1.2812 | 2.0882
| 1059 | 0.40741 | 3.2881 | 0.90625 | 2.1008
| 1060 | 0.25 | 2.7966 | 1.125 | 2.4454
| 1061 | 0.56481 | 3 | 1.375 | 2.1261
| 1062 | 0.57407 | 2.678 | 1.4375 | 1.9706
| 1063 | 0.30556 | 2.8136 | 1.375 | 2.1807
| 1064 | 0.25926 | 2.7458 | 1.8438 | 2.3151
| 1065 | 0.40741 | 1.8983 | 1.8125 | 1.7647
| 1066 | 0.53704 | 2.3729 | 1.5938 | 2.3277
| 1067 | 0.30556 | 2.6441 | 1.4375 | 2.437
| 1068 | 0.50926 | 3.5254 | 2.0625 | 2.4958
| 1069 | 0.40741 | 2.8305 | 1.2188 | 2.2815
| 1070 | 0.40741 | 3.0847 | 1.4688 | 2.0756
| 1071 | 0.26852 | 2.7458 | 1.3438 | 2.2689
| 1072 | 0.48148 | 1.6441 | 1.1562 | 2.5294
| 1073 | 0.5 | 3.2034 | 1.5 | 1.9328
| 1074 | 0.59259 | 2.7966 | 1.5312 | 1.7059
| 1075 | 0.43519 | 2.2712 | 1.4062 | 1.8908
| 1076 | 0.42593 | 2.5085 | 1.4375 | 1.9874
| 1077 | 0.39815 | 2.3559 | 1.4375 | 2.1849
| 1078 | 0.44444 | 2.6102 | 1.3438 | 2.0462
| 1079 | 0.41667 | 3.5932 | 1.125 | 2.4244
| 1080 | 0.41667 | 2.3051 | 1.0312 | 2.4748
| 1081 | 0.28704 | 2.661 | 1.4375 | 2.0966
| 1082 | 0.51852 | 2.4746 | 2.7188 | 2.437
| 1083 | 0.35185 | 2.2373 | 1.3438 | 1.8151
| 1084 | 0.37037 | 2.6102 | 0.9375 | 2.0714
| 1085 | 0.51852 | 2.661 | 1.2188 | 2.2395
| 1086 | 0.2963 | 2.6271 | 2.1875 | 2.1723
| 1087 | 0.37963 | 3.4915 | 1.4688 | 2.1891
| 1088 | 0.33333 | 2.8305 | 0.5 | 2.0336
| 1089 | 0.47222 | 2.5932 | 1.3438 | 2.437
| 1090 | 0.47222 | 2.7119 | 1.5312 | 2.2815
| 1091 | 0.5 | 2.1186 | 2.1875 | 2.4832
| 1092 | 0.34259 | 2.8644 | 0.9375 | 2.063
| 1093 | 0.35185 | 2.3729 | 1.25 | 1.979
| 1094 | 0.40741 | 2.8983 | 1.1562 | 2.0588
| 1095 | 0.59259 | 2.1186 | 1.9375 | 2.1933
| 1096 | 0.32407 | 3.1864 | 1.625 | 2.2521
| 1097 | 0.40741 | 3.1356 | 1.6875 | 1.8403
| 1098 | 0.37037 | 2.7458 | 1.3438 | 2.0714
| 1099 | 0.26852 | 1.5254 | 1.9062 | 2.2731
| 1100 | 0.38889 | 3.5085 | 0.4375 | 2.105
| 1101 | 0.41667 | 2.9831 | 2.0312 | 2.1891
| 1102 | 0.37963 | 2.4407 | 1.75 | 2.2269
| 1103 | 0.36111 | 2.8814 | 1.4375 | 2.1303
| 1104 | 0.5463 | 3.1525 | 2.1875 | 1.7815
| 1105 | 0.38889 | 3.0169 | 1.125 | 1.9958
| 1106 | 0.34259 | 2.3051 | 1.0312 | 1.937
| 1107 | 0.58333 | 2.9322 | 1.1562 | 1.7647
| 1108 | 0.40741 | 2.7458 | 1.1562 | 2.1555
| 1109 | 0.37963 | 2.9153 | 1.9375 | 1.8992
| 1110 | 0.2963 | 2.4068 | 1.625 | 1.8445
| 1111 | 0.49074 | 2.4746 | 1.3438 | 1.8067
| 1112 | 0.37037 | 2.661 | 0.6875 | 1.9706
| 1113 | 0.40741 | 2.9492 | 2.0625 | 1.8445
| 1114 | 0.47222 | 2.5932 | 1.4062 | 2.3151
| 1115 | 0.23148 | 2.9492 | 1.375 | 2.042
| 1116 | 0.42593 | 2.0169 | 1.4688 | 1.9076
| 1117 | 0.38889 | 2.1356 | 1.5312 | 2.3109
| 1118 | 0.37963 | 2.8305 | 1.9062 | 2.1555
| 1119 | 0.35185 | 2.0339 | 0.875 | 2.0756
| 1120 | 0.44444 | 2.3898 | 1.3438 | 2.0462
| 1121 | 0.39815 | 3.6102 | 1.7188 | 1.8487
| 1122 | 0.37963 | 2.6949 | 1.4062 | 2.2185
| 1123 | 0.41667 | 3.322 | 1.1562 | 2.1639
| 1124 | 0.43519 | 2.2881 | 1.6875 | 2.6261
| 1125 | 0.38889 | 2.8814 | 1.5625 | 2.1429
| 1126 | 0.41667 | 2.2203 | 2.2188 | 2.2941
| 1127 | 0.5 | 2.7288 | 1.0938 | 1.9916
| 1128 | 0.50926 | 2.7119 | 2.2188 | 1.8908
| 1129 | 0.42593 | 2.5424 | 1.3125 | 1.7899
| 1130 | 0.58333 | 3.1017 | 1.125 | 2.1639
| 1131 | 0.60185 | 2.0508 | 1.3438 | 2.4118
| 1132 | 0.32407 | 2.5593 | 1.3438 | 1.937
| 1133 | 0.2963 | 2.2034 | 0.875 | 1.937
| 1134 | 0.42593 | 3.7458 | 2.0312 | 2.2647
| 1135 | 0.33333 | 2.678 | 0.9375 | 1.937
| 1136 | 0.34259 | 2.7288 | 0.8125 | 2.1597
| 1137 | 0.57407 | 2.4237 | 1.4688 | 1.9958
| 1138 | 0.40741 | 3.2034 | 0.78125 | 2.1008
| 1139 | 0.30556 | 2.2881 | 1.2812 | 1.7689
| 1140 | 0.66667 | 2.6271 | 1.3438 | 2.2899
| 1141 | 0.43519 | 2.4068 | 1.75 | 1.8403
| 1142 | 0.40741 | 2.8475 | 2.0625 | 2.2563
| 1143 | 0.32407 | 2.9492 | 1.5312 | 2.2311
| 1144 | 0.44444 | 2.1017 | 1.4062 | 2.063
| 1145 | 0.43519 | 2.5424 | 1.5 | 1.9454
| 1146 | 0.4537 | 2.7119 | 1.8438 | 2.1975
| 1147 | 0.42593 | 3.6949 | 1.0625 | 2.0714
| 1148 | 0.42593 | 2.4237 | 2.0312 | 2.0504
| 1149 | 0.53704 | 3.339 | 1.7812 | 2.0252
| 1150 | 0.38889 | 2.4237 | 0.84375 | 2.3445
| 1151 | 0.32407 | 2.322 | 1.2188 | 2.0252
| 1152 | 0.42593 | 2.7966 | 2 | 1.8403
| 1153 | 0.57407 | 2.6271 | 1.3125 | 2.1933
| 1154 | 0.32407 | 2.661 | 2.0312 | 1.958
| 1155 | 0.52778 | 2.7966 | 0.90625 | 2.0588
| 1156 | 0.42593 | 2.4576 | 0.9375 | 2.4664
| 1157 | 0.33333 | 2.678 | 0.9375 | 2.0882
| 1158 | 0.5463 | 3.0339 | 1.0312 | 2.1429
| 1159 | 0.52778 | 2.5763 | 1.25 | 2.2395
| 1160 | 0.27778 | 2.4068 | 1.25 | 2.0672
| 1161 | 0.19444 | 2.8136 | 1.4688 | 2.4034
| 1162 | 0.41667 | 2.322 | 1.1562 | 1.6975
| 1163 | 0.5 | 2.5763 | 1.4062 | 2.0126
| 1164 | 0.47222 | 2.2542 | 1.5625 | 2.1387
| 1165 | 0.43519 | 2.1695 | 2.2812 | 2.1345
| 1166 | 0.36111 | 2.4746 | 1.875 | 2.2017
| 1167 | 0.42593 | 2.4068 | 1.1562 | 1.7731
| 1168 | 0.34259 | 2.0339 | 1.3438 | 2.2269
| 1169 | 0.39815 | 3.5254 | 1.0312 | 2.0798
| 1170 | 0.49074 | 2.4576 | 0.53125 | 2.2269
| 1171 | 0.42593 | 3.0169 | 0.875 | 2.0084
| 1172 | 0.28704 | 2.339 | 1.9062 | 1.8403
| 1173 | 0.41667 | 2.7119 | 1.4375 | 2.1975
| 1174 | 0.35185 | 2.8814 | 1.5 | 2.4076
| 1175 | 0.7037 | 2.3051 | 1.75 | 1.9244
| 1176 | 0.46296 | 3.339 | 2.4688 | 1.9412
| 1177 | 0.52778 | 3.2881 | 1.2812 | 1.8109
| 1178 | 0.59259 | 2.8475 | 2.5 | 1.8739
| 1179 | 0.57407 | 3.2881 | 2.6562 | 2.0924
| 1180 | 0.41667 | 3.6271 | 0.75 | 2.0462
| 1181 | 0.38889 | 2.0339 | 1.75 | 2.0966
| 1182 | 0.39815 | 2.661 | 1.1875 | 2.1218
| 1183 | 0.51852 | 3.0678 | 0.875 | 1.9916
| 1184 | 0.35185 | 3.0169 | 1.4688 | 1.895
| 1185 | 0.39815 | 2.3898 | 0.9375 | 2.0504
| 1186 | 0.30556 | 3.0169 | 1.0938 | 2.1387
| 1187 | 0.33333 | 2.7627 | 1.7812 | 1.9496
| 1188 | 0.38889 | 3 | 1.1875 | 2.3277
| 1189 | 0.39815 | 2.8983 | 1.5625 | 1.7857
| 1190 | 0.43519 | 2.1695 | 1.875 | 2.0042
| 1191 | 0.40741 | 2.7119 | 1.2812 | 2.0504
| 1192 | 0.33333 | 2.0508 | 0.96875 | 2.1975
| 1193 | 0.32407 | 2.5932 | 1.2812 | 2.2731
| 1194 | 0.53704 | 2.2542 | 0.875 | 2.105
| 1195 | 0.48148 | 2.4915 | 2 | 1.9118
| 1196 | 0.39815 | 3.4237 | 0.9375 | 1.7563
| 1197 | 0.56481 | 2.8475 | 2.0312 | 1.9034
| 1198 | 0.38889 | 2.6441 | 0.8125 | 1.8361
| 1199 | 0.59259 | 3.0339 | 1.0938 | 1.958
| 1200 | 0.37963 | 2.678 | 1.6875 | 1.9412
| 1201 | 0.32407 | 2.8305 | 1.6562 | 2.1092
| 1202 | 0.39815 | 3.1017 | 1.7188 | 2.2101
| 1203 | 0.40741 | 2.9831 | 1.1562 | 2.1765
| 1204 | 0.42593 | 3.0169 | 1.75 | 2.1134
| 1205 | 0.44444 | 2.6441 | 0.875 | 2.458
| 1206 | 0.4537 | 3.0169 | 1.7812 | 2.3613
| 1207 | 0.53704 | 3.5254 | 1.5625 | 1.9874
| 1208 | 0.31481 | 3.1356 | 1.1562 | 1.8824
| 1209 | 0.35185 | 2.5424 | 0.9375 | 1.9496
| 1210 | 0.42593 | 2.3559 | 1.4688 | 2.2479
| 1211 | 0.41667 | 3.1525 | 1.25 | 2.2941
| 1212 | 0.38889 | 2.2712 | 1.1875 | 2.1765
| 1213 | 0.52778 | 2.2712 | 1.5 | 2.2815
| 1214 | 0.35185 | 2.339 | 0.59375 | 2.1387
| 1215 | 0.33333 | 3.1864 | 2.1875 | 2.2689
| 1216 | 0.41667 | 2.1864 | 1.4375 | 1.979
| 1217 | 0.55556 | 2.4407 | 1.5938 | 2.0042
| 1218 | 0.38889 | 2.2203 | 1.4688 | 2.4118
| 1219 | 0.36111 | 1.9661 | 0.84375 | 2.2311
| 1220 | 0.5 | 2.1864 | 1.875 | 2.1429
| 1221 | 0.49074 | 2.5932 | 1.1562 | 2.1008
| 1222 | 0.49074 | 2.9831 | 1.9062 | 2.0714
| 1223 | 0.44444 | 2.8475 | 1.6562 | 2.1975
| 1224 | 0.53704 | 2.8983 | 1.3438 | 2.1008
| 1225 | 0.42593 | 2.339 | 1 | 2.1176
| 1226 | 0.33333 | 2.8983 | 1.375 | 2.0924
| 1227 | 0.30556 | 2.8475 | 1.4688 | 2.2857
| 1228 | 0.34259 | 2.7119 | 2.0625 | 1.7269
| 1229 | 0.40741 | 2.7458 | 1.0938 | 2.1807
| 1230 | 0.35185 | 3.3559 | 1.5938 | 2.2269
| 1231 | 0.34259 | 2.7288 | 1.9375 | 2.2941
| 1232 | 0.46296 | 3.1525 | 1.5312 | 2.4664
| 1233 | 0.48148 | 3.0169 | 2.2812 | 2.2689
| 1234 | 0.44444 | 3.0339 | 0.90625 | 2.3193
| 1235 | 0.34259 | 2.0847 | 1.75 | 2.3487
| 1236 | 0.42593 | 2.6949 | 1.1875 | 2.3697
| 1237 | 0.39815 | 2.5085 | 1.4688 | 2.1681
| 1238 | 0.38889 | 2.8644 | 1.9375 | 2.021
| 1239 | 0.28704 | 3.3559 | 0.96875 | 2.0378
| 1240 | 0.36111 | 2.6949 | 1.1875 | 2.2101
| 1241 | 0.49074 | 2.2373 | 1.5 | 2.1597
| 1242 | 0.41667 | 2.6949 | 1 | 2.3571
| 1243 | 0.25926 | 2.6441 | 1.2812 | 2.4412
| 1244 | 0.28704 | 2.7627 | 1.6562 | 2.0462
| 1245 | 0.4537 | 3.5085 | 1.3438 | 2.2647
| 1246 | 0.36111 | 2.0847 | 2.25 | 1.8025
| 1247 | 0.53704 | 2.2881 | 1.4062 | 1.8908
| 1248 | 0.37963 | 2.8136 | 1.4688 | 1.8403
| 1249 | 0.38889 | 3.1695 | 1.3438 | 2.2605
| 1250 | 0.5463 | 2.4576 | 1.5938 | 2.0882
| 1251 | 0.62037 | 2.322 | 1.125 | 2.3151
| 1252 | 0.37037 | 2.6271 | 1.375 | 1.9538
| 1253 | 0.50926 | 2.2712 | 1.8125 | 2.2773
| 1254 | 0.64815 | 2.1525 | 1.5 | 1.9832
| 1255 | 0.44444 | 3.0678 | 1.5312 | 2.1387
| 1256 | 0.44444 | 2.1695 | 2.25 | 2.0336
| 1257 | 0.37037 | 2.2542 | 1.5938 | 2.6387
| 1258 | 0.37963 | 2.3729 | 1.1875 | 2.2689
| 1259 | 0.37963 | 2.1695 | 1.8438 | 2.4706
| 1260 | 0.36111 | 2.3051 | 1.125 | 2.2227
| 1261 | 0.34259 | 2.9492 | 1.3125 | 1.979
| 1262 | 0.33333 | 3.2881 | 1.4375 | 2.3824
| 1263 | 0.39815 | 2.5593 | 1.75 | 2.1261
| 1264 | 0.38889 | 2.3051 | 1.2812 | 1.9412
| 1265 | 0.43519 | 3.5763 | 1.0938 | 2.4202
| 1266 | 0.39815 | 2.1864 | 1.0312 | 1.7563
| 1267 | 0.39815 | 3.0508 | 1.3438 | 2.2101
| 1268 | 0.37963 | 2.322 | 1.1875 | 2.9748
| 1269 | 0.42593 | 2.7797 | 1.0312 | 2.2983
| 1270 | 0.32407 | 2.9322 | 1.4375 | 2.2521
| 1271 | 0.39815 | 2.9322 | 1.375 | 2.2479
| 1272 | 0.40741 | 3.1017 | 1.4688 | 2.1513
| 1273 | 0.60185 | 2.5593 | 0.96875 | 1.9412
| 1274 | 0.5 | 1.8814 | 0.59375 | 2.063
| 1275 | 0.39815 | 2.3898 | 1.1562 | 2.0084
| 1276 | 0.59259 | 2.5932 | 1.375 | 2.0084
| 1277 | 0.31481 | 1.6949 | 1.3438 | 2.0798
| 1278 | 0.57407 | 3.0169 | 1.0625 | 1.7773
| 1279 | 0.47222 | 3.1186 | 1.2188 | 1.8655
| 1280 | 0.50926 | 2.661 | 1.1562 | 2.4034
| 1281 | 0.37963 | 2.8136 | 0.90625 | 2.105
| 1282 | 0.44444 | 2.322 | 1.4375 | 2.2269
| 1283 | 0.40741 | 2.6271 | 0.625 | 2.1387
| 1284 | 0.5 | 2.4915 | 1.25 | 2.1429
| 1285 | 0.56481 | 2.7966 | 1.3438 | 2.0672
| 1286 | 0.52778 | 2.8475 | 1.5312 | 1.9538
| 1287 | 0.50926 | 2.8305 | 0.8125 | 1.7269
| 1288 | 0.57407 | 2.678 | 1.3438 | 2.1681
| 1289 | 0.47222 | 3.4068 | 0.8125 | 2.0378
| 1290 | 0.34259 | 3.1864 | 1.125 | 1.9076
| 1291 | 0.49074 | 2.5763 | 1.5625 | 2.2227
| 1292 | 0.53704 | 3.0508 | 1.9688 | 2.4076
| 1293 | 0.71296 | 3 | 1.4688 | 1.9916
| 1294 | 0.39815 | 2.5932 | 2.2188 | 2.0462
| 1295 | 0.43519 | 2.4237 | 2 | 1.958
| 1296 | 0.35185 | 2.9153 | 1.4375 | 2.1303
| 1297 | 0.33333 | 3.661 | 1.5625 | 1.8193
| 1298 | 0.31481 | 2.322 | 1.9375 | 1.7689
| 1299 | 0.31481 | 2.2881 | 1.9062 | 2.1429
| 1300 | 0.41667 | 3.4915 | 1.1875 | 1.7815
| 1301 | 0.37037 | 3.5424 | 1.75 | 2.0294
| 1302 | 0.38889 | 2.2373 | 1.1562 | 2.1303
| 1303 | 0.24074 | 2.3729 | 1.5312 | 2.063
| 1304 | 0.57407 | 2.5593 | 1.875 | 2.3193
| 1305 | 0.41667 | 2.5424 | 0.96875 | 2.2689
| 1306 | 0.38889 | 2.5254 | 1.0625 | 2.2143
| 1307 | 0.44444 | 1.9153 | 1.625 | 1.9496
| 1308 | 0.40741 | 2.2712 | 0.96875 | 2.0504
| 1309 | 0.38889 | 2.7288 | 1.5938 | 1.6975
| 1310 | 0.27778 | 2.9831 | 1.625 | 2.3109
| 1311 | 0.39815 | 2.8475 | 1.6875 | 2.4034
| 1312 | 0.34259 | 3.0847 | 1.1562 | 2.1975
| 1313 | 0.47222 | 2.6102 | 1.3438 | 2.1807
| 1314 | 0.46296 | 2.8305 | 0.875 | 2.1345
| 1315 | 0.28704 | 2.5424 | 1.4062 | 1.8782
| 1316 | 0.66667 | 2.4746 | 2.0625 | 2.2773
| 1317 | 0.57407 | 3.2712 | 1.6875 | 2.2311
| 1318 | 0.42593 | 2.8136 | 1.0625 | 1.8824
| 1319 | 0.43519 | 2.1356 | 1.9688 | 2.0924
| 1320 | 0.31481 | 2.4407 | 1.6562 | 2.3025
| 1321 | 0.50926 | 2.8305 | 1.3438 | 1.8403
| 1322 | 0.5 | 2.3559 | 1.0938 | 2.3319
| 1323 | 0.41667 | 2.9661 | 1.0312 | 2.1765
| 1324 | 0.25926 | 3.2203 | 1.125 | 2.2017
| 1325 | 0.49074 | 3.0678 | 0.4375 | 2.1639
| 1326 | 0.42593 | 2.3051 | 1.5 | 2.1975
| 1327 | 0.35185 | 2.9153 | 1.5625 | 2.1303
| 1328 | 0.33333 | 2.3051 | 0.9375 | 2.021
| 1329 | 0.35185 | 2.6102 | 2.0938 | 1.895
| 1330 | 0.42593 | 2.678 | 1.4375 | 2.3361
| 1331 | 0.43519 | 3 | 1 | 1.8992
| 1332 | 0.25 | 2.5085 | 1.6562 | 2.2101
| 1333 | 0.50926 | 3.0847 | 1.3438 | 1.8193
| 1334 | 0.38889 | 2.5424 | 1.5938 | 2.1176
| 1335 | 0.25926 | 2.6441 | 1.125 | 2.5672
| 1336 | 0.24074 | 3.0508 | 1.0312 | 1.8067
| 1337 | 0.35185 | 2.1864 | 1.375 | 2.1261
| 1338 | 0.37037 | 2.7797 | 1.6875 | 2.0756
| 1339 | 0.4537 | 2.3559 | 0.59375 | 2.3319
| 1340 | 0.36111 | 3.2712 | 1.75 | 2.2647
| 1341 | 0.42593 | 3.4915 | 1.0312 | 2.2227
| 1342 | 0.44444 | 2.9153 | 1.25 | 2.0462
| 1343 | 0.27778 | 2.2542 | 1.4375 | 2.3151
| 1344 | 0.27778 | 2.1864 | 0.875 | 2.1639
| 1345 | 0.36111 | 2.3898 | 0.78125 | 1.9664
| 1346 | 0.49074 | 2.0678 | 1.1875 | 2.1092
| 1347 | 0.4537 | 2.7119 | 1.5 | 1.9496
| 1348 | 0.42593 | 2.7627 | 1.4688 | 2.3403
| 1349 | 0.5 | 3.2542 | 1.625 | 2.5
| 1350 | 0.40741 | 3.0508 | 1.25 | 2.1008
| 1351 | 0.40741 | 2.7966 | 2.0938 | 1.7647
| 1352 | 0.44444 | 2.1695 | 1.7188 | 2.105
| 1353 | 0.4537 | 1.6949 | 2.7188 | 2.2773
| 1354 | 0.44444 | 2.1695 | 1.1562 | 2.1261
| 1355 | 0.35185 | 2.6102 | 0.90625 | 2.4202
| 1356 | 0.46296 | 2.7966 | 1.6875 | 1.7353
| 1357 | 0.48148 | 3.0847 | 1.0938 | 2.1765
| 1358 | 0.47222 | 2.4746 | 1.7188 | 2.2983
| 1359 | 0.47222 | 2.3898 | 1.6875 | 2.3235
| 1360 | 0.37963 | 2.3559 | 1.75 | 2.0882
| 1361 | 0.36111 | 3.1356 | 0.65625 | 2.1176
| 1362 | 0.35185 | 2.8136 | 1.5938 | 2.0798
| 1363 | 0.24074 | 2.8136 | 1.875 | 1.9034
| 1364 | 0.4537 | 2.8983 | 1.5625 | 2.105
| 1365 | 0.36111 | 3.0169 | 1.5938 | 2.1765
| 1366 | 0.34259 | 1.9831 | 1.0938 | 1.9034
| 1367 | 0.5463 | 1.9831 | 1.5312 | 1.8866
| 1368 | 0.46296 | 3.0339 | 1.25 | 1.9202
| 1369 | 0.5 | 3.3051 | 1.9375 | 1.7773
| 1370 | 0.38889 | 2.5763 | 1.9375 | 2.105
| 1371 | 0.42593 | 3.1186 | 1.5625 | 2.0546
| 1372 | 0.47222 | 3.0508 | 1.4062 | 2.5168
| 1373 | 0.18519 | 2.4407 | 1.25 | 1.8992
| 1374 | 0.4537 | 2.6271 | 0.8125 | 2.0672
| 1375 | 0.39815 | 2.8475 | 1.5 | 1.9622
| 1376 | 0.40741 | 2.7966 | 1.0312 | 2.6849
| 1377 | 0.40741 | 3.0847 | 1.5938 | 2.1387
| 1378 | 0.38889 | 2.7797 | 1.25 | 2.1765
| 1379 | 0.63889 | 2.3898 | 1.3438 | 2.1387
| 1380 | 0.2963 | 3.1017 | 1.5625 | 2.0378
| 1381 | 0.5 | 2.1695 | 1.4375 | 2.2311
| 1382 | 0.4537 | 2.9322 | 1.5312 | 2
| 1383 | 0.38889 | 2.4746 | 2.0312 | 2.1134
| 1384 | 0.40741 | 3.1186 | 1.2812 | 1.9748
| 1385 | 0.44444 | 2.2203 | 1.5938 | 2.5042
| 1386 | 0.42593 | 2.1695 | 1.4375 | 2.1218
| 1387 | 0.58333 | 2.7119 | 1.3125 | 2.2269
| 1388 | 0.46296 | 2.3898 | 1.1875 | 2.3025
| 1389 | 0.44444 | 3.1695 | 1.25 | 2.0882
| 1390 | 0.39815 | 2.5424 | 1.4375 | 2.5378
| 1391 | 0.59259 | 2.4915 | 2.125 | 1.9832
| 1392 | 0.46296 | 2.339 | 1.4688 | 1.9748
| 1393 | 0.40741 | 2.3559 | 1.4062 | 1.7563
| 1394 | 0.32407 | 2.6271 | 1.2188 | 2.042
| 1395 | 0.46296 | 2.8644 | 1.1562 | 2.1008
| 1396 | 0.39815 | 3.5593 | 0.625 | 2.0084
| 1397 | 0.2963 | 2.7458 | 1.1875 | 1.9412
| 1398 | 0.40741 | 2.3898 | 1.3125 | 2.1681
| 1399 | 0.41667 | 2.6441 | 1.5625 | 2.7311
| 1400 | 0.44444 | 2.6271 | 1.0312 | 2.5336
| 1401 | 0.41667 | 3.661 | 0.8125 | 2.1092
| 1402 | 0.52778 | 3.1864 | 2.1562 | 1.9412
| 1403 | 0.42593 | 2.4237 | 2.4375 | 2.0168
| 1404 | 0.39815 | 2.5424 | 0.875 | 2.1008
| 1405 | 0.32407 | 3.1356 | 1.3125 | 2.3529
| 1406 | 0.32407 | 2.4576 | 1.625 | 2.2143
| 1407 | 0.38889 | 2.2373 | 1.5938 | 2.0504
| 1408 | 0.49074 | 2.6949 | 1.9688 | 2.1933
| 1409 | 0.37037 | 2.7288 | 1.0938 | 1.916
| 1410 | 0.30556 | 2.4915 | 1.9062 | 2.2017
| 1411 | 0.37037 | 2.1017 | 1.25 | 1.916
| 1412 | 0.51852 | 3.322 | 1.1562 | 2.2605
| 1413 | 0.44444 | 2.7119 | 1.5625 | 1.8613
| 1414 | 0.49074 | 1.8814 | 1.875 | 2.1765
| 1415 | 0.53704 | 3.3898 | 0.875 | 1.7269
| 1416 | 0.34259 | 2.0678 | 1.1562 | 2.3824
| 1417 | 0.48148 | 2.6441 | 2.0625 | 2.0378
| 1418 | 0.50926 | 2.678 | 1.1562 | 2.1555
| 1419 | 0.39815 | 2.2373 | 1.625 | 2.1387
| 1420 | 0.43519 | 2.5085 | 1.2812 | 2.542
| 1421 | 0.56481 | 2.2881 | 1.1875 | 2.1597
| 1422 | 0.43519 | 2.2881 | 1.4062 | 2.2899
| 1423 | 0.37963 | 2.2542 | 1.0625 | 1.9664
| 1424 | 0.4537 | 2.5593 | 1.4688 | 1.9706
| 1425 | 0.59259 | 2.4746 | 1.6875 | 1.9706
| 1426 | 0.37037 | 2.5593 | 0.9375 | 2.1555
| 1427 | 0.62037 | 2.7797 | 1.625 | 2.2185
| 1428 | 0.37963 | 2.4237 | 1.5 | 2.1975
| 1429 | 0.50926 | 2.8305 | 1.2812 | 2.1765
| 1430 | 0.46296 | 1.9322 | 1.375 | 2.0126
| 1431 | 0.36111 | 2.4237 | 1.9375 | 2.2017
| 1432 | 0.25 | 3.2034 | 2.4062 | 1.8613
| 1433 | 0.32407 | 2.9492 | 1.3125 | 1.9034
| 1434 | 0.41667 | 2.4915 | 1.7188 | 2.1471
| 1435 | 0.50926 | 2.5593 | 0.65625 | 1.9202
| 1436 | 0.39815 | 2.5932 | 1.375 | 2.1975
| 1437 | 0.43519 | 2.5763 | 0.90625 | 2.3403
| 1438 | 0.34259 | 2.2034 | 1.5625 | 2.2101
| 1439 | 0.37037 | 2.9322 | 0.90625 | 2.1723
| 1440 | 0.65741 | 2.5424 | 0.6875 | 1.9958
| 1441 | 0.39815 | 2.4237 | 1.9062 | 2.0462
| 1442 | 0.63889 | 3.0169 | 1.1562 | 2.2773
| 1443 | 0.28704 | 2.9153 | 1.1562 | 1.8739
| 1444 | 0.39815 | 2.1356 | 1.5 | 2.4328
| 1445 | 0.34259 | 3.5763 | 1.0312 | 1.7731
| 1446 | 0.43519 | 3.0169 | 1.5 | 2.1765
| 1447 | 0.41667 | 3.2712 | 1 | 2.0084
| 1448 | 0.35185 | 2.0339 | 1.125 | 2.0798
| 1449 | 0.37037 | 2.5932 | 1.9375 | 2.0672
| 1450 | 0.43519 | 2.5254 | 1.25 | 2.3151
| 1451 | 0.57407 | 2.4407 | 1.7812 | 2.105
| 1452 | 0.47222 | 2.2373 | 1.6562 | 2.3319
| 1453 | 0.2963 | 2.2542 | 1.9688 | 1.9118
| 1454 | 0.61111 | 2.5254 | 1.5938 | 2.0378
| 1455 | 0.46296 | 2.6271 | 1.8125 | 2.2857
| 1456 | 0.42593 | 2.4576 | 1.5938 | 2.2689
| 1457 | 0.43519 | 3.7288 | 1.5938 | 1.8782
| 1458 | 0.40741 | 2.7119 | 1.5312 | 1.7983
| 1459 | 0.43519 | 3.2712 | 1.1875 | 2.6387
| 1460 | 0.36111 | 3.0508 | 0.5625 | 2.2941
| 1461 | 0.32407 | 2.4915 | 2.1562 | 2.4622
| 1462 | 0.25 | 2.7119 | 0.6875 | 2.1639
| 1463 | 0.39815 | 2.4746 | 1.625 | 2.0168
| 1464 | 0.44444 | 2.8305 | 1.5 | 2.0336
| 1465 | 0.61111 | 2.5593 | 1.3125 | 1.8908
| 1466 | 0.41667 | 2.5763 | 1.1875 | 2.2059
| 1467 | 0.48148 | 3.1695 | 0.90625 | 1.8445
| 1468 | 0.49074 | 2.8644 | 1.1875 | 2.1008
| 1469 | 0.2963 | 2.6441 | 2 | 2.0672
| 1470 | 0.59259 | 2.9492 | 2.5625 | 2.5294
| 1471 | 0.39815 | 2.7627 | 1 | 1.9832
| 1472 | 0.36111 | 2.9322 | 1.625 | 2.5714
| 1473 | 0.37037 | 2.6441 | 1.1875 | 2.021
| 1474 | 0.33333 | 2.0339 | 1.875 | 1.9412
| 1475 | 0.31481 | 2.0847 | 1.0938 | 1.9664
| 1476 | 0.43519 | 2.4407 | 1.1875 | 2.1975
| 1477 | 0.57407 | 3.4407 | 2.0938 | 2.3319
| 1478 | 0.43519 | 2.678 | 1.0312 | 1.9076
| 1479 | 0.34259 | 2.9492 | 1.4688 | 2.1891
| 1480 | 0.35185 | 2.2034 | 2.2188 | 2.0882
| 1481 | 0.5 | 2.4068 | 0.90625 | 2.3235
| 1482 | 0.37963 | 2.3729 | 1.125 | 1.8277
| 1483 | 0.51852 | 2.6441 | 1.1875 | 2.0882
| 1484 | 0.26852 | 3.0169 | 1.1875 | 2.1471
| 1485 | 0.36111 | 3.1356 | 0.8125 | 2.2563
| 1486 | 0.58333 | 2.4407 | 1.7812 | 2.0672
| 1487 | 0.39815 | 2.1864 | 1.5625 | 2.3025
| 1488 | 0.49074 | 2.8136 | 1.6562 | 2.3824
| 1489 | 0.52778 | 3.0339 | 1.75 | 2.0168
| 1490 | 0.42593 | 3.0847 | 1.75 | 2.2395
| 1491 | 0.48148 | 2.7119 | 1.75 | 2.1303
| 1492 | 0.36111 | 2.8983 | 1.4062 | 2.2395
| 1493 | 0.44444 | 1.6102 | 1.625 | 2.2059
| 1494 | 0.46296 | 3.0508 | 1.5312 | 2.0798
| 1495 | 0.49074 | 2.678 | 1 | 2.063
| 1496 | 0.25926 | 2.2542 | 1.2812 | 2.2479
| 1497 | 0.37037 | 3.0678 | 2.4062 | 2.2521
| 1498 | 0.5 | 2.1695 | 1.3438 | 2.0042
| 1499 | 0.56481 | 2.4068 | 1.1875 | 2.2269
| 1500 | 0.30556 | 2.322 | 1.5625 | 2.0588
| 1501 | 0.40741 | 2.9831 | 2.25 | 1.895
| 1502 | 0.36111 | 2.4576 | 1.4375 | 2.0882
| 1503 | 0.35185 | 3.2712 | 0.5 | 2.0546
| 1504 | 0.24074 | 2.2034 | 1.5 | 1.8992
| 1505 | 0.5 | 2.7288 | 1.8438 | 1.8697
| 1506 | 0.31481 | 2.6441 | 1.5312 | 2.1681
| 1507 | 0.33333 | 1.9153 | 2.0625 | 1.979
| 1508 | 0.4537 | 2.3051 | 1.5312 | 2.0966
| 1509 | 0.50926 | 2.8644 | 1.8125 | 2.1681
| 1510 | 0.42593 | 2.8475 | 1 | 2.1471
| 1511 | 0.42593 | 2.5254 | 1.9062 | 1.9454
| 1512 | 0.47222 | 3.2542 | 1.0625 | 2.2941
| 1513 | 0.57407 | 2.5932 | 1.9062 | 1.8739
| 1514 | 0.4537 | 2.5932 | 0.96875 | 1.8571
| 1515 | 0.47222 | 2.339 | 0.9375 | 2.1639
| 1516 | 0.34259 | 2.1186 | 1.6562 | 1.7983
| 1517 | 0.2963 | 2.9831 | 0.78125 | 2.042
| 1518 | 0.37037 | 2.1695 | 1.5312 | 2
| 1519 | 0.30556 | 2.9153 | 0.90625 | 1.8571
| 1520 | 0.33333 | 2.7119 | 1.4062 | 2.1261
| 1521 | 0.37037 | 2.6441 | 1.6562 | 1.8403
| 1522 | 0.38889 | 2.5763 | 1.5 | 2.2059
| 1523 | 0.51852 | 2.661 | 1.6562 | 1.8487
| 1524 | 0.37037 | 2.678 | 1.1562 | 2.0714
| 1525 | 0.42593 | 2.2034 | 0.90625 | 2.1765
| 1526 | 0.37963 | 2.7288 | 1.625 | 2.1092
| 1527 | 0.50926 | 3.1017 | 1.5625 | 2.1303
| 1528 | 0.40741 | 2.7288 | 1.6875 | 2.2101
| 1529 | 0.55556 | 2.0339 | 0.9375 | 2.0042
| 1530 | 0.50926 | 2.2712 | 1.5938 | 2.0672
| 1531 | 0.41667 | 2.5424 | 0.9375 | 1.9202
| 1532 | 0.50926 | 2.661 | 1.0625 | 1.9244
| 1533 | 0.5 | 2.5254 | 0.65625 | 1.9832
| 1534 | 0.35185 | 2.0847 | 0.90625 | 2.1807
| 1535 | 0.47222 | 2.7119 | 2 | 2.0882
| 1536 | 0.39815 | 2.7458 | 0.9375 | 1.8109
| 1537 | 0.42593 | 2.0508 | 1.3438 | 2.2227
| 1538 | 0.47222 | 2.7797 | 0.84375 | 1.9664
| 1539 | 0.44444 | 2.1864 | 1.5938 | 1.8193
| 1540 | 0.38889 | 2.7288 | 2.1875 | 2.5462
| 1541 | 0.47222 | 2.678 | 1.0312 | 1.9328
| 1542 | 0.37037 | 2.8814 | 1.2188 | 2.0798
| 1543 | 0.56481 | 2.1356 | 1.5312 | 1.937
| 1544 | 0.38889 | 2.9492 | 1.9062 | 2.2689
| 1545 | 0.38889 | 3.0678 | 1.6875 | 1.8151
| 1546 | 0.5 | 2.3729 | 1.375 | 2.0672
| 1547 | 0.46296 | 2.9322 | 0.90625 | 2.2269
| 1548 | 0.48148 | 2.678 | 1.125 | 2.2647
| 1549 | 0.38889 | 2.4068 | 1.625 | 1.7857
| 1550 | 0.4537 | 2.6102 | 0.96875 | 2.2731
| 1551 | 0.4537 | 2.7119 | 0.96875 | 2.1555
| 1552 | 0.39815 | 2.1864 | 1.4375 | 2.0378
| 1553 | 0.32407 | 2.5932 | 0.84375 | 1.8655
| 1554 | 0.4537 | 3.1017 | 1.1562 | 2.2605
| 1555 | 0.50926 | 2.661 | 1.5625 | 1.9748
| 1556 | 0.5463 | 2.3051 | 1.1875 | 2.1008
| 1557 | 0.46296 | 3.4237 | 1.0312 | 2.0588
| 1558 | 0.52778 | 2.1695 | 1.1562 | 2.3571
| 1559 | 0.32407 | 3.2373 | 0.90625 | 1.7815
| 1560 | 0.37037 | 2.7119 | 1.4375 | 1.9202
| 1561 | 0.42593 | 3.2373 | 1.7188 | 1.9706
| 1562 | 0.2963 | 2.7458 | 1.375 | 1.8277
| 1563 | 0.33333 | 2.3051 | 1.875 | 1.8487
| 1564 | 0.53704 | 2.678 | 1.375 | 2.0546
| 1565 | 0.43519 | 2.3729 | 1.7188 | 2.0084
| 1566 | 0.24074 | 2.4915 | 2.2188 | 2
| 1567 | 0.32407 | 2.7797 | 2 | 1.9496
| 1568 | 0.4537 | 2.2373 | 1.4062 | 1.9118
| 1569 | 0.37963 | 3.322 | 1.125 | 2.0462
| 1570 | 0.37037 | 2.4746 | 1.1875 | 1.8235
| 1571 | 0.39815 | 2.4746 | 0.84375 | 2.0882
| 1572 | 0.5463 | 2.5254 | 1.4062 | 2.2983
| 1573 | 0.39815 | 2.5424 | 1.4062 | 2.0126
| 1574 | 0.50926 | 2.7797 | 1.3438 | 1.8697
| 1575 | 0.56481 | 2.4407 | 0.75 | 2.3445
| 1576 | 0.39815 | 3.2881 | 1.9062 | 2.1387
| 1577 | 0.39815 | 1.8644 | 1.375 | 2.1345
| 1578 | 0.52778 | 3.1017 | 1.125 | 2.1513
| 1579 | 0.50926 | 2.2203 | 1.5625 | 2.6008
| 1580 | 0.39815 | 2.6441 | 1.6875 | 2.3908
| 1581 | 0.38889 | 2.3898 | 1.25 | 2.1345
| 1582 | 0.33333 | 2.6441 | 0.90625 | 1.9622
| 1583 | 0.43519 | 2.7458 | 1.4062 | 2.0462
| 1584 | 0.4537 | 2.3898 | 1.75 | 2.3235
| 1585 | 0.41667 | 2.7288 | 0.71875 | 2.0126
| 1586 | 0.5 | 3.5932 | 1.4688 | 1.9454
| 1587 | 0.19444 | 2.322 | 1.0312 | 2.1008
| 1588 | 0.31481 | 2.8136 | 1.0938 | 1.7857
| 1589 | 0.4537 | 2.8983 | 1.7812 | 2.2605
| 1590 | 0.38889 | 3.0678 | 1.3125 | 2.0336
| 1591 | 0.44444 | 3.1525 | 0.84375 | 1.937
| 1592 | 0.40741 | 2.9322 | 1.4062 | 2.2353
| 1593 | 0.36111 | 2.322 | 1.875 | 2.3739
| 1594 | 0.37037 | 3.1695 | 2.1562 | 1.8908
| 1595 | 0.26852 | 2.7119 | 1.9375 | 1.7395
| 1596 | 0.55556 | 2.8814 | 1.2812 | 2.105
| 1597 | 0.43519 | 2.7119 | 1.9375 | 1.9076
| 1598 | 0.49074 | 2.2881 | 1.1562 | 2.0252
| 1599 | 0.38889 | 2.8644 | 1.4062 | 1.9286
| 1600 | 0.30556 | 3 | 1.0625 | 1.8529
| 1601 | 0.5 | 2.3559 | 1.1875 | 1.9958
| 1602 | 0.47222 | 2.4068 | 2 | 1.7563
| 1603 | 0.37963 | 2.4915 | 1.4688 | 1.8866
| 1604 | 0.34259 | 2.2373 | 1.625 | 2.0336
| 1605 | 0.40741 | 2.8983 | 1.625 | 2.1176
| 1606 | 0.5463 | 2.0169 | 1.625 | 1.7647
| 1607 | 0.41667 | 1.9831 | 0.84375 | 1.8277
| 1608 | 0.43519 | 2.678 | 1.9062 | 2.1765
| 1609 | 0.5 | 2.661 | 0.8125 | 1.9496
| 1610 | 0.53704 | 3.1525 | 1.5 | 2.0756
| 1611 | 0.33333 | 2.9831 | 1.1875 | 1.8739
| 1612 | 0.31481 | 2.4746 | 1.6562 | 1.8782
| 1613 | 0.46296 | 2.4407 | 0.78125 | 2.0588
| 1614 | 0.35185 | 3.2542 | 1.625 | 2.4454
| 1615 | 0.40741 | 2.9153 | 1.1562 | 1.958
| 1616 | 0.58333 | 3.661 | 1.6562 | 2.0462
| 1617 | 0.30556 | 1.5932 | 1.75 | 2.0504
| 1618 | 0.41667 | 2.6949 | 1.625 | 2.542
| 1619 | 0.30556 | 2.5254 | 2.0312 | 2.1765
| 1620 | 0.43519 | 2.4915 | 1.5312 | 1.9832
| 1621 | 0.27778 | 3.3898 | 1.1562 | 2.458
| 1622 | 0.34259 | 2.3559 | 2.5312 | 2.1303
| 1623 | 0.25 | 2.8475 | 1.5 | 2.0546
| 1624 | 0.41667 | 2.2034 | 1.75 | 2.105
| 1625 | 0.39815 | 2.322 | 2.0938 | 1.8908
| 1626 | 0.39815 | 2.2542 | 1.5312 | 2.1303
| 1627 | 0.26852 | 2.8983 | 1.75 | 2.084
| 1628 | 0.37963 | 3.3898 | 0.9375 | 2.2353
| 1629 | 0.33333 | 3.1864 | 1.9062 | 2.2143
| 1630 | 0.38889 | 2.6441 | 1.9688 | 2.3445
| 1631 | 0.26852 | 2.339 | 1.75 | 1.937
| 1632 | 0.51852 | 2.1017 | 1.2812 | 2.1218
| 1633 | 0.37963 | 3.1525 | 1.8438 | 1.8445
| 1634 | 0.50926 | 2 | 1.1562 | 1.9286
| 1635 | 0.39815 | 2.7966 | 1.125 | 2.0378
| 1636 | 0.30556 | 2.6441 | 1.2812 | 2.1261
| 1637 | 0.30556 | 2.1525 | 1.0312 | 2.1345
| 1638 | 0.48148 | 3.0847 | 0.9375 | 1.9118
| 1639 | 0.31481 | 3.5085 | 0.71875 | 2.2563
| 1640 | 0.40741 | 2.3051 | 1.0625 | 2.2563
| 1641 | 0.49074 | 2.9492 | 1.1875 | 2.1975
| 1642 | 0.38889 | 1.7119 | 1.8125 | 2.0168
| 1643 | 0.34259 | 2.7627 | 2 | 2.0714
| 1644 | 0.50926 | 2.4237 | 1.625 | 2.1134
| 1645 | 0.35185 | 3.6441 | 1.0625 | 1.7773
| 1646 | 0.41667 | 3.1695 | 1.2812 | 1.8487
| 1647 | 0.4537 | 2.1356 | 1.25 | 2.1387
| 1648 | 0.34259 | 2.9831 | 0.9375 | 2.0588
| 1649 | 0.28704 | 2.1695 | 1.1875 | 2.1134
| 1650 | 0.37963 | 2.3051 | 0.71875 | 1.8445
| 1651 | 0.34259 | 3.2712 | 1.9062 | 2.3361
| 1652 | 0.48148 | 3.1017 | 1.625 | 1.9496
| 1653 | 0.4537 | 1.5932 | 1.5625 | 2.1933
| 1654 | 0.47222 | 3.1017 | 1.0625 | 2.0504
| 1655 | 0.37037 | 2.7966 | 1.0938 | 2.1555
| 1656 | 0.43519 | 2.4068 | 2.0625 | 2.4034
| 1657 | 0.38889 | 2.7797 | 0.9375 | 1.8992
| 1658 | 0.53704 | 2.5254 | 0.875 | 2.2479
| 1659 | 0.40741 | 2.678 | 1.1562 | 2.105
| 1660 | 0.32407 | 3.0847 | 1.6562 | 2.1303
| 1661 | 0.43519 | 2.6102 | 0.84375 | 2.2731
| 1662 | 0.42593 | 1.678 | 1.375 | 2.2185
| 1663 | 0.42593 | 2.8983 | 1.2188 | 2.0294
| 1664 | 0.47222 | 3.0847 | 1.0312 | 2.4874
| 1665 | 0.32407 | 2.3729 | 1.5 | 1.9664
| 1666 | 0.42593 | 1.5763 | 1.8438 | 1.9958
| 1667 | 0.40741 | 2.7627 | 1.5312 | 1.9748
| 1668 | 0.36111 | 2.1525 | 1.875 | 1.8866
| 1669 | 0.46296 | 2.7119 | 1.6562 | 2.1723
| 1670 | 0.36111 | 2.1017 | 1.2188 | 2.3151
| 1671 | 0.42593 | 2.8136 | 1.6562 | 1.7689
| 1672 | 0.50926 | 2.8305 | 1.25 | 2.1008
| 1673 | 0.34259 | 2.0678 | 1.0938 | 2.4286
| 1674 | 0.27778 | 2.2712 | 1.5938 | 2.0588
| 1675 | 0.37037 | 2.8305 | 2.1562 | 1.9454
| 1676 | 0.62963 | 2.8644 | 1.4062 | 2.1849
| 1677 | 0.26852 | 2.4576 | 1.5938 | 2.4706
| 1678 | 0.46296 | 2.5424 | 1.7188 | 1.937
| 1679 | 0.33333 | 2.678 | 0.96875 | 1.937
| 1680 | 0.40741 | 2.2373 | 1.125 | 1.9538
| 1681 | 0.47222 | 2.3729 | 1.25 | 2.1639
| 1682 | 0.5 | 2.1864 | 1.7188 | 2.1218
| 1683 | 0.58333 | 2.7458 | 1.3125 | 2.2479
| 1684 | 0.37963 | 2.5085 | 1.9688 | 2.0252
| 1685 | 0.5 | 2.4915 | 1.9688 | 2.4538
| 1686 | 0.53704 | 2.5763 | 1.4688 | 1.8109
| 1687 | 0.51852 | 3.2373 | 1.0625 | 2.2773
| 1688 | 0.19444 | 2.5254 | 1.3125 | 2.2185
| 1689 | 0.62963 | 3.0847 | 1.9375 | 2.3151
| 1690 | 0.39815 | 2.2712 | 1.6875 | 1.7983
| 1691 | 0.39815 | 2.2881 | 1.25 | 2.2311
| 1692 | 0.47222 | 2.3051 | 1.0625 | 2.1765
| 1693 | 0.55556 | 2.4746 | 1.125 | 2.2899
| 1694 | 0.42593 | 2.8305 | 0.84375 | 2.0462
| 1695 | 0.30556 | 3.0847 | 2.0312 | 2.0042
| 1696 | 0.31481 | 3.2373 | 1 | 2.1261
| 1697 | 0.39815 | 1.8475 | 1.0625 | 1.7311
| 1698 | 0.38889 | 2.4576 | 1.4062 | 2.0588
| 1699 | 0.44444 | 2.5763 | 0.9375 | 1.9412
| 1700 | 0.44444 | 3.3898 | 0.75 | 2.0084
| 1701 | 0.43519 | 4.0508 | 1.625 | 2.4286
| 1702 | 0.43519 | 2.0847 | 1.2188 | 2.5
| 1703 | 0.48148 | 1.7966 | 2.2812 | 1.8445
| 1704 | 0.40741 | 2.7119 | 1.3438 | 2.084
| 1705 | 0.46296 | 2.5254 | 1.2812 | 2.0756
| 1706 | 0.35185 | 3.4237 | 1.9688 | 2.1008
| 1707 | 0.33333 | 3.0847 | 0.78125 | 2.0966
| 1708 | 0.21296 | 3.2203 | 2.1875 | 2.063
| 1709 | 0.43519 | 2.7458 | 0.84375 | 1.7647
| 1710 | 0.43519 | 2.4068 | 1.25 | 1.958
| 1711 | 0.30556 | 2.678 | 1.4375 | 1.958
| 1712 | 0.44444 | 2.3051 | 0.96875 | 2.2269
| 1713 | 0.35185 | 2.0508 | 1.3125 | 1.9748
| 1714 | 0.47222 | 2.1695 | 1.4375 | 1.9664
| 1715 | 0.52778 | 2.9322 | 1.9375 | 2.1933
| 1716 | 0.44444 | 2.3559 | 1.1562 | 2.021
| 1717 | 0.37963 | 2.4237 | 1.3438 | 2.4244
| 1718 | 0.31481 | 2.0847 | 0.6875 | 2.0546
| 1719 | 0.4537 | 2.4407 | 0.5625 | 2.0294
| 1720 | 0.5 | 2.1017 | 1.2812 | 1.895
| 1721 | 0.37037 | 2.4237 | 1.4062 | 2.2647
| 1722 | 0.35185 | 2.2712 | 1.9062 | 1.9874
| 1723 | 0.34259 | 2.1356 | 1.1562 | 2.1849
| 1724 | 0.4537 | 2.5763 | 1.7812 | 2.1681
| 1725 | 0.35185 | 2.0508 | 1.3438 | 2.1765
| 1726 | 0.36111 | 2.7966 | 1.25 | 1.9748
| 1727 | 0.41667 | 2.2881 | 1.25 | 2.1387
| 1728 | 0.38889 | 2.9831 | 1.8125 | 2.3529
| 1729 | 0.47222 | 2.2542 | 1.9375 | 2.4034
| 1730 | 0.56481 | 3.4576 | 1.875 | 2.2017
| 1731 | 0.34259 | 2.7288 | 1.7812 | 2.0462
| 1732 | 0.39815 | 2.5085 | 0.96875 | 2.2311
| 1733 | 0.41667 | 1.9153 | 1.6875 | 2.021
| 1734 | 0.49074 | 2.1356 | 2.4375 | 2.1681
| 1735 | 0.62963 | 2.7797 | 1.5938 | 2.0504
| 1736 | 0.42593 | 2.1356 | 1.3125 | 2.3655
| 1737 | 0.50926 | 2.8644 | 2.375 | 2.1303
| 1738 | 0.50926 | 2.9153 | 1.25 | 1.8403
| 1739 | 0.47222 | 3.0678 | 1.2188 | 2.6429
| 1740 | 0.30556 | 2.7797 | 1.625 | 2.0126
| 1741 | 0.39815 | 2.0169 | 1.1875 | 2.0546
| 1742 | 0.41667 | 2.4407 | 1.2188 | 2.042
| 1743 | 0.2963 | 2.4407 | 1.5 | 2.1681
| 1744 | 0.34259 | 2.5932 | 1.6562 | 2.3151
| 1745 | 0.58333 | 2.6441 | 1.75 | 2.105
| 1746 | 0.39815 | 2.4915 | 1.625 | 2
| 1747 | 0.35185 | 2.3729 | 1.0312 | 2.1723
| 1748 | 0.40741 | 2.6102 | 1.375 | 2.3403
| 1749 | 0.50926 | 2.1864 | 1.3125 | 2.0336
| 1750 | 0.2963 | 2.6949 | 1.5625 | 1.8529
| 1751 | 0.34259 | 2.7627 | 1.75 | 1.7857
| 1752 | 0.39815 | 3.2542 | 1.0938 | 1.9244
| 1753 | 0.43519 | 3.1186 | 2.1562 | 1.8824
| 1754 | 0.57407 | 2.4915 | 0.875 | 2.2857
| 1755 | 0.41667 | 2.678 | 1.375 | 2.1639
| 1756 | 0.44444 | 2.8475 | 1.5 | 1.8277
| 1757 | 0.40741 | 2.1356 | 2.0312 | 2.2563
| 1758 | 0.53704 | 2.7288 | 1.0938 | 1.9706
| 1759 | 0.41667 | 2.8814 | 1.7812 | 2.0462
| 1760 | 0.42593 | 2.0678 | 0.875 | 2.084
| 1761 | 0.42593 | 3.0847 | 0.9375 | 2.1303
| 1762 | 0.4537 | 2.2034 | 0.78125 | 2.1008
| 1763 | 0.48148 | 2.7458 | 1.5312 | 2.1639
| 1764 | 0.35185 | 2.5593 | 2.2188 | 2.3697
| 1765 | 0.26852 | 2.1525 | 1.3125 | 2.1092
| 1766 | 0.52778 | 2.4915 | 1.5625 | 1.9412
| 1767 | 0.33333 | 2.3729 | 1.2812 | 2.3655
| 1768 | 0.53704 | 1.7119 | 1.4062 | 1.958
| 1769 | 0.49074 | 2.5085 | 1.5312 | 2.5462
| 1770 | 0.38889 | 3.5085 | 1.1562 | 1.7773
| 1771 | 0.34259 | 3.0847 | 1.375 | 1.9832
| 1772 | 0.52778 | 2.4915 | 1.8438 | 2.0294
| 1773 | 0.26852 | 2.5254 | 0.9375 | 1.9454
| 1774 | 0.27778 | 2.3729 | 0.875 | 2.1218
| 1775 | 0.43519 | 2.5593 | 1.3125 | 1.979
| 1776 | 0.32407 | 2.8136 | 1.125 | 2.1134
| 1777 | 0.27778 | 2.7458 | 1.5312 | 2.0546
| 1778 | 0.43519 | 2.2373 | 0.875 | 2.084
| 1779 | 0.48148 | 3 | 1 | 2.0462
| 1780 | 0.44444 | 2.5763 | 2.0938 | 1.9202
| 1781 | 0.40741 | 3.5763 | 1.8438 | 2.2563
| 1782 | 0.50926 | 3.4746 | 1.1875 | 2.1092
| 1783 | 0.4537 | 2.5763 | 1.3125 | 1.9664
| 1784 | 0.31481 | 3.322 | 2.0625 | 2.2059
| 1785 | 0.44444 | 3.3898 | 1.25 | 2.1471
| 1786 | 0.42593 | 2.9322 | 1.5 | 1.8824
| 1787 | 0.30556 | 3.1695 | 1.625 | 2.0756
| 1788 | 0.41667 | 2.5085 | 0.84375 | 2.1849
| 1789 | 0.37037 | 2.7797 | 1.5312 | 2.2479
| 1790 | 0.42593 | 2.3559 | 0.875 | 2.1975
| 1791 | 0.32407 | 2.6441 | 2.5 | 2.2227
| 1792 | 0.27778 | 2.1695 | 1.4688 | 2.2857
| 1793 | 0.33333 | 2.5593 | 1.3438 | 1.8782
| 1794 | 0.46296 | 2.8136 | 1.4688 | 1.8908
| 1795 | 0.19444 | 2.9492 | 1.6562 | 2.1555
| 1796 | 0.43519 | 2.3729 | 1.5 | 2.0336
| 1797 | 0.43519 | 2.7458 | 1.2188 | 2.6513
| 1798 | 0.37963 | 3.0169 | 1.5938 | 1.7437
| 1799 | 0.25926 | 3.0678 | 1.0312 | 1.8571
| 1800 | 0.31481 | 2.9492 | 1.7188 | 1.9748
| 1801 | 0.44444 | 2.4576 | 1.4062 | 2.0336
| 1802 | 0.36111 | 2.6949 | 1.5625 | 2.2941
| 1803 | 0.25926 | 3 | 2.6562 | 2.2731
| 1804 | 0.41667 | 1.8983 | 1.25 | 2.3067
| 1805 | 0.33333 | 2.4576 | 1.9688 | 1.9034
| 1806 | 0.47222 | 3.1525 | 1.4688 | 1.8571
| 1807 | 0.62963 | 2.3051 | 2.0938 | 2.1513
| 1808 | 0.37037 | 1.7288 | 1.25 | 2.0126
| 1809 | 0.61111 | 2.3729 | 1.4688 | 2.1176
| 1810 | 0.49074 | 2.322 | 1.5938 | 2.1176
| 1811 | 0.43519 | 2.9322 | 0.6875 | 1.8571
| 1812 | 0.5 | 3.3898 | 1.1562 | 2.0042
| 1813 | 0.40741 | 3.0847 | 0.78125 | 2.2479
| 1814 | 0.47222 | 2.4237 | 1.2812 | 2.1933
| 1815 | 0.5 | 3.1356 | 1.3125 | 1.937
| 1816 | 0.36111 | 2.5254 | 1.4062 | 2.2731
| 1817 | 0.41667 | 3.1356 | 1.5 | 1.9706
| 1818 | 0.43519 | 2.5085 | 1.4688 | 2.0882
| 1819 | 0.5 | 2.339 | 1.4688 | 1.958
| 1820 | 0.36111 | 2.1695 | 2 | 1.8908
| 1821 | 0.41667 | 2.4576 | 1.25 | 2.2689
| 1822 | 0.5463 | 2.7627 | 1.7188 | 2.3529
| 1823 | 0.39815 | 2.0678 | 1.0938 | 2.2017
| 1824 | 0.49074 | 2.4237 | 0.96875 | 2.2353
| 1825 | 0.37963 | 2.9661 | 1.5625 | 2.5588
| 1826 | 0.35185 | 2.8644 | 1.7812 | 2.1092
| 1827 | 0.31481 | 2.7119 | 1.6875 | 1.8992
| 1828 | 0.42593 | 2.5254 | 2 | 1.9118
| 1829 | 0.27778 | 2.0169 | 1.1562 | 2.1092
| 1830 | 0.40741 | 2.9831 | 2.3438 | 2.2941
| 1831 | 0.47222 | 2.2881 | 1.0312 | 2.1933
| 1832 | 0.62037 | 3.0169 | 1.3125 | 2.042
| 1833 | 0.44444 | 2.6949 | 1.6875 | 2.395
| 1834 | 0.60185 | 2.5254 | 1.5 | 1.916
| 1835 | 0.2963 | 2.4407 | 1.5625 | 1.9916
| 1836 | 0.38889 | 2.1017 | 2.0625 | 1.9538
| 1837 | 0.52778 | 2.3898 | 2 | 2.2605
| 1838 | 0.38889 | 2.7288 | 1.125 | 2.5462
| 1839 | 0.37037 | 2.1864 | 2.6562 | 1.9706
| 1840 | 0.46296 | 2.5254 | 1.7188 | 2.0756
| 1841 | 0.5 | 2.9831 | 2.4375 | 2.0546
| 1842 | 0.37963 | 3.0678 | 0.9375 | 2.0924
| 1843 | 0.30556 | 2.661 | 1.3125 | 2.0504
| 1844 | 0.35185 | 2.2881 | 1.4688 | 2.1471
| 1845 | 0.34259 | 2.9492 | 1.5 | 2.2017
| 1846 | 0.33333 | 2.661 | 1.1562 | 1.958
| 1847 | 0.38889 | 3.1017 | 1.5625 | 2.042
| 1848 | 0.38889 | 2.4746 | 2.4375 | 2.0084
| 1849 | 0.37963 | 2.8644 | 0.65625 | 2.2521
| 1850 | 0.41667 | 2.9661 | 2.125 | 2.1849
| 1851 | 0.49074 | 4.1356 | 0.9375 | 2.084
| 1852 | 0.38889 | 3.2712 | 1.625 | 2.458
| 1853 | 0.58333 | 2.4746 | 2.1875 | 2.6933
| 1854 | 0.33333 | 2.9322 | 1.5625 | 1.8739
| 1855 | 0.37963 | 3.1186 | 1.5625 | 2.0504
| 1856 | 0.50926 | 2.4407 | 1.9062 | 2.0714
| 1857 | 0.44444 | 2.8814 | 1.2188 | 2.1471
| 1858 | 0.35185 | 3.0847 | 1.1875 | 2.3067
| 1859 | 0.21296 | 2.8983 | 1.4375 | 1.9958
| 1860 | 0.36111 | 3.0169 | 1.3438 | 1.9664
| 1861 | 0.40741 | 2.9831 | 1.5938 | 2.2941
| 1862 | 0.63889 | 2.8136 | 1.7188 | 2.0252
| 1863 | 0.40741 | 3.4068 | 1.625 | 2.1639
| 1864 | 0.28704 | 2.6949 | 0.9375 | 1.8824
| 1865 | 0.37963 | 2.1864 | 0.75 | 2.1261
| 1866 | 0.44444 | 2.8136 | 0.9375 | 1.979
| 1867 | 0.22222 | 2.5932 | 1.25 | 1.9328
| 1868 | 0.32407 | 2.9153 | 1.2812 | 2.2059
| 1869 | 0.44444 | 2.678 | 1.3125 | 1.8487
| 1870 | 0.39815 | 3.0339 | 1.2812 | 2.0546
| 1871 | 0.38889 | 2.6102 | 0.71875 | 2.3109
| 1872 | 0.32407 | 2.7966 | 1.25 | 2.0756
| 1873 | 0.59259 | 2 | 1.3438 | 2.2143
| 1874 | 0.36111 | 2.3051 | 2.3125 | 2.0504
| 1875 | 0.47222 | 2.9661 | 1.4375 | 2.0336
| 1876 | 0.37037 | 2.2373 | 0.75 | 2.042
| 1877 | 0.41667 | 2.3729 | 1.6562 | 2.3109
| 1878 | 0.42593 | 2.4915 | 1.2188 | 1.8571
| 1879 | 0.47222 | 2.9322 | 0.9375 | 2.0336
| 1880 | 0.37963 | 3.2034 | 0.90625 | 2.0588
| 1881 | 0.53704 | 2.5763 | 1.1562 | 2.0882
| 1882 | 0.42593 | 2.6441 | 1.625 | 2.2101
| 1883 | 0.38889 | 2.2881 | 1.1562 | 2.0714
| 1884 | 0.40741 | 3.3051 | 1.1875 | 2.1597
| 1885 | 0.43519 | 1.9322 | 0.96875 | 2.0798
| 1886 | 0.39815 | 2.7797 | 0.65625 | 1.8151
| 1887 | 0.37963 | 2.5085 | 1.9062 | 1.9034
| 1888 | 0.41667 | 2.2881 | 1.3125 | 1.7185
| 1889 | 0.2963 | 3.1864 | 0.96875 | 2.3319
| 1890 | 0.27778 | 2.7119 | 1.4375 | 1.9202
| 1891 | 0.39815 | 2.7627 | 1.6562 | 2.1723
| 1892 | 0.33333 | 2.7288 | 2.25 | 2.0756
| 1893 | 0.37037 | 2.5085 | 1.1562 | 1.9622
| 1894 | 0.43519 | 2.5424 | 2 | 2.0168
| 1895 | 0.34259 | 2.7288 | 1.0938 | 2.0966
| 1896 | 0.33333 | 2.3729 | 1.2188 | 2.1218
| 1897 | 0.44444 | 2.5932 | 1.25 | 2.1891
| 1898 | 0.5463 | 2.8475 | 1.2188 | 2.3109
| 1899 | 0.35185 | 2.4915 | 1.8438 | 2.0546
| 1900 | 0.39815 | 2.5932 | 1.2188 | 2.2479
| 1901 | 0.38889 | 2.339 | 1.5 | 1.9706
| 1902 | 0.36111 | 2.1864 | 2.0625 | 1.9286
| 1903 | 0.46296 | 2 | 1 | 1.9538
| 1904 | 0.40741 | 2.6441 | 1.375 | 2.1597
| 1905 | 0.35185 | 2.4407 | 1.9688 | 2.084
| 1906 | 0.47222 | 3.0169 | 2.0938 | 1.8277
| 1907 | 0.51852 | 2.6949 | 1.9062 | 2.1303
| 1908 | 0.38889 | 3.0678 | 1.5 | 2.0756
| 1909 | 0.46296 | 2.3729 | 1.0625 | 1.9538
| 1910 | 0.50926 | 1.9322 | 1.4062 | 1.8697
| 1911 | 0.42593 | 3.0508 | 1.625 | 2.2857
| 1912 | 0.41667 | 2.6271 | 1.4062 | 2.1218
| 1913 | 0.41667 | 2.0169 | 1.875 | 2.0588
| 1914 | 0.38889 | 3.1864 | 1.0625 | 2.1345
| 1915 | 0.38889 | 2.1356 | 1.4688 | 2.0798
| 1916 | 0.32407 | 3.0508 | 1.1562 | 2.042
| 1917 | 0.44444 | 2.8305 | 1.6875 | 2.0378
| 1918 | 0.2963 | 2.4746 | 0.5625 | 2.2689
| 1919 | 0.53704 | 2.5932 | 1.8125 | 1.7815
| 1920 | 0.39815 | 2.4576 | 1.6562 | 2.5252
| 1921 | 0.4537 | 2.3898 | 2.4688 | 2.2647
| 1922 | 0.25 | 3.3898 | 1.4688 | 2.0126
| 1923 | 0.41667 | 2.5254 | 1.25 | 2.563
| 1924 | 0.51852 | 2.8475 | 1.1562 | 2.0672
| 1925 | 0.2963 | 2.4915 | 1.7188 | 1.7185
| 1926 | 0.47222 | 2.9492 | 1.3438 | 2.3992
| 1927 | 0.50926 | 3.0678 | 0.8125 | 1.9496
| 1928 | 0.39815 | 2.7627 | 2.1562 | 2.1849
| 1929 | 0.32407 | 2.339 | 0.84375 | 2.0504
| 1930 | 0.59259 | 3.6271 | 1.9062 | 2.2311
| 1931 | 0.39815 | 3.2034 | 1.875 | 1.9538
| 1932 | 0.38889 | 2.4915 | 1.1562 | 2.0378
| 1933 | 0.36111 | 2.5424 | 0.8125 | 2.0966
| 1934 | 0.47222 | 2.678 | 1.1875 | 2.3571
| 1935 | 0.33333 | 2.3898 | 1.25 | 1.916
| 1936 | 0.40741 | 3.2881 | 1.75 | 2.1261
| 1937 | 0.37037 | 2.4407 | 1.4688 | 2.1218
| 1938 | 0.35185 | 2.5932 | 1.2812 | 1.6933
| 1939 | 0.42593 | 3.1525 | 1.9375 | 2.0924
| 1940 | 0.46296 | 2.2712 | 1.8438 | 1.979
| 1941 | 0.46296 | 2.2034 | 0.8125 | 1.8235
| 1942 | 0.39815 | 2.6441 | 2.25 | 2.0588
| 1943 | 0.37963 | 2.661 | 1.5 | 2.1471
| 1944 | 0.35185 | 2.4068 | 1.0625 | 1.9328
| 1945 | 0.43519 | 2.5254 | 1.5 | 1.9496
| 1946 | 0.33333 | 2.1356 | 2.0312 | 2.0546
| 1947 | 0.26852 | 2.2203 | 1.25 | 2.1134
| 1948 | 0.48148 | 2.4746 | 0.9375 | 1.7773
| 1949 | 0.48148 | 2.339 | 1.125 | 2.3109
| 1950 | 0.57407 | 2.0339 | 1.875 | 2.0042
| 1951 | 0.30556 | 2.7288 | 1.0312 | 1.9832
| 1952 | 0.40741 | 3.322 | 1.7812 | 2.0714
| 1953 | 0.48148 | 3.0678 | 1.25 | 2.1387
| 1954 | 0.35185 | 2.6271 | 0.90625 | 1.8992
| 1955 | 0.62037 | 2.9831 | 0.90625 | 2.5
| 1956 | 0.4537 | 2.9322 | 2.25 | 1.8445
| 1957 | 0.39815 | 2.5254 | 1.625 | 2.1134
| 1958 | 0.5463 | 3.2203 | 1.9688 | 1.9706
| 1959 | 0.44444 | 2.6102 | 1.0312 | 2.0504
| 1960 | 0.50926 | 2.1864 | 0.96875 | 2.2857
| 1961 | 0.39815 | 2.9153 | 2.375 | 1.937
| 1962 | 0.25 | 2.9831 | 0.65625 | 2.1555
| 1963 | 0.37963 | 2.322 | 1.25 | 1.9244
| 1964 | 0.2963 | 2.7288 | 1.5 | 2.2059
| 1965 | 0.42593 | 2.5763 | 1.875 | 1.7563
| 1966 | 0.5463 | 2.1186 | 0.9375 | 2.1807
| 1967 | 0.35185 | 2.8475 | 1.25 | 2.4706
| 1968 | 0.36111 | 2.4576 | 1 | 1.9202
| 1969 | 0.4537 | 2.5593 | 1 | 2.1807
| 1970 | 0.34259 | 2.0169 | 1.4375 | 2.5378
| 1971 | 0.39815 | 2.9831 | 0.8125 | 2.3487
| 1972 | 0.48148 | 2.0508 | 1.4688 | 1.7731
| 1973 | 0.4537 | 2.8136 | 0.84375 | 2.6975
| 1974 | 0.55556 | 2.7119 | 0.78125 | 2.1092
| 1975 | 0.44444 | 3.4068 | 1.3438 | 2.2773
| 1976 | 0.44444 | 2.4237 | 1.125 | 2.1513
| 1977 | 0.4537 | 2.4576 | 2.0312 | 2.1765
| 1978 | 0.34259 | 3.1017 | 1.4375 | 2.2605
| 1979 | 0.43519 | 3.0508 | 1.5 | 2.0756
| 1980 | 0.53704 | 2.339 | 1.3438 | 2.1345
| 1981 | 0.49074 | 3.2034 | 1.375 | 2.2185
| 1982 | 0.43519 | 2.1695 | 1.0312 | 1.9748
| 1983 | 0.37037 | 2.7288 | 1.5938 | 2.2521
| 1984 | 0.42593 | 3.1017 | 1.8438 | 2.1176
| 1985 | 0.38889 | 2.3898 | 1.75 | 1.9286
| 1986 | 0.34259 | 2.7119 | 1.3438 | 1.7353
| 1987 | 0.37963 | 3.1525 | 1.3438 | 1.8782
| 1988 | 0.24074 | 2.4746 | 1.2188 | 2.1891
| 1989 | 0.39815 | 4.0847 | 1.2188 | 2
| 1990 | 0.38889 | 2.7966 | 0.8125 | 2.2437
| 1991 | 0.50926 | 3.2712 | 1.1875 | 2.1597
| 1992 | 0.5463 | 2.6441 | 1.5312 | 1.9244
| 1993 | 0.43519 | 2.7966 | 0.90625 | 1.9034
| 1994 | 0.46296 | 2.6441 | 1.625 | 2.0168
| 1995 | 0.49074 | 2.5085 | 1.9688 | 2.1387
| 1996 | 0.25 | 2.0169 | 1.8438 | 2.0504
| 1997 | 0.25926 | 2.9322 | 0.75 | 1.7101
| 1998 | 0.34259 | 2.8475 | 1.5938 | 2.1092
| 1999 | 0.46296 | 3.339 | 1.4062 | 1.9286
| 2000 | 0.57407 | 2.2542 | 1.9062 | 2.1513
| 2001 | 0.53704 | 2.8644 | 1.375 | 2.1429
| 2002 | 0.55556 | 2.4915 | 1.125 | 2.2143
| 2003 | 0.48148 | 2.9153 | 0.96875 | 2.0546
| 2004 | 0.32407 | 2.3051 | 1.3125 | 2.0462
| 2005 | 0.25 | 2.9322 | 1.9062 | 2.4706
| 2006 | 0.51852 | 1.7627 | 1.4062 | 2.4748
| 2007 | 0.44444 | 2.7797 | 1.5938 | 2.1345
| 2008 | 0.2963 | 2.1864 | 0.96875 | 2.4706
| 2009 | 0.49074 | 2.322 | 1.2188 | 2.3655
| 2010 | 0.44444 | 2.3051 | 1.4375 | 2.2563
| 2011 | 0.33333 | 2.9153 | 1.4375 | 2.0126
| 2012 | 0.36111 | 3.1864 | 1.9062 | 2.3782
| 2013 | 0.40741 | 2.2712 | 1.6562 | 2.2227
| 2014 | 0.37963 | 3.1186 | 1.75 | 1.7395
| 2015 | 0.41667 | 2.322 | 1.8125 | 1.9454
| 2016 | 0.32407 | 3 | 1.375 | 2.3739
| 2017 | 0.4537 | 2.4237 | 0.90625 | 2.3487
| 2018 | 0.41667 | 2.9153 | 2 | 1.895
| 2019 | 0.44444 | 2.7797 | 1.375 | 1.8739
| 2020 | 0.5 | 2.7627 | 1.3438 | 2.3361
| 2021 | 0.60185 | 2.8644 | 0.78125 | 1.916
| 2022 | 0.43519 | 2 | 0.96875 | 2.1303
| 2023 | 0.27778 | 2.8305 | 1.2812 | 2.1891
| 2024 | 0.30556 | 2.8475 | 1.1875 | 2.3613
| 2025 | 0.30556 | 2.5085 | 0.9375 | 1.9748
| 2026 | 0.30556 | 3.1186 | 1.5938 | 1.8529
| 2027 | 0.37037 | 3.0169 | 1.5312 | 1.9454
| 2028 | 0.4537 | 2.5085 | 1 | 2.2437
| 2029 | 0.47222 | 2.4237 | 1.3438 | 2.3151
| 2030 | 0.35185 | 2 | 0.625 | 1.8655
| 2031 | 0.38889 | 2.7797 | 1.4062 | 2.0882
| 2032 | 0.52778 | 2.1695 | 0.90625 | 2.3445
| 2033 | 0.37963 | 2.4746 | 1.8438 | 2.2563
| 2034 | 0.2963 | 2.7966 | 1.25 | 1.9622
| 2035 | 0.50926 | 3.1017 | 1.4375 | 2.3655
| 2036 | 0.4537 | 3.2712 | 1.75 | 2.0462
| 2037 | 0.37037 | 2.5932 | 1.6562 | 1.7563
| 2038 | 0.32407 | 3.2034 | 1.0938 | 2.1134
| 2039 | 0.38889 | 3.2034 | 1.9375 | 1.9454
| 2040 | 0.31481 | 2.5424 | 1.625 | 1.8992
| 2041 | 0.36111 | 3.1864 | 0.84375 | 1.979
| 2042 | 0.37037 | 2.4576 | 0.9375 | 2.042
| 2043 | 0.5463 | 2.2881 | 1.8125 | 2.5126
| 2044 | 0.40741 | 2.6102 | 1.625 | 1.7941
| 2045 | 0.37963 | 2.6271 | 1.2812 | 1.895
| 2046 | 0.36111 | 2.6441 | 1.5625 | 1.8992
| 2047 | 0.31481 | 2.9831 | 0.71875 | 2.1891
| 2048 | 0.34259 | 2.7458 | 1.0312 | 2.0672
| 2049 | 0.43519 | 2.6949 | 1.0938 | 2.0672
| 2050 | 0.46296 | 2.5254 | 1.3125 | 2.0714
| 2051 | 0.50926 | 2.9322 | 1.4375 | 2.2899
| 2052 | 0.24074 | 2.5932 | 1.1875 | 2.2563
| 2053 | 0.30556 | 2.4915 | 2.75 | 2
| 2054 | 0.5 | 2.9492 | 0.78125 | 1.9874
| 2055 | 0.48148 | 2.3898 | 1.8125 | 2.1471
| 2056 | 0.4537 | 2.9492 | 2.9375 | 2.1765
| 2057 | 0.50926 | 3.322 | 1.125 | 1.9286
| 2058 | 0.57407 | 2.678 | 1.1562 | 2.1933
| 2059 | 0.38889 | 2.5254 | 1.375 | 2.0756
| 2060 | 0.39815 | 2.8814 | 1.6562 | 1.9958
| 2061 | 0.39815 | 2.7458 | 1.3125 | 1.8697
| 2062 | 0.38889 | 2.5593 | 1.0625 | 2.0252
| 2063 | 0.43519 | 3.5763 | 2.5938 | 1.9622
| 2064 | 0.35185 | 2.7288 | 1.125 | 1.7773
| 2065 | 0.46296 | 2.2542 | 1.9688 | 1.8908
| 2066 | 0.48148 | 2.3051 | 1.25 | 2.1513
| 2067 | 0.49074 | 2.3559 | 2.0312 | 2.1303
| 2068 | 0.33333 | 2.5424 | 0.9375 | 2.2605
| 2069 | 0.41667 | 2.5932 | 1.625 | 2.3361
| 2070 | 0.40741 | 2.9831 | 1.1562 | 1.9664
| 2071 | 0.46296 | 3.1525 | 2.5 | 2.0924
| 2072 | 0.35185 | 2.6441 | 1.1875 | 2.2857
| 2073 | 0.34259 | 2.2881 | 1.2188 | 2.1765
| 2074 | 0.39815 | 3.0339 | 1.3438 | 2.2185
| 2075 | 0.26852 | 2.4068 | 1.4375 | 2.0168
| 2076 | 0.37963 | 2.8814 | 1.5625 | 2.1555
| 2077 | 0.42593 | 2.5932 | 0.96875 | 2.1176
| 2078 | 0.47222 | 2.5932 | 0.96875 | 2.2521
| 2079 | 0.50926 | 2.7458 | 1.8125 | 2.0336
| 2080 | 0.55556 | 3.1186 | 1.4688 | 2.1597
| 2081 | 0.35185 | 2.2034 | 1.625 | 2.2311
| 2082 | 0.37963 | 2.8983 | 2.0625 | 2.0294
| 2083 | 0.38889 | 2.9153 | 1.7812 | 2.2311
| 2084 | 0.65741 | 3.2373 | 0.875 | 2.1975
| 2085 | 0.40741 | 2.1864 | 1.9062 | 1.8992
| 2086 | 0.58333 | 1.7288 | 1.4375 | 2.0966
| 2087 | 0.43519 | 2.5085 | 1.25 | 1.958
| 2088 | 0.46296 | 2.9153 | 2.4375 | 2.0756
| 2089 | 0.42593 | 2.2542 | 1.8125 | 2.1261
| 2090 | 0.46296 | 3 | 1.7812 | 1.9076
| 2091 | 0.5 | 2.0508 | 1.9375 | 2.2059
| 2092 | 0.51852 | 2.1017 | 1.0625 | 2.2521
| 2093 | 0.33333 | 2.4915 | 0.75 | 2.0504
| 2094 | 0.41667 | 1.7797 | 1.5 | 2.1639
| 2095 | 0.25 | 3 | 1.6562 | 2.0252
| 2096 | 0.37037 | 3.339 | 1.5938 | 2.3739
| 2097 | 0.36111 | 3.6949 | 1.7812 | 1.8908
| 2098 | 0.30556 | 2.9492 | 1.7188 | 1.8403
| 2099 | 0.42593 | 2.8644 | 1.9062 | 1.7899
| 2100 | 0.26852 | 2.6949 | 1.0625 | 2.1429
| 2101 | 0.27778 | 2.4407 | 2.2188 | 1.9748
| 2102 | 0.43519 | 2.7288 | 1.25 | 2.0882
| 2103 | 0.48148 | 3.0508 | 1.375 | 2.2941
| 2104 | 0.40741 | 2.678 | 2.1562 | 2.3193
| 2105 | 0.40741 | 2.1864 | 0.71875 | 2.2059
| 2106 | 0.4537 | 3.0847 | 1.1875 | 1.8193
| 2107 | 0.35185 | 2.9492 | 1.5625 | 2.1933
| 2108 | 0.28704 | 1.9153 | 1.1562 | 2.042
| 2109 | 0.36111 | 2.9831 | 0.78125 | 1.7227
| 2110 | 0.37963 | 2.5593 | 1.3125 | 1.9916
| 2111 | 0.52778 | 2.7119 | 1.2188 | 2.1765
| 2112 | 0.39815 | 3.4407 | 1.5625 | 2.0252
| 2113 | 0.39815 | 3.2203 | 1.1562 | 2.0588
| 2114 | 0.5 | 3.0508 | 0.9375 | 1.9244
| 2115 | 0.27778 | 2.3729 | 1.5 | 1.7857
| 2116 | 0.32407 | 3.5085 | 1.1875 | 2.3151
| 2117 | 0.37963 | 3.4915 | 0.8125 | 1.8487
| 2118 | 0.37037 | 4.0339 | 1.8125 | 1.8025
| 2119 | 0.41667 | 3.0847 | 1.6875 | 2.2983
| 2120 | 0.36111 | 2.7966 | 1.1562 | 1.958
| 2121 | 0.5 | 2.9831 | 0.8125 | 1.8235
| 2122 | 0.33333 | 2.7797 | 2.3438 | 2.1345
| 2123 | 0.2963 | 2.8305 | 2.0312 | 2.0252
| 2124 | 0.56481 | 3.4915 | 1.4688 | 2.3529
| 2125 | 0.43519 | 1.7797 | 1.1562 | 1.937
| 2126 | 0.39815 | 2.6271 | 1.75 | 2.0378
| 2127 | 0.4537 | 3 | 1.25 | 2.0588
| 2128 | 0.39815 | 2.5593 | 0.46875 | 1.8235
| 2129 | 0.37963 | 2.322 | 1.875 | 2.1513
| 2130 | 0.37037 | 2.661 | 1.4375 | 1.9034
| 2131 | 0.5 | 2.339 | 1.9062 | 1.8445
| 2132 | 0.41667 | 2.5254 | 1.25 | 2.1933
| 2133 | 0.32407 | 2.8814 | 1.4375 | 2.105
| 2134 | 0.40741 | 3.2712 | 2.625 | 2.2185
| 2135 | 0.39815 | 3.0847 | 1.7812 | 2.084
| 2136 | 0.2037 | 2.7458 | 1.7188 | 2.395
| 2137 | 0.32407 | 2.3051 | 1.0625 | 1.9664
| 2138 | 0.46296 | 2.9831 | 1.625 | 2.4412
| 2139 | 0.42593 | 2.1864 | 1.6875 | 1.7689
| 2140 | 0.43519 | 2.4746 | 2.25 | 1.9706
| 2141 | 0.59259 | 2.8305 | 1.5625 | 2.4958
| 2142 | 0.4537 | 3.0169 | 1.2188 | 2.1891
| 2143 | 0.50926 | 3.5424 | 1.6875 | 2.4328
| 2144 | 0.40741 | 3.2712 | 1.0625 | 2.3866
| 2145 | 0.47222 | 2.9153 | 1.5625 | 2.0588
| 2146 | 0.40741 | 2.4407 | 1.3125 | 1.7773
| 2147 | 0.38889 | 3.0678 | 2.1562 | 1.9874
| 2148 | 0.56481 | 2.1695 | 1.3125 | 2.2353
| 2149 | 0.39815 | 3.1356 | 1.4375 | 2.2017
| 2150 | 0.24074 | 2.9661 | 1.3125 | 1.9874
| 2151 | 0.41667 | 2.6271 | 1.1875 | 2.0336
| 2152 | 0.35185 | 2.8983 | 1.4375 | 1.979
| 2153 | 0.5 | 2.1525 | 1.3125 | 2.0966
| 2154 | 0.35185 | 3.3729 | 1.1875 | 2.3697
| 2155 | 0.60185 | 2.3051 | 0.875 | 2.2605
| 2156 | 0.4537 | 3.0169 | 1.3125 | 2.2059
| 2157 | 0.40741 | 2.6102 | 0.90625 | 1.9538
| 2158 | 0.38889 | 2.2034 | 1.3125 | 2.2395
| 2159 | 0.41667 | 3.1017 | 1.5625 | 2.2983
| 2160 | 0.31481 | 2.5085 | 1.8438 | 2.1765
| 2161 | 0.40741 | 2.5932 | 1.4375 | 1.8529
| 2162 | 0.42593 | 2.7458 | 0.75 | 2.5042
| 2163 | 0.4537 | 2.7288 | 1.2188 | 2.1723
| 2164 | 0.43519 | 2.5593 | 1.625 | 2.2437
| 2165 | 0.44444 | 2.5763 | 1.5 | 1.979
| 2166 | 0.43519 | 3.1525 | 1.4688 | 2.0336
| 2167 | 0.36111 | 2.9322 | 1.0938 | 1.7983
| 2168 | 0.39815 | 3.1356 | 0.875 | 2.1176
| 2169 | 0.62963 | 3 | 1.4688 | 2.2311
| 2170 | 0.31481 | 3.4237 | 1.9062 | 2.3908
| 2171 | 0.37037 | 2.4407 | 1.25 | 2.1807
| 2172 | 0.42593 | 2.9153 | 2.125 | 2.2857
| 2173 | 0.36111 | 3.0169 | 1.6562 | 1.7353
| 2174 | 0.44444 | 3.4915 | 1.7188 | 2.4412
| 2175 | 0.33333 | 2.4068 | 1 | 1.9664
| 2176 | 0.60185 | 3.0508 | 1 | 1.8866
| 2177 | 0.36111 | 2.4407 | 1.375 | 2.0042
| 2178 | 0.43519 | 3.0847 | 1.6875 | 2.2143
| 2179 | 0.38889 | 2.9153 | 2.5 | 2.1471
| 2180 | 0.44444 | 2.6271 | 1.9062 | 2.084
| 2181 | 0.33333 | 2.7797 | 1.6875 | 1.7815
| 2182 | 0.28704 | 2.4576 | 1.2188 | 2.2059
| 2183 | 0.37037 | 1.8644 | 1.25 | 1.9832
| 2184 | 0.34259 | 2.5254 | 1 | 2.0588
| 2185 | 0.44444 | 2.1695 | 1.1875 | 1.8866
| 2186 | 0.55556 | 2.4746 | 1.2188 | 1.9034
| 2187 | 0.42593 | 2.4407 | 0.90625 | 1.8193
| 2188 | 0.60185 | 3.4237 | 1.2812 | 2.3277
| 2189 | 0.39815 | 2.8136 | 1.8125 | 2.0588
| 2190 | 0.30556 | 2.322 | 2.3125 | 1.937
| 2191 | 0.47222 | 3.2881 | 1.0938 | 2.0378
| 2192 | 0.49074 | 2.8475 | 1 | 1.8613
| 2193 | 0.4537 | 3.0847 | 1.25 | 1.7311
| 2194 | 0.53704 | 2.0508 | 0.96875 | 2.2479
| 2195 | 0.32407 | 2.6441 | 1.3438 | 1.8739
| 2196 | 0.40741 | 3.1356 | 1.5 | 2.1555
| 2197 | 0.49074 | 2.7966 | 1.8125 | 1.8235
| 2198 | 0.50926 | 1.8475 | 1.5625 | 2.1261
| 2199 | 0.41667 | 2.2712 | 1.5625 | 1.9328
| 2200 | 0.5463 | 2.7627 | 1.5 | 2.6639
| 2201 | 0.4537 | 2.8814 | 1.8438 | 1.8782
| 2202 | 0.33333 | 2.9153 | 0.75 | 2.0714
| 2203 | 0.17593 | 2.0678 | 0.96875 | 1.9454
| 2204 | 0.28704 | 3.1525 | 1.25 | 2.1092
| 2205 | 0.51852 | 2.6271 | 1.9062 | 1.9412
| 2206 | 0.37037 | 2.3729 | 1.125 | 2.1134
| 2207 | 0.44444 | 2.1525 | 1.9375 | 2.105
| 2208 | 0.5463 | 2.7458 | 1.75 | 1.8445
| 2209 | 0.51852 | 3.0678 | 1.25 | 1.9748
| 2210 | 0.4537 | 3.2712 | 1.8125 | 2.3571
| 2211 | 0.28704 | 2.9661 | 1.8438 | 1.7437
| 2212 | 0.41667 | 2.678 | 2.5625 | 2.1933
| 2213 | 0.36111 | 2.0169 | 1.3438 | 2.4118
| 2214 | 0.37963 | 2.8136 | 1.9375 | 2.1429
| 2215 | 0.37963 | 2.9661 | 2.2188 | 2.2941
| 2216 | 0.49074 | 3.0508 | 1.5 | 1.8739
| 2217 | 0.4537 | 2.8136 | 1.0625 | 1.9286
| 2218 | 0.43519 | 3.1695 | 1.2812 | 2.1261
| 2219 | 0.43519 | 2.8814 | 1.6875 | 2.2773
| 2220 | 0.34259 | 2.0847 | 1.375 | 1.979
| 2221 | 0.36111 | 2.5763 | 1.0938 | 1.6345
| 2222 | 0.47222 | 3.2203 | 1.1875 | 2.1513
| 2223 | 0.5 | 2.7966 | 1.5 | 1.9244
| 2224 | 0.41667 | 1.9322 | 2.0938 | 2.1218
| 2225 | 0.47222 | 2.1864 | 1.5625 | 1.9496
| 2226 | 0.34259 | 3.1864 | 1.375 | 2.2521
| 2227 | 0.42593 | 2.7966 | 2.3438 | 2.2185
| 2228 | 0.5463 | 2.7119 | 1.0312 | 2.2941
| 2229 | 0.56481 | 1.8136 | 1.5 | 2.0546
| 2230 | 0.35185 | 2.6102 | 1.5938 | 2.0588
| 2231 | 0.42593 | 3.5085 | 1.0938 | 2.021
| 2232 | 0.52778 | 3.1525 | 1.375 | 2.5546
| 2233 | 0.59259 | 2.7288 | 1.6875 | 2.0966
| 2234 | 0.40741 | 2.6271 | 0.96875 | 1.8571
| 2235 | 0.39815 | 2.7627 | 2.5 | 2.2269
| 2236 | 0.71296 | 2.5763 | 1.8438 | 2.1975
| 2237 | 0.47222 | 2.322 | 2.0938 | 2.0378
| 2238 | 0.41667 | 2.1864 | 1.3125 | 2.0756
| 2239 | 0.52778 | 2.6949 | 1.2812 | 2.2983
| 2240 | 0.40741 | 2.8983 | 1.3125 | 2.0336
| 2241 | 0.49074 | 3.7458 | 1.125 | 2.1303
| 2242 | 0.39815 | 3.0339 | 1.1562 | 2.0084
| 2243 | 0.39815 | 2.4576 | 1.9375 | 2.0966
| 2244 | 0.42593 | 3.1017 | 1.4688 | 2.1513
| 2245 | 0.43519 | 2.6271 | 1.375 | 2.084
| 2246 | 0.58333 | 2.0678 | 1.25 | 2.0714
| 2247 | 0.46296 | 2.0169 | 0.90625 | 1.937
| 2248 | 0.35185 | 2.8136 | 0.71875 | 2.0756
| 2249 | 0.5463 | 2.4576 | 1.3125 | 1.937
| 2250 | 0.52778 | 2.1695 | 1.2188 | 2.4076
| 2251 | 0.27778 | 2.4576 | 1.4688 | 2.105
| 2252 | 0.27778 | 3.1017 | 0.9375 | 1.9958
| 2253 | 0.43519 | 2.5085 | 1.5938 | 1.958
| 2254 | 0.33333 | 3.5254 | 1.3125 | 2.0924
| 2255 | 0.39815 | 2.7627 | 1.6562 | 1.8782
| 2256 | 0.32407 | 2.678 | 1.9375 | 1.9286
| 2257 | 0.47222 | 2.9661 | 1.5 | 1.9412
| 2258 | 0.36111 | 3.1525 | 1.5625 | 1.8824
| 2259 | 0.37963 | 3.4746 | 1.4688 | 2.3908
| 2260 | 0.37037 | 3.0847 | 1.3438 | 2.0252
| 2261 | 0.44444 | 2.4915 | 1.4688 | 2.2479
| 2262 | 0.48148 | 2.9492 | 2.1875 | 2.2353
| 2263 | 0.37963 | 1.9492 | 1.0312 | 2.1555
| 2264 | 0.36111 | 3.3559 | 1.4375 | 1.7479
| 2265 | 0.50926 | 2.322 | 1.2812 | 2.0042
| 2266 | 0.36111 | 2.2881 | 1.875 | 1.958
| 2267 | 0.37037 | 2.8814 | 1.3438 | 2.1555
| 2268 | 0.42593 | 3.0508 | 2.3125 | 2.2689
| 2269 | 0.49074 | 2.5254 | 1.3125 | 2.4118
| 2270 | 0.25 | 2.7288 | 1.8125 | 2.1933
| 2271 | 0.34259 | 2.6271 | 2 | 2.0126
| 2272 | 0.36111 | 2.3559 | 1.2188 | 2.1218
| 2273 | 0.48148 | 2.6102 | 2.2812 | 2.0126
| 2274 | 0.49074 | 2.7966 | 1.4062 | 2.0672
| 2275 | 0.24074 | 3.1017 | 1.25 | 2.1134
| 2276 | 0.4537 | 2.6102 | 0.6875 | 2.4286
| 2277 | 0.37037 | 2.1525 | 1.0938 | 1.9538
| 2278 | 0.38889 | 2.0339 | 1.5625 | 2.2185
| 2279 | 0.48148 | 3.0169 | 1.7812 | 2.6471
| 2280 | 0.32407 | 3 | 1.5312 | 2.3025
| 2281 | 0.47222 | 3.8305 | 0.8125 | 2.0294
| 2282 | 0.53704 | 3.1356 | 1.625 | 2.0252
| 2283 | 0.40741 | 2.2881 | 1.625 | 2.1008
| 2284 | 0.39815 | 1.7288 | 0.5625 | 1.9874
| 2285 | 0.37963 | 3.1864 | 1.7812 | 2.0336
| 2286 | 0.5463 | 2.4407 | 1.6875 | 1.8403
| 2287 | 0.41667 | 2.5085 | 1.5312 | 2.2437
| 2288 | 0.38889 | 3.1356 | 1.1875 | 2.5042
| 2289 | 0.5 | 2.4068 | 0.90625 | 2.1176
| 2290 | 0.53704 | 2.1525 | 1.4062 | 2.0672
| 2291 | 0.4537 | 2.2881 | 1.0938 | 2.1008
| 2292 | 0.5 | 2.4746 | 1.2188 | 1.8739
| 2293 | 0.43519 | 3.1525 | 2.0625 | 1.8992
| 2294 | 0.50926 | 1.8983 | 0.71875 | 2.042
| 2295 | 0.56481 | 2.7458 | 1.3438 | 1.7395
| 2296 | 0.56481 | 2.3559 | 1.4375 | 1.7563
| 2297 | 0.41667 | 2.1525 | 1.6562 | 2.1303
| 2298 | 0.34259 | 3.0169 | 1.2188 | 2.1723
| 2299 | 0.33333 | 2.9322 | 1.3125 | 2.1639
| 2300 | 0.28704 | 2.7797 | 0.96875 | 1.9118
| 2301 | 0.31481 | 2.3898 | 1.4688 | 1.8487
| 2302 | 0.35185 | 2.339 | 0.9375 | 2.1555
| 2303 | 0.27778 | 2.9661 | 1.1875 | 1.8529
| 2304 | 0.49074 | 3.2373 | 1.2812 | 2.1387
| 2305 | 0.37037 | 2.7627 | 1.25 | 2.0168
| 2306 | 0.41667 | 3.2881 | 1.2188 | 2.2689
| 2307 | 0.30556 | 2.2373 | 1.5938 | 2.0672
| 2308 | 0.49074 | 2.5763 | 2.4688 | 1.9622
| 2309 | 0.34259 | 2.6949 | 1.0938 | 2.2899
| 2310 | 0.35185 | 2.8814 | 1.625 | 2.2101
| 2311 | 0.4537 | 2.9661 | 1.7188 | 2.3739
| 2312 | 0.33333 | 3.1017 | 1.5 | 2.063
| 2313 | 0.2963 | 3.1017 | 1.3438 | 2.3613
| 2314 | 0.51852 | 2.4746 | 1.4062 | 1.9328
| 2315 | 0.4537 | 3.5763 | 1.9375 | 2.2227
| 2316 | 0.36111 | 2.6441 | 1.4062 | 1.9412
| 2317 | 0.25926 | 3.4576 | 1.8438 | 2.1639
| 2318 | 0.43519 | 2.8983 | 1.3125 | 2.0546
| 2319 | 0.5 | 2.1525 | 1.4688 | 1.9244
| 2320 | 0.35185 | 2.7627 | 1.375 | 1.9454
| 2321 | 0.39815 | 2.2373 | 2.2812 | 2.063
| 2322 | 0.38889 | 2.3898 | 1.1562 | 2.3739
| 2323 | 0.42593 | 2.5593 | 1.3125 | 1.8992
| 2324 | 0.39815 | 2.6441 | 1.1562 | 2.1975
| 2325 | 0.51852 | 2.5593 | 1.6562 | 2.1176
| 2326 | 0.36111 | 2.8475 | 1.3438 | 2.3655
| 2327 | 0.38889 | 2.661 | 1.0938 | 1.9118
| 2328 | 0.41667 | 3.0339 | 1.7812 | 2.1471
| 2329 | 0.49074 | 2.3559 | 1.6562 | 2.3908
| 2330 | 0.38889 | 2.6102 | 1.9688 | 2.063
| 2331 | 0.47222 | 2.7966 | 1.5 | 2.1303
| 2332 | 0.35185 | 2.3051 | 1.4688 | 1.8739
| 2333 | 0.37037 | 2.0847 | 2.125 | 2.1092
| 2334 | 0.31481 | 2.661 | 1.2188 | 2.063
| 2335 | 0.36111 | 2.8814 | 1.8125 | 2.0798
| 2336 | 0.28704 | 2.4068 | 1.0625 | 2.6597
| 2337 | 0.46296 | 2.4576 | 1.2812 | 2.4034
| 2338 | 0.39815 | 2.8136 | 1.75 | 2.1765
| 2339 | 0.33333 | 2.3729 | 0.90625 | 1.9748
| 2340 | 0.37037 | 2.6102 | 1.2188 | 1.9286
| 2341 | 0.32407 | 3.1864 | 1 | 2.4496
| 2342 | 0.2963 | 2.1695 | 0.6875 | 2.1303
| 2343 | 0.39815 | 2.8136 | 0.75 | 2.0462
| 2344 | 0.53704 | 2.6102 | 0.8125 | 2.0126
| 2345 | 0.40741 | 2.2373 | 1.5 | 1.916
| 2346 | 0.55556 | 2.7119 | 1.6875 | 2.0882
| 2347 | 0.68519 | 2 | 1.4688 | 2.3992
| 2348 | 0.51852 | 2.7458 | 1.1875 | 2.0252
| 2349 | 0.41667 | 2.4915 | 1.4688 | 2.0294
| 2350 | 0.33333 | 2.8983 | 1.9062 | 2.1429
| 2351 | 0.42593 | 3.4915 | 1.125 | 2.1597
| 2352 | 0.47222 | 3.2542 | 2.2812 | 2.0168
| 2353 | 0.41667 | 2.4237 | 1.6875 | 2.1387
| 2354 | 0.42593 | 2.8475 | 1.25 | 2.1891
| 2355 | 0.27778 | 2.9322 | 1.0938 | 1.7899
| 2356 | 0.37963 | 3.1186 | 1.6875 | 2.3571
| 2357 | 0.35185 | 2.1017 | 2 | 2.3529
| 2358 | 0.49074 | 2.6102 | 1.4688 | 1.9622
| 2359 | 0.46296 | 2.5932 | 0.90625 | 2.105
| 2360 | 0.31481 | 2.4746 | 1.1562 | 1.9118
| 2361 | 0.2963 | 2.4746 | 0.9375 | 1.9664
| 2362 | 0.49074 | 2.322 | 1.2188 | 1.8908
| 2363 | 0.38889 | 3.0339 | 1 | 2.1807
| 2364 | 0.39815 | 1.9661 | 0.75 | 1.9244
| 2365 | 0.42593 | 2.8305 | 1.8125 | 1.9118
| 2366 | 0.37963 | 3.3898 | 1.7188 | 2.2311
| 2367 | 0.36111 | 2.5932 | 1.75 | 1.979
| 2368 | 0.49074 | 2.4068 | 0.84375 | 1.937
| 2369 | 0.48148 | 2.5254 | 1.8438 | 2.0504
| 2370 | 0.34259 | 2.7627 | 1.0625 | 1.7059
| 2371 | 0.34259 | 2.5424 | 1.8125 | 1.9076
| 2372 | 0.38889 | 2.6102 | 1.8125 | 1.9496
| 2373 | 0.5 | 2.4915 | 2.125 | 1.8908
| 2374 | 0.43519 | 2.8305 | 1.125 | 2.2479
| 2375 | 0.25 | 3.0508 | 2.7188 | 1.9916
| 2376 | 0.35185 | 2.678 | 1.5 | 2.1387
| 2377 | 0.43519 | 3.1695 | 0.6875 | 1.7227
| 2378 | 0.61111 | 3.4237 | 1.7812 | 2.1513
| 2379 | 0.47222 | 2.2034 | 1.5312 | 2.2437
| 2380 | 0.42593 | 2.7288 | 1.0938 | 1.9034
| 2381 | 0.35185 | 2.7797 | 1.3438 | 2.1345
| 2382 | 0.44444 | 2.3051 | 1.2188 | 2.0714
| 2383 | 0.48148 | 3.0169 | 1.5625 | 1.9118
| 2384 | 0.39815 | 2.9831 | 1.0312 | 2.8697
| 2385 | 0.31481 | 2.3729 | 1.4688 | 2.2143
| 2386 | 0.2963 | 2.5424 | 1.3125 | 2.1723
| 2387 | 0.33333 | 3.8814 | 1.1562 | 2.2311
| 2388 | 0.47222 | 3.0678 | 1.5938 | 2.0966
| 2389 | 0.38889 | 2.8644 | 0.96875 | 2.1513
| 2390 | 0.4537 | 2.6271 | 0.84375 | 2.1134
| 2391 | 0.34259 | 2.1017 | 1.5625 | 1.937
| 2392 | 0.51852 | 2.8305 | 0.84375 | 2.1008
| 2393 | 0.40741 | 2.6441 | 2.8125 | 2.3992
| 2394 | 0.41667 | 2 | 1 | 2.2899
| 2395 | 0.40741 | 2.5932 | 1.9688 | 2.0084
| 2396 | 0.39815 | 3.1017 | 1.375 | 2.0084
| 2397 | 0.38889 | 3.1186 | 1.2188 | 2.1008
| 2398 | 0.37037 | 2.0339 | 1.1562 | 1.8866
| 2399 | 0.40741 | 2.2881 | 1.6875 | 2.0546
| 2400 | 0.44444 | 2.1864 | 2.4375 | 1.7731
| 2401 | 0.53704 | 2.9322 | 0.65625 | 2.4664
| 2402 | 0.51852 | 2.9661 | 1.0312 | 2.3235
| 2403 | 0.5 | 2.7797 | 1.1562 | 2.1933
| 2404 | 0.42593 | 2.0678 | 1.2812 | 2.0168
| 2405 | 0.33333 | 2.8644 | 1 | 2.0084
| 2406 | 0.48148 | 2.3559 | 1.6875 | 2.021
| 2407 | 0.37037 | 2.5593 | 0.84375 | 2.0504
| 2408 | 0.28704 | 3.1186 | 1 | 2.2563
| 2409 | 0.37963 | 2.7966 | 1.2812 | 2.2941
| 2410 | 0.44444 | 2.9661 | 1.2812 | 1.9412
| 2411 | 0.39815 | 2.4068 | 0.875 | 1.958
| 2412 | 0.49074 | 2.7966 | 1.4375 | 2.2857
| 2413 | 0.74074 | 2.2203 | 1.1562 | 2.0546
| 2414 | 0.33333 | 2.5763 | 1.1562 | 1.8403
| 2415 | 0.44444 | 2.5763 | 1.4062 | 1.9328
| 2416 | 0.48148 | 2.7288 | 1.1562 | 1.9118
| 2417 | 0.34259 | 2.322 | 1.8125 | 2.1681
| 2418 | 0.44444 | 2.678 | 2.25 | 1.895
| 2419 | 0.46296 | 2.7288 | 1.0938 | 2.063
| 2420 | 0.50926 | 2.7288 | 1.75 | 2.1387
| 2421 | 0.47222 | 2.8814 | 1.2812 | 1.8824
| 2422 | 0.5 | 2.6271 | 2.0312 | 2.1134
| 2423 | 0.41667 | 2.8983 | 1.4375 | 1.9622
| 2424 | 0.4537 | 3.5593 | 1.4062 | 2.1555
| 2425 | 0.48148 | 2.5763 | 1.875 | 2.3697
| 2426 | 0.32407 | 2.2881 | 1.4062 | 2.1639
| 2427 | 0.51852 | 2.8983 | 1.125 | 1.8739
| 2428 | 0.44444 | 3.3729 | 1.8438 | 2.2059
| 2429 | 0.69444 | 2.8983 | 1.0938 | 2.1345
| 2430 | 0.37037 | 2.4576 | 1.7188 | 1.8782
| 2431 | 0.35185 | 3.6271 | 1.2188 | 2.0924
| 2432 | 0.34259 | 2.322 | 1.6875 | 2.1261
| 2433 | 0.40741 | 3.6949 | 1.0938 | 2.063
| 2434 | 0.59259 | 3.0678 | 1.9062 | 1.9034
| 2435 | 0.47222 | 2.3729 | 1.0312 | 2.1429
| 2436 | 0.38889 | 2.4576 | 1.1562 | 2.0924
| 2437 | 0.33333 | 2.4237 | 1.75 | 2.1008
| 2438 | 0.51852 | 2.6949 | 1.8438 | 2.2185
| 2439 | 0.5463 | 2.6271 | 1.3438 | 1.8403
| 2440 | 0.46296 | 2.7458 | 1.0938 | 2.0168
| 2441 | 0.38889 | 2.3559 | 1.5938 | 2.1891
| 2442 | 0.37963 | 2.1356 | 1.9375 | 2.0966
| 2443 | 0.41667 | 3.9322 | 1.4062 | 1.9874
| 2444 | 0.36111 | 2.7627 | 0.71875 | 1.9076
| 2445 | 0.42593 | 2.1186 | 0.9375 | 1.9412
| 2446 | 0.32407 | 2.9492 | 1.7812 | 2.2059
| 2447 | 0.53704 | 2.2034 | 1.9375 | 2.5378
| 2448 | 0.37963 | 2.1525 | 0.90625 | 2.1597
| 2449 | 0.38889 | 3.0339 | 1.5938 | 1.9328
| 2450 | 0.41667 | 2.7966 | 1.125 | 2.1849
| 2451 | 0.47222 | 2.2881 | 0.90625 | 2.0168
| 2452 | 0.49074 | 2.339 | 0.5625 | 1.8529
| 2453 | 0.38889 | 2.3729 | 1.125 | 2.1513
| 2454 | 0.40741 | 3.0847 | 1.0938 | 2.1639
| 2455 | 0.46296 | 2.0508 | 1.2812 | 2.3445
| 2456 | 0.38889 | 2.9153 | 0.9375 | 2.2101
| 2457 | 0.44444 | 3.0847 | 2.1875 | 2.1933
| 2458 | 0.37037 | 2.3898 | 1.375 | 2.3151
| 2459 | 0.5 | 2.9831 | 1.7188 | 2.1134
| 2460 | 0.25 | 2.3729 | 1 | 2.0168
| 2461 | 0.34259 | 2.339 | 0.90625 | 2.1639
| 2462 | 0.32407 | 2.8644 | 1.75 | 2.0588
| 2463 | 0.50926 | 2.339 | 0.9375 | 2.0588
| 2464 | 0.39815 | 2.4576 | 1.8438 | 2.3403
| 2465 | 0.52778 | 2.8136 | 1.8438 | 1.9328
| 2466 | 0.44444 | 3.2542 | 1.9375 | 2.0966
| 2467 | 0.46296 | 2.1695 | 1.0312 | 2.0966
| 2468 | 0.62963 | 2.5932 | 1.2812 | 2.3908
| 2469 | 0.28704 | 2.9153 | 1.75 | 2.1387
| 2470 | 0.46296 | 2.3051 | 0.96875 | 2.5882
| 2471 | 0.41667 | 2.8136 | 1.7188 | 1.9538
| 2472 | 0.51852 | 2.7119 | 1.7812 | 1.9706
| 2473 | 0.40741 | 1.8814 | 2.25 | 1.9916
| 2474 | 0.43519 | 2.7458 | 1.0938 | 2.2689
| 2475 | 0.22222 | 2.4068 | 1.8125 | 2.3487
| 2476 | 0.55556 | 2.7627 | 1.6875 | 1.9622
| 2477 | 0.31481 | 2.8814 | 1.4375 | 2.0126
| 2478 | 0.46296 | 2.8475 | 1.5938 | 1.979
| 2479 | 0.35185 | 2.7288 | 2.125 | 2.1975
| 2480 | 0.41667 | 2.6441 | 1 | 2.2689
| 2481 | 0.32407 | 3.0847 | 1.7188 | 2.0084
| 2482 | 0.4537 | 2.7458 | 1.3438 | 2.1555
| 2483 | 0.41667 | 2.8305 | 1.8438 | 1.9622
| 2484 | 0.49074 | 2.8475 | 1.3125 | 1.7269
| 2485 | 0.30556 | 2.4576 | 1.25 | 2.0378
| 2486 | 0.38889 | 2.2881 | 1.2812 | 2.395
| 2487 | 0.43519 | 2.7119 | 1.8125 | 2.3361
| 2488 | 0.36111 | 2.8475 | 1.0625 | 2.3319
| 2489 | 0.37037 | 2.8475 | 1.6562 | 1.895
| 2490 | 0.34259 | 2.6441 | 0.90625 | 2.3319
| 2491 | 0.36111 | 3.0678 | 1.2188 | 2.1303
| 2492 | 0.37963 | 2.4237 | 1.375 | 1.6513
| 2493 | 0.37037 | 2.5085 | 1.5312 | 2.021
| 2494 | 0.51852 | 3.4068 | 1.4062 | 1.8992
| 2495 | 0.66667 | 3.0169 | 1.1562 | 1.8151
| 2496 | 0.4537 | 2.4746 | 1.3438 | 2.0966
| 2497 | 0.39815 | 3.2712 | 1.8125 | 2.416
| 2498 | 0.41667 | 2 | 1.25 | 1.8487
| 2499 | 0.31481 | 2.1356 | 1.0312 | 2.1723
| 2500 | 0.37037 | 3.0339 | 0.84375 | 1.9622
| 2501 | 0.33333 | 3.1695 | 1.375 | 2.2689
| 2502 | 0.38889 | 2.4576 | 2.0312 | 2.1303
| 2503 | 0.41667 | 2.4746 | 1.4062 | 2.2269
| 2504 | 0.31481 | 2.5424 | 0.9375 | 1.8697
| 2505 | 0.5 | 2.339 | 0.71875 | 1.9412
| 2506 | 0.2963 | 2.7797 | 1.5938 | 1.937
| 2507 | 0.30556 | 3.2712 | 1.5938 | 2.0126
| 2508 | 0.39815 | 2.7797 | 2.125 | 2.1345
| 2509 | 0.47222 | 2.8983 | 1.3438 | 1.7899
| 2510 | 0.44444 | 2.5085 | 1.8125 | 2.1134
| 2511 | 0.49074 | 2.6102 | 0.8125 | 2.1471
| 2512 | 0.37963 | 2.5085 | 1.8438 | 2.0588
| 2513 | 0.52778 | 2.3051 | 1.75 | 1.7353
| 2514 | 0.32407 | 2.678 | 0.9375 | 2
| 2515 | 0.32407 | 2.8644 | 0.625 | 1.8824
| 2516 | 0.44444 | 2.2712 | 1.6562 | 1.9454
| 2517 | 0.23148 | 2.8136 | 1.6875 | 1.8866
| 2518 | 0.40741 | 3.4407 | 0.96875 | 2.3025
| 2519 | 0.37963 | 3.4746 | 1.25 | 1.9496
| 2520 | 0.37963 | 3.0847 | 0.875 | 2.0168
| 2521 | 0.37963 | 2.5763 | 1.6562 | 1.8109
| 2522 | 0.41667 | 2.3559 | 1.9688 | 2.2605
| 2523 | 0.47222 | 3.678 | 1.3438 | 1.9706
| 2524 | 0.46296 | 2.7458 | 1.6562 | 1.9832
| 2525 | 0.38889 | 2.8644 | 1.0625 | 2.0294
| 2526 | 0.37963 | 2.0847 | 1.7188 | 1.9622
| 2527 | 0.51852 | 2.5424 | 1.0625 | 2.2983
| 2528 | 0.31481 | 2.9661 | 0.90625 | 2.021
| 2529 | 0.32407 | 2.5763 | 1.5938 | 2.063
| 2530 | 0.26852 | 2.9661 | 1.8438 | 2.021
| 2531 | 0.35185 | 3 | 1.3125 | 2.5294
| 2532 | 0.41667 | 2.1695 | 0.9375 | 2.0714
| 2533 | 0.48148 | 3.4407 | 1.0312 | 1.9832
| 2534 | 0.2963 | 2.4068 | 1.8438 | 2.0798
| 2535 | 0.33333 | 2.4746 | 1.1875 | 1.9748
| 2536 | 0.64815 | 2.339 | 1.6875 | 2.2731
| 2537 | 0.16667 | 2.5763 | 1.8438 | 2.1975
| 2538 | 0.40741 | 2.4068 | 2.125 | 2.1807
| 2539 | 0.40741 | 2.6271 | 1.375 | 2.1723
| 2540 | 0.26852 | 2.5932 | 1.25 | 2.3655
| 2541 | 0.38889 | 3.4576 | 2.0938 | 2.3697
| 2542 | 0.33333 | 2.4407 | 1.2188 | 2.0672
| 2543 | 0.42593 | 2.6949 | 1.0938 | 2.1471
| 2544 | 0.32407 | 2.2881 | 0.84375 | 1.9748
| 2545 | 0.35185 | 2.7119 | 1.1562 | 2.105
| 2546 | 0.2963 | 2.2542 | 1.1875 | 2.1597
| 2547 | 0.52778 | 3.2712 | 1.4375 | 2.4748
| 2548 | 0.37963 | 2.1017 | 1.4375 | 2.3067
| 2549 | 0.37963 | 1.8983 | 0.9375 | 1.9748
| 2550 | 0.43519 | 2.4915 | 2.3125 | 1.9748
| 2551 | 0.27778 | 2.9492 | 1 | 2.1218
| 2552 | 0.39815 | 2.5593 | 1.1875 | 1.8908
| 2553 | 0.49074 | 3.0339 | 1.1875 | 2.1429
| 2554 | 0.48148 | 3.2712 | 1.1875 | 2.1303
| 2555 | 0.4537 | 2.4915 | 1.1562 | 2.0504
| 2556 | 0.47222 | 2.4576 | 1.75 | 2.2605
| 2557 | 0.49074 | 2.7458 | 1.9688 | 2.1933
| 2558 | 0.38889 | 2.678 | 1.875 | 1.8739
| 2559 | 0.31481 | 3.2203 | 1.4688 | 2.0042
| 2560 | 0.53704 | 2.9661 | 1.625 | 1.6471
| 2561 | 0.28704 | 3.1356 | 0.9375 | 2.1555
| 2562 | 0.43519 | 1.9153 | 2.0938 | 1.9118
| 2563 | 0.43519 | 2.8644 | 1.5938 | 1.8571
| 2564 | 0.37037 | 2.6271 | 1.5 | 2.4958
| 2565 | 0.30556 | 2.4068 | 0.90625 | 2.0924
| 2566 | 0.33333 | 2.4237 | 2.2188 | 1.895
| 2567 | 0.35185 | 2.9492 | 1.1562 | 2.105
| 2568 | 0.2963 | 2.7119 | 2.0625 | 1.8277
| 2569 | 0.5 | 3.5593 | 1.125 | 1.7773
| 2570 | 0.31481 | 2.8305 | 1.8438 | 1.7857
| 2571 | 0.37037 | 3 | 0.96875 | 1.9874
| 2572 | 0.40741 | 2.0847 | 1.7812 | 1.958
| 2573 | 0.37963 | 3.661 | 2.1562 | 1.8487
| 2574 | 0.47222 | 2.339 | 1.5312 | 1.9328
| 2575 | 0.39815 | 2.5424 | 1.125 | 2.5084
| 2576 | 0.38889 | 3.3729 | 2.0312 | 2
| 2577 | 0.38889 | 1.5254 | 1.5625 | 2.105
| 2578 | 0.44444 | 2.1695 | 1.1875 | 1.9202
| 2579 | 0.47222 | 3.1695 | 2.0625 | 2.1471
| 2580 | 0.44444 | 3.6271 | 1.5312 | 1.9706
| 2581 | 0.35185 | 2.2203 | 1.6875 | 2.0126
| 2582 | 0.38889 | 2.661 | 1.4062 | 2.0588
| 2583 | 0.56481 | 4.0847 | 0.65625 | 2.1429
| 2584 | 0.25926 | 2.1525 | 1.75 | 1.9244
| 2585 | 0.36111 | 2.3051 | 2.0312 | 2.3193
| 2586 | 0.38889 | 2.5763 | 1.5938 | 1.9034
| 2587 | 0.2963 | 2.1356 | 0.9375 | 2.0042
| 2588 | 0.4537 | 3.1695 | 1.2188 | 2.2437
| 2589 | 0.41667 | 2.2203 | 1.1562 | 2.0588
| 2590 | 0.38889 | 1.9322 | 1.3125 | 2.3193
| 2591 | 0.41667 | 2.3559 | 1.75 | 1.9706
| 2592 | 0.39815 | 2.9661 | 1.6562 | 2.0546
| 2593 | 0.25926 | 1.8644 | 2.1562 | 1.7983
| 2594 | 0.46296 | 2.3559 | 2.2188 | 2.0168
| 2595 | 0.38889 | 2.678 | 0.9375 | 2.4664
| 2596 | 0.36111 | 3.1864 | 0.84375 | 2.3403
| 2597 | 0.44444 | 2.8644 | 1.5312 | 2.2479
| 2598 | 0.5 | 2.7966 | 1.0625 | 2.0798
| 2599 | 0.39815 | 2.5254 | 1.0625 | 2.2227
| 2600 | 0.4537 | 2.5424 | 2.3125 | 2.1849
| 2601 | 0.51852 | 2.4576 | 1 | 1.9874
| 2602 | 0.42593 | 3.1695 | 1.6562 | 2.1218
| 2603 | 0.5 | 2.5085 | 1.2812 | 2.063
| 2604 | 0.41667 | 3.2373 | 0.53125 | 2.3445
| 2605 | 0.34259 | 3.4915 | 1.9375 | 1.8739
| 2606 | 0.49074 | 2.6441 | 0.84375 | 2.1429
| 2607 | 0.4537 | 2.2203 | 1.1875 | 1.6555
| 2608 | 0.43519 | 3.0508 | 1.5 | 2.2437
| 2609 | 0.56481 | 2.6441 | 2.0312 | 2.0462
| 2610 | 0.5 | 3.5085 | 1.1875 | 1.9622
| 2611 | 0.5463 | 3.2712 | 1.75 | 2.0504
| 2612 | 0.63889 | 2.3729 | 1.0625 | 2.1681
| 2613 | 0.4537 | 2.7966 | 1.0312 | 1.9664
| 2614 | 0.39815 | 2.8644 | 1.125 | 2.416
| 2615 | 0.37037 | 3.4237 | 0.9375 | 1.7437
| 2616 | 0.4537 | 2.4068 | 2.4688 | 2.2857
| 2617 | 0.39815 | 2.9492 | 1.2188 | 2.1681
| 2618 | 0.37963 | 2.1017 | 1.7188 | 2.3193
| 2619 | 0.34259 | 2.8814 | 0.84375 | 2.4496
| 2620 | 0.22222 | 2.9322 | 1.0625 | 2.063
| 2621 | 0.47222 | 3.322 | 0.875 | 2.021
| 2622 | 0.48148 | 2.8136 | 0.625 | 2.2605
| 2623 | 0.38889 | 2.5085 | 2.5 | 2.0756
| 2624 | 0.52778 | 2.7797 | 0.84375 | 2.0756
| 2625 | 0.39815 | 3.1186 | 1.75 | 1.9118
| 2626 | 0.34259 | 3.0169 | 1.4062 | 1.8487
| 2627 | 0.57407 | 2.1017 | 1.3438 | 2.0924
| 2628 | 0.33333 | 2.9492 | 1.2188 | 1.8109
| 2629 | 0.39815 | 2 | 0.75 | 2
| 2630 | 0.49074 | 3.7627 | 1.0625 | 2.395
| 2631 | 0.30556 | 2.0508 | 1.125 | 2.1471
| 2632 | 0.40741 | 2.0169 | 2.1562 | 1.7899
| 2633 | 0.47222 | 3.1864 | 1.2812 | 2.0546
| 2634 | 0.46296 | 2.2034 | 1.0625 | 1.8992
| 2635 | 0.26852 | 3.1525 | 1.4688 | 2.3697
| 2636 | 0.41667 | 2.5932 | 1.1875 | 1.7941
| 2637 | 0.41667 | 3.1017 | 2.3125 | 2.1471
| 2638 | 0.37037 | 2.5424 | 1.8125 | 2.2101
| 2639 | 0.61111 | 2.4746 | 2.2188 | 2.2731
| 2640 | 0.38889 | 2.4576 | 1.9688 | 2.1176
| 2641 | 0.37037 | 2.4915 | 1.625 | 1.8193
| 2642 | 0.43519 | 2.7797 | 1.3438 | 2.1008
| 2643 | 0.39815 | 2.6441 | 1.5 | 2.2731
| 2644 | 0.38889 | 3.3559 | 0.9375 | 1.7857
| 2645 | 0.39815 | 1.8814 | 2.4375 | 1.8866
| 2646 | 0.39815 | 2.339 | 0.75 | 2.0546
| 2647 | 0.49074 | 2.5593 | 0.75 | 2.1597
| 2648 | 0.59259 | 2.1356 | 1 | 2.3613
| 2649 | 0.48148 | 3.2881 | 0.875 | 1.8361
| 2650 | 0.58333 | 2.9153 | 1.8125 | 1.979
| 2651 | 0.42593 | 2.7627 | 1.7188 | 2.2017
| 2652 | 0.41667 | 3.322 | 1.25 | 2.1387
| 2653 | 0.35185 | 2.8814 | 0.9375 | 2.2143
| 2654 | 0.40741 | 3.5254 | 2.5312 | 1.7605
| 2655 | 0.44444 | 3.0847 | 1.6875 | 1.9034
| 2656 | 0.39815 | 2.8305 | 1.0938 | 2.2059
| 2657 | 0.41667 | 2.8814 | 1.7812 | 2.2563
| 2658 | 0.38889 | 3.1356 | 0.9375 | 2.3067
| 2659 | 0.41667 | 1.9322 | 0.96875 | 2.3571
| 2660 | 0.42593 | 2.1695 | 0.96875 | 2.0294
| 2661 | 0.36111 | 3.2881 | 1.4688 | 2.1134
| 2662 | 0.37037 | 2.7627 | 1.4062 | 1.8866
| 2663 | 0.60185 | 2.4915 | 1.625 | 2.2143
| 2664 | 0.26852 | 2.1356 | 2.0625 | 2.0882
| 2665 | 0.27778 | 2.6271 | 1.125 | 1.8992
| 2666 | 0.5 | 2.4407 | 1.2188 | 2.0084
| 2667 | 0.37037 | 2.339 | 1.5938 | 2.0336
| 2668 | 0.34259 | 2.5932 | 1.7812 | 1.7815
| 2669 | 0.33333 | 3.9492 | 0.8125 | 2.2899
| 2670 | 0.43519 | 3.1864 | 1.4688 | 2.0378
| 2671 | 0.39815 | 2.7458 | 0.84375 | 2.2395
| 2672 | 0.48148 | 3.1525 | 1.25 | 2.1639
| 2673 | 0.47222 | 2.6441 | 1.3438 | 1.9454
| 2674 | 0.2963 | 2.0508 | 1.5312 | 1.8109
| 2675 | 0.30556 | 2.7119 | 0.59375 | 2.0252
| 2676 | 0.37037 | 2.3898 | 0.84375 | 2.2185
| 2677 | 0.37963 | 2.5932 | 2.0625 | 2.2521
| 2678 | 0.40741 | 2.9322 | 1.6562 | 2.5462
| 2679 | 0.43519 | 2.2373 | 1.5 | 1.7521
| 2680 | 0.57407 | 2.8983 | 0.8125 | 1.9664
| 2681 | 0.37963 | 2.6949 | 1.5312 | 2.0924
| 2682 | 0.47222 | 2.339 | 2.125 | 1.9538
| 2683 | 0.38889 | 2.0678 | 0.78125 | 1.8992
| 2684 | 0.4537 | 2.0508 | 1.2188 | 1.8529
| 2685 | 0.5 | 2.7627 | 1.0312 | 1.9832
| 2686 | 0.37037 | 3.1356 | 1.5938 | 2.0924
| 2687 | 0.44444 | 3.2712 | 0.6875 | 1.979
| 2688 | 0.50926 | 2.4407 | 1.1562 | 1.9622
| 2689 | 0.32407 | 2.7797 | 1.5938 | 2.2017
| 2690 | 0.41667 | 3.1017 | 1.6562 | 2.3193
| 2691 | 0.41667 | 2.5085 | 1.0312 | 1.9958
| 2692 | 0.38889 | 2.4068 | 1.4375 | 1.8613
| 2693 | 0.34259 | 2.2712 | 1.1562 | 2.021
| 2694 | 0.35185 | 3.3051 | 1.5312 | 2.0252
| 2695 | 0.43519 | 2.7627 | 0.65625 | 2.1639
| 2696 | 0.41667 | 2.661 | 1.9688 | 1.8613
| 2697 | 0.39815 | 2.9153 | 2.2812 | 1.9244
| 2698 | 0.34259 | 2.9831 | 1.375 | 2.3361
| 2699 | 0.53704 | 2.9153 | 1.5312 | 1.979
| 2700 | 0.44444 | 2.7288 | 1.9062 | 2.1218
| 2701 | 0.46296 | 2.4407 | 1.2188 | 2.0462
| 2702 | 0.43519 | 2.5593 | 0.875 | 1.6807
| 2703 | 0.42593 | 2.0847 | 1.1875 | 1.9328
| 2704 | 0.48148 | 2.9153 | 1.6875 | 2.2899
| 2705 | 0.44444 | 2.5254 | 1.5 | 1.958
| 2706 | 0.38889 | 2.5254 | 1.2812 | 2.021
| 2707 | 0.44444 | 1.8644 | 1.3438 | 1.8193
| 2708 | 0.52778 | 2.5763 | 1.5312 | 2.1345
| 2709 | 0.30556 | 2.3898 | 1.4375 | 1.8992
| 2710 | 0.48148 | 2.1186 | 1.25 | 1.9412
| 2711 | 0.40741 | 2.1186 | 2.0312 | 2.1933
| 2712 | 0.33333 | 2.0339 | 1.4688 | 1.9328
| 2713 | 0.38889 | 3.1525 | 1.1562 | 2.3487
| 2714 | 0.49074 | 2.3898 | 1.6562 | 2.3529
| 2715 | 0.39815 | 2.678 | 1.5312 | 2.1975
| 2716 | 0.39815 | 2.3559 | 2.5938 | 2.2983
| 2717 | 0.43519 | 2.5593 | 2.2812 | 2.1134
| 2718 | 0.32407 | 2.1017 | 1.1875 | 2.021
| 2719 | 0.53704 | 2.2881 | 1.3438 | 2.1513
| 2720 | 0.41667 | 2.7288 | 2.0312 | 2.063
| 2721 | 0.39815 | 3.2881 | 2 | 1.9538
| 2722 | 0.58333 | 3.2203 | 1.5938 | 2.1723
| 2723 | 0.43519 | 2.339 | 1.0312 | 1.9034
| 2724 | 0.37963 | 2.8136 | 1.7812 | 1.8445
| 2725 | 0.40741 | 2.1695 | 2 | 2.2521
| 2726 | 0.37037 | 2.9831 | 0.78125 | 2.0336
| 2727 | 0.37037 | 3.2881 | 1.375 | 2.2311
| 2728 | 0.53704 | 2 | 1.75 | 1.8109
| 2729 | 0.34259 | 2.7966 | 1.5 | 1.9286
| 2730 | 0.43519 | 3.0169 | 1.1875 | 2.1218
| 2731 | 0.40741 | 2.5254 | 1.8438 | 2.1639
| 2732 | 0.53704 | 2.9831 | 1.875 | 1.9664
| 2733 | 0.40741 | 3.3051 | 1.9375 | 2.0588
| 2734 | 0.5463 | 2.3051 | 1.1875 | 2.3782
| 2735 | 0.46296 | 2.5424 | 1.625 | 2.1134
| 2736 | 0.52778 | 2.8814 | 1.4062 | 1.9244
| 2737 | 0.30556 | 4 | 1.5312 | 2.2647
| 2738 | 0.43519 | 2.4915 | 1.4375 | 1.9538
| 2739 | 0.35185 | 2.8814 | 0.46875 | 2.2857
| 2740 | 0.33333 | 2.6271 | 0.71875 | 2.0168
| 2741 | 0.43519 | 2.9492 | 2.0625 | 2.0588
| 2742 | 0.5 | 3 | 1.4688 | 1.9286
| 2743 | 0.31481 | 2.2373 | 1.375 | 2.0966
| 2744 | 0.48148 | 2.8475 | 1.4062 | 1.9664
| 2745 | 0.40741 | 2.678 | 0.8125 | 2.4454
| 2746 | 0.46296 | 2.5593 | 1.7188 | 2.2269
| 2747 | 0.41667 | 2.4576 | 1.125 | 2.2941
| 2748 | 0.34259 | 2.3898 | 1.9375 | 1.9244
| 2749 | 0.37037 | 2.1525 | 1.3125 | 1.8655
| 2750 | 0.37037 | 1.8136 | 1.5625 | 2.3193
| 2751 | 0.4537 | 1.9492 | 1.5625 | 1.9454
| 2752 | 0.37037 | 2.6271 | 1.7188 | 2.2059
| 2753 | 0.47222 | 2.2373 | 1.1875 | 1.9958
| 2754 | 0.40741 | 2.8475 | 1.9375 | 2.063
| 2755 | 0.46296 | 2.5932 | 1 | 2.1261
| 2756 | 0.30556 | 2.6949 | 1.2188 | 2.1134
| 2757 | 0.35185 | 2.4407 | 1.0938 | 2.1681
| 2758 | 0.47222 | 2.8814 | 2.5625 | 1.8782
| 2759 | 0.38889 | 2.8644 | 1.8125 | 2.2059
| 2760 | 0.36111 | 2.7966 | 2.0312 | 2.0336
| 2761 | 0.37963 | 1.9492 | 1.1875 | 1.8782
| 2762 | 0.42593 | 2.8644 | 1.625 | 2.0966
| 2763 | 0.41667 | 2.7797 | 0.90625 | 2.0588
| 2764 | 0.47222 | 2.0678 | 0.6875 | 2.2437
| 2765 | 0.48148 | 3.1017 | 1.3438 | 1.8992
| 2766 | 0.32407 | 2.6102 | 0.78125 | 2.0462
| 2767 | 0.41667 | 3.1017 | 1 | 1.7857
| 2768 | 0.56481 | 3.4746 | 1 | 1.9664
| 2769 | 0.5463 | 2.4915 | 1.4375 | 2.0756
| 2770 | 0.36111 | 3.1186 | 1.125 | 1.9454
| 2771 | 0.49074 | 2.5254 | 1.7188 | 2.2311
| 2772 | 0.56481 | 2.678 | 1.75 | 2.3697
| 2773 | 0.43519 | 2.5763 | 1.3438 | 2.3824
| 2774 | 0.42593 | 1.8305 | 1.6562 | 2.1765
| 2775 | 0.4537 | 3.1864 | 0.84375 | 2.437
| 2776 | 0.36111 | 2.1864 | 1.5 | 2.0336
| 2777 | 0.47222 | 2.7627 | 1.3438 | 2.0588
| 2778 | 0.21296 | 2.6271 | 2.25 | 2.0084
| 2779 | 0.42593 | 2.6271 | 0.5625 | 2.2563
| 2780 | 0.43519 | 2.9661 | 1 | 1.9412
| 2781 | 0.39815 | 2.2881 | 1.5312 | 2.2143
| 2782 | 0.36111 | 2.678 | 1 | 1.9496
| 2783 | 0.42593 | 2.4746 | 1.3125 | 2.3697
| 2784 | 0.51852 | 2.5085 | 0.9375 | 2.2437
| 2785 | 0.35185 | 3.8136 | 2.125 | 1.8403
| 2786 | 0.63889 | 2.9661 | 2 | 1.7185
| 2787 | 0.51852 | 2.2373 | 1.6875 | 2.3445
| 2788 | 0.41667 | 2.3559 | 1.3438 | 2.2689
| 2789 | 0.27778 | 2.2712 | 1.9375 | 2.2437
| 2790 | 0.4537 | 2.8814 | 1.2188 | 1.979
| 2791 | 0.26852 | 2.4068 | 1.4688 | 2.0798
| 2792 | 0.34259 | 2.4915 | 0.78125 | 1.8571
| 2793 | 0.38889 | 2.6271 | 1.4062 | 1.8487
| 2794 | 0.38889 | 2.9153 | 1.5312 | 2.0084
| 2795 | 0.46296 | 3.0847 | 1.75 | 1.9916
| 2796 | 0.37037 | 2.1356 | 1.4375 | 2.0924
| 2797 | 0.49074 | 2.7797 | 1.4688 | 2.4916
| 2798 | 0.48148 | 2.0508 | 0.59375 | 2.437
| 2799 | 0.37963 | 2.5254 | 1.125 | 2.0336
| 2800 | 0.41667 | 2.6949 | 1.4688 | 1.9622
| 2801 | 0.37037 | 2.2542 | 1.25 | 2.3739
| 2802 | 0.43519 | 2.2034 | 1.5938 | 2.4202
| 2803 | 0.37037 | 2.5254 | 1.1875 | 1.8529
| 2804 | 0.35185 | 2.7627 | 0.96875 | 1.8487
| 2805 | 0.43519 | 3.0847 | 1.0938 | 2.2185
| 2806 | 0.39815 | 3.2542 | 1.7188 | 2.1471
| 2807 | 0.42593 | 2.322 | 1.1562 | 2.0294
| 2808 | 0.47222 | 2.3051 | 2.2188 | 2.1555
| 2809 | 0.46296 | 2.5254 | 1.1875 | 2.6176
| 2810 | 0.37963 | 2.339 | 0.78125 | 2.1513
| 2811 | 0.55556 | 2.6949 | 1.6562 | 2.2773
| 2812 | 0.36111 | 2.7458 | 1.1875 | 2.0546
| 2813 | 0.52778 | 3.1017 | 1.3125 | 2.2395
| 2814 | 0.32407 | 3.1695 | 1.7188 | 2.2311
| 2815 | 0.53704 | 2.3559 | 2.0312 | 2.2479
| 2816 | 0.34259 | 3.2712 | 1.0625 | 2.2647
| 2817 | 0.39815 | 2.3898 | 1.125 | 2.1849
| 2818 | 0.41667 | 1.9322 | 1.5938 | 2.1555
| 2819 | 0.39815 | 2.8983 | 0.90625 | 2.0126
| 2820 | 0.44444 | 2.2712 | 1.375 | 1.8824
| 2821 | 0.35185 | 2.1356 | 2.3125 | 2.2773
| 2822 | 0.38889 | 3.0339 | 1.5625 | 2.0756
| 2823 | 0.39815 | 2.5085 | 0.8125 | 2.3655
| 2824 | 0.40741 | 2.2203 | 1.3125 | 2.416
| 2825 | 0.44444 | 2.5932 | 0.96875 | 2.0924
| 2826 | 0.34259 | 2.8305 | 1.5938 | 1.895
| 2827 | 0.38889 | 2.6271 | 1.0625 | 2.2311
| 2828 | 0.44444 | 3.2881 | 2.3438 | 1.937
| 2829 | 0.41667 | 2.7119 | 1.125 | 1.9748
| 2830 | 0.48148 | 2.2203 | 0.65625 | 1.8866
| 2831 | 0.37037 | 2.4237 | 1.375 | 1.8866
| 2832 | 0.46296 | 2.2542 | 0.96875 | 2.2437
| 2833 | 0.28704 | 2.322 | 1 | 2.084
| 2834 | 0.41667 | 3.1525 | 1.375 | 2.2395
| 2835 | 0.41667 | 3.2881 | 1.875 | 2.0756
| 2836 | 0.39815 | 2.9153 | 1.0938 | 2.1092
| 2837 | 0.43519 | 2.8136 | 1.5312 | 1.6218
| 2838 | 0.42593 | 1.661 | 2.25 | 2.3235
| 2839 | 0.4537 | 2.678 | 2.0625 | 2.084
| 2840 | 0.40741 | 2.7797 | 2.125 | 2.0462
| 2841 | 0.50926 | 2.661 | 1.9062 | 2.0504
| 2842 | 0.50926 | 2.6271 | 1.0312 | 2.3782
| 2843 | 0.47222 | 2.7627 | 1.4062 | 1.9454
| 2844 | 0.41667 | 1.8136 | 1.1875 | 2.2605
| 2845 | 0.40741 | 3.4407 | 1.9375 | 2.2605
| 2846 | 0.37963 | 2.339 | 1.1875 | 2.0588
| 2847 | 0.36111 | 3.5254 | 1.6562 | 2.3445
| 2848 | 0.52778 | 2.339 | 1.3125 | 2.105
| 2849 | 0.34259 | 2.5424 | 1.0938 | 1.7731
| 2850 | 0.5 | 1.7966 | 2.1562 | 2.1723
| 2851 | 0.34259 | 2.322 | 2.6562 | 2.395
| 2852 | 0.57407 | 2.5424 | 1.7812 | 1.9244
| 2853 | 0.50926 | 2.5424 | 1.2188 | 1.9874
| 2854 | 0.41667 | 1.8983 | 1.0938 | 2.0924
| 2855 | 0.39815 | 2.5593 | 0.96875 | 2.3109
| 2856 | 0.5463 | 2.7458 | 1.5625 | 1.7353
| 2857 | 0.37963 | 3.4746 | 1.4375 | 2.4328
| 2858 | 0.33333 | 2.2542 | 1.5312 | 2.1555
| 2859 | 0.4537 | 1.9661 | 1.2188 | 2.2353
| 2860 | 0.48148 | 3.1695 | 1.0938 | 2.0546
| 2861 | 0.41667 | 1.8136 | 1.2812 | 1.895
| 2862 | 0.4537 | 1.7627 | 1.5625 | 2.0168
| 2863 | 0.27778 | 3.3729 | 1.0938 | 1.7101
| 2864 | 0.47222 | 2.6441 | 1.4062 | 2.1387
| 2865 | 0.39815 | 2.7627 | 1.9062 | 2.0336
| 2866 | 0.41667 | 3.1525 | 1.3438 | 2.3151
| 2867 | 0.43519 | 2.6102 | 1.5938 | 2.0798
| 2868 | 0.47222 | 2.3898 | 1.125 | 2.1765
| 2869 | 0.4537 | 3.661 | 1.2812 | 2.0756
| 2870 | 0.5463 | 1.8475 | 0.71875 | 1.9664
| 2871 | 0.28704 | 2.1017 | 2.9375 | 2.3067
| 2872 | 0.43519 | 2.8136 | 1.375 | 2.2395
| 2873 | 0.36111 | 2.9661 | 1.4375 | 1.9748
| 2874 | 0.56481 | 3.0847 | 1.5938 | 2.2647
| 2875 | 0.48148 | 1.8644 | 1.0625 | 2.3992
| 2876 | 0.4537 | 2.8644 | 0.46875 | 1.9832
| 2877 | 0.42593 | 2.2542 | 1.4375 | 2.0966
| 2878 | 0.2963 | 3.3559 | 1.875 | 1.8235
| 2879 | 0.50926 | 2.9153 | 1.2188 | 2.1849
| 2880 | 0.37963 | 2.9492 | 1.5312 | 2.3151
| 2881 | 0.34259 | 2.8136 | 1.5938 | 2.3655
| 2882 | 0.53704 | 2.3898 | 1.875 | 2.0168
| 2883 | 0.49074 | 2.5593 | 1.2188 | 1.8151
| 2884 | 0.53704 | 2.2203 | 1.1562 | 1.8655
| 2885 | 0.46296 | 2.0847 | 1.5625 | 2.0168
| 2886 | 0.44444 | 3 | 1.625 | 2.1513
| 2887 | 0.50926 | 2.8475 | 1.1875 | 2.1218
| 2888 | 0.39815 | 1.8983 | 1.5938 | 1.9916
| 2889 | 0.38889 | 3.0169 | 1.9375 | 2.1597
| 2890 | 0.26852 | 2.7458 | 1.4062 | 2.042
| 2891 | 0.4537 | 2 | 1.6875 | 2.1261
| 2892 | 0.37963 | 2.7288 | 1.125 | 1.8992
| 2893 | 0.38889 | 2.2881 | 1.2188 | 2.3235
| 2894 | 0.43519 | 2.4576 | 0.90625 | 2.0546
| 2895 | 0.46296 | 2.9153 | 1.0625 | 2.0168
| 2896 | 0.2963 | 2.7797 | 1.125 | 2.3361
| 2897 | 0.47222 | 2.4237 | 1.3438 | 1.7395
| 2898 | 0.5463 | 2.3559 | 2.375 | 2.105
| 2899 | 0.5463 | 2.0169 | 1.6562 | 2.4916
| 2900 | 0.52778 | 2.5424 | 1.125 | 2.1975
| 2901 | 0.44444 | 3.5932 | 0.84375 | 2.0546
| 2902 | 0.50926 | 2.9492 | 0.90625 | 1.9076
| 2903 | 0.36111 | 3.1695 | 1.5 | 1.8109
| 2904 | 0.39815 | 2.9153 | 1.2188 | 2.0378
| 2905 | 0.38889 | 2.2373 | 1.9688 | 2.0546
| 2906 | 0.43519 | 2.7797 | 1 | 2.0294
| 2907 | 0.50926 | 2.3898 | 1 | 1.9958
| 2908 | 0.44444 | 3.2373 | 1.6875 | 2.1134
| 2909 | 0.5 | 2.3898 | 2.2188 | 1.8655
| 2910 | 0.36111 | 2.7627 | 1.6562 | 2.5504
| 2911 | 0.4537 | 2.1017 | 1.1875 | 2.2143
| 2912 | 0.25926 | 2.2881 | 1.2188 | 2.1891
| 2913 | 0.51852 | 3.339 | 1.25 | 2.2353
| 2914 | 0.32407 | 2.339 | 1.0625 | 2.1303
| 2915 | 0.38889 | 2.6441 | 1.5312 | 2
| 2916 | 0.5 | 2.2542 | 1.6562 | 2.3782
| 2917 | 0.5 | 2.1525 | 2.125 | 2.0798
| 2918 | 0.42593 | 2.661 | 1.9688 | 2.0294
| 2919 | 0.42593 | 3.3051 | 1.2188 | 2.3235
| 2920 | 0.37037 | 2.4915 | 1.125 | 2.7185
| 2921 | 0.37037 | 2.0508 | 1.4688 | 2.1555
| 2922 | 0.52778 | 4.2034 | 1.0312 | 2.5714
| 2923 | 0.50926 | 2.3051 | 1.375 | 2.0462
| 2924 | 0.32407 | 2.9492 | 1.3125 | 2.3067
| 2925 | 0.38889 | 1.4407 | 1.3125 | 2.0168
| 2926 | 0.43519 | 3.1864 | 0.59375 | 1.9412
| 2927 | 0.46296 | 2.4237 | 0.75 | 2.1681
| 2928 | 0.24074 | 2.4746 | 1.125 | 2.2311
| 2929 | 0.23148 | 2.4237 | 0.875 | 1.8866
| 2930 | 0.33333 | 1.9153 | 1.375 | 2.0168
| 2931 | 0.47222 | 2.3559 | 1.0625 | 2.1681
| 2932 | 0.35185 | 1.3051 | 1.125 | 2.2143
| 2933 | 0.52778 | 1.9831 | 1.4375 | 2.0462
| 2934 | 0.37963 | 3.5932 | 0.78125 | 2.0714
| 2935 | 0.42593 | 2.8983 | 2.3125 | 2.0924
| 2936 | 0.43519 | 2.0847 | 1.625 | 2.3739
| 2937 | 0.2963 | 2.7119 | 1.6562 | 1.895
| 2938 | 0.36111 | 2.4237 | 2.2812 | 2.0714
| 2939 | 0.40741 | 2.0169 | 1.2188 | 2.5378
| 2940 | 0.5 | 2.5932 | 1.25 | 2.1176
| 2941 | 0.59259 | 2.9661 | 1.4688 | 2.1597
| 2942 | 0.36111 | 2.1864 | 1 | 2.2143
| 2943 | 0.58333 | 2.3051 | 1.3438 | 2.4664
| 2944 | 0.39815 | 2.4068 | 1.3125 | 1.8109
| 2945 | 0.5 | 2.7288 | 1.75 | 2.2815
| 2946 | 0.43519 | 1.8305 | 1.3438 | 2.2773
| 2947 | 0.52778 | 2.6441 | 1.8438 | 1.9664
| 2948 | 0.38889 | 2.9661 | 0.96875 | 2.2983
| 2949 | 0.27778 | 2.4576 | 1.1562 | 1.7311
| 2950 | 0.52778 | 2.3559 | 1.9688 | 1.9622
| 2951 | 0.35185 | 2.322 | 1.625 | 1.937
| 2952 | 0.50926 | 2.0169 | 1.75 | 2.042
| 2953 | 0.47222 | 2.4915 | 1.3125 | 1.9874
| 2954 | 0.50926 | 2.2373 | 1.2812 | 2
| 2955 | 0.5463 | 2.3729 | 1.1875 | 2.3109
| 2956 | 0.46296 | 2.0508 | 1.2812 | 2.1429
| 2957 | 0.42593 | 2.7119 | 0.8125 | 2.0714
| 2958 | 0.38889 | 2.1186 | 1.8125 | 2.2941
| 2959 | 0.44444 | 3.678 | 2.0625 | 2.2059
| 2960 | 0.44444 | 2.3898 | 1.2188 | 2.1681
| 2961 | 0.38889 | 2.4237 | 1.1875 | 2.3571
| 2962 | 0.31481 | 2 | 1.3125 | 2.0126
| 2963 | 0.40741 | 2.3898 | 1.0938 | 2.1765
| 2964 | 0.49074 | 2.8644 | 1.8438 | 1.8403
| 2965 | 0.40741 | 2.4407 | 2 | 1.8067
| 2966 | 0.41667 | 3.5254 | 0.96875 | 2.1555
| 2967 | 0.46296 | 2.8475 | 1.3125 | 2.2605
| 2968 | 0.31481 | 2.5424 | 1.0312 | 2.3824
| 2969 | 0.46296 | 2.5593 | 2.1562 | 2.0588
| 2970 | 0.24074 | 2.6271 | 0.6875 | 1.8403
| 2971 | 0.5 | 3.2881 | 0.875 | 2.2689
| 2972 | 0.52778 | 2.5424 | 2.0625 | 1.8361
| 2973 | 0.50926 | 2.322 | 1.5312 | 1.916
| 2974 | 0.34259 | 2.5424 | 1.4375 | 1.9454
| 2975 | 0.43519 | 2.6271 | 1.3125 | 2.1176
| 2976 | 0.44444 | 2.9492 | 1.8438 | 1.8445
| 2977 | 0.47222 | 3.4576 | 1.125 | 1.9412
| 2978 | 0.34259 | 2.5593 | 0.65625 | 1.6891
| 2979 | 0.41667 | 2.6102 | 1.3125 | 2.1218
| 2980 | 0.25926 | 2.4576 | 1.4062 | 1.8235
| 2981 | 0.43519 | 2.9831 | 1.375 | 1.8109
| 2982 | 0.34259 | 2.7627 | 1.3125 | 2.0798
| 2983 | 0.49074 | 1.8305 | 0.84375 | 2.1261
| 2984 | 0.47222 | 3.0678 | 1.5 | 1.9958
| 2985 | 0.27778 | 2.4746 | 1.2188 | 2.4244
| 2986 | 0.5 | 2.5085 | 1.625 | 2.1891
| 2987 | 0.41667 | 2.8814 | 1.2812 | 2.2017
| 2988 | 0.31481 | 3.0847 | 1.2812 | 2.1092
| 2989 | 0.48148 | 2.0847 | 2.5 | 1.8193
| 2990 | 0.38889 | 2.5254 | 1.625 | 2.3361
| 2991 | 0.38889 | 3 | 1.3125 | 1.9412
| 2992 | 0.46296 | 2.7119 | 2.4375 | 2.021
| 2993 | 0.49074 | 3.1695 | 1.6875 | 2.0294
| 2994 | 0.50926 | 2.2034 | 1.4688 | 1.9748
| 2995 | 0.44444 | 2.1525 | 1.1562 | 1.8697
| 2996 | 0.50926 | 2.5085 | 1.6562 | 2.2899
| 2997 | 0.37037 | 1.6949 | 1.5625 | 1.9874
| 2998 | 0.34259 | 2.5593 | 1.8438 | 1.8277
| 2999 | 0.46296 | 3.2203 | 1.1562 | 2.0252
| 3000 | 0.49074 | 2.4068 | 1.9688 | 1.8866
| 3001 | 0.26852 | 2.2542 | 1.6562 | 2.2353
| 3002 | 0.43519 | 2.661 | 1.5938 | 1.9916
| 3003 | 0.43519 | 3 | 0.84375 | 2.2521
| 3004 | 0.49074 | 2.678 | 0.875 | 2.0126
| 3005 | 0.26852 | 2.1017 | 0.6875 | 1.958
| 3006 | 0.34259 | 3.4576 | 1.6875 | 2.1849
| 3007 | 0.40741 | 2.9153 | 1.3438 | 2.0294
| 3008 | 0.4537 | 2.8644 | 1.375 | 1.9538
| 3009 | 0.62963 | 3.0678 | 1.4062 | 2.0672
| 3010 | 0.53704 | 2.5763 | 1.375 | 2.5
| 3011 | 0.5463 | 2.6102 | 1.8125 | 2.1008
| 3012 | 0.42593 | 2.5763 | 1.375 | 2.0042
| 3013 | 0.62963 | 2.322 | 1.25 | 1.9958
| 3014 | 0.51852 | 2.0847 | 1.3125 | 2.1008
| 3015 | 0.37037 | 2.4237 | 1.6562 | 2.042
| 3016 | 0.28704 | 2.1864 | 2 | 1.9916
| 3017 | 0.47222 | 2.7966 | 1.0938 | 1.7563
| 3018 | 0.4537 | 2.322 | 1.7188 | 1.9748
| 3019 | 0.34259 | 2.5932 | 1.375 | 2.2479
| 3020 | 0.65741 | 2.6102 | 1.8438 | 2.0336
| 3021 | 0.38889 | 2.9831 | 1.9375 | 2.042
| 3022 | 0.28704 | 3.0847 | 1.2188 | 2.3571
| 3023 | 0.31481 | 2.7797 | 2.1562 | 2.1891
| 3024 | 0.49074 | 2.5424 | 1.3125 | 1.7773
| 3025 | 0.47222 | 2.9492 | 1.5312 | 1.8151
| 3026 | 0.37037 | 2.7966 | 1.6562 | 2.395
| 3027 | 0.41667 | 3.0508 | 1.5625 | 2.2647
| 3028 | 0.34259 | 2.1864 | 1.7188 | 2.0546
| 3029 | 0.60185 | 2.5085 | 0.96875 | 2.042
| 3030 | 0.37963 | 2.9831 | 1.4375 | 2.0714
| 3031 | 0.39815 | 2.4237 | 0.96875 | 2.4202
| 3032 | 0.44444 | 2 | 1.4688 | 2.0882
| 3033 | 0.47222 | 3.2373 | 1.25 | 2.458
| 3034 | 0.5 | 2.3051 | 1.4688 | 2.021
| 3035 | 0.35185 | 3 | 0.8125 | 1.916
| 3036 | 0.41667 | 2.4068 | 1.0938 | 1.8235
| 3037 | 0.43519 | 2.678 | 1.7812 | 2
| 3038 | 0.47222 | 2.4746 | 1.3438 | 2.1303
| 3039 | 0.4537 | 2.6441 | 1.0625 | 2.1218
| 3040 | 0.36111 | 3.0847 | 1.7812 | 2.1176
| 3041 | 0.44444 | 2.3559 | 3.125 | 1.958
| 3042 | 0.55556 | 2.3051 | 2.125 | 1.9202
| 3043 | 0.42593 | 3.0508 | 0.96875 | 2.2689
| 3044 | 0.39815 | 2.8136 | 0.78125 | 2.1723
| 3045 | 0.25926 | 2.7119 | 2.3125 | 2.0546
| 3046 | 0.4537 | 2.9322 | 1.6875 | 2.1429
| 3047 | 0.48148 | 2.7627 | 1.5 | 1.9916
| 3048 | 0.25 | 2.6102 | 1.9375 | 1.937
| 3049 | 0.49074 | 3.1017 | 1.2812 | 1.9076
| 3050 | 0.37037 | 2.0847 | 1.125 | 2.1891
| 3051 | 0.34259 | 2.6271 | 1.1562 | 2.0798
| 3052 | 0.37037 | 3.2203 | 1.3438 | 2.084
| 3053 | 0.39815 | 3 | 1.5312 | 2.0084
| 3054 | 0.26852 | 2.661 | 1.2188 | 1.9034
| 3055 | 0.4537 | 3.2712 | 1 | 1.9202
| 3056 | 0.5 | 2.5932 | 1.0625 | 1.9664
| 3057 | 0.47222 | 2.4068 | 2.2188 | 1.895
| 3058 | 0.31481 | 2.1017 | 0.84375 | 2.1513
| 3059 | 0.37963 | 2.7966 | 1.1875 | 2.1765
| 3060 | 0.37963 | 2.0847 | 2.0312 | 2.1134
| 3061 | 0.53704 | 3.0678 | 1.5938 | 2.2983
| 3062 | 0.34259 | 2.8644 | 1.2188 | 2.5756
| 3063 | 0.48148 | 2.5763 | 1.375 | 2.0336
| 3064 | 0.41667 | 2.9831 | 1.375 | 1.9076
| 3065 | 0.4537 | 2.6102 | 1.7188 | 1.9034
| 3066 | 0.39815 | 3.3051 | 1.5 | 2.1639
| 3067 | 0.4537 | 2.3051 | 1.0312 | 2.1176
| 3068 | 0.37037 | 2.8136 | 1.5312 | 2.2983
| 3069 | 0.47222 | 3.0678 | 1.4062 | 2.2983
| 3070 | 0.52778 | 3 | 2.4688 | 2.1008
| 3071 | 0.5 | 3.1017 | 1.3438 | 2.0126
| 3072 | 0.37963 | 3.0508 | 0.78125 | 2.1176
| 3073 | 0.39815 | 2.3898 | 2.1875 | 1.9706
| 3074 | 0.47222 | 2.4576 | 1.6875 | 2.4412
| 3075 | 0.43519 | 1.8814 | 1.125 | 1.9958
| 3076 | 0.39815 | 3.2034 | 1.6562 | 2.458
| 3077 | 0.32407 | 3.4237 | 1.2812 | 2.1471
| 3078 | 0.40741 | 2.339 | 2.0625 | 2.0546
| 3079 | 0.42593 | 2.9492 | 1.0625 | 2.1975
| 3080 | 0.44444 | 2.322 | 1.375 | 2.1261
| 3081 | 0.55556 | 3.1695 | 0.53125 | 2.5672
| 3082 | 0.40741 | 2.8814 | 1.375 | 1.895
| 3083 | 0.33333 | 2.5254 | 1.1562 | 2.1303
| 3084 | 0.43519 | 2.3898 | 0.75 | 1.8193
| 3085 | 0.5 | 2.0678 | 0.6875 | 2.0588
| 3086 | 0.58333 | 2.8136 | 0.9375 | 2.1807
| 3087 | 0.37037 | 3.1356 | 1.375 | 1.979
| 3088 | 0.52778 | 1.3559 | 2.0625 | 1.8235
| 3089 | 0.43519 | 2.4068 | 1.5938 | 2.0714
| 3090 | 0.38889 | 2.4746 | 1.4375 | 1.895
| 3091 | 0.47222 | 2.6949 | 1.25 | 1.7983
| 3092 | 0.5463 | 2.7966 | 2.2188 | 2.0252
| 3093 | 0.4537 | 2.7458 | 1.4688 | 1.8109
| 3094 | 0.42593 | 2.2712 | 1.4688 | 2.1387
| 3095 | 0.5463 | 2.2373 | 1.6562 | 1.7437
| 3096 | 0.46296 | 2.4407 | 1.2812 | 2.3277
| 3097 | 0.38889 | 1.8644 | 1.3438 | 1.9454
| 3098 | 0.47222 | 2.7119 | 1.3438 | 2.1092
| 3099 | 0.46296 | 2.9322 | 1.4062 | 2.0672
| 3100 | 0.32407 | 3.2881 | 1.8438 | 1.9412
| 3101 | 0.52778 | 2.8983 | 1.6875 | 2.1513
| 3102 | 0.51852 | 2.5085 | 1.3125 | 2.042
| 3103 | 0.38889 | 2.9831 | 1.1562 | 2.4118
| 3104 | 0.63889 | 2.1017 | 1.4688 | 2.0966
| 3105 | 0.43519 | 2.4576 | 1.375 | 2.0588
| 3106 | 0.44444 | 2.5763 | 1.9375 | 1.979
| 3107 | 0.36111 | 2.5932 | 1 | 2.0084
| 3108 | 0.53704 | 2.9661 | 2.1875 | 2.1513
| 3109 | 0.42593 | 2.5593 | 0.53125 | 2.105
| 3110 | 0.32407 | 2.7288 | 0.84375 | 2.1807
| 3111 | 0.50926 | 2.5424 | 0.875 | 2.2605
| 3112 | 0.37037 | 1.9492 | 1.2188 | 1.8235
| 3113 | 0.41667 | 2.3559 | 1.2188 | 2.0924
| 3114 | 0.33333 | 2.1186 | 1.4688 | 1.8235
| 3115 | 0.44444 | 2.5932 | 1.5938 | 2.1134
| 3116 | 0.36111 | 3.2712 | 1.0625 | 1.8571
| 3117 | 0.39815 | 2.2034 | 0.84375 | 1.9748
| 3118 | 0.33333 | 2.4746 | 1.3438 | 2.1387
| 3119 | 0.2963 | 2.7119 | 1 | 1.9874
| 3120 | 0.41667 | 2.5593 | 1.9062 | 2.0672
| 3121 | 0.5463 | 2.4237 | 1.125 | 1.9454
| 3122 | 0.41667 | 2.3729 | 1.75 | 2.7059
| 3123 | 0.34259 | 2.8305 | 1.375 | 1.958
| 3124 | 0.4537 | 3.0339 | 1.125 | 1.8067
| 3125 | 0.60185 | 2.7966 | 1 | 2.2899
| 3126 | 0.55556 | 2.1525 | 1.25 | 1.8529
| 3127 | 0.28704 | 2.7966 | 1.2812 | 2.1387
| 3128 | 0.49074 | 2.0508 | 1.3438 | 2.0714
| 3129 | 0.42593 | 3.0169 | 1.6875 | 2.0546
| 3130 | 0.50926 | 2.2373 | 2.0625 | 2.0252
| 3131 | 0.33333 | 2.5085 | 0.9375 | 2.1134
| 3132 | 0.47222 | 2.8983 | 1.5625 | 2.1345
| 3133 | 0.50926 | 2.0169 | 1.5 | 2.2689
| 3134 | 0.37037 | 2.9661 | 1.3125 | 2.2605
| 3135 | 0.55556 | 2.4576 | 1 | 2.3277
| 3136 | 0.28704 | 3 | 1.5625 | 2.4202
| 3137 | 0.37037 | 2.3898 | 1.125 | 1.9118
| 3138 | 0.34259 | 2.2373 | 1.1562 | 1.958
| 3139 | 0.51852 | 2.7288 | 1.25 | 2.0378
| 3140 | 0.33333 | 2.7966 | 1.5 | 2.0252
| 3141 | 0.58333 | 2.6271 | 1.3438 | 2.1218
| 3142 | 0.49074 | 2.7797 | 1.0625 | 1.9328
| 3143 | 0.42593 | 2.4746 | 0.5625 | 2.0672
| 3144 | 0.38889 | 1.9831 | 1.3125 | 2.1975
| 3145 | 0.51852 | 2.0508 | 1.5312 | 1.9454
| 3146 | 0.33333 | 2.6949 | 0.78125 | 2.2101
| 3147 | 0.25 | 2.678 | 2.4375 | 2.2227
| 3148 | 0.61111 | 2.4746 | 0.9375 | 2.2773
| 3149 | 0.44444 | 2.7966 | 1.1875 | 2.1891
| 3150 | 0.49074 | 2.339 | 1.9375 | 1.9664
| 3151 | 0.37963 | 2.0678 | 2.2188 | 1.9538
| 3152 | 0.48148 | 2.8136 | 1.0938 | 1.937
| 3153 | 0.41667 | 2.9492 | 1.6562 | 2.6681
| 3154 | 0.4537 | 2.3559 | 1.625 | 1.9538
| 3155 | 0.35185 | 3.0339 | 1.0312 | 1.979
| 3156 | 0.34259 | 2.3051 | 1.5625 | 1.9118
| 3157 | 0.47222 | 2.4407 | 1.0312 | 1.9748
| 3158 | 0.52778 | 2.8136 | 0.78125 | 1.8613
| 3159 | 0.46296 | 3.2373 | 1.875 | 2.2815
| 3160 | 0.62037 | 3.1525 | 1.25 | 2.3655
| 3161 | 0.38889 | 2.339 | 2.3125 | 2.0126
| 3162 | 0.46296 | 3.0508 | 1.1875 | 2.1345
| 3163 | 0.56481 | 2.3729 | 1.6875 | 2.0462
| 3164 | 0.37037 | 1.7119 | 1.6562 | 2.0798
| 3165 | 0.33333 | 3.339 | 1.25 | 1.8403
| 3166 | 0.35185 | 2.7627 | 1.375 | 2.6303
| 3167 | 0.34259 | 2.8644 | 2 | 2.3403
| 3168 | 0.49074 | 2.5593 | 1.1875 | 1.9538
| 3169 | 0.35185 | 3.3898 | 1.125 | 2.3151
| 3170 | 0.35185 | 2.6441 | 1.5 | 2.2605
| 3171 | 0.42593 | 2.6102 | 1.3125 | 1.9874
| 3172 | 0.5 | 3.0169 | 1.625 | 2.4622
| 3173 | 0.38889 | 2.2034 | 1.9688 | 2.1176
| 3174 | 0.49074 | 2.4746 | 1.2812 | 2.1429
| 3175 | 0.5 | 2.2203 | 1.5 | 2.2227
| 3176 | 0.5 | 3.1525 | 0.625 | 1.8487
| 3177 | 0.4537 | 3.4068 | 1.6562 | 1.9748
| 3178 | 0.2037 | 3.0339 | 0.4375 | 2.437
| 3179 | 0.53704 | 2.7966 | 1.8438 | 1.9454
| 3180 | 0.42593 | 2.4237 | 1.4375 | 2.2479
| 3181 | 0.2963 | 3.0169 | 1.8438 | 2.2941
| 3182 | 0.49074 | 2.2881 | 1.125 | 2.2857
| 3183 | 0.39815 | 2.5085 | 1.9688 | 1.8277
| 3184 | 0.36111 | 2.1186 | 1.5 | 2.0126
| 3185 | 0.39815 | 1.9661 | 1.5625 | 1.9328
| 3186 | 0.41667 | 2.0508 | 1.9062 | 2.0126
| 3187 | 0.47222 | 2.6949 | 1.3438 | 2.2395
| 3188 | 0.33333 | 2.6441 | 2.2188 | 2.1723
| 3189 | 0.53704 | 2.7458 | 0.78125 | 1.7563
| 3190 | 0.47222 | 2.8814 | 1.3438 | 2.2647
| 3191 | 0.34259 | 2.1695 | 1.6562 | 2
| 3192 | 0.31481 | 2.339 | 1.25 | 2.2773
| 3193 | 0.35185 | 2.1695 | 1.8125 | 2.2185
| 3194 | 0.57407 | 2.5254 | 0.78125 | 2.0252
| 3195 | 0.5 | 2.7797 | 1.0938 | 2.1345
| 3196 | 0.44444 | 3.2203 | 1.875 | 2.0924
| 3197 | 0.39815 | 3.4407 | 1.125 | 1.9706
| 3198 | 0.52778 | 2.8983 | 0.96875 | 2.0924
| 3199 | 0.41667 | 2.4407 | 0.65625 | 2.1639
| 3200 | 0.37963 | 2.8475 | 0.84375 | 2.0966
| 3201 | 0.33333 | 2.5085 | 1.5 | 2.1597
| 3202 | 0.37037 | 2.661 | 1.1875 | 1.9832
| 3203 | 0.52778 | 3.3559 | 1.2188 | 2.021
| 3204 | 0.37963 | 3.0678 | 1.9688 | 2.4328
| 3205 | 0.42593 | 2.2034 | 2.2188 | 2.1008
| 3206 | 0.39815 | 2.5593 | 1.2812 | 1.9244
| 3207 | 0.34259 | 3.2542 | 1.3438 | 2.1723
| 3208 | 0.32407 | 2.3729 | 2.5 | 2.0168
| 3209 | 0.24074 | 3 | 1.6875 | 2.4664
| 3210 | 0.38889 | 3.2881 | 1.1562 | 2.084
| 3211 | 0.38889 | 3.2542 | 1.7188 | 2.6092
| 3212 | 0.48148 | 2.8305 | 1.125 | 2.1387
| 3213 | 0.58333 | 3.2203 | 1.2812 | 1.9286
| 3214 | 0.44444 | 3.0508 | 1.9062 | 1.9748
| 3215 | 0.40741 | 3.1864 | 1.0938 | 2.1597
| 3216 | 0.47222 | 2.4746 | 1.2188 | 1.8908
| 3217 | 0.41667 | 2.5932 | 1.9062 | 2.1513
| 3218 | 0.51852 | 2.5085 | 2.3438 | 2.1681
| 3219 | 0.30556 | 2.4068 | 1.4688 | 2.1176
| 3220 | 0.30556 | 2.6271 | 1.0938 | 2.0126
| 3221 | 0.31481 | 2.8305 | 1.0938 | 2.2773
| 3222 | 0.37963 | 2.7797 | 1.625 | 2.4706
| 3223 | 0.5 | 2.8305 | 1.5625 | 2.2143
| 3224 | 0.36111 | 2.1186 | 1.8125 | 1.9118
| 3225 | 0.37963 | 1.5932 | 2.0938 | 2.3277
| 3226 | 0.2963 | 2.8814 | 1.0938 | 2.395
| 3227 | 0.51852 | 2.661 | 1.0312 | 1.8655
| 3228 | 0.5 | 2.3729 | 1 | 1.7311
| 3229 | 0.51852 | 2.4576 | 1.8438 | 2.0924
| 3230 | 0.42593 | 2.661 | 0.9375 | 1.9538
| 3231 | 0.33333 | 2.339 | 1.375 | 2.1681
| 3232 | 0.50926 | 2.7458 | 1.1562 | 1.8655
| 3233 | 0.41667 | 2.2373 | 0.875 | 2.2983
| 3234 | 0.53704 | 2.5085 | 1.3438 | 1.9958
| 3235 | 0.42593 | 3.4068 | 1.2812 | 2.084
| 3236 | 0.37963 | 2.6271 | 0.875 | 2.2059
| 3237 | 0.35185 | 2.3559 | 1.7188 | 2.063
| 3238 | 0.44444 | 2.1356 | 1.9062 | 2.1471
| 3239 | 0.34259 | 2.7458 | 0.59375 | 2.1471
| 3240 | 0.36111 | 2.3051 | 1.4375 | 2.3739
| 3241 | 0.37963 | 2.7627 | 1.25 | 2.1134
| 3242 | 0.57407 | 2.6441 | 1.8125 | 2.042
| 3243 | 0.37037 | 2.0847 | 0.9375 | 2.2185
| 3244 | 0.44444 | 2.7627 | 1.7812 | 2.3571
| 3245 | 0.38889 | 3.0169 | 1.9062 | 2.2437
| 3246 | 0.58333 | 2.6949 | 1.5938 | 1.9454
| 3247 | 0.41667 | 2.7119 | 1.1562 | 1.9328
| 3248 | 0.50926 | 3.2203 | 1.4375 | 2.2899
| 3249 | 0.48148 | 2.4068 | 1.2188 | 2.0714
| 3250 | 0.24074 | 2.4237 | 0.8125 | 2.2101
| 3251 | 0.40741 | 2.4407 | 1.0938 | 2.4832
| 3252 | 0.52778 | 2.678 | 1.1562 | 2.0378
| 3253 | 0.42593 | 2.5932 | 1.375 | 2.1807
| 3254 | 0.36111 | 3.3051 | 1.3438 | 2.0756
| 3255 | 0.61111 | 2.5763 | 1.6562 | 1.8109
| 3256 | 0.38889 | 2.4915 | 1.125 | 2.2395
| 3257 | 0.35185 | 2.4237 | 1.2812 | 2.0126
| 3258 | 0.4537 | 2.6271 | 1.4375 | 2.0966
| 3259 | 0.31481 | 2.6271 | 1.7812 | 2.3697
| 3260 | 0.43519 | 2.3898 | 1.375 | 2.0546
| 3261 | 0.5 | 2.5424 | 1.8438 | 2
| 3262 | 0.31481 | 2.339 | 1.2812 | 2.3151
| 3263 | 0.47222 | 2.7119 | 1 | 2.0588
| 3264 | 0.37037 | 1.9831 | 1.3125 | 1.8529
| 3265 | 0.30556 | 2.5932 | 1.625 | 2.0336
| 3266 | 0.39815 | 3.322 | 2.125 | 1.8445
| 3267 | 0.31481 | 2.6271 | 1.3125 | 2.0798
| 3268 | 0.2963 | 2.2373 | 1.25 | 2.0504
| 3269 | 0.34259 | 2.4237 | 1.2188 | 2.3739
| 3270 | 0.41667 | 3.1864 | 0.96875 | 1.9454
| 3271 | 0.38889 | 2.339 | 1.25 | 1.8697
| 3272 | 0.35185 | 2.339 | 1.5938 | 2.1849
| 3273 | 0.34259 | 3.1695 | 1.7188 | 2.1555
| 3274 | 0.50926 | 2.5593 | 1.125 | 2.2059
| 3275 | 0.43519 | 2.4407 | 1.4375 | 1.8782
| 3276 | 0.47222 | 3.0508 | 1.5312 | 2.1261
| 3277 | 0.44444 | 3.1864 | 1.6562 | 2.2101
| 3278 | 0.41667 | 2.3559 | 1.4688 | 1.9706
| 3279 | 0.4537 | 3 | 1.5625 | 1.979
| 3280 | 0.25 | 2.5254 | 1.4375 | 2.2227
| 3281 | 0.33333 | 3.1695 | 1.8125 | 2.458
| 3282 | 0.46296 | 2.5763 | 0.84375 | 2.0168
| 3283 | 0.37963 | 2.4407 | 0.71875 | 2.0042
| 3284 | 0.4537 | 2.2881 | 0.9375 | 1.6639
| 3285 | 0.33333 | 3.339 | 1.75 | 2.0252
| 3286 | 0.56481 | 2.6271 | 1.0938 | 2.0756
| 3287 | 0.30556 | 2.5085 | 1.8125 | 2.1513
| 3288 | 0.34259 | 3.0339 | 1.2188 | 2.0924
| 3289 | 0.40741 | 2.4746 | 0.5 | 2.4664
| 3290 | 0.48148 | 2.8305 | 1.0625 | 1.8697
| 3291 | 0.42593 | 2.339 | 1.5 | 2.1429
| 3292 | 0.53704 | 2.7458 | 1.7188 | 2.2227
| 3293 | 0.39815 | 2.6441 | 1.9375 | 2.0714
| 3294 | 0.60185 | 2.4576 | 2.1875 | 2.4202
| 3295 | 0.37963 | 2.339 | 1.4062 | 2.563
| 3296 | 0.4537 | 2.4746 | 1.0938 | 1.7353
| 3297 | 0.44444 | 2.2712 | 1.9062 | 1.8908
| 3298 | 0.26852 | 2.2712 | 1.0312 | 1.7059
| 3299 | 0.49074 | 2.4407 | 1.4375 | 2.1723
| 3300 | 0.40741 | 2.4237 | 1.5625 | 2.0084
| 3301 | 0.4537 | 2.4746 | 0.90625 | 2.2773
| 3302 | 0.34259 | 2.661 | 0.84375 | 1.7815
| 3303 | 0.37037 | 3.0339 | 1.8438 | 1.9832
| 3304 | 0.36111 | 2.5254 | 1.3125 | 1.9622
| 3305 | 0.44444 | 2.5593 | 1.4062 | 2.0714
| 3306 | 0.37037 | 2.5424 | 1.6562 | 2.1681
| 3307 | 0.37963 | 2.8475 | 1.9688 | 2.105
| 3308 | 0.46296 | 2.4576 | 0.75 | 2.1218
| 3309 | 0.47222 | 2.339 | 0.90625 | 2.0756
| 3310 | 0.42593 | 3 | 2.4688 | 2.1261
| 3311 | 0.5 | 2.1017 | 1.9688 | 1.9538
| 3312 | 0.41667 | 3.0508 | 1.25 | 2.1176
| 3313 | 0.31481 | 2.1525 | 1.1875 | 2.4832
| 3314 | 0.53704 | 2.678 | 1.8125 | 2.0252
| 3315 | 0.28704 | 2.8136 | 1.0938 | 1.9748
| 3316 | 0.30556 | 2.7458 | 1.0938 | 2.1471
| 3317 | 0.50926 | 3.0678 | 1.2812 | 1.7563
| 3318 | 0.4537 | 2.2203 | 1.2812 | 2.0126
| 3319 | 0.4537 | 2.3898 | 1.3125 | 1.9328
| 3320 | 0.37963 | 2.9492 | 1.1875 | 1.8739
| 3321 | 0.51852 | 3.2712 | 0.8125 | 1.8025
| 3322 | 0.41667 | 2.6271 | 2.5 | 1.9622
| 3323 | 0.47222 | 2.8475 | 1.4375 | 2.2479
| 3324 | 0.48148 | 3.2034 | 1.125 | 2.0378
| 3325 | 0.40741 | 3.0339 | 1.25 | 2.2143
| 3326 | 0.5 | 3.1525 | 1 | 2.021
| 3327 | 0.37037 | 2.2712 | 1.625 | 2.5252
| 3328 | 0.38889 | 2.4915 | 1.625 | 2.1849
| 3329 | 0.39815 | 2.4237 | 1.5938 | 1.7899
| 3330 | 0.42593 | 3.0508 | 2.125 | 2.3109
| 3331 | 0.51852 | 2.7797 | 2.2188 | 2.3403
| 3332 | 0.39815 | 2.4746 | 0.75 | 2.0546
| 3333 | 0.31481 | 2.6271 | 1 | 1.9622
| 3334 | 0.36111 | 2.322 | 2.1562 | 2.0924
| 3335 | 0.25 | 2.4576 | 1.625 | 1.9538
| 3336 | 0.38889 | 2.7119 | 1.0938 | 2.0336
| 3337 | 0.40741 | 2.8305 | 3.0625 | 2.4874
| 3338 | 0.39815 | 1.6102 | 1.2188 | 2.1134
| 3339 | 0.37037 | 2.4407 | 1.8125 | 2.2101
| 3340 | 0.46296 | 1.8305 | 1.0938 | 2.0336
| 3341 | 0.43519 | 3.2881 | 1.0312 | 2.1261
| 3342 | 0.27778 | 2.661 | 0.875 | 1.979
| 3343 | 0.4537 | 1.9322 | 0.8125 | 1.9622
| 3344 | 0.4537 | 2.2373 | 2.2812 | 2.2479
| 3345 | 0.5463 | 3.8136 | 0.75 | 2.0336
| 3346 | 0.59259 | 2.9492 | 1.375 | 2.416
| 3347 | 0.38889 | 2.8983 | 1.9375 | 2.1218
| 3348 | 0.40741 | 3.2373 | 1.5 | 2.1807
| 3349 | 0.38889 | 4.2881 | 1.875 | 1.7815
| 3350 | 0.49074 | 2.8983 | 1.2188 | 2.0462
| 3351 | 0.40741 | 2.3729 | 1.8438 | 2
| 3352 | 0.47222 | 2.3559 | 0.96875 | 2.2353
| 3353 | 0.2963 | 2.2542 | 1.5 | 2.2311
| 3354 | 0.38889 | 2.4068 | 1.3125 | 1.9832
| 3355 | 0.31481 | 2.9153 | 0.90625 | 2.1933
| 3356 | 0.41667 | 2.9153 | 1 | 2.2437
| 3357 | 0.41667 | 2.661 | 1.6875 | 2.2773
| 3358 | 0.40741 | 3.0339 | 0.90625 | 1.8908
| 3359 | 0.42593 | 3.0339 | 1.1562 | 2.2815
| 3360 | 0.48148 | 2.9492 | 1.1875 | 2.1723
| 3361 | 0.51852 | 2.5763 | 1.1875 | 2.2941
| 3362 | 0.37037 | 2.2373 | 0.65625 | 2.3908
| 3363 | 0.37037 | 1.8136 | 2.25 | 2.084
| 3364 | 0.42593 | 2.6102 | 1.0625 | 2.0504
| 3365 | 0.32407 | 1.8814 | 1.2812 | 1.9538
| 3366 | 0.32407 | 2.8305 | 2.1875 | 1.9454
| 3367 | 0.39815 | 3.4915 | 1.5625 | 1.9958
| 3368 | 0.36111 | 3.1864 | 1.5625 | 2.0168
| 3369 | 0.42593 | 3.4237 | 1.5312 | 2.105
| 3370 | 0.42593 | 2.2203 | 1.6562 | 1.8445
| 3371 | 0.5 | 3.3051 | 1.125 | 2.0294
| 3372 | 0.28704 | 2.8136 | 1.25 | 2.1429
| 3373 | 0.52778 | 3.1356 | 0.84375 | 2.2521
| 3374 | 0.46296 | 2.7119 | 1.7812 | 2.0588
| 3375 | 0.33333 | 1.9831 | 2.4062 | 1.8992
| 3376 | 0.5 | 2.2542 | 1.5625 | 2.2311
| 3377 | 0.47222 | 2.2034 | 1.4688 | 2.0462
| 3378 | 0.37037 | 2.8475 | 1.7812 | 1.937
| 3379 | 0.30556 | 2.9322 | 1.75 | 2.4286
| 3380 | 0.43519 | 3.5932 | 1.1562 | 2.0462
| 3381 | 0.49074 | 3.1695 | 1.375 | 2.0756
| 3382 | 0.4537 | 2.3559 | 2.25 | 2.0042
| 3383 | 0.51852 | 2.9322 | 1.2188 | 1.8992
| 3384 | 0.41667 | 2.8814 | 1.1875 | 2.2563
| 3385 | 0.47222 | 2.7966 | 1.1562 | 2.1429
| 3386 | 0.39815 | 3.2373 | 1.3125 | 2.084
| 3387 | 0.42593 | 3.339 | 1.0312 | 1.8697
| 3388 | 0.35185 | 2.2373 | 1.8438 | 2.1429
| 3389 | 0.38889 | 2.7627 | 2.1562 | 1.9664
| 3390 | 0.56481 | 2.6271 | 1.7812 | 1.9202
| 3391 | 0.62037 | 2.8983 | 1.4062 | 2.0294
| 3392 | 0.41667 | 2.4915 | 0.84375 | 2.1933
| 3393 | 0.32407 | 3.322 | 1.3125 | 2.3193
| 3394 | 0.40741 | 2.9153 | 1.4062 | 1.8487
| 3395 | 0.27778 | 4.322 | 1.375 | 1.7689
| 3396 | 0.42593 | 2.7119 | 1.2812 | 2.1345
| 3397 | 0.52778 | 3.0339 | 1.3438 | 2.0714
| 3398 | 0.39815 | 2.2203 | 1.0312 | 2.5252
| 3399 | 0.5 | 2.9153 | 1.0938 | 1.895
| 3400 | 0.46296 | 2.8644 | 1.6875 | 2.105
| 3401 | 0.47222 | 2.7627 | 1.5 | 2.1555
| 3402 | 0.37037 | 2.8475 | 1.2812 | 2.0546
| 3403 | 0.47222 | 2.4746 | 1.3125 | 2.2101
| 3404 | 0.42593 | 3.0847 | 1.75 | 2.1723
| 3405 | 0.46296 | 3.0339 | 1.4375 | 2.5672
| 3406 | 0.58333 | 2.3051 | 1.9062 | 2.2899
| 3407 | 0.39815 | 2.678 | 1.125 | 2.2227
| 3408 | 0.62963 | 3.4068 | 1.1875 | 1.8067
| 3409 | 0.47222 | 2.6441 | 1.75 | 1.7605
| 3410 | 0.2037 | 2.3898 | 1.7812 | 2.3067
| 3411 | 0.39815 | 3.5254 | 1.5312 | 2.0252
| 3412 | 0.50926 | 2.2203 | 1.4688 | 2.1218
| 3413 | 0.38889 | 3.0678 | 1.0312 | 2.2059
| 3414 | 0.37963 | 2.9153 | 1.7188 | 1.9664
| 3415 | 0.61111 | 2.9492 | 1.6875 | 2.3487
| 3416 | 0.39815 | 2.0339 | 1.125 | 1.9202
| 3417 | 0.33333 | 3.3051 | 1.0625 | 2.1218
| 3418 | 0.37037 | 2.7458 | 0.9375 | 2.4496
| 3419 | 0.39815 | 2.9322 | 1.4062 | 2.1849
| 3420 | 0.37963 | 2.9661 | 1.3438 | 2.1681
| 3421 | 0.37037 | 2.8136 | 1.375 | 1.9706
| 3422 | 0.38889 | 2.6949 | 1.4062 | 2.2017
| 3423 | 0.38889 | 2.6102 | 0.96875 | 1.8782
| 3424 | 0.34259 | 2.5424 | 0.875 | 2.1176
| 3425 | 0.58333 | 2.7119 | 1.3438 | 2.5294
| 3426 | 0.46296 | 3.3559 | 1.3125 | 1.9622
| 3427 | 0.32407 | 2.5254 | 2.0312 | 2.0294
| 3428 | 0.40741 | 2.3898 | 1.6562 | 2.0798
| 3429 | 0.21296 | 3.0339 | 0.75 | 2.3403
| 3430 | 0.37037 | 2.4746 | 1.0312 | 2.1555
| 3431 | 0.51852 | 3.339 | 1.6562 | 2.2437
| 3432 | 0.49074 | 2.1525 | 1.6875 | 1.9538
| 3433 | 0.58333 | 2.9322 | 0.78125 | 2
| 3434 | 0.43519 | 3.322 | 1.25 | 2.5966
| 3435 | 0.28704 | 2.9661 | 1.1875 | 2.3782
| 3436 | 0.44444 | 2.4746 | 1.3438 | 2.1092
| 3437 | 0.51852 | 2.3898 | 1.5312 | 1.979
| 3438 | 0.39815 | 3.2034 | 1 | 2.1303
| 3439 | 0.40741 | 2.7627 | 1.4375 | 2.1807
| 3440 | 0.39815 | 2.2712 | 1.4062 | 2.3235
| 3441 | 0.41667 | 2.7458 | 1 | 2.3782
| 3442 | 0.28704 | 2.4068 | 1.25 | 2
| 3443 | 0.35185 | 2.7288 | 1.5938 | 1.7983
| 3444 | 0.49074 | 2.5763 | 1.6562 | 2.021
| 3445 | 0.50926 | 2.322 | 1.3438 | 2.3025
| 3446 | 0.39815 | 2.8475 | 0.71875 | 2.1471
| 3447 | 0.38889 | 3.4915 | 0.96875 | 2.2647
| 3448 | 0.5 | 2.5763 | 1.1875 | 2.3487
| 3449 | 0.32407 | 2.8983 | 1.6875 | 2.084
| 3450 | 0.49074 | 3.6271 | 1.1562 | 1.958
| 3451 | 0.49074 | 2.9661 | 1.2188 | 1.8908
| 3452 | 0.43519 | 3.3051 | 1.2812 | 2.0882
| 3453 | 0.5 | 2.9831 | 2.0312 | 2.2731
| 3454 | 0.61111 | 2.0508 | 1.4062 | 2.0294
| 3455 | 0.42593 | 3.0169 | 0.9375 | 2.0462
| 3456 | 0.25926 | 2.2203 | 0.96875 | 2.605
| 3457 | 0.36111 | 2.5763 | 1.0938 | 2.0462
| 3458 | 0.40741 | 2.1525 | 1.5312 | 2.3319
| 3459 | 0.38889 | 2.4407 | 2.4062 | 2.2311
| 3460 | 0.51852 | 3.2034 | 1.125 | 2.0588
| 3461 | 0.35185 | 3.1186 | 1.4688 | 2.084
| 3462 | 0.4537 | 2.7458 | 1.7188 | 2.1555
| 3463 | 0.43519 | 2.9322 | 1.75 | 2.3319
| 3464 | 0.35185 | 1.9153 | 1.4688 | 2.3277
| 3465 | 0.32407 | 2.4915 | 1.625 | 2.021
| 3466 | 0.4537 | 2.5763 | 1.5938 | 2.0672
| 3467 | 0.4537 | 2.6102 | 1.0625 | 2.3151
| 3468 | 0.33333 | 2.4915 | 0.96875 | 1.895
| 3469 | 0.43519 | 3.0169 | 1.5 | 2.0168
| 3470 | 0.34259 | 2.5254 | 1.3438 | 2.0882
| 3471 | 0.2963 | 2.3729 | 1.125 | 2.0504
| 3472 | 0.57407 | 1.9661 | 1.625 | 1.8655
| 3473 | 0.36111 | 1.9322 | 1.2812 | 2.1975
| 3474 | 0.52778 | 2.4068 | 1.0625 | 2.2563
| 3475 | 0.35185 | 2.7119 | 1.3438 | 2.0336
| 3476 | 0.34259 | 2.3559 | 1.4375 | 1.9412
| 3477 | 0.42593 | 3.1525 | 0.8125 | 1.9328
| 3478 | 0.62963 | 3.1186 | 1.5938 | 1.7731
| 3479 | 0.32407 | 3.1356 | 1.6562 | 1.7983
| 3480 | 0.42593 | 3.0169 | 1.9688 | 2.1639
| 3481 | 0.48148 | 2.4746 | 0.8125 | 2.2227
| 3482 | 0.26852 | 2.5085 | 1 | 2.0924
| 3483 | 0.49074 | 2.7288 | 0.75 | 2.1513
| 3484 | 0.22222 | 2.3051 | 1.9062 | 2.0714
| 3485 | 0.55556 | 2.9322 | 1.25 | 1.9832
| 3486 | 0.36111 | 2.1356 | 1.2812 | 1.7773
| 3487 | 0.5 | 2.3051 | 1.625 | 2.1681
| 3488 | 0.50926 | 3.0508 | 0.9375 | 2.0924
| 3489 | 0.49074 | 2.5085 | 1.125 | 1.916
| 3490 | 0.24074 | 3.1695 | 1.9375 | 2.2227
| 3491 | 0.4537 | 3.0678 | 1.75 | 1.7773
| 3492 | 0.31481 | 2.2712 | 1.25 | 2.042
| 3493 | 0.40741 | 3.2712 | 1 | 2.0546
| 3494 | 0.53704 | 2.7797 | 1.5625 | 2.1303
| 3495 | 0.56481 | 1.9831 | 0.8125 | 2.1933
| 3496 | 0.32407 | 1.9831 | 0.78125 | 1.9118
| 3497 | 0.53704 | 2.2034 | 1.25 | 2.4328
| 3498 | 0.41667 | 2.7797 | 1.625 | 2.2521
| 3499 | 0.37963 | 2.6102 | 1.4062 | 1.9538
| 3500 | 0.34259 | 2.2712 | 1.4375 | 1.9874
| 3501 | 0.58333 | 2.8814 | 1 | 2.0126
| 3502 | 0.36111 | 2.678 | 1.5938 | 2.3361
| 3503 | 0.25926 | 2.9492 | 1.5625 | 2.021
| 3504 | 0.46296 | 2.6441 | 1.9062 | 1.8529
| 3505 | 0.38889 | 2.4576 | 1.5625 | 2.2647
| 3506 | 0.48148 | 3.0508 | 1.2812 | 1.8529
| 3507 | 0.25926 | 2.2542 | 1.6562 | 1.9748
| 3508 | 0.38889 | 2.9831 | 0.96875 | 2.2269
| 3509 | 0.5463 | 3.1525 | 0.96875 | 2.1134
| 3510 | 0.51852 | 2.9322 | 0.90625 | 1.9874
| 3511 | 0.38889 | 2.5763 | 1.1562 | 2.1092
| 3512 | 0.38889 | 2.8475 | 2.2188 | 2.2353
| 3513 | 0.42593 | 2.8305 | 1.0312 | 2.1429
| 3514 | 0.36111 | 3.0847 | 2 | 1.8361
| 3515 | 0.38889 | 3.0847 | 1.125 | 2.0798
| 3516 | 0.44444 | 3.1186 | 1.5625 | 2.042
| 3517 | 0.42593 | 2.2712 | 1.5312 | 2.2815
| 3518 | 0.48148 | 2.678 | 0.90625 | 2.1429
| 3519 | 0.37963 | 1.9153 | 0.84375 | 2.1681
| 3520 | 0.40741 | 2.4068 | 1.2188 | 1.9076
| 3521 | 0.44444 | 3 | 2.0625 | 2.063
| 3522 | 0.38889 | 2.9492 | 1.1562 | 1.8992
| 3523 | 0.37037 | 2.1695 | 2.3438 | 2.2101
| 3524 | 0.37963 | 2.5932 | 1.5625 | 2.1387
| 3525 | 0.42593 | 2.7119 | 1.75 | 2.0294
| 3526 | 0.50926 | 2.8475 | 2 | 2.2227
| 3527 | 0.39815 | 2.4746 | 1.2188 | 2.1723
| 3528 | 0.37963 | 2.0169 | 1.5 | 1.9706
| 3529 | 0.37037 | 2.4576 | 1.3125 | 2.2899
| 3530 | 0.37037 | 3 | 1.3125 | 2.1261
| 3531 | 0.39815 | 3.5763 | 2.5938 | 2.0924
| 3532 | 0.42593 | 2.3729 | 1.9375 | 1.895
| 3533 | 0.5 | 2.5763 | 1.5625 | 1.9874
| 3534 | 0.52778 | 2.1017 | 1.4062 | 2.2899
| 3535 | 0.46296 | 2.4407 | 1.3125 | 2.4328
| 3536 | 0.25 | 2.8983 | 1 | 2.0378
| 3537 | 0.25 | 2.7458 | 1.75 | 2.3319
| 3538 | 0.30556 | 2.4407 | 2.8438 | 1.7773
| 3539 | 0.37037 | 3.0339 | 2.3125 | 2.395
| 3540 | 0.37037 | 2.5254 | 1.0938 | 2.1303
| 3541 | 0.51852 | 2.1356 | 2.0938 | 2.2017
| 3542 | 0.47222 | 2.2034 | 1.9375 | 1.9664
| 3543 | 0.48148 | 2.2881 | 1.4062 | 2.1513
| 3544 | 0.42593 | 3.0339 | 0.96875 | 2.0168
| 3545 | 0.33333 | 2.1695 | 1.1562 | 2.395
| 3546 | 0.40741 | 2.8814 | 2.0938 | 2.2731
| 3547 | 0.37037 | 1.8644 | 1.25 | 2.2689
| 3548 | 0.32407 | 2.678 | 1.6562 | 2.2605
| 3549 | 0.34259 | 2.7288 | 1.9062 | 1.8277
| 3550 | 0.46296 | 2.6949 | 0.84375 | 2.0168
| 3551 | 0.39815 | 2.4576 | 1.8438 | 1.8782
| 3552 | 0.32407 | 2.1864 | 1 | 2.0462
| 3553 | 0.33333 | 2.5593 | 1.4375 | 2.0588
| 3554 | 0.5463 | 3.1017 | 0.75 | 2.2311
| 3555 | 0.36111 | 2.4237 | 1.25 | 2.4328
| 3556 | 0.27778 | 2.6102 | 1.625 | 2.0546
| 3557 | 0.39815 | 2.9153 | 0.875 | 2.105
| 3558 | 0.39815 | 2.0339 | 1.1562 | 2.0966
| 3559 | 0.41667 | 3.1695 | 0.625 | 1.9202
| 3560 | 0.27778 | 2 | 0.8125 | 2.2227
| 3561 | 0.28704 | 2.4915 | 1.0312 | 2.2269
| 3562 | 0.42593 | 2.7458 | 1.9375 | 2.1471
| 3563 | 0.38889 | 3.0339 | 0.5625 | 2.1597
| 3564 | 0.46296 | 2.0508 | 1.4375 | 1.9748
| 3565 | 0.32407 | 2.1525 | 1.5 | 2.2521
| 3566 | 0.41667 | 2.7966 | 1.3125 | 2.563
| 3567 | 0.44444 | 2.2203 | 0.84375 | 2.1261
| 3568 | 0.40741 | 2.4576 | 1.125 | 2.0462
| 3569 | 0.38889 | 1.661 | 1.7188 | 2.2563
| 3570 | 0.56481 | 2.9153 | 3 | 1.9034
| 3571 | 0.37037 | 3.7797 | 1.7188 | 2.0504
| 3572 | 0.43519 | 2.2203 | 2.2188 | 1.6807
| 3573 | 0.36111 | 2.1186 | 1.3438 | 1.9874
| 3574 | 0.2963 | 2.1695 | 2.1875 | 2.2815
| 3575 | 0.44444 | 2.7627 | 0.96875 | 2.2143
| 3576 | 0.43519 | 1.8644 | 0.9375 | 2.3571
| 3577 | 0.39815 | 2.4068 | 1.5625 | 2.0378
| 3578 | 0.33333 | 2.7458 | 0.75 | 1.9202
| 3579 | 0.46296 | 2.8983 | 1.1875 | 1.7815
| 3580 | 0.28704 | 2.4915 | 1.2812 | 1.8908
| 3581 | 0.26852 | 2.0169 | 1.6875 | 1.9706
| 3582 | 0.42593 | 3.4237 | 1.4062 | 2.1303
| 3583 | 0.28704 | 2.9153 | 1.7812 | 2.0042
| 3584 | 0.37963 | 2.8475 | 1.0938 | 2.2143
| 3585 | 0.46296 | 1.678 | 1 | 2.2353
| 3586 | 0.34259 | 3.322 | 1.0938 | 1.9748
| 3587 | 0.43519 | 2.6102 | 1.8438 | 2.5714
| 3588 | 0.4537 | 3.1525 | 1.5 | 2.7479
| 3589 | 0.38889 | 2.2203 | 1.4062 | 1.7815
| 3590 | 0.34259 | 3.4915 | 2.125 | 2.3697
| 3591 | 0.32407 | 3.9322 | 1.7812 | 2.4328
| 3592 | 0.48148 | 2.9661 | 1.3438 | 2.3697
| 3593 | 0.46296 | 2.678 | 2.0625 | 2.063
| 3594 | 0.41667 | 2.1186 | 1.2188 | 1.9622
| 3595 | 0.69444 | 3 | 1.6875 | 1.8109
| 3596 | 0.33333 | 2.9153 | 0.96875 | 2.0798
| 3597 | 0.37963 | 2.6271 | 1.7188 | 1.9706
| 3598 | 0.48148 | 2.661 | 1.625 | 2.1555
| 3599 | 0.44444 | 3.1864 | 1.4375 | 2.4118
| 3600 | 0.42593 | 2.7966 | 1.4688 | 1.9958
| 3601 | 0.59259 | 2.322 | 2.0312 | 2.2941
| 3602 | 0.5463 | 3.0847 | 1.3125 | 1.8908
| 3603 | 0.41667 | 2.5254 | 1.125 | 1.937
| 3604 | 0.46296 | 2.4915 | 1.75 | 2.0714
| 3605 | 0.56481 | 2.7627 | 1 | 2.2479
| 3606 | 0.37037 | 2.2203 | 1.7812 | 2.1261
| 3607 | 0.5 | 3.8136 | 1.0312 | 2.2941
| 3608 | 0.30556 | 3.0339 | 1.25 | 1.9832
| 3609 | 0.42593 | 2.9153 | 1.0312 | 2.3697
| 3610 | 0.25 | 2.8814 | 1.7812 | 2.0294
| 3611 | 0.4537 | 2.6271 | 1.1875 | 1.8571
| 3612 | 0.43519 | 3.0339 | 1.8125 | 2.1513
| 3613 | 0.42593 | 2.2034 | 1.5625 | 2.1681
| 3614 | 0.38889 | 2.322 | 2.125 | 1.8697
| 3615 | 0.38889 | 2.0508 | 1.2812 | 2.2479
| 3616 | 0.46296 | 2.4237 | 1.4375 | 2.0504
| 3617 | 0.4537 | 2.4576 | 0.96875 | 1.9496
| 3618 | 0.44444 | 2.5763 | 1 | 2.1933
| 3619 | 0.32407 | 3.1864 | 1.3125 | 2.1765
| 3620 | 0.37037 | 2.678 | 1.5 | 1.6933
| 3621 | 0.35185 | 3.0169 | 1.5 | 2.1891
| 3622 | 0.46296 | 3.0169 | 1.1562 | 2.4118
| 3623 | 0.37963 | 3.3898 | 0.9375 | 2.3361
| 3624 | 0.56481 | 2.8983 | 2.0625 | 1.6429
| 3625 | 0.49074 | 2.7288 | 1.4062 | 2.0882
| 3626 | 0.44444 | 3.1695 | 1.3125 | 2.0588
| 3627 | 0.5 | 1.8644 | 1.4688 | 1.9454
| 3628 | 0.28704 | 2.7119 | 1.3125 | 2.2395
| 3629 | 0.30556 | 2.8814 | 1 | 1.7815
| 3630 | 0.43519 | 3.0678 | 1.5 | 1.9958
| 3631 | 0.42593 | 1.6271 | 2 | 2.1261
| 3632 | 0.5 | 2.7288 | 1.5312 | 2.2017
| 3633 | 0.42593 | 3.0678 | 1.7812 | 2.5672
| 3634 | 0.41667 | 3.0339 | 1.5625 | 1.6765
| 3635 | 0.34259 | 2.8305 | 1.5 | 1.9286
| 3636 | 0.52778 | 2.9492 | 1.8438 | 1.7101
| 3637 | 0.2963 | 2.1186 | 1.7812 | 2.1134
| 3638 | 0.26852 | 3.1695 | 1.25 | 1.8992
| 3639 | 0.28704 | 2.8644 | 1.0938 | 1.895
| 3640 | 0.35185 | 2.8814 | 1.7812 | 2.0588
| 3641 | 0.37963 | 2.9492 | 2.0625 | 2.0042
| 3642 | 0.28704 | 2.4746 | 1.0938 | 2.0546
| 3643 | 0.55556 | 2.5593 | 1.375 | 1.8109
| 3644 | 0.47222 | 3.339 | 1.2188 | 2.0504
| 3645 | 0.30556 | 2.7458 | 1.7812 | 2.1218
| 3646 | 0.47222 | 2.9492 | 1.2188 | 1.9748
| 3647 | 0.41667 | 2.4068 | 2.4062 | 2.2395
| 3648 | 0.33333 | 2.4576 | 0.75 | 2.2563
| 3649 | 0.47222 | 2.6441 | 1.125 | 2.1723
| 3650 | 0.27778 | 3.4068 | 1.5312 | 2.3151
| 3651 | 0.37037 | 2.8305 | 1.125 | 2.2101
| 3652 | 0.57407 | 2.8983 | 1.7812 | 2.0546
| 3653 | 0.52778 | 3.4915 | 1.0625 | 2.3655
| 3654 | 0.57407 | 2.4915 | 1.9062 | 2.2773
| 3655 | 0.47222 | 3.1864 | 1.7812 | 1.7899
| 3656 | 0.43519 | 2.1525 | 0.875 | 2.0252
| 3657 | 0.47222 | 2.5593 | 1.9375 | 2.0798
| 3658 | 0.42593 | 2.1356 | 1.6875 | 2.2101
| 3659 | 0.27778 | 3.1186 | 2.5312 | 2.0126
| 3660 | 0.38889 | 2.0678 | 0.75 | 2.0966
| 3661 | 0.28704 | 1.9661 | 0.875 | 2.0294
| 3662 | 0.47222 | 2.5932 | 1.8125 | 1.7815
| 3663 | 0.48148 | 3.2542 | 0.9375 | 1.8487
| 3664 | 0.38889 | 2.8136 | 1.7188 | 2.2395
| 3665 | 0.51852 | 3.1017 | 1.1875 | 2.0336
| 3666 | 0.4537 | 1.9153 | 1.2812 | 1.9076
| 3667 | 0.37963 | 1.8983 | 1.7812 | 2.1807
| 3668 | 0.47222 | 2.8644 | 1.8438 | 2.2437
| 3669 | 0.52778 | 1.8475 | 1.4375 | 1.8739
| 3670 | 0.38889 | 2.9322 | 2 | 2.4202
| 3671 | 0.23148 | 2.5932 | 1.125 | 1.9244
| 3672 | 0.5463 | 2.1695 | 1.6875 | 2.1261
| 3673 | 0.31481 | 2.1695 | 1.3125 | 2.0462
| 3674 | 0.36111 | 3.1356 | 1.0312 | 1.9916
| 3675 | 0.5 | 2.7458 | 1 | 2.2857
| 3676 | 0.51852 | 3.2203 | 1.375 | 1.937
| 3677 | 0.46296 | 2.7966 | 1.3125 | 1.9244
| 3678 | 0.52778 | 2.4237 | 1.2812 | 1.7437
| 3679 | 0.41667 | 3.0169 | 0.84375 | 2.479
| 3680 | 0.41667 | 2.661 | 1.375 | 2.1092
| 3681 | 0.42593 | 2.3729 | 1.0938 | 2.1891
| 3682 | 0.52778 | 3.5763 | 1.2188 | 2.021
| 3683 | 0.39815 | 3.4068 | 1.5312 | 2.2185
| 3684 | 0.27778 | 2.3729 | 1 | 2.1639
| 3685 | 0.46296 | 2.4407 | 1.9375 | 1.9916
| 3686 | 0.37037 | 2.4915 | 1.5 | 2.0294
| 3687 | 0.31481 | 3.2712 | 1.3125 | 2.1345
| 3688 | 0.42593 | 2.4746 | 1.25 | 2.0714
| 3689 | 0.34259 | 2.0339 | 1 | 2.1008
| 3690 | 0.37037 | 2.7119 | 1.6562 | 2.458
| 3691 | 0.37037 | 2.7288 | 1.7188 | 2.0924
| 3692 | 0.59259 | 3.2542 | 2.1562 | 2.042
| 3693 | 0.40741 | 2.1525 | 1.5 | 2.105
| 3694 | 0.48148 | 3.2542 | 1.0625 | 1.8235
| 3695 | 0.37037 | 3.1017 | 1.5312 | 1.9244
| 3696 | 0.34259 | 3 | 1.7188 | 1.9664
| 3697 | 0.42593 | 3.2542 | 0.65625 | 2.1975
| 3698 | 0.38889 | 2.8983 | 1.3438 | 2.3487
| 3699 | 0.37963 | 2.7966 | 1.0625 | 2.4538
| 3700 | 0.47222 | 2.7119 | 1 | 1.958
| 3701 | 0.47222 | 2.1356 | 1 | 2.2269
| 3702 | 0.2963 | 2.6949 | 1.25 | 2.2185
| 3703 | 0.49074 | 2.3898 | 0.96875 | 1.9538
| 3704 | 0.44444 | 2.7288 | 2.4062 | 2.0882
| 3705 | 0.4537 | 3.3729 | 1.5312 | 1.8613
| 3706 | 0.47222 | 1.6271 | 1.25 | 2.0378
| 3707 | 0.42593 | 2.9661 | 1 | 1.9622
| 3708 | 0.60185 | 2.7288 | 1.5312 | 1.8992
| 3709 | 0.48148 | 2.1186 | 1.4375 | 2.0588
| 3710 | 0.40741 | 3.3051 | 1.1562 | 2.1765
| 3711 | 0.24074 | 2.322 | 1.3438 | 2.2815
| 3712 | 0.47222 | 2.322 | 2.0625 | 1.9832
| 3713 | 0.44444 | 2.7458 | 1.4688 | 2.6429
| 3714 | 0.52778 | 2.9322 | 1.2188 | 2.2521
| 3715 | 0.39815 | 3.1186 | 0.75 | 2.1513
| 3716 | 0.30556 | 2.6102 | 1.1562 | 2.2815
| 3717 | 0.4537 | 2.0339 | 1.5312 | 2.0252
| 3718 | 0.43519 | 2.4746 | 1.625 | 2.0966
| 3719 | 0.36111 | 2.3559 | 1.25 | 2.1134
| 3720 | 0.28704 | 2.2712 | 1.0312 | 2.2899
| 3721 | 0.30556 | 2.5424 | 0.78125 | 2.395
| 3722 | 0.36111 | 3.7966 | 1.3125 | 1.895
| 3723 | 0.62037 | 2.3898 | 1.0312 | 1.8403
| 3724 | 0.41667 | 3.0847 | 1.7188 | 2.0168
| 3725 | 0.35185 | 2.4068 | 1.2188 | 1.9874
| 3726 | 0.4537 | 2.2712 | 1.7812 | 2.3613
| 3727 | 0.44444 | 2.6102 | 1.75 | 1.8235
| 3728 | 0.36111 | 2.9492 | 1.3125 | 1.979
| 3729 | 0.46296 | 2.2881 | 1.1875 | 1.479
| 3730 | 0.59259 | 2.4915 | 0.71875 | 1.9286
| 3731 | 0.2963 | 2.6102 | 1.1562 | 1.9496
| 3732 | 0.34259 | 3.0169 | 2.1562 | 2.2983
| 3733 | 0.43519 | 2.4915 | 1.0625 | 2.1723
| 3734 | 0.34259 | 2.6441 | 1.0625 | 2.3445
| 3735 | 0.44444 | 1.8305 | 1.1875 | 1.9244
| 3736 | 0.41667 | 2.5424 | 1.8125 | 2.0252
| 3737 | 0.4537 | 3.0339 | 1.125 | 2.1303
| 3738 | 0.32407 | 2.322 | 1.2188 | 2.084
| 3739 | 0.43519 | 2.339 | 1.8438 | 2.1555
| 3740 | 0.33333 | 2.9831 | 0.875 | 2.1975
| 3741 | 0.26852 | 2.661 | 1.75 | 2.0966
| 3742 | 0.53704 | 2.5932 | 1.5938 | 1.7689
| 3743 | 0.25926 | 2.322 | 0.9375 | 1.8739
| 3744 | 0.49074 | 1.9153 | 1.5625 | 2.5336
| 3745 | 0.37037 | 2.1525 | 1.4062 | 1.8487
| 3746 | 0.41667 | 3.0339 | 1.1875 | 2.4202
| 3747 | 0.53704 | 2.6949 | 1.8125 | 2.1933
| 3748 | 0.4537 | 3.0847 | 1.4375 | 1.9202
| 3749 | 0.34259 | 2.4576 | 1.6875 | 1.9244
| 3750 | 0.52778 | 2.7966 | 1.2188 | 1.8151
| 3751 | 0.53704 | 2.7458 | 1.8438 | 2.395
| 3752 | 0.43519 | 2.8136 | 0.8125 | 2.1303
| 3753 | 0.4537 | 2.5424 | 0.90625 | 1.9076
| 3754 | 0.36111 | 2.0847 | 0.71875 | 1.9328
| 3755 | 0.53704 | 3.0508 | 1.25 | 2.416
| 3756 | 0.53704 | 2.0678 | 1.75 | 1.5336
| 3757 | 0.63889 | 2.5763 | 1.4688 | 2.2143
| 3758 | 0.39815 | 3.322 | 2.7812 | 2.3067
| 3759 | 0.5463 | 2.322 | 0.78125 | 2.1471
| 3760 | 0.31481 | 3.0508 | 1.5312 | 1.9874
| 3761 | 0.37037 | 2.8136 | 1.5625 | 2.0168
| 3762 | 0.41667 | 2.6102 | 1.125 | 2.2143
| 3763 | 0.49074 | 2.9661 | 0.9375 | 2.0294
| 3764 | 0.35185 | 1.9661 | 0.96875 | 2.0336
| 3765 | 0.52778 | 3.678 | 2.4375 | 2.1429
| 3766 | 0.49074 | 2.4407 | 1.2812 | 2.0042
| 3767 | 0.47222 | 2.661 | 1.25 | 1.9706
| 3768 | 0.2963 | 2.7797 | 1.0312 | 2.1891
| 3769 | 0.31481 | 2.2203 | 1 | 2.1807
| 3770 | 0.47222 | 2.2712 | 1.375 | 1.8782
| 3771 | 0.27778 | 3.0678 | 1.25 | 2.105
| 3772 | 0.56481 | 3.5932 | 1.6875 | 2.4034
| 3773 | 0.44444 | 2.5424 | 1.1875 | 1.979
| 3774 | 0.44444 | 2.2542 | 0.75 | 2.3025
| 3775 | 0.30556 | 2.6949 | 1.25 | 2.2437
| 3776 | 0.47222 | 2.4068 | 2.25 | 2.105
| 3777 | 0.43519 | 3.4746 | 1.5 | 2.1471
| 3778 | 0.58333 | 3.0508 | 1.4375 | 1.9538
| 3779 | 0.37963 | 3.1356 | 1.5312 | 2.1765
| 3780 | 0.39815 | 3.1356 | 0.9375 | 2.0042
| 3781 | 0.27778 | 2.4746 | 1.6875 | 2.1765
| 3782 | 0.59259 | 3.0339 | 1.6562 | 2.0924
| 3783 | 0.51852 | 3.0508 | 0.71875 | 1.8109
| 3784 | 0.38889 | 2.2712 | 0.9375 | 1.937
| 3785 | 0.31481 | 2.5424 | 2.5625 | 1.8866
| 3786 | 0.2037 | 2.5424 | 1.1562 | 2.395
| 3787 | 0.50926 | 2.9322 | 1.2188 | 2.3571
| 3788 | 0.28704 | 3.0847 | 0.90625 | 2.0672
| 3789 | 0.35185 | 2.3898 | 2.125 | 1.8908
| 3790 | 0.44444 | 2.2203 | 1.9375 | 2.0588
| 3791 | 0.37963 | 2.4237 | 1.1875 | 2.2185
| 3792 | 0.50926 | 2.5085 | 1.1875 | 1.8655
| 3793 | 0.61111 | 1.6441 | 1.3125 | 2.063
| 3794 | 0.44444 | 3.1695 | 1.5312 | 2.0294
| 3795 | 0.56481 | 2.3898 | 1.7188 | 2.3109
| 3796 | 0.36111 | 2.5593 | 1.0938 | 2.2395
| 3797 | 0.28704 | 3 | 1.0312 | 1.7773
| 3798 | 0.38889 | 1.7797 | 1.1562 | 1.7605
| 3799 | 0.33333 | 2.1017 | 1.4062 | 2.1008
| 3800 | 0.49074 | 2.4576 | 0.96875 | 2.1975
| 3801 | 0.31481 | 2.5593 | 1.25 | 2.1765
| 3802 | 0.56481 | 2.5593 | 1.8125 | 2.042
| 3803 | 0.38889 | 2.6949 | 2.5312 | 1.9622
| 3804 | 0.41667 | 2.5932 | 1.375 | 2.1639
| 3805 | 0.42593 | 1.8983 | 1.6875 | 2.1849
| 3806 | 0.41667 | 2.3729 | 1.3438 | 1.7605
| 3807 | 0.61111 | 2.7627 | 1 | 1.9874
| 3808 | 0.34259 | 3.6271 | 1.1875 | 1.9958
| 3809 | 0.52778 | 3.2373 | 1.4375 | 2.0756
| 3810 | 0.61111 | 2.4068 | 0.46875 | 2.4244
| 3811 | 0.41667 | 2.3729 | 1.3125 | 2.2437
| 3812 | 0.44444 | 2.4576 | 1.4062 | 1.9916
| 3813 | 0.35185 | 2.4407 | 1.9688 | 1.9034
| 3814 | 0.66667 | 2.5763 | 0.90625 | 2.2605
| 3815 | 0.38889 | 3.1695 | 1.5312 | 2.1008
| 3816 | 0.33333 | 2.7288 | 1.1875 | 2.021
| 3817 | 0.38889 | 3.1186 | 1.375 | 2.4958
| 3818 | 0.59259 | 2.7627 | 1.4375 | 2.0168
| 3819 | 0.33333 | 2.2881 | 1.25 | 2.0168
| 3820 | 0.41667 | 3.0678 | 1.1875 | 2.4286
| 3821 | 0.34259 | 2.7797 | 0.875 | 2.2521
| 3822 | 0.61111 | 3.661 | 1.0312 | 2.1176
| 3823 | 0.40741 | 2.6102 | 1.1875 | 2.0672
| 3824 | 0.38889 | 2.6271 | 2.9062 | 2.0546
| 3825 | 0.37037 | 2.8136 | 1 | 2.105
| 3826 | 0.38889 | 3 | 1.9375 | 2.0798
| 3827 | 0.37963 | 2.4746 | 1.8438 | 2.063
| 3828 | 0.37963 | 2.6102 | 2 | 2.1134
| 3829 | 0.41667 | 3.0508 | 1.7188 | 2.3992
| 3830 | 0.53704 | 3.339 | 1.1875 | 1.9916
| 3831 | 0.48148 | 2.2034 | 1.5625 | 1.7689
| 3832 | 0.44444 | 3.0508 | 1.75 | 2.1849
| 3833 | 0.32407 | 3.3051 | 1.2188 | 2.3193
| 3834 | 0.40741 | 2.5932 | 2.1875 | 2.5588
| 3835 | 0.43519 | 2.339 | 0.625 | 2.1429
| 3836 | 0.22222 | 2.5424 | 1.4688 | 1.9748
| 3837 | 0.37037 | 2.7288 | 1.2188 | 2.2311
| 3838 | 0.46296 | 3.1525 | 0.84375 | 2.4538
| 3839 | 0.48148 | 2.3559 | 1.125 | 2.6345
| 3840 | 0.37963 | 3.1186 | 1.5312 | 1.8487
| 3841 | 0.49074 | 2.6102 | 1.4375 | 1.9244
| 3842 | 0.28704 | 2.2203 | 1.0312 | 1.9958
| 3843 | 0.35185 | 2.8644 | 0.9375 | 2.0462
| 3844 | 0.25 | 3.4237 | 1.0938 | 2.3445
| 3845 | 0.48148 | 2.5085 | 1.4688 | 2.0672
| 3846 | 0.46296 | 2.9153 | 1.7812 | 1.8824
| 3847 | 0.38889 | 3.0847 | 0.875 | 2.1849
| 3848 | 0.53704 | 2.4576 | 0.96875 | 2.1092
| 3849 | 0.37963 | 2.1525 | 1.1875 | 2.4748
| 3850 | 0.46296 | 2.4576 | 1.25 | 2.1303
| 3851 | 0.36111 | 2.4915 | 1.625 | 2.6261
| 3852 | 0.34259 | 2.9153 | 2.25 | 2.0798
| 3853 | 0.42593 | 2.6102 | 1.4062 | 2.2227
| 3854 | 0.36111 | 1.8814 | 1.75 | 2.1387
| 3855 | 0.2963 | 1.9661 | 2.125 | 2.2437
| 3856 | 0.37037 | 1.7627 | 1.0625 | 1.9832
| 3857 | 0.4537 | 3.3559 | 1.375 | 2.2227
| 3858 | 0.58333 | 2.3051 | 1.4062 | 1.9748
| 3859 | 0.43519 | 2.678 | 0.9375 | 2.1555
| 3860 | 0.41667 | 3.9322 | 1.0312 | 2.2437
| 3861 | 0.32407 | 3.1017 | 1.2812 | 2.3529
| 3862 | 0.47222 | 2.9831 | 1.0625 | 1.9916
| 3863 | 0.31481 | 2.5932 | 1.1875 | 1.9538
| 3864 | 0.2963 | 3.2542 | 0.75 | 2.2311
| 3865 | 0.39815 | 2.678 | 1.1875 | 2.1387
| 3866 | 0.42593 | 2.7119 | 1.5 | 2.2059
| 3867 | 0.2963 | 2.2542 | 1.5938 | 1.895
| 3868 | 0.5 | 2.2881 | 1.375 | 2.0252
| 3869 | 0.38889 | 2.661 | 1.6875 | 2.1681
| 3870 | 0.37963 | 2.8475 | 1.7188 | 2.1513
| 3871 | 0.46296 | 2.322 | 1.4375 | 1.9454
| 3872 | 0.34259 | 2.4576 | 1.625 | 1.916
| 3873 | 0.33333 | 2.5593 | 1.2812 | 2.2395
| 3874 | 0.35185 | 2.2712 | 1.9062 | 1.8866
| 3875 | 0.25926 | 3.0339 | 1.1875 | 2.1765
| 3876 | 0.57407 | 1.9492 | 1.2812 | 2.0126
| 3877 | 0.43519 | 2.7797 | 1.0312 | 1.6765
| 3878 | 0.51852 | 3.0508 | 0.96875 | 1.9118
| 3879 | 0.24074 | 2.3729 | 1.8438 | 1.8908
| 3880 | 0.30556 | 2.9153 | 1.3125 | 2.2017
| 3881 | 0.31481 | 2.9492 | 1.75 | 2.5168
| 3882 | 0.40741 | 1.7627 | 1.1562 | 2.042
| 3883 | 0.30556 | 2.3898 | 1.25 | 2.5168
| 3884 | 0.38889 | 3.0508 | 1 | 2.416
| 3885 | 0.51852 | 3.2881 | 1.3125 | 2.2185
| 3886 | 0.37963 | 3.2034 | 2 | 2.063
| 3887 | 0.56481 | 2.5593 | 1.3125 | 1.958
| 3888 | 0.44444 | 2.9492 | 1.0625 | 2.4202
| 3889 | 0.53704 | 2.8983 | 0.8125 | 1.8992
| 3890 | 0.40741 | 3 | 1.25 | 2.2269
| 3891 | 0.44444 | 2.8305 | 2.5312 | 2.1092
| 3892 | 0.43519 | 2.4068 | 1.625 | 1.8908
| 3893 | 0.57407 | 2.5424 | 1.2188 | 1.8193
| 3894 | 0.61111 | 2.7797 | 1.2188 | 2.1513
| 3895 | 0.48148 | 2.661 | 1.2188 | 2.2269
| 3896 | 0.27778 | 2.4746 | 1.125 | 2.1849
| 3897 | 0.4537 | 3.0169 | 1.5 | 2.1975
| 3898 | 0.30556 | 2.3898 | 2.2188 | 1.8277
| 3899 | 0.46296 | 2.6949 | 0.90625 | 1.979
| 3900 | 0.50926 | 2.2203 | 1.125 | 2.3866
| 3901 | 0.35185 | 2.4237 | 2.4062 | 1.8992
| 3902 | 0.50926 | 2.322 | 1.6875 | 1.8908
| 3903 | 0.37963 | 2.8644 | 1.8125 | 2.6807
| 3904 | 0.39815 | 2.7627 | 1.8125 | 2.0924
| 3905 | 0.44444 | 3.1356 | 1.2812 | 1.7815
| 3906 | 0.32407 | 2.7797 | 1.3125 | 1.958
| 3907 | 0.48148 | 2.2881 | 1.4375 | 1.8697
| 3908 | 0.34259 | 2.7458 | 0.8125 | 2.3151
| 3909 | 0.42593 | 3.1017 | 1.1562 | 2.1723
| 3910 | 0.57407 | 2.661 | 0.78125 | 2.0294
| 3911 | 0.58333 | 2.3898 | 1.5938 | 2.2227
| 3912 | 0.59259 | 3.1186 | 0.90625 | 2.3109
| 3913 | 0.33333 | 2.7288 | 1.2812 | 1.8866
| 3914 | 0.42593 | 3.0339 | 1.4375 | 2.0546
| 3915 | 0.43519 | 1.9831 | 1.375 | 2.042
| 3916 | 0.27778 | 2.6441 | 1.7188 | 2.0672
| 3917 | 0.53704 | 2.7288 | 1.3438 | 2.2563
| 3918 | 0.43519 | 2.2881 | 1.4688 | 2.1513
| 3919 | 0.50926 | 2.4576 | 1.7188 | 2.1513
| 3920 | 0.39815 | 2.2034 | 2 | 2.3992
| 3921 | 0.41667 | 2.322 | 1.8125 | 1.9958
| 3922 | 0.37037 | 2.4576 | 1.0938 | 2.0084
| 3923 | 0.4537 | 3.0847 | 0.96875 | 2.2941
| 3924 | 0.50926 | 2.322 | 1 | 1.7689
| 3925 | 0.38889 | 3.7797 | 1.5 | 2.3697
| 3926 | 0.48148 | 2.4576 | 1.1875 | 2.3277
| 3927 | 0.40741 | 2.1017 | 0.78125 | 2.0252
| 3928 | 0.44444 | 3.5085 | 1.9062 | 2.605
| 3929 | 0.46296 | 2.7458 | 1.5312 | 2.2101
| 3930 | 0.46296 | 3.4068 | 1.3438 | 2.1513
| 3931 | 0.38889 | 2.9661 | 1.1875 | 1.937
| 3932 | 0.34259 | 2.7119 | 1.5938 | 2.1008
| 3933 | 0.49074 | 1.7627 | 0.84375 | 2.2857
| 3934 | 0.37037 | 2.2712 | 1.6875 | 2
| 3935 | 0.26852 | 2.3898 | 2.0312 | 2.1471
| 3936 | 0.32407 | 2.8644 | 1.2812 | 1.9244
| 3937 | 0.44444 | 2.7627 | 1.4062 | 2.021
| 3938 | 0.35185 | 3.0339 | 1.7812 | 2.1176
| 3939 | 0.27778 | 3.0169 | 1.2188 | 2.1639
| 3940 | 0.33333 | 2.4746 | 1.0625 | 2.2857
| 3941 | 0.62037 | 2.8305 | 1.2188 | 2.0588
| 3942 | 0.42593 | 2.5763 | 2.7188 | 1.8655
| 3943 | 0.50926 | 2.5424 | 2.0312 | 2.2311
| 3944 | 0.48148 | 3.2881 | 1.0938 | 1.8824
| 3945 | 0.33333 | 2.9492 | 1.5 | 2.1261
| 3946 | 0.38889 | 2.5763 | 1.5 | 2.0252
| 3947 | 0.67593 | 3.2373 | 1.625 | 1.7479
| 3948 | 0.41667 | 2.5593 | 1.3438 | 2.0966
| 3949 | 0.49074 | 2.4068 | 1.2188 | 1.9244
| 3950 | 0.34259 | 2.5763 | 1.3125 | 1.7353
| 3951 | 0.46296 | 2.4407 | 0.96875 | 2.2311
| 3952 | 0.43519 | 2.9661 | 1 | 2.416
| 3953 | 0.5 | 2.9492 | 1 | 2.1471
| 3954 | 0.51852 | 2.2373 | 1.5 | 1.8151
| 3955 | 0.2963 | 2.9661 | 1.6875 | 1.9538
| 3956 | 0.37037 | 2.9153 | 1.7188 | 1.9244
| 3957 | 0.47222 | 2.3559 | 1.8125 | 2.063
| 3958 | 0.43519 | 2.7966 | 1.1562 | 2.0672
| 3959 | 0.44444 | 3.1017 | 0.6875 | 1.8235
| 3960 | 0.47222 | 2.7288 | 0.9375 | 2.2773
| 3961 | 0.42593 | 2.1695 | 2.0312 | 2.0168
| 3962 | 0.44444 | 3.2034 | 1.2812 | 1.979
| 3963 | 0.38889 | 2.2203 | 1.7812 | 2.1345
| 3964 | 0.43519 | 3.3729 | 0.84375 | 2.1092
| 3965 | 0.35185 | 2.6949 | 1.3438 | 2.021
| 3966 | 0.50926 | 2.2034 | 1.7188 | 2.0252
| 3967 | 0.41667 | 2.5932 | 0.96875 | 2.5336
| 3968 | 0.40741 | 2.8644 | 1.375 | 2.0042
| 3969 | 0.40741 | 2.2881 | 1.7188 | 1.9328
| 3970 | 0.32407 | 2.0678 | 2.375 | 1.8487
| 3971 | 0.31481 | 3 | 1.0625 | 2.021
| 3972 | 0.40741 | 3.2881 | 1.4688 | 2.3403
| 3973 | 0.42593 | 2.2542 | 1.0938 | 1.8319
| 3974 | 0.56481 | 1.9661 | 2.3438 | 1.979
| 3975 | 0.41667 | 3.1695 | 1.3125 | 2.1092
| 3976 | 0.34259 | 3.4237 | 1.25 | 1.8866
| 3977 | 0.42593 | 2.339 | 1.5625 | 2.1429
| 3978 | 0.34259 | 2.2373 | 0.8125 | 2.0756
| 3979 | 0.42593 | 2.678 | 0.875 | 2.1218
| 3980 | 0.2963 | 2.339 | 1.3125 | 2.4832
| 3981 | 0.56481 | 2.661 | 1.0625 | 2.105
| 3982 | 0.40741 | 2.7119 | 1.9375 | 2.4916
| 3983 | 0.38889 | 2.7966 | 1.6562 | 2.1849
| 3984 | 0.59259 | 2.3559 | 1.1875 | 2.2983
| 3985 | 0.43519 | 2.9322 | 1.3125 | 2.3193
| 3986 | 0.4537 | 3.0339 | 1.1562 | 2.0252
| 3987 | 0.5 | 2.3051 | 1.5312 | 2.0672
| 3988 | 0.2963 | 2.9492 | 1.5938 | 1.9328
| 3989 | 0.43519 | 2.7288 | 1.9375 | 2.2731
| 3990 | 0.31481 | 3 | 1.125 | 2.2101
| 3991 | 0.30556 | 2.7119 | 1.3438 | 2.1261
| 3992 | 0.46296 | 2.4407 | 1.125 | 2
| 3993 | 0.30556 | 3.1186 | 1.9688 | 2.2143
| 3994 | 0.37037 | 2.339 | 1.6875 | 2.0084
| 3995 | 0.42593 | 2.9661 | 1.4062 | 1.9622
| 3996 | 0.39815 | 2.8136 | 0.71875 | 1.7983
| 3997 | 0.35185 | 3.2542 | 1.7812 | 2.0756
| 3998 | 0.37037 | 2.7966 | 2.1875 | 1.7353
| 3999 | 0.37963 | 2.8305 | 1.6875 | 2.0042
| 4000 | 0.48148 | 2.7797 | 1.25 | 2.1807
| 4001 | 0.46296 | 3.0678 | 1.625 | 2.0798
| 4002 | 0.39815 | 2.8136 | 1.5625 | 2.1303
| 4003 | 0.38889 | 3.1864 | 1.5312 | 2.437
| 4004 | 0.49074 | 2.678 | 1.4062 | 1.9412
| 4005 | 0.52778 | 3.0169 | 1.9062 | 2.3445
| 4006 | 0.47222 | 2.9661 | 2.0938 | 2.1513
| 4007 | 0.37037 | 2.5763 | 0.875 | 2.0966
| 4008 | 0.41667 | 2.1356 | 1.6875 | 2.3361
| 4009 | 0.41667 | 2.1356 | 1.7188 | 1.9034
| 4010 | 0.55556 | 3 | 0.96875 | 1.8151
| 4011 | 0.37037 | 2.6102 | 1.25 | 1.9412
| 4012 | 0.5 | 2.3729 | 1.1875 | 2.3571
| 4013 | 0.43519 | 2.5085 | 1.625 | 1.8782
| 4014 | 0.56481 | 2.9322 | 0.9375 | 1.8025
| 4015 | 0.33333 | 2.5932 | 1.5938 | 2.1176
| 4016 | 0.38889 | 2.9322 | 1.7188 | 2.1975
| 4017 | 0.32407 | 2.5085 | 1.3438 | 2.0378
| 4018 | 0.44444 | 3.1864 | 1.5312 | 1.895
| 4019 | 0.48148 | 2.4576 | 1.3125 | 2.3992
| 4020 | 0.37963 | 2.9492 | 0.9375 | 2.3866
| 4021 | 0.37963 | 2.1186 | 1.8438 | 2.1933
| 4022 | 0.39815 | 2.1525 | 1.5625 | 2.0798
| 4023 | 0.50926 | 2.0169 | 1.5938 | 1.9202
| 4024 | 0.38889 | 2.5085 | 1.0625 | 2.1597
| 4025 | 0.39815 | 3.5254 | 1.9062 | 2.0294
| 4026 | 0.49074 | 3.0847 | 1.9062 | 1.9622
| 4027 | 0.4537 | 2.8136 | 1.125 | 2.0042
| 4028 | 0.41667 | 2.5763 | 1.9062 | 2.042
| 4029 | 0.32407 | 2.1525 | 2.125 | 2.1849
| 4030 | 0.25926 | 3.1695 | 1.125 | 2.1134
| 4031 | 0.42593 | 3.4068 | 1.4688 | 1.916
| 4032 | 0.43519 | 2.3051 | 1.875 | 2.0252
| 4033 | 0.37037 | 2.2881 | 1.2188 | 2
| 4034 | 0.28704 | 2.7966 | 2.0312 | 2.0378
| 4035 | 0.52778 | 2.5254 | 0.84375 | 2.042
| 4036 | 0.33333 | 3.0508 | 0.6875 | 2.2521
| 4037 | 0.43519 | 3 | 0.78125 | 1.8782
| 4038 | 0.41667 | 2.2034 | 1 | 1.9706
| 4039 | 0.40741 | 2.4915 | 1.4062 | 2.1345
| 4040 | 0.36111 | 2.7458 | 1.2812 | 1.9748
| 4041 | 0.43519 | 2.678 | 2 | 2.5588
| 4042 | 0.49074 | 3.1695 | 1.3438 | 1.9454
| 4043 | 0.48148 | 3.3051 | 1.2812 | 2.1176
| 4044 | 0.59259 | 2.8814 | 0.875 | 1.8403
| 4045 | 0.39815 | 2.5085 | 0.9375 | 2.3277
| 4046 | 0.44444 | 2.8644 | 1.3125 | 2.2941
| 4047 | 0.38889 | 2.6949 | 1.25 | 2.2395
| 4048 | 0.36111 | 2.7966 | 1.6875 | 1.8782
| 4049 | 0.39815 | 2.9661 | 0.75 | 2.2941
| 4050 | 0.5 | 2.5763 | 1.625 | 1.8908
| 4051 | 0.59259 | 2.5932 | 2 | 2.0294
| 4052 | 0.50926 | 2.5424 | 1.75 | 2.3235
| 4053 | 0.31481 | 2.1017 | 0.90625 | 1.8361
| 4054 | 0.31481 | 3.0508 | 1.1562 | 2.3866
| 4055 | 0.24074 | 2.9492 | 1.5312 | 2.021
| 4056 | 0.25 | 3.2542 | 1.5625 | 2.2731
| 4057 | 0.28704 | 3.7119 | 0.96875 | 2.1765
| 4058 | 0.38889 | 3.0678 | 1.4688 | 2.3067
| 4059 | 0.5 | 1.9831 | 0.90625 | 2.6933
| 4060 | 0.5 | 2.2203 | 1.4062 | 2.0294
| 4061 | 0.42593 | 2.8814 | 1.3125 | 2.3824
| 4062 | 0.50926 | 2.5763 | 1.5938 | 1.8487
| 4063 | 0.37963 | 2.678 | 0.75 | 1.9706
| 4064 | 0.34259 | 3.2373 | 0.90625 | 2.0672
| 4065 | 0.33333 | 2.6949 | 0.84375 | 1.8739
| 4066 | 0.38889 | 3 | 1.625 | 1.9454
| 4067 | 0.37037 | 3.4746 | 2.5312 | 1.9706
| 4068 | 0.40741 | 3.1864 | 1 | 2.2353
| 4069 | 0.39815 | 2.5763 | 1.9688 | 2.0966
| 4070 | 0.28704 | 1.8983 | 1.0312 | 2.3571
| 4071 | 0.30556 | 2.8814 | 1.375 | 2.2983
| 4072 | 0.56481 | 2.8644 | 2.0938 | 2.4328
| 4073 | 0.53704 | 2.5932 | 0.6875 | 2.2395
| 4074 | 0.38889 | 2.6102 | 0.59375 | 1.9118
| 4075 | 0.47222 | 2.7119 | 1.4688 | 2.3025
| 4076 | 0.33333 | 2.0678 | 1.7812 | 2.1303
| 4077 | 0.57407 | 3.0169 | 1.5 | 2.542
| 4078 | 0.37037 | 3.1864 | 1.4062 | 1.9748
| 4079 | 0.40741 | 3.2203 | 1.8125 | 2.2437
| 4080 | 0.25 | 2.8136 | 1.5312 | 1.9076
| 4081 | 0.37037 | 2.8475 | 1.1562 | 2.1134
| 4082 | 0.39815 | 2.3559 | 0.8125 | 2.0966
| 4083 | 0.37963 | 2.1525 | 1.125 | 2.1513
| 4084 | 0.34259 | 2.9831 | 1.5625 | 2.0462
| 4085 | 0.49074 | 2.1186 | 1.25 | 2.2521
| 4086 | 0.26852 | 2.322 | 1.125 | 2.2395
| 4087 | 0.38889 | 2.5254 | 2.5625 | 2.0042
| 4088 | 0.36111 | 2.1525 | 1.6875 | 1.8445
| 4089 | 0.40741 | 2.2712 | 1.1875 | 2.1765
| 4090 | 0.34259 | 2.5763 | 0.96875 | 2.2269
| 4091 | 0.25926 | 2.3051 | 1.3438 | 2.2773
| 4092 | 0.47222 | 3.2034 | 1.7812 | 2.1303
| 4093 | 0.33333 | 1.8983 | 1.3438 | 1.8782
| 4094 | 0.37963 | 2.6441 | 0.90625 | 1.7857
| 4095 | 0.37963 | 2.9322 | 1.5625 | 2.1387
| 4096 | 0.50926 | 2.5424 | 1.0312 | 2.084
| 4097 | 0.39815 | 2.0169 | 0.9375 | 2.5588
| 4098 | 0.46296 | 3.6102 | 1.7812 | 1.9034
| 4099 | 0.37963 | 2.4407 | 1.25 | 2.0588
| 4100 | 0.34259 | 2.9492 | 0.65625 | 2.2227
| 4101 | 0.40741 | 2.3559 | 1.6562 | 2
| 4102 | 0.30556 | 2.7119 | 1.3438 | 2.1092
| 4103 | 0.55556 | 2.7627 | 0.78125 | 2.2563
| 4104 | 0.34259 | 2.8644 | 1.2812 | 2.1176
| 4105 | 0.39815 | 3.4068 | 1.0938 | 1.8992
| 4106 | 0.42593 | 2.2881 | 1.4688 | 2.4286
| 4107 | 0.4537 | 2.2881 | 1.3438 | 1.7185
| 4108 | 0.42593 | 2.9153 | 1.5312 | 2.3067
| 4109 | 0.41667 | 2.4915 | 1.7188 | 2.4832
| 4110 | 0.37963 | 2.322 | 2.375 | 2.416
| 4111 | 0.38889 | 3.1695 | 1.1562 | 1.8487
| 4112 | 0.47222 | 2.678 | 1.125 | 1.8235
| 4113 | 0.39815 | 2.9153 | 0.5625 | 2.0798
| 4114 | 0.37037 | 2.7288 | 1.0938 | 1.9076
| 4115 | 0.52778 | 2.0169 | 1.375 | 2.1387
| 4116 | 0.4537 | 2.8475 | 1.1562 | 2.0084
| 4117 | 0.43519 | 2.4407 | 1.6562 | 1.8067
| 4118 | 0.37037 | 3.1525 | 1.4375 | 1.9328
| 4119 | 0.33333 | 2.8305 | 1.5 | 1.8571
| 4120 | 0.53704 | 3.1695 | 1.0312 | 1.9916
| 4121 | 0.2963 | 2.2712 | 1.625 | 2.0714
| 4122 | 0.49074 | 3.2034 | 1.25 | 1.8025
| 4123 | 0.51852 | 2.2712 | 0.96875 | 2.0084
| 4124 | 0.48148 | 3.1017 | 1.75 | 2.3151
| 4125 | 0.31481 | 3.339 | 3 | 2.3403
| 4126 | 0.39815 | 2.4746 | 1.375 | 2.2101
| 4127 | 0.66667 | 2.6102 | 1.625 | 2.1261
| 4128 | 0.21296 | 2.4576 | 1.3438 | 2.1387
| 4129 | 0.48148 | 3.5593 | 1.3125 | 1.9958
| 4130 | 0.46296 | 2.7288 | 1.3125 | 2.2059
| 4131 | 0.34259 | 2.3898 | 0.90625 | 2.0966
| 4132 | 0.47222 | 2.2712 | 1.3438 | 1.9076
| 4133 | 0.35185 | 3.1186 | 0.84375 | 2.3992
| 4134 | 0.37037 | 1.8305 | 1.625 | 1.979
| 4135 | 0.35185 | 3.0678 | 1.0938 | 2.084
| 4136 | 0.34259 | 2.6441 | 2.0938 | 2.1765
| 4137 | 0.40741 | 2.4915 | 1.2812 | 2.0462
| 4138 | 0.4537 | 2.4407 | 1.1875 | 2.0504
| 4139 | 0.4537 | 3.1186 | 0.875 | 1.9664
| 4140 | 0.26852 | 2.8475 | 1.4375 | 2.1303
| 4141 | 0.43519 | 2.3051 | 1.625 | 2.3109
| 4142 | 0.48148 | 2.3898 | 2 | 2.3613
| 4143 | 0.7037 | 2.2712 | 1.4375 | 1.9244
| 4144 | 0.48148 | 2.2542 | 1.1875 | 1.895
| 4145 | 0.55556 | 2.9153 | 1.1875 | 1.7647
| 4146 | 0.31481 | 2.5763 | 1.1875 | 1.9748
| 4147 | 0.64815 | 2.4746 | 1.1562 | 2.0336
| 4148 | 0.30556 | 3.4915 | 1.5625 | 2.2059
| 4149 | 0.39815 | 2.7966 | 2.0938 | 1.7731
| 4150 | 0.44444 | 2.4915 | 1.0625 | 2.6303
| 4151 | 0.30556 | 2.6949 | 1.875 | 2.2815
| 4152 | 0.51852 | 2.4237 | 0.90625 | 2.1891
| 4153 | 0.44444 | 2.678 | 0.90625 | 2.5882
| 4154 | 0.31481 | 2.8136 | 1.5938 | 1.9874
| 4155 | 0.46296 | 3.2542 | 1.5312 | 1.9244
| 4156 | 0.37963 | 3.4746 | 1.5312 | 2.084
| 4157 | 0.42593 | 2.3051 | 1.1875 | 2.0126
| 4158 | 0.41667 | 2.9153 | 1.0312 | 2.1681
| 4159 | 0.49074 | 2.6441 | 1.5625 | 2.3361
| 4160 | 0.42593 | 2.678 | 1.125 | 2.1555
| 4161 | 0.42593 | 2.7119 | 1.1875 | 1.9412
| 4162 | 0.37963 | 2.8814 | 1.125 | 2.0672
| 4163 | 0.2963 | 3.0339 | 1.3438 | 2.2437
| 4164 | 0.32407 | 1.9661 | 2.25 | 2.4286
| 4165 | 0.44444 | 2.1017 | 1.25 | 1.9958
| 4166 | 0.33333 | 2.8814 | 1.3125 | 2.042
| 4167 | 0.50926 | 2.8814 | 1.125 | 2.1345
| 4168 | 0.4537 | 2.7119 | 1.1562 | 2.1513
| 4169 | 0.61111 | 2.8305 | 1.75 | 2.0672
| 4170 | 0.32407 | 2.7627 | 1.625 | 2.2227
| 4171 | 0.28704 | 2.7797 | 0.96875 | 1.9874
| 4172 | 0.37037 | 2.7966 | 1.0938 | 1.9328
| 4173 | 0.35185 | 2.8983 | 1.5 | 2.1008
| 4174 | 0.36111 | 3 | 1.0938 | 1.8908
| 4175 | 0.40741 | 3.2203 | 2.0312 | 2.0252
| 4176 | 0.43519 | 3.5932 | 1.6875 | 1.9538
| 4177 | 0.48148 | 2.9831 | 2.0938 | 2.0714
| 4178 | 0.39815 | 2.6271 | 1.375 | 2.1513
| 4179 | 0.62037 | 2.8983 | 1.375 | 1.9958
| 4180 | 0.33333 | 3.2203 | 1.2188 | 2.0756
| 4181 | 0.47222 | 2.678 | 1.8125 | 2.105
| 4182 | 0.43519 | 3.1017 | 1.4688 | 2.1807
| 4183 | 0.35185 | 2.0339 | 2.125 | 1.9286
| 4184 | 0.47222 | 2.5763 | 1.375 | 2.2941
| 4185 | 0.43519 | 2.678 | 1.5938 | 2.5462
| 4186 | 0.39815 | 2.322 | 1.2812 | 2.0588
| 4187 | 0.62963 | 2.6271 | 1.25 | 1.9538
| 4188 | 0.43519 | 3.0169 | 0.96875 | 1.8697
| 4189 | 0.48148 | 2.5254 | 0.71875 | 1.9118
| 4190 | 0.40741 | 2.678 | 1.25 | 2.0966
| 4191 | 0.4537 | 2.8136 | 1.6562 | 2.3025
| 4192 | 0.4537 | 3.678 | 1.7812 | 2.2227
| 4193 | 0.62963 | 3.0508 | 1.2188 | 1.979
| 4194 | 0.38889 | 2.8136 | 1.6562 | 1.9832
| 4195 | 0.50926 | 2.6102 | 0.75 | 2.1849
| 4196 | 0.39815 | 3.4068 | 1.1562 | 2.3319
| 4197 | 0.34259 | 2.9492 | 1.0625 | 2.0588
| 4198 | 0.4537 | 2.6102 | 1.2812 | 1.7899
| 4199 | 0.38889 | 1.6441 | 1.75 | 2
| 4200 | 0.44444 | 3.0169 | 1.8438 | 1.8571
| 4201 | 0.48148 | 2.8475 | 1.1562 | 2.6513
| 4202 | 0.40741 | 2.661 | 1.3125 | 2.5504
| 4203 | 0.44444 | 3.0339 | 1.5312 | 1.8992
| 4204 | 0.33333 | 2.0339 | 1.25 | 2.0924
| 4205 | 0.36111 | 2.4915 | 1.375 | 2.1597
| 4206 | 0.38889 | 3.5254 | 1.2812 | 2.2227
| 4207 | 0.47222 | 2.8983 | 1.0938 | 2.0882
| 4208 | 0.5463 | 2.4915 | 0.6875 | 2.0126
| 4209 | 0.39815 | 2.3898 | 1.9062 | 2.1765
| 4210 | 0.5 | 3.2034 | 2.0312 | 1.9538
| 4211 | 0.40741 | 3.1695 | 1.75 | 1.8613
| 4212 | 0.37963 | 2.6949 | 1.6875 | 2.1008
| 4213 | 0.33333 | 2.7119 | 1.4062 | 1.7899
| 4214 | 0.64815 | 2.2373 | 1.25 | 1.9412
| 4215 | 0.27778 | 2.2373 | 2.9062 | 2.0672
| 4216 | 0.39815 | 2.9153 | 1.625 | 2.1429
| 4217 | 0.48148 | 3.8475 | 1.4688 | 2.0756
| 4218 | 0.49074 | 2.7458 | 1.5 | 1.9328
| 4219 | 0.26852 | 2.6102 | 1.5 | 1.7983
| 4220 | 0.44444 | 2.1186 | 0.90625 | 2.1765
| 4221 | 0.57407 | 2.5424 | 1.8438 | 2.2563
| 4222 | 0.41667 | 2.1695 | 0.8125 | 1.8067
| 4223 | 0.62037 | 3.5593 | 0.96875 | 2.4034
| 4224 | 0.38889 | 2.7458 | 1.9062 | 1.8571
| 4225 | 0.34259 | 2.4576 | 1.6875 | 1.9034
| 4226 | 0.51852 | 2.5593 | 2.2188 | 2.2143
| 4227 | 0.31481 | 2.8814 | 1.25 | 2.1387
| 4228 | 0.32407 | 2.5424 | 1.3125 | 1.937
| 4229 | 0.5 | 2.6271 | 1.6562 | 2.0924
| 4230 | 0.46296 | 2.7966 | 1.8438 | 1.9664
| 4231 | 0.47222 | 2.3898 | 2 | 2.0546
| 4232 | 0.37963 | 2.4068 | 0.78125 | 2.1092
| 4233 | 0.31481 | 2.6102 | 1.5312 | 1.9706
| 4234 | 0.40741 | 2.2881 | 0.96875 | 1.979
| 4235 | 0.46296 | 2.4068 | 1.0938 | 2.2059
| 4236 | 0.30556 | 2.8644 | 1.9688 | 2.3109
| 4237 | 0.36111 | 2.9661 | 1.7812 | 2.3655
| 4238 | 0.5 | 1.5932 | 0.8125 | 1.7815
| 4239 | 0.41667 | 2.5424 | 0.96875 | 2.3992
| 4240 | 0.39815 | 3.0847 | 0.84375 | 2.2437
| 4241 | 0.4537 | 2.4068 | 1.0312 | 1.9958
| 4242 | 0.43519 | 3.2034 | 1.375 | 2.1933
| 4243 | 0.37963 | 2.6102 | 1.5938 | 2.1849
| 4244 | 0.40741 | 1.9153 | 1 | 1.9034
| 4245 | 0.55556 | 2.2542 | 1.4062 | 2.1975
| 4246 | 0.25926 | 3.2034 | 1.9062 | 2.0588
| 4247 | 0.39815 | 2.0847 | 1.5938 | 2.2395
| 4248 | 0.49074 | 2.5085 | 1.125 | 1.8445
| 4249 | 0.26852 | 2.661 | 2.9375 | 2.3782
| 4250 | 0.41667 | 2.6102 | 1.1875 | 2.3235
| 4251 | 0.4537 | 2.661 | 1.2812 | 1.8361
| 4252 | 0.36111 | 2.2034 | 1.4375 | 2.0168
| 4253 | 0.35185 | 2.8305 | 1.1562 | 1.9832
| 4254 | 0.28704 | 2.1864 | 0.78125 | 2.2815
| 4255 | 0.43519 | 3.3559 | 1.4375 | 1.7479
| 4256 | 0.46296 | 2.5593 | 1 | 2.0336
| 4257 | 0.51852 | 3.5763 | 1.3438 | 1.9454
| 4258 | 0.46296 | 2.4746 | 0.90625 | 1.8067
| 4259 | 0.38889 | 3.1186 | 1.0312 | 1.7605
| 4260 | 0.47222 | 3.4407 | 1.5625 | 2.4748
| 4261 | 0.41667 | 3.1695 | 0.90625 | 1.7857
| 4262 | 0.37037 | 2.8305 | 1.3125 | 2.2521
| 4263 | 0.67593 | 3.4576 | 1.9688 | 2.063
| 4264 | 0.38889 | 3.0339 | 1.5938 | 1.7017
| 4265 | 0.41667 | 2.5763 | 1.9375 | 2.1218
| 4266 | 0.2037 | 3.0847 | 0.90625 | 2.1933
| 4267 | 0.57407 | 2.5085 | 2.2812 | 2.2269
| 4268 | 0.5 | 2.678 | 1.4375 | 1.8782
| 4269 | 0.32407 | 2.7627 | 1.0312 | 2.437
| 4270 | 0.40741 | 2.5424 | 0.84375 | 2.0168
| 4271 | 0.67593 | 2.4915 | 1.7188 | 2.2143
| 4272 | 0.44444 | 2.4237 | 1.125 | 1.7983
| 4273 | 0.43519 | 2.7797 | 1.0938 | 2.1134
| 4274 | 0.38889 | 2.4237 | 1.875 | 2.0966
| 4275 | 0.4537 | 2.4407 | 0.9375 | 2.4454
| 4276 | 0.40741 | 2.7966 | 1.6562 | 2.0504
| 4277 | 0.31481 | 2.6102 | 1.2188 | 2.2647
| 4278 | 0.51852 | 2.7288 | 1.125 | 2.042
| 4279 | 0.62963 | 2.8983 | 0.75 | 1.9874
| 4280 | 0.27778 | 2.2373 | 1.0938 | 2.4328
| 4281 | 0.28704 | 2.8136 | 1 | 1.9412
| 4282 | 0.58333 | 2.4237 | 0.90625 | 2.2101
| 4283 | 0.38889 | 2.7627 | 1.75 | 1.8866
| 4284 | 0.38889 | 2.3729 | 1.5625 | 2.1723
| 4285 | 0.49074 | 2.4576 | 1.625 | 1.8908
| 4286 | 0.25 | 2.4915 | 1.4375 | 2.3025
| 4287 | 0.67593 | 3.2712 | 1.625 | 2.1933
| 4288 | 0.46296 | 2.8136 | 1.7812 | 1.8908
| 4289 | 0.39815 | 2.5932 | 1.0938 | 1.8655
| 4290 | 0.37963 | 2.8136 | 1.4062 | 2.1092
| 4291 | 0.38889 | 2.8136 | 1.5938 | 2.2143
| 4292 | 0.34259 | 1.9661 | 1.5938 | 1.9538
| 4293 | 0.40741 | 3.2373 | 1.0625 | 2.0756
| 4294 | 0.48148 | 2.3051 | 1.5 | 2.0168
| 4295 | 0.48148 | 2.0847 | 1.625 | 2.2311
| 4296 | 0.40741 | 2.6949 | 1.0312 | 1.9202
| 4297 | 0.5 | 2.6102 | 1.5938 | 1.895
| 4298 | 0.36111 | 2.6949 | 1.2812 | 2.3193
| 4299 | 0.49074 | 2.8475 | 1.2188 | 2.3109
| 4300 | 0.41667 | 2.4407 | 1.5938 | 2.1261
| 4301 | 0.33333 | 2.4746 | 1.625 | 2.3193
| 4302 | 0.40741 | 2.9831 | 0.96875 | 2.1513
| 4303 | 0.37037 | 2.1695 | 1.0938 | 1.9034
| 4304 | 0.31481 | 2.4915 | 1.6875 | 1.9454
| 4305 | 0.39815 | 2.5763 | 1.6875 | 2.0084
| 4306 | 0.46296 | 2.3898 | 1.4062 | 2.4202
| 4307 | 0.38889 | 2.7119 | 2.0625 | 2.4412
| 4308 | 0.30556 | 2.4237 | 1.4062 | 1.9622
| 4309 | 0.51852 | 3.0339 | 3.0312 | 2.1849
| 4310 | 0.4537 | 2.4576 | 1.6875 | 2.1471
| 4311 | 0.53704 | 2.1356 | 1.3438 | 2.0882
| 4312 | 0.37037 | 2.3898 | 1.25 | 1.9916
| 4313 | 0.36111 | 1.9831 | 0.5625 | 2.0462
| 4314 | 0.55556 | 2.7119 | 1.125 | 2.2143
| 4315 | 0.44444 | 2.4576 | 0.8125 | 2.0084
| 4316 | 0.33333 | 3.1864 | 1 | 1.9706
| 4317 | 0.59259 | 2.7119 | 1.4375 | 2.3151
| 4318 | 0.34259 | 2.9322 | 1 | 2.2521
| 4319 | 0.47222 | 2.8305 | 0.75 | 2.063
| 4320 | 0.41667 | 3.3559 | 0.6875 | 2.4202
| 4321 | 0.48148 | 3.322 | 1.4375 | 1.9664
| 4322 | 0.39815 | 1.9153 | 1.4062 | 1.9034
| 4323 | 0.36111 | 2.3051 | 1.1562 | 1.9706
| 4324 | 0.49074 | 3.6271 | 2.1562 | 2.1849
| 4325 | 0.33333 | 2.322 | 1.5312 | 2.2185
| 4326 | 0.5 | 2.4237 | 1.25 | 1.7647
| 4327 | 0.40741 | 2.6271 | 2.2812 | 2.3319
| 4328 | 0.38889 | 2.2542 | 1.75 | 1.6681
| 4329 | 0.49074 | 2.661 | 1.625 | 2.042
| 4330 | 0.52778 | 2.2373 | 1.6562 | 2.3067
| 4331 | 0.36111 | 2.4746 | 1.2188 | 1.9706
| 4332 | 0.43519 | 2.2542 | 1.1562 | 2.2395
| 4333 | 0.38889 | 2.5932 | 0.90625 | 2.0042
| 4334 | 0.37037 | 2.8136 | 1.0312 | 2.3193
| 4335 | 0.4537 | 2.4746 | 1.5312 | 1.8739
| 4336 | 0.41667 | 2.4407 | 2.5312 | 2.1134
| 4337 | 0.37037 | 2.2373 | 0.5625 | 2.2353
| 4338 | 0.22222 | 2.1356 | 1.0312 | 2.105
| 4339 | 0.36111 | 2.661 | 2.5 | 1.9496
| 4340 | 0.4537 | 2.4915 | 0.9375 | 2.4076
| 4341 | 0.47222 | 2.2712 | 1.4375 | 1.979
| 4342 | 0.2963 | 2.3559 | 1.5312 | 2.1933
| 4343 | 0.27778 | 2.4237 | 1.4688 | 2.1303
| 4344 | 0.34259 | 2.678 | 1.125 | 2.1134
| 4345 | 0.43519 | 2.678 | 2 | 2.437
| 4346 | 0.49074 | 2.661 | 1.875 | 2.1008
| 4347 | 0.36111 | 3.2203 | 0.8125 | 2.1134
| 4348 | 0.5 | 3.0678 | 1.4688 | 1.958
| 4349 | 0.49074 | 2.7458 | 1.4375 | 2.0462
| 4350 | 0.56481 | 2.4237 | 1.0625 | 2.0252
| 4351 | 0.51852 | 3.1017 | 1.875 | 2.1008
| 4352 | 0.42593 | 2.661 | 1.1562 | 2.0924
| 4353 | 0.49074 | 2.6102 | 0.96875 | 2.0672
| 4354 | 0.42593 | 3.1525 | 1.6875 | 1.9916
| 4355 | 0.39815 | 2.7797 | 1.125 | 2.105
| 4356 | 0.40741 | 3.4068 | 1.125 | 2.0126
| 4357 | 0.40741 | 1.9661 | 1.125 | 2.1597
| 4358 | 0.25926 | 2.9661 | 1.625 | 2.1639
| 4359 | 0.38889 | 2.5424 | 0.59375 | 1.8908
| 4360 | 0.44444 | 2.2373 | 2.0625 | 2.3025
| 4361 | 0.5 | 2.2712 | 1.1875 | 2.2017
| 4362 | 0.36111 | 3.4407 | 0.8125 | 2.2479
| 4363 | 0.43519 | 3.4407 | 1.1875 | 2.3992
| 4364 | 0.31481 | 2.8983 | 1.4062 | 2.3403
| 4365 | 0.36111 | 2.2034 | 2.4375 | 1.8361
| 4366 | 0.41667 | 3.1525 | 1.3125 | 2.084
| 4367 | 0.40741 | 2.4915 | 0.5625 | 2.0672
| 4368 | 0.4537 | 2.5085 | 1.4688 | 2.1261
| 4369 | 0.37963 | 2.8136 | 1.1875 | 2.084
| 4370 | 0.5 | 2.6949 | 1 | 1.9958
| 4371 | 0.36111 | 2.4915 | 1.5312 | 2.2059
| 4372 | 0.35185 | 3 | 1.6875 | 2.1387
| 4373 | 0.42593 | 2.8644 | 1.0312 | 2.0882
| 4374 | 0.41667 | 2.8644 | 1.7188 | 1.7731
| 4375 | 0.36111 | 1.7627 | 1.5625 | 1.8487
| 4376 | 0.37037 | 2.3898 | 0.875 | 1.9412
| 4377 | 0.37037 | 3.0678 | 0.84375 | 1.9622
| 4378 | 0.50926 | 2.0169 | 1.3438 | 2.1303
| 4379 | 0.43519 | 2.7458 | 1.25 | 1.9622
| 4380 | 0.55556 | 2.4068 | 0.6875 | 2.2311
| 4381 | 0.35185 | 2.7966 | 0.84375 | 2.4034
| 4382 | 0.40741 | 2.0678 | 0.84375 | 1.7437
| 4383 | 0.31481 | 2.5085 | 0.96875 | 2.0294
| 4384 | 0.32407 | 2.1864 | 1.125 | 2.2563
| 4385 | 0.37037 | 2.2542 | 1 | 1.6513
| 4386 | 0.56481 | 2.4068 | 1.4062 | 1.8235
| 4387 | 0.4537 | 2.2881 | 0.6875 | 1.9076
| 4388 | 0.43519 | 2.5085 | 2 | 2.1555
| 4389 | 0.44444 | 2.5763 | 1.2812 | 2.0882
| 4390 | 0.42593 | 2.2203 | 1.9062 | 2.0714
| 4391 | 0.36111 | 3.8305 | 0.875 | 2.0462
| 4392 | 0.37963 | 2.5254 | 0.90625 | 2.1513
| 4393 | 0.63889 | 2.2034 | 1.1562 | 2.1429
| 4394 | 0.30556 | 2.4237 | 1.1875 | 2.4034
| 4395 | 0.62037 | 2.1695 | 1.4375 | 2.0294
| 4396 | 0.49074 | 2.2881 | 1.375 | 2.1303
| 4397 | 0.50926 | 2.5763 | 1.0312 | 2.084
| 4398 | 0.2963 | 2.9831 | 1.3125 | 1.937
| 4399 | 0.51852 | 2.8136 | 0.90625 | 2.0504
| 4400 | 0.57407 | 2.8983 | 0.90625 | 2.1261
| 4401 | 0.50926 | 2.2034 | 1.0312 | 2.4874
| 4402 | 0.35185 | 3.1525 | 1.5938 | 2.1218
| 4403 | 0.33333 | 2.339 | 1.875 | 2.063
| 4404 | 0.39815 | 3.6102 | 1.7812 | 2.0168
| 4405 | 0.58333 | 2.0678 | 0.90625 | 2.2227
| 4406 | 0.49074 | 3.661 | 0.78125 | 1.8193
| 4407 | 0.41667 | 2.2034 | 1.5312 | 2.1134
| 4408 | 0.39815 | 2.4915 | 1.0938 | 2.1134
| 4409 | 0.33333 | 2.4746 | 2.0312 | 2.0042
| 4410 | 0.50926 | 2.2712 | 0.8125 | 2.5
| 4411 | 0.43519 | 2.4746 | 0.5625 | 2.0756
| 4412 | 0.42593 | 2.2881 | 1.3438 | 2.084
| 4413 | 0.28704 | 2.5763 | 1 | 2.2899
| 4414 | 0.43519 | 2.8475 | 0.84375 | 2.0882
| 4415 | 0.35185 | 2.2542 | 1.4062 | 2.1008
| 4416 | 0.49074 | 2.4237 | 1.125 | 2.2857
| 4417 | 0.53704 | 2 | 1.8125 | 2.5882
| 4418 | 0.44444 | 2.5424 | 1.5312 | 1.9748
| 4419 | 0.25 | 2.6271 | 0.875 | 1.7605
| 4420 | 0.34259 | 2.5763 | 0.96875 | 2.3403
| 4421 | 0.31481 | 2.4068 | 1.1875 | 2.1765
| 4422 | 0.36111 | 3 | 1.1562 | 1.7857
| 4423 | 0.52778 | 2.3729 | 1.25 | 1.8151
| 4424 | 0.37037 | 3.1525 | 1.5625 | 1.8571
| 4425 | 0.44444 | 3.1186 | 1.1562 | 2.2101
| 4426 | 0.32407 | 1.9661 | 1.7812 | 1.8403
| 4427 | 0.48148 | 2.1695 | 1.25 | 2.1849
| 4428 | 0.40741 | 3.9492 | 2.0938 | 2.2269
| 4429 | 0.37037 | 2.4407 | 2.6875 | 2.1723
| 4430 | 0.4537 | 2.1186 | 2.2188 | 2.1303
| 4431 | 0.31481 | 2.6441 | 1.2188 | 2.8613
| 4432 | 0.5 | 3.5424 | 1.1875 | 2.042
| 4433 | 0.33333 | 2.5593 | 1.375 | 2.0966
| 4434 | 0.44444 | 2.4237 | 2.0938 | 2.0924
| 4435 | 0.46296 | 2.339 | 1.3125 | 2.1218
| 4436 | 0.5463 | 2.5085 | 0.71875 | 2.4034
| 4437 | 0.41667 | 2.8136 | 1.8438 | 1.8782
| 4438 | 0.23148 | 2.5763 | 1.5312 | 2.0042
| 4439 | 0.39815 | 2.6102 | 1.7188 | 2.1555
| 4440 | 0.51852 | 3.4576 | 1.4375 | 2.2731
| 4441 | 0.37037 | 2.5932 | 2.0938 | 2.2101
| 4442 | 0.33333 | 2.4746 | 1.9062 | 2.2983
| 4443 | 0.36111 | 2.0339 | 0.90625 | 1.8529
| 4444 | 0.49074 | 3.5424 | 1.4688 | 1.895
| 4445 | 0.39815 | 2.3729 | 1.125 | 2.0462
| 4446 | 0.4537 | 2.9153 | 1.5 | 2.6345
| 4447 | 0.43519 | 2.8475 | 1.0938 | 2.2311
| 4448 | 0.25 | 3.2203 | 1.9375 | 1.9244
| 4449 | 0.48148 | 2.9831 | 0.65625 | 1.8992
| 4450 | 0.59259 | 2.339 | 1.9062 | 2.1975
| 4451 | 0.38889 | 3.0847 | 1.6875 | 1.9286
| 4452 | 0.39815 | 3.0508 | 0.9375 | 2.2269
| 4453 | 0.37037 | 2.8644 | 1.1562 | 1.7185
| 4454 | 0.52778 | 2.7966 | 1.3125 | 2.395
| 4455 | 0.4537 | 2.8983 | 0.90625 | 2.0588
| 4456 | 0.55556 | 2.1186 | 2.0625 | 1.9202
| 4457 | 0.48148 | 3.2203 | 1.125 | 2.0336
| 4458 | 0.5 | 2 | 1.625 | 2.1387
| 4459 | 0.35185 | 2.1017 | 1.0312 | 2.0084
| 4460 | 0.48148 | 2.9661 | 0.78125 | 2.1303
| 4461 | 0.35185 | 2.9153 | 1.1875 | 1.9202
| 4462 | 0.62037 | 3.4068 | 1.2188 | 2.1218
| 4463 | 0.28704 | 2.7627 | 0.65625 | 2.0714
| 4464 | 0.30556 | 3 | 1.7188 | 2.2899
| 4465 | 0.75 | 2.2373 | 1.8125 | 2.1555
| 4466 | 0.42593 | 2.0847 | 1.1875 | 2.1555
| 4467 | 0.28704 | 3.1864 | 1.4375 | 2.2983
| 4468 | 0.55556 | 2.8475 | 1.5312 | 1.895
| 4469 | 0.43519 | 3.0678 | 1.25 | 2.1933
| 4470 | 0.36111 | 2.678 | 2.25 | 2.4244
| 4471 | 0.36111 | 2.7966 | 1.6875 | 2.1765
| 4472 | 0.58333 | 2.6271 | 1.9062 | 1.9496
| 4473 | 0.37963 | 2.339 | 1.5625 | 2.1513
| 4474 | 0.38889 | 2.5763 | 1.25 | 2.1891
| 4475 | 0.40741 | 2.6949 | 1.5 | 2.2353
| 4476 | 0.28704 | 3.322 | 1 | 2.084
| 4477 | 0.37037 | 2.4576 | 0.90625 | 1.8025
| 4478 | 0.53704 | 2.2712 | 1.8438 | 1.9244
| 4479 | 0.40741 | 2.2373 | 1.6562 | 2.3277
| 4480 | 0.36111 | 3.1525 | 1.9062 | 2.1681
| 4481 | 0.65741 | 3.4068 | 1.4375 | 2.0546
| 4482 | 0.27778 | 3.5254 | 2.0938 | 1.9916
| 4483 | 0.34259 | 1.9661 | 1.6562 | 2.1008
| 4484 | 0.33333 | 2.5932 | 0.9375 | 2.063
| 4485 | 0.28704 | 2.2712 | 1 | 2.0462
| 4486 | 0.4537 | 3.0847 | 1.5 | 1.9412
| 4487 | 0.33333 | 2.0847 | 0.75 | 1.8319
| 4488 | 0.59259 | 2.9661 | 1.875 | 2.0714
| 4489 | 0.5463 | 2.9153 | 1.3438 | 2.2437
| 4490 | 0.43519 | 3.2712 | 0.84375 | 1.7017
| 4491 | 0.48148 | 2.4068 | 1.1562 | 1.6975
| 4492 | 0.33333 | 2.4576 | 1.2188 | 2.1218
| 4493 | 0.50926 | 2.8305 | 1.3125 | 2.2353
| 4494 | 0.42593 | 2.2203 | 1.1562 | 1.8025
| 4495 | 0.5463 | 3.0847 | 1.0625 | 2.1261
| 4496 | 0.34259 | 2.339 | 1.4375 | 1.8445
| 4497 | 0.46296 | 2.4915 | 0.8125 | 2.0966
| 4498 | 0.34259 | 3 | 1.5625 | 2.1933
| 4499 | 0.5463 | 3.1695 | 1.4375 | 2.2185
| 4500 | 0.48148 | 2.9492 | 0.8125 | 2.3866
| 4501 | 0.47222 | 2.4576 | 1.1875 | 2.0462
| 4502 | 0.41667 | 2.9492 | 2.1562 | 2.021
| 4503 | 0.4537 | 2.2881 | 1.2188 | 2.3319
| 4504 | 0.31481 | 3 | 1.4062 | 1.9706
| 4505 | 0.47222 | 2.322 | 1.1562 | 2.3655
| 4506 | 0.48148 | 2.4237 | 1.0938 | 1.8487
| 4507 | 0.28704 | 3.2034 | 1.2812 | 2.3655
| 4508 | 0.28704 | 2.7119 | 1.1875 | 2.1387
| 4509 | 0.43519 | 2.2712 | 0.96875 | 1.9286
| 4510 | 0.47222 | 3.1525 | 1.4688 | 2.0546
| 4511 | 0.33333 | 2.5763 | 1.5938 | 1.9916
| 4512 | 0.4537 | 2.8305 | 1.4375 | 2.1681
| 4513 | 0.40741 | 3.1356 | 1.2812 | 1.937
| 4514 | 0.36111 | 2.3559 | 1 | 2.0336
| 4515 | 0.36111 | 2.9661 | 1.5312 | 1.8908
| 4516 | 0.40741 | 2.2881 | 1.9062 | 2.1723
| 4517 | 0.4537 | 2.3898 | 2.0938 | 2.0504
| 4518 | 0.48148 | 2.1525 | 1.3125 | 2.1345
| 4519 | 0.37037 | 2.3559 | 1.8125 | 2.3529
| 4520 | 0.41667 | 2.8644 | 1.2188 | 1.9496
| 4521 | 0.28704 | 2.678 | 0.84375 | 2.1092
| 4522 | 0.59259 | 2.5085 | 1.7188 | 2.2311
| 4523 | 0.37963 | 2.5254 | 2.5938 | 2.1849
| 4524 | 0.42593 | 2.339 | 1.1562 | 2.2353
| 4525 | 0.38889 | 2.3729 | 0.96875 | 2.3782
| 4526 | 0.35185 | 2.8814 | 1.1562 | 2.0252
| 4527 | 0.4537 | 2.5932 | 1.0625 | 2.1387
| 4528 | 0.61111 | 2.322 | 1.1875 | 2.1975
| 4529 | 0.35185 | 2.5085 | 1.9062 | 1.9034
| 4530 | 0.49074 | 2.5254 | 1.5312 | 2.0168
| 4531 | 0.53704 | 2.661 | 1.2812 | 2.4328
| 4532 | 0.4537 | 2.678 | 0.625 | 2.084
| 4533 | 0.36111 | 3.0339 | 1.0625 | 2.1218
| 4534 | 0.46296 | 3.0339 | 0.71875 | 2.8277
| 4535 | 0.36111 | 3.0678 | 1.0938 | 2.063
| 4536 | 0.35185 | 3.3898 | 1.125 | 2.1303
| 4537 | 0.35185 | 2.4576 | 1.9375 | 2.1261
| 4538 | 0.37963 | 3.7627 | 2.5938 | 2
| 4539 | 0.56481 | 3 | 1.4062 | 1.9958
| 4540 | 0.38889 | 3.1186 | 1.5312 | 2.3739
| 4541 | 0.43519 | 3.4915 | 1.2812 | 1.916
| 4542 | 0.53704 | 2.2542 | 0.8125 | 1.9664
| 4543 | 0.34259 | 2.5254 | 1 | 1.7857
| 4544 | 0.60185 | 2.5763 | 2.3125 | 1.8193
| 4545 | 0.4537 | 3.0169 | 0.625 | 1.9496
| 4546 | 0.33333 | 2.3898 | 1.125 | 1.979
| 4547 | 0.37037 | 2.7458 | 0.40625 | 2.0672
| 4548 | 0.52778 | 2.5254 | 1.1875 | 2.1092
| 4549 | 0.43519 | 2.8305 | 1.5938 | 1.937
| 4550 | 0.4537 | 3.1864 | 1.5 | 1.9748
| 4551 | 0.42593 | 3.0339 | 1.6562 | 1.9916
| 4552 | 0.47222 | 2.8136 | 1.4062 | 1.8109
| 4553 | 0.41667 | 1.9492 | 0.84375 | 2.0924
| 4554 | 0.41667 | 3.7288 | 1.4688 | 2.1134
| 4555 | 0.42593 | 2.8136 | 1.2812 | 2.2647
| 4556 | 0.33333 | 2.5763 | 0.9375 | 2.2857
| 4557 | 0.42593 | 2.5254 | 1.9375 | 1.8613
| 4558 | 0.24074 | 2.2881 | 1.6562 | 1.9832
| 4559 | 0.25926 | 3.0847 | 1.4062 | 2.3571
| 4560 | 0.2963 | 2.0169 | 2.0938 | 1.9286
| 4561 | 0.30556 | 3.661 | 1.3438 | 1.7563
| 4562 | 0.37963 | 3.1017 | 1.5938 | 2.2017
| 4563 | 0.44444 | 2.8475 | 1.4688 | 2.2689
| 4564 | 0.63889 | 2.3898 | 1.75 | 2.0252
| 4565 | 0.31481 | 2.1695 | 1.25 | 2.0924
| 4566 | 0.35185 | 2.322 | 1.1562 | 2.6975
| 4567 | 0.36111 | 2.9831 | 1.1875 | 1.9076
| 4568 | 0.39815 | 2.6949 | 1.375 | 2.3571
| 4569 | 0.5 | 3.0339 | 1.4062 | 1.8908
| 4570 | 0.24074 | 2.5763 | 0.96875 | 2.105
| 4571 | 0.47222 | 2.9322 | 1.2188 | 2.0966
| 4572 | 0.41667 | 3.0847 | 1.0625 | 1.9622
| 4573 | 0.37037 | 2.8983 | 0.8125 | 1.7815
| 4574 | 0.37037 | 2.7966 | 1.3125 | 2.2353
| 4575 | 0.44444 | 2.4237 | 1.875 | 1.8403
| 4576 | 0.56481 | 2.7627 | 1.3438 | 1.9286
| 4577 | 0.40741 | 3.2542 | 1.9375 | 2.1891
| 4578 | 0.59259 | 3.3051 | 1.0938 | 2.3193
| 4579 | 0.42593 | 3.0339 | 1.3125 | 2.063
| 4580 | 0.5 | 2.2203 | 1.1875 | 2.2395
| 4581 | 0.4537 | 2.7458 | 1.4375 | 1.8361
| 4582 | 0.48148 | 2.4068 | 1.4062 | 1.8613
| 4583 | 0.43519 | 2.5593 | 1.1875 | 2.6513
| 4584 | 0.42593 | 2.6271 | 1.6562 | 2.3824
| 4585 | 0.46296 | 2.7119 | 2.125 | 1.9118
| 4586 | 0.50926 | 2.8136 | 0.96875 | 2.0084
| 4587 | 0.40741 | 2.8983 | 1.75 | 2.1261
| 4588 | 0.31481 | 2.2373 | 0.9375 | 1.7185
| 4589 | 0.51852 | 2.678 | 1.375 | 1.8193
| 4590 | 0.46296 | 2.6271 | 1 | 2.7479
| 4591 | 0.48148 | 2.5254 | 1.4062 | 2.0756
| 4592 | 0.42593 | 2.3729 | 1.75 | 2.3319
| 4593 | 0.5463 | 3.2203 | 1.25 | 2.2059
| 4594 | 0.4537 | 2.0339 | 0.875 | 1.8193
| 4595 | 0.44444 | 2.8136 | 1.1875 | 2.3445
| 4596 | 0.4537 | 2.0508 | 2 | 2.0798
| 4597 | 0.36111 | 3.1356 | 1.1562 | 1.9916
| 4598 | 0.40741 | 2.9322 | 2 | 2.0672
| 4599 | 0.5 | 2.2034 | 1.4062 | 1.9538
| 4600 | 0.40741 | 2.7458 | 1.5625 | 2.084
| 4601 | 0.30556 | 2.7288 | 1.6875 | 1.8445
| 4602 | 0.40741 | 2.6949 | 1.25 | 2.1555
| 4603 | 0.42593 | 2.7288 | 1.0312 | 2.1134
| 4604 | 0.41667 | 3.0847 | 1.3125 | 2.0042
| 4605 | 0.39815 | 2.8305 | 1.7812 | 2.0756
| 4606 | 0.51852 | 2.8983 | 1.25 | 1.9622
| 4607 | 0.2037 | 2.6441 | 1.7188 | 2.1471
| 4608 | 0.32407 | 2.7458 | 1.375 | 2.0966
| 4609 | 0.32407 | 2.5424 | 0.84375 | 2.0252
| 4610 | 0.42593 | 2.7966 | 1.9375 | 1.9244
| 4611 | 0.50926 | 2.4237 | 1.1875 | 2.3739
| 4612 | 0.32407 | 2.5763 | 1.4688 | 2.2353
| 4613 | 0.46296 | 2.5424 | 1.5312 | 2.0168
| 4614 | 0.36111 | 3 | 1.2188 | 2.2353
| 4615 | 0.44444 | 2.1356 | 1.3438 | 1.937
| 4616 | 0.23148 | 3.4407 | 1.5625 | 2.0966
| 4617 | 0.37037 | 2.3051 | 2.1875 | 2.2773
| 4618 | 0.48148 | 2.4237 | 2.125 | 1.8277
| 4619 | 0.47222 | 2.8644 | 2.25 | 2.2059
| 4620 | 0.32407 | 2.4407 | 2.4062 | 2.1261
| 4621 | 0.5 | 2.1695 | 0.9375 | 1.9622
| 4622 | 0.53704 | 2.6949 | 1.0938 | 1.9244
| 4623 | 0.33333 | 2.9661 | 1.1562 | 1.8992
| 4624 | 0.48148 | 2.5254 | 0.9375 | 2.4328
| 4625 | 0.44444 | 1.5085 | 1.2188 | 2.0924
| 4626 | 0.52778 | 2.4915 | 1.875 | 2.1597
| 4627 | 0.50926 | 2.4237 | 0.96875 | 2.1261
| 4628 | 0.48148 | 2.8983 | 1.2812 | 2.0672
| 4629 | 0.43519 | 3.4068 | 1.1875 | 1.8403
| 4630 | 0.46296 | 2.9153 | 1.625 | 2.3109
| 4631 | 0.43519 | 3 | 1.7188 | 2.1218
| 4632 | 0.40741 | 2.9661 | 1.7188 | 2.0378
| 4633 | 0.41667 | 1.8983 | 0.96875 | 2.4034
| 4634 | 0.37963 | 2.2034 | 1.875 | 2
| 4635 | 0.41667 | 2.9153 | 1.3438 | 2.042
| 4636 | 0.43519 | 2.3898 | 1.2812 | 2.2185
| 4637 | 0.4537 | 1.9322 | 0.9375 | 2.2101
| 4638 | 0.35185 | 2.9153 | 0.71875 | 1.9496
| 4639 | 0.44444 | 3.1695 | 0.90625 | 2.1345
| 4640 | 0.47222 | 2.5593 | 1.2812 | 1.8908
| 4641 | 0.35185 | 2.6102 | 1.4062 | 2.1807
| 4642 | 0.48148 | 3.4576 | 1 | 1.9496
| 4643 | 0.37963 | 3.3559 | 1.2188 | 2.1765
| 4644 | 0.43519 | 2.8814 | 1.4062 | 2.2059
| 4645 | 0.56481 | 1.8475 | 0.59375 | 2.084
| 4646 | 0.47222 | 2.7966 | 1.5625 | 2.3067
| 4647 | 0.46296 | 2.5932 | 1.7812 | 1.9748
| 4648 | 0.28704 | 2.9831 | 1.5625 | 2.1471
| 4649 | 0.38889 | 2.7797 | 1.2188 | 1.9202
| 4650 | 0.39815 | 2.9322 | 1.2812 | 1.7899
| 4651 | 0.47222 | 2.8814 | 1.25 | 2.1807
| 4652 | 0.36111 | 2.3898 | 1.7188 | 2.2479
| 4653 | 0.37037 | 2.4407 | 1.4688 | 2.1513
| 4654 | 0.47222 | 2.9492 | 1.125 | 1.979
| 4655 | 0.41667 | 2.2881 | 1.75 | 2.4118
| 4656 | 0.36111 | 3 | 1.375 | 2.0126
| 4657 | 0.41667 | 3.661 | 1.1562 | 1.9118
| 4658 | 0.48148 | 2.2034 | 1.9375 | 1.9874
| 4659 | 0.32407 | 2.661 | 1.7812 | 2.1387
| 4660 | 0.39815 | 2.5593 | 1.9375 | 2.2857
| 4661 | 0.32407 | 3.1017 | 1.125 | 1.7479
| 4662 | 0.37037 | 2.7288 | 1.9688 | 1.916
| 4663 | 0.24074 | 3.1525 | 0.84375 | 2.1303
| 4664 | 0.57407 | 2.6102 | 0.84375 | 2.2437
| 4665 | 0.51852 | 2.678 | 1.3125 | 2.0546
| 4666 | 0.42593 | 2.9322 | 0.96875 | 2.3025
| 4667 | 0.31481 | 3.4068 | 1.2188 | 2.0714
| 4668 | 0.43519 | 2.1186 | 1.7188 | 2.0168
| 4669 | 0.37037 | 2.8305 | 1.8125 | 1.9412
| 4670 | 0.36111 | 2.5932 | 1.2812 | 2.063
| 4671 | 0.35185 | 2.6102 | 1.7188 | 2.1765
| 4672 | 0.32407 | 1.8305 | 1.5 | 1.6975
| 4673 | 0.30556 | 3 | 1.4375 | 2.1471
| 4674 | 0.32407 | 3.339 | 1.9688 | 1.9328
| 4675 | 0.44444 | 2.0339 | 1.6875 | 1.9328
| 4676 | 0.48148 | 2.5254 | 1.1875 | 2.1218
| 4677 | 0.31481 | 1.7627 | 1.375 | 2.0042
| 4678 | 0.35185 | 2.5593 | 0.96875 | 2.0756
| 4679 | 0.31481 | 2.8644 | 1.125 | 2.3866
| 4680 | 0.32407 | 3.339 | 1.8125 | 2.1765
| 4681 | 0.43519 | 2.8475 | 1.5312 | 2.1471
| 4682 | 0.38889 | 2.1864 | 1.0625 | 1.9412
| 4683 | 0.37963 | 2.7627 | 1.6875 | 1.9076
| 4684 | 0.48148 | 3 | 1.5 | 2.042
| 4685 | 0.46296 | 2.1186 | 0.84375 | 2.1681
| 4686 | 0.34259 | 2.7458 | 1.0312 | 2.0714
| 4687 | 0.52778 | 2.1356 | 1.3125 | 2.3277
| 4688 | 0.35185 | 3 | 1.375 | 2.2311
| 4689 | 0.43519 | 2.5593 | 1.4688 | 1.7899
| 4690 | 0.41667 | 2.2034 | 1.1562 | 1.8277
| 4691 | 0.44444 | 2.5763 | 1.4688 | 2.2017
| 4692 | 0.40741 | 2.8814 | 1.4062 | 2.1387
| 4693 | 0.34259 | 2.5085 | 1.7188 | 2.2479
| 4694 | 0.55556 | 3.3051 | 1.2188 | 2.0378
| 4695 | 0.32407 | 3.4068 | 1.0938 | 2.0294
| 4696 | 0.42593 | 2.8983 | 1.2188 | 2.0252
| 4697 | 0.38889 | 2.7627 | 1.2188 | 1.9748
| 4698 | 0.38889 | 2.4407 | 1.3125 | 1.7479
| 4699 | 0.34259 | 2.4407 | 2 | 2.1303
| 4700 | 0.39815 | 2.6949 | 0.78125 | 2.1429
| 4701 | 0.55556 | 3.2542 | 1.0625 | 1.8908
| 4702 | 0.39815 | 2.2712 | 0.90625 | 2.3571
| 4703 | 0.46296 | 2.4576 | 0.71875 | 2.1429
| 4704 | 0.36111 | 2.7119 | 1.6875 | 2.2311
| 4705 | 0.40741 | 3.1695 | 1.0312 | 1.9664
| 4706 | 0.35185 | 2.0678 | 1.5625 | 2.0714
| 4707 | 0.47222 | 2.3559 | 1.5938 | 2.0462
| 4708 | 0.50926 | 1.9492 | 1.625 | 1.7899
| 4709 | 0.37963 | 3.2034 | 1.875 | 1.9622
| 4710 | 0.50926 | 2.339 | 1.875 | 2.3193
| 4711 | 0.36111 | 2.7119 | 0.96875 | 1.9202
| 4712 | 0.40741 | 2.4576 | 1 | 2.2353
| 4713 | 0.42593 | 3.0678 | 0.90625 | 1.6555
| 4714 | 0.40741 | 3.2203 | 2.3438 | 1.8908
| 4715 | 0.53704 | 2.7627 | 1.3438 | 2.0294
| 4716 | 0.25 | 2.7458 | 2.375 | 2.1849
| 4717 | 0.36111 | 2.1186 | 0.78125 | 2.0924
| 4718 | 0.42593 | 2.8305 | 0.71875 | 2.479
| 4719 | 0.37037 | 3.2542 | 1.375 | 2.0798
| 4720 | 0.48148 | 2.7119 | 0.90625 | 2.063
| 4721 | 0.62963 | 2.5932 | 1.4688 | 1.916
| 4722 | 0.53704 | 2.6949 | 1.0938 | 1.8235
| 4723 | 0.42593 | 3.1864 | 1.375 | 1.979
| 4724 | 0.34259 | 2.678 | 0.9375 | 2.0714
| 4725 | 0.52778 | 2.6441 | 1.9375 | 2.1345
| 4726 | 0.42593 | 2.7797 | 1.0625 | 2.3487
| 4727 | 0.34259 | 3.1186 | 2.3438 | 2.042
| 4728 | 0.31481 | 2.0508 | 0.71875 | 2.0546
| 4729 | 0.36111 | 2.4915 | 1.5625 | 2.2437
| 4730 | 0.36111 | 2.7627 | 1.9375 | 2.0798
| 4731 | 0.52778 | 3.0678 | 2.625 | 1.9748
| 4732 | 0.24074 | 2.4746 | 1.5625 | 2.0588
| 4733 | 0.55556 | 2.7458 | 1.5938 | 2.0798
| 4734 | 0.27778 | 2.678 | 1.6875 | 2.0042
| 4735 | 0.44444 | 2.3051 | 1.1875 | 2.5714
| 4736 | 0.34259 | 2.4576 | 1.6562 | 2.1387
| 4737 | 0.31481 | 2.1017 | 1.125 | 1.8361
| 4738 | 0.41667 | 3.2203 | 1.4688 | 2.2185
| 4739 | 0.35185 | 2.7119 | 1.625 | 2.1723
| 4740 | 0.50926 | 2.4237 | 1.4062 | 2.0462
| 4741 | 0.56481 | 2.322 | 1.8125 | 2.3992
| 4742 | 0.39815 | 1.9661 | 1.8438 | 2.5504
| 4743 | 0.39815 | 2.2712 | 2.125 | 2.0336
| 4744 | 0.42593 | 2.2881 | 0.71875 | 2.1639
| 4745 | 0.55556 | 3.0339 | 1.4688 | 2.0084
| 4746 | 0.52778 | 3.0169 | 0.78125 | 2.1134
| 4747 | 0.37963 | 1.9831 | 1.5625 | 1.958
| 4748 | 0.31481 | 2.2203 | 1.4375 | 2.1555
| 4749 | 0.39815 | 2.4746 | 1.3125 | 2.0042
| 4750 | 0.40741 | 2.9661 | 0.75 | 2.0672
| 4751 | 0.52778 | 3.0169 | 1.75 | 2.3529
| 4752 | 0.46296 | 3.1525 | 1.8125 | 2.2101
| 4753 | 0.5 | 2.3559 | 1.5938 | 1.7815
| 4754 | 0.32407 | 2.2373 | 1.25 | 2.2647
| 4755 | 0.35185 | 2.5763 | 1.4688 | 2.021
| 4756 | 0.44444 | 2.4746 | 0.6875 | 2.2227
| 4757 | 0.38889 | 2.8136 | 1.2812 | 2.0504
| 4758 | 0.52778 | 2.7458 | 0.84375 | 2.3824
| 4759 | 0.36111 | 1.9661 | 1.3438 | 2.0504
| 4760 | 0.37963 | 3.4237 | 1.5312 | 1.9412
| 4761 | 0.48148 | 3.3729 | 1.7188 | 2.1261
| 4762 | 0.24074 | 3.1695 | 1 | 2.1933
| 4763 | 0.34259 | 2.2542 | 2 | 2.0168
| 4764 | 0.41667 | 2.5763 | 0.9375 | 2.0504
| 4765 | 0.4537 | 1.8814 | 1.1562 | 2.3571
| 4766 | 0.4537 | 1.9831 | 1.0312 | 2.105
| 4767 | 0.37963 | 2.5763 | 2.2188 | 2.021
| 4768 | 0.32407 | 1.7627 | 1.4375 | 2.0504
| 4769 | 0.4537 | 3.2373 | 1.8438 | 2.1513
| 4770 | 0.65741 | 2.2034 | 1.5625 | 2.1429
| 4771 | 0.37963 | 2.6102 | 1.0938 | 2.2395
| 4772 | 0.49074 | 2.7966 | 2 | 2.2353
| 4773 | 0.37963 | 2.5593 | 1.5938 | 2.2353
| 4774 | 0.46296 | 2.8814 | 1.2812 | 1.7773
| 4775 | 0.46296 | 3.1356 | 1.6562 | 1.9118
| 4776 | 0.43519 | 2.3898 | 1.2188 | 2.2143
| 4777 | 0.47222 | 2.7288 | 1.3438 | 2.0966
| 4778 | 0.4537 | 2.5085 | 1.125 | 2.3487
| 4779 | 0.49074 | 2.9153 | 1.7188 | 1.6975
| 4780 | 0.50926 | 2.661 | 1.875 | 1.9202
| 4781 | 0.28704 | 2.6102 | 0.75 | 2.0588
| 4782 | 0.22222 | 2.8644 | 1.75 | 2.458
| 4783 | 0.39815 | 2.6271 | 1.7188 | 2.1008
| 4784 | 0.43519 | 3.0339 | 1.5312 | 2.2017
| 4785 | 0.32407 | 2.7119 | 1.5 | 2.1513
| 4786 | 0.47222 | 2.6271 | 1.6875 | 2.4958
| 4787 | 0.35185 | 2.9492 | 1.5 | 2.2269
| 4788 | 0.34259 | 2.2373 | 0.8125 | 2.0252
| 4789 | 0.43519 | 3.2034 | 1.4375 | 1.9034
| 4790 | 0.53704 | 2.8305 | 1.5625 | 2.2059
| 4791 | 0.58333 | 2.339 | 1.5 | 1.9664
| 4792 | 0.37037 | 2.9153 | 1.0312 | 2.2941
| 4793 | 0.34259 | 3.3898 | 1.0312 | 2.3824
| 4794 | 0.41667 | 2.4746 | 0.96875 | 2.1723
| 4795 | 0.41667 | 3.4237 | 2.25 | 2.3571
| 4796 | 0.51852 | 2.6441 | 1.0625 | 2.3739
| 4797 | 0.40741 | 2.0847 | 1.5625 | 1.7521
| 4798 | 0.47222 | 2.7119 | 1.625 | 1.7857
| 4799 | 0.37037 | 2.1017 | 1.6562 | 2.1387
| 4800 | 0.4537 | 1.9492 | 2.4375 | 2.2899
| 4801 | 0.50926 | 2.5254 | 2.9375 | 2.105
| 4802 | 0.40741 | 2.5085 | 0.90625 | 2.1303
| 4803 | 0.34259 | 2.4915 | 1.5625 | 1.8529
| 4804 | 0.39815 | 2.9661 | 0.875 | 2.2899
| 4805 | 0.55556 | 2.7797 | 1.0312 | 1.8697
| 4806 | 0.46296 | 2.4407 | 1.1562 | 1.9328
| 4807 | 0.35185 | 2.4237 | 1.7188 | 2.0924
| 4808 | 0.37037 | 3.4237 | 2 | 2.0882
| 4809 | 0.31481 | 3.0169 | 0.96875 | 1.9454
| 4810 | 0.47222 | 1.8983 | 1.0312 | 2.1134
| 4811 | 0.47222 | 2.7288 | 1.5938 | 2.2521
| 4812 | 0.23148 | 2.9492 | 0.71875 | 2.2521
| 4813 | 0.44444 | 2.2034 | 1.1875 | 2.0924
| 4814 | 0.47222 | 3.4915 | 0.96875 | 2.0924
| 4815 | 0.37963 | 2.4915 | 2 | 2.4034
| 4816 | 0.36111 | 2.2373 | 2.4062 | 1.8866
| 4817 | 0.53704 | 2.9661 | 1.2812 | 2.4454
| 4818 | 0.38889 | 2.2034 | 0.875 | 1.916
| 4819 | 0.34259 | 2.3559 | 1.2188 | 2.0924
| 4820 | 0.4537 | 3.2881 | 2.25 | 2.0546
| 4821 | 0.37037 | 3.0847 | 1.2812 | 2.1597
| 4822 | 0.46296 | 3.3898 | 1.0938 | 2.3403
| 4823 | 0.39815 | 2.1356 | 1.75 | 2.063
| 4824 | 0.48148 | 2.4915 | 0.59375 | 2.1303
| 4825 | 0.28704 | 2.4407 | 1.9062 | 2.0378
| 4826 | 0.46296 | 3 | 0.71875 | 2.084
| 4827 | 0.27778 | 2.4237 | 2.625 | 2.0756
| 4828 | 0.27778 | 2.8475 | 1.9062 | 1.9454
| 4829 | 0.37963 | 2.7797 | 1.1875 | 2.2437
| 4830 | 0.27778 | 2.1864 | 1.125 | 2.479
| 4831 | 0.41667 | 2.8983 | 0.9375 | 2
| 4832 | 0.47222 | 3.1695 | 1.8438 | 1.8151
| 4833 | 0.36111 | 1.8475 | 0.9375 | 2.0966
| 4834 | 0.61111 | 1.6271 | 1.2188 | 1.9076
| 4835 | 0.44444 | 2.7966 | 1.375 | 1.979
| 4836 | 0.47222 | 2.6271 | 1.25 | 2.3487
| 4837 | 0.47222 | 2.6441 | 1.1875 | 2.1218
| 4838 | 0.33333 | 2.7458 | 2.2812 | 1.895
| 4839 | 0.30556 | 3.5424 | 0.875 | 2.2227
| 4840 | 0.30556 | 2.5932 | 1.5 | 1.9454
| 4841 | 0.47222 | 3.0678 | 1.9375 | 2.1429
| 4842 | 0.36111 | 3.0678 | 0.875 | 2.2143
| 4843 | 0.32407 | 3.0678 | 1.8125 | 2.0714
| 4844 | 0.30556 | 2.1695 | 0.90625 | 2.3571
| 4845 | 0.40741 | 2.2034 | 1.9062 | 2.1555
| 4846 | 0.38889 | 2.9831 | 1.0938 | 2.0756
| 4847 | 0.51852 | 2.5763 | 1.4375 | 2.0546
| 4848 | 0.49074 | 2.8475 | 0.9375 | 2.0546
| 4849 | 0.43519 | 2.7119 | 1.3125 | 1.9496
| 4850 | 0.40741 | 2.1525 | 1.0625 | 2.3193
| 4851 | 0.37963 | 2.6102 | 1.5312 | 2.1092
| 4852 | 0.48148 | 2.8814 | 2.0625 | 2.1975
| 4853 | 0.5463 | 2.3729 | 1.4688 | 2.0588
| 4854 | 0.35185 | 2.2373 | 1.0938 | 2
| 4855 | 0.60185 | 2.6102 | 1.9062 | 2.1597
| 4856 | 0.33333 | 2.7627 | 1 | 1.895
| 4857 | 0.37037 | 3.0169 | 1.3438 | 2.0126
| 4858 | 0.24074 | 2.2712 | 1.4688 | 2.3992
| 4859 | 0.38889 | 2.1695 | 1.6875 | 2.3151
| 4860 | 0.31481 | 2.4576 | 0.9375 | 2.2773
| 4861 | 0.4537 | 1.8644 | 1.6562 | 2.1261
| 4862 | 0.4537 | 3.1186 | 1.3125 | 2.3445
| 4863 | 0.49074 | 2.7966 | 1.5 | 1.9832
| 4864 | 0.41667 | 2.8814 | 0.90625 | 1.9076
| 4865 | 0.42593 | 3.1864 | 1.5 | 2.2941
| 4866 | 0.38889 | 2.5593 | 1.25 | 2.0378
| 4867 | 0.52778 | 2.1864 | 1.125 | 1.9874
| 4868 | 0.27778 | 2.7458 | 2.0938 | 2.1471
| 4869 | 0.37037 | 2.6441 | 1.875 | 2.1513
| 4870 | 0.2963 | 2.0339 | 1.1562 | 2.0378
| 4871 | 0.36111 | 3.8644 | 1.4375 | 2.2899
| 4872 | 0.37037 | 2.4068 | 1.0312 | 1.7479
| 4873 | 0.31481 | 2.7627 | 1.4375 | 2.1975
| 4874 | 0.52778 | 2.7119 | 1.1562 | 1.9622
| 4875 | 0.44444 | 2.8644 | 1.4062 | 2.3613
| 4876 | 0.42593 | 2.6102 | 0.8125 | 2.0126
| 4877 | 0.39815 | 2.7966 | 2.1562 | 2.0882
| 4878 | 0.53704 | 2.5593 | 1.5 | 2.063
| 4879 | 0.41667 | 2.0339 | 1.2812 | 2.0882
| 4880 | 0.42593 | 2.9492 | 1.1875 | 2.0126
| 4881 | 0.43519 | 1.9492 | 2.5 | 2
| 4882 | 0.43519 | 2.9831 | 0.78125 | 2.1303
| 4883 | 0.49074 | 2.4068 | 0.96875 | 2.4538
| 4884 | 0.40741 | 3.1695 | 1.4375 | 2.3025
| 4885 | 0.32407 | 3.3051 | 1.8438 | 2.3613
| 4886 | 0.31481 | 2.7627 | 1.5312 | 2.1891
| 4887 | 0.22222 | 1.7966 | 1.5 | 2.1261
| 4888 | 0.36111 | 2.4407 | 1.2812 | 2.3235
| 4889 | 0.2963 | 2.2881 | 1.5625 | 2.458
| 4890 | 0.40741 | 2.3898 | 2.125 | 1.8403
| 4891 | 0.5463 | 2.4576 | 1.0312 | 2.2941
| 4892 | 0.5 | 2.1525 | 1.5938 | 2.2479
| 4893 | 0.38889 | 2.9322 | 1.75 | 2.2227
| 4894 | 0.49074 | 3.2881 | 1.2188 | 2.0084
| 4895 | 0.38889 | 2.8983 | 1.3125 | 1.9958
| 4896 | 0.38889 | 2.8814 | 1.5312 | 2.0126
| 4897 | 0.39815 | 2.4407 | 1.9062 | 2.3403
| 4898 | 0.46296 | 2.1356 | 1.4062 | 2.3487
| 4899 | 0.31481 | 2.7458 | 1.4375 | 2.2311
| 4900 | 0.41667 | 2.7797 | 1.5625 | 2.1303
| 4901 | 0.37963 | 2.9831 | 1 | 2.0294
| 4902 | 0.41667 | 3.2542 | 0.59375 | 1.8782
| 4903 | 0.46296 | 3.1017 | 0.875 | 2.1345
| 4904 | 0.33333 | 2.8136 | 1.5312 | 1.8487
| 4905 | 0.27778 | 2.0508 | 2.0625 | 2.1849
| 4906 | 0.50926 | 3.6102 | 1.375 | 2.042
| 4907 | 0.47222 | 3.0169 | 1.5938 | 2.4118
| 4908 | 0.36111 | 2.9831 | 1.5938 | 2.3487
| 4909 | 0.32407 | 2.8983 | 1.0938 | 2.1176
| 4910 | 0.42593 | 2.9831 | 1.75 | 2.1218
| 4911 | 0.2037 | 2.3051 | 1.2812 | 2.4496
| 4912 | 0.34259 | 2.7966 | 0.90625 | 1.9412
| 4913 | 0.31481 | 2.5424 | 1.3125 | 2.1891
| 4914 | 0.50926 | 2.6271 | 1.6875 | 2.1807
| 4915 | 0.42593 | 2.661 | 1.375 | 2.2059
| 4916 | 0.53704 | 2.8136 | 1.5938 | 2.1218
| 4917 | 0.47222 | 3.1186 | 0.96875 | 2.0504
| 4918 | 0.17593 | 3.5763 | 1.3438 | 2.0882
| 4919 | 0.5 | 3.3559 | 1.4062 | 2.0882
| 4920 | 0.31481 | 2.9322 | 1.375 | 1.9328
| 4921 | 0.37037 | 2.678 | 0.78125 | 2.2185
| 4922 | 0.56481 | 2.7627 | 1.5312 | 2.3908
| 4923 | 0.56481 | 2.9322 | 1.9062 | 2.0546
| 4924 | 0.40741 | 2.5593 | 1.2188 | 1.9748
| 4925 | 0.43519 | 2.2203 | 1.4688 | 1.9874
| 4926 | 0.44444 | 2.4407 | 1.7188 | 1.9496
| 4927 | 0.37037 | 2.9322 | 1.1562 | 1.9328
| 4928 | 0.40741 | 2.8305 | 1.875 | 2.0084
| 4929 | 0.46296 | 2.9322 | 1.5312 | 2.1261
| 4930 | 0.42593 | 3.0508 | 1.2188 | 2.1723
| 4931 | 0.34259 | 2.2881 | 1.0938 | 2.1891
| 4932 | 0.5 | 2.4746 | 1.5938 | 2.0504
| 4933 | 0.34259 | 2.6271 | 1.7812 | 1.9496
| 4934 | 0.58333 | 3.1525 | 1.5312 | 2.2059
| 4935 | 0.43519 | 2.5593 | 1.1875 | 2.1891
| 4936 | 0.41667 | 3.2203 | 0.71875 | 2.0462
| 4937 | 0.55556 | 2.8305 | 2.2188 | 2.3193
| 4938 | 0.43519 | 2.0508 | 1.5 | 2.479
| 4939 | 0.41667 | 3 | 1.8125 | 2.0294
| 4940 | 0.49074 | 2.7288 | 1.2188 | 1.7563
| 4941 | 0.58333 | 2.678 | 0.875 | 2.4538
| 4942 | 0.51852 | 3.1017 | 1.3125 | 2.3908
| 4943 | 0.4537 | 3.0847 | 1.875 | 1.9286
| 4944 | 0.41667 | 2.8475 | 2.0312 | 2.2899
| 4945 | 0.40741 | 2.5424 | 0.9375 | 2.1471
| 4946 | 0.47222 | 2.5593 | 2.1875 | 2.0672
| 4947 | 0.5 | 2.8305 | 0.90625 | 1.9958
| 4948 | 0.32407 | 3.7627 | 1.625 | 2.2059
| 4949 | 0.40741 | 2.2203 | 1.9375 | 1.8025
| 4950 | 0.37963 | 3.1017 | 1.2812 | 2.0294
| 4951 | 0.47222 | 2.1525 | 1.4375 | 1.9034
| 4952 | 0.36111 | 2.8136 | 0.9375 | 1.9832
| 4953 | 0.56481 | 2.6271 | 0.96875 | 2.0546
| 4954 | 0.21296 | 2.2712 | 1.4375 | 2.1429
| 4955 | 0.35185 | 3.4407 | 1.7812 | 2.3277
| 4956 | 0.58333 | 2.5424 | 1.1875 | 2.2815
| 4957 | 0.30556 | 3.8475 | 1.6875 | 2.1429
| 4958 | 0.40741 | 2.2203 | 1 | 2.1303
| 4959 | 0.31481 | 3.1525 | 1.4375 | 1.8782
| 4960 | 0.36111 | 2.2203 | 1.6562 | 2.0966
| 4961 | 0.40741 | 3.4746 | 0.65625 | 1.9622
| 4962 | 0.33333 | 2.8644 | 1.9688 | 2.0798
| 4963 | 0.37037 | 2.1356 | 1.1875 | 1.7731
| 4964 | 0.32407 | 2.339 | 1.5938 | 1.9622
| 4965 | 0.69444 | 2.661 | 1.1562 | 2.3025
| 4966 | 0.44444 | 2.4915 | 1.5312 | 2.2521
| 4967 | 0.33333 | 3.7119 | 1.1875 | 1.8487
| 4968 | 0.44444 | 2.5085 | 0.96875 | 2.0294
| 4969 | 0.38889 | 2.0339 | 1.5312 | 2.1513
| 4970 | 0.4537 | 3.0508 | 1.0312 | 2.4034
| 4971 | 0.43519 | 2.6102 | 1.6875 | 2.2143
| 4972 | 0.41667 | 2.8644 | 1.625 | 2.105
| 4973 | 0.58333 | 2.2712 | 1 | 2.3908
| 4974 | 0.42593 | 2.4407 | 1.0312 | 1.7689
| 4975 | 0.33333 | 2.3729 | 1.8438 | 2.0966
| 4976 | 0.30556 | 1.8475 | 2.2188 | 1.7899
| 4977 | 0.35185 | 2.6271 | 0.75 | 2.3908
| 4978 | 0.37037 | 1.7627 | 1.1875 | 2.0756
| 4979 | 0.31481 | 1.8305 | 1.7188 | 2.1471
| 4980 | 0.53704 | 3 | 1.1562 | 2.1807
| 4981 | 0.49074 | 3.5593 | 1.3125 | 2.4244
| 4982 | 0.38889 | 2.1186 | 1.0312 | 1.9958
| 4983 | 0.47222 | 3.0169 | 0.71875 | 1.895
| 4984 | 0.39815 | 2.6271 | 0.8125 | 2.0504
| 4985 | 0.37963 | 2.9153 | 1.9688 | 2.084
| 4986 | 0.2037 | 2.4237 | 1.1562 | 2.1303
| 4987 | 0.48148 | 3.4915 | 1.625 | 2.1387
| 4988 | 0.32407 | 2.5932 | 1 | 2.0966
| 4989 | 0.2963 | 2.8814 | 0.71875 | 1.8193
| 4990 | 0.53704 | 2.9831 | 0.9375 | 1.9202
| 4991 | 0.35185 | 2.2712 | 0.78125 | 1.8739
| 4992 | 0.34259 | 3.6271 | 1.0938 | 1.9496
| 4993 | 0.46296 | 2.8475 | 0.8125 | 2.1429
| 4994 | 0.37963 | 2.0847 | 1.2812 | 2.0294
| 4995 | 0.46296 | 2.7288 | 1.75 | 2.2479
| 4996 | 0.43519 | 2.4237 | 1.2188 | 2.2101
| 4997 | 0.51852 | 2.1017 | 2.1562 | 2.1975
| 4998 | 0.33333 | 3.0847 | 1.8438 | 2.1176
| 4999 | 0.39815 | 2.9153 | 0.75 | 2.1807
| 5000 | 0.36111 | 2.8644 | 1.7812 | 1.7857
| 5001 | 0.40741 | 2.3559 | 1.0938 | 2.5714
| 5002 | 0.44444 | 2.5085 | 0.875 | 1.7647
| 5003 | 0.26852 | 2.7797 | 1.0625 | 1.9748
| 5004 | 0.37037 | 3.0847 | 1.1875 | 2.0672
| 5005 | 0.31481 | 2.661 | 1.875 | 2.5294
| 5006 | 0.39815 | 2.322 | 1.6875 | 2.1134
| 5007 | 0.44444 | 3.1695 | 1.7812 | 1.8487
| 5008 | 0.44444 | 3.0678 | 0.4375 | 2.2017
| 5009 | 0.35185 | 2.9661 | 0.5 | 1.8193
| 5010 | 0.43519 | 3.0847 | 1.0312 | 2.1597
| 5011 | 0.41667 | 2.7797 | 1.1562 | 2.1345
| 5012 | 0.41667 | 2.4237 | 1.4375 | 1.8235
| 5013 | 0.34259 | 2.1525 | 1.0938 | 2.1261
| 5014 | 0.4537 | 2.0339 | 2.0312 | 2.2353
| 5015 | 0.35185 | 2.9153 | 2.1875 | 2.3992
| 5016 | 0.40741 | 3.2373 | 1.5938 | 2.4496
| 5017 | 0.37037 | 2.6441 | 0.96875 | 2.0042
| 5018 | 0.37037 | 2.4746 | 1.2812 | 2.2899
| 5019 | 0.31481 | 2.7797 | 1.5938 | 2.0756
| 5020 | 0.40741 | 2.0508 | 1.2812 | 2.1555
| 5021 | 0.31481 | 2.5593 | 1.2188 | 2.063
| 5022 | 0.30556 | 3.2203 | 1.625 | 1.9958
| 5023 | 0.2963 | 3 | 1.1875 | 2.0798
| 5024 | 0.33333 | 3.7966 | 1.4688 | 2.2395
| 5025 | 0.47222 | 3.5424 | 1.375 | 2.2899
| 5026 | 0.59259 | 2.7119 | 1.4062 | 2.1597
| 5027 | 0.38889 | 2.5932 | 0.78125 | 1.9496
| 5028 | 0.46296 | 2.5424 | 1.8125 | 2.0714
| 5029 | 0.30556 | 2.2542 | 1.4688 | 2.1387
| 5030 | 0.33333 | 1.9492 | 1.75 | 2.3235
| 5031 | 0.58333 | 3.1017 | 1.2188 | 2.416
| 5032 | 0.46296 | 3 | 1.75 | 1.8613
| 5033 | 0.33333 | 2.678 | 1.375 | 2.4454
| 5034 | 0.2963 | 2.322 | 1.1562 | 1.8403
| 5035 | 0.26852 | 2.3898 | 1.9062 | 2.2479
| 5036 | 0.4537 | 2.7458 | 1.2812 | 1.9832
| 5037 | 0.5 | 3.7458 | 1.9062 | 2.1681
| 5038 | 0.52778 | 3.5085 | 1.3125 | 1.8109
| 5039 | 0.30556 | 3.0847 | 1.4375 | 2.4202
| 5040 | 0.59259 | 2.5593 | 1.9688 | 2.5252
| 5041 | 0.38889 | 2.8305 | 1.1875 | 2.3151
| 5042 | 0.46296 | 2.8475 | 1.6875 | 2.1008
| 5043 | 0.64815 | 2.3729 | 1.25 | 2.2143
| 5044 | 0.37963 | 3.0169 | 1.5312 | 2.1849
| 5045 | 0.44444 | 2.4407 | 1.75 | 2.2857
| 5046 | 0.48148 | 1.8814 | 1.2188 | 2.479
| 5047 | 0.40741 | 2.3051 | 0.71875 | 1.7983
| 5048 | 0.51852 | 2.4576 | 1.3125 | 2.3235
| 5049 | 0.55556 | 2.2881 | 1.625 | 2.2605
| 5050 | 0.62037 | 1.8644 | 1.0938 | 1.9874
| 5051 | 0.5 | 3.4746 | 0.78125 | 2.5336
| 5052 | 0.5 | 2.8814 | 1.5312 | 2.1681
| 5053 | 0.44444 | 2.5085 | 1.25 | 2.0042
| 5054 | 0.35185 | 2.7966 | 1.7188 | 2.1975
| 5055 | 0.37963 | 2.9492 | 0.9375 | 2.1387
| 5056 | 0.51852 | 2.661 | 1.6875 | 2.1639
| 5057 | 0.36111 | 3.2542 | 1.9375 | 1.9874
| 5058 | 0.48148 | 2.322 | 1.4062 | 2.1008
| 5059 | 0.38889 | 2.4576 | 1.1875 | 1.8193
| 5060 | 0.47222 | 2.322 | 1 | 2.1008
| 5061 | 0.39815 | 2.1525 | 1.25 | 1.9412
| 5062 | 0.47222 | 1.4407 | 1.8438 | 1.8824
| 5063 | 0.41667 | 3.3051 | 0.6875 | 2.0924
| 5064 | 0.42593 | 2.2034 | 1.4688 | 2.4916
| 5065 | 0.53704 | 2.3559 | 1.125 | 1.958
| 5066 | 0.43519 | 3.7966 | 0.9375 | 1.9244
| 5067 | 0.4537 | 2.5424 | 1.3438 | 1.937
| 5068 | 0.25 | 2.6102 | 1.0938 | 2.0756
| 5069 | 0.49074 | 2.9831 | 1.25 | 2.2815
| 5070 | 0.37037 | 2.8644 | 1.3125 | 2.0756
| 5071 | 0.55556 | 2.678 | 1.5625 | 1.9454
| 5072 | 0.23148 | 2.3051 | 0.8125 | 2.437
| 5073 | 0.39815 | 2.4407 | 1.6562 | 1.8361
| 5074 | 0.25926 | 2.9492 | 1.3125 | 2.1176
| 5075 | 0.41667 | 2.661 | 0.75 | 1.8992
| 5076 | 0.5 | 2.8305 | 1.4688 | 2.0504
| 5077 | 0.56481 | 2.4068 | 1.4375 | 2.1513
| 5078 | 0.40741 | 3.0339 | 1.7188 | 1.8277
| 5079 | 0.47222 | 3.3729 | 2.0625 | 2.2563
| 5080 | 0.22222 | 2.8814 | 1.75 | 1.7731
| 5081 | 0.38889 | 1.9492 | 1.4688 | 2.2731
| 5082 | 0.37963 | 2.9661 | 2.3438 | 1.9874
| 5083 | 0.47222 | 2.3729 | 2.1562 | 2.5084
| 5084 | 0.21296 | 2.3559 | 1.25 | 2
| 5085 | 0.50926 | 3.1356 | 1.375 | 2.0714
| 5086 | 0.32407 | 3.0169 | 2.5625 | 1.895
| 5087 | 0.40741 | 2.6271 | 1.3438 | 2.0714
| 5088 | 0.37037 | 2.8136 | 0.6875 | 2.0714
| 5089 | 0.53704 | 3 | 1 | 2.0672
| 5090 | 0.37037 | 3.1864 | 2.3438 | 2.2983
| 5091 | 0.44444 | 2.3559 | 1.9688 | 1.9076
| 5092 | 0.49074 | 2.6949 | 2.375 | 2.3109
| 5093 | 0.40741 | 3.7458 | 1.3438 | 1.7521
| 5094 | 0.37963 | 3.0678 | 0.9375 | 2.063
| 5095 | 0.33333 | 2.7797 | 1.0938 | 1.9958
| 5096 | 0.46296 | 2.3729 | 1.875 | 1.7269
| 5097 | 0.31481 | 1.7966 | 1.75 | 1.916
| 5098 | 0.37963 | 2.1695 | 1.25 | 1.8782
| 5099 | 0.36111 | 2.9322 | 0.84375 | 2.2353
| 5100 | 0.32407 | 2.4068 | 1.4062 | 1.8193
| 5101 | 0.33333 | 2.3729 | 1.7812 | 2.1513
| 5102 | 0.46296 | 3.3559 | 2.25 | 2
| 5103 | 0.52778 | 3.4068 | 1.6875 | 1.9454
| 5104 | 0.42593 | 2.0678 | 0.78125 | 2.2395
| 5105 | 0.39815 | 2.2542 | 1.625 | 2.2563
| 5106 | 0.38889 | 2.661 | 0.5625 | 2.2185
| 5107 | 0.40741 | 3.1017 | 1.4062 | 2.1639
| 5108 | 0.42593 | 2.6441 | 1.125 | 1.9874
| 5109 | 0.44444 | 3.0169 | 2 | 2.1807
| 5110 | 0.48148 | 2.2034 | 1.4062 | 2.1303
| 5111 | 0.44444 | 2.7119 | 1.4375 | 2.2647
| 5112 | 0.32407 | 2.2373 | 1.0625 | 2.0336
| 5113 | 0.34259 | 2.2881 | 1.2188 | 1.9748
| 5114 | 0.31481 | 1.9831 | 0.96875 | 2.0084
| 5115 | 0.43519 | 3.5085 | 1.2188 | 1.916
| 5116 | 0.35185 | 2.4068 | 1.375 | 2.1723
| 5117 | 0.37037 | 2.1864 | 1.6875 | 2.0126
| 5118 | 0.48148 | 2.6949 | 0.71875 | 2.1849
| 5119 | 0.38889 | 2.4746 | 1.625 | 2.437
| 5120 | 0.44444 | 2.8305 | 1.7188 | 1.9832
| 5121 | 0.4537 | 3 | 1.4375 | 1.9706
| 5122 | 0.31481 | 2.7119 | 2.2188 | 2.0672
| 5123 | 0.37963 | 3.4576 | 1.2812 | 1.958
| 5124 | 0.33333 | 2.7627 | 1.9062 | 2.0924
| 5125 | 0.68519 | 2.1525 | 1.625 | 1.8992
| 5126 | 0.4537 | 2.3559 | 1.5 | 2.0546
| 5127 | 0.35185 | 2.4746 | 0.9375 | 1.9454
| 5128 | 0.36111 | 2.3051 | 1.0938 | 1.9244
| 5129 | 0.25 | 2.7119 | 1.8438 | 1.9958
| 5130 | 0.35185 | 2.3898 | 1.5312 | 2.2101
| 5131 | 0.41667 | 3.1864 | 1.5625 | 2.1387
| 5132 | 0.50926 | 2.2203 | 1.1875 | 2.416
| 5133 | 0.37963 | 3.0847 | 1.5938 | 2.1303
| 5134 | 0.46296 | 3.6102 | 0.75 | 1.8277
| 5135 | 0.53704 | 2.9661 | 1.1875 | 2.5
| 5136 | 0.37037 | 3.2542 | 1.875 | 2.0882
| 5137 | 0.43519 | 3.1356 | 1.5938 | 2.0882
| 5138 | 0.44444 | 2.2203 | 1.2812 | 2.0042
| 5139 | 0.35185 | 2.8305 | 0.90625 | 2.2059
| 5140 | 0.47222 | 3.322 | 0.625 | 1.8824
| 5141 | 0.39815 | 2.2712 | 1.2188 | 2.6303
| 5142 | 0.53704 | 2.5593 | 2.0938 | 2.1723
| 5143 | 0.2963 | 2.6441 | 1.2812 | 2.4412
| 5144 | 0.43519 | 2.4576 | 1.7812 | 1.8908
| 5145 | 0.28704 | 1.8305 | 0.96875 | 2.3571
| 5146 | 0.62963 | 2.1017 | 1.4375 | 2.2059
| 5147 | 0.47222 | 2.5763 | 1.6562 | 2.0168
| 5148 | 0.53704 | 3.4576 | 1.125 | 2.2395
| 5149 | 0.41667 | 2.6949 | 1.0312 | 1.8992
| 5150 | 0.44444 | 2.4915 | 2.125 | 2.0924
| 5151 | 0.50926 | 2.4746 | 0.9375 | 1.8403
| 5152 | 0.31481 | 2.3729 | 1.3438 | 1.8529
| 5153 | 0.4537 | 2.0678 | 1.0938 | 2.2563
| 5154 | 0.58333 | 3.2034 | 1.0312 | 2.0546
| 5155 | 0.5 | 2.3559 | 0.625 | 2.1471
| 5156 | 0.41667 | 2.3051 | 1.2812 | 2.4328
| 5157 | 0.52778 | 2.5593 | 1.1875 | 2.2185
| 5158 | 0.47222 | 2.3729 | 1.8125 | 2.0672
| 5159 | 0.53704 | 1.6441 | 1.3125 | 1.9958
| 5160 | 0.49074 | 3.0678 | 1.6875 | 2.5252
| 5161 | 0.37037 | 2.8305 | 1.8125 | 1.8655
| 5162 | 0.52778 | 2.1525 | 1.4062 | 1.916
| 5163 | 0.4537 | 3.3898 | 1.5625 | 2.3697
| 5164 | 0.2963 | 2.6102 | 2.0625 | 2.1681
| 5165 | 0.47222 | 2.661 | 2.1875 | 2.1008
| 5166 | 0.35185 | 2.8475 | 0.9375 | 2.1891
| 5167 | 0.39815 | 2.8644 | 0.59375 | 2.4748
| 5168 | 0.32407 | 3.2881 | 1.2188 | 2.1933
| 5169 | 0.37963 | 2.4746 | 1.5625 | 2.3487
| 5170 | 0.32407 | 2.4576 | 1.25 | 2.063
| 5171 | 0.47222 | 2.2712 | 1.5 | 2.1891
| 5172 | 0.43519 | 1.8475 | 1.2812 | 1.9118
| 5173 | 0.5 | 2.4068 | 2.2812 | 2.1092
| 5174 | 0.38889 | 2.1356 | 1.1875 | 2.1429
| 5175 | 0.30556 | 3.2542 | 1.0625 | 2.458
| 5176 | 0.41667 | 2.9492 | 1.4375 | 2.1555
| 5177 | 0.36111 | 2.8136 | 1.5938 | 2.0546
| 5178 | 0.60185 | 2.678 | 2.125 | 2.416
| 5179 | 0.5 | 1.6441 | 1.5938 | 1.9622
| 5180 | 0.32407 | 2.7119 | 1.75 | 2.3782
| 5181 | 0.35185 | 3.1356 | 1.3125 | 2.1387
| 5182 | 0.25926 | 2.3051 | 1.625 | 2.0924
| 5183 | 0.46296 | 2.5593 | 1.2188 | 2.5546
| 5184 | 0.53704 | 3.3898 | 1.2812 | 1.9244
| 5185 | 0.30556 | 2.2542 | 1.5312 | 2.2185
| 5186 | 0.42593 | 2.6102 | 1.5 | 2.2059
| 5187 | 0.33333 | 2.4915 | 1.4062 | 1.9412
| 5188 | 0.43519 | 2.6271 | 1.4688 | 2.0756
| 5189 | 0.39815 | 2.3051 | 1.6875 | 1.9874
| 5190 | 0.34259 | 2.0847 | 1.0938 | 2.0462
| 5191 | 0.5 | 2.1695 | 1.5312 | 2.0168
| 5192 | 0.36111 | 2.5254 | 1.75 | 2.1639
| 5193 | 0.37963 | 2.5932 | 1.7812 | 2.042
| 5194 | 0.51852 | 3.4407 | 1.2812 | 2.6218
| 5195 | 0.46296 | 3.8814 | 1.125 | 1.8529
| 5196 | 0.53704 | 2.6271 | 1.9688 | 2.3277
| 5197 | 0.42593 | 2.5763 | 1.5312 | 2.416
| 5198 | 0.33333 | 3.0678 | 2.2812 | 1.9202
| 5199 | 0.49074 | 2.5254 | 1.2812 | 1.9832
| 5200 | 0.5 | 3.1525 | 1.3125 | 2.1975
| 5201 | 0.50926 | 2.5085 | 2.0312 | 2.2563
| 5202 | 0.28704 | 2.8305 | 1.7812 | 1.9202
| 5203 | 0.36111 | 2.4407 | 1.7812 | 2.0168
| 5204 | 0.36111 | 2.4915 | 1.625 | 2.0966
| 5205 | 0.32407 | 2.7627 | 1.5312 | 2.2563
| 5206 | 0.42593 | 2.7458 | 1.25 | 2.0882
| 5207 | 0.43519 | 2.9661 | 1.8438 | 1.8403
| 5208 | 0.37037 | 2.9492 | 1.875 | 2.2689
| 5209 | 0.49074 | 2.1864 | 1.1875 | 2.2101
| 5210 | 0.37963 | 2.9831 | 0.96875 | 2.479
| 5211 | 0.38889 | 2.322 | 1.4375 | 2.2605
| 5212 | 0.44444 | 3.2542 | 1.6562 | 2.1303
| 5213 | 0.39815 | 2.7966 | 1.5625 | 2.1807
| 5214 | 0.43519 | 3.1356 | 1.625 | 2.2185
| 5215 | 0.35185 | 2.7627 | 1.0938 | 1.7479
| 5216 | 0.40741 | 3.2034 | 1.8125 | 2.1975
| 5217 | 0.42593 | 2.2542 | 1.6875 | 2.2017
| 5218 | 0.40741 | 2.6949 | 1.6562 | 2.1639
| 5219 | 0.58333 | 2.9322 | 1.3438 | 1.8193
| 5220 | 0.49074 | 2.678 | 0.8125 | 2.1639
| 5221 | 0.37963 | 2.5424 | 1.8438 | 1.8403
| 5222 | 0.33333 | 2.661 | 1.8125 | 2.3992
| 5223 | 0.33333 | 3.1186 | 1.7188 | 2.1975
| 5224 | 0.34259 | 3.1186 | 1.4375 | 2.1597
| 5225 | 0.5 | 2.8475 | 1.5312 | 1.9244
| 5226 | 0.56481 | 2.4746 | 2.0312 | 2.3655
| 5227 | 0.56481 | 2.661 | 1.5938 | 1.9538
| 5228 | 0.42593 | 3.339 | 1.6562 | 2.1723
| 5229 | 0.35185 | 2.3051 | 1.5 | 2.1429
| 5230 | 0.4537 | 3.3559 | 1.2812 | 2.2605
| 5231 | 0.25 | 2.4915 | 1.4062 | 2.0798
| 5232 | 0.26852 | 2.2712 | 2.3125 | 2.1597
| 5233 | 0.55556 | 2.2542 | 1.2188 | 2.1639
| 5234 | 0.38889 | 2.2881 | 1.375 | 2.2269
| 5235 | 0.22222 | 2.8814 | 0.8125 | 1.9748
| 5236 | 0.35185 | 3.2034 | 1.8438 | 2.2353
| 5237 | 0.46296 | 2.2542 | 1.0312 | 2.1891
| 5238 | 0.47222 | 2.4068 | 1.5 | 2.4118
| 5239 | 0.40741 | 1.9322 | 1.2812 | 2.0756
| 5240 | 0.2963 | 3.2034 | 1.5312 | 1.8025
| 5241 | 0.28704 | 2.5085 | 1.4375 | 2.0168
| 5242 | 0.39815 | 2.8814 | 1.2188 | 1.7899
| 5243 | 0.37037 | 2.678 | 1.1875 | 2.3361
| 5244 | 0.39815 | 2.4237 | 1.6562 | 1.8782
| 5245 | 0.47222 | 3.6102 | 1.3438 | 2.2059
| 5246 | 0.50926 | 2.3559 | 1.5312 | 2.5168
| 5247 | 0.40741 | 2.5254 | 1.2812 | 2.1933
| 5248 | 0.32407 | 2.2542 | 1.4375 | 1.958
| 5249 | 0.36111 | 2.2712 | 0.9375 | 2.3782
| 5250 | 0.50926 | 2.3729 | 1.0312 | 2.1849
| 5251 | 0.46296 | 3.1186 | 1.2188 | 2.4244
| 5252 | 0.27778 | 3.0847 | 1.625 | 2.0084
| 5253 | 0.30556 | 3.4237 | 1.4688 | 2.084
| 5254 | 0.37963 | 2.1525 | 2.2812 | 2.1008
| 5255 | 0.47222 | 2.339 | 1 | 2.1555
| 5256 | 0.26852 | 2.4576 | 1.1562 | 1.9202
| 5257 | 0.39815 | 2.6949 | 1 | 1.8824
| 5258 | 0.31481 | 2.3898 | 0.6875 | 2.1176
| 5259 | 0.42593 | 2.2373 | 0.90625 | 2.3235
| 5260 | 0.44444 | 3 | 2.0312 | 1.9454
| 5261 | 0.62037 | 2.5254 | 0.71875 | 2.2941
| 5262 | 0.60185 | 2.4407 | 1.9688 | 2.2857
| 5263 | 0.32407 | 3.1186 | 1.0312 | 2.1429
| 5264 | 0.49074 | 2.9831 | 1.0312 | 1.9748
| 5265 | 0.5 | 2.678 | 1.625 | 2.0168
| 5266 | 0.43519 | 2.2542 | 1 | 1.9958
| 5267 | 0.36111 | 2.8305 | 1.3438 | 2.2731
| 5268 | 0.33333 | 2.8814 | 1.1562 | 2.0462
| 5269 | 0.5 | 2.5085 | 1.9688 | 2.1933
| 5270 | 0.41667 | 2.661 | 1.1875 | 2.1134
| 5271 | 0.37037 | 2.7797 | 0.875 | 1.9916
| 5272 | 0.31481 | 2.4068 | 0.8125 | 2.2647
| 5273 | 0.5463 | 3.4237 | 1.1875 | 2.4748
| 5274 | 0.4537 | 3.5254 | 1.625 | 2.0924
| 5275 | 0.56481 | 2.678 | 1.2188 | 2.7479
| 5276 | 0.35185 | 2.9322 | 0.90625 | 1.8193
| 5277 | 0.4537 | 2.339 | 0.40625 | 2.0042
| 5278 | 0.43519 | 2.1695 | 2.6562 | 2.0924
| 5279 | 0.46296 | 2.4746 | 1.9375 | 2.3403
| 5280 | 0.61111 | 2.3729 | 1.375 | 2.2815
| 5281 | 0.43519 | 3.2712 | 1 | 2.0336
| 5282 | 0.46296 | 2.2881 | 1.5 | 2.2605
| 5283 | 0.35185 | 1.7119 | 2.125 | 2.3193
| 5284 | 0.37037 | 2.8475 | 1.7812 | 1.8277
| 5285 | 0.49074 | 2.5932 | 1.0625 | 2.084
| 5286 | 0.39815 | 2.7458 | 0.90625 | 2.4958
| 5287 | 0.36111 | 2.2881 | 0.96875 | 1.7815
| 5288 | 0.40741 | 1.8814 | 0.75 | 1.8067
| 5289 | 0.46296 | 2.3559 | 1.25 | 2.2563
| 5290 | 0.5 | 2.8644 | 1.5625 | 2.4244
| 5291 | 0.36111 | 2.7119 | 1 | 1.9748
| 5292 | 0.41667 | 2.322 | 1.4688 | 2.2983
| 5293 | 0.34259 | 3.4237 | 1.875 | 2.1429
| 5294 | 0.32407 | 2.6441 | 1.6875 | 2.2395
| 5295 | 0.38889 | 2.9831 | 0.90625 | 2.3193
| 5296 | 0.4537 | 2.5254 | 1.125 | 2.1849
| 5297 | 0.52778 | 2.4407 | 1 | 2.5
| 5298 | 0.2963 | 2.1695 | 1.625 | 2.0336
| 5299 | 0.50926 | 2.7797 | 1.6562 | 2.3025
| 5300 | 0.38889 | 2.4576 | 2.0938 | 1.8992
| 5301 | 0.37037 | 3.2373 | 1.4375 | 2.3487
| 5302 | 0.27778 | 2.4237 | 1.3438 | 2.3529
| 5303 | 0.38889 | 3.0339 | 1.125 | 2.2773
| 5304 | 0.37037 | 2.678 | 2 | 1.979
| 5305 | 0.66667 | 2.4576 | 0.84375 | 2.5672
| 5306 | 0.36111 | 2.1017 | 0.90625 | 2.2185
| 5307 | 0.40741 | 3.1525 | 1.6562 | 2.1891
| 5308 | 0.47222 | 2.5932 | 1.8125 | 2.1723
| 5309 | 0.46296 | 3.1695 | 1.0312 | 2.2521
| 5310 | 0.37963 | 3 | 1.2812 | 2.0882
| 5311 | 0.59259 | 2.4915 | 1.9375 | 2.0798
| 5312 | 0.39815 | 2.5932 | 1.5 | 2.1933
| 5313 | 0.37963 | 2.2712 | 1.5938 | 2.042
| 5314 | 0.50926 | 2.7797 | 1.5312 | 1.958
| 5315 | 0.5 | 3.0847 | 1 | 1.9454
| 5316 | 0.35185 | 2.6271 | 2.0312 | 2.0924
| 5317 | 0.37963 | 2.6271 | 2.125 | 2.2479
| 5318 | 0.42593 | 2.2881 | 0.9375 | 2.2521
| 5319 | 0.53704 | 2.678 | 1.4062 | 2.5966
| 5320 | 0.40741 | 1.8814 | 1.4688 | 2.0252
| 5321 | 0.39815 | 3.0678 | 1.1875 | 1.9496
| 5322 | 0.61111 | 2.3898 | 1.375 | 2.0252
| 5323 | 0.50926 | 3.1695 | 1.0625 | 1.9454
| 5324 | 0.52778 | 3.0847 | 1.3438 | 1.8025
| 5325 | 0.36111 | 3.3729 | 1.6875 | 2.5714
| 5326 | 0.38889 | 2.7119 | 1.2812 | 2.084
| 5327 | 0.40741 | 2.5763 | 1.5312 | 2.1639
| 5328 | 0.36111 | 2.5763 | 1.5 | 2.1723
| 5329 | 0.41667 | 2.0678 | 3.3438 | 2.6639
| 5330 | 0.5 | 2.4407 | 0.875 | 2.416
| 5331 | 0.37963 | 2.8475 | 0.96875 | 2.0168
| 5332 | 0.4537 | 3.1525 | 1.3438 | 1.9076
| 5333 | 0.39815 | 2.8814 | 1.625 | 1.979
| 5334 | 0.51852 | 2.4915 | 0.9375 | 2.1513
| 5335 | 0.48148 | 2.322 | 1 | 1.8992
| 5336 | 0.44444 | 2.661 | 1.0625 | 2.1218
| 5337 | 0.49074 | 3.2203 | 1.9062 | 2.1765
| 5338 | 0.41667 | 2.1695 | 1.625 | 2.2689
| 5339 | 0.48148 | 2.678 | 1.9688 | 1.9664
| 5340 | 0.40741 | 2.339 | 1.125 | 2.0336
| 5341 | 0.35185 | 2.3898 | 1.375 | 2.2479
| 5342 | 0.60185 | 1.6441 | 0.75 | 2.4622
| 5343 | 0.37037 | 2.4237 | 1.2812 | 2.3361
| 5344 | 0.33333 | 2.339 | 1.7812 | 1.7773
| 5345 | 0.49074 | 2.3898 | 1.0312 | 2.2479
| 5346 | 0.48148 | 1.8305 | 1.0938 | 2.1933
| 5347 | 0.34259 | 2.9322 | 1 | 2.1008
| 5348 | 0.48148 | 2.8644 | 1.1875 | 1.9874
| 5349 | 0.32407 | 2.2712 | 0.875 | 2.0126
| 5350 | 0.50926 | 3.4407 | 0.90625 | 1.9412
| 5351 | 0.52778 | 2.8136 | 1.2812 | 2.2563
| 5352 | 0.41667 | 2.7458 | 0.9375 | 1.7815
| 5353 | 0.27778 | 2.3559 | 1.125 | 2.2479
| 5354 | 0.16667 | 2.6441 | 1.4375 | 2.2059
| 5355 | 0.51852 | 2.7119 | 1.2188 | 2.4076
| 5356 | 0.25926 | 2.3559 | 1.5312 | 2.3109
| 5357 | 0.55556 | 3.1695 | 1.4375 | 1.8866
| 5358 | 0.44444 | 1.9661 | 1.5938 | 1.8361
| 5359 | 0.41667 | 2.6949 | 1 | 1.8235
| 5360 | 0.30556 | 2.9492 | 1.0938 | 1.9706
| 5361 | 0.38889 | 3.0847 | 1.5625 | 2.0672
| 5362 | 0.4537 | 3.4407 | 1.1875 | 2.105
| 5363 | 0.47222 | 2.661 | 1.6875 | 2.3992
| 5364 | 0.39815 | 2.1186 | 1.1562 | 2.2227
| 5365 | 0.48148 | 2.4407 | 1.25 | 2.0336
| 5366 | 0.43519 | 2.7288 | 1.0938 | 2.5168
| 5367 | 0.4537 | 3.322 | 1.4688 | 1.9202
| 5368 | 0.36111 | 3.3729 | 1.5938 | 1.9244
| 5369 | 0.43519 | 3.0339 | 1.2812 | 2.1681
| 5370 | 0.37037 | 2.7797 | 1.7188 | 2.021
| 5371 | 0.34259 | 3.4576 | 1.2188 | 2.2857
| 5372 | 0.40741 | 2.4576 | 1.0625 | 1.9202
| 5373 | 0.21296 | 2.5085 | 1.4062 | 2.2563
| 5374 | 0.41667 | 2.2881 | 1.7188 | 2.1555
| 5375 | 0.49074 | 2.4068 | 1.875 | 2.4832
| 5376 | 0.47222 | 2.5593 | 1.3125 | 1.9622
| 5377 | 0.49074 | 2.8136 | 1.125 | 2.1807
| 5378 | 0.4537 | 2.2034 | 1.6562 | 1.8361
| 5379 | 0.37963 | 2.6441 | 1.4375 | 2.3361
| 5380 | 0.31481 | 2.661 | 2.1562 | 2.416
| 5381 | 0.35185 | 3.8644 | 1.7812 | 2.3151
| 5382 | 0.4537 | 2.6949 | 1.2812 | 2.1387
| 5383 | 0.41667 | 2.5085 | 1 | 1.9664
| 5384 | 0.41667 | 2.2203 | 1.9062 | 2.4244
| 5385 | 0.46296 | 3.339 | 1.5312 | 2.542
| 5386 | 0.33333 | 2.1864 | 1.4062 | 2.4958
| 5387 | 0.32407 | 2.9492 | 0.8125 | 2.2521
| 5388 | 0.25926 | 2.8136 | 1.4062 | 2.0504
| 5389 | 0.34259 | 2.8983 | 2.0312 | 2.4118
| 5390 | 0.27778 | 2.5763 | 1.5938 | 2.1807
| 5391 | 0.44444 | 2.3729 | 1.0938 | 2.3067
| 5392 | 0.57407 | 3.2034 | 1.6875 | 1.9748
| 5393 | 0.48148 | 2.4407 | 1.4375 | 2.3824
| 5394 | 0.44444 | 2.5932 | 2.1562 | 2.0168
| 5395 | 0.42593 | 2.322 | 1.0938 | 2.1387
| 5396 | 0.2963 | 2.6441 | 1.125 | 2.1723
| 5397 | 0.23148 | 2.7288 | 0.875 | 2.1261
| 5398 | 0.33333 | 3.1356 | 1.2812 | 2.1891
| 5399 | 0.37037 | 3.1186 | 1.6562 | 1.9832
| 5400 | 0.43519 | 1.9153 | 1 | 1.8824
| 5401 | 0.39815 | 3.0508 | 2.1875 | 2.5294
| 5402 | 0.39815 | 2.4576 | 2.1875 | 2.1807
| 5403 | 0.5463 | 2.8475 | 1.1562 | 1.8824
| 5404 | 0.37963 | 2.8814 | 0.96875 | 1.8109
| 5405 | 0.4537 | 3.6441 | 1.9375 | 2.4328
| 5406 | 0.32407 | 2.4746 | 1.375 | 2.605
| 5407 | 0.37963 | 3.2203 | 2.4375 | 2.1513
| 5408 | 0.41667 | 2.0678 | 1.8438 | 2.4328
| 5409 | 0.52778 | 2.7458 | 1.2188 | 1.9706
| 5410 | 0.49074 | 2.3729 | 0.78125 | 2.0294
| 5411 | 0.46296 | 3.0508 | 1.125 | 2.0168
| 5412 | 0.39815 | 3.2203 | 0.90625 | 2.2395
| 5413 | 0.34259 | 2.322 | 1.4375 | 2.0756
| 5414 | 0.30556 | 2.1864 | 1.1875 | 1.7731
| 5415 | 0.36111 | 2.4915 | 1.1562 | 1.8866
| 5416 | 0.43519 | 2.2373 | 1.2188 | 2.0882
| 5417 | 0.53704 | 2.4915 | 1.2812 | 2.3487
| 5418 | 0.52778 | 2.3559 | 0.9375 | 2.1345
| 5419 | 0.26852 | 2.5085 | 0.71875 | 2.1387
| 5420 | 0.47222 | 2.2034 | 1.0625 | 2.1597
| 5421 | 0.42593 | 2.5763 | 2.0938 | 2.063
| 5422 | 0.36111 | 2.7119 | 1.4062 | 2.1387
| 5423 | 0.2963 | 2.339 | 1.5 | 2.2731
| 5424 | 0.4537 | 2.6102 | 1.3438 | 2.0798
| 5425 | 0.53704 | 2.4068 | 1.0312 | 2.0252
| 5426 | 0.44444 | 3.5593 | 0.8125 | 2.0882
| 5427 | 0.5463 | 2.6949 | 1.875 | 1.9748
| 5428 | 0.55556 | 3.1356 | 0.875 | 2.021
| 5429 | 0.43519 | 3.0508 | 1.7188 | 2.0084
| 5430 | 0.40741 | 2.9322 | 0.71875 | 1.9496
| 5431 | 0.33333 | 2.5932 | 1.5625 | 2.3613
| 5432 | 0.48148 | 2.5254 | 1.25 | 1.9874
| 5433 | 0.26852 | 2.0678 | 1.0938 | 2.1933
| 5434 | 0.41667 | 2.1525 | 1.5312 | 2.1092
| 5435 | 0.41667 | 3.5085 | 1.0625 | 2.1218
| 5436 | 0.49074 | 2.8644 | 1.3438 | 2.1345
| 5437 | 0.34259 | 2.6271 | 1.3438 | 2.3025
| 5438 | 0.40741 | 2.8644 | 1.5 | 2.1134
| 5439 | 0.36111 | 2.8983 | 1.625 | 2.1092
| 5440 | 0.41667 | 2.6441 | 1.9375 | 2.042
| 5441 | 0.53704 | 2.2712 | 1.0625 | 2.0378
| 5442 | 0.58333 | 2.8305 | 1.3125 | 2.3782
| 5443 | 0.36111 | 2.7797 | 2.75 | 1.7815
| 5444 | 0.38889 | 2.3729 | 0.96875 | 2.2017
| 5445 | 0.32407 | 4.0678 | 1.5312 | 2.3235
| 5446 | 0.47222 | 2 | 1.8125 | 2.4958
| 5447 | 0.49074 | 2.9661 | 1.1562 | 1.7605
| 5448 | 0.32407 | 2.9831 | 1.125 | 2.0336
| 5449 | 0.47222 | 2.322 | 1.5312 | 2.2437
| 5450 | 0.41667 | 2.5763 | 1.5938 | 2.1429
| 5451 | 0.49074 | 2.661 | 1.4375 | 1.9874
| 5452 | 0.52778 | 2.8475 | 1.25 | 1.9328
| 5453 | 0.36111 | 2.7458 | 1.6875 | 2.1597
| 5454 | 0.33333 | 2.7458 | 1.1875 | 2.3782
| 5455 | 0.25926 | 2.8136 | 1 | 2.1092
| 5456 | 0.31481 | 2.678 | 1.5938 | 1.9622
| 5457 | 0.2963 | 2.5593 | 1.2188 | 2.2899
| 5458 | 0.38889 | 3.1356 | 0.78125 | 2.0672
| 5459 | 0.31481 | 2.0508 | 2.2812 | 2.5084
| 5460 | 0.37037 | 2.4576 | 1.25 | 2.3361
| 5461 | 0.53704 | 2.4237 | 1.7812 | 2.1176
| 5462 | 0.50926 | 1.9831 | 0.90625 | 2.1933
| 5463 | 0.56481 | 2.1186 | 1.25 | 2.2815
| 5464 | 0.52778 | 2.7797 | 1.4062 | 1.8529
| 5465 | 0.37963 | 2.8814 | 2.125 | 2
| 5466 | 0.40741 | 2.3559 | 0.9375 | 2.4034
| 5467 | 0.52778 | 2.1695 | 2.3125 | 1.9622
| 5468 | 0.40741 | 2.4068 | 0.9375 | 2.0336
| 5469 | 0.48148 | 2.8644 | 1.2812 | 2.1218
| 5470 | 0.4537 | 2.7627 | 1.4688 | 2.1681
| 5471 | 0.55556 | 3.3898 | 1.5625 | 2.021
| 5472 | 0.49074 | 2.4407 | 1.6562 | 1.937
| 5473 | 0.32407 | 2.5593 | 0.8125 | 2.0714
| 5474 | 0.35185 | 2.7458 | 1.5312 | 2.2059
| 5475 | 0.33333 | 2.1864 | 2.25 | 1.958
| 5476 | 0.41667 | 2.0169 | 1.2188 | 2.2605
| 5477 | 0.50926 | 2.3559 | 1.5938 | 2.3109
| 5478 | 0.38889 | 3.1186 | 1.1875 | 1.937
| 5479 | 0.44444 | 1.8475 | 1.5312 | 2.1092
| 5480 | 0.28704 | 2.8305 | 1 | 2.1765
| 5481 | 0.34259 | 2.8644 | 1.4688 | 1.9286
| 5482 | 0.53704 | 2.5593 | 1.2188 | 2.1807
| 5483 | 0.37037 | 2.6271 | 1.25 | 2.2647
| 5484 | 0.61111 | 3.3559 | 0.9375 | 1.9538
| 5485 | 0.33333 | 2.6271 | 1.9375 | 1.9412
| 5486 | 0.22222 | 2.4576 | 1.8438 | 2.0966
| 5487 | 0.46296 | 2.7288 | 1.7812 | 2.2353
| 5488 | 0.43519 | 2.322 | 0.78125 | 2.605
| 5489 | 0.34259 | 3.0339 | 0.8125 | 1.9328
| 5490 | 0.60185 | 2.1864 | 1.5 | 1.6723
| 5491 | 0.37037 | 2.7627 | 1.25 | 1.8824
| 5492 | 0.32407 | 2.8644 | 1.7188 | 2.0588
| 5493 | 0.37037 | 2.7966 | 1.3125 | 2.2395
| 5494 | 0.34259 | 2.3051 | 1.3438 | 2.063
| 5495 | 0.44444 | 2.7288 | 0.71875 | 2.6261
| 5496 | 0.42593 | 2.8475 | 1.2188 | 1.7689
| 5497 | 0.42593 | 3.1186 | 1.2812 | 2.1555
| 5498 | 0.32407 | 2 | 1.0938 | 2.105
| 5499 | 0.38889 | 2.8136 | 2.125 | 2.021
| 5500 | 0.40741 | 2.8475 | 1.2188 | 1.9118
| 5501 | 0.31481 | 2.5593 | 0.875 | 2.4916
| 5502 | 0.51852 | 2.8814 | 0.875 | 2.0126
| 5503 | 0.47222 | 2.8475 | 2.3438 | 1.7857
| 5504 | 0.39815 | 2.678 | 1.9062 | 2.1218
| 5505 | 0.33333 | 2.9153 | 0.78125 | 2.0042
| 5506 | 0.62037 | 2.9492 | 1.4375 | 2.0378
| 5507 | 0.44444 | 3.0508 | 0.9375 | 1.9706
| 5508 | 0.40741 | 2.322 | 1.6875 | 2.0798
| 5509 | 0.44444 | 3.0508 | 0.65625 | 1.9244
| 5510 | 0.36111 | 3.0508 | 0.65625 | 1.7353
| 5511 | 0.42593 | 2.9492 | 1.0625 | 1.8193
| 5512 | 0.27778 | 3.9831 | 1.5312 | 2.1891
| 5513 | 0.4537 | 1.9661 | 0.71875 | 1.8782
| 5514 | 0.36111 | 2.8475 | 1.625 | 2.2941
| 5515 | 0.34259 | 2.9492 | 1.1875 | 2.1807
| 5516 | 0.49074 | 2.7627 | 1.3438 | 2.2899
| 5517 | 0.40741 | 1.8136 | 1.9375 | 2.0504
| 5518 | 0.43519 | 3.1186 | 1.5938 | 1.9034
| 5519 | 0.35185 | 2.1864 | 0.96875 | 2.105
| 5520 | 0.30556 | 3.0339 | 1.2188 | 2.4958
| 5521 | 0.39815 | 3.339 | 1.6875 | 1.7815
| 5522 | 0.58333 | 3.0847 | 1.3125 | 2.563
| 5523 | 0.32407 | 2.0678 | 2.3438 | 2.3235
| 5524 | 0.5 | 3.0169 | 1.2188 | 1.8193
| 5525 | 0.39815 | 2.4746 | 2.5 | 2.021
| 5526 | 0.4537 | 2.4237 | 1.0625 | 2.2059
| 5527 | 0.4537 | 2.3729 | 1.4375 | 2.105
| 5528 | 0.2963 | 2.7966 | 0.6875 | 1.9118
| 5529 | 0.38889 | 3.7288 | 1.7812 | 2.1092
| 5530 | 0.5463 | 3.2542 | 0.8125 | 2.2689
| 5531 | 0.37037 | 2.2712 | 1.5 | 1.9496
| 5532 | 0.32407 | 2.1864 | 1.25 | 1.8697
| 5533 | 0.49074 | 2.0169 | 1.3438 | 1.8109
| 5534 | 0.40741 | 2.9831 | 1.3438 | 2.0714
| 5535 | 0.42593 | 2.5254 | 1.3125 | 2.1891
| 5536 | 0.4537 | 2.1695 | 1.6562 | 2.1176
| 5537 | 0.23148 | 2.4746 | 1.6562 | 2.2017
| 5538 | 0.25926 | 2.6271 | 1.4062 | 1.7479
| 5539 | 0.47222 | 3.6441 | 0.59375 | 1.8361
| 5540 | 0.40741 | 2.8983 | 1.9062 | 2.1092
| 5541 | 0.44444 | 2.322 | 0.9375 | 2.084
| 5542 | 0.64815 | 2.661 | 2 | 1.9958
| 5543 | 0.34259 | 2.9661 | 1 | 1.9538
| 5544 | 0.5 | 2.4237 | 1.8125 | 2.2311
| 5545 | 0.66667 | 2.9492 | 0.6875 | 2.3487
| 5546 | 0.36111 | 2.8814 | 1.1562 | 1.9286
| 5547 | 0.4537 | 2.7288 | 2 | 1.8571
| 5548 | 0.34259 | 3.2034 | 0.6875 | 2.1975
| 5549 | 0.36111 | 2.8305 | 1.2812 | 1.8992
| 5550 | 0.47222 | 2.9322 | 1.5 | 1.8697
| 5551 | 0.37963 | 2.7966 | 1.75 | 2.2563
| 5552 | 0.44444 | 2.678 | 1.2188 | 1.7269
| 5553 | 0.34259 | 2.5085 | 1.0625 | 1.9832
| 5554 | 0.42593 | 2.6441 | 1.25 | 2.0084
| 5555 | 0.58333 | 2.4915 | 2.3438 | 2.1471
| 5556 | 0.56481 | 2.322 | 1.6875 | 1.9874
| 5557 | 0.40741 | 2.2203 | 1 | 2.1975
| 5558 | 0.51852 | 3.1017 | 0.8125 | 2.2521
| 5559 | 0.43519 | 2.3051 | 1.2188 | 2.0882
| 5560 | 0.55556 | 2.8475 | 1.8125 | 2.0378
| 5561 | 0.52778 | 2.3559 | 1 | 2.0546
| 5562 | 0.40741 | 3.4746 | 1 | 1.895
| 5563 | 0.37037 | 3.2373 | 0.65625 | 1.8151
| 5564 | 0.48148 | 3.0678 | 1.1875 | 1.8445
| 5565 | 0.41667 | 2.4915 | 0.90625 | 2.0252
| 5566 | 0.42593 | 1.7966 | 2.25 | 1.7815
| 5567 | 0.41667 | 2.4576 | 0.96875 | 1.916
| 5568 | 0.61111 | 2.9661 | 1.6562 | 2.063
| 5569 | 0.46296 | 3.2034 | 2.375 | 2.3739
| 5570 | 0.48148 | 2.9322 | 1.4688 | 2.0084
| 5571 | 0.46296 | 3.1356 | 1.5938 | 1.9538
| 5572 | 0.5 | 3.0508 | 1.5 | 2.2605
| 5573 | 0.41667 | 1.7288 | 2.3125 | 1.8782
| 5574 | 0.37037 | 3.2712 | 1.5625 | 2.2857
| 5575 | 0.46296 | 2.7966 | 1.0938 | 2.4202
| 5576 | 0.37963 | 3.0339 | 1.375 | 1.7899
| 5577 | 0.39815 | 2.8983 | 1.375 | 2.3361
| 5578 | 0.37037 | 3.339 | 1.5625 | 2.5336
| 5579 | 0.5463 | 2.1356 | 1.4062 | 2.1134
| 5580 | 0.44444 | 2.7119 | 1.125 | 2.3319
| 5581 | 0.27778 | 2.5763 | 1.25 | 2.0588
| 5582 | 0.37963 | 2.5085 | 0.875 | 1.8445
| 5583 | 0.40741 | 2.6441 | 1.5938 | 1.7731
| 5584 | 0.5 | 2.6271 | 1.4062 | 2.416
| 5585 | 0.37037 | 2.4746 | 1.5 | 1.7059
| 5586 | 0.30556 | 2.3898 | 1.25 | 2.2101
| 5587 | 0.40741 | 2.9661 | 0.8125 | 2.1387
| 5588 | 0.41667 | 2.5254 | 1.625 | 2.1513
| 5589 | 0.36111 | 2.9492 | 1.0312 | 2.2059
| 5590 | 0.36111 | 2.6949 | 2.25 | 1.8992
| 5591 | 0.27778 | 2.5254 | 1.8438 | 1.9076
| 5592 | 0.4537 | 1.7119 | 1 | 2.3697
| 5593 | 0.51852 | 2.4746 | 1.5 | 2.4748
| 5594 | 0.35185 | 2 | 1.6875 | 1.9706
| 5595 | 0.35185 | 3.1186 | 0.96875 | 2.4496
| 5596 | 0.37963 | 3 | 0.6875 | 2.0588
| 5597 | 0.44444 | 3.322 | 1.125 | 2.1218
| 5598 | 0.42593 | 1.8136 | 1.9062 | 1.9118
| 5599 | 0.48148 | 2.7119 | 1.25 | 2.1429
| 5600 | 0.4537 | 2.8814 | 1.3438 | 2.0882
| 5601 | 0.34259 | 2.8136 | 0.875 | 2.1303
| 5602 | 0.4537 | 2.9153 | 0.84375 | 2.2941
| 5603 | 0.35185 | 2.6441 | 1.5 | 2.0588
| 5604 | 0.49074 | 2.4915 | 1.2188 | 2.584
| 5605 | 0.44444 | 2.6271 | 1.25 | 2.1387
| 5606 | 0.37037 | 2.322 | 0.9375 | 2.1429
| 5607 | 0.37963 | 2.5254 | 2.5312 | 1.7479
| 5608 | 0.33333 | 2.339 | 1.2188 | 2.3571
| 5609 | 0.30556 | 3.0508 | 1.5625 | 2.2857
| 5610 | 0.30556 | 2.3051 | 1.875 | 2.0882
| 5611 | 0.30556 | 3.3559 | 2.0938 | 2.063
| 5612 | 0.33333 | 2.4915 | 1.75 | 2.1765
| 5613 | 0.59259 | 2.7627 | 1.2812 | 2.4496
| 5614 | 0.37037 | 3.1017 | 0.875 | 2
| 5615 | 0.37963 | 3.2373 | 1.6562 | 2.0588
| 5616 | 0.33333 | 3.2542 | 0.90625 | 1.9202
| 5617 | 0.36111 | 2 | 1.6875 | 2.2731
| 5618 | 0.37963 | 2.6271 | 1.625 | 2.084
| 5619 | 0.35185 | 2.7797 | 1.7812 | 1.9958
| 5620 | 0.37037 | 2.7966 | 1 | 2.1261
| 5621 | 0.41667 | 2.8475 | 1.375 | 1.9832
| 5622 | 0.42593 | 2.5424 | 2.4688 | 2.0798
| 5623 | 0.2963 | 2.1186 | 1.4375 | 2.1765
| 5624 | 0.44444 | 3.1017 | 1.625 | 1.9034
| 5625 | 0.44444 | 2.1695 | 1.3438 | 2.4454
| 5626 | 0.42593 | 2.7627 | 1.25 | 2.2311
| 5627 | 0.34259 | 2.1017 | 1.8125 | 1.7563
| 5628 | 0.47222 | 2.8136 | 1.1875 | 1.8908
| 5629 | 0.47222 | 2.322 | 1.125 | 1.7731
| 5630 | 0.41667 | 2.2034 | 1 | 2.0756
| 5631 | 0.46296 | 3.0847 | 1.4062 | 2.2101
| 5632 | 0.41667 | 2.6102 | 1.1562 | 1.9958
| 5633 | 0.40741 | 2.1864 | 1.125 | 2.2941
| 5634 | 0.30556 | 2.5932 | 1.25 | 2.2605
| 5635 | 0.57407 | 2.9322 | 1 | 1.9664
| 5636 | 0.49074 | 3.0339 | 1.4062 | 1.9538
| 5637 | 0.41667 | 2.7119 | 1.1562 | 2.4034
| 5638 | 0.40741 | 2.8814 | 1.3438 | 1.979
| 5639 | 0.59259 | 3 | 1.3438 | 2.0084
| 5640 | 0.34259 | 2.4576 | 2.25 | 1.7605
| 5641 | 0.55556 | 3.1525 | 1.625 | 1.9748
| 5642 | 0.43519 | 2.2542 | 1.5312 | 2.1176
| 5643 | 0.4537 | 2.678 | 1.5312 | 2.0756
| 5644 | 0.49074 | 2.6949 | 0.96875 | 2.3067
| 5645 | 0.42593 | 3.1525 | 2.4062 | 2
| 5646 | 0.42593 | 3.1864 | 1.1875 | 2.0756
| 5647 | 0.50926 | 2.7119 | 1.4062 | 1.9286
| 5648 | 0.38889 | 2.5763 | 1.6875 | 2.1555
| 5649 | 0.33333 | 2.5763 | 1.1562 | 2.2353
| 5650 | 0.21296 | 2.2881 | 1.2188 | 2.2185
| 5651 | 0.46296 | 2.2542 | 1.7812 | 2.1092
| 5652 | 0.50926 | 3.0847 | 1.0625 | 2.0336
| 5653 | 0.42593 | 2.9492 | 1.1875 | 2.3109
| 5654 | 0.32407 | 3.661 | 1.2812 | 2.1261
| 5655 | 0.62963 | 1.5763 | 2.0625 | 2.2353
| 5656 | 0.37037 | 2.4915 | 1.2812 | 2.1176
| 5657 | 0.30556 | 2.3559 | 1.2188 | 2.3992
| 5658 | 0.36111 | 2.8475 | 1 | 1.937
| 5659 | 0.52778 | 2.2373 | 1.8438 | 2.2479
| 5660 | 0.30556 | 3.1017 | 1.5312 | 2.1639
| 5661 | 0.49074 | 2.8983 | 0.9375 | 2.542
| 5662 | 0.31481 | 3.3051 | 1.6875 | 2.0336
| 5663 | 0.2963 | 3.1017 | 1.3125 | 2.0252
| 5664 | 0.37037 | 2.4068 | 1.0312 | 2.2269
| 5665 | 0.43519 | 3.5254 | 0.96875 | 2.0168
| 5666 | 0.4537 | 2.4407 | 1.8125 | 2.1303
| 5667 | 0.42593 | 2.2542 | 0.875 | 2.5042
| 5668 | 0.44444 | 2.8305 | 0.9375 | 1.8277
| 5669 | 0.41667 | 2.1864 | 1.6562 | 2.1471
| 5670 | 0.43519 | 3.339 | 1.4375 | 2.3109
| 5671 | 0.35185 | 2.9492 | 1.6562 | 1.958
| 5672 | 0.4537 | 2.9831 | 1.1875 | 2.1134
| 5673 | 0.37037 | 2.2203 | 1.5312 | 2.1429
| 5674 | 0.43519 | 3.1356 | 1.3438 | 2
| 5675 | 0.51852 | 2.2034 | 1.5312 | 2.0924
| 5676 | 0.40741 | 3.6441 | 1.5625 | 2.2227
| 5677 | 0.41667 | 2.1017 | 1.8438 | 2.1639
| 5678 | 0.42593 | 2.5254 | 1.8438 | 2.2899
| 5679 | 0.36111 | 3.0508 | 1.375 | 1.7983
| 5680 | 0.38889 | 2.4237 | 2.1875 | 1.9538
| 5681 | 0.38889 | 4.1525 | 1.125 | 1.9286
| 5682 | 0.37037 | 2.8814 | 1.4062 | 1.9916
| 5683 | 0.30556 | 2.5593 | 1.1875 | 2.0168
| 5684 | 0.39815 | 2.2203 | 1.6562 | 2.0252
| 5685 | 0.32407 | 2.8814 | 1.9688 | 1.6849
| 5686 | 0.5 | 2.8644 | 1.25 | 2.2941
| 5687 | 0.38889 | 2.4237 | 1.4375 | 1.8739
| 5688 | 0.49074 | 2.1695 | 1.3438 | 1.9706
| 5689 | 0.53704 | 2.7288 | 1.3125 | 1.8445
| 5690 | 0.39815 | 3.1186 | 1.5 | 1.9916
| 5691 | 0.53704 | 2.1186 | 0.96875 | 1.8319
| 5692 | 0.37963 | 2.9322 | 1.9688 | 2.1513
| 5693 | 0.41667 | 3.3051 | 1.0625 | 2.0672
| 5694 | 0.5463 | 3.1864 | 2.1562 | 1.9328
| 5695 | 0.51852 | 2.4576 | 1.0312 | 2.2647
| 5696 | 0.52778 | 2.322 | 1.6562 | 2.0378
| 5697 | 0.36111 | 3.0508 | 2.2188 | 1.8697
| 5698 | 0.46296 | 2.8305 | 1.4688 | 2.0336
| 5699 | 0.43519 | 3.1017 | 1.6875 | 1.9496
| 5700 | 0.26852 | 2.2203 | 0.84375 | 2.0294
| 5701 | 0.39815 | 2.3559 | 1.625 | 2.021
| 5702 | 0.47222 | 2.7966 | 1.3125 | 2.105
| 5703 | 0.50926 | 3.4237 | 2.0312 | 1.958
| 5704 | 0.4537 | 2.2542 | 2 | 2.0588
| 5705 | 0.38889 | 2.7119 | 1.8125 | 2.1134
| 5706 | 0.38889 | 2.2203 | 1.4688 | 1.9244
| 5707 | 0.28704 | 3.4746 | 1.6875 | 2.2269
| 5708 | 0.35185 | 2.6441 | 1.0312 | 2.0336
| 5709 | 0.31481 | 3.322 | 1.1562 | 1.9874
| 5710 | 0.41667 | 2.6949 | 0.8125 | 2.6471
| 5711 | 0.38889 | 2.2881 | 1.7188 | 2.416
| 5712 | 0.37963 | 3.1525 | 1.2188 | 2.2059
| 5713 | 0.33333 | 2.1695 | 1.4375 | 2.1387
| 5714 | 0.40741 | 3.7288 | 1.0625 | 2.2101
| 5715 | 0.2963 | 2.5424 | 1.2812 | 2.1345
| 5716 | 0.47222 | 3.0339 | 1.25 | 1.7941
| 5717 | 0.37963 | 2.339 | 0.90625 | 1.8739
| 5718 | 0.37963 | 2.6441 | 1.25 | 1.9664
| 5719 | 0.34259 | 2.2712 | 1.1562 | 1.9328
| 5720 | 0.37963 | 2.6441 | 1.1875 | 2.1429
| 5721 | 0.56481 | 3.0847 | 1 | 1.7227
| 5722 | 0.34259 | 2.5763 | 0.9375 | 1.7983
| 5723 | 0.43519 | 3.3729 | 1.375 | 2.0756
| 5724 | 0.50926 | 1.8814 | 1.625 | 1.979
| 5725 | 0.27778 | 2.4407 | 1.3438 | 1.9538
| 5726 | 0.49074 | 3.0847 | 1.6562 | 2.2227
| 5727 | 0.51852 | 3.9322 | 1.2812 | 2.0546
| 5728 | 0.41667 | 2.0678 | 1 | 2.4958
| 5729 | 0.33333 | 2.7119 | 1.2188 | 2.0462
| 5730 | 0.37963 | 3.2881 | 1.6562 | 2.0756
| 5731 | 0.44444 | 2.8305 | 1.125 | 2.2185
| 5732 | 0.41667 | 3.3051 | 1.9688 | 1.8151
| 5733 | 0.53704 | 1.7797 | 1.75 | 2.1345
| 5734 | 0.26852 | 2.3729 | 0.875 | 2.1303
| 5735 | 0.35185 | 3.0847 | 1.2812 | 2.084
| 5736 | 0.30556 | 3.2034 | 1.4688 | 1.8487
| 5737 | 0.43519 | 3.1017 | 1.875 | 1.9706
| 5738 | 0.46296 | 3.5593 | 1.875 | 1.9118
| 5739 | 0.42593 | 2.7966 | 1.5312 | 1.6891
| 5740 | 0.40741 | 2.6102 | 1.25 | 2.1513
| 5741 | 0.46296 | 2.2373 | 1.0625 | 2.0924
| 5742 | 0.47222 | 2.7966 | 2.5 | 2.3319
| 5743 | 0.34259 | 2.8644 | 1.9062 | 1.7227
| 5744 | 0.33333 | 2.4407 | 2.125 | 2.021
| 5745 | 0.39815 | 2.6441 | 1.2812 | 2.1975
| 5746 | 0.32407 | 2.661 | 2.1562 | 2.0042
| 5747 | 0.62963 | 2.2542 | 0.96875 | 1.9454
| 5748 | 0.37037 | 2 | 0.96875 | 2.2143
| 5749 | 0.37037 | 2.9322 | 1.25 | 1.9202
| 5750 | 0.51852 | 2.322 | 1.9062 | 1.9286
| 5751 | 0.4537 | 3.0339 | 1.4688 | 2.0252
| 5752 | 0.2963 | 1.8136 | 1.1562 | 1.8025
| 5753 | 0.37037 | 2.5593 | 1.75 | 1.9538
| 5754 | 0.41667 | 2.6441 | 1.3438 | 2.3571
| 5755 | 0.25926 | 2.7119 | 2.5938 | 2.2983
| 5756 | 0.31481 | 2.4237 | 0.90625 | 1.8193
| 5757 | 0.52778 | 2.8814 | 1.9688 | 2.458
| 5758 | 0.48148 | 2.8136 | 2.625 | 2.1765
| 5759 | 0.37037 | 2.1864 | 1.3125 | 2.1933
| 5760 | 0.38889 | 2.7288 | 1.0938 | 1.8445
| 5761 | 0.36111 | 2.4915 | 2.5312 | 2.2017
| 5762 | 0.2963 | 2.5932 | 1 | 1.9706
| 5763 | 0.39815 | 2.7966 | 1.5938 | 1.895
| 5764 | 0.35185 | 2.8475 | 1.2188 | 2.2059
| 5765 | 0.30556 | 2.3051 | 1.5625 | 1.9328
| 5766 | 0.40741 | 2.9661 | 1.5625 | 1.8697
| 5767 | 0.43519 | 3.0169 | 1.4375 | 2.1471
| 5768 | 0.37963 | 2.8305 | 1.3125 | 2.3151
| 5769 | 0.37963 | 2.4407 | 1.875 | 2.2143
| 5770 | 0.33333 | 2.2203 | 2.5 | 2.0042
| 5771 | 0.33333 | 2.5932 | 1.0625 | 1.9538
| 5772 | 0.50926 | 3.4407 | 1.4688 | 2.1765
| 5773 | 0.23148 | 2.3729 | 1.625 | 1.7563
| 5774 | 0.37963 | 3.4407 | 1.625 | 2.2311
| 5775 | 0.46296 | 2.6271 | 1.2812 | 2.4034
| 5776 | 0.37037 | 2.3729 | 2.2188 | 2.458
| 5777 | 0.44444 | 2.8644 | 1.2812 | 2.0042
| 5778 | 0.36111 | 2.7288 | 2.375 | 1.9664
| 5779 | 0.37963 | 1.9831 | 1.8125 | 2.3277
| 5780 | 0.40741 | 2.6949 | 2.75 | 2.2059
| 5781 | 0.44444 | 3.3898 | 0.8125 | 2.2395
| 5782 | 0.53704 | 3.4068 | 1.3125 | 2.0882
| 5783 | 0.30556 | 2.2542 | 1.5938 | 2
| 5784 | 0.37963 | 2.3559 | 1.375 | 2.1513
| 5785 | 0.39815 | 2.5424 | 1.625 | 1.8319
| 5786 | 0.5 | 2.2373 | 2.7188 | 2.0546
| 5787 | 0.35185 | 3.3559 | 1.5938 | 2.2857
| 5788 | 0.47222 | 3.2373 | 2.125 | 1.7311
| 5789 | 0.41667 | 2.2034 | 2.25 | 1.8403
| 5790 | 0.5463 | 2.5254 | 1.0312 | 2.1933
| 5791 | 0.47222 | 2.8814 | 1.5625 | 1.8866
| 5792 | 0.31481 | 2.3729 | 1.4688 | 1.9538
| 5793 | 0.31481 | 2.0847 | 1.3438 | 2.2185
| 5794 | 0.31481 | 3.6441 | 1.9062 | 2.4664
| 5795 | 0.36111 | 2.2203 | 1.3125 | 1.958
| 5796 | 0.7037 | 2.661 | 1.0625 | 2.1891
| 5797 | 0.35185 | 1.8475 | 1.4688 | 2.458
| 5798 | 0.40741 | 2.4915 | 1.3125 | 2.0966
| 5799 | 0.37037 | 2.7797 | 1.6875 | 1.8824
| 5800 | 0.33333 | 2.7288 | 1.7188 | 2.0546
| 5801 | 0.51852 | 3.0339 | 1.5 | 1.7395
| 5802 | 0.41667 | 2.8305 | 0.71875 | 2.2899
| 5803 | 0.59259 | 2.8136 | 1.75 | 2.0126
| 5804 | 0.53704 | 2.3051 | 1.25 | 1.8529
| 5805 | 0.44444 | 3.6271 | 2.0938 | 1.9244
| 5806 | 0.38889 | 2.4576 | 0.875 | 2.0126
| 5807 | 0.35185 | 3.2034 | 1.125 | 2.1008
| 5808 | 0.35185 | 2.322 | 1.7812 | 2.3067
| 5809 | 0.37963 | 3.0339 | 1.7188 | 1.9286
| 5810 | 0.38889 | 2.1356 | 0.875 | 2.0882
| 5811 | 0.39815 | 2.2712 | 0.9375 | 1.8908
| 5812 | 0.39815 | 2.5593 | 1.25 | 1.9496
| 5813 | 0.34259 | 2.6949 | 1.4062 | 2.2521
| 5814 | 0.50926 | 1.8983 | 0.78125 | 2.4076
| 5815 | 0.32407 | 2.5424 | 1.0625 | 2.0798
| 5816 | 0.41667 | 2.4576 | 1.0625 | 1.8361
| 5817 | 0.31481 | 2.3051 | 2.2188 | 2.4916
| 5818 | 0.35185 | 2.8305 | 1.5 | 2.2983
| 5819 | 0.2963 | 2.2712 | 0.71875 | 2.3067
| 5820 | 0.48148 | 2.9492 | 1.5625 | 2.2689
| 5821 | 0.5463 | 3.2881 | 1.5625 | 1.979
| 5822 | 0.34259 | 2.5254 | 0.96875 | 2.5126
| 5823 | 0.39815 | 3.2373 | 0.625 | 2
| 5824 | 0.26852 | 3.1864 | 1.8438 | 2.1261
| 5825 | 0.2963 | 2.4576 | 1.1562 | 2.3571
| 5826 | 0.37037 | 2.9153 | 0.96875 | 2.1555
| 5827 | 0.49074 | 2.6949 | 1.6562 | 1.9748
| 5828 | 0.2963 | 3.4068 | 1.6562 | 2.1261
| 5829 | 0.4537 | 2.8136 | 1.2812 | 2.1891
| 5830 | 0.55556 | 2.0169 | 0.78125 | 1.7647
| 5831 | 0.30556 | 2.7797 | 1.7188 | 2.1008
| 5832 | 0.41667 | 2.5424 | 1.8438 | 2.1639
| 5833 | 0.33333 | 3.4237 | 1.5625 | 1.9958
| 5834 | 0.39815 | 2.339 | 0.875 | 2.105
| 5835 | 0.37963 | 2.3559 | 1.1875 | 1.9664
| 5836 | 0.25926 | 3.3729 | 1.2188 | 2.2101
| 5837 | 0.40741 | 2.6949 | 1.8438 | 1.9748
| 5838 | 0.37037 | 2.2373 | 0.90625 | 2.3866
| 5839 | 0.36111 | 2.4068 | 1.5312 | 2.2689
| 5840 | 0.36111 | 2.6271 | 0.96875 | 2.6555
| 5841 | 0.34259 | 2.3559 | 1.375 | 1.9286
| 5842 | 0.24074 | 2.6441 | 1.1875 | 2.1765
| 5843 | 0.41667 | 3.0339 | 1.5312 | 2.0126
| 5844 | 0.42593 | 2.2881 | 1.8438 | 2.2185
| 5845 | 0.48148 | 3.0339 | 1.5312 | 1.9706
| 5846 | 0.4537 | 2.8305 | 1.1875 | 2.3445
| 5847 | 0.35185 | 2.8644 | 0.6875 | 1.937
| 5848 | 0.51852 | 3.0847 | 1.7188 | 2.0462
| 5849 | 0.41667 | 2.4407 | 0.84375 | 1.9244
| 5850 | 0.41667 | 2.7119 | 1.0938 | 2.0042
| 5851 | 0.44444 | 2.6949 | 1.6562 | 2.1597
| 5852 | 0.28704 | 3.2542 | 1.0312 | 2.0378
| 5853 | 0.2037 | 2.6949 | 1.2188 | 2.0504
| 5854 | 0.31481 | 2.4068 | 1.3125 | 1.9664
| 5855 | 0.49074 | 2.6102 | 1.0938 | 2.2269
| 5856 | 0.36111 | 3.2712 | 1.25 | 1.9034
| 5857 | 0.41667 | 2.2881 | 1 | 1.8361
| 5858 | 0.37963 | 2.5254 | 0.96875 | 2.1891
| 5859 | 0.4537 | 2.6441 | 1.75 | 2.2689
| 5860 | 0.32407 | 1.9831 | 1.6562 | 2.3193
| 5861 | 0.35185 | 3.1017 | 1.5 | 2.2563
| 5862 | 0.31481 | 2.322 | 1.75 | 2.0042
| 5863 | 0.5 | 3.1864 | 1.125 | 2.0588
| 5864 | 0.43519 | 2.9831 | 1.5312 | 1.9874
| 5865 | 0.5 | 3.1356 | 1.4375 | 1.8992
| 5866 | 0.52778 | 2.339 | 1.1562 | 2.1681
| 5867 | 0.4537 | 2.8305 | 0.78125 | 1.9076
| 5868 | 0.44444 | 2.2034 | 1.6562 | 2.1429
| 5869 | 0.34259 | 2.8983 | 2.0625 | 1.9706
| 5870 | 0.30556 | 3.1864 | 1.8438 | 1.958
| 5871 | 0.55556 | 2.3729 | 1.3125 | 1.937
| 5872 | 0.38889 | 2.9153 | 1.125 | 1.8319
| 5873 | 0.38889 | 2.1017 | 1.5938 | 2.2269
| 5874 | 0.43519 | 2.2203 | 1.25 | 1.8235
| 5875 | 0.4537 | 2.2881 | 0.90625 | 1.8782
| 5876 | 0.37963 | 3.0169 | 0.96875 | 1.9454
| 5877 | 0.39815 | 2.5593 | 1.3438 | 1.9958
| 5878 | 0.52778 | 3.0678 | 1.0312 | 1.9454
| 5879 | 0.50926 | 3.2373 | 0.875 | 2.1597
| 5880 | 0.34259 | 2.7627 | 1.75 | 1.9916
| 5881 | 0.37963 | 2.8136 | 1.0938 | 2.2101
| 5882 | 0.39815 | 3.7119 | 1.5 | 2.2563
| 5883 | 0.37963 | 2.9661 | 1.5312 | 2.021
| 5884 | 0.46296 | 2.0847 | 2.125 | 2.0126
| 5885 | 0.38889 | 2.8305 | 1.3125 | 1.9286
| 5886 | 0.42593 | 2.5763 | 1.5938 | 2.1555
| 5887 | 0.41667 | 2.4915 | 1.7188 | 1.8992
| 5888 | 0.42593 | 2.5932 | 1.3125 | 1.6975
| 5889 | 0.4537 | 2.4576 | 2.3438 | 2.2689
| 5890 | 0.38889 | 2.7119 | 0.84375 | 2.1134
| 5891 | 0.42593 | 2.8305 | 1.2188 | 2.1555
| 5892 | 0.34259 | 2.3898 | 0.78125 | 2.5588
| 5893 | 0.53704 | 1.9492 | 1.1562 | 2.1975
| 5894 | 0.36111 | 3.1186 | 2.0938 | 1.9622
| 5895 | 0.59259 | 2.661 | 1.625 | 2
| 5896 | 0.36111 | 3.4915 | 1.7812 | 2.1134
| 5897 | 0.51852 | 3.1356 | 1.0938 | 1.958
| 5898 | 0.52778 | 2.5593 | 1.5938 | 2.3235
| 5899 | 0.37963 | 2.322 | 1 | 1.9034
| 5900 | 0.48148 | 2.3729 | 1.2188 | 1.8613
| 5901 | 0.49074 | 2.5424 | 1.3438 | 2.2605
| 5902 | 0.32407 | 2.8136 | 1.2188 | 1.8529
| 5903 | 0.48148 | 2.9831 | 1.25 | 1.9244
| 5904 | 0.7037 | 3.1864 | 1.2188 | 2.3824
| 5905 | 0.42593 | 2.4068 | 1.0938 | 1.9286
| 5906 | 0.35185 | 2.5932 | 1 | 1.9958
| 5907 | 0.63889 | 2.9661 | 1.25 | 2.1345
| 5908 | 0.32407 | 1.8475 | 1.7188 | 2.0084
| 5909 | 0.40741 | 2.9831 | 1.2812 | 1.8193
| 5910 | 0.37963 | 2 | 0.78125 | 1.9328
| 5911 | 0.37037 | 2.6949 | 2.2812 | 2.1975
| 5912 | 0.39815 | 2.8814 | 1.5312 | 2.0252
| 5913 | 0.32407 | 2.8136 | 1.4688 | 2.0924
| 5914 | 0.34259 | 2.0678 | 1.75 | 2.0336
| 5915 | 0.52778 | 3.2203 | 1.9688 | 1.9496
| 5916 | 0.50926 | 2.6102 | 0.53125 | 2.1008
| 5917 | 0.44444 | 2.3559 | 1.5938 | 2.0294
| 5918 | 0.50926 | 3.3559 | 1.1562 | 1.9958
| 5919 | 0.48148 | 2.4746 | 2.1875 | 2.1597
| 5920 | 0.49074 | 1.9831 | 0.65625 | 2.2017
| 5921 | 0.41667 | 2.3898 | 1.1875 | 2.3193
| 5922 | 0.41667 | 2.3729 | 0.9375 | 1.8445
| 5923 | 0.47222 | 2.4237 | 1.4375 | 2.2395
| 5924 | 0.37963 | 1.6949 | 1.4062 | 2.2437
| 5925 | 0.27778 | 2.9831 | 1.2188 | 2.0042
| 5926 | 0.36111 | 2.322 | 1 | 2.0126
| 5927 | 0.26852 | 2.4407 | 0.96875 | 1.8319
| 5928 | 0.41667 | 2.4407 | 0.90625 | 1.7941
| 5929 | 0.25 | 2.2373 | 1.25 | 2.105
| 5930 | 0.50926 | 2.4576 | 0.6875 | 1.8361
| 5931 | 0.44444 | 2.2712 | 2.4062 | 1.8235
| 5932 | 0.42593 | 2.5932 | 1.9375 | 2.0714
| 5933 | 0.57407 | 2.5763 | 1.625 | 2.0546
| 5934 | 0.25926 | 2.7458 | 0.96875 | 2.1513
| 5935 | 0.5 | 3.6102 | 0.9375 | 1.958
| 5936 | 0.33333 | 3.2203 | 0.625 | 2.1807
| 5937 | 0.44444 | 2.9153 | 1.2188 | 2.3403
| 5938 | 0.4537 | 2.9661 | 1.9062 | 1.8487
| 5939 | 0.37963 | 2.2373 | 1.5938 | 1.8782
| 5940 | 0.53704 | 2.8475 | 1.125 | 2.0504
| 5941 | 0.4537 | 2.4915 | 1.1562 | 2.2353
| 5942 | 0.34259 | 3.0847 | 1.3438 | 1.9412
| 5943 | 0.40741 | 2.8475 | 0.9375 | 2.1723
| 5944 | 0.40741 | 3.0339 | 1.4375 | 2.0378
| 5945 | 0.32407 | 2.2203 | 1.7812 | 2.1597
| 5946 | 0.47222 | 2.8814 | 1.2188 | 2
| 5947 | 0.58333 | 2.6271 | 1.125 | 2.0168
| 5948 | 0.46296 | 2.4407 | 1.4375 | 2.2479
| 5949 | 0.35185 | 3 | 1.2188 | 2.2479
| 5950 | 0.34259 | 2.9661 | 1.3438 | 2.6008
| 5951 | 0.40741 | 2.8814 | 1.2188 | 1.8067
| 5952 | 0.4537 | 2.7627 | 1.0312 | 1.9958
| 5953 | 0.38889 | 2.2881 | 1.6875 | 1.7395
| 5954 | 0.43519 | 2.8305 | 1.4375 | 2.042
| 5955 | 0.34259 | 2.8136 | 1.0938 | 2.4118
| 5956 | 0.62037 | 3.2034 | 1.5 | 2.2017
| 5957 | 0.43519 | 3.1695 | 2.125 | 2.1639
| 5958 | 0.4537 | 2.9661 | 0.96875 | 2.1891
| 5959 | 0.60185 | 3.2373 | 1.5312 | 2.1933
| 5960 | 0.44444 | 2.5085 | 1.5 | 2.3908
| 5961 | 0.42593 | 2.5593 | 1.3438 | 2.1218
| 5962 | 0.37963 | 3.5932 | 1.0938 | 2.1807
| 5963 | 0.42593 | 3.5593 | 2.5938 | 2.2395
| 5964 | 0.39815 | 2.322 | 1.625 | 1.937
| 5965 | 0.4537 | 2.6441 | 1.375 | 2.3697
| 5966 | 0.2963 | 2.6271 | 1.5625 | 2.3067
| 5967 | 0.51852 | 3.339 | 0.84375 | 1.9454
| 5968 | 0.58333 | 2.0169 | 1.8125 | 1.9832
| 5969 | 0.41667 | 2.5763 | 1.7812 | 1.8697
| 5970 | 0.28704 | 2.0678 | 1.3125 | 1.9496
| 5971 | 0.34259 | 2.6441 | 1.1875 | 2.2479
| 5972 | 0.55556 | 1.9492 | 1.0938 | 2.0126
| 5973 | 0.31481 | 2.7966 | 1.5 | 2.1807
| 5974 | 0.53704 | 2.5763 | 1.3125 | 2.0294
| 5975 | 0.26852 | 2.2712 | 0.96875 | 2.0378
| 5976 | 0.31481 | 3.1186 | 0.75 | 2.0756
| 5977 | 0.40741 | 3.6949 | 1.0938 | 2.1891
| 5978 | 0.5 | 3.2034 | 1.3438 | 2.0336
| 5979 | 0.34259 | 2.3559 | 2.2812 | 1.9244
| 5980 | 0.37037 | 2.2203 | 1.2812 | 2.084
| 5981 | 0.37037 | 2.8136 | 1.25 | 1.9454
| 5982 | 0.34259 | 2.8475 | 1.0312 | 1.937
| 5983 | 0.60185 | 3.1186 | 0.71875 | 1.9244
| 5984 | 0.31481 | 1.8814 | 2.125 | 1.8908
| 5985 | 0.65741 | 2.8475 | 1.8438 | 2.1975
| 5986 | 0.57407 | 2.6102 | 0.90625 | 2.3992
| 5987 | 0.42593 | 2.3051 | 1.4375 | 1.8487
| 5988 | 0.49074 | 2.5593 | 1.0312 | 1.9496
| 5989 | 0.34259 | 2.1186 | 0.65625 | 1.9748
| 5990 | 0.86111 | 2.0678 | 1.9062 | 2.2857
| 5991 | 0.5463 | 2.4237 | 2.0938 | 1.937
| 5992 | 0.38889 | 3.3051 | 0.8125 | 1.9832
| 5993 | 0.53704 | 2.8644 | 1.6562 | 2.1891
| 5994 | 0.50926 | 3.3559 | 1.5312 | 2.2773
| 5995 | 0.37037 | 3.1017 | 0.9375 | 2.2311
| 5996 | 0.49074 | 2.9831 | 1.2812 | 1.9958
| 5997 | 0.39815 | 1.7627 | 1.3125 | 2.2353
| 5998 | 0.57407 | 3.0678 | 1.4688 | 2.1176
| 5999 | 0.30556 | 3.2542 | 0.96875 | 2.1723
| 6000 | 0.26852 | 2.7966 | 1.3438 | 2.0504
| 6001 | 0.42593 | 2.5763 | 2.0625 | 1.9706
| 6002 | 0.35185 | 2.2203 | 1.1562 | 2.0882
| 6003 | 0.37963 | 3.1356 | 1.7188 | 2.0294
| 6004 | 0.44444 | 2.322 | 1.5312 | 1.895
| 6005 | 0.59259 | 2.7119 | 1.1875 | 2.1008
| 6006 | 0.36111 | 2.7458 | 1.5938 | 1.8866
| 6007 | 0.26852 | 1.7119 | 1.2188 | 2.2101
| 6008 | 0.26852 | 2.678 | 1.875 | 2.5
| 6009 | 0.28704 | 2.0508 | 2.5 | 2.0168
| 6010 | 0.40741 | 3.4915 | 0.90625 | 2.3235
| 6011 | 0.46296 | 2.5932 | 1 | 1.9118
| 6012 | 0.49074 | 2.8475 | 1.1562 | 2.1303
| 6013 | 0.4537 | 2.1017 | 1.375 | 1.9958
| 6014 | 0.43519 | 3.661 | 1.5938 | 1.9538
| 6015 | 0.44444 | 2.8305 | 0.96875 | 2.0882
| 6016 | 0.5 | 3.2712 | 1.25 | 2.2521
| 6017 | 0.2963 | 2.322 | 1.8125 | 2.7647
| 6018 | 0.38889 | 2.2542 | 1.7188 | 2.2395
| 6019 | 0.38889 | 3.1864 | 1.5312 | 2.4202
| 6020 | 0.25926 | 2.7797 | 0.96875 | 2.3151
| 6021 | 0.4537 | 2.1864 | 2.1875 | 2.1933
| 6022 | 0.37963 | 2.4746 | 1.125 | 2.0672
| 6023 | 0.40741 | 3.1525 | 1.7812 | 2
| 6024 | 0.34259 | 2.9831 | 1.9375 | 1.8697
| 6025 | 0.47222 | 2.4746 | 1.3438 | 1.9076
| 6026 | 0.5463 | 2.5254 | 1.8125 | 1.9916
| 6027 | 0.5 | 3.5424 | 1 | 2.0504
| 6028 | 0.5 | 2.6949 | 1.4688 | 1.9496
| 6029 | 0.44444 | 2.7458 | 1.0938 | 2.1429
| 6030 | 0.49074 | 2.2542 | 1.5938 | 2.1555
| 6031 | 0.39815 | 2.1864 | 2.25 | 1.8529
| 6032 | 0.25926 | 4.0169 | 1.8125 | 2.2017
| 6033 | 0.44444 | 3.0678 | 2.0938 | 2.0924
| 6034 | 0.37037 | 3.1186 | 1.75 | 2.1134
| 6035 | 0.38889 | 2.2712 | 1.4688 | 1.9832
| 6036 | 0.2963 | 2.8475 | 1.0625 | 1.9328
| 6037 | 0.42593 | 2.2373 | 2 | 2.2773
| 6038 | 0.34259 | 4.0339 | 1.5938 | 1.9622
| 6039 | 0.48148 | 2.6271 | 1.875 | 2.3403
| 6040 | 0.43519 | 3.3051 | 1.3438 | 2.0168
| 6041 | 0.2963 | 2.1525 | 1.0625 | 2.1387
| 6042 | 0.2963 | 2.4407 | 1.125 | 2.2857
| 6043 | 0.46296 | 2.1864 | 1.5 | 2.4034
| 6044 | 0.41667 | 2.7458 | 1.7812 | 1.8571
| 6045 | 0.41667 | 2.8814 | 2.4062 | 2.1008
| 6046 | 0.47222 | 2.2881 | 1.1875 | 2.5378
| 6047 | 0.38889 | 2.8305 | 1.25 | 2.021
| 6048 | 0.47222 | 2.0678 | 2.625 | 1.895
| 6049 | 0.37037 | 3.2373 | 0.90625 | 1.8992
| 6050 | 0.44444 | 2.2034 | 1.3438 | 2.042
| 6051 | 0.26852 | 2.4915 | 2.0312 | 2.6597
| 6052 | 0.39815 | 2.2034 | 1.3125 | 2.416
| 6053 | 0.57407 | 3.0678 | 1.0625 | 2.1218
| 6054 | 0.30556 | 2.0339 | 1.625 | 1.9748
| 6055 | 0.39815 | 2.3898 | 1.375 | 2.2815
| 6056 | 0.44444 | 2.2203 | 1.125 | 2.1387
| 6057 | 0.44444 | 2.8305 | 1.5938 | 2.1134
| 6058 | 0.40741 | 2.0508 | 1.875 | 1.8739
| 6059 | 0.42593 | 3.0169 | 1.0312 | 2.1218
| 6060 | 0.53704 | 3.5254 | 1.3438 | 1.8445
| 6061 | 0.55556 | 2.4915 | 2.0938 | 1.8277
| 6062 | 0.32407 | 3.9661 | 1.1562 | 2
| 6063 | 0.30556 | 2.2881 | 1.8125 | 1.9916
| 6064 | 0.26852 | 2.3898 | 1.4062 | 2.1975
| 6065 | 0.41667 | 2.9492 | 1.25 | 1.8025
| 6066 | 0.43519 | 1.7627 | 1.7812 | 2.4244
| 6067 | 0.25 | 2.8475 | 1.5312 | 1.8655
| 6068 | 0.36111 | 3.1356 | 1.6562 | 2.1807
| 6069 | 0.52778 | 2.5424 | 1.5312 | 2.042
| 6070 | 0.37037 | 3.0847 | 0.96875 | 2.1597
| 6071 | 0.47222 | 2.7288 | 1.5 | 2.0462
| 6072 | 0.44444 | 2.9322 | 1.5312 | 2.2647
| 6073 | 0.41667 | 3 | 1.5312 | 2.1681
| 6074 | 0.52778 | 2.2542 | 1.5625 | 2.1345
| 6075 | 0.37963 | 2.8136 | 1.6562 | 1.8571
| 6076 | 0.39815 | 2.0678 | 2.2812 | 1.9916
| 6077 | 0.44444 | 2.4915 | 2.0312 | 2.5546
| 6078 | 0.37037 | 3.2542 | 1.625 | 1.7269
| 6079 | 0.49074 | 2.322 | 1.3125 | 2.0966
| 6080 | 0.41667 | 3.2034 | 1.4688 | 1.7143
| 6081 | 0.61111 | 2.7966 | 0.8125 | 2.0966
| 6082 | 0.53704 | 2.7119 | 1.375 | 1.9412
| 6083 | 0.38889 | 2.4068 | 1.7188 | 2.2941
| 6084 | 0.40741 | 3 | 2.25 | 2.1092
| 6085 | 0.4537 | 2.6102 | 1.4062 | 2.2059
| 6086 | 0.43519 | 2.5593 | 1.8438 | 2.2647
| 6087 | 0.46296 | 2.2542 | 1.25 | 2.2773
| 6088 | 0.43519 | 2.8305 | 1.4062 | 2.1891
| 6089 | 0.39815 | 2.4915 | 1.75 | 2.021
| 6090 | 0.33333 | 2.339 | 1.3438 | 1.8487
| 6091 | 0.27778 | 2.9153 | 1.2188 | 2.0546
| 6092 | 0.41667 | 3.5085 | 1.2188 | 1.9748
| 6093 | 0.37037 | 2.7119 | 1.1875 | 2.4286
| 6094 | 0.58333 | 2.8136 | 0.96875 | 1.9244
| 6095 | 0.25926 | 2.4576 | 0.6875 | 1.8529
| 6096 | 0.49074 | 3.2542 | 1.4062 | 2.1176
| 6097 | 0.41667 | 2.7797 | 1.25 | 2.2143
| 6098 | 0.35185 | 2.6949 | 1.375 | 1.9076
| 6099 | 0.60185 | 3.2881 | 1.125 | 2.1891
| 6100 | 0.48148 | 2.7627 | 1 | 2.1513
| 6101 | 0.43519 | 2.661 | 1.4688 | 2.1513
| 6102 | 0.56481 | 2.1017 | 0.875 | 1.937
| 6103 | 0.35185 | 3.0678 | 0.8125 | 2.1681
| 6104 | 0.46296 | 3.661 | 1.1875 | 2.3613
| 6105 | 0.38889 | 2.4915 | 1.1875 | 1.9664
| 6106 | 0.52778 | 3.1864 | 1.7188 | 2.5084
| 6107 | 0.42593 | 2.7627 | 1.1875 | 2.1723
| 6108 | 0.36111 | 2 | 0.84375 | 1.9832
| 6109 | 0.38889 | 2.8644 | 1.8438 | 2.2311
| 6110 | 0.31481 | 2.661 | 1.5625 | 1.8445
| 6111 | 0.39815 | 2.7966 | 1.0312 | 2.3992
| 6112 | 0.32407 | 3.1356 | 2.0938 | 2.0798
| 6113 | 0.24074 | 3.1864 | 1.4375 | 1.979
| 6114 | 0.49074 | 2.1356 | 1.4688 | 1.9832
| 6115 | 0.35185 | 3.0508 | 1.5938 | 1.8782
| 6116 | 0.39815 | 3.5763 | 1.1562 | 1.916
| 6117 | 0.37963 | 2.7119 | 1.6875 | 2.1639
| 6118 | 0.44444 | 2.7119 | 1.8125 | 2.3529
| 6119 | 0.49074 | 2.8814 | 1.9062 | 1.8613
| 6120 | 0.44444 | 2.3559 | 1.5625 | 1.9286
| 6121 | 0.52778 | 2.7288 | 1.5 | 1.7857
| 6122 | 0.35185 | 2.5593 | 2.1875 | 2.0966
| 6123 | 0.28704 | 2.5085 | 1.1562 | 1.9244
| 6124 | 0.41667 | 3.7627 | 1.0312 | 2.1471
| 6125 | 0.37037 | 2.9153 | 1.375 | 1.9706
| 6126 | 0.42593 | 3.0339 | 2.3438 | 2.0168
| 6127 | 0.51852 | 2.6441 | 1.4375 | 2.1555
| 6128 | 0.38889 | 2.678 | 1.4375 | 2.0504
| 6129 | 0.44444 | 2.5424 | 1.0312 | 2.1092
| 6130 | 0.36111 | 3.2542 | 0.78125 | 1.9454
| 6131 | 0.30556 | 2.5085 | 1.75 | 1.8613
| 6132 | 0.33333 | 2.7797 | 1.3125 | 1.9706
| 6133 | 0.40741 | 3.2373 | 0.84375 | 2.042
| 6134 | 0.47222 | 3.4068 | 1.7812 | 1.9664
| 6135 | 0.49074 | 2.9831 | 2 | 2.3739
| 6136 | 0.40741 | 2.3729 | 1.8125 | 2.0504
| 6137 | 0.62037 | 2.6441 | 0.8125 | 2.2815
| 6138 | 0.44444 | 3.3051 | 1.1562 | 2.2563
| 6139 | 0.33333 | 3.1186 | 1.5938 | 1.9538
| 6140 | 0.34259 | 2.339 | 1 | 2.2521
| 6141 | 0.35185 | 3.7119 | 1.1562 | 1.9706
| 6142 | 0.61111 | 2.8983 | 1.875 | 2.2059
| 6143 | 0.52778 | 2.7288 | 0.5 | 2.3361
| 6144 | 0.51852 | 2.4068 | 0.71875 | 2.0378
| 6145 | 0.37037 | 3.0847 | 1.625 | 2.1092
| 6146 | 0.25926 | 2.5254 | 1.0938 | 2.1261
| 6147 | 0.42593 | 2.3559 | 1.3125 | 1.916
| 6148 | 0.2963 | 2.5254 | 0.59375 | 2.3866
| 6149 | 0.33333 | 3.1017 | 1.1562 | 1.8109
| 6150 | 0.42593 | 2.5424 | 2.2812 | 2.2395
| 6151 | 0.17593 | 2.2542 | 0.96875 | 2.3571
| 6152 | 0.40741 | 2.678 | 2.0938 | 2.0756
| 6153 | 0.43519 | 2.2542 | 1.5625 | 2.2479
| 6154 | 0.36111 | 2.3559 | 0.875 | 2.1681
| 6155 | 0.36111 | 2.2881 | 1.4375 | 2.2647
| 6156 | 0.41667 | 2.6271 | 1.4062 | 1.9916
| 6157 | 0.56481 | 2.5593 | 1.5 | 1.937
| 6158 | 0.4537 | 2.8305 | 1.6562 | 1.8824
| 6159 | 0.34259 | 2.5085 | 1.0625 | 1.8025
| 6160 | 0.52778 | 2.9153 | 1.4375 | 2.2521
| 6161 | 0.35185 | 1.9153 | 1 | 2.4664
| 6162 | 0.2963 | 3.4237 | 2.125 | 2.1933
| 6163 | 0.46296 | 2.5424 | 1.4375 | 2.042
| 6164 | 0.30556 | 4.0339 | 1.0625 | 2.084
| 6165 | 0.37037 | 2.7288 | 1.5312 | 2.2605
| 6166 | 0.38889 | 2.5085 | 1.5625 | 2.395
| 6167 | 0.39815 | 3.2034 | 1.2812 | 1.9538
| 6168 | 0.2963 | 3.4237 | 0.96875 | 1.9328
| 6169 | 0.4537 | 2.6949 | 2.0312 | 2.1218
| 6170 | 0.51852 | 3.2203 | 1.1562 | 2
| 6171 | 0.31481 | 2.7797 | 1.3125 | 2.1261
| 6172 | 0.37963 | 3.1525 | 1.0625 | 2.0546
| 6173 | 0.37037 | 2.7627 | 1.5312 | 2.2731
| 6174 | 0.40741 | 2.2881 | 1 | 2.0336
| 6175 | 0.40741 | 2 | 1.375 | 2.0798
| 6176 | 0.37037 | 2.7966 | 1.4062 | 1.6975
| 6177 | 0.48148 | 2.4746 | 1.4062 | 2.0966
| 6178 | 0.4537 | 2.7797 | 1.6562 | 2.3025
| 6179 | 0.43519 | 2.5932 | 1.0312 | 2.0756
| 6180 | 0.39815 | 2.8814 | 0.96875 | 2.1261
| 6181 | 0.49074 | 2.0847 | 0.84375 | 2.4034
| 6182 | 0.32407 | 2.4746 | 1.8438 | 1.8193
| 6183 | 0.39815 | 2.4915 | 0.84375 | 2.105
| 6184 | 0.41667 | 3.3898 | 2.125 | 1.9916
| 6185 | 0.56481 | 3.4068 | 0.59375 | 2.1345
| 6186 | 0.24074 | 2.8475 | 0.59375 | 1.9748
| 6187 | 0.43519 | 3.4237 | 1.8125 | 2.1429
| 6188 | 0.30556 | 2.5254 | 1.3438 | 2.1555
| 6189 | 0.47222 | 2.5593 | 1.7188 | 2.0924
| 6190 | 0.49074 | 2.1017 | 1.375 | 2.2899
| 6191 | 0.31481 | 1.6102 | 1.0938 | 2.1807
| 6192 | 0.44444 | 2.7119 | 1.1562 | 1.9748
| 6193 | 0.47222 | 2.4746 | 0.78125 | 2.0378
| 6194 | 0.53704 | 2.0169 | 0.59375 | 2.4076
| 6195 | 0.25 | 3.2712 | 1.2188 | 1.8739
| 6196 | 0.34259 | 2.4915 | 1.5312 | 2.063
| 6197 | 0.51852 | 2.661 | 2.0312 | 2.1471
| 6198 | 0.25926 | 2.2203 | 0.90625 | 1.979
| 6199 | 0.48148 | 3.0169 | 1.8438 | 2.0504
| 6200 | 0.35185 | 2.9322 | 0.90625 | 1.9328
| 6201 | 0.46296 | 2.4068 | 1.375 | 2.1849
| 6202 | 0.41667 | 2.8475 | 1.625 | 2.2143
| 6203 | 0.2963 | 2.9661 | 1.1875 | 2.2059
| 6204 | 0.37963 | 1.7627 | 1.2812 | 2.3739
| 6205 | 0.47222 | 2.7119 | 1.0312 | 1.9664
| 6206 | 0.42593 | 2.9322 | 2 | 2.584
| 6207 | 0.37963 | 2.1864 | 1.5938 | 2.0336
| 6208 | 0.5463 | 3.0508 | 1.875 | 1.9664
| 6209 | 0.40741 | 2.9492 | 0.9375 | 1.979
| 6210 | 0.67593 | 1.9661 | 1.3125 | 1.916
| 6211 | 0.36111 | 3.2712 | 0.90625 | 2.1975
| 6212 | 0.50926 | 2.9492 | 0.6875 | 2.0756
| 6213 | 0.35185 | 2.8644 | 1.1875 | 1.9958
| 6214 | 0.48148 | 2.7288 | 2.0312 | 2.0252
| 6215 | 0.62963 | 2.4068 | 2 | 1.8109
| 6216 | 0.31481 | 1.9661 | 0.875 | 2.042
| 6217 | 0.32407 | 3 | 1.875 | 1.9034
| 6218 | 0.43519 | 3.3051 | 1.375 | 1.958
| 6219 | 0.43519 | 2.5763 | 0.84375 | 1.7395
| 6220 | 0.32407 | 2.5424 | 1.9062 | 1.8655
| 6221 | 0.39815 | 3.0847 | 1.5938 | 1.9244
| 6222 | 0.41667 | 2.1186 | 1.9375 | 1.9916
| 6223 | 0.5463 | 3.0339 | 1.1875 | 2.0336
| 6224 | 0.28704 | 2.2881 | 1.6562 | 2.2185
| 6225 | 0.27778 | 2.9831 | 1.5625 | 1.8235
| 6226 | 0.4537 | 2.8475 | 1.75 | 2.1303
| 6227 | 0.47222 | 2.2034 | 1.1875 | 1.9958
| 6228 | 0.40741 | 3.1017 | 1.1562 | 1.8613
| 6229 | 0.35185 | 2.5254 | 0.71875 | 1.7437
| 6230 | 0.32407 | 3.4746 | 1.4375 | 2.2563
| 6231 | 0.42593 | 2.7966 | 1.1875 | 2.0168
| 6232 | 0.40741 | 3.1017 | 1.7812 | 2.0336
| 6233 | 0.50926 | 2.9661 | 1.1875 | 2.0588
| 6234 | 0.62037 | 2.8475 | 2.0312 | 1.6933
| 6235 | 0.48148 | 3.2712 | 1.5 | 2.6471
| 6236 | 0.36111 | 3.0508 | 0.9375 | 2.1975
| 6237 | 0.41667 | 2.5254 | 1.5312 | 2.105
| 6238 | 0.57407 | 2.8814 | 1.5938 | 2.6849
| 6239 | 0.68519 | 2.2712 | 1.1562 | 1.9202
| 6240 | 0.4537 | 3.2373 | 1.4375 | 1.979
| 6241 | 0.59259 | 2.4746 | 1.3438 | 1.9412
| 6242 | 0.51852 | 2.7458 | 1.125 | 2.1597
| 6243 | 0.31481 | 2.6271 | 2.0938 | 2.0546
| 6244 | 0.33333 | 2.4576 | 0.625 | 1.8613
| 6245 | 0.43519 | 2.661 | 1.8438 | 2.0546
| 6246 | 0.30556 | 2 | 1.7812 | 2.2773
| 6247 | 0.47222 | 2.1864 | 1.9688 | 1.7437
| 6248 | 0.37963 | 2.5593 | 2.1875 | 1.9916
| 6249 | 0.30556 | 2.6102 | 2.1562 | 2.4328
| 6250 | 0.32407 | 3.661 | 1.2812 | 2.3487
| 6251 | 0.38889 | 2.6102 | 1.7812 | 2.6303
| 6252 | 0.49074 | 2.9492 | 1.3438 | 1.8782
| 6253 | 0.52778 | 2.3898 | 1.2812 | 1.9286
| 6254 | 0.39815 | 2.6271 | 1.5312 | 2.3529
| 6255 | 0.33333 | 2.2881 | 1.4688 | 2.3109
| 6256 | 0.37037 | 1.7966 | 1.75 | 2.0378
| 6257 | 0.28704 | 3.1695 | 0.9375 | 2.2605
| 6258 | 0.4537 | 2.339 | 0.84375 | 2.2143
| 6259 | 0.42593 | 2.5085 | 1.75 | 2.2101
| 6260 | 0.37963 | 2.5593 | 2.0625 | 2.0336
| 6261 | 0.33333 | 2.2034 | 1.25 | 2.2815
| 6262 | 0.5 | 2.4576 | 1.8438 | 2.2269
| 6263 | 0.40741 | 2.2034 | 2.5 | 2.1134
| 6264 | 0.37963 | 2.7288 | 0.8125 | 2.1176
| 6265 | 0.34259 | 3.0678 | 1.4375 | 2.4496
| 6266 | 0.36111 | 2.661 | 1.5 | 2.0672
| 6267 | 0.36111 | 3.0339 | 1.5938 | 2.1303
| 6268 | 0.30556 | 1.8305 | 0.71875 | 1.9664
| 6269 | 0.39815 | 2.1525 | 0.9375 | 1.9244
| 6270 | 0.55556 | 2.678 | 0.9375 | 2.0462
| 6271 | 0.34259 | 2.7966 | 0.9375 | 2.4748
| 6272 | 0.36111 | 2.661 | 0.78125 | 2.084
| 6273 | 0.42593 | 2.5593 | 1.2812 | 2.0504
| 6274 | 0.46296 | 2.8644 | 1.5625 | 2.0714
| 6275 | 0.42593 | 2.4915 | 0.90625 | 1.7059
| 6276 | 0.48148 | 2.3559 | 1.875 | 1.7689
| 6277 | 0.47222 | 3.4068 | 1.375 | 1.9328
| 6278 | 0.43519 | 3.339 | 1.5625 | 2.0546
| 6279 | 0.37963 | 3.5085 | 1.0938 | 2.2311
| 6280 | 0.42593 | 2.3898 | 1.4062 | 1.7647
| 6281 | 0.30556 | 2.5085 | 0.8125 | 1.7689
| 6282 | 0.42593 | 2.2034 | 1.2188 | 1.8824
| 6283 | 0.49074 | 3.4746 | 1.4062 | 2.0378
| 6284 | 0.47222 | 2.4407 | 2.2812 | 2.2269
| 6285 | 0.48148 | 2.5254 | 1 | 1.6933
| 6286 | 0.38889 | 2.3729 | 1.125 | 1.916
| 6287 | 0.49074 | 3.1356 | 1.2812 | 1.979
| 6288 | 0.44444 | 2.9322 | 1.75 | 2.0084
| 6289 | 0.30556 | 2.339 | 1.625 | 1.9454
| 6290 | 0.51852 | 2.7288 | 1.5 | 1.8277
| 6291 | 0.25926 | 2.4237 | 1.3438 | 2
| 6292 | 0.5 | 2.7458 | 1.7812 | 2.0924
| 6293 | 0.5 | 2.5254 | 1.6875 | 2.2311
| 6294 | 0.40741 | 3 | 0.78125 | 2.1218
| 6295 | 0.33333 | 3.1525 | 1.375 | 1.8992
| 6296 | 0.36111 | 2.3051 | 1.125 | 2.2227
| 6297 | 0.40741 | 3.0339 | 0.9375 | 2.0798
| 6298 | 0.41667 | 1.9661 | 1.4375 | 2.2143
| 6299 | 0.35185 | 2.6441 | 1.1875 | 2.1723
| 6300 | 0.25 | 3.6271 | 2.0312 | 1.8697
| 6301 | 0.35185 | 2.9322 | 1.6875 | 2.063
| 6302 | 0.41667 | 2.3559 | 1.2812 | 2.0546
| 6303 | 0.30556 | 3.1525 | 1.75 | 2.1639
| 6304 | 0.38889 | 2.6441 | 1.875 | 2.2731
| 6305 | 0.37963 | 2.1356 | 1.375 | 2.7353
| 6306 | 0.55556 | 2.3051 | 1.875 | 2.2605
| 6307 | 0.5 | 2.1017 | 1.4375 | 2.1891
| 6308 | 0.40741 | 2.3559 | 1.375 | 2.4244
| 6309 | 0.44444 | 1.9661 | 0.90625 | 1.8529
| 6310 | 0.47222 | 3 | 1.4688 | 2.2941
| 6311 | 0.43519 | 2.8644 | 1.7188 | 2
| 6312 | 0.33333 | 3.1695 | 2.0938 | 2.395
| 6313 | 0.40741 | 1.9322 | 1.3125 | 2.0252
| 6314 | 0.38889 | 3.3051 | 1.8125 | 2.0714
| 6315 | 0.31481 | 2.5085 | 1.6875 | 1.7941
| 6316 | 0.47222 | 2.9661 | 1.0938 | 2.1387
| 6317 | 0.31481 | 2.8983 | 1.0938 | 1.8908
| 6318 | 0.39815 | 2.2881 | 1.0312 | 1.9202
| 6319 | 0.42593 | 2.4576 | 1.5 | 2.1975
| 6320 | 0.47222 | 2.0678 | 1.875 | 2.1008
| 6321 | 0.37963 | 2.5424 | 1.25 | 2.1218
| 6322 | 0.34259 | 2.5763 | 1.9375 | 1.8992
| 6323 | 0.36111 | 2.9831 | 1.1562 | 2.2311
| 6324 | 0.38889 | 3 | 1.4375 | 2.3193
| 6325 | 0.42593 | 2.6441 | 1.5 | 1.958
| 6326 | 0.5463 | 2.5424 | 1.4375 | 2.0546
| 6327 | 0.53704 | 1.9661 | 0.59375 | 2.0546
| 6328 | 0.23148 | 3.0339 | 0.6875 | 2.2479
| 6329 | 0.32407 | 2.2881 | 2.4375 | 1.9748
| 6330 | 0.36111 | 2.6949 | 1.3125 | 1.8655
| 6331 | 0.41667 | 2.5593 | 1.5312 | 2.1303
| 6332 | 0.4537 | 2.8305 | 1.625 | 2.2269
| 6333 | 0.5 | 2.3898 | 2.4375 | 2.1303
| 6334 | 0.42593 | 2.2373 | 1.2812 | 1.7563
| 6335 | 0.37963 | 3.3729 | 0.8125 | 2.2269
| 6336 | 0.48148 | 2.4576 | 2.0938 | 2.0756
| 6337 | 0.37963 | 2.6102 | 1.6875 | 1.9286
| 6338 | 0.42593 | 3.7288 | 0.90625 | 1.9244
| 6339 | 0.35185 | 2.1525 | 1.1875 | 2.0546
| 6340 | 0.35185 | 2.1186 | 0.8125 | 2.1975
| 6341 | 0.41667 | 1.9153 | 1.4062 | 2
| 6342 | 0.43519 | 2.8814 | 1.4062 | 2.3025
| 6343 | 0.34259 | 2.8814 | 1.625 | 2.0042
| 6344 | 0.37037 | 2.6102 | 2.5625 | 2.1723
| 6345 | 0.40741 | 2.0339 | 1.8438 | 2.1387
| 6346 | 0.49074 | 3.2373 | 1.5625 | 1.9748
| 6347 | 0.42593 | 2.4068 | 1.625 | 2.0924
| 6348 | 0.50926 | 2.1186 | 1.1562 | 2.2437
| 6349 | 0.32407 | 2.9492 | 1.4375 | 2.2899
| 6350 | 0.47222 | 3.1186 | 1.2188 | 1.9412
| 6351 | 0.46296 | 2.5424 | 1.2812 | 2.6933
| 6352 | 0.46296 | 2.1695 | 1.4375 | 2.5042
| 6353 | 0.35185 | 2.1695 | 1.5938 | 1.7143
| 6354 | 0.5463 | 2.8136 | 1.5938 | 1.9286
| 6355 | 0.48148 | 2.5424 | 1.0938 | 2.1218
| 6356 | 0.36111 | 2.5932 | 1.25 | 2
| 6357 | 0.36111 | 2.6441 | 0.625 | 1.9748
| 6358 | 0.21296 | 2.9153 | 2.5312 | 1.9454
| 6359 | 0.46296 | 2.4576 | 1.25 | 2.1597
| 6360 | 0.43519 | 3.4576 | 1.2812 | 2.3487
| 6361 | 0.32407 | 3.2542 | 0.9375 | 2.1975
| 6362 | 0.53704 | 2.3898 | 1.2812 | 2.3992
| 6363 | 0.40741 | 2.7966 | 1.0625 | 2.7899
| 6364 | 0.52778 | 2.7797 | 1.5938 | 2.0042
| 6365 | 0.37963 | 2.4576 | 1.375 | 2.3361
| 6366 | 0.48148 | 2.7797 | 1.6562 | 1.9706
| 6367 | 0.37037 | 2.0508 | 1.4062 | 1.958
| 6368 | 0.40741 | 1.9322 | 1.3125 | 2.4328
| 6369 | 0.32407 | 2.4915 | 1.7812 | 2.0126
| 6370 | 0.30556 | 2.9661 | 1.7812 | 1.9244
| 6371 | 0.35185 | 4.0169 | 1.25 | 1.9076
| 6372 | 0.55556 | 2.1864 | 1.7188 | 2.063
| 6373 | 0.37963 | 2.6271 | 1.0625 | 2.3445
| 6374 | 0.39815 | 3.2034 | 1.3438 | 2.0882
| 6375 | 0.41667 | 2.7627 | 1.4688 | 2.1008
| 6376 | 0.41667 | 2.661 | 1.3438 | 1.9412
| 6377 | 0.34259 | 2.6271 | 2.7812 | 2.0756
| 6378 | 0.32407 | 2.1864 | 1.0938 | 1.8782
| 6379 | 0.35185 | 2.3051 | 1.7188 | 2.0294
| 6380 | 0.53704 | 1.8983 | 1.2188 | 2.1807
| 6381 | 0.55556 | 3.339 | 1.4062 | 2.2311
| 6382 | 0.43519 | 2.4915 | 0.875 | 2
| 6383 | 0.43519 | 2.4237 | 1 | 2.0504
| 6384 | 0.37963 | 2.5763 | 0.96875 | 2.4412
| 6385 | 0.5463 | 2.678 | 1.5938 | 2.2101
| 6386 | 0.56481 | 2.4068 | 1.5938 | 2.063
| 6387 | 0.41667 | 2.7119 | 0.625 | 2.2101
| 6388 | 0.53704 | 2.4237 | 0.8125 | 2.458
| 6389 | 0.25 | 3.0508 | 2.0625 | 2.3361
| 6390 | 0.42593 | 2.2881 | 2.0625 | 2.2269
| 6391 | 0.28704 | 2.4068 | 0.78125 | 1.937
| 6392 | 0.47222 | 2.6949 | 2.375 | 2.1681
| 6393 | 0.4537 | 2.8644 | 2.6875 | 2.2395
| 6394 | 0.41667 | 2.6102 | 2.3125 | 1.9538
| 6395 | 0.42593 | 2.3729 | 1.6875 | 1.9706
| 6396 | 0.37963 | 2.9492 | 1.3125 | 2.0798
| 6397 | 0.38889 | 2.0169 | 1.3438 | 1.7941
| 6398 | 0.52778 | 2.1356 | 1.2188 | 1.895
| 6399 | 0.37037 | 2.3729 | 0.46875 | 1.8571
| 6400 | 0.64815 | 1.678 | 0.59375 | 1.9454
| 6401 | 0.4537 | 2.5085 | 1.75 | 2.2563
| 6402 | 0.40741 | 2.1695 | 2.1875 | 2.0714
| 6403 | 0.37037 | 3.8475 | 2.125 | 2.3109
| 6404 | 0.61111 | 3.2373 | 2.9375 | 2.1765
| 6405 | 0.47222 | 2.5593 | 1.4688 | 2.0294
| 6406 | 0.30556 | 2.7797 | 0.78125 | 2.3571
| 6407 | 0.31481 | 2.5763 | 1.0312 | 1.916
| 6408 | 0.37037 | 2.9831 | 1.5312 | 1.8277
| 6409 | 0.31481 | 2.8983 | 2.1562 | 2.0546
| 6410 | 0.59259 | 2.9492 | 1.125 | 2.3235
| 6411 | 0.30556 | 2.7627 | 1.25 | 2.2983
| 6412 | 0.32407 | 3.3559 | 1.2188 | 1.9118
| 6413 | 0.57407 | 2.661 | 1.1875 | 2.2101
| 6414 | 0.33333 | 3.1017 | 1.8438 | 1.9076
| 6415 | 0.5463 | 2.3898 | 1.875 | 1.9244
| 6416 | 0.39815 | 2.4576 | 0.90625 | 2.0924
| 6417 | 0.37037 | 2.8305 | 0.96875 | 2.1008
| 6418 | 0.46296 | 2.7966 | 1.5 | 1.9454
| 6419 | 0.47222 | 1.8644 | 1.375 | 1.6639
| 6420 | 0.47222 | 2.9322 | 1.25 | 2.1008
| 6421 | 0.36111 | 2.5763 | 1.7188 | 1.9664
| 6422 | 0.37037 | 2.3729 | 1.0625 | 2.0462
| 6423 | 0.64815 | 2.8136 | 1.0625 | 1.7479
| 6424 | 0.50926 | 3.3898 | 1.1562 | 1.8487
| 6425 | 0.49074 | 2.5085 | 1.1562 | 1.9244
| 6426 | 0.38889 | 2.7627 | 1.5312 | 2.1429
| 6427 | 0.38889 | 2.5085 | 1.0938 | 2.0042
| 6428 | 0.53704 | 2.8983 | 1.6562 | 2.2815
| 6429 | 0.5 | 2.7797 | 0.875 | 2.1555
| 6430 | 0.44444 | 2.4237 | 1.625 | 2.3697
| 6431 | 0.37963 | 3 | 0.71875 | 2.1345
| 6432 | 0.5 | 2.8136 | 1.2812 | 2.3655
| 6433 | 0.53704 | 2.3051 | 2.4062 | 1.8361
| 6434 | 0.40741 | 2.8136 | 1.4688 | 1.7773
| 6435 | 0.30556 | 2.5593 | 1.5 | 2.084
| 6436 | 0.25 | 3.7288 | 1.7188 | 1.9118
| 6437 | 0.41667 | 2.5593 | 0.875 | 2.2227
| 6438 | 0.53704 | 2.5932 | 1.6875 | 2.2395
| 6439 | 0.35185 | 2.7797 | 2.125 | 1.9664
| 6440 | 0.32407 | 2.2542 | 2.0312 | 2.6681
| 6441 | 0.51852 | 3.1356 | 1.4062 | 2.1218
| 6442 | 0.26852 | 2.2034 | 1.2812 | 1.7899
| 6443 | 0.57407 | 2.0169 | 1.4062 | 2.1303
| 6444 | 0.33333 | 2.2034 | 1.0625 | 2.2395
| 6445 | 0.41667 | 3.4407 | 0.84375 | 2.0966
| 6446 | 0.37963 | 2.7966 | 1.9688 | 2.1555
| 6447 | 0.36111 | 3.3729 | 1.8438 | 2.1261
| 6448 | 0.42593 | 2.5932 | 1.5 | 2.0462
| 6449 | 0.5 | 1.8983 | 0.78125 | 1.958
| 6450 | 0.34259 | 2.7119 | 1.4062 | 2.4664
| 6451 | 0.44444 | 2.7119 | 2.2812 | 2.1008
| 6452 | 0.56481 | 3.1525 | 0.84375 | 1.9874
| 6453 | 0.34259 | 3.2034 | 1.3125 | 2.2857
| 6454 | 0.36111 | 3.0508 | 2.3125 | 2.1681
| 6455 | 0.28704 | 2.8136 | 0.9375 | 1.9118
| 6456 | 0.57407 | 2.7966 | 1.4688 | 2.2311
| 6457 | 0.39815 | 2.6102 | 2 | 2.2437
| 6458 | 0.44444 | 2.2203 | 1.25 | 2.1807
| 6459 | 0.31481 | 3.0508 | 2.0938 | 2.2311
| 6460 | 0.53704 | 3.8814 | 1.9688 | 2.1471
| 6461 | 0.43519 | 2.4915 | 1.3125 | 2.2185
| 6462 | 0.50926 | 2.7797 | 0.625 | 2.1387
| 6463 | 0.49074 | 2.8644 | 1.6562 | 1.8235
| 6464 | 0.36111 | 2.6949 | 1.75 | 2.2521
| 6465 | 0.39815 | 1.8305 | 1.5938 | 2.0966
| 6466 | 0.40741 | 3.0339 | 1.3438 | 2.0294
| 6467 | 0.41667 | 2.661 | 1.4688 | 2.0798
| 6468 | 0.34259 | 2.339 | 0.625 | 2.1723
| 6469 | 0.62037 | 2.5932 | 1.3125 | 1.9454
| 6470 | 0.52778 | 3.0847 | 2 | 1.958
| 6471 | 0.49074 | 2.5254 | 1.9688 | 1.8403
| 6472 | 0.61111 | 3.322 | 1.1562 | 2.1176
| 6473 | 0.28704 | 3.322 | 1.375 | 2.0378
| 6474 | 0.36111 | 2.7627 | 1.5938 | 2.5966
| 6475 | 0.35185 | 2.9153 | 1.3125 | 2.2815
| 6476 | 0.35185 | 2.6441 | 1.4375 | 2.2521
| 6477 | 0.36111 | 2.5593 | 1.9375 | 2.2143
| 6478 | 0.43519 | 2.5763 | 0.90625 | 2.4118
| 6479 | 0.26852 | 2.7627 | 2.2188 | 1.8739
| 6480 | 0.43519 | 2.3898 | 2.5312 | 2.0462
| 6481 | 0.55556 | 2.9492 | 1.2812 | 2.0168
| 6482 | 0.50926 | 2.5932 | 1.0938 | 2.1134
| 6483 | 0.46296 | 2.1017 | 1.5625 | 2.2479
| 6484 | 0.5 | 2.322 | 0.9375 | 2.0924
| 6485 | 0.57407 | 2.5424 | 1.3125 | 2.0798
| 6486 | 0.44444 | 2.5932 | 0.65625 | 2.042
| 6487 | 0.26852 | 2.8136 | 1 | 1.8067
| 6488 | 0.30556 | 3.2203 | 0.84375 | 2.2395
| 6489 | 0.36111 | 3.0339 | 1.75 | 2.1555
| 6490 | 0.34259 | 2.1525 | 1.7812 | 2.3487
| 6491 | 0.53704 | 2.7797 | 1.25 | 2.1092
| 6492 | 0.51852 | 2.1525 | 2.4375 | 2.0546
| 6493 | 0.4537 | 3.0169 | 1.9375 | 2.1387
| 6494 | 0.39815 | 2.4237 | 0.96875 | 1.9748
| 6495 | 0.43519 | 3.2203 | 1.2188 | 1.9706
| 6496 | 0.52778 | 2.5254 | 0.84375 | 2.1008
| 6497 | 0.48148 | 3.0339 | 1.3438 | 2.2773
| 6498 | 0.43519 | 2.6271 | 1.8125 | 2.0756
| 6499 | 0.41667 | 2.8305 | 1.4688 | 2.5042
| 6500 | 0.39815 | 3.2881 | 1.8125 | 2.1261
| 6501 | 0.24074 | 2.9322 | 1.75 | 1.8655
| 6502 | 0.34259 | 2.5932 | 1.9062 | 1.937
| 6503 | 0.40741 | 2.0847 | 1.3125 | 2.1134
| 6504 | 0.44444 | 2.8983 | 1.0625 | 2.4202
| 6505 | 0.43519 | 2.678 | 1.2188 | 2
| 6506 | 0.43519 | 2.0339 | 1.5312 | 2.0882
| 6507 | 0.57407 | 2.8644 | 0.96875 | 2.0924
| 6508 | 0.50926 | 2.3051 | 1.5625 | 1.9832
| 6509 | 0.4537 | 2.9322 | 1.9375 | 2.2983
| 6510 | 0.32407 | 2.6102 | 1.625 | 2.042
| 6511 | 0.5 | 2.339 | 0.78125 | 2.395
| 6512 | 0.30556 | 2.4068 | 1.5312 | 2.6429
| 6513 | 0.47222 | 2.5085 | 1.5312 | 1.895
| 6514 | 0.41667 | 3.0847 | 0.53125 | 2.1008
| 6515 | 0.5463 | 3.322 | 0.9375 | 2.2857
| 6516 | 0.39815 | 2.8475 | 1.4688 | 1.8782
| 6517 | 0.40741 | 2.9831 | 0.8125 | 1.9454
| 6518 | 0.56481 | 2.7966 | 1.7188 | 1.8992
| 6519 | 0.47222 | 2.8475 | 1.0625 | 1.7941
| 6520 | 0.36111 | 3.3898 | 1.75 | 2.1513
| 6521 | 0.44444 | 1.7797 | 1.2812 | 2.3739
| 6522 | 0.55556 | 2.1864 | 1.625 | 2.3529
| 6523 | 0.34259 | 3.8983 | 1.4062 | 2.4454
| 6524 | 0.47222 | 2.6102 | 1.5938 | 2.2563
| 6525 | 0.50926 | 3.322 | 0.65625 | 2.1723
| 6526 | 0.42593 | 1.8475 | 1.2188 | 2.0504
| 6527 | 0.46296 | 3.2034 | 1.5 | 1.9706
| 6528 | 0.5463 | 3.1186 | 1.0312 | 1.8193
| 6529 | 0.42593 | 2.8814 | 0.65625 | 2.1471
| 6530 | 0.4537 | 2.8644 | 1.7188 | 2.1639
| 6531 | 0.58333 | 2.8305 | 2.5312 | 1.8908
| 6532 | 0.42593 | 2.7458 | 1.625 | 2.4706
| 6533 | 0.48148 | 2.678 | 0.90625 | 2.2185
| 6534 | 0.62963 | 3.1525 | 1 | 2.0042
| 6535 | 0.36111 | 2.4407 | 1.4375 | 2.1092
| 6536 | 0.5463 | 3.2542 | 1.5938 | 1.9496
| 6537 | 0.49074 | 2.7627 | 2.0938 | 1.7647
| 6538 | 0.5 | 2.7458 | 0.96875 | 2.105
| 6539 | 0.32407 | 1.8814 | 0.9375 | 2.1513
| 6540 | 0.34259 | 2.7288 | 1.5312 | 1.916
| 6541 | 0.36111 | 3.5085 | 1.6875 | 2.2521
| 6542 | 0.27778 | 3.678 | 2.5312 | 1.895
| 6543 | 0.37037 | 2.6441 | 1.5625 | 2.2395
| 6544 | 0.2963 | 2.8136 | 2.3125 | 2.021
| 6545 | 0.34259 | 2.7966 | 1.0938 | 2.3655
| 6546 | 0.30556 | 2.5932 | 1.4062 | 2.2395
| 6547 | 0.30556 | 2.5424 | 1.75 | 1.979
| 6548 | 0.37037 | 2.2712 | 1.8125 | 2.6176
| 6549 | 0.4537 | 2.5254 | 1.4688 | 2.0252
| 6550 | 0.39815 | 2.6441 | 1.3125 | 2.5084
| 6551 | 0.50926 | 2.7458 | 1.8125 | 2.0672
| 6552 | 0.38889 | 1.4407 | 1.9062 | 2.2479
| 6553 | 0.48148 | 2.6102 | 1.2188 | 2.3151
| 6554 | 0.40741 | 3.1525 | 1.6875 | 1.7857
| 6555 | 0.34259 | 3.1695 | 1.125 | 2.0126
| 6556 | 0.55556 | 2.5932 | 1.7188 | 1.8277
| 6557 | 0.28704 | 3 | 1.75 | 2.0924
| 6558 | 0.34259 | 2.4915 | 0.84375 | 2.2521
| 6559 | 0.48148 | 2.1525 | 1.75 | 1.9832
| 6560 | 0.36111 | 2.4237 | 1.8438 | 2.1681
| 6561 | 0.34259 | 1.8305 | 1.0312 | 1.979
| 6562 | 0.46296 | 2.5424 | 1.7812 | 1.9202
| 6563 | 0.40741 | 3.0847 | 0.90625 | 1.6975
| 6564 | 0.34259 | 2.8305 | 1.6562 | 1.979
| 6565 | 0.26852 | 2.7966 | 1.5625 | 2.1176
| 6566 | 0.52778 | 2.2881 | 0.375 | 2.2143
| 6567 | 0.35185 | 2.5593 | 1.1875 | 2.4118
| 6568 | 0.40741 | 2.4407 | 1.4062 | 1.8025
| 6569 | 0.25926 | 2.9492 | 0.96875 | 1.9916
| 6570 | 0.52778 | 2.7458 | 1.1875 | 1.8613
| 6571 | 0.2963 | 2.6441 | 1.5312 | 2
| 6572 | 0.47222 | 2.6271 | 1.5625 | 1.8361
| 6573 | 0.50926 | 2.5932 | 1.4375 | 2.1849
| 6574 | 0.61111 | 2.9153 | 1.6875 | 2.2395
| 6575 | 0.30556 | 2.1525 | 1.5625 | 2.1681
| 6576 | 0.39815 | 2.9153 | 1.5312 | 2.2521
| 6577 | 0.60185 | 1.8305 | 1.25 | 2.2311
| 6578 | 0.30556 | 2.9831 | 1.1875 | 2.2227
| 6579 | 0.28704 | 2.5254 | 1.375 | 1.9286
| 6580 | 0.34259 | 2.5932 | 0.90625 | 2.1471
| 6581 | 0.41667 | 3.0678 | 1.0312 | 1.9496
| 6582 | 0.35185 | 2.661 | 1.625 | 2.1891
| 6583 | 0.31481 | 2.9322 | 1.5938 | 1.8445
| 6584 | 0.2963 | 3.0678 | 1.5 | 2.2101
| 6585 | 0.49074 | 3.4407 | 1.2188 | 2.6092
| 6586 | 0.4537 | 2.6271 | 0.34375 | 1.937
| 6587 | 0.39815 | 2.3051 | 1.0312 | 1.8487
| 6588 | 0.39815 | 2.3559 | 0.8125 | 1.9706
| 6589 | 0.53704 | 2.6271 | 1.25 | 2.3866
| 6590 | 0.50926 | 2.5593 | 2.5625 | 1.8613
| 6591 | 0.31481 | 2.5593 | 1.2188 | 2.1765
| 6592 | 0.58333 | 2.6441 | 1.3125 | 1.937
| 6593 | 0.37037 | 2.5593 | 1.4375 | 1.895
| 6594 | 0.48148 | 2.5085 | 1.4375 | 2.0966
| 6595 | 0.37037 | 2.8475 | 1.9688 | 2.0378
| 6596 | 0.43519 | 2.9153 | 1.2188 | 2.0714
| 6597 | 0.43519 | 2.5593 | 1.25 | 2.0924
| 6598 | 0.49074 | 2.339 | 0.75 | 1.9328
| 6599 | 0.35185 | 2.2034 | 1.7188 | 2.2185
| 6600 | 0.39815 | 2.3051 | 1.4375 | 2.4454
| 6601 | 0.34259 | 2.8644 | 2.0312 | 2.2941
| 6602 | 0.38889 | 2.6102 | 2 | 2.1639
| 6603 | 0.38889 | 2.8305 | 1.75 | 1.8319
| 6604 | 0.47222 | 2.9831 | 1.0312 | 2.0672
| 6605 | 0.42593 | 2.5085 | 0.90625 | 2.0798
| 6606 | 0.41667 | 2.339 | 1.4375 | 2.1218
| 6607 | 0.30556 | 2.1186 | 1.125 | 1.8782
| 6608 | 0.48148 | 2.7119 | 1.1875 | 2.0294
| 6609 | 0.44444 | 3.5932 | 1.0625 | 1.8445
| 6610 | 0.50926 | 2.0678 | 1.1562 | 2.2059
| 6611 | 0.25 | 2.4237 | 1.6562 | 2.3277
| 6612 | 0.37963 | 2.6949 | 0.65625 | 2.0714
| 6613 | 0.41667 | 3.1864 | 1.1875 | 1.9202
| 6614 | 0.4537 | 2.8983 | 1.8125 | 2.1303
| 6615 | 0.4537 | 2.2034 | 1.3438 | 1.9832
| 6616 | 0.39815 | 2.5932 | 1.1875 | 2.1218
| 6617 | 0.4537 | 3.2881 | 1.5312 | 2.1176
| 6618 | 0.33333 | 2.339 | 2.375 | 2.0462
| 6619 | 0.2963 | 2.3559 | 1.0312 | 1.8613
| 6620 | 0.47222 | 2.5932 | 1.5312 | 2.0462
| 6621 | 0.40741 | 2.2373 | 1.7812 | 2.3824
| 6622 | 0.28704 | 2.2542 | 0.625 | 2.0588
| 6623 | 0.42593 | 3.4237 | 1.8438 | 2.1092
| 6624 | 0.39815 | 2.7119 | 1.5312 | 2.0924
| 6625 | 0.42593 | 2.4068 | 1.5 | 2.3529
| 6626 | 0.44444 | 2.7119 | 2.0312 | 1.7269
| 6627 | 0.39815 | 3.1186 | 1.5312 | 2.1092
| 6628 | 0.56481 | 2.2203 | 1.3125 | 2.0798
| 6629 | 0.43519 | 2.4576 | 1.625 | 2.0714
| 6630 | 0.4537 | 2.4068 | 1.5625 | 2.0546
| 6631 | 0.48148 | 2.7966 | 1.9062 | 2.2353
| 6632 | 0.47222 | 3.0169 | 0.84375 | 2.4328
| 6633 | 0.50926 | 2.4237 | 0.8125 | 2.4328
| 6634 | 0.58333 | 3.3729 | 0.875 | 2.0294
| 6635 | 0.41667 | 3.0678 | 1.5 | 2.1639
| 6636 | 0.30556 | 2.1864 | 1.875 | 2.0714
| 6637 | 0.4537 | 2.7797 | 1.25 | 1.8908
| 6638 | 0.40741 | 2.9322 | 1.6562 | 2.1218
| 6639 | 0.26852 | 2.0169 | 1.75 | 2.042
| 6640 | 0.39815 | 2.5424 | 1.6875 | 1.9538
| 6641 | 0.56481 | 2.5254 | 1.2812 | 2.1681
| 6642 | 0.50926 | 2.5424 | 1.5 | 2.0504
| 6643 | 0.47222 | 3.0678 | 1.1562 | 1.8613
| 6644 | 0.33333 | 2.6102 | 1.5 | 1.8908
| 6645 | 0.40741 | 2.5254 | 1.8125 | 2.4244
| 6646 | 0.39815 | 3.5932 | 1.625 | 2.1429
| 6647 | 0.39815 | 2.8305 | 1.75 | 2.1555
| 6648 | 0.27778 | 2.1186 | 1.4688 | 1.916
| 6649 | 0.51852 | 2.8305 | 1.4375 | 2.1008
| 6650 | 0.40741 | 2.4915 | 1.4375 | 2.063
| 6651 | 0.2963 | 2.339 | 1.1875 | 2.2647
| 6652 | 0.40741 | 2.2034 | 1.5312 | 2.0588
| 6653 | 0.37963 | 2.4068 | 1.5312 | 2.4202
| 6654 | 0.47222 | 2.339 | 1.7812 | 1.6975
| 6655 | 0.44444 | 2.3898 | 1.375 | 2.2647
| 6656 | 0.56481 | 2.1695 | 1.8438 | 1.9916
| 6657 | 0.47222 | 2.8305 | 1.4688 | 2.2059
| 6658 | 0.35185 | 2.3898 | 1.4688 | 2
| 6659 | 0.32407 | 2.661 | 1.8125 | 2.0798
| 6660 | 0.28704 | 2.678 | 2.2812 | 2.3319
| 6661 | 0.49074 | 2.8305 | 1.3438 | 2.4118
| 6662 | 0.55556 | 2.8983 | 1.2812 | 2.2143
| 6663 | 0.42593 | 2.2034 | 1.375 | 2.0084
| 6664 | 0.43519 | 3.0169 | 2.5312 | 1.9748
| 6665 | 0.2963 | 2.7458 | 1.375 | 1.9496
| 6666 | 0.44444 | 2.3729 | 2.0938 | 2.3361
| 6667 | 0.33333 | 3.2373 | 1.625 | 1.8487
| 6668 | 0.28704 | 2.7627 | 1.125 | 1.9034
| 6669 | 0.41667 | 3.0169 | 1.0312 | 2.2059
| 6670 | 0.42593 | 3.2712 | 1.25 | 1.9538
| 6671 | 0.40741 | 1.7288 | 1.1562 | 2.2773
| 6672 | 0.36111 | 3.4068 | 1.5 | 2.3908
| 6673 | 0.37037 | 1.6949 | 1.2188 | 2.4412
| 6674 | 0.58333 | 2.3729 | 1.7812 | 2.4748
| 6675 | 0.40741 | 3 | 1.1562 | 1.8824
| 6676 | 0.46296 | 2.7966 | 1.0625 | 2.1639
| 6677 | 0.43519 | 2.5763 | 0.40625 | 1.895
| 6678 | 0.36111 | 2.5085 | 1 | 2.1092
| 6679 | 0.38889 | 3.4746 | 1.6562 | 1.9328
| 6680 | 0.30556 | 2.0169 | 1.5312 | 2.2521
| 6681 | 0.39815 | 2.5593 | 1.0312 | 1.9286
| 6682 | 0.32407 | 2.6271 | 0.96875 | 2.0168
| 6683 | 0.37963 | 2.4237 | 2.0312 | 1.9664
| 6684 | 0.37963 | 3.7627 | 2.2188 | 2.1807
| 6685 | 0.39815 | 2.5763 | 1.5 | 1.7269
| 6686 | 0.35185 | 2.6271 | 1.0938 | 1.6807
| 6687 | 0.43519 | 3.3051 | 1.2188 | 2.0882
| 6688 | 0.26852 | 1.9153 | 1.0312 | 2.063
| 6689 | 0.40741 | 2.5593 | 0.65625 | 2.3739
| 6690 | 0.38889 | 2.6441 | 1.9688 | 1.8193
| 6691 | 0.5 | 1.8305 | 1.6562 | 2.2143
| 6692 | 0.35185 | 2.9661 | 1.75 | 2.0882
| 6693 | 0.47222 | 2.8814 | 1.125 | 2.1471
| 6694 | 0.42593 | 2.2373 | 2.2188 | 2.0756
| 6695 | 0.38889 | 2.1186 | 1.625 | 2.0756
| 6696 | 0.46296 | 2.4407 | 2.0625 | 2.1134
| 6697 | 0.39815 | 3.2034 | 1.875 | 1.916
| 6698 | 0.30556 | 2.9492 | 3.3125 | 2.1387
| 6699 | 0.58333 | 2.3051 | 1.9062 | 2.0756
| 6700 | 0.62963 | 2.5593 | 1.0312 | 1.8445
| 6701 | 0.38889 | 2.4407 | 1.25 | 2.1387
| 6702 | 0.46296 | 2.4576 | 0.6875 | 1.9202
| 6703 | 0.49074 | 2.3729 | 1.0625 | 2.0504
| 6704 | 0.39815 | 2.1017 | 1.6875 | 2.2185
| 6705 | 0.37037 | 2.8814 | 1.8125 | 1.6933
| 6706 | 0.34259 | 2.4576 | 1.25 | 1.9832
| 6707 | 0.38889 | 2.7966 | 0.96875 | 2.0672
| 6708 | 0.42593 | 2.3051 | 0.875 | 2.5336
| 6709 | 0.2963 | 2.6271 | 1.3438 | 2.0294
| 6710 | 0.42593 | 2.3898 | 1.7812 | 2.1008
| 6711 | 0.43519 | 3.1356 | 1.5312 | 1.8613
| 6712 | 0.33333 | 2.1525 | 1.6562 | 2.2983
| 6713 | 0.39815 | 2.4068 | 1.2812 | 2.2899
| 6714 | 0.40741 | 3.2542 | 1.4375 | 2.2143
| 6715 | 0.42593 | 2.678 | 1.75 | 2.0126
| 6716 | 0.37037 | 2.2373 | 2.1875 | 2.1471
| 6717 | 0.47222 | 2.1017 | 0.9375 | 2.3025
| 6718 | 0.36111 | 2.8644 | 1.4688 | 2.2983
| 6719 | 0.40741 | 2.6949 | 1.0312 | 2.1345
| 6720 | 0.60185 | 1.8814 | 2.4062 | 1.9538
| 6721 | 0.39815 | 2.8305 | 1.5312 | 1.8697
| 6722 | 0.31481 | 2.7288 | 1.9062 | 2.1134
| 6723 | 0.33333 | 3.2712 | 2.6875 | 1.8487
| 6724 | 0.52778 | 2.8136 | 2.0625 | 2.3487
| 6725 | 0.37037 | 2.8814 | 2.2188 | 2.5
| 6726 | 0.37037 | 2.9492 | 1.5625 | 2.563
| 6727 | 0.24074 | 2.7797 | 0.96875 | 1.8445
| 6728 | 0.30556 | 2.7458 | 1.5625 | 2.3824
| 6729 | 0.42593 | 2.2712 | 1.2188 | 1.9538
| 6730 | 0.2963 | 2.7288 | 1.5 | 1.9874
| 6731 | 0.33333 | 2.6441 | 1.4375 | 2.2857
| 6732 | 0.38889 | 3.4576 | 1.125 | 2.2899
| 6733 | 0.52778 | 3.1017 | 1.75 | 2.0168
| 6734 | 0.46296 | 2.4237 | 1.5938 | 2.6555
| 6735 | 0.32407 | 1.8644 | 1.5 | 2.4664
| 6736 | 0.31481 | 2.1017 | 1.1875 | 2.1639
| 6737 | 0.35185 | 2.678 | 1.4688 | 2.1891
| 6738 | 0.5 | 2.661 | 1.4062 | 2.021
| 6739 | 0.34259 | 2.7627 | 1.375 | 2.2857
| 6740 | 0.37037 | 2.7288 | 0.8125 | 1.9412
| 6741 | 0.37963 | 2.6271 | 1.6562 | 2.1092
| 6742 | 0.41667 | 2.4746 | 1.5625 | 2.0378
| 6743 | 0.47222 | 2.4576 | 1.4375 | 1.8908
| 6744 | 0.47222 | 2.6102 | 1.4375 | 1.8613
| 6745 | 0.51852 | 2.9322 | 0.96875 | 1.8403
| 6746 | 0.38889 | 2.3051 | 2.9375 | 1.8361
| 6747 | 0.43519 | 2.1356 | 2.0625 | 2.4538
| 6748 | 0.43519 | 2.4576 | 0.6875 | 2.1261
| 6749 | 0.34259 | 2.7458 | 1.5312 | 1.6807
| 6750 | 0.47222 | 3.1695 | 2.125 | 1.9874
| 6751 | 0.41667 | 2.661 | 2.4062 | 2.1807
| 6752 | 0.4537 | 3.4915 | 1.5 | 2.1092
| 6753 | 0.50926 | 2.9153 | 1.5312 | 1.8782
| 6754 | 0.47222 | 2.5932 | 1.6875 | 1.9916
| 6755 | 0.53704 | 2.0508 | 0.90625 | 1.7269
| 6756 | 0.55556 | 2.1525 | 1.5625 | 2.2311
| 6757 | 0.27778 | 2.8305 | 2.7812 | 1.958
| 6758 | 0.37037 | 2.0678 | 2.25 | 2.4706
| 6759 | 0.51852 | 2.3898 | 1.0625 | 1.9706
| 6760 | 0.4537 | 2.678 | 1.4688 | 2.0378
| 6761 | 0.49074 | 2.678 | 1.625 | 1.9076
| 6762 | 0.33333 | 3.5254 | 2.3125 | 2.1639
| 6763 | 0.37037 | 2.4237 | 0.84375 | 1.8866
| 6764 | 0.37963 | 2.0339 | 1.0625 | 1.7479
| 6765 | 0.2963 | 2.2712 | 0.625 | 2.021
| 6766 | 0.62963 | 2.5932 | 0.71875 | 1.8571
| 6767 | 0.49074 | 2.4746 | 1.4062 | 2.105
| 6768 | 0.48148 | 3.339 | 1.9688 | 2.2647
| 6769 | 0.42593 | 2.6949 | 1.4062 | 1.6975
| 6770 | 0.41667 | 2.5593 | 0.96875 | 1.8739
| 6771 | 0.44444 | 2.8475 | 1.0938 | 1.916
| 6772 | 0.41667 | 2.7966 | 1.5312 | 2.0084
| 6773 | 0.53704 | 2.2203 | 1.4688 | 1.9496
| 6774 | 0.42593 | 2.2203 | 1.2812 | 2.0294
| 6775 | 0.49074 | 2 | 1.5938 | 2.3529
| 6776 | 0.41667 | 2.4746 | 1.5625 | 2.1134
| 6777 | 0.49074 | 2.7627 | 1.875 | 1.937
| 6778 | 0.53704 | 3.0508 | 1.7812 | 1.8361
| 6779 | 0.43519 | 1.9322 | 1.0938 | 1.9664
| 6780 | 0.28704 | 2.1864 | 1.3438 | 1.7815
| 6781 | 0.30556 | 3.0169 | 2.5 | 1.9202
| 6782 | 0.26852 | 2.5254 | 1.75 | 1.9034
| 6783 | 0.41667 | 2.1864 | 1.5625 | 2.1345
| 6784 | 0.49074 | 2.7119 | 1.4062 | 1.9958
| 6785 | 0.47222 | 3.2034 | 0.84375 | 1.937
| 6786 | 0.37037 | 2.661 | 1.0312 | 1.8235
| 6787 | 0.53704 | 2.5254 | 1.375 | 2.1765
| 6788 | 0.44444 | 2.8305 | 1.7812 | 2.5588
| 6789 | 0.4537 | 2.2712 | 1.625 | 2.3277
| 6790 | 0.25926 | 3.8644 | 1.5625 | 2.1891
| 6791 | 0.51852 | 1.9661 | 1.4375 | 2.4748
| 6792 | 0.37037 | 2.339 | 0.59375 | 2.1345
| 6793 | 0.35185 | 2.3729 | 1.0938 | 1.937
| 6794 | 0.33333 | 2.7119 | 0.96875 | 2.2269
| 6795 | 0.33333 | 2.8305 | 1.0938 | 2.1513
| 6796 | 0.42593 | 2.6102 | 0.6875 | 2.3908
| 6797 | 0.46296 | 2.6271 | 1.375 | 1.8277
| 6798 | 0.39815 | 2.2373 | 0.6875 | 2.2227
| 6799 | 0.69444 | 3.3559 | 2.5 | 2.2983
| 6800 | 0.38889 | 3.2712 | 1.3438 | 1.916
| 6801 | 0.41667 | 3.1186 | 1.5625 | 1.8571
| 6802 | 0.49074 | 2.4915 | 1.3125 | 2.0462
| 6803 | 0.50926 | 3.3898 | 1.125 | 2.0924
| 6804 | 0.57407 | 3.1017 | 1.3125 | 2.2269
| 6805 | 0.4537 | 2.0847 | 1.25 | 2.1471
| 6806 | 0.40741 | 2.2881 | 1.375 | 2.0168
| 6807 | 0.40741 | 2.661 | 1.4375 | 2.1639
| 6808 | 0.5 | 2.6271 | 1.5 | 2.0504
| 6809 | 0.37963 | 3 | 1.625 | 2.063
| 6810 | 0.34259 | 2.0847 | 0.59375 | 2.4118
| 6811 | 0.48148 | 2.7966 | 0.96875 | 1.9202
| 6812 | 0.25926 | 2.4068 | 1.125 | 1.9706
| 6813 | 0.2963 | 2.4068 | 1.4375 | 2.3529
| 6814 | 0.41667 | 2.1695 | 1.875 | 1.9874
| 6815 | 0.43519 | 2.4746 | 1.4375 | 1.7563
| 6816 | 0.34259 | 2.5593 | 2.7812 | 2.1176
| 6817 | 0.53704 | 2.8814 | 0.875 | 1.8866
| 6818 | 0.36111 | 2.9153 | 1.8125 | 1.8613
| 6819 | 0.5 | 2.2034 | 1.2188 | 1.7983
| 6820 | 0.31481 | 1.9322 | 1.5 | 1.9664
| 6821 | 0.5463 | 2.9492 | 0.75 | 1.9622
| 6822 | 0.40741 | 2.4576 | 1.125 | 1.6807
| 6823 | 0.50926 | 2.661 | 1.6562 | 2.0042
| 6824 | 0.5 | 2.0339 | 2.2188 | 2.437
| 6825 | 0.38889 | 3.2203 | 1.2812 | 1.9328
| 6826 | 0.28704 | 2.9492 | 1.5 | 2.1387
| 6827 | 0.47222 | 2.4068 | 1.5938 | 2.021
| 6828 | 0.5 | 2.339 | 1.1875 | 2.2941
| 6829 | 0.43519 | 3.0508 | 1.2188 | 1.9958
| 6830 | 0.39815 | 3.1695 | 1.7812 | 1.8613
| 6831 | 0.42593 | 2.7627 | 1.25 | 2.0378
| 6832 | 0.41667 | 3 | 2.75 | 2.2269
| 6833 | 0.5463 | 2.4237 | 1.5312 | 2.0378
| 6834 | 0.31481 | 3.1186 | 1.3125 | 2.2227
| 6835 | 0.25 | 2.8136 | 1.625 | 1.8571
| 6836 | 0.35185 | 3.6102 | 1.875 | 2.2899
| 6837 | 0.53704 | 2.7966 | 1.3438 | 1.9328
| 6838 | 0.42593 | 2.5424 | 1.8438 | 2.2563
| 6839 | 0.4537 | 2.0339 | 1.7188 | 2.3067
| 6840 | 0.40741 | 2.6271 | 2.3438 | 2.2731
| 6841 | 0.2963 | 2.678 | 1.4688 | 2.2185
| 6842 | 0.41667 | 3.1186 | 1.0312 | 2.084
| 6843 | 0.31481 | 2.9153 | 2.0625 | 2.1176
| 6844 | 0.43519 | 2.4915 | 0.90625 | 2.0462
| 6845 | 0.40741 | 2.5085 | 1.9375 | 2.1975
| 6846 | 0.36111 | 3.3559 | 0.96875 | 1.8908
| 6847 | 0.5463 | 2.7797 | 1.0625 | 1.9958
| 6848 | 0.40741 | 2.3051 | 1.1562 | 2.0672
| 6849 | 0.51852 | 3.2881 | 1.5312 | 2.0504
| 6850 | 0.43519 | 2.3559 | 1.2812 | 2.2983
| 6851 | 0.46296 | 3.2712 | 1.7812 | 2.084
| 6852 | 0.53704 | 3 | 1.9062 | 2.3992
| 6853 | 0.34259 | 1.8983 | 0.71875 | 2.1639
| 6854 | 0.39815 | 2.2542 | 1.4375 | 2.0882
| 6855 | 0.38889 | 3.0508 | 1.3438 | 1.7815
| 6856 | 0.40741 | 3.3559 | 1.8438 | 2.1471
| 6857 | 0.60185 | 2.4576 | 2.1562 | 1.8992
| 6858 | 0.43519 | 2.8814 | 0.875 | 1.9916
| 6859 | 0.34259 | 3.1695 | 1.0938 | 2.2437
| 6860 | 0.63889 | 2.3898 | 1.5625 | 2.1092
| 6861 | 0.35185 | 2.7966 | 1.5938 | 2.1597
| 6862 | 0.53704 | 2.4746 | 0.90625 | 1.8866
| 6863 | 0.25926 | 2.7627 | 1.4688 | 2.2059
| 6864 | 0.4537 | 3 | 2 | 1.8445
| 6865 | 0.34259 | 3.1356 | 1.5625 | 2.1765
| 6866 | 0.32407 | 2.0339 | 1.5625 | 2.3361
| 6867 | 0.41667 | 2.339 | 2.0625 | 2.3739
| 6868 | 0.34259 | 2.1695 | 1.0625 | 2.0462
| 6869 | 0.38889 | 2.4915 | 0.84375 | 1.916
| 6870 | 0.37963 | 2.4746 | 2.0625 | 2.5336
| 6871 | 0.42593 | 2.3729 | 1.375 | 1.895
| 6872 | 0.50926 | 2.322 | 1.2188 | 2.0504
| 6873 | 0.44444 | 2.3729 | 1.5625 | 2.3739
| 6874 | 0.4537 | 3.0508 | 2.0625 | 1.8613
| 6875 | 0.38889 | 3.0169 | 1.3438 | 2.0336
| 6876 | 0.53704 | 2.3559 | 2.0312 | 2.0924
| 6877 | 0.36111 | 3.2034 | 1.5938 | 1.937
| 6878 | 0.36111 | 2.6102 | 1.5938 | 2.0168
| 6879 | 0.51852 | 2.4237 | 1 | 2.0126
| 6880 | 0.43519 | 3.4237 | 0.875 | 2.0336
| 6881 | 0.2963 | 2.9322 | 0.75 | 2.2311
| 6882 | 0.41667 | 2.7458 | 1.4688 | 2.0252
| 6883 | 0.26852 | 2.2373 | 2.3125 | 2.3277
| 6884 | 0.2963 | 2.3559 | 1.125 | 1.9958
| 6885 | 0.27778 | 2.8644 | 0.9375 | 2.4748
| 6886 | 0.37037 | 2.3898 | 0.9375 | 2.021
| 6887 | 0.61111 | 2.6102 | 1.2188 | 1.8487
| 6888 | 0.43519 | 2.9492 | 0.84375 | 1.9454
| 6889 | 0.4537 | 2.1017 | 2 | 1.6807
| 6890 | 0.38889 | 2.3729 | 1.9375 | 2.2941
| 6891 | 0.41667 | 2.5932 | 1.1875 | 2.1891
| 6892 | 0.33333 | 2.1017 | 0.9375 | 2.1134
| 6893 | 0.51852 | 3.1695 | 0.875 | 2.1555
| 6894 | 0.47222 | 2.9322 | 1.625 | 1.9202
| 6895 | 0.37963 | 2.4576 | 1.6875 | 1.9664
| 6896 | 0.32407 | 2.9322 | 1.9688 | 2.0882
| 6897 | 0.39815 | 2 | 0.75 | 2.1429
| 6898 | 0.61111 | 2.8475 | 0.53125 | 1.9706
| 6899 | 0.38889 | 2.7966 | 1.2812 | 2.021
| 6900 | 0.39815 | 2.5932 | 1.375 | 2.1303
| 6901 | 0.38889 | 3.0339 | 1.2188 | 1.8445
| 6902 | 0.37963 | 2.2203 | 1.1562 | 2.2941
| 6903 | 0.49074 | 3.2712 | 1.3125 | 1.958
| 6904 | 0.37963 | 2.5763 | 1.6562 | 1.7101
| 6905 | 0.2037 | 2.2881 | 1.5938 | 2.4748
| 6906 | 0.41667 | 2.4746 | 1.3438 | 2.1975
| 6907 | 0.44444 | 3.0169 | 1.9062 | 2.1176
| 6908 | 0.22222 | 2.4576 | 1.4375 | 2.2731
| 6909 | 0.39815 | 2.4915 | 2.125 | 1.8067
| 6910 | 0.62037 | 2.6102 | 2.2188 | 1.8151
| 6911 | 0.32407 | 2.7458 | 1.2812 | 2.1092
| 6912 | 0.40741 | 2.9153 | 0.59375 | 2.1807
| 6913 | 0.52778 | 2.9322 | 1.5 | 1.8992
| 6914 | 0.33333 | 3.1186 | 1.3125 | 2.084
| 6915 | 0.40741 | 2.0847 | 1.3125 | 2.2185
| 6916 | 0.46296 | 2.3051 | 1.3125 | 2.1639
| 6917 | 0.41667 | 3.0678 | 1.4062 | 1.7017
| 6918 | 0.44444 | 2.4576 | 1.3438 | 2.0588
| 6919 | 0.47222 | 1.678 | 1.5312 | 2.5714
| 6920 | 0.35185 | 3.0508 | 1.5312 | 2.3655
| 6921 | 0.48148 | 3.3729 | 2.625 | 2.0336
| 6922 | 0.34259 | 2.3898 | 0.78125 | 1.9034
| 6923 | 0.5 | 2.2712 | 1 | 2.2689
| 6924 | 0.39815 | 3.8136 | 1.9688 | 2.2899
| 6925 | 0.35185 | 3.6441 | 0.9375 | 1.9706
| 6926 | 0.42593 | 2.3729 | 2 | 2.2479
| 6927 | 0.5463 | 2.6441 | 0.5625 | 2.1345
| 6928 | 0.28704 | 2.339 | 2.125 | 1.8529
| 6929 | 0.38889 | 1.6441 | 1.9062 | 2.0672
| 6930 | 0.42593 | 2.5932 | 1.375 | 2.0798
| 6931 | 0.37963 | 2.5254 | 1.625 | 1.9538
| 6932 | 0.4537 | 2.3051 | 2.0625 | 2.2983
| 6933 | 0.2963 | 2.5763 | 1.75 | 2.0672
| 6934 | 0.4537 | 3.4576 | 1.6875 | 2.1176
| 6935 | 0.40741 | 2.3559 | 1.25 | 2.1218
| 6936 | 0.41667 | 2.4068 | 1.625 | 2.6261
| 6937 | 0.50926 | 2.322 | 2.0938 | 1.9538
| 6938 | 0.52778 | 2.678 | 1 | 2.3613
| 6939 | 0.49074 | 3.1525 | 2.3125 | 2.4076
| 6940 | 0.37963 | 2.5254 | 1.4375 | 1.9706
| 6941 | 0.40741 | 2.6271 | 1.375 | 1.9622
| 6942 | 0.36111 | 3.2034 | 1.4688 | 2.0378
| 6943 | 0.5463 | 2.322 | 1.7188 | 2.1429
| 6944 | 0.38889 | 2.5424 | 1.8125 | 2.1975
| 6945 | 0.39815 | 2.5254 | 1.375 | 1.7563
| 6946 | 0.37963 | 2.4068 | 1.6562 | 2.0504
| 6947 | 0.47222 | 2.6271 | 1.5 | 2.1765
| 6948 | 0.36111 | 3.3051 | 1.2812 | 2.1471
| 6949 | 0.36111 | 2.7119 | 0.75 | 1.7479
| 6950 | 0.58333 | 2.5763 | 1.3438 | 2.042
| 6951 | 0.43519 | 3.0339 | 2.1562 | 2.1471
| 6952 | 0.39815 | 2.7627 | 1.3438 | 2.3193
| 6953 | 0.34259 | 1.9661 | 1.1562 | 2.0378
| 6954 | 0.30556 | 3.0678 | 1.3438 | 1.9664
| 6955 | 0.42593 | 2.2542 | 0.96875 | 2.0084
| 6956 | 0.49074 | 3.4576 | 1.375 | 2.2437
| 6957 | 0.4537 | 2.4407 | 1.5938 | 2.2059
| 6958 | 0.38889 | 2.3898 | 0.875 | 2.0084
| 6959 | 0.43519 | 2.2881 | 1.3125 | 1.9832
| 6960 | 0.62963 | 2.6102 | 1.8125 | 2.1513
| 6961 | 0.37963 | 2.2373 | 1.5 | 2.2605
| 6962 | 0.66667 | 2.4068 | 0.5 | 1.9664
| 6963 | 0.37963 | 3.2712 | 0.65625 | 2.021
| 6964 | 0.33333 | 2.7966 | 1.0625 | 2
| 6965 | 0.4537 | 2.7966 | 1 | 1.958
| 6966 | 0.43519 | 2.6271 | 1.6875 | 2
| 6967 | 0.43519 | 3.0678 | 1.2812 | 2.2311
| 6968 | 0.37963 | 2.5254 | 1.4375 | 2.0252
| 6969 | 0.5463 | 2.2373 | 1.7812 | 1.979
| 6970 | 0.40741 | 2.2034 | 1.625 | 1.9874
| 6971 | 0.43519 | 2.5085 | 2.1875 | 1.8613
| 6972 | 0.27778 | 2.7966 | 1.1875 | 1.9706
| 6973 | 0.33333 | 2.8475 | 1.2188 | 2.4664
| 6974 | 0.37037 | 2.6271 | 1.6562 | 2.4412
| 6975 | 0.37963 | 2.9831 | 2.4062 | 1.9496
| 6976 | 0.50926 | 2.9831 | 1.8125 | 1.8235
| 6977 | 0.5 | 2.4576 | 1.9062 | 2.4916
| 6978 | 0.41667 | 2.5763 | 0.90625 | 2.4034
| 6979 | 0.5 | 2.6102 | 1.2188 | 2.2941
| 6980 | 0.36111 | 2.4237 | 1.3125 | 2.3067
| 6981 | 0.39815 | 3.0508 | 1.3438 | 2.0084
| 6982 | 0.39815 | 1.9492 | 1.8438 | 1.916
| 6983 | 0.33333 | 2.5424 | 1.8125 | 2.0966
| 6984 | 0.37963 | 2.6949 | 1.1562 | 1.9496
| 6985 | 0.43519 | 1.9322 | 2.0312 | 2.2227
| 6986 | 0.52778 | 2.4068 | 0.90625 | 2.1723
| 6987 | 0.49074 | 2.2203 | 1.5 | 2.2311
| 6988 | 0.42593 | 2.2542 | 2.4375 | 2.0924
| 6989 | 0.31481 | 2.2034 | 1.375 | 2.1092
| 6990 | 0.30556 | 3.7966 | 0.8125 | 2.9958
| 6991 | 0.4537 | 2.7627 | 1.5625 | 1.8403
| 6992 | 0.40741 | 2.5763 | 1.0625 | 1.9328
| 6993 | 0.40741 | 2.3051 | 1.4375 | 2.0798
| 6994 | 0.37963 | 3.1525 | 2.0938 | 2.0798
| 6995 | 0.56481 | 2.4237 | 1.8438 | 2.021
| 6996 | 0.53704 | 2.6441 | 1.4062 | 2.2143
| 6997 | 0.4537 | 2.8983 | 1.1875 | 1.9958
| 6998 | 0.52778 | 2.339 | 2.1562 | 1.9832
| 6999 | 0.37037 | 3.2712 | 1.625 | 2.0546
| 7000 | 0.34259 | 2.339 | 0.9375 | 2.2521
| 7001 | 0.53704 | 2.4915 | 1.8125 | 1.8866
| 7002 | 0.34259 | 2.8475 | 1.7812 | 2.4958
| 7003 | 0.5463 | 1.9153 | 0.875 | 1.9874
| 7004 | 0.52778 | 3.5254 | 1.9375 | 1.9286
| 7005 | 0.37963 | 2.8305 | 1.0312 | 1.9328
| 7006 | 0.38889 | 3.3051 | 1.2812 | 2.3403
| 7007 | 0.51852 | 2.9153 | 1.4062 | 2.0882
| 7008 | 0.39815 | 3.1864 | 1.25 | 1.9706
| 7009 | 0.35185 | 2.6102 | 1.5625 | 2.5798
| 7010 | 0.38889 | 2.7288 | 2.0625 | 2.0462
| 7011 | 0.30556 | 2.4407 | 1.75 | 2.1849
| 7012 | 0.37037 | 2.7966 | 1.5625 | 2.0924
| 7013 | 0.44444 | 2.7966 | 1.25 | 2.2983
| 7014 | 0.55556 | 3.3898 | 1.3438 | 2.1723
| 7015 | 0.40741 | 2.4576 | 1.125 | 2.1639
| 7016 | 0.31481 | 2.1017 | 2.25 | 1.8445
| 7017 | 0.43519 | 2.3729 | 0.78125 | 1.9202
| 7018 | 0.37037 | 2.4915 | 1.0938 | 1.8992
| 7019 | 0.46296 | 3.1525 | 2.4688 | 1.8866
| 7020 | 0.41667 | 2.4915 | 1.1875 | 2.1387
| 7021 | 0.35185 | 2.9661 | 1.5 | 2.3571
| 7022 | 0.49074 | 2.9831 | 1.375 | 2.2101
| 7023 | 0.4537 | 2.2373 | 0.84375 | 2.0084
| 7024 | 0.40741 | 3.0847 | 1.7812 | 2.0294
| 7025 | 0.47222 | 3.339 | 0.9375 | 2.1429
| 7026 | 0.36111 | 2.8475 | 0.8125 | 1.9622
| 7027 | 0.51852 | 2.7288 | 1.4062 | 2.1849
| 7028 | 0.39815 | 2.6271 | 1.4062 | 1.8319
| 7029 | 0.32407 | 2.7627 | 1.5625 | 1.8109
| 7030 | 0.24074 | 2.2881 | 1.5938 | 2.0336
| 7031 | 0.37963 | 2.5424 | 1.8125 | 2.063
| 7032 | 0.27778 | 2.661 | 2.125 | 2.2059
| 7033 | 0.32407 | 2.0847 | 1.5312 | 1.9832
| 7034 | 0.47222 | 2.8814 | 1.7812 | 2.2857
| 7035 | 0.36111 | 2.5254 | 0.9375 | 2.1429
| 7036 | 0.34259 | 2.7119 | 0.84375 | 2.1345
| 7037 | 0.53704 | 2.7627 | 1.1875 | 2.1975
| 7038 | 0.46296 | 2.5424 | 1.1562 | 1.7941
| 7039 | 0.34259 | 2.6441 | 1.75 | 2.0882
| 7040 | 0.34259 | 3.7119 | 1.0625 | 2.2185
| 7041 | 0.52778 | 3.0169 | 1.25 | 2.2311
| 7042 | 0.35185 | 3.2712 | 0.75 | 1.9832
| 7043 | 0.43519 | 2.4068 | 0.78125 | 2.2983
| 7044 | 0.41667 | 3.0169 | 1.5 | 1.8193
| 7045 | 0.42593 | 2.7288 | 1.375 | 2.2311
| 7046 | 0.44444 | 2.6949 | 0.9375 | 1.9748
| 7047 | 0.5 | 2.4237 | 1.5312 | 2.2479
| 7048 | 0.37963 | 2.8136 | 2.1562 | 2.0126
| 7049 | 0.49074 | 2.6271 | 1.6875 | 2.1555
| 7050 | 0.31481 | 3.1525 | 1.375 | 2.3361
| 7051 | 0.33333 | 2.4915 | 1.3125 | 2.1681
| 7052 | 0.4537 | 3.4915 | 0.90625 | 2.2689
| 7053 | 0.57407 | 2.5593 | 1.2188 | 1.937
| 7054 | 0.32407 | 2.1695 | 0.96875 | 2.4076
| 7055 | 0.30556 | 2.6949 | 1.9062 | 1.9496
| 7056 | 0.4537 | 2.8305 | 1.6562 | 2.3824
| 7057 | 0.2963 | 2.9153 | 1.2812 | 2.0126
| 7058 | 0.41667 | 3.6271 | 1.3125 | 2.4118
| 7059 | 0.31481 | 2.7458 | 1.4688 | 2.0924
| 7060 | 0.59259 | 2.6949 | 1.9062 | 2.0294
| 7061 | 0.5 | 2.9831 | 1.6562 | 2.0168
| 7062 | 0.28704 | 2.7797 | 1 | 2.1765
| 7063 | 0.37963 | 2.322 | 0.8125 | 2.2731
| 7064 | 0.58333 | 2.4746 | 1.4375 | 2.4244
| 7065 | 0.4537 | 2.5254 | 0.90625 | 2.0672
| 7066 | 0.33333 | 2.9153 | 1.5312 | 1.8193
| 7067 | 0.44444 | 2.5763 | 1.0938 | 2.4706
| 7068 | 0.41667 | 2.2542 | 1.5625 | 1.9412
| 7069 | 0.48148 | 2.2034 | 2.2812 | 1.8487
| 7070 | 0.27778 | 3.0339 | 1.8438 | 1.7941
| 7071 | 0.51852 | 3.1695 | 1.5 | 2.021
| 7072 | 0.38889 | 2.6271 | 1.2188 | 2.2773
| 7073 | 0.34259 | 2.678 | 1.625 | 2.0042
| 7074 | 0.49074 | 2.5424 | 1.1875 | 2.1765
| 7075 | 0.38889 | 2.2712 | 1.1875 | 2.0378
| 7076 | 0.51852 | 3.1525 | 1.0625 | 1.7983
| 7077 | 0.49074 | 2.7627 | 1.0625 | 1.8613
| 7078 | 0.5 | 2.678 | 1.3125 | 2.2479
| 7079 | 0.32407 | 2.3559 | 1.0312 | 1.9664
| 7080 | 0.53704 | 1.8475 | 0.53125 | 1.9748
| 7081 | 0.34259 | 2.3051 | 1.0938 | 2.0126
| 7082 | 0.33333 | 2.1356 | 1.6562 | 2.3067
| 7083 | 0.47222 | 2.8983 | 2 | 2.2773
| 7084 | 0.55556 | 1.7119 | 1.4375 | 2.0378
| 7085 | 0.39815 | 1.9153 | 1.4375 | 1.8319
| 7086 | 0.34259 | 3.0678 | 0.8125 | 1.8361
| 7087 | 0.63889 | 2.5763 | 1.5625 | 2.0798
| 7088 | 0.37963 | 2.5593 | 2.625 | 2.2143
| 7089 | 0.33333 | 2.3898 | 2.0625 | 1.8571
| 7090 | 0.40741 | 2.8644 | 1.2812 | 2
| 7091 | 0.36111 | 3.4407 | 1.25 | 2.1555
| 7092 | 0.17593 | 1.8644 | 1.125 | 2.042
| 7093 | 0.39815 | 3.0508 | 1.0625 | 2.1765
| 7094 | 0.23148 | 2.8644 | 2 | 2.3613
| 7095 | 0.40741 | 2.5085 | 1.0625 | 2.2941
| 7096 | 0.36111 | 2.2373 | 2.0938 | 1.8782
| 7097 | 0.52778 | 3.339 | 1.25 | 1.9832
| 7098 | 0.34259 | 2.6271 | 2.125 | 2.3866
| 7099 | 0.37963 | 2.4407 | 1.0312 | 2.2857
| 7100 | 0.40741 | 3.0169 | 1.75 | 1.9328
| 7101 | 0.38889 | 2.8644 | 2.0312 | 2.0252
| 7102 | 0.39815 | 1.8475 | 2 | 1.8487
| 7103 | 0.41667 | 2.7288 | 0.875 | 2.5672
| 7104 | 0.40741 | 2.9661 | 1.9688 | 2.0126
| 7105 | 0.38889 | 3.0508 | 1.0625 | 2.2395
| 7106 | 0.42593 | 2.678 | 1.4375 | 2.5126
| 7107 | 0.73148 | 2.1695 | 0.71875 | 2.0798
| 7108 | 0.46296 | 2.8983 | 1.2812 | 2.2143
| 7109 | 0.35185 | 2.7288 | 2.2812 | 2.0504
| 7110 | 0.38889 | 2.3729 | 1.3125 | 2.0966
| 7111 | 0.46296 | 2.8644 | 1.3438 | 2.3571
| 7112 | 0.48148 | 2.4407 | 1.3125 | 1.937
| 7113 | 0.42593 | 2.7288 | 1.1562 | 2.1597
| 7114 | 0.37037 | 3.5932 | 1.2812 | 1.8824
| 7115 | 0.72222 | 2.6102 | 1.4375 | 2.0378
| 7116 | 0.4537 | 2.9661 | 1.9688 | 1.9664
| 7117 | 0.30556 | 2.2542 | 1.7812 | 1.8824
| 7118 | 0.39815 | 2.7966 | 1.6562 | 2.063
| 7119 | 0.39815 | 2.339 | 1.3438 | 2.3529
| 7120 | 0.49074 | 2.678 | 1.125 | 2.2773
| 7121 | 0.42593 | 3 | 1.125 | 2.2857
| 7122 | 0.56481 | 2.6949 | 0.96875 | 2.0378
| 7123 | 0.49074 | 2.7966 | 1.5938 | 2.2395
| 7124 | 0.47222 | 2.0508 | 1 | 1.8613
| 7125 | 0.53704 | 2.2881 | 1.25 | 2.0084
| 7126 | 0.36111 | 2.7458 | 1.7812 | 1.8866
| 7127 | 0.32407 | 2.3898 | 0.8125 | 2.4034
| 7128 | 0.47222 | 2.4237 | 1.0625 | 2.2353
| 7129 | 0.32407 | 2.5763 | 1.5312 | 2.0756
| 7130 | 0.46296 | 2.4746 | 1.75 | 2.0756
| 7131 | 0.41667 | 1.9831 | 1.7812 | 2.0504
| 7132 | 0.2963 | 2.5932 | 1.8125 | 2.0966
| 7133 | 0.30556 | 2.1525 | 2.2812 | 2.2479
| 7134 | 0.39815 | 2.7627 | 2.125 | 2.2857
| 7135 | 0.48148 | 3.1525 | 1.375 | 2.1891
| 7136 | 0.32407 | 2.6441 | 1.0938 | 1.8235
| 7137 | 0.36111 | 2.5932 | 1 | 2.1597
| 7138 | 0.38889 | 2.7627 | 1.5938 | 2.1176
| 7139 | 0.41667 | 2.5932 | 2.125 | 2.2395
| 7140 | 0.34259 | 3.3729 | 1.4688 | 2.479
| 7141 | 0.44444 | 1.5085 | 1.75 | 2.2479
| 7142 | 0.42593 | 2.6102 | 1.1875 | 1.8824
| 7143 | 0.55556 | 2.2203 | 1.3125 | 2.1891
| 7144 | 0.4537 | 2.5593 | 2.0625 | 2.2857
| 7145 | 0.26852 | 2.5593 | 1.1562 | 2.4034
| 7146 | 0.4537 | 1.6441 | 0.84375 | 2.0252
| 7147 | 0.33333 | 2.6102 | 1.2188 | 1.8908
| 7148 | 0.34259 | 2.5085 | 0.8125 | 1.9706
| 7149 | 0.7037 | 2.339 | 1.25 | 2.2983
| 7150 | 0.40741 | 3.2373 | 0.65625 | 1.9622
| 7151 | 0.34259 | 3.0339 | 0.78125 | 2.0252
| 7152 | 0.40741 | 3.0508 | 1.7812 | 2.3025
| 7153 | 0.35185 | 2.322 | 1.25 | 2.437
| 7154 | 0.35185 | 3.2373 | 1.3438 | 2.0588
| 7155 | 0.48148 | 3.9153 | 1.4375 | 2.0714
| 7156 | 0.44444 | 2.678 | 0.9375 | 2.5462
| 7157 | 0.39815 | 2.8644 | 1 | 2.3782
| 7158 | 0.47222 | 2.2203 | 0.8125 | 1.9706
| 7159 | 0.42593 | 2.6271 | 1.3438 | 2.1345
| 7160 | 0.56481 | 2.661 | 1.9375 | 2.1387
| 7161 | 0.31481 | 2.7288 | 1.25 | 1.9496
| 7162 | 0.32407 | 3.1864 | 1.4375 | 1.9202
| 7163 | 0.44444 | 2.6949 | 1.0625 | 2.3277
| 7164 | 0.39815 | 2.3729 | 0.8125 | 1.9328
| 7165 | 0.34259 | 3.5932 | 1.1562 | 2.4076
| 7166 | 0.50926 | 2.7288 | 1.9688 | 2.2101
| 7167 | 0.4537 | 2.6949 | 1.75 | 1.8277
| 7168 | 0.52778 | 2.7797 | 1.6562 | 1.8571
| 7169 | 0.44444 | 2.4576 | 0.90625 | 1.8193
| 7170 | 0.41667 | 2.8305 | 1.3125 | 2.1849
| 7171 | 0.27778 | 2.4746 | 1.75 | 2.1597
| 7172 | 0.4537 | 2.4746 | 1.5625 | 2.1134
| 7173 | 0.61111 | 3.3729 | 1.5 | 2.2353
| 7174 | 0.41667 | 2.4237 | 1.4688 | 2.3193
| 7175 | 0.38889 | 2.8814 | 1.7812 | 2.0336
| 7176 | 0.39815 | 3.2034 | 1.8438 | 2.1555
| 7177 | 0.43519 | 3.1864 | 1.8438 | 1.9244
| 7178 | 0.36111 | 2.7797 | 2.375 | 1.9874
| 7179 | 0.37037 | 2.4915 | 1.5625 | 2.2479
| 7180 | 0.53704 | 2.6102 | 1.1562 | 1.6387
| 7181 | 0.43519 | 3.1017 | 1.5938 | 2.2815
| 7182 | 0.34259 | 2.661 | 0.875 | 1.8697
| 7183 | 0.38889 | 2.9492 | 0.8125 | 2.1008
| 7184 | 0.26852 | 2.1186 | 1.8125 | 2.5756
| 7185 | 0.5 | 2.1864 | 1.7188 | 1.9244
| 7186 | 0.40741 | 2.5424 | 1.5312 | 1.7689
| 7187 | 0.35185 | 3 | 1.1562 | 1.7395
| 7188 | 0.58333 | 2.1017 | 1.1562 | 2.1891
| 7189 | 0.33333 | 2.2203 | 1.3125 | 2.1008
| 7190 | 0.25926 | 2.6949 | 1.9688 | 2
| 7191 | 0.52778 | 2.0847 | 1.3125 | 2.021
| 7192 | 0.59259 | 3.1525 | 1.1875 | 1.8992
| 7193 | 0.52778 | 3.1017 | 1.5 | 2.3151
| 7194 | 0.50926 | 2.2712 | 1.4375 | 1.9412
| 7195 | 0.56481 | 2.9322 | 0.96875 | 2.2353
| 7196 | 0.36111 | 1.9661 | 1.4688 | 1.9076
| 7197 | 0.46296 | 2.7797 | 1.6875 | 2.2731
| 7198 | 0.53704 | 2.3559 | 1.6562 | 1.9958
| 7199 | 0.42593 | 2.1525 | 1.1562 | 2.1723
| 7200 | 0.39815 | 1.7627 | 1.2812 | 1.8319
| 7201 | 0.36111 | 2.5085 | 1.625 | 2.2479
| 7202 | 0.41667 | 2.0169 | 1.125 | 2.021
| 7203 | 0.41667 | 2.6271 | 1.125 | 1.7731
| 7204 | 0.37037 | 2.2203 | 2.2188 | 2.4454
| 7205 | 0.43519 | 2.2881 | 1.375 | 2.1471
| 7206 | 0.58333 | 2.3051 | 2.1562 | 2.3235
| 7207 | 0.4537 | 3.6271 | 1.4062 | 1.9328
| 7208 | 0.47222 | 2.3729 | 1.1562 | 1.9496
| 7209 | 0.44444 | 2.6441 | 1.2188 | 2.2647
| 7210 | 0.48148 | 3.0678 | 1.5625 | 1.9244
| 7211 | 0.2963 | 2.7119 | 0.90625 | 2.1513
| 7212 | 0.36111 | 1.9492 | 1.5938 | 2.2059
| 7213 | 0.61111 | 2.2712 | 1.5 | 2.4538
| 7214 | 0.44444 | 3.3051 | 2.0938 | 2.0462
| 7215 | 0.33333 | 2.8305 | 1.8125 | 2.0798
| 7216 | 0.44444 | 2.2881 | 0.59375 | 2.1513
| 7217 | 0.46296 | 2.0847 | 0.53125 | 1.9202
| 7218 | 0.39815 | 2.3051 | 1.125 | 2.2899
| 7219 | 0.52778 | 2.5763 | 1.1562 | 2.0084
| 7220 | 0.40741 | 2.4407 | 1.4375 | 2.4328
| 7221 | 0.48148 | 2.7119 | 1.4062 | 1.9538
| 7222 | 0.37963 | 2.6441 | 1.75 | 1.9412
| 7223 | 0.30556 | 3.2373 | 1.0312 | 2.5546
| 7224 | 0.5 | 2.3051 | 1.5312 | 1.9664
| 7225 | 0.49074 | 2.8136 | 1.5625 | 2.1429
| 7226 | 0.2963 | 3.1864 | 1.5625 | 2.3025
| 7227 | 0.43519 | 2.9661 | 1.125 | 2.2227
| 7228 | 0.42593 | 2.8305 | 1.375 | 2.0756
| 7229 | 0.2963 | 2.5593 | 2.5938 | 1.9202
| 7230 | 0.56481 | 1.8814 | 1.4062 | 2.0168
| 7231 | 0.36111 | 2.8475 | 1.0938 | 2.2227
| 7232 | 0.49074 | 3.2034 | 1.375 | 2.2521
| 7233 | 0.48148 | 2.6271 | 1.625 | 2.5504
| 7234 | 0.37963 | 2.0508 | 1.3438 | 2.4244
| 7235 | 0.39815 | 2.4068 | 1.2188 | 2.1723
| 7236 | 0.38889 | 3.2881 | 0.84375 | 1.979
| 7237 | 0.42593 | 2.6441 | 1.25 | 2.2521
| 7238 | 0.37963 | 3.5932 | 0.84375 | 2.0966
| 7239 | 0.56481 | 2.7966 | 2.0938 | 2
| 7240 | 0.37963 | 2.339 | 1.3125 | 1.9412
| 7241 | 0.37963 | 2.4237 | 1.4062 | 2.2017
| 7242 | 0.35185 | 3.1525 | 1.4688 | 2.2479
| 7243 | 0.46296 | 2.678 | 2.7812 | 2.4832
| 7244 | 0.57407 | 2.1186 | 1.9375 | 2.0168
| 7245 | 0.22222 | 2.1356 | 1.25 | 2.1639
| 7246 | 0.43519 | 2.5932 | 1.0938 | 1.9412
| 7247 | 0.38889 | 2.5593 | 1 | 1.937
| 7248 | 0.47222 | 2.9661 | 2.1875 | 2.0546
| 7249 | 0.41667 | 2.3898 | 1.125 | 2.3319
| 7250 | 0.48148 | 2.4576 | 0.78125 | 1.8697
| 7251 | 0.5 | 2.5085 | 1.1562 | 2.3025
| 7252 | 0.48148 | 2.5932 | 1.4688 | 2.5042
| 7253 | 0.40741 | 2.4915 | 1.7812 | 2.2689
| 7254 | 0.37963 | 2.5593 | 1.0625 | 2.2521
| 7255 | 0.25 | 2.4746 | 1.6875 | 2.6008
| 7256 | 0.30556 | 2.322 | 1.5625 | 2.2773
| 7257 | 0.4537 | 2.9831 | 0.75 | 1.8487
| 7258 | 0.48148 | 3.4576 | 1.1875 | 2.0924
| 7259 | 0.28704 | 1.9831 | 1.9062 | 2.1261
| 7260 | 0.38889 | 2.1695 | 1.3125 | 2.2689
| 7261 | 0.42593 | 2.2034 | 1.4062 | 1.937
| 7262 | 0.40741 | 2.2542 | 1.5 | 2.1429
| 7263 | 0.44444 | 2.3729 | 1.125 | 2.1807
| 7264 | 0.48148 | 3.1186 | 1.7812 | 2.0084
| 7265 | 0.40741 | 3 | 0.90625 | 2.1303
| 7266 | 0.42593 | 2.8305 | 0.6875 | 1.8277
| 7267 | 0.27778 | 2.9492 | 1.8125 | 2.0798
| 7268 | 0.37963 | 1.9831 | 1.375 | 2.1092
| 7269 | 0.51852 | 3.5932 | 1.4062 | 1.8739
| 7270 | 0.47222 | 2.4237 | 1.0625 | 2.063
| 7271 | 0.47222 | 3.7119 | 1.4688 | 2.1975
| 7272 | 0.34259 | 2.2881 | 1.4375 | 1.8782
| 7273 | 0.30556 | 2.8475 | 0.90625 | 2.1345
| 7274 | 0.51852 | 2.5424 | 0.9375 | 2.2143
| 7275 | 0.34259 | 2.3051 | 1.8438 | 2.021
| 7276 | 0.39815 | 1.9831 | 1.5 | 2
| 7277 | 0.52778 | 4.0678 | 1.5312 | 1.9202
| 7278 | 0.34259 | 2.322 | 1.3438 | 1.7605
| 7279 | 0.51852 | 2.0678 | 2 | 1.7479
| 7280 | 0.4537 | 2.5254 | 1.9375 | 2.3824
| 7281 | 0.48148 | 3.2542 | 1.9688 | 2.1597
| 7282 | 0.66667 | 2.6271 | 1.25 | 1.9538
| 7283 | 0.49074 | 2.4407 | 1.9688 | 1.9328
| 7284 | 0.42593 | 2.8475 | 1.125 | 1.7689
| 7285 | 0.44444 | 3.1356 | 1.6875 | 2.2017
| 7286 | 0.37963 | 2.7458 | 1.4688 | 2.0294
| 7287 | 0.31481 | 1.9661 | 2 | 2.2395
| 7288 | 0.39815 | 2.0678 | 2.125 | 2.1807
| 7289 | 0.31481 | 2.678 | 1.6562 | 2.3151
| 7290 | 0.38889 | 2.2881 | 1.5 | 2.1008
| 7291 | 0.35185 | 3.6441 | 1.4375 | 2.1513
| 7292 | 0.39815 | 2.4237 | 0.40625 | 2.1555
| 7293 | 0.43519 | 2.5932 | 1.625 | 1.8613
| 7294 | 0.26852 | 1.7966 | 1.5938 | 1.7731
| 7295 | 0.42593 | 3.1525 | 1.5 | 2.4286
| 7296 | 0.5 | 3.1186 | 2.4062 | 2.2227
| 7297 | 0.42593 | 2 | 1.125 | 2.3403
| 7298 | 0.61111 | 2.3898 | 0.625 | 2.1597
| 7299 | 0.41667 | 2.2203 | 1.5938 | 1.9706
| 7300 | 0.46296 | 2.2203 | 1 | 2.0336
| 7301 | 0.27778 | 2.4915 | 1.1875 | 2.1975
| 7302 | 0.35185 | 2.9492 | 1 | 1.9202
| 7303 | 0.38889 | 3.1525 | 2.0625 | 2.105
| 7304 | 0.41667 | 1.9322 | 1.375 | 1.9874
| 7305 | 0.37037 | 2.8136 | 1.5 | 2.0084
| 7306 | 0.46296 | 2.4407 | 1.9688 | 2.4412
| 7307 | 0.48148 | 2.339 | 0.96875 | 1.9034
| 7308 | 0.5 | 3.0339 | 1.5312 | 2.0756
| 7309 | 0.37963 | 2.5254 | 0.875 | 2.3319
| 7310 | 0.47222 | 3.3729 | 1.3438 | 2.5882
| 7311 | 0.5 | 2.4576 | 1.2812 | 1.8739
| 7312 | 0.47222 | 2.4237 | 2.4062 | 2.3403
| 7313 | 0.41667 | 2.4746 | 0.71875 | 1.6891
| 7314 | 0.60185 | 3.2034 | 1.6875 | 1.9538
| 7315 | 0.34259 | 3.2712 | 1.4375 | 1.8445
| 7316 | 0.44444 | 2.1017 | 1.1875 | 2.8445
| 7317 | 0.5 | 2.8475 | 1.6875 | 2.1471
| 7318 | 0.47222 | 2.4237 | 2.3438 | 1.9538
| 7319 | 0.42593 | 2.2712 | 1.7188 | 2.063
| 7320 | 0.30556 | 2.9661 | 1.4375 | 2.0462
| 7321 | 0.43519 | 3.2712 | 2.0312 | 2.0084
| 7322 | 0.48148 | 2.6102 | 1.4688 | 1.9454
| 7323 | 0.5 | 2.7288 | 2.2812 | 2.0756
| 7324 | 0.4537 | 2.4237 | 1.8438 | 1.9622
| 7325 | 0.41667 | 2.0678 | 1.625 | 2.7101
| 7326 | 0.46296 | 2.7288 | 1.1562 | 2.1092
| 7327 | 0.41667 | 2.5763 | 0.96875 | 1.8487
| 7328 | 0.46296 | 3.1356 | 2.375 | 2.2269
| 7329 | 0.33333 | 2.7797 | 1.75 | 2.1681
| 7330 | 0.44444 | 2.1017 | 1.6562 | 2.395
| 7331 | 0.27778 | 2.3729 | 1.4688 | 2.042
| 7332 | 0.56481 | 2.6949 | 1.9062 | 2.1092
| 7333 | 0.44444 | 2.7288 | 1.5312 | 2.416
| 7334 | 0.41667 | 1.661 | 1.3125 | 1.937
| 7335 | 0.44444 | 3.4576 | 1.3438 | 2.3235
| 7336 | 0.65741 | 3.1864 | 1.125 | 1.916
| 7337 | 0.37037 | 3.2373 | 1.9062 | 1.8908
| 7338 | 0.40741 | 2.5763 | 1.5 | 2.0588
| 7339 | 0.2963 | 2.3051 | 0.96875 | 2.2857
| 7340 | 0.57407 | 2.6271 | 1.1562 | 2.1723
| 7341 | 0.32407 | 2.9661 | 0.46875 | 2.2479
| 7342 | 0.44444 | 2.8305 | 1.6562 | 2.063
| 7343 | 0.5463 | 2.1356 | 2.0312 | 2.0252
| 7344 | 0.41667 | 2.5424 | 3.0625 | 2.3109
| 7345 | 0.44444 | 3.0169 | 1.1875 | 2.084
| 7346 | 0.34259 | 3.1017 | 1.375 | 1.6765
| 7347 | 0.38889 | 2.5424 | 1.0625 | 2.3193
| 7348 | 0.46296 | 3.1695 | 1.125 | 2.1933
| 7349 | 0.39815 | 2.2373 | 2.2188 | 2.437
| 7350 | 0.32407 | 2.2712 | 1.1562 | 1.9706
| 7351 | 0.48148 | 2.3729 | 1.1875 | 1.7731
| 7352 | 0.35185 | 2.661 | 1.9688 | 2.1807
| 7353 | 0.49074 | 2.6949 | 1.3438 | 2.0462
| 7354 | 0.43519 | 2.3729 | 1.2188 | 1.937
| 7355 | 0.35185 | 2.2034 | 1.375 | 1.9706
| 7356 | 0.37037 | 3 | 2.0625 | 1.9874
| 7357 | 0.50926 | 2.9153 | 1.625 | 2.3319
| 7358 | 0.36111 | 2.4576 | 1.1562 | 2.1807
| 7359 | 0.38889 | 3.1356 | 1 | 2.1008
| 7360 | 0.52778 | 2.1525 | 1.625 | 2.0588
| 7361 | 0.46296 | 2.6271 | 1.2812 | 2.1134
| 7362 | 0.51852 | 3.339 | 1.7188 | 2.2563
| 7363 | 0.36111 | 2.4068 | 1.875 | 2.1933
| 7364 | 0.43519 | 3.3559 | 1.1875 | 2.021
| 7365 | 0.42593 | 3.1017 | 1.9375 | 2.1807
| 7366 | 0.28704 | 2.3729 | 0.96875 | 2.0336
| 7367 | 0.4537 | 2.6949 | 1.1875 | 2.2773
| 7368 | 0.40741 | 2.4237 | 1.3438 | 2.2101
| 7369 | 0.5 | 3.0847 | 0.96875 | 1.937
| 7370 | 0.52778 | 2.5593 | 2.0938 | 1.8403
| 7371 | 0.40741 | 3.1356 | 1.0938 | 2.0504
| 7372 | 0.33333 | 2.6102 | 1.6875 | 2.0966
| 7373 | 0.47222 | 3.1695 | 0.90625 | 1.9118
| 7374 | 0.42593 | 2.9661 | 1.2812 | 1.9412
| 7375 | 0.35185 | 2.0847 | 1.6875 | 1.9412
| 7376 | 0.43519 | 2.5424 | 1.125 | 1.8739
| 7377 | 0.33333 | 2.5763 | 1.4375 | 2.2185
| 7378 | 0.40741 | 3.339 | 1.5312 | 2.1597
| 7379 | 0.44444 | 2.1864 | 1.9688 | 2.0672
| 7380 | 0.39815 | 2.9492 | 1.1875 | 2.1471
| 7381 | 0.39815 | 2.7119 | 1.5938 | 2.2899
| 7382 | 0.34259 | 2.8305 | 2.125 | 2.084
| 7383 | 0.4537 | 2.322 | 1.9062 | 1.9622
| 7384 | 0.42593 | 2.4746 | 1.9062 | 1.8067
| 7385 | 0.34259 | 2.2034 | 2.25 | 2.0966
| 7386 | 0.36111 | 2.0847 | 0.90625 | 2.4538
| 7387 | 0.41667 | 2.8475 | 0.96875 | 2.0042
| 7388 | 0.46296 | 2.1356 | 1.0938 | 2.1849
| 7389 | 0.47222 | 2.8983 | 1.8125 | 1.8908
| 7390 | 0.33333 | 2.7119 | 1.375 | 1.9034
| 7391 | 0.38889 | 2.8475 | 0.625 | 2.3866
| 7392 | 0.38889 | 2.5932 | 0.875 | 2.2353
| 7393 | 0.51852 | 2.4237 | 0.6875 | 2.0126
| 7394 | 0.55556 | 2.2373 | 1.5 | 1.9874
| 7395 | 0.4537 | 3.1864 | 1.9062 | 2.2353
| 7396 | 0.42593 | 2.4746 | 1.25 | 2.1681
| 7397 | 0.2963 | 3.1186 | 1.5 | 2.3403
| 7398 | 0.34259 | 2.6441 | 1.2188 | 2.2815
| 7399 | 0.27778 | 3.5932 | 1.7188 | 2.2941
| 7400 | 0.56481 | 2.2203 | 0.90625 | 2.1681
| 7401 | 0.39815 | 2.8136 | 2.2812 | 1.8739
| 7402 | 0.25926 | 2.6441 | 1.5938 | 1.8992
| 7403 | 0.50926 | 2.8983 | 1.3438 | 1.9244
| 7404 | 0.46296 | 2.6271 | 0.96875 | 2.1218
| 7405 | 0.33333 | 2.9661 | 1.0625 | 2.3697
| 7406 | 0.31481 | 2.1525 | 1.0625 | 1.9076
| 7407 | 0.43519 | 2.661 | 0.65625 | 2.0924
| 7408 | 0.43519 | 2.6949 | 3.1875 | 2.1639
| 7409 | 0.62963 | 2.4237 | 1.7188 | 2.0462
| 7410 | 0.42593 | 2.339 | 0.71875 | 2.0672
| 7411 | 0.5 | 1.8644 | 1 | 2.0798
| 7412 | 0.31481 | 2.339 | 1.25 | 1.9034
| 7413 | 0.37037 | 2 | 1.4688 | 2.3361
| 7414 | 0.35185 | 2.2034 | 1.4688 | 2.6387
| 7415 | 0.28704 | 2.0678 | 1.1875 | 2.0042
| 7416 | 0.43519 | 2.9831 | 1.1875 | 1.9244
| 7417 | 0.43519 | 2.8305 | 0.5625 | 2.0924
| 7418 | 0.46296 | 2.3898 | 1.5938 | 2.4454
| 7419 | 0.31481 | 2.3051 | 1.7812 | 2.6975
| 7420 | 0.37037 | 2.8814 | 1.7188 | 2
| 7421 | 0.35185 | 2.7966 | 2.375 | 2.6303
| 7422 | 0.41667 | 2.1356 | 1.9062 | 2.1134
| 7423 | 0.66667 | 2.8814 | 1.375 | 1.8739
| 7424 | 0.53704 | 2.5085 | 1.125 | 2.5
| 7425 | 0.47222 | 2.1864 | 1.2812 | 2.3025
| 7426 | 0.49074 | 2.8983 | 0.78125 | 2.0504
| 7427 | 0.52778 | 2.661 | 1.7812 | 2.0294
| 7428 | 0.39815 | 3.6441 | 1.4688 | 2.2017
| 7429 | 0.62963 | 2.9153 | 1.4062 | 2.2815
| 7430 | 0.44444 | 2.7458 | 1.3125 | 1.9244
| 7431 | 0.43519 | 2.8814 | 1.625 | 2.4664
| 7432 | 0.48148 | 3.322 | 1.4688 | 2.1681
| 7433 | 0.31481 | 2.6441 | 2.0625 | 1.9328
| 7434 | 0.4537 | 2.6271 | 0.71875 | 2.3403
| 7435 | 0.40741 | 4.0847 | 1.9688 | 2.0126
| 7436 | 0.43519 | 2.7119 | 1.0938 | 2.0714
| 7437 | 0.31481 | 2.3729 | 1.625 | 2.2017
| 7438 | 0.36111 | 1.9831 | 1.4688 | 2.1429
| 7439 | 0.48148 | 2.8475 | 0.65625 | 2.4328
| 7440 | 0.40741 | 2.8305 | 0.84375 | 2.2353
| 7441 | 0.44444 | 2 | 1.6875 | 2.2773
| 7442 | 0.25926 | 2.1356 | 1.7188 | 1.6807
| 7443 | 0.36111 | 3.2542 | 1.1562 | 2.1429
| 7444 | 0.37963 | 2.8644 | 0.90625 | 2.1471
| 7445 | 0.41667 | 1.9661 | 0.96875 | 1.9664
| 7446 | 0.37963 | 3.6441 | 1.6562 | 2.0336
| 7447 | 0.5 | 2.3898 | 1.5312 | 1.8824
| 7448 | 0.37963 | 2.7119 | 1.4688 | 2.3655
| 7449 | 0.53704 | 2.9322 | 1.4688 | 1.7857
| 7450 | 0.44444 | 2 | 1.875 | 2.4034
| 7451 | 0.36111 | 2.1864 | 1.6875 | 2.0672
| 7452 | 0.35185 | 3.4915 | 1.1875 | 1.9664
| 7453 | 0.42593 | 2.4915 | 1.0938 | 2.3193
| 7454 | 0.5 | 2.5085 | 1 | 1.7479
| 7455 | 0.47222 | 2.0339 | 1.3438 | 2.0714
| 7456 | 0.32407 | 3.1356 | 2.3125 | 2.2731
| 7457 | 0.30556 | 2.7458 | 0.875 | 1.9832
| 7458 | 0.40741 | 2.7627 | 1.125 | 1.9916
| 7459 | 0.40741 | 2.8983 | 1.5 | 2.3067
| 7460 | 0.41667 | 2.339 | 1 | 2.0798
| 7461 | 0.38889 | 2.8983 | 0.75 | 1.9328
| 7462 | 0.37963 | 2.2542 | 1.7188 | 1.8613
| 7463 | 0.41667 | 2.7966 | 1.4375 | 1.8529
| 7464 | 0.40741 | 2.9661 | 0.78125 | 1.8025
| 7465 | 0.27778 | 2.2542 | 1.0625 | 1.8277
| 7466 | 0.48148 | 2.4915 | 0.96875 | 1.7857
| 7467 | 0.44444 | 2 | 0.625 | 2.0294
| 7468 | 0.42593 | 2.8983 | 1.875 | 1.9748
| 7469 | 0.46296 | 1.8136 | 1.5625 | 1.979
| 7470 | 0.5 | 2.339 | 1.3125 | 2.0378
| 7471 | 0.48148 | 4.1017 | 1.4062 | 2.3739
| 7472 | 0.43519 | 1.8983 | 1.125 | 2.0168
| 7473 | 0.37963 | 2.661 | 1.125 | 1.9832
| 7474 | 0.31481 | 2.9153 | 1.6875 | 1.9748
| 7475 | 0.37963 | 2.322 | 1.625 | 1.895
| 7476 | 0.40741 | 2.0339 | 1.5 | 2.2227
| 7477 | 0.44444 | 3.1695 | 1.0938 | 1.9832
| 7478 | 0.43519 | 2.4746 | 1.1562 | 1.9664
| 7479 | 0.31481 | 3.1186 | 2.125 | 2.4118
| 7480 | 0.4537 | 2.1017 | 1.5938 | 2.1723
| 7481 | 0.56481 | 2.8983 | 1.25 | 2.2101
| 7482 | 0.43519 | 2.6102 | 1.2812 | 2.0924
| 7483 | 0.43519 | 2.5254 | 2.0312 | 1.7899
| 7484 | 0.32407 | 2.8136 | 1.4062 | 1.7521
| 7485 | 0.33333 | 2.4068 | 3 | 2.416
| 7486 | 0.30556 | 1.9492 | 2.0312 | 2.1681
| 7487 | 0.4537 | 2.7458 | 1.75 | 2.3529
| 7488 | 0.43519 | 2.8644 | 1.25 | 1.8613
| 7489 | 0.32407 | 3.2373 | 0.90625 | 2.0126
| 7490 | 0.35185 | 2.8475 | 1.3125 | 2.2059
| 7491 | 0.32407 | 2.5424 | 1.8125 | 1.9412
| 7492 | 0.4537 | 3.3051 | 1 | 2.4538
| 7493 | 0.49074 | 2.1695 | 1.4688 | 2.2521
| 7494 | 0.50926 | 2.661 | 1.5625 | 2.1261
| 7495 | 0.37963 | 2.1695 | 2.4375 | 2.0756
| 7496 | 0.53704 | 2.4237 | 1.5938 | 2.4832
| 7497 | 0.27778 | 3.2034 | 1.5 | 2.3319
| 7498 | 0.58333 | 2.8983 | 1.4375 | 2.3025
| 7499 | 0.39815 | 2.678 | 1.0625 | 1.8445
| 7500 | 0.4537 | 2.8814 | 0.96875 | 1.7479
| 7501 | 0.40741 | 2.7627 | 2.0625 | 2.0042
| 7502 | 0.32407 | 3.0169 | 1.9688 | 2.021
| 7503 | 0.41667 | 3.7119 | 1.3438 | 2.1807
| 7504 | 0.48148 | 2.2712 | 0.75 | 2.1387
| 7505 | 0.4537 | 2.7458 | 0.59375 | 1.9622
| 7506 | 0.32407 | 3.1017 | 1.0312 | 2.2773
| 7507 | 0.51852 | 2.3729 | 1.9062 | 2.1261
| 7508 | 0.41667 | 2.6102 | 1.875 | 2.021
| 7509 | 0.37963 | 2.8305 | 2 | 1.9706
| 7510 | 0.51852 | 2.7458 | 1.2188 | 2.1807
| 7511 | 0.51852 | 2.8814 | 0.8125 | 2.1639
| 7512 | 0.43519 | 2.4407 | 1.1562 | 1.8403
| 7513 | 0.35185 | 2.7288 | 2.3438 | 2.2563
| 7514 | 0.37037 | 2.2034 | 1.0938 | 2.1513
| 7515 | 0.35185 | 3.0678 | 1.1562 | 1.9874
| 7516 | 0.42593 | 2.661 | 1.3125 | 1.9832
| 7517 | 0.26852 | 3.4237 | 2.5312 | 1.8571
| 7518 | 0.37963 | 3.1186 | 1.1562 | 2.1134
| 7519 | 0.65741 | 3.4746 | 1.2188 | 1.8908
| 7520 | 0.37037 | 3.4746 | 1.125 | 1.9034
| 7521 | 0.42593 | 2.1525 | 1.9375 | 1.9328
| 7522 | 0.51852 | 3.4237 | 0.90625 | 2.1429
| 7523 | 0.36111 | 2.7966 | 1.8125 | 2.1092
| 7524 | 0.41667 | 2.5763 | 1.4062 | 2.1345
| 7525 | 0.44444 | 2.3051 | 1.1875 | 2.2311
| 7526 | 0.35185 | 2.6102 | 0.96875 | 2.1891
| 7527 | 0.37963 | 2.5254 | 1.0625 | 1.8277
| 7528 | 0.52778 | 2 | 1.4062 | 2.3571
| 7529 | 0.53704 | 2.8475 | 1.375 | 1.9412
| 7530 | 0.28704 | 3.1525 | 1.2188 | 2.1261
| 7531 | 0.31481 | 2.4746 | 2.2188 | 2.021
| 7532 | 0.4537 | 2.661 | 2.5625 | 1.9664
| 7533 | 0.37037 | 3.3051 | 1.3438 | 2.0672
| 7534 | 0.38889 | 2.5932 | 2.0312 | 1.9244
| 7535 | 0.37037 | 2.1525 | 0.84375 | 2.0462
| 7536 | 0.43519 | 2.2712 | 1.0312 | 2.0588
| 7537 | 0.37037 | 2.5932 | 1.125 | 2.1555
| 7538 | 0.43519 | 2.3898 | 1.4062 | 1.9034
| 7539 | 0.53704 | 2.0508 | 1.5312 | 1.958
| 7540 | 0.53704 | 2.8305 | 1.1875 | 2.2857
| 7541 | 0.31481 | 2.7288 | 1.2188 | 2.2017
| 7542 | 0.39815 | 3.5932 | 1.4062 | 1.9622
| 7543 | 0.37963 | 3.0169 | 1 | 1.9832
| 7544 | 0.37037 | 2.7119 | 1.4688 | 2.0882
| 7545 | 0.43519 | 2.4915 | 1.6875 | 2.2899
| 7546 | 0.42593 | 2.4746 | 1 | 2.3151
| 7547 | 0.48148 | 3.1186 | 1.75 | 1.8655
| 7548 | 0.58333 | 2.9831 | 2 | 2.0042
| 7549 | 0.34259 | 2.5763 | 1.5 | 2.1303
| 7550 | 0.43519 | 2.4237 | 1.1875 | 1.937
| 7551 | 0.4537 | 2.9831 | 1.2812 | 1.979
| 7552 | 0.47222 | 2.7119 | 2.1562 | 2.8025
| 7553 | 0.49074 | 2.7966 | 0.96875 | 2.2479
| 7554 | 0.37037 | 3.2203 | 1.25 | 1.9496
| 7555 | 0.36111 | 1.7627 | 1.0312 | 2.3235
| 7556 | 0.44444 | 1.9661 | 1.2188 | 2.3824
| 7557 | 0.49074 | 2.2203 | 0.90625 | 1.9832
| 7558 | 0.44444 | 2.1864 | 0.96875 | 2
| 7559 | 0.37963 | 3.0508 | 1.7188 | 2.1555
| 7560 | 0.35185 | 3.2542 | 1.625 | 1.7647
| 7561 | 0.38889 | 2.4576 | 1.8125 | 1.9748
| 7562 | 0.48148 | 2.6271 | 1.2188 | 2.1176
| 7563 | 0.38889 | 2.0847 | 1.5312 | 2.0462
| 7564 | 0.40741 | 2.6441 | 1.7812 | 2.2227
| 7565 | 0.38889 | 2.9831 | 1.5312 | 2.1092
| 7566 | 0.49074 | 3.4068 | 1.9688 | 2.1555
| 7567 | 0.36111 | 2.1525 | 1.125 | 2.021
| 7568 | 0.43519 | 3.4237 | 1.0938 | 2.4916
| 7569 | 0.37963 | 3.322 | 1.9688 | 2.4874
| 7570 | 0.42593 | 2.339 | 1.5625 | 2.063
| 7571 | 0.47222 | 3.0847 | 1.375 | 1.8403
| 7572 | 0.23148 | 2.2203 | 1.9688 | 2.4622
| 7573 | 0.31481 | 2.5763 | 1.1875 | 1.8277
| 7574 | 0.4537 | 2.3559 | 0.75 | 1.8277
| 7575 | 0.37037 | 2.6271 | 1.5625 | 1.9454
| 7576 | 0.49074 | 2.5932 | 1.7812 | 2.2311
| 7577 | 0.65741 | 2.4576 | 0.65625 | 2.2899
| 7578 | 0.39815 | 2.6102 | 1.4688 | 2.0462
| 7579 | 0.36111 | 2.6441 | 1.3125 | 2.3025
| 7580 | 0.49074 | 2.6102 | 1.7812 | 1.7857
| 7581 | 0.48148 | 3.0339 | 1.1875 | 2.4916
| 7582 | 0.33333 | 2.7627 | 1.0625 | 2.0252
| 7583 | 0.5 | 2.6949 | 1.2188 | 1.7017
| 7584 | 0.26852 | 2.2034 | 1.5938 | 1.8235
| 7585 | 0.38889 | 2.5424 | 2.125 | 1.8782
| 7586 | 0.41667 | 2.4407 | 1.2188 | 1.9454
| 7587 | 0.39815 | 2.8644 | 2.3125 | 2.0966
| 7588 | 0.39815 | 2.9322 | 1.375 | 2.0546
| 7589 | 0.41667 | 2.7119 | 1.5 | 2.3445
| 7590 | 0.42593 | 2.2712 | 0.90625 | 1.9664
| 7591 | 0.33333 | 2.322 | 1.125 | 2.3319
| 7592 | 0.2963 | 2.3729 | 1.75 | 1.8193
| 7593 | 0.49074 | 2.3898 | 1.375 | 2.0882
| 7594 | 0.48148 | 3.3729 | 1.7188 | 2.0672
| 7595 | 0.50926 | 3.1695 | 0.78125 | 1.979
| 7596 | 0.37037 | 2.0847 | 1.6562 | 2.063
| 7597 | 0.37037 | 3.0678 | 1.5938 | 1.8487
| 7598 | 0.36111 | 2.0508 | 1.0625 | 1.8697
| 7599 | 0.25926 | 1.9831 | 1.9062 | 2.3782
| 7600 | 0.46296 | 2.4576 | 1.4688 | 2.1345
| 7601 | 0.27778 | 2.3051 | 1.0312 | 2.2227
| 7602 | 0.38889 | 2.3559 | 1.625 | 2.2311
| 7603 | 0.4537 | 3.2034 | 0.8125 | 1.8109
| 7604 | 0.43519 | 2.2542 | 0.84375 | 1.9034
| 7605 | 0.4537 | 2.661 | 1.875 | 1.8529
| 7606 | 0.66667 | 2.7458 | 0.71875 | 1.9538
| 7607 | 0.37963 | 3.1864 | 1.6875 | 2.1092
| 7608 | 0.37037 | 2.6441 | 1.4375 | 1.9874
| 7609 | 0.40741 | 2.4068 | 1.125 | 2.3109
| 7610 | 0.63889 | 3.4746 | 1.1562 | 2.2731
| 7611 | 0.43519 | 2.5085 | 1.7188 | 2.1513
| 7612 | 0.33333 | 3.2542 | 1.6875 | 2.0546
| 7613 | 0.39815 | 2.9831 | 1.0625 | 2.2983
| 7614 | 0.5463 | 2.7627 | 1.4688 | 2.2143
| 7615 | 0.32407 | 2.5763 | 1.0938 | 1.7899
| 7616 | 0.37963 | 2.0339 | 1.1875 | 1.7689
| 7617 | 0.43519 | 2.4915 | 1.5 | 1.9454
| 7618 | 0.49074 | 3.1017 | 1 | 2.0336
| 7619 | 0.60185 | 1.9831 | 1.5625 | 2.1933
| 7620 | 0.58333 | 2.6271 | 1.0938 | 2.0546
| 7621 | 0.46296 | 2.7288 | 1.1875 | 2.1933
| 7622 | 0.47222 | 1.5593 | 1.0625 | 2.0084
| 7623 | 0.35185 | 3.1525 | 1.1562 | 2.2521
| 7624 | 0.39815 | 3.2542 | 1.1562 | 1.937
| 7625 | 0.33333 | 2.9153 | 2 | 1.9916
| 7626 | 0.33333 | 2.7966 | 1.625 | 1.9118
| 7627 | 0.55556 | 2.8136 | 1.8438 | 1.8824
| 7628 | 0.44444 | 2.4915 | 1.5 | 1.9832
| 7629 | 0.56481 | 3.3051 | 0.90625 | 2.6345
| 7630 | 0.2963 | 3.1017 | 1.7188 | 2.2857
| 7631 | 0.47222 | 2.4068 | 1.7188 | 2
| 7632 | 0.52778 | 2.8136 | 1.3125 | 2.7143
| 7633 | 0.28704 | 2.7966 | 1 | 2.2101
| 7634 | 0.44444 | 2.7119 | 1.375 | 1.9664
| 7635 | 0.32407 | 2.3898 | 1.1875 | 1.937
| 7636 | 0.44444 | 2.5424 | 1.5312 | 2.1345
| 7637 | 0.5 | 2.7627 | 2.4062 | 1.8908
| 7638 | 0.36111 | 3.5424 | 1.1875 | 1.9538
| 7639 | 0.50926 | 2.2881 | 1.4375 | 2.0756
| 7640 | 0.48148 | 2.339 | 1.4688 | 2.5588
| 7641 | 0.41667 | 3.4407 | 1.7188 | 2.7353
| 7642 | 0.38889 | 2.5085 | 1.6875 | 2.4496
| 7643 | 0.39815 | 1.9661 | 1.9688 | 2.0882
| 7644 | 0.46296 | 2.8305 | 1.1562 | 2.1134
| 7645 | 0.48148 | 2.6271 | 1.5312 | 2.1471
| 7646 | 0.43519 | 2.4407 | 1.875 | 2.2017
| 7647 | 0.58333 | 2.8305 | 2 | 2.2731
| 7648 | 0.34259 | 2.1864 | 2.25 | 2.1681
| 7649 | 0.44444 | 2.4068 | 1.6562 | 2.3866
| 7650 | 0.39815 | 2.7966 | 1.5312 | 2.2353
| 7651 | 0.4537 | 2.678 | 1.5625 | 1.7773
| 7652 | 0.4537 | 3.3898 | 2.2188 | 2.3824
| 7653 | 0.37963 | 2.2034 | 1.1875 | 2.1261
| 7654 | 0.41667 | 2.0678 | 1.4062 | 1.8866
| 7655 | 0.43519 | 2.1695 | 1 | 1.9076
| 7656 | 0.42593 | 2.9831 | 2.9062 | 1.9454
| 7657 | 0.37963 | 2.2034 | 1.0938 | 1.9958
| 7658 | 0.61111 | 2.2203 | 0.9375 | 1.8866
| 7659 | 0.53704 | 2.5593 | 1.7812 | 2.1849
| 7660 | 0.40741 | 1.9492 | 1.4375 | 2.063
| 7661 | 0.38889 | 2.2373 | 0.875 | 2.1134
| 7662 | 0.39815 | 2.2203 | 0.78125 | 2.3109
| 7663 | 0.46296 | 2.5763 | 1.4688 | 1.9076
| 7664 | 0.41667 | 2.1186 | 1.5625 | 1.8445
| 7665 | 0.28704 | 2.4068 | 1.0938 | 1.9958
| 7666 | 0.49074 | 2.6102 | 1.1562 | 2.1513
| 7667 | 0.49074 | 2.2881 | 1.625 | 1.9202
| 7668 | 0.5 | 3.1864 | 1.125 | 2.3235
| 7669 | 0.58333 | 2.4068 | 1.2812 | 2.0588
| 7670 | 0.42593 | 2.8814 | 1.4062 | 2.0546
| 7671 | 0.47222 | 2.7288 | 1.625 | 1.9328
| 7672 | 0.33333 | 2.2712 | 1.0312 | 1.7605
| 7673 | 0.4537 | 3.2034 | 1.0625 | 1.9328
| 7674 | 0.56481 | 2.1186 | 1.3125 | 2.0798
| 7675 | 0.46296 | 2.4068 | 1.9375 | 2
| 7676 | 0.48148 | 2.1356 | 1.6562 | 2.1429
| 7677 | 0.48148 | 2.3898 | 1 | 1.895
| 7678 | 0.41667 | 3.0508 | 2.2812 | 2.0126
| 7679 | 0.43519 | 2.9322 | 1.3125 | 2.0588
| 7680 | 0.37963 | 2.7627 | 0.75 | 2.2227
| 7681 | 0.5 | 2.1525 | 1.9375 | 1.9328
| 7682 | 0.67593 | 2.5254 | 1.5 | 2.0084
| 7683 | 0.35185 | 2.7458 | 1.0938 | 1.958
| 7684 | 0.43519 | 2.0508 | 1.0938 | 1.9706
| 7685 | 0.47222 | 2.3559 | 1.6875 | 1.8782
| 7686 | 0.35185 | 2.2373 | 1.4062 | 2.3445
| 7687 | 0.32407 | 2.4407 | 1.875 | 2.1597
| 7688 | 0.26852 | 3.1017 | 0.9375 | 2.084
| 7689 | 0.42593 | 2.678 | 1.4688 | 1.9874
| 7690 | 0.49074 | 3.2881 | 1.6875 | 2.0798
| 7691 | 0.2963 | 3.2203 | 1.8438 | 1.9874
| 7692 | 0.41667 | 2.5424 | 1.2188 | 1.7437
| 7693 | 0.5 | 2.5424 | 0.96875 | 2.2353
| 7694 | 0.47222 | 1.8644 | 1.2812 | 2.0588
| 7695 | 0.43519 | 3.2034 | 1.3438 | 2.0126
| 7696 | 0.44444 | 2.8983 | 1.2188 | 2.1471
| 7697 | 0.43519 | 2.2542 | 1.2812 | 2.1597
| 7698 | 0.48148 | 2.2034 | 0.96875 | 1.8487
| 7699 | 0.41667 | 2.6102 | 2.0625 | 2.1092
| 7700 | 0.5 | 2.8983 | 1.0625 | 1.8571
| 7701 | 0.56481 | 2.8644 | 1.5312 | 2.1513
| 7702 | 0.51852 | 2.7288 | 1.5 | 2.105
| 7703 | 0.5 | 2.4237 | 1.75 | 2
| 7704 | 0.40741 | 2.1864 | 1.3125 | 2.0084
| 7705 | 0.60185 | 2.5254 | 1.0312 | 2.0546
| 7706 | 0.28704 | 2.1017 | 1.9062 | 2.4706
| 7707 | 0.46296 | 2.7288 | 2.3438 | 1.9034
| 7708 | 0.47222 | 2.7288 | 1.375 | 1.8235
| 7709 | 0.4537 | 2.9153 | 1.2812 | 1.9706
| 7710 | 0.65741 | 2.2034 | 1.3125 | 1.9622
| 7711 | 0.38889 | 2.3559 | 0.9375 | 2.0084
| 7712 | 0.53704 | 2.7966 | 1.4688 | 2.2479
| 7713 | 0.37037 | 3.2542 | 2.0625 | 1.6765
| 7714 | 0.40741 | 3.0339 | 1.5625 | 1.9916
| 7715 | 0.35185 | 3.0339 | 1.5312 | 2.2899
| 7716 | 0.37963 | 2.8814 | 1.4375 | 2.1555
| 7717 | 0.40741 | 1.7627 | 1.25 | 2.2311
| 7718 | 0.39815 | 2.8644 | 1.6875 | 1.9202
| 7719 | 0.42593 | 2.2712 | 1.3438 | 2.2983
| 7720 | 0.35185 | 2.5085 | 3 | 2.0462
| 7721 | 0.37963 | 2.7288 | 1.2812 | 2.2353
| 7722 | 0.26852 | 2.5932 | 1.7188 | 2.1933
| 7723 | 0.48148 | 3.4237 | 2.375 | 2.3487
| 7724 | 0.35185 | 3.1695 | 1.125 | 2.2479
| 7725 | 0.47222 | 2.5763 | 2.25 | 1.8655
| 7726 | 0.39815 | 2.7288 | 0.71875 | 2.0294
| 7727 | 0.62037 | 2.9661 | 1.5625 | 2.084
| 7728 | 0.37963 | 2.9492 | 0.9375 | 1.7815
| 7729 | 0.37037 | 2.3898 | 2.0625 | 1.9874
| 7730 | 0.26852 | 3.2203 | 1.9062 | 2.2395
| 7731 | 0.42593 | 2.661 | 1.625 | 2.1429
| 7732 | 0.4537 | 2.4407 | 1.1875 | 2.1134
| 7733 | 0.49074 | 2.6441 | 1.1875 | 1.7563
| 7734 | 0.46296 | 2.9661 | 1.4688 | 1.7311
| 7735 | 0.55556 | 1.7288 | 1.8438 | 1.916
| 7736 | 0.38889 | 2.6441 | 1.5938 | 1.9076
| 7737 | 0.47222 | 2.5763 | 1.0938 | 2.2143
| 7738 | 0.55556 | 3.1864 | 1.5938 | 2.2143
| 7739 | 0.50926 | 4 | 1.5938 | 2.0672
| 7740 | 0.38889 | 3.1186 | 1.75 | 1.8193
| 7741 | 0.4537 | 2.4576 | 0.78125 | 2.2227
| 7742 | 0.5463 | 2.4407 | 0.65625 | 1.958
| 7743 | 0.33333 | 3.2203 | 1.3125 | 2.5504
| 7744 | 0.36111 | 2.661 | 0.78125 | 1.9706
| 7745 | 0.5463 | 3.2034 | 0.90625 | 2.1513
| 7746 | 0.34259 | 2.339 | 1.4062 | 2.2017
| 7747 | 0.56481 | 2.5763 | 1.3125 | 2.1008
| 7748 | 0.65741 | 2.6441 | 1.4688 | 2.0378
| 7749 | 0.2963 | 2.6441 | 1.25 | 1.8067
| 7750 | 0.25 | 2.1356 | 1.0312 | 2.1092
| 7751 | 0.44444 | 2.1864 | 1.375 | 2
| 7752 | 0.41667 | 2.7119 | 1.2188 | 2.2269
| 7753 | 0.41667 | 2.0847 | 0.96875 | 1.9664
| 7754 | 0.49074 | 1.7627 | 1.5312 | 2.2941
| 7755 | 0.35185 | 3.1186 | 1.5938 | 2.3193
| 7756 | 0.27778 | 2.5763 | 1.1562 | 2.0798
| 7757 | 0.61111 | 2.3898 | 1.875 | 2.1008
| 7758 | 0.42593 | 2.8136 | 0.875 | 1.9706
| 7759 | 0.42593 | 3.0847 | 0.875 | 2
| 7760 | 0.40741 | 3.0678 | 1.0938 | 1.9958
| 7761 | 0.40741 | 2.3898 | 1.0938 | 1.9874
| 7762 | 0.43519 | 2.8136 | 2.3125 | 2.1849
| 7763 | 0.24074 | 3.6949 | 0.96875 | 2.084
| 7764 | 0.37037 | 2.4407 | 1.4688 | 2.0462
| 7765 | 0.36111 | 2.2881 | 1.1875 | 2.2101
| 7766 | 0.21296 | 3.0508 | 1.0625 | 1.7773
| 7767 | 0.47222 | 2.5932 | 1.3438 | 2.0336
| 7768 | 0.38889 | 2.9661 | 1.875 | 2.2143
| 7769 | 0.43519 | 2.661 | 0.84375 | 2.4076
| 7770 | 0.38889 | 3.3051 | 2.4062 | 1.8571
| 7771 | 0.47222 | 2.3729 | 1 | 2.0126
| 7772 | 0.2963 | 3.4576 | 1.125 | 1.9076
| 7773 | 0.5 | 3.1864 | 0.6875 | 2.0882
| 7774 | 0.43519 | 2.5932 | 2.0938 | 1.8151
| 7775 | 0.37037 | 3.0169 | 1.5312 | 2.2479
| 7776 | 0.55556 | 2.0339 | 1.0625 | 2.0966
| 7777 | 0.42593 | 2.1186 | 1.3125 | 2.3193
| 7778 | 0.26852 | 2.8644 | 1.0938 | 2.1008
| 7779 | 0.23148 | 2 | 1.125 | 2.042
| 7780 | 0.52778 | 2.7458 | 1.8125 | 1.895
| 7781 | 0.31481 | 2.8644 | 1.875 | 2.0504
| 7782 | 0.63889 | 2.9661 | 1.1875 | 2.063
| 7783 | 0.30556 | 3.3051 | 2.3438 | 2.0336
| 7784 | 0.35185 | 2.9153 | 0.96875 | 2.1008
| 7785 | 0.30556 | 2.6441 | 1.2812 | 2.5294
| 7786 | 0.26852 | 2.8475 | 0.9375 | 2.1765
| 7787 | 0.42593 | 2.4407 | 1.0625 | 2.0378
| 7788 | 0.38889 | 2.661 | 1.0938 | 2.0798
| 7789 | 0.53704 | 3.0508 | 1.5625 | 2.2269
| 7790 | 0.31481 | 2.4746 | 1.125 | 2.2101
| 7791 | 0.4537 | 3.1864 | 1.3125 | 2.3319
| 7792 | 0.33333 | 2.3051 | 1.875 | 1.9328
| 7793 | 0.33333 | 2.5593 | 1.625 | 2.1513
| 7794 | 0.32407 | 2.7627 | 1.5 | 2.0966
| 7795 | 0.46296 | 2.7288 | 2 | 2.0294
| 7796 | 0.40741 | 3.1017 | 2.2812 | 1.9244
| 7797 | 0.40741 | 2.7458 | 1.2812 | 2.2647
| 7798 | 0.55556 | 2.3051 | 1.3125 | 2.1176
| 7799 | 0.39815 | 2.1017 | 1.5 | 2.3782
| 7800 | 0.47222 | 1.8475 | 1.0625 | 2.1261
| 7801 | 0.41667 | 3 | 1.6875 | 1.7479
| 7802 | 0.2963 | 2.678 | 1.5625 | 2.1597
| 7803 | 0.37963 | 3.4237 | 0.8125 | 1.8739
| 7804 | 0.40741 | 2.5085 | 1.7188 | 2.2269
| 7805 | 0.42593 | 2.4407 | 1.2812 | 2.0336
| 7806 | 0.39815 | 2.9661 | 1.4062 | 2.1176
| 7807 | 0.5 | 3.4746 | 0.9375 | 2.0714
| 7808 | 0.4537 | 2.661 | 2.0625 | 2.1555
| 7809 | 0.31481 | 3.8814 | 1.4062 | 2.3571
| 7810 | 0.42593 | 2.3559 | 1.4375 | 2.0126
| 7811 | 0.34259 | 2.7288 | 1.2812 | 2.3529
| 7812 | 0.31481 | 2.8136 | 1.625 | 2.0378
| 7813 | 0.51852 | 2.661 | 1.25 | 1.8908
| 7814 | 0.44444 | 3.9661 | 0.875 | 1.8824
| 7815 | 0.41667 | 1.7627 | 1.4688 | 2.6303
| 7816 | 0.4537 | 2.5254 | 0.90625 | 2.2185
| 7817 | 0.51852 | 2.4576 | 1.0312 | 2.2647
| 7818 | 0.36111 | 2.322 | 1.4375 | 2.1092
| 7819 | 0.47222 | 3.2034 | 2.2812 | 2.1933
| 7820 | 0.43519 | 2.9661 | 1.2188 | 2.4874
| 7821 | 0.41667 | 2.3729 | 1.5938 | 1.9328
| 7822 | 0.44444 | 3.2373 | 1.5938 | 1.9244
| 7823 | 0.35185 | 2.9492 | 1.4375 | 1.9622
| 7824 | 0.48148 | 2.5085 | 1.3438 | 2.1429
| 7825 | 0.46296 | 2.3051 | 2.1875 | 2.063
| 7826 | 0.39815 | 2.1186 | 1.1875 | 2.1429
| 7827 | 0.41667 | 2.8644 | 1.2188 | 2.0378
| 7828 | 0.40741 | 2.2712 | 1.4688 | 1.8109
| 7829 | 0.32407 | 3 | 1.875 | 1.6387
| 7830 | 0.48148 | 2.339 | 1.875 | 2.3824
| 7831 | 0.47222 | 2.678 | 1.375 | 2.2479
| 7832 | 0.41667 | 2.4576 | 1.2188 | 2.1765
| 7833 | 0.38889 | 2.1356 | 1.4688 | 2.1092
| 7834 | 0.40741 | 2.7119 | 1.125 | 2.2731
| 7835 | 0.34259 | 2.4237 | 1.1562 | 1.9832
| 7836 | 0.30556 | 2.7288 | 1.4062 | 1.8992
| 7837 | 0.41667 | 3.661 | 1.125 | 2.3403
| 7838 | 0.44444 | 2.4576 | 1.625 | 2.542
| 7839 | 0.49074 | 2.322 | 1.0312 | 1.8319
| 7840 | 0.48148 | 2.4237 | 1.0312 | 1.916
| 7841 | 0.41667 | 2.5085 | 2.5938 | 2.5378
| 7842 | 0.44444 | 2.1864 | 1.3438 | 2.0546
| 7843 | 0.75 | 3.2542 | 0.46875 | 1.9538
| 7844 | 0.39815 | 2.1186 | 1.4688 | 2.3571
| 7845 | 0.37037 | 2.322 | 1.4688 | 2.1681
| 7846 | 0.48148 | 2.1864 | 1.1562 | 2.1092
| 7847 | 0.37037 | 2.6271 | 1.0312 | 2.2563
| 7848 | 0.36111 | 2.4915 | 0.96875 | 2.1176
| 7849 | 0.4537 | 3.3559 | 1.2812 | 2.2479
| 7850 | 0.41667 | 3.3729 | 1.25 | 1.8235
| 7851 | 0.43519 | 2.6271 | 1.7812 | 2.0462
| 7852 | 0.44444 | 2.8983 | 1.5 | 2.2815
| 7853 | 0.37963 | 2.5593 | 2.3125 | 2.2269
| 7854 | 0.38889 | 2.5424 | 1.0312 | 1.9706
| 7855 | 0.49074 | 2.9492 | 1.7812 | 1.958
| 7856 | 0.43519 | 3.5424 | 1.4375 | 1.8782
| 7857 | 0.5 | 3.0847 | 1.5 | 1.9748
| 7858 | 0.36111 | 2.8814 | 1.5938 | 2.1092
| 7859 | 0.31481 | 2.6271 | 0.9375 | 2
| 7860 | 0.33333 | 2.3898 | 0.9375 | 1.7605
| 7861 | 0.36111 | 2.322 | 0.625 | 1.8613
| 7862 | 0.41667 | 2.7627 | 1.4375 | 1.9664
| 7863 | 0.38889 | 2.6949 | 1.0938 | 1.9118
| 7864 | 0.48148 | 2.1864 | 1.4375 | 1.7479
| 7865 | 0.42593 | 2.4407 | 1.125 | 2.3193
| 7866 | 0.51852 | 3.2712 | 0.78125 | 1.7647
| 7867 | 0.48148 | 2.2712 | 1.4062 | 1.8277
| 7868 | 0.50926 | 2.4576 | 0.90625 | 2.1261
| 7869 | 0.47222 | 2.7966 | 1.9062 | 1.9958
| 7870 | 0.52778 | 1.9661 | 1.0938 | 2.0462
| 7871 | 0.41667 | 2.9153 | 1.1875 | 2.042
| 7872 | 0.43519 | 2.3729 | 1.4375 | 2.3025
| 7873 | 0.36111 | 2.8814 | 1.8125 | 1.9412
| 7874 | 0.50926 | 2.9492 | 1.8125 | 2.1555
| 7875 | 0.42593 | 3.2203 | 1.2188 | 2.2395
| 7876 | 0.37963 | 2.6949 | 1.9062 | 2.1345
| 7877 | 0.31481 | 2.3898 | 1.9688 | 2.0504
| 7878 | 0.30556 | 2.2712 | 1.4062 | 2.2185
| 7879 | 0.4537 | 2.7458 | 1.6875 | 1.9622
| 7880 | 0.32407 | 2.8814 | 1.0625 | 2.3403
| 7881 | 0.35185 | 3.2373 | 1.4375 | 2.3403
| 7882 | 0.32407 | 2.2203 | 1.0312 | 2.1261
| 7883 | 0.33333 | 2.339 | 0.75 | 2.2437
| 7884 | 0.37037 | 3 | 1.8438 | 2.1555
| 7885 | 0.4537 | 2.9492 | 1.5312 | 1.9496
| 7886 | 0.44444 | 2.5424 | 1.125 | 2.0924
| 7887 | 0.48148 | 3 | 1.125 | 1.7689
| 7888 | 0.4537 | 2.3898 | 1.0625 | 1.8109
| 7889 | 0.34259 | 2.4576 | 2.0312 | 2.084
| 7890 | 0.33333 | 2.1864 | 2.25 | 1.8613
| 7891 | 0.37963 | 2.8305 | 1.3125 | 2.6092
| 7892 | 0.51852 | 3.2542 | 2.3438 | 2.0882
| 7893 | 0.43519 | 2.6949 | 1.5 | 2.7311
| 7894 | 0.38889 | 2.8136 | 1.6875 | 2.2689
| 7895 | 0.32407 | 2.2373 | 1.2188 | 1.8824
| 7896 | 0.57407 | 2.1017 | 1.875 | 2.105
| 7897 | 0.52778 | 2.4407 | 0.96875 | 1.8824
| 7898 | 0.28704 | 3.3729 | 0.59375 | 2.2605
| 7899 | 0.39815 | 2.6102 | 1.625 | 2.1176
| 7900 | 0.49074 | 2.2373 | 1.5 | 2
| 7901 | 0.41667 | 3.4407 | 0.9375 | 2.084
| 7902 | 0.28704 | 2.5593 | 0.8125 | 2.0168
| 7903 | 0.42593 | 2.7119 | 1.125 | 2.1723
| 7904 | 0.30556 | 2.4746 | 0.9375 | 1.8487
| 7905 | 0.4537 | 2.8475 | 1.0938 | 1.916
| 7906 | 0.42593 | 3.3898 | 1.3438 | 2.0084
| 7907 | 0.43519 | 2.9153 | 1.625 | 2.5084
| 7908 | 0.34259 | 2.9153 | 1.4688 | 2.4076
| 7909 | 0.52778 | 2.7797 | 1.7188 | 2.1807
| 7910 | 0.32407 | 3.0339 | 1.375 | 1.9748
| 7911 | 0.38889 | 2.6271 | 1.375 | 2.0546
| 7912 | 0.36111 | 2.5424 | 1.4688 | 2.2899
| 7913 | 0.2963 | 1.8814 | 1.375 | 2.3403
| 7914 | 0.41667 | 2.339 | 0.75 | 2.3235
| 7915 | 0.39815 | 2.5254 | 1.6562 | 2.2269
| 7916 | 0.31481 | 2.4915 | 1.0938 | 2.0084
| 7917 | 0.26852 | 1.5254 | 1.9062 | 2.0546
| 7918 | 0.36111 | 3.3051 | 0.78125 | 1.7647
| 7919 | 0.39815 | 2.4237 | 1 | 2.3782
| 7920 | 0.40741 | 2.0678 | 1.8125 | 2.2185
| 7921 | 0.41667 | 2.8305 | 1.5938 | 2.2185
| 7922 | 0.39815 | 2.9661 | 1.2812 | 2.042
| 7923 | 0.42593 | 2.5593 | 1.2188 | 2.6218
| 7924 | 0.47222 | 2.9322 | 1.4688 | 2.3319
| 7925 | 0.5 | 2.4576 | 1.5312 | 1.9706
| 7926 | 0.39815 | 2.8305 | 2.0938 | 1.7857
| 7927 | 0.33333 | 3.5593 | 1.7812 | 2.0126
| 7928 | 0.53704 | 2.6441 | 1.625 | 1.9496
| 7929 | 0.31481 | 3.1186 | 0.8125 | 2.0798
| 7930 | 0.33333 | 2.7627 | 1.2188 | 2.3319
| 7931 | 0.61111 | 2.3729 | 1.2188 | 2.042
| 7932 | 0.31481 | 1.7119 | 0.8125 | 2.0714
| 7933 | 0.34259 | 2.5932 | 1.8125 | 2.5042
| 7934 | 0.34259 | 2.1017 | 1.2188 | 2.0126
| 7935 | 0.35185 | 2.4915 | 2.2812 | 2.2647
| 7936 | 0.28704 | 3.1695 | 1.5312 | 2.1387
| 7937 | 0.35185 | 2.4915 | 1.0312 | 1.5966
| 7938 | 0.25926 | 2.7119 | 1.875 | 2.0672
| 7939 | 0.42593 | 2.678 | 1.25 | 1.8908
| 7940 | 0.49074 | 2.9153 | 1.4375 | 2.3109
| 7941 | 0.53704 | 2.4068 | 1.375 | 2.1639
| 7942 | 0.42593 | 3.2203 | 1.4688 | 2.3235
| 7943 | 0.41667 | 2.7288 | 1.2188 | 1.937
| 7944 | 0.5463 | 2.9492 | 1.3125 | 2.3571
| 7945 | 0.56481 | 2.9831 | 0.8125 | 2.1261
| 7946 | 0.50926 | 3.1017 | 0.8125 | 2.063
| 7947 | 0.38889 | 2.7797 | 1.75 | 2.0042
| 7948 | 0.58333 | 2.4915 | 1.125 | 2.2857
| 7949 | 0.25 | 3.8305 | 1.5625 | 1.9958
| 7950 | 0.51852 | 2.2542 | 1.2188 | 2.2689
| 7951 | 0.31481 | 3 | 1.375 | 2.1008
| 7952 | 0.53704 | 2.7458 | 1.2188 | 2.2689
| 7953 | 0.30556 | 3.0339 | 1.7188 | 2.1092
| 7954 | 0.49074 | 2.7458 | 1.7812 | 2.042
| 7955 | 0.49074 | 3.2881 | 2.4062 | 2.0378
| 7956 | 0.2963 | 3.2034 | 1.3438 | 2.1008
| 7957 | 0.40741 | 2.5932 | 1.9375 | 2.0756
| 7958 | 0.35185 | 2.2034 | 2.4688 | 2.1639
| 7959 | 0.53704 | 2.2542 | 0.8125 | 2.021
| 7960 | 0.51852 | 2.8305 | 1.4062 | 1.8866
| 7961 | 0.38889 | 3.2034 | 1.125 | 2.0546
| 7962 | 0.40741 | 2.7288 | 0.78125 | 2.3571
| 7963 | 0.46296 | 2.5593 | 1.125 | 2.0126
| 7964 | 0.33333 | 2.7797 | 1.8125 | 2.2563
| 7965 | 0.33333 | 3.0508 | 0.90625 | 1.7311
| 7966 | 0.33333 | 3.1186 | 0.8125 | 1.9202
| 7967 | 0.56481 | 3.339 | 0.71875 | 1.9622
| 7968 | 0.37963 | 2.0678 | 1.2812 | 2.2311
| 7969 | 0.37963 | 3.0508 | 1.125 | 1.958
| 7970 | 0.34259 | 2.5593 | 2.3125 | 1.7857
| 7971 | 0.34259 | 2.5085 | 1.3438 | 2.0126
| 7972 | 0.55556 | 2.5085 | 1.6875 | 2.2395
| 7973 | 0.32407 | 2.5932 | 1.4375 | 2.0546
| 7974 | 0.46296 | 2.2373 | 1.1875 | 1.9916
| 7975 | 0.50926 | 3.4915 | 0.84375 | 2.4118
| 7976 | 0.30556 | 3.2034 | 1.5625 | 2.3235
| 7977 | 0.40741 | 2.5932 | 1 | 2.1218
| 7978 | 0.51852 | 2.3898 | 0.84375 | 2.105
| 7979 | 0.39815 | 2.9153 | 1.3125 | 2.3697
| 7980 | 0.41667 | 3.1356 | 1.5312 | 1.9328
| 7981 | 0.37963 | 2.2881 | 1.4688 | 2.1765
| 7982 | 0.37037 | 2.4746 | 1.625 | 2.021
| 7983 | 0.43519 | 2.339 | 0.84375 | 2.1807
| 7984 | 0.38889 | 2.9661 | 1.0625 | 2.3025
| 7985 | 0.23148 | 2.9661 | 0.875 | 1.8403
| 7986 | 0.42593 | 2.4237 | 1.0312 | 1.8782
| 7987 | 0.34259 | 2.9661 | 1.9375 | 1.895
| 7988 | 0.35185 | 2.4576 | 1.4688 | 2.2521
| 7989 | 0.36111 | 2.4576 | 1.4688 | 2.3277
| 7990 | 0.43519 | 2.7288 | 1.5625 | 1.9958
| 7991 | 0.39815 | 2.7627 | 2.2188 | 2.1429
| 7992 | 0.25926 | 3.0169 | 0.8125 | 2.1681
| 7993 | 0.62037 | 2.8305 | 1.8438 | 2.1765
| 7994 | 0.35185 | 2.8983 | 1.125 | 2.1387
| 7995 | 0.38889 | 3.3729 | 1.3438 | 2.2269
| 7996 | 0.25926 | 2.1864 | 0.9375 | 2.1597
| 7997 | 0.5 | 2.5932 | 1.875 | 2.1513
| 7998 | 0.49074 | 3.1017 | 1.625 | 2.0546
| 7999 | 0.37963 | 2.6441 | 2.1875 | 2.1555
| 8000 | 0.37037 | 2.7797 | 1.8125 | 2.2437
| 8001 | 0.49074 | 2.3559 | 1.5625 | 2.0966
| 8002 | 0.4537 | 2.8136 | 1.5625 | 1.9034
| 8003 | 0.53704 | 2.5424 | 1.3125 | 1.9916
| 8004 | 0.38889 | 2.1356 | 1.2188 | 1.9034
| 8005 | 0.36111 | 2.5254 | 1.875 | 1.8697
| 8006 | 0.40741 | 3.1864 | 1.3125 | 2.0546
| 8007 | 0.37037 | 3 | 1.2812 | 1.9958
| 8008 | 0.34259 | 1.9661 | 1.875 | 2.0546
| 8009 | 0.52778 | 2.8644 | 1.25 | 1.9328
| 8010 | 0.32407 | 2.4068 | 1.5312 | 1.9916
| 8011 | 0.48148 | 2.3729 | 1.4688 | 2.2983
| 8012 | 0.47222 | 3.3898 | 1.75 | 1.9958
| 8013 | 0.5 | 2.1186 | 2.25 | 2
| 8014 | 0.40741 | 2.6949 | 2.125 | 2.4622
| 8015 | 0.35185 | 2.661 | 2.0625 | 2.1723
| 8016 | 0.26852 | 2.1356 | 1.2812 | 2.0126
| 8017 | 0.4537 | 2.1356 | 1.75 | 2.2605
| 8018 | 0.47222 | 3.5085 | 1.2188 | 2.1092
| 8019 | 0.48148 | 3.2542 | 0.8125 | 1.8403
| 8020 | 0.31481 | 2.9322 | 1.6875 | 1.9958
| 8021 | 0.62963 | 2.4068 | 1.4062 | 2.2017
| 8022 | 0.2963 | 2.1695 | 1.7188 | 1.9034
| 8023 | 0.5 | 2.8136 | 0.9375 | 2.063
| 8024 | 0.23148 | 2.7966 | 1.4062 | 2.105
| 8025 | 0.36111 | 2.3559 | 1.375 | 2.2731
| 8026 | 0.4537 | 2.1695 | 1.4688 | 2.0126
| 8027 | 0.46296 | 2.5763 | 1.5312 | 2.1849
| 8028 | 0.48148 | 2.3729 | 2.0938 | 2.1891
| 8029 | 0.37037 | 2.5424 | 1.5625 | 2.1387
| 8030 | 0.5 | 3 | 1.6562 | 2.1092
| 8031 | 0.37963 | 2.8983 | 1.125 | 2.042
| 8032 | 0.39815 | 3.1017 | 0.40625 | 2.0714
| 8033 | 0.62037 | 2.5593 | 0.96875 | 2.021
| 8034 | 0.39815 | 2.7627 | 1.8438 | 1.9328
| 8035 | 0.43519 | 2.1356 | 1.7188 | 2.0966
| 8036 | 0.50926 | 3.1356 | 1.0938 | 2.0084
| 8037 | 0.31481 | 2.8136 | 2.7188 | 2.2143
| 8038 | 0.43519 | 2.6102 | 0.8125 | 2.0546
| 8039 | 0.33333 | 2.1864 | 1.4062 | 2.2395
| 8040 | 0.33333 | 2.1864 | 1.8438 | 1.9034
| 8041 | 0.39815 | 2.2881 | 1.4688 | 2.1261
| 8042 | 0.2963 | 2.8814 | 1.4062 | 1.8151
| 8043 | 0.35185 | 2.9492 | 1.4062 | 1.9076
| 8044 | 0.4537 | 2.1864 | 1.8125 | 2.1176
| 8045 | 0.47222 | 2.661 | 1.3438 | 2.0882
| 8046 | 0.68519 | 2.7966 | 1.3438 | 2.1891
| 8047 | 0.43519 | 3.1525 | 1.5312 | 1.8739
| 8048 | 0.38889 | 2.9831 | 1.5625 | 2.1639
| 8049 | 0.28704 | 3.2034 | 1.0625 | 2.0756
| 8050 | 0.34259 | 2.9831 | 1.4688 | 2.1513
| 8051 | 0.51852 | 2.5085 | 1.5 | 1.7773
| 8052 | 0.43519 | 2.3898 | 1.75 | 2.0924
| 8053 | 0.42593 | 2.5932 | 1.3125 | 1.9538
| 8054 | 0.34259 | 3.3051 | 1.5625 | 1.7983
| 8055 | 0.59259 | 2.9831 | 2.375 | 1.8992
| 8056 | 0.46296 | 2.4576 | 1.0938 | 1.8866
| 8057 | 0.28704 | 1.9661 | 1.25 | 2.0042
| 8058 | 0.4537 | 3.5254 | 1.5 | 2.0504
| 8059 | 0.39815 | 2.9661 | 1 | 2.063
| 8060 | 0.37963 | 2.3559 | 1.5625 | 2.2983
| 8061 | 0.51852 | 2.0508 | 1.6875 | 2.4244
| 8062 | 0.58333 | 2.4237 | 1.6875 | 2.2479
| 8063 | 0.31481 | 2.678 | 1.0312 | 1.8529
| 8064 | 0.56481 | 2.4746 | 1.1562 | 2.3235
| 8065 | 0.2963 | 4.0339 | 1.1562 | 1.8571
| 8066 | 0.50926 | 3.322 | 2.7812 | 2.0126
| 8067 | 0.43519 | 2.322 | 1.9688 | 1.9958
| 8068 | 0.36111 | 2.5254 | 1.8125 | 2.1176
| 8069 | 0.47222 | 3.0847 | 1.2188 | 1.8487
| 8070 | 0.41667 | 2.9153 | 0.96875 | 1.9244
| 8071 | 0.43519 | 1.9831 | 1.5938 | 1.6723
| 8072 | 0.37963 | 3.0508 | 1.25 | 1.9832
| 8073 | 0.55556 | 2.339 | 1.1562 | 2.2689
| 8074 | 0.52778 | 2.7458 | 1 | 1.9454
| 8075 | 0.31481 | 3.2542 | 3.2188 | 2.1218
| 8076 | 0.33333 | 3.6949 | 0.875 | 1.9286
| 8077 | 0.48148 | 2.322 | 1.5 | 1.9958
| 8078 | 0.47222 | 3.4068 | 1.6875 | 1.9412
| 8079 | 0.30556 | 2.6441 | 1 | 2.1008
| 8080 | 0.41667 | 2.1356 | 1.5625 | 2.395
| 8081 | 0.40741 | 1.678 | 0.8125 | 2.1555
| 8082 | 0.43519 | 1.9322 | 1.4062 | 1.9454
| 8083 | 0.43519 | 3.4576 | 1.1875 | 2.1975
| 8084 | 0.34259 | 2.9153 | 1.375 | 2.3025
| 8085 | 0.57407 | 2.0678 | 1.8125 | 2.0924
| 8086 | 0.33333 | 2.4407 | 1.375 | 2.1723
| 8087 | 0.49074 | 2.8475 | 1.9375 | 1.8151
| 8088 | 0.53704 | 3.1864 | 1.4062 | 1.9538
| 8089 | 0.41667 | 2.5254 | 2.1875 | 2.0126
| 8090 | 0.46296 | 3.0169 | 1.6562 | 2.1849
| 8091 | 0.43519 | 2.1525 | 1.5938 | 2.3319
| 8092 | 0.34259 | 3.0339 | 1.75 | 2.4244
| 8093 | 0.48148 | 2.7458 | 1.1562 | 2.0462
| 8094 | 0.34259 | 3.1356 | 1.1875 | 1.9958
| 8095 | 0.44444 | 2.3051 | 1.5312 | 1.8655
| 8096 | 0.2963 | 3.0169 | 1.125 | 2.0798
| 8097 | 0.37037 | 3.0339 | 1.2812 | 2.0924
| 8098 | 0.47222 | 2.4746 | 2.125 | 2.0378
| 8099 | 0.34259 | 3.1017 | 1.5625 | 2.0672
| 8100 | 0.38889 | 2.4576 | 2.0625 | 1.7521
| 8101 | 0.38889 | 2.3559 | 1.5938 | 1.9832
| 8102 | 0.43519 | 3.5763 | 1.375 | 2.3361
| 8103 | 0.37037 | 2.8136 | 1.5 | 1.8655
| 8104 | 0.50926 | 2.3729 | 1.4375 | 2.3782
| 8105 | 0.40741 | 2.5424 | 1.125 | 2.063
| 8106 | 0.28704 | 2.9153 | 1.5312 | 2.1933
| 8107 | 0.50926 | 3.2034 | 1.375 | 2.2647
| 8108 | 0.41667 | 3.4576 | 1.4688 | 2.1008
| 8109 | 0.51852 | 3.3898 | 1 | 2.0714
| 8110 | 0.33333 | 2.1864 | 1.2188 | 1.8235
| 8111 | 0.35185 | 2.5085 | 2.0312 | 2.2605
| 8112 | 0.26852 | 2 | 1.7812 | 2.0798
| 8113 | 0.37963 | 2.4915 | 0.71875 | 2.1513
| 8114 | 0.49074 | 3.2034 | 2 | 2.1597
| 8115 | 0.43519 | 2.8814 | 1.3125 | 2.2143
| 8116 | 0.32407 | 2.5593 | 0.71875 | 2.0756
| 8117 | 0.5 | 3.2373 | 1.7188 | 2.1891
| 8118 | 0.28704 | 2.4237 | 1.3438 | 1.9496
| 8119 | 0.5 | 3.1864 | 1.875 | 2.3067
| 8120 | 0.28704 | 2.5763 | 0.75 | 2.1218
| 8121 | 0.52778 | 3 | 1.4062 | 1.9622
| 8122 | 0.31481 | 2.3729 | 1 | 2.2437
| 8123 | 0.44444 | 2.8644 | 1.375 | 1.8824
| 8124 | 0.59259 | 2.7288 | 2.4375 | 2.1849
| 8125 | 0.35185 | 2.8136 | 1.5938 | 2.2647
| 8126 | 0.55556 | 2.0678 | 1.2812 | 2.0294
| 8127 | 0.37963 | 3.1017 | 1.3125 | 2.3782
| 8128 | 0.49074 | 2.6441 | 1.0625 | 2.1261
| 8129 | 0.50926 | 2.5593 | 1.25 | 1.7185
| 8130 | 0.33333 | 2.8983 | 1.6562 | 1.8697
| 8131 | 0.36111 | 2.3559 | 1.0938 | 2.0462
| 8132 | 0.38889 | 3 | 0.75 | 2.4958
| 8133 | 0.2963 | 3.0339 | 0.875 | 2.4244
| 8134 | 0.32407 | 2.2034 | 0.96875 | 2.3025
| 8135 | 0.41667 | 1.7797 | 1.9688 | 2.3655
| 8136 | 0.40741 | 2.678 | 1.5312 | 1.8151
| 8137 | 0.30556 | 2.1017 | 1.4375 | 1.9412
| 8138 | 0.52778 | 2.7119 | 1.7812 | 2.3487
| 8139 | 0.4537 | 2.1864 | 1.5 | 2.1639
| 8140 | 0.35185 | 2.8983 | 2.3125 | 2.1176
| 8141 | 0.33333 | 2.5424 | 1.9688 | 2.0462
| 8142 | 0.42593 | 2.8305 | 1.6562 | 2.0504
| 8143 | 0.47222 | 1.9322 | 0.625 | 2.1218
| 8144 | 0.27778 | 3.2203 | 1.4062 | 2.3655
| 8145 | 0.37963 | 2.6102 | 1.125 | 1.8782
| 8146 | 0.37963 | 2.661 | 1 | 2.0882
| 8147 | 0.4537 | 2.6949 | 1.2812 | 2.042
| 8148 | 0.39815 | 2.7288 | 0.8125 | 1.7857
| 8149 | 0.34259 | 3.7966 | 1.25 | 2.2857
| 8150 | 0.51852 | 2.9661 | 1.5 | 1.8361
| 8151 | 0.37037 | 3.5424 | 1.5312 | 1.7815
| 8152 | 0.42593 | 2.661 | 1.1875 | 2.0168
| 8153 | 0.51852 | 2.4407 | 1.5 | 2.1387
| 8154 | 0.4537 | 2.5932 | 1.9688 | 2.2899
| 8155 | 0.27778 | 2.1186 | 1.375 | 1.8908
| 8156 | 0.38889 | 3.0847 | 1.0312 | 2.4916
| 8157 | 0.48148 | 2.5593 | 1.8125 | 2.0588
| 8158 | 0.44444 | 2.7966 | 1.2812 | 2.1681
| 8159 | 0.37037 | 3.0678 | 0.9375 | 2.0588
| 8160 | 0.5463 | 2.661 | 1.75 | 2.1008
| 8161 | 0.38889 | 2.1525 | 1.5938 | 2.5
| 8162 | 0.46296 | 2.4237 | 1.875 | 1.7983
| 8163 | 0.40741 | 2.2373 | 1.5938 | 1.9664
| 8164 | 0.39815 | 3.3898 | 1.0625 | 1.7983
| 8165 | 0.40741 | 2.6271 | 1.9062 | 2.1261
| 8166 | 0.40741 | 2.5254 | 0.96875 | 2.2017
| 8167 | 0.40741 | 2.9492 | 1.0625 | 1.9118
| 8168 | 0.50926 | 2.661 | 1.3438 | 1.6218
| 8169 | 0.27778 | 2.2034 | 1.5625 | 1.9118
| 8170 | 0.48148 | 2.678 | 1.5938 | 2.4076
| 8171 | 0.27778 | 2.7119 | 1.4688 | 2.0966
| 8172 | 0.43519 | 2.7797 | 1.5938 | 2.2395
| 8173 | 0.37037 | 2.0169 | 1.7188 | 2.1597
| 8174 | 0.66667 | 2.339 | 1.6562 | 2.1092
| 8175 | 0.48148 | 2.8136 | 1.375 | 2.0672
| 8176 | 0.53704 | 2.0678 | 1.5938 | 2.0798
| 8177 | 0.42593 | 1.9831 | 1.9062 | 2.0882
| 8178 | 0.34259 | 1.7458 | 0.84375 | 2.0042
| 8179 | 0.49074 | 2.661 | 1.0625 | 1.8866
| 8180 | 0.35185 | 2.1186 | 1.6875 | 2.105
| 8181 | 0.36111 | 3.2203 | 1.5625 | 2.105
| 8182 | 0.38889 | 3.3559 | 1.8125 | 2.1849
| 8183 | 0.50926 | 1.9831 | 0.46875 | 1.8824
| 8184 | 0.2963 | 2.5932 | 0.6875 | 2.1218
| 8185 | 0.42593 | 2.4915 | 1.375 | 2.2857
| 8186 | 0.49074 | 1.8814 | 0.84375 | 1.958
| 8187 | 0.2963 | 2.6102 | 1.2812 | 2.1261
| 8188 | 0.46296 | 1.8983 | 0.9375 | 2.0504
| 8189 | 0.38889 | 2.9831 | 1.2812 | 1.958
| 8190 | 0.41667 | 2.1356 | 1.5 | 2.1807
| 8191 | 0.43519 | 2.7119 | 1.7812 | 2.063
| 8192 | 0.30556 | 2.6271 | 1.3438 | 2.2059
| 8193 | 0.51852 | 3.4576 | 0.875 | 2.1134
| 8194 | 0.47222 | 2.5593 | 1.2812 | 2.2941
| 8195 | 0.52778 | 2.9661 | 1.5625 | 2.1176
| 8196 | 0.41667 | 2.2712 | 2.3438 | 1.8824
| 8197 | 0.50926 | 2.7966 | 1.5312 | 2.1387
| 8198 | 0.57407 | 1.9661 | 1.0312 | 2.4412
| 8199 | 0.38889 | 3.4237 | 1.6875 | 2.0084
| 8200 | 0.37963 | 3.1356 | 1.3438 | 1.7941
| 8201 | 0.49074 | 2.4237 | 2 | 2.063
| 8202 | 0.47222 | 2.8305 | 1.625 | 2.2647
| 8203 | 0.46296 | 3.2712 | 1.25 | 1.9748
| 8204 | 0.4537 | 2.4407 | 1.125 | 2.2983
| 8205 | 0.32407 | 3.5254 | 1.5312 | 2.4832
| 8206 | 0.49074 | 2.5593 | 2.4688 | 2.1303
| 8207 | 0.34259 | 2.9492 | 0.875 | 2.0252
| 8208 | 0.5463 | 2.3051 | 2 | 2.1008
| 8209 | 0.34259 | 2.6102 | 2.2188 | 2.0168
| 8210 | 0.40741 | 2.6441 | 1.625 | 2.3445
| 8211 | 0.27778 | 2.2203 | 1.875 | 2.105
| 8212 | 0.41667 | 3.0508 | 1.3438 | 1.7731
| 8213 | 0.5 | 2.7458 | 2.4375 | 2.1218
| 8214 | 0.53704 | 2.8814 | 2.125 | 1.9664
| 8215 | 0.33333 | 2.2034 | 1.5312 | 1.8529
| 8216 | 0.43519 | 2.7966 | 2.25 | 1.9874
| 8217 | 0.5463 | 3.3729 | 1.1562 | 1.9622
| 8218 | 0.40741 | 2.5763 | 1.875 | 1.8277
| 8219 | 0.40741 | 2.9153 | 1.4375 | 1.9244
| 8220 | 0.31481 | 3.2203 | 0.78125 | 1.9874
| 8221 | 0.50926 | 1.9661 | 0.90625 | 2.0378
| 8222 | 0.36111 | 1.9492 | 0.96875 | 2.3361
| 8223 | 0.4537 | 2.1525 | 2.0625 | 2.2017
| 8224 | 0.34259 | 3.2712 | 0.875 | 2.3193
| 8225 | 0.49074 | 2.7797 | 1.5 | 2.0714
| 8226 | 0.36111 | 2.4237 | 1.2812 | 2.0798
| 8227 | 0.25 | 2.7458 | 1.2188 | 2.0294
| 8228 | 0.42593 | 2.2373 | 1.1875 | 1.9076
| 8229 | 0.39815 | 2.2881 | 1.5938 | 2.0588
| 8230 | 0.34259 | 2.6949 | 1.2188 | 2.0126
| 8231 | 0.30556 | 2.8644 | 1.1875 | 1.9454
| 8232 | 0.39815 | 3.1864 | 1.3438 | 1.979
| 8233 | 0.37963 | 2.3559 | 1.3438 | 2.105
| 8234 | 0.30556 | 3.1186 | 1.5 | 1.8866
| 8235 | 0.47222 | 3.5254 | 2.4375 | 2.1218
| 8236 | 0.49074 | 2.8983 | 1.6562 | 1.9664
| 8237 | 0.40741 | 2.322 | 1.2812 | 2.0504
| 8238 | 0.38889 | 3.2542 | 1.6875 | 2.5
| 8239 | 0.36111 | 2.6102 | 1.25 | 1.7605
| 8240 | 0.39815 | 2.5932 | 1.75 | 2
| 8241 | 0.32407 | 1.6102 | 0.875 | 2.479
| 8242 | 0.2963 | 2.5254 | 2 | 2.1975
| 8243 | 0.44444 | 2.1186 | 0.9375 | 2.395
| 8244 | 0.49074 | 3.7288 | 1.4688 | 1.9454
| 8245 | 0.61111 | 2.8814 | 0.875 | 2.0084
| 8246 | 0.34259 | 2.8814 | 1.2812 | 2.0672
| 8247 | 0.58333 | 2.8814 | 1.0625 | 1.7899
| 8248 | 0.36111 | 2.8305 | 1.75 | 1.8151
| 8249 | 0.62963 | 2.7288 | 0.75 | 1.9454
| 8250 | 0.37963 | 2.7119 | 2.2188 | 1.8361
| 8251 | 0.36111 | 2.9492 | 1.5 | 1.9832
| 8252 | 0.37037 | 2.7288 | 1.625 | 2.1471
| 8253 | 0.47222 | 3.6441 | 1.125 | 2.1681
| 8254 | 0.34259 | 2.8136 | 1.25 | 2.2185
| 8255 | 0.39815 | 3.1356 | 0.875 | 2.3655
| 8256 | 0.42593 | 2.8136 | 1.4688 | 1.7059
| 8257 | 0.37037 | 3.3898 | 1.5938 | 2.2647
| 8258 | 0.38889 | 2.4576 | 2.25 | 1.8235
| 8259 | 0.27778 | 2.4746 | 1.375 | 2.0168
| 8260 | 0.30556 | 2.6102 | 1.5625 | 1.8866
| 8261 | 0.38889 | 2.8305 | 1.5625 | 2.416
| 8262 | 0.40741 | 2.7288 | 1.5625 | 2.3445
| 8263 | 0.36111 | 2.2542 | 1.5312 | 1.8613
| 8264 | 0.36111 | 2.7288 | 2.0312 | 2.1765
| 8265 | 0.32407 | 2.0508 | 1.25 | 1.8697
| 8266 | 0.50926 | 2.5085 | 0.625 | 2.0084
| 8267 | 0.35185 | 2.5424 | 1.9688 | 2.0798
| 8268 | 0.43519 | 2.7966 | 1.4375 | 2.0378
| 8269 | 0.42593 | 2.6949 | 2 | 2.2563
| 8270 | 0.41667 | 2.4576 | 0.90625 | 2.2941
| 8271 | 0.52778 | 2.5763 | 0.8125 | 2.2689
| 8272 | 0.36111 | 2.6271 | 2.0312 | 1.8529
| 8273 | 0.32407 | 2.0339 | 1.4375 | 2.021
| 8274 | 0.2963 | 3.1864 | 1.8438 | 1.8866
| 8275 | 0.4537 | 2 | 1.9062 | 1.9706
| 8276 | 0.40741 | 2.7627 | 1.4688 | 1.9874
| 8277 | 0.40741 | 2.7458 | 1.1562 | 2.4622
| 8278 | 0.60185 | 2.322 | 1.75 | 2.0042
| 8279 | 0.41667 | 2.2034 | 1.3438 | 2.0966
| 8280 | 0.28704 | 2.4068 | 1.1875 | 2.0462
| 8281 | 0.4537 | 2.3729 | 1.875 | 2.2815
| 8282 | 0.36111 | 2.8475 | 1.5938 | 1.9202
| 8283 | 0.41667 | 2.9831 | 1.8438 | 1.916
| 8284 | 0.46296 | 2.6949 | 0.78125 | 1.9622
| 8285 | 0.37963 | 2.4407 | 1.3438 | 2.1933
| 8286 | 0.5 | 2.4068 | 1.625 | 2.3739
| 8287 | 0.30556 | 2.4237 | 2.1562 | 1.9622
| 8288 | 0.25926 | 3.9492 | 1.0312 | 2.0084
| 8289 | 0.36111 | 2.5763 | 1.5312 | 2.1092
| 8290 | 0.37963 | 1.7966 | 1.9375 | 2.105
| 8291 | 0.47222 | 3.6102 | 1.3125 | 2.2899
| 8292 | 0.4537 | 2.0678 | 2.0312 | 2.4622
| 8293 | 0.44444 | 3.1356 | 1.5625 | 2.1849
| 8294 | 0.51852 | 3.4407 | 1.2812 | 2.3529
| 8295 | 0.28704 | 2.1186 | 1.0625 | 2.1933
| 8296 | 0.32407 | 2.6102 | 1.6562 | 2.0504
| 8297 | 0.5 | 2.678 | 1.0312 | 1.8235
| 8298 | 0.33333 | 3.5593 | 1.125 | 2
| 8299 | 0.41667 | 3.1525 | 1.4375 | 1.9412
| 8300 | 0.31481 | 2.8644 | 1.0625 | 1.9244
| 8301 | 0.27778 | 2.7797 | 1.625 | 1.8992
| 8302 | 0.2037 | 2.5085 | 1.4375 | 2.2899
| 8303 | 0.28704 | 1.8983 | 2.5625 | 2.105
| 8304 | 0.4537 | 2.1017 | 1.1562 | 2.0756
| 8305 | 0.5 | 2.7119 | 1.1562 | 1.9454
| 8306 | 0.44444 | 2.0169 | 1.5 | 2.2605
| 8307 | 0.40741 | 2.8983 | 1.125 | 2.4958
| 8308 | 0.31481 | 2.322 | 1.1562 | 1.9286
| 8309 | 0.32407 | 2.1525 | 2.0938 | 2.2983
| 8310 | 0.30556 | 3.1186 | 1.6875 | 1.8697
| 8311 | 0.32407 | 2.6441 | 0.875 | 2.105
| 8312 | 0.34259 | 3.2542 | 1.0625 | 2.1639
| 8313 | 0.28704 | 2.339 | 1.2812 | 2.3235
| 8314 | 0.42593 | 3.3051 | 1.5312 | 1.9958
| 8315 | 0.35185 | 1.8305 | 0.40625 | 1.979
| 8316 | 0.28704 | 2.1356 | 0.625 | 2.0588
| 8317 | 0.23148 | 2.9831 | 1.0938 | 1.8277
| 8318 | 0.4537 | 2.2203 | 0.8125 | 1.958
| 8319 | 0.36111 | 2.7458 | 1.9375 | 1.7059
| 8320 | 0.37037 | 2.2034 | 1.2812 | 2.2563
| 8321 | 0.37037 | 2.9661 | 1.625 | 1.9832
| 8322 | 0.46296 | 3.0678 | 2.4688 | 2.2059
| 8323 | 0.44444 | 2.4746 | 1.3125 | 2.084
| 8324 | 0.37963 | 2.6441 | 2.0625 | 2.0084
| 8325 | 0.5 | 3.3051 | 1.0312 | 2.1008
| 8326 | 0.31481 | 2.6949 | 1.6562 | 2.1429
| 8327 | 0.46296 | 2.4915 | 0.8125 | 2.1303
| 8328 | 0.51852 | 2.3729 | 1.4062 | 2.1387
| 8329 | 0.51852 | 3.1356 | 0.65625 | 2.1471
| 8330 | 0.5 | 2.6271 | 1.2188 | 2.3361
| 8331 | 0.48148 | 2.7288 | 0.875 | 2.5798
| 8332 | 0.46296 | 2.6949 | 1.5625 | 2.2983
| 8333 | 0.33333 | 1.9322 | 1.9688 | 2.2605
| 8334 | 0.46296 | 3.5424 | 1.1875 | 1.895
| 8335 | 0.33333 | 2.8136 | 2.0625 | 2.1639
| 8336 | 0.46296 | 2.5932 | 1.25 | 2.3361
| 8337 | 0.62963 | 2.5254 | 1.1875 | 1.8193
| 8338 | 0.5 | 2.1695 | 1.25 | 2.0336
| 8339 | 0.49074 | 2.7288 | 1.5312 | 1.9202
| 8340 | 0.38889 | 2.7627 | 0.84375 | 1.8824
| 8341 | 0.43519 | 2.8475 | 1.9062 | 2.2605
| 8342 | 0.57407 | 3.4746 | 1.75 | 2.2815
| 8343 | 0.56481 | 2.2542 | 1.2188 | 2.0966
| 8344 | 0.39815 | 2.4746 | 0.90625 | 2.0504
| 8345 | 0.50926 | 3.0508 | 0.84375 | 1.9916
| 8346 | 0.38889 | 2.1017 | 1.1875 | 1.8739
| 8347 | 0.4537 | 2.0847 | 1.5312 | 2.2227
| 8348 | 0.42593 | 2.0847 | 0.875 | 2.1639
| 8349 | 0.57407 | 2.1356 | 1.6875 | 2.1975
| 8350 | 0.41667 | 2.9831 | 1.0625 | 1.937
| 8351 | 0.30556 | 2.4576 | 1.7812 | 2.1429
| 8352 | 0.36111 | 2.7458 | 1.125 | 1.7899
| 8353 | 0.38889 | 3.2712 | 1.875 | 2.1008
| 8354 | 0.32407 | 2.5424 | 1.9688 | 2.1345
| 8355 | 0.43519 | 2.9322 | 2.875 | 1.9496
| 8356 | 0.47222 | 3.2034 | 1.2188 | 2.063
| 8357 | 0.26852 | 2.7966 | 1.625 | 2.1471
| 8358 | 0.34259 | 1.9831 | 1.5625 | 2.1092
| 8359 | 0.47222 | 3.3559 | 1.4062 | 2.2437
| 8360 | 0.34259 | 3.2203 | 0.9375 | 2.2311
| 8361 | 0.43519 | 3.4068 | 2.1875 | 2.2017
| 8362 | 0.47222 | 3.4237 | 1.4062 | 2.1765
| 8363 | 0.38889 | 2.6271 | 0.5625 | 2.0336
| 8364 | 0.35185 | 2.8136 | 1.0938 | 2.2311
| 8365 | 0.51852 | 2.6949 | 2.0625 | 2.1176
| 8366 | 0.38889 | 2.5424 | 1.7188 | 1.9328
| 8367 | 0.35185 | 3.6441 | 2.8125 | 1.8025
| 8368 | 0.5 | 2.339 | 0.90625 | 2.2227
| 8369 | 0.35185 | 3.6441 | 2.4688 | 2.2227
| 8370 | 0.47222 | 2.9153 | 1.0312 | 2.437
| 8371 | 0.48148 | 3.5424 | 1.25 | 1.9202
| 8372 | 0.34259 | 3.1356 | 1.625 | 2.5
| 8373 | 0.46296 | 2.5085 | 1.4375 | 2.1807
| 8374 | 0.37963 | 2.6102 | 1.625 | 2.2269
| 8375 | 0.40741 | 2.6441 | 1.7812 | 2.1639
| 8376 | 0.50926 | 2.5763 | 0.9375 | 2.2857
| 8377 | 0.22222 | 2.6102 | 1.5312 | 2.021
| 8378 | 0.36111 | 1.9661 | 1.4375 | 2.2521
| 8379 | 0.38889 | 2.1864 | 2.3125 | 2.3529
| 8380 | 0.44444 | 2.5254 | 1.4375 | 2.0714
| 8381 | 0.55556 | 2.8136 | 0.875 | 2.0546
| 8382 | 0.43519 | 3.0339 | 0.90625 | 2.2983
| 8383 | 0.50926 | 1.9322 | 1.5312 | 2.1303
| 8384 | 0.25926 | 2.4068 | 0.78125 | 1.9412
| 8385 | 0.40741 | 2.4915 | 1.7812 | 2.084
| 8386 | 0.43519 | 2.8814 | 1.0625 | 2.5378
| 8387 | 0.44444 | 2.5763 | 1.9062 | 2.1134
| 8388 | 0.49074 | 2.3729 | 1.125 | 2.3025
| 8389 | 0.38889 | 2.5424 | 1.1875 | 2.1429
| 8390 | 0.37037 | 2.6441 | 1.25 | 2.2311
| 8391 | 0.42593 | 2.5593 | 2.0312 | 2.6639
| 8392 | 0.39815 | 2.4746 | 1.3438 | 2.0168
| 8393 | 0.44444 | 2.2881 | 1.0938 | 1.8697
| 8394 | 0.38889 | 2.7627 | 1.875 | 2.2185
| 8395 | 0.4537 | 3.0169 | 1.6875 | 2.3571
| 8396 | 0.46296 | 3.2881 | 0.78125 | 2.1891
| 8397 | 0.5 | 2.8136 | 0.625 | 1.9496
| 8398 | 0.35185 | 3.2542 | 1.375 | 2.1429
| 8399 | 0.30556 | 2.2034 | 1.125 | 1.9706
| 8400 | 0.39815 | 3.0339 | 1.25 | 2.1807
| 8401 | 0.41667 | 3.6441 | 0.96875 | 2.3571
| 8402 | 0.43519 | 2.7458 | 1.0312 | 2.6891
| 8403 | 0.33333 | 2.0847 | 1.1875 | 2.2227
| 8404 | 0.50926 | 4.0169 | 1.375 | 2.0588
| 8405 | 0.46296 | 2.6949 | 1.875 | 1.979
| 8406 | 0.51852 | 2.4237 | 1.5312 | 1.9202
| 8407 | 0.32407 | 2.7627 | 1.25 | 1.8445
| 8408 | 0.39815 | 2.7119 | 0.84375 | 1.9118
| 8409 | 0.44444 | 2.8983 | 1.5625 | 2.458
| 8410 | 0.24074 | 1.9322 | 1 | 2.1597
| 8411 | 0.44444 | 3.6271 | 0.9375 | 1.8529
| 8412 | 0.35185 | 2.2542 | 1.1875 | 2.3235
| 8413 | 0.33333 | 2.5763 | 1.25 | 2.2017
| 8414 | 0.25926 | 2.1017 | 0.9375 | 1.7437
| 8415 | 0.39815 | 3.0678 | 1.3438 | 2.0882
| 8416 | 0.25 | 3.8644 | 1.125 | 1.937
| 8417 | 0.35185 | 2.3898 | 0.5 | 2.0504
| 8418 | 0.24074 | 3.4915 | 1.4062 | 1.9874
| 8419 | 0.40741 | 2.5085 | 1.6875 | 2.3824
| 8420 | 0.43519 | 3.322 | 1.4062 | 2.105
| 8421 | 0.43519 | 2.8644 | 1.0938 | 1.8782
| 8422 | 0.41667 | 2.8136 | 1.7188 | 2.021
| 8423 | 0.2963 | 2.0339 | 1.75 | 2.021
| 8424 | 0.32407 | 3.1864 | 1.6562 | 2.2773
| 8425 | 0.30556 | 2.4576 | 1.7812 | 1.8866
| 8426 | 0.2963 | 2.0339 | 1.0625 | 2.1513
| 8427 | 0.5463 | 2.9492 | 0.875 | 2.1092
| 8428 | 0.53704 | 2.4576 | 1.0625 | 2.1261
| 8429 | 0.35185 | 2.8305 | 0.9375 | 2.0126
| 8430 | 0.33333 | 2.3051 | 0.40625 | 1.6975
| 8431 | 0.35185 | 3.3898 | 1.4688 | 2.3151
| 8432 | 0.59259 | 2.8475 | 1.8125 | 2.2731
| 8433 | 0.50926 | 2.0847 | 1.8438 | 2.0168
| 8434 | 0.52778 | 2.5932 | 1.6562 | 1.916
| 8435 | 0.48148 | 2.8814 | 1.125 | 2.4034
| 8436 | 0.37037 | 2.5254 | 1.4375 | 2.0252
| 8437 | 0.22222 | 1.8136 | 1.5312 | 1.9412
| 8438 | 0.37037 | 2.7627 | 0.84375 | 2.2269
| 8439 | 0.42593 | 2.9153 | 1 | 2.1681
| 8440 | 0.40741 | 2.4915 | 1.375 | 2.1218
| 8441 | 0.34259 | 3.8814 | 1.7188 | 2.0714
| 8442 | 0.34259 | 2.0508 | 0.625 | 1.9748
| 8443 | 0.37037 | 3.0339 | 2.0312 | 1.8866
| 8444 | 0.42593 | 2.3051 | 1.4375 | 2.0924
| 8445 | 0.39815 | 2.8305 | 1.2812 | 1.8824
| 8446 | 0.5463 | 3.1525 | 1.2188 | 2.1134
| 8447 | 0.41667 | 2.5254 | 0.90625 | 2.2101
| 8448 | 0.4537 | 2.7119 | 1.875 | 2.1387
| 8449 | 0.39815 | 2.5763 | 1.4375 | 2.2227
| 8450 | 0.37037 | 2.6271 | 1.7812 | 2.1723
| 8451 | 0.36111 | 2.0339 | 1.0312 | 2.4244
| 8452 | 0.26852 | 2.7119 | 0.9375 | 1.9328
| 8453 | 0.55556 | 2.4576 | 1.4688 | 2.1429
| 8454 | 0.33333 | 2.7966 | 1.8438 | 2.2143
| 8455 | 0.34259 | 1.9492 | 0.59375 | 2.437
| 8456 | 0.4537 | 2.6271 | 0.78125 | 1.9412
| 8457 | 0.37037 | 2.8305 | 1.0625 | 1.8697
| 8458 | 0.31481 | 2.5932 | 1.3438 | 1.9538
| 8459 | 0.31481 | 2.6102 | 0.71875 | 1.9076
| 8460 | 0.43519 | 2.2034 | 1.375 | 2.6471
| 8461 | 0.43519 | 2.6271 | 1.7188 | 1.8319
| 8462 | 0.34259 | 2.4746 | 1.0312 | 1.9454
| 8463 | 0.28704 | 2.4915 | 0.71875 | 1.937
| 8464 | 0.43519 | 3.3051 | 1.5938 | 2.021
| 8465 | 0.28704 | 2.339 | 1.4062 | 2.2185
| 8466 | 0.33333 | 2.3729 | 1.625 | 2.1471
| 8467 | 0.41667 | 2.2034 | 1.8438 | 2.0882
| 8468 | 0.51852 | 2.7797 | 1.0938 | 2.1218
| 8469 | 0.46296 | 2.5932 | 1.25 | 2.1176
| 8470 | 0.33333 | 2.7627 | 2.0938 | 2.1681
| 8471 | 0.47222 | 3.3729 | 1 | 1.9328
| 8472 | 0.21296 | 2.9661 | 2.0938 | 1.9538
| 8473 | 0.46296 | 3.0678 | 1.5312 | 2.042
| 8474 | 0.44444 | 1.7966 | 1.0312 | 1.9118
| 8475 | 0.33333 | 2.7966 | 1.4688 | 1.9034
| 8476 | 0.48148 | 2.4576 | 0.78125 | 1.7857
| 8477 | 0.41667 | 2.7627 | 0.875 | 2.0798
| 8478 | 0.55556 | 2.2373 | 0.875 | 1.7563
| 8479 | 0.32407 | 2.4237 | 1.4062 | 2.3613
| 8480 | 0.31481 | 3.0339 | 0.90625 | 1.8782
| 8481 | 0.44444 | 1.8475 | 1.4062 | 2.0798
| 8482 | 0.30556 | 3.0508 | 1.3125 | 2.063
| 8483 | 0.31481 | 2.6102 | 0.96875 | 2.0336
| 8484 | 0.34259 | 2.5763 | 1.0625 | 1.9034
| 8485 | 0.46296 | 3.0508 | 1.4375 | 2.3025
| 8486 | 0.39815 | 3.2203 | 1.3125 | 2.0798
| 8487 | 0.47222 | 2.6102 | 1.1562 | 1.9412
| 8488 | 0.41667 | 2.7458 | 2.4688 | 1.8235
| 8489 | 0.43519 | 2.7288 | 1.2812 | 2.0252
| 8490 | 0.36111 | 2.5254 | 1.5938 | 2.2479
| 8491 | 0.44444 | 2.1864 | 1.1562 | 1.916
| 8492 | 0.33333 | 2.5254 | 1.0312 | 2.1891
| 8493 | 0.32407 | 2.4576 | 0.71875 | 2.0672
| 8494 | 0.52778 | 2.661 | 0.9375 | 2.2773
| 8495 | 0.51852 | 2.1017 | 1.8125 | 1.9706
| 8496 | 0.52778 | 3 | 1.6562 | 2.1891
| 8497 | 0.23148 | 2.2203 | 1.9688 | 2.1218
| 8498 | 0.37037 | 3.5085 | 2.375 | 2.0294
| 8499 | 0.52778 | 3.1695 | 2.1562 | 2.4706
| 8500 | 0.28704 | 2.8136 | 1.3125 | 2.0168
| 8501 | 0.36111 | 2.9661 | 1.1562 | 1.8277
| 8502 | 0.30556 | 3 | 1.1875 | 1.937
| 8503 | 0.37963 | 2.7966 | 1.5312 | 2.2437
| 8504 | 0.27778 | 2.4576 | 1.1875 | 1.9034
| 8505 | 0.49074 | 2.0847 | 1.0938 | 2
| 8506 | 0.4537 | 2.6949 | 1.7188 | 2.1429
| 8507 | 0.4537 | 3.5763 | 1.8125 | 2.2143
| 8508 | 0.61111 | 2.8136 | 0.78125 | 1.9328
| 8509 | 0.5 | 3.339 | 1.1562 | 2.4328
| 8510 | 0.40741 | 1.8136 | 0.90625 | 2.0504
| 8511 | 0.43519 | 2.8644 | 1.4688 | 2.1765
| 8512 | 0.38889 | 3.0847 | 1.125 | 1.916
| 8513 | 0.42593 | 2.8814 | 1.8438 | 1.9328
| 8514 | 0.35185 | 3.0508 | 1.0625 | 2.2311
| 8515 | 0.36111 | 2.9831 | 1.5 | 1.958
| 8516 | 0.36111 | 3.0339 | 1.5 | 1.979
| 8517 | 0.38889 | 2.6102 | 1.5625 | 1.937
| 8518 | 0.31481 | 2.4576 | 0.9375 | 2.2479
| 8519 | 0.42593 | 2.8475 | 1 | 2.2647
| 8520 | 0.30556 | 2.4407 | 1.1875 | 1.9832
| 8521 | 0.31481 | 2.5085 | 1 | 2
| 8522 | 0.33333 | 3.1695 | 1.375 | 2.2815
| 8523 | 0.4537 | 2.7288 | 1.8125 | 2.0294
| 8524 | 0.44444 | 2.6271 | 0.75 | 2.2395
| 8525 | 0.41667 | 2.2203 | 1.3125 | 2.0462
| 8526 | 0.35185 | 2.9661 | 1.4688 | 2.2983
| 8527 | 0.46296 | 2.4407 | 1.0312 | 2.063
| 8528 | 0.38889 | 3 | 1.125 | 2.4916
| 8529 | 0.41667 | 2.5424 | 1.5938 | 2.0882
| 8530 | 0.49074 | 2.2203 | 1.125 | 2.2143
| 8531 | 0.4537 | 2.6271 | 1.0938 | 2.0294
| 8532 | 0.43519 | 2.4915 | 1.7812 | 2.0042
| 8533 | 0.40741 | 2.7119 | 0.875 | 2.1597
| 8534 | 0.38889 | 1.7119 | 1.2812 | 2.1513
| 8535 | 0.36111 | 2.2203 | 0.9375 | 1.9622
| 8536 | 0.39815 | 2.9492 | 1.75 | 1.9034
| 8537 | 0.5 | 2.1356 | 0.875 | 1.9538
| 8538 | 0.39815 | 3.2034 | 1 | 2.3403
| 8539 | 0.44444 | 3.4915 | 0.875 | 2.0042
| 8540 | 0.34259 | 3.0339 | 1.4688 | 2.1218
| 8541 | 0.36111 | 2.5254 | 2 | 2.3109
| 8542 | 0.25 | 2.5593 | 1.1875 | 2.1008
| 8543 | 0.37963 | 2.4068 | 1.1562 | 2.021
| 8544 | 0.40741 | 2.2034 | 1.0938 | 2.0462
| 8545 | 0.41667 | 2.0339 | 1.125 | 2.7437
| 8546 | 0.44444 | 2.2034 | 1.3125 | 2.3319
| 8547 | 0.43519 | 2.339 | 1.4062 | 2.0882
| 8548 | 0.30556 | 3.1186 | 1.625 | 2.0336
| 8549 | 0.42593 | 2.4237 | 1.4375 | 2.0126
| 8550 | 0.34259 | 2.6271 | 0.6875 | 2.3655
| 8551 | 0.32407 | 3.4237 | 1.7188 | 2.2647
| 8552 | 0.31481 | 3.4068 | 1.0938 | 2.3319
| 8553 | 0.47222 | 2.9322 | 1.4375 | 2.1681
| 8554 | 0.5463 | 2.7458 | 1.875 | 2.2605
| 8555 | 0.44444 | 2.5254 | 0.875 | 1.8529
| 8556 | 0.36111 | 3.0169 | 0.9375 | 2.0672
| 8557 | 0.50926 | 2.7966 | 1.125 | 2.0546
| 8558 | 0.53704 | 2.9322 | 1.2188 | 2.4244
| 8559 | 0.42593 | 3.339 | 1.2812 | 2.1723
| 8560 | 0.40741 | 2.5424 | 1.5 | 1.8319
| 8561 | 0.5463 | 2.5593 | 1.6562 | 2.1008
| 8562 | 0.26852 | 2.9322 | 1.5625 | 1.9748
| 8563 | 0.49074 | 2.5593 | 1.6562 | 1.7563
| 8564 | 0.37963 | 3.3051 | 1.0938 | 2.1849
| 8565 | 0.33333 | 2.1186 | 2.6562 | 2.0126
| 8566 | 0.41667 | 2.7797 | 0.65625 | 2.9412
| 8567 | 0.43519 | 3.1356 | 1.875 | 2.1933
| 8568 | 0.69444 | 3.9492 | 1.375 | 2.1134
| 8569 | 0.4537 | 3.8475 | 1.3125 | 2.1471
| 8570 | 0.52778 | 2.7797 | 1.25 | 2
| 8571 | 0.47222 | 3.0169 | 1.2188 | 2.2353
| 8572 | 0.51852 | 3.1356 | 1.6875 | 2.1513
| 8573 | 0.42593 | 3.8475 | 1.4062 | 1.895
| 8574 | 0.26852 | 2.6441 | 1 | 2.1429
| 8575 | 0.40741 | 2.2034 | 2.1562 | 2.2983
| 8576 | 0.34259 | 2.5932 | 1.0312 | 2.3193
| 8577 | 0.39815 | 2.3051 | 1.4375 | 2.042
| 8578 | 0.37037 | 3.1356 | 1.1875 | 2.2143
| 8579 | 0.36111 | 3.0339 | 2.4375 | 2.2437
| 8580 | 0.31481 | 2.2034 | 1.0625 | 2.1008
| 8581 | 0.49074 | 2.4237 | 1.7188 | 1.9202
| 8582 | 0.24074 | 2.5254 | 1.0938 | 2.2353
| 8583 | 0.31481 | 3.2203 | 1.0938 | 2.0126
| 8584 | 0.51852 | 2.5085 | 2 | 2.0882
| 8585 | 0.39815 | 2.8136 | 1.1875 | 2.0966
| 8586 | 0.30556 | 3.6271 | 2.3438 | 2.4118
| 8587 | 0.31481 | 3.339 | 1.4688 | 2.1134
| 8588 | 0.40741 | 3.1017 | 1.0312 | 1.8655
| 8589 | 0.51852 | 2.7966 | 1.5 | 2.0672
| 8590 | 0.46296 | 3.8305 | 0.84375 | 1.9076
| 8591 | 0.65741 | 2.0847 | 1.6562 | 2.105
| 8592 | 0.46296 | 2.0678 | 1.1562 | 2.2479
| 8593 | 0.47222 | 3.2542 | 2.1562 | 2.3277
| 8594 | 0.57407 | 2.7797 | 1.5625 | 1.9286
| 8595 | 0.48148 | 2.5085 | 1.5312 | 2.1723
| 8596 | 0.5 | 2.4746 | 1.2188 | 2.3655
| 8597 | 0.27778 | 3.1695 | 1.25 | 2.1134
| 8598 | 0.49074 | 2.1864 | 1.7188 | 2.0462
| 8599 | 0.38889 | 2.9492 | 1.8438 | 2.0294
| 8600 | 0.38889 | 2.322 | 1.5938 | 2.2185
| 8601 | 0.51852 | 3.2881 | 1.5938 | 2.1387
| 8602 | 0.60185 | 2.322 | 1.3125 | 2.0168
| 8603 | 0.31481 | 2.678 | 1.0938 | 2.0924
| 8604 | 0.31481 | 2.1356 | 1.5938 | 2.0714
| 8605 | 0.38889 | 2.7966 | 0.78125 | 2.2353
| 8606 | 0.39815 | 3.0508 | 1.5625 | 2.021
| 8607 | 0.44444 | 2.8983 | 1.3125 | 1.937
| 8608 | 0.49074 | 2.3051 | 1.1562 | 2.2353
| 8609 | 0.25926 | 2.9322 | 1.875 | 2.0546
| 8610 | 0.34259 | 2.678 | 1.8438 | 1.9286
| 8611 | 0.37963 | 2.7966 | 2.0312 | 2.0168
| 8612 | 0.31481 | 2.6271 | 2 | 2.0672
| 8613 | 0.19444 | 3.3051 | 1.4062 | 2.2521
| 8614 | 0.44444 | 2.9492 | 1.3438 | 1.9874
| 8615 | 0.46296 | 2.5254 | 1.375 | 2.479
| 8616 | 0.41667 | 3.5254 | 0.59375 | 2.563
| 8617 | 0.37963 | 2.678 | 1.4688 | 2.105
| 8618 | 0.4537 | 2.3559 | 1.2812 | 1.895
| 8619 | 0.35185 | 3.0678 | 1.125 | 2.1134
| 8620 | 0.40741 | 2.9322 | 1.1562 | 2.1134
| 8621 | 0.5463 | 3.3051 | 2.5625 | 2.2689
| 8622 | 0.47222 | 3.2034 | 1 | 2.042
| 8623 | 0.30556 | 2.322 | 1.6875 | 2.3319
| 8624 | 0.5 | 3.3051 | 2.0625 | 1.9244
| 8625 | 0.39815 | 3.0847 | 2.0625 | 2.1933
| 8626 | 0.5 | 2.6441 | 1.5 | 2.1345
| 8627 | 0.37037 | 2.4068 | 1.3438 | 1.8655
| 8628 | 0.52778 | 2.4915 | 1.0938 | 2.0462
| 8629 | 0.44444 | 2.2712 | 0.84375 | 1.937
| 8630 | 0.40741 | 3.2373 | 1.9375 | 1.9832
| 8631 | 0.49074 | 2.3559 | 1.0938 | 2.0084
| 8632 | 0.37037 | 2.5763 | 1.25 | 2.2689
| 8633 | 0.57407 | 3.2712 | 1.1562 | 1.9202
| 8634 | 0.37963 | 2.9322 | 1.4062 | 2.3487
| 8635 | 0.42593 | 3.2712 | 1.8438 | 2.3445
| 8636 | 0.48148 | 3.4915 | 1.625 | 1.8319
| 8637 | 0.44444 | 3 | 1.5625 | 2.0714
| 8638 | 0.41667 | 2.7119 | 1 | 2.1597
| 8639 | 0.41667 | 2.7119 | 1.4375 | 2.2353
| 8640 | 0.37037 | 3.4915 | 0.25 | 2.0588
| 8641 | 0.30556 | 3.8814 | 1.7812 | 1.7269
| 8642 | 0.4537 | 3.4407 | 1.6875 | 1.9664
| 8643 | 0.4537 | 3.3729 | 1.4062 | 2.2647
| 8644 | 0.36111 | 3.0339 | 1.4375 | 2.0924
| 8645 | 0.38889 | 2.8644 | 1.5312 | 1.8782
| 8646 | 0.38889 | 3.9492 | 0.96875 | 2.1176
| 8647 | 0.2963 | 2.5763 | 1.2188 | 2.2647
| 8648 | 0.40741 | 3.2542 | 1.4688 | 2.0336
| 8649 | 0.38889 | 2.6441 | 1.2812 | 1.9496
| 8650 | 0.44444 | 2.322 | 1.5625 | 1.9034
| 8651 | 0.52778 | 2.9322 | 1.4375 | 2.2353
| 8652 | 0.32407 | 2.4915 | 1.4688 | 2.0672
| 8653 | 0.51852 | 2.1695 | 0.90625 | 2.0378
| 8654 | 0.33333 | 2.7966 | 1.375 | 2.521
| 8655 | 0.41667 | 3.0169 | 1.125 | 2.1176
| 8656 | 0.5 | 2.8305 | 1.6562 | 2.0714
| 8657 | 0.49074 | 2.2203 | 2.2188 | 2.0252
| 8658 | 0.47222 | 3.0508 | 1.0625 | 2.0546
| 8659 | 0.39815 | 2.4407 | 1.4062 | 2.0882
| 8660 | 0.37963 | 3.0169 | 0.8125 | 2.1849
| 8661 | 0.46296 | 3.1186 | 1.875 | 1.9748
| 8662 | 0.39815 | 2.8644 | 1.5625 | 1.9076
| 8663 | 0.44444 | 2.4915 | 1.75 | 2.1765
| 8664 | 0.32407 | 2.5424 | 1 | 2.0588
| 8665 | 0.42593 | 2.339 | 1.2812 | 1.9916
| 8666 | 0.38889 | 2.3559 | 1.25 | 1.9118
| 8667 | 0.37037 | 3.1864 | 1.625 | 1.8529
| 8668 | 0.43519 | 2.7458 | 1.1562 | 2.0798
| 8669 | 0.59259 | 2.661 | 2.0938 | 2.0966
| 8670 | 0.49074 | 2.9322 | 1.1875 | 1.9202
| 8671 | 0.48148 | 2.5254 | 1.0312 | 1.9664
| 8672 | 0.47222 | 2.6102 | 1.7188 | 1.8739
| 8673 | 0.35185 | 2.7119 | 1.375 | 2.0546
| 8674 | 0.40741 | 2.9153 | 1.0625 | 2.2899
| 8675 | 0.62037 | 2.5932 | 1.4375 | 2.2017
| 8676 | 0.63889 | 3.2203 | 0.9375 | 2.1429
| 8677 | 0.35185 | 2.661 | 1.9062 | 2.0252
| 8678 | 0.46296 | 2.5593 | 2.1562 | 1.979
| 8679 | 0.42593 | 2.9831 | 2.0625 | 2.1176
| 8680 | 0.2963 | 1.9831 | 1.1875 | 2.1639
| 8681 | 0.36111 | 2.7966 | 0.84375 | 1.7017
| 8682 | 0.40741 | 2.7458 | 2.4062 | 1.9244
| 8683 | 0.41667 | 2.2203 | 1.1875 | 2.2017
| 8684 | 0.30556 | 2.8475 | 1.4375 | 2.2017
| 8685 | 0.38889 | 2.9322 | 1.0312 | 1.8613
| 8686 | 0.43519 | 2.7966 | 1.2188 | 2.5714
| 8687 | 0.33333 | 1.8644 | 1.25 | 2.3655
| 8688 | 0.37037 | 3.322 | 1.3125 | 1.8992
| 8689 | 0.32407 | 2.6271 | 1.5625 | 1.9328
| 8690 | 0.62037 | 2.322 | 1.1875 | 2.2395
| 8691 | 0.49074 | 2.4407 | 1.0625 | 2.1513
| 8692 | 0.5 | 3.2542 | 1.125 | 2.1092
| 8693 | 0.35185 | 2.2203 | 1.625 | 1.9916
| 8694 | 0.42593 | 2.3559 | 1 | 2.1933
| 8695 | 0.46296 | 2.7966 | 0.875 | 1.9832
| 8696 | 0.59259 | 2.4068 | 1.375 | 2.1218
| 8697 | 0.49074 | 2.7797 | 0.8125 | 2.1008
| 8698 | 0.37037 | 2.4746 | 1.1562 | 2.1008
| 8699 | 0.49074 | 3.1864 | 1.0938 | 2.3571
| 8700 | 0.4537 | 3.0847 | 0.875 | 2.1513
| 8701 | 0.2963 | 2.661 | 1.25 | 2.2479
| 8702 | 0.30556 | 3.1356 | 1.625 | 2.2479
| 8703 | 0.38889 | 3.1695 | 1.9062 | 2.1555
| 8704 | 0.41667 | 1.7458 | 1.5 | 2.0084
| 8705 | 0.39815 | 2.339 | 1.5938 | 1.8487
| 8706 | 0.39815 | 2.7966 | 1.4375 | 1.8571
| 8707 | 0.40741 | 2.678 | 2.0625 | 1.9454
| 8708 | 0.44444 | 2.9831 | 1.125 | 1.7143
| 8709 | 0.36111 | 2.1695 | 0.8125 | 1.8782
| 8710 | 0.55556 | 2.0678 | 2.375 | 2.1933
| 8711 | 0.33333 | 2.8983 | 1.9688 | 2
| 8712 | 0.32407 | 2.9322 | 0.875 | 2.105
| 8713 | 0.48148 | 2.8305 | 1.4375 | 2.0462
| 8714 | 0.40741 | 2.5593 | 0.9375 | 1.9748
| 8715 | 0.38889 | 2.6102 | 1.25 | 1.9202
| 8716 | 0.36111 | 2.6271 | 1.4688 | 2.1303
| 8717 | 0.27778 | 2.3898 | 0.96875 | 2.0798
| 8718 | 0.37037 | 3.1356 | 1.0938 | 2.063
| 8719 | 0.36111 | 2.8475 | 1.2812 | 2
| 8720 | 0.37037 | 3.6271 | 1.5312 | 1.8866
| 8721 | 0.39815 | 2.7797 | 1.5 | 1.916
| 8722 | 0.43519 | 2.6102 | 2.0312 | 2.2269
| 8723 | 0.56481 | 2.7966 | 1.0625 | 2.3782
| 8724 | 0.33333 | 2.7458 | 1.2812 | 1.9832
| 8725 | 0.39815 | 3.1864 | 1.3438 | 1.8824
| 8726 | 0.33333 | 1.661 | 1.1875 | 1.937
| 8727 | 0.52778 | 3.4746 | 1.4688 | 2.0042
| 8728 | 0.38889 | 2.1017 | 1.2188 | 1.9076
| 8729 | 0.43519 | 2.6949 | 1.625 | 1.979
| 8730 | 0.49074 | 2.5085 | 1.875 | 2.2353
| 8731 | 0.33333 | 1.9322 | 0.875 | 2.458
| 8732 | 0.33333 | 3.339 | 1.9375 | 2.5462
| 8733 | 0.36111 | 2.1695 | 1.375 | 2.3319
| 8734 | 0.37963 | 2.6271 | 2.1562 | 2.0336
| 8735 | 0.40741 | 2.2373 | 1.7188 | 1.8361
| 8736 | 0.47222 | 2.1695 | 1.9688 | 1.895
| 8737 | 0.31481 | 2.8475 | 1.3438 | 2.2185
| 8738 | 0.33333 | 3.2373 | 2.3438 | 1.7941
| 8739 | 0.34259 | 2.2373 | 1.7812 | 1.8193
| 8740 | 0.42593 | 2.0508 | 1.125 | 2.1176
| 8741 | 0.46296 | 2.6102 | 1.5625 | 1.9664
| 8742 | 0.52778 | 2.661 | 1.5625 | 2.4286
| 8743 | 0.40741 | 3.1695 | 1.0938 | 2.3319
| 8744 | 0.55556 | 3.1017 | 1.9688 | 2.021
| 8745 | 0.22222 | 3.2712 | 0.90625 | 1.8655
| 8746 | 0.38889 | 3.322 | 1.6875 | 2
| 8747 | 0.36111 | 2.2542 | 0.875 | 2.0588
| 8748 | 0.47222 | 3.2034 | 1.1562 | 2.3487
| 8749 | 0.36111 | 2.4068 | 1.125 | 2.4412
| 8750 | 0.36111 | 3.8814 | 1.375 | 2.0504
| 8751 | 0.44444 | 2.6102 | 1.625 | 2.2647
| 8752 | 0.26852 | 2.8305 | 2.0625 | 2.0882
| 8753 | 0.41667 | 3.8305 | 1.6562 | 1.9832
| 8754 | 0.55556 | 2.8136 | 0.8125 | 2.3739
| 8755 | 0.30556 | 2.3898 | 1.2188 | 2.2521
| 8756 | 0.38889 | 2.5254 | 1.2812 | 2.2395
| 8757 | 0.42593 | 1.9831 | 1.8438 | 2.4412
| 8758 | 0.57407 | 2.339 | 0.96875 | 2.0966
| 8759 | 0.4537 | 2.9831 | 1.7812 | 2.1176
| 8760 | 0.58333 | 2.4576 | 1.4688 | 1.9916
| 8761 | 0.37963 | 3.4237 | 2.0312 | 2.1471
| 8762 | 0.40741 | 3.1186 | 1.375 | 1.8403
| 8763 | 0.38889 | 2.5424 | 0.75 | 1.8655
| 8764 | 0.37037 | 2.5593 | 1.0938 | 2.1387
| 8765 | 0.47222 | 2.1186 | 2.1562 | 2.2605
| 8766 | 0.50926 | 2.7797 | 1.4375 | 2.0168
| 8767 | 0.40741 | 2.4746 | 2.2188 | 2.3235
| 8768 | 0.31481 | 2.3898 | 1 | 1.9706
| 8769 | 0.2963 | 2.7288 | 1.6875 | 1.9664
| 8770 | 0.25 | 2.3559 | 1.9688 | 2.1345
| 8771 | 0.43519 | 3.2712 | 2.2188 | 2.1008
| 8772 | 0.46296 | 3.0847 | 2.0625 | 2.4034
| 8773 | 0.53704 | 2.5424 | 1.3125 | 2.2395
| 8774 | 0.51852 | 2.3898 | 1.5625 | 2.0042
| 8775 | 0.43519 | 2.4915 | 1.4688 | 2.0504
| 8776 | 0.4537 | 3.0508 | 2.0625 | 2.3109
| 8777 | 0.7037 | 2.5085 | 1.625 | 1.9244
| 8778 | 0.4537 | 2.3729 | 2.125 | 1.8277
| 8779 | 0.44444 | 3.1017 | 1.0312 | 1.9706
| 8780 | 0.2963 | 2.8305 | 2.6562 | 2.0462
| 8781 | 0.56481 | 2.4068 | 1.25 | 2.0126
| 8782 | 0.5463 | 2.8814 | 1.5938 | 1.958
| 8783 | 0.34259 | 1.8644 | 1.6875 | 2.1513
| 8784 | 0.43519 | 2.8644 | 1 | 2.1807
| 8785 | 0.43519 | 2.2373 | 0.875 | 1.8655
| 8786 | 0.39815 | 2.5085 | 1.1562 | 2.084
| 8787 | 0.40741 | 2.6102 | 2 | 2.1387
| 8788 | 0.50926 | 3.1525 | 1.3438 | 2.4664
| 8789 | 0.28704 | 2.0847 | 1.1875 | 2.0672
| 8790 | 0.40741 | 2.6271 | 1.5938 | 1.8992
| 8791 | 0.38889 | 2.322 | 1.1875 | 2.2185
| 8792 | 0.40741 | 2.6441 | 1.875 | 1.916
| 8793 | 0.38889 | 2.1356 | 1.7812 | 2.3655
| 8794 | 0.4537 | 2.4746 | 2 | 2.2605
| 8795 | 0.48148 | 2.5593 | 2.125 | 2.4286
| 8796 | 0.31481 | 2.7288 | 1.1875 | 1.979
| 8797 | 0.37037 | 3.0339 | 1.2188 | 2.0294
| 8798 | 0.43519 | 2.3051 | 0.96875 | 2.1471
| 8799 | 0.41667 | 2.0339 | 2.125 | 1.9118
| 8800 | 0.31481 | 2.8305 | 1.7188 | 2.5252
| 8801 | 0.50926 | 3.4068 | 0.625 | 2.0252
| 8802 | 0.38889 | 1.5424 | 2.1562 | 2.7815
| 8803 | 0.40741 | 2.7458 | 1.2188 | 2.2269
| 8804 | 0.36111 | 3.3051 | 1.4688 | 2.1975
| 8805 | 0.4537 | 3.4068 | 1.6875 | 2.4118
| 8806 | 0.40741 | 2.678 | 1.0625 | 1.9916
| 8807 | 0.35185 | 2.7966 | 0.9375 | 1.7311
| 8808 | 0.51852 | 2.4576 | 1.5 | 1.9286
| 8809 | 0.26852 | 3.3729 | 2.0938 | 2.1387
| 8810 | 0.42593 | 2.678 | 1.1562 | 2.063
| 8811 | 0.5 | 2.0678 | 1.25 | 2.2437
| 8812 | 0.24074 | 3.1186 | 1.9688 | 1.9958
| 8813 | 0.57407 | 2.8814 | 1.1875 | 2.5462
| 8814 | 0.61111 | 2.1356 | 1.875 | 2.0336
| 8815 | 0.40741 | 2.9661 | 1.8438 | 2.1933
| 8816 | 0.42593 | 3.3051 | 1.625 | 2.0756
| 8817 | 0.27778 | 2.678 | 0.875 | 2.4832
| 8818 | 0.41667 | 2.3729 | 1.3438 | 1.9118
| 8819 | 0.37037 | 2.6441 | 1.6875 | 2.1681
| 8820 | 0.42593 | 2.678 | 1.9062 | 2.021
| 8821 | 0.37037 | 2.5254 | 2.1562 | 2.1008
| 8822 | 0.49074 | 3.4915 | 1.4688 | 2.1975
| 8823 | 0.46296 | 2.3729 | 0.96875 | 1.8613
| 8824 | 0.50926 | 2.4237 | 1.0625 | 2.042
| 8825 | 0.62963 | 2.8136 | 1.7188 | 2.0252
| 8826 | 0.48148 | 2.8644 | 0.9375 | 1.8571
| 8827 | 0.32407 | 2.9153 | 1.0938 | 1.8866
| 8828 | 0.46296 | 2 | 1.1875 | 1.8151
| 8829 | 0.37037 | 3.2034 | 1.7188 | 2.1218
| 8830 | 0.40741 | 2.0847 | 1.8125 | 2.042
| 8831 | 0.40741 | 2.5085 | 1.3125 | 2.1303
| 8832 | 0.57407 | 2.7458 | 1 | 1.8908
| 8833 | 0.39815 | 3.0339 | 1.4375 | 2.1765
| 8834 | 0.53704 | 3.3559 | 1.4062 | 2.3403
| 8835 | 0.42593 | 2.9661 | 0.875 | 2.1092
| 8836 | 0.47222 | 3.4407 | 1.75 | 2.1891
| 8837 | 0.42593 | 2.8475 | 1.5 | 2.1597
| 8838 | 0.37963 | 2.8644 | 1.6875 | 1.9496
| 8839 | 0.39815 | 3.661 | 1.5938 | 1.8992
| 8840 | 0.4537 | 2.3729 | 1.2812 | 2.5378
| 8841 | 0.33333 | 2.7288 | 1.4688 | 2.0756
| 8842 | 0.49074 | 3.0169 | 0.90625 | 2.0462
| 8843 | 0.36111 | 2.5254 | 1.1562 | 2.2017
| 8844 | 0.50926 | 2.6441 | 1.5625 | 2.2647
| 8845 | 0.49074 | 2.1356 | 1.7188 | 1.9034
| 8846 | 0.43519 | 2.3051 | 1.625 | 2.0588
| 8847 | 0.49074 | 2.6271 | 1.0625 | 2.0966
| 8848 | 0.25926 | 2.8136 | 1.5625 | 2.2311
| 8849 | 0.30556 | 1.6102 | 1.9062 | 1.9412
| 8850 | 0.4537 | 2.322 | 1.5 | 2.1933
| 8851 | 0.43519 | 3.0847 | 1.7188 | 1.8109
| 8852 | 0.31481 | 2.4576 | 1.4375 | 2.1891
| 8853 | 0.43519 | 2.6271 | 2 | 2.3613
| 8854 | 0.37963 | 2.2712 | 2.0625 | 2.0882
| 8855 | 0.30556 | 2.7288 | 2.7812 | 1.9244
| 8856 | 0.37963 | 2.7288 | 1.4375 | 1.7605
| 8857 | 0.33333 | 2.5424 | 1.75 | 2.105
| 8858 | 0.34259 | 2.9322 | 0.46875 | 2.2689
| 8859 | 0.64815 | 2.2881 | 0.90625 | 1.9202
| 8860 | 0.37037 | 2.2203 | 2.0312 | 2.0462
| 8861 | 0.35185 | 2.8305 | 1.9062 | 2.2521
| 8862 | 0.44444 | 3.0169 | 0.75 | 2.1471
| 8863 | 0.31481 | 2.9492 | 1.7812 | 1.8529
| 8864 | 0.42593 | 2.3898 | 0.9375 | 2.1176
| 8865 | 0.42593 | 3.1186 | 1.0625 | 1.8445
| 8866 | 0.65741 | 2.4068 | 1.5625 | 1.8866
| 8867 | 0.57407 | 2.5085 | 1.9688 | 2.2017
| 8868 | 0.37037 | 2.5932 | 1.4062 | 1.9874
| 8869 | 0.33333 | 3.0169 | 0.9375 | 1.9328
| 8870 | 0.50926 | 2.5085 | 0.875 | 2.2185
| 8871 | 0.5 | 4.4746 | 1.5312 | 2.1723
| 8872 | 0.32407 | 3.1017 | 1.25 | 2.3319
| 8873 | 0.39815 | 2.1017 | 1.125 | 2.063
| 8874 | 0.36111 | 2.9831 | 1.6562 | 2.084
| 8875 | 0.49074 | 2.7627 | 1.4688 | 2.2143
| 8876 | 0.44444 | 3.1864 | 1.5625 | 2.2437
| 8877 | 0.33333 | 2.4915 | 1 | 2.2941
| 8878 | 0.38889 | 2.9661 | 1.6875 | 2.0966
| 8879 | 0.60185 | 2.7458 | 2.0625 | 2.0462
| 8880 | 0.5463 | 3.4237 | 1.0312 | 1.979
| 8881 | 0.42593 | 3.322 | 0.875 | 2.5126
| 8882 | 0.44444 | 2.6949 | 1.3438 | 2.2731
| 8883 | 0.48148 | 2.7797 | 2.1562 | 1.9748
| 8884 | 0.34259 | 2.9661 | 1.7188 | 2.1597
| 8885 | 0.41667 | 2.661 | 0.9375 | 1.8361
| 8886 | 0.46296 | 2.2712 | 0.84375 | 2.2311
| 8887 | 0.5 | 3.5593 | 1.125 | 2.1218
| 8888 | 0.42593 | 3.2542 | 1.5 | 2.0924
| 8889 | 0.37037 | 2.5763 | 0.9375 | 2.1765
| 8890 | 0.34259 | 2.2203 | 1 | 2.2731
| 8891 | 0.41667 | 2.4915 | 1.1875 | 2
| 8892 | 0.44444 | 2.9661 | 1.2812 | 1.6849
| 8893 | 0.36111 | 2.1525 | 1.9062 | 2.0882
| 8894 | 0.37037 | 3.4068 | 1.375 | 2.4076
| 8895 | 0.2963 | 2.3051 | 1.5 | 2.084
| 8896 | 0.39815 | 2 | 1.5938 | 2.3613
| 8897 | 0.37963 | 2.5254 | 1.2188 | 2.1891
| 8898 | 0.37037 | 2.6441 | 1.4062 | 1.9496
| 8899 | 0.43519 | 2.6271 | 1.125 | 2.4118
| 8900 | 0.36111 | 3 | 2.625 | 2.042
| 8901 | 0.5463 | 3.1525 | 1.8125 | 2.3193
| 8902 | 0.42593 | 2.2373 | 1.25 | 1.8782
| 8903 | 0.40741 | 2.7458 | 1.4688 | 2.0042
| 8904 | 0.37037 | 3.3898 | 1.1562 | 2.1261
| 8905 | 0.36111 | 2.661 | 1.4375 | 2.2227
| 8906 | 0.43519 | 2.8983 | 1.4688 | 2.3824
| 8907 | 0.48148 | 2.0339 | 1.5 | 2.2185
| 8908 | 0.51852 | 3.5254 | 0.84375 | 2.0882
| 8909 | 0.48148 | 2.8305 | 1 | 2.3782
| 8910 | 0.39815 | 3.339 | 1.9062 | 2.1092
| 8911 | 0.41667 | 3.3051 | 1.3438 | 1.8571
| 8912 | 0.35185 | 2.7288 | 2.375 | 1.6303
| 8913 | 0.46296 | 2.7797 | 1.6875 | 2.0126
| 8914 | 0.36111 | 2.3729 | 1.6562 | 1.8571
| 8915 | 0.5 | 3.5085 | 1.6875 | 2.1849
| 8916 | 0.39815 | 3.0339 | 1.4062 | 2.2647
| 8917 | 0.46296 | 2.3559 | 0.84375 | 2.1597
| 8918 | 0.35185 | 2.7966 | 0.90625 | 2.0798
| 8919 | 0.46296 | 2.8305 | 0.65625 | 2.1597
| 8920 | 0.35185 | 2.7966 | 1.4375 | 2.458
| 8921 | 0.50926 | 2.4407 | 1.1875 | 1.8319
| 8922 | 0.56481 | 2.6102 | 0.875 | 2.084
| 8923 | 0.46296 | 3.6102 | 1.375 | 2.1723
| 8924 | 0.5 | 2.4068 | 1.4062 | 2.0672
| 8925 | 0.57407 | 2.1864 | 1.7188 | 2.1345
| 8926 | 0.38889 | 2.2542 | 0.9375 | 1.8277
| 8927 | 0.30556 | 2.4915 | 1.3125 | 2.0546
| 8928 | 0.36111 | 1.8136 | 0.40625 | 1.9664
| 8929 | 0.33333 | 2.8305 | 1.5938 | 1.7479
| 8930 | 0.46296 | 2.4746 | 1.125 | 2.0042
| 8931 | 0.4537 | 2.3051 | 1.5625 | 2.2731
| 8932 | 0.47222 | 3.1186 | 1.6875 | 2.2395
| 8933 | 0.37037 | 2.2034 | 1.3438 | 2.1513
| 8934 | 0.37037 | 2.2881 | 1.7188 | 2.1218
| 8935 | 0.25926 | 1.5763 | 1.0625 | 1.9454
| 8936 | 0.47222 | 2.5932 | 1.5 | 2.1765
| 8937 | 0.39815 | 2.5424 | 1.7812 | 2.1471
| 8938 | 0.27778 | 3.0339 | 0.75 | 1.8992
| 8939 | 0.43519 | 3.0508 | 1.625 | 1.9034
| 8940 | 0.35185 | 2.5932 | 1.3438 | 2.1345
| 8941 | 0.48148 | 2.3898 | 0.90625 | 2.0924
| 8942 | 0.39815 | 2.4407 | 0.96875 | 2.0756
| 8943 | 0.64815 | 2.9492 | 2.25 | 2.0966
| 8944 | 0.46296 | 2.7797 | 1.4688 | 1.7605
| 8945 | 0.27778 | 2.8136 | 1.9375 | 2.3487
| 8946 | 0.5463 | 3.1356 | 1.4375 | 2.1387
| 8947 | 0.4537 | 2.9153 | 1.6562 | 1.8445
| 8948 | 0.44444 | 2.5593 | 1.3125 | 2.0588
| 8949 | 0.32407 | 2.2034 | 1.4688 | 1.8361
| 8950 | 0.47222 | 3.6271 | 1.2188 | 1.979
| 8951 | 0.2963 | 2.339 | 0.96875 | 2.1807
| 8952 | 0.34259 | 2.7966 | 2.25 | 2.042
| 8953 | 0.34259 | 2.6102 | 1.7188 | 2.4622
| 8954 | 0.34259 | 2.8644 | 1.375 | 1.9874
| 8955 | 0.35185 | 2.5424 | 0.9375 | 2.1303
| 8956 | 0.47222 | 3.4746 | 0.59375 | 2.0252
| 8957 | 0.43519 | 2.2542 | 1.7812 | 2.063
| 8958 | 0.38889 | 2.3898 | 1.5938 | 2.2899
| 8959 | 0.40741 | 1.8983 | 1.0312 | 1.9664
| 8960 | 0.37037 | 3.0678 | 1.6562 | 2.3067
| 8961 | 0.30556 | 3.1017 | 2.1562 | 2.0924
| 8962 | 0.35185 | 2.7627 | 1.5 | 2.2017
| 8963 | 0.37963 | 3 | 0.78125 | 2.2101
| 8964 | 0.55556 | 1.8983 | 0.90625 | 2.0504
| 8965 | 0.49074 | 2.7966 | 0.96875 | 2.0798
| 8966 | 0.44444 | 2.2034 | 1.7188 | 2.3277
| 8967 | 0.53704 | 2.7966 | 1.0625 | 1.8277
| 8968 | 0.4537 | 2.5763 | 1.9375 | 2.3655
| 8969 | 0.30556 | 2.4068 | 1.5625 | 1.8319
| 8970 | 0.31481 | 2.5254 | 1.5312 | 1.8613
| 8971 | 0.39815 | 2.2034 | 0.46875 | 1.937
| 8972 | 0.32407 | 3.2034 | 0.84375 | 2.2395
| 8973 | 0.5 | 2.9153 | 0.96875 | 1.9286
| 8974 | 0.34259 | 3.9831 | 1.375 | 2.2647
| 8975 | 0.2963 | 2.5424 | 1.3438 | 2.1891
| 8976 | 0.52778 | 2.3051 | 1.1562 | 1.916
| 8977 | 0.31481 | 3.7458 | 1.1562 | 2.0126
| 8978 | 0.43519 | 3.1525 | 0.9375 | 2.3655
| 8979 | 0.44444 | 2.2034 | 0.875 | 1.8992
| 8980 | 0.36111 | 2.2542 | 1.7812 | 2.2227
| 8981 | 0.34259 | 2.4746 | 1.0938 | 2.0378
| 8982 | 0.33333 | 1.8475 | 1.4688 | 2.0714
| 8983 | 0.31481 | 2.8814 | 1.875 | 2.3109
| 8984 | 0.28704 | 2.4746 | 1.0938 | 1.7647
| 8985 | 0.39815 | 2.5763 | 1.1875 | 2.042
| 8986 | 0.33333 | 2.9661 | 1.7188 | 1.9118
| 8987 | 0.32407 | 2.8475 | 1.5625 | 2.7101
| 8988 | 0.34259 | 2.5593 | 1.0625 | 2.2605
| 8989 | 0.42593 | 2.6102 | 2.0312 | 2.0126
| 8990 | 0.47222 | 3.0169 | 1.3125 | 2.0756
| 8991 | 0.35185 | 2.6949 | 2.5 | 2.1555
| 8992 | 0.47222 | 2.1864 | 1.6875 | 1.9034
| 8993 | 0.37963 | 2.8814 | 0.9375 | 1.7563
| 8994 | 0.44444 | 2.7288 | 0.8125 | 2.1134
| 8995 | 0.47222 | 2.8305 | 1.25 | 2.1134
| 8996 | 0.35185 | 2.9831 | 1.25 | 1.937
| 8997 | 0.5463 | 3.8136 | 2.1562 | 2.3109
| 8998 | 0.40741 | 2.4746 | 1.625 | 2.1597
| 8999 | 0.30556 | 2.9661 | 0.65625 | 2.3824
| 9000 | 0.5 | 2.5593 | 1.3125 | 1.8613
| 9001 | 0.44444 | 3 | 1.1562 | 2.1681
| 9002 | 0.4537 | 2.6271 | 1.3438 | 2.0336
| 9003 | 0.43519 | 2.8475 | 1.6562 | 1.9622
| 9004 | 0.37037 | 2.9322 | 2.0625 | 2.1387
| 9005 | 0.46296 | 2.678 | 1.9688 | 2.0798
| 9006 | 0.48148 | 2.9153 | 1.125 | 2.2395
| 9007 | 0.46296 | 2.7458 | 1.4375 | 2.1345
| 9008 | 0.47222 | 2.661 | 2.0938 | 1.8319
| 9009 | 0.25 | 2.4915 | 1.3438 | 2.0672
| 9010 | 0.41667 | 2.3729 | 1.5 | 2.1429
| 9011 | 0.31481 | 3.2373 | 1.4375 | 1.8361
| 9012 | 0.37037 | 2.9153 | 1.2188 | 2.479
| 9013 | 0.48148 | 3.0169 | 0.875 | 2.1303
| 9014 | 0.38889 | 2.7119 | 1.1875 | 2.0588
| 9015 | 0.47222 | 2.2203 | 1.4375 | 2.2353
| 9016 | 0.46296 | 3.7458 | 1 | 2.2731
| 9017 | 0.62037 | 2.678 | 1.7188 | 2.3782
| 9018 | 0.38889 | 2.322 | 1.5312 | 1.9118
| 9019 | 0.40741 | 2.4407 | 1.75 | 1.916
| 9020 | 0.26852 | 3.1864 | 1.25 | 2.1345
| 9021 | 0.40741 | 2.8983 | 1.125 | 2.1555
| 9022 | 0.26852 | 3.4068 | 1.2188 | 2.5084
| 9023 | 0.50926 | 2.9661 | 1.4688 | 2.3025
| 9024 | 0.46296 | 3.4746 | 1.625 | 2.0504
| 9025 | 0.43519 | 3.1356 | 1.2188 | 2.3908
| 9026 | 0.37037 | 3.322 | 1.9375 | 2.0462
| 9027 | 0.49074 | 2.339 | 1.875 | 2.1261
| 9028 | 0.4537 | 2.0847 | 0.6875 | 1.937
| 9029 | 0.4537 | 2.8644 | 0.96875 | 2
| 9030 | 0.39815 | 2.4576 | 1.2812 | 2.1975
| 9031 | 0.43519 | 2.8983 | 1.8125 | 2.084
| 9032 | 0.44444 | 2.0678 | 0.65625 | 2.0756
| 9033 | 0.50926 | 3.0678 | 0.78125 | 2.2059
| 9034 | 0.57407 | 2.5593 | 0.59375 | 1.8361
| 9035 | 0.40741 | 3.0678 | 1 | 1.9706
| 9036 | 0.4537 | 3.3559 | 1.125 | 1.9622
| 9037 | 0.28704 | 3.2203 | 1.25 | 1.9118
| 9038 | 0.36111 | 2.2034 | 1 | 2.1471
| 9039 | 0.34259 | 2.3898 | 1.5312 | 2.2227
| 9040 | 0.36111 | 3.2373 | 1.3125 | 2.2689
| 9041 | 0.38889 | 2.2203 | 1.4688 | 2.1092
| 9042 | 0.35185 | 2.4576 | 1.1875 | 1.8361
| 9043 | 0.41667 | 3 | 1.4062 | 2.0546
| 9044 | 0.4537 | 3.6102 | 1.8125 | 2.2353
| 9045 | 0.33333 | 2.3729 | 2.0312 | 2.4034
| 9046 | 0.42593 | 3.0508 | 1.2812 | 1.9118
| 9047 | 0.38889 | 3.4237 | 1.9062 | 2.2563
| 9048 | 0.30556 | 2.9492 | 1.2188 | 1.7605
| 9049 | 0.2963 | 2.7288 | 1.7188 | 2.1008
| 9050 | 0.35185 | 3.5254 | 1.375 | 1.8908
| 9051 | 0.46296 | 2.8305 | 1.4062 | 2.2521
| 9052 | 0.41667 | 2.2542 | 1.75 | 1.9538
| 9053 | 0.36111 | 2.8475 | 1.8438 | 2.0378
| 9054 | 0.42593 | 2.7966 | 0.9375 | 2.1303
| 9055 | 0.4537 | 2.339 | 1.5625 | 2.0966
| 9056 | 0.2037 | 1.8814 | 1.5 | 1.9538
| 9057 | 0.38889 | 2.6949 | 1.7188 | 2.2773
| 9058 | 0.41667 | 2.339 | 1 | 2.1891
| 9059 | 0.35185 | 2.9153 | 1.5625 | 1.958
| 9060 | 0.28704 | 2.5254 | 1.5 | 1.8571
| 9061 | 0.38889 | 3.1525 | 1.5312 | 2.1092
| 9062 | 0.38889 | 2.8983 | 1.625 | 1.979
| 9063 | 0.37037 | 2.0678 | 1.1875 | 1.937
| 9064 | 0.5 | 2.5593 | 1.2188 | 2.1555
| 9065 | 0.42593 | 2.3051 | 1.0312 | 2.4916
| 9066 | 0.37963 | 2.8136 | 1.2812 | 2.2479
| 9067 | 0.39815 | 2.5932 | 1.3438 | 2.042
| 9068 | 0.4537 | 2.339 | 0.78125 | 2.2521
| 9069 | 0.36111 | 3.8983 | 1.9688 | 2.0714
| 9070 | 0.28704 | 2.1017 | 1.0938 | 1.8487
| 9071 | 0.5463 | 2.1017 | 1.1875 | 2.0714
| 9072 | 0.31481 | 2.7627 | 1.2188 | 2.3025
| 9073 | 0.57407 | 2.8983 | 1.5 | 2.2437
| 9074 | 0.39815 | 2.1186 | 0.78125 | 2.0294
| 9075 | 0.62037 | 3.0678 | 1.875 | 1.7815
| 9076 | 0.48148 | 3.2203 | 1.1875 | 2.2395
| 9077 | 0.41667 | 2.8814 | 1.8438 | 2.6218
| 9078 | 0.5 | 2.8136 | 1.5938 | 1.9328
| 9079 | 0.38889 | 2.4746 | 1.1562 | 2.3739
| 9080 | 0.37963 | 2.6441 | 2.7188 | 2.0798
| 9081 | 0.56481 | 2.2712 | 1.625 | 1.7899
| 9082 | 0.30556 | 2.4237 | 1.5625 | 1.7437
| 9083 | 0.48148 | 3.339 | 1.3125 | 2.3319
| 9084 | 0.30556 | 3 | 1.4062 | 2.063
| 9085 | 0.47222 | 2.5424 | 0.9375 | 2.0252
| 9086 | 0.61111 | 2.1017 | 0.8125 | 2.2479
| 9087 | 0.25926 | 2.3898 | 2.25 | 2.2605
| 9088 | 0.39815 | 2.4068 | 1.625 | 2.0504
| 9089 | 0.31481 | 2.8983 | 1.6562 | 2.521
| 9090 | 0.34259 | 2.5424 | 1.1562 | 2.0126
| 9091 | 0.37963 | 2.5593 | 1.2188 | 2.1765
| 9092 | 0.30556 | 2.1017 | 1.9375 | 2.021
| 9093 | 0.5 | 2.4068 | 1.2188 | 2.0798
| 9094 | 0.40741 | 2.3559 | 1.4375 | 2.4286
| 9095 | 0.35185 | 3.0678 | 0.90625 | 2.3571
| 9096 | 0.41667 | 2.4576 | 1.25 | 2.1218
| 9097 | 0.5 | 2.8136 | 0.78125 | 2.1681
| 9098 | 0.38889 | 2.9492 | 2.1562 | 1.9412
| 9099 | 0.37963 | 2 | 2.0312 | 1.9958
| 9100 | 0.39815 | 2.6271 | 1.7188 | 1.8866
| 9101 | 0.51852 | 2.6949 | 0.9375 | 2.1849
| 9102 | 0.40741 | 2.9153 | 1.1875 | 2.0462
| 9103 | 0.49074 | 3.3051 | 1.8438 | 1.895
| 9104 | 0.49074 | 2.6441 | 0.625 | 2.1218
| 9105 | 0.37963 | 2.9153 | 1.125 | 1.8739
| 9106 | 0.34259 | 1.8475 | 1.6562 | 1.9202
| 9107 | 0.35185 | 2.661 | 1.5312 | 2.1387
| 9108 | 0.47222 | 2.8814 | 1.0938 | 2.0798
| 9109 | 0.42593 | 2.5424 | 1.625 | 2.2185
| 9110 | 0.42593 | 2.2881 | 1.0938 | 2.042
| 9111 | 0.31481 | 2.0847 | 1.1562 | 2.0462
| 9112 | 0.2963 | 2.7119 | 1.0625 | 2.1303
| 9113 | 0.38889 | 2.4407 | 1.9375 | 2.1639
| 9114 | 0.37037 | 2.7458 | 1.2188 | 2.0126
| 9115 | 0.33333 | 2.4068 | 1.3438 | 1.9958
| 9116 | 0.40741 | 3.2881 | 1.25 | 2.5378
| 9117 | 0.33333 | 2.6441 | 1.4688 | 1.9454
| 9118 | 0.30556 | 2.6271 | 1.2812 | 2.105
| 9119 | 0.39815 | 2.7797 | 1.3438 | 2.3193
| 9120 | 0.37037 | 3.339 | 0.8125 | 1.8824
| 9121 | 0.34259 | 3.4407 | 1.0938 | 1.7983
| 9122 | 0.36111 | 2.2542 | 0.78125 | 2.0756
| 9123 | 0.41667 | 2.2203 | 1.1562 | 2.4832
| 9124 | 0.58333 | 3.5763 | 0.625 | 2.2941
| 9125 | 0.19444 | 3.0847 | 1.4375 | 2.1008
| 9126 | 0.40741 | 2.6271 | 1.2812 | 2.7899
| 9127 | 0.30556 | 2.4237 | 1.8125 | 2.0966
| 9128 | 0.58333 | 2.3898 | 1.3438 | 2.4622
| 9129 | 0.37037 | 2.6271 | 1.5 | 2.0084
| 9130 | 0.56481 | 3.1356 | 1.9375 | 2.3151
| 9131 | 0.5463 | 2.7627 | 1.2812 | 1.7647
| 9132 | 0.27778 | 3.5763 | 1.4375 | 2.1429
| 9133 | 0.25926 | 2.9831 | 1.0312 | 1.916
| 9134 | 0.49074 | 2.9661 | 1.9062 | 2.0126
| 9135 | 0.39815 | 2.5424 | 0.6875 | 1.9832
| 9136 | 0.34259 | 2.5593 | 1.125 | 1.8655
| 9137 | 0.34259 | 3.4068 | 1.875 | 2.3235
| 9138 | 0.37037 | 2.678 | 1.0938 | 1.9958
| 9139 | 0.2963 | 2.4576 | 0.875 | 2.458
| 9140 | 0.68519 | 2.4746 | 1.5 | 1.895
| 9141 | 0.39815 | 3.7458 | 0.90625 | 2.0462
| 9142 | 0.33333 | 2.4915 | 0.875 | 2.1218
| 9143 | 0.58333 | 2.3898 | 1.75 | 2.2941
| 9144 | 0.5 | 2.5763 | 1.2188 | 2.0084
| 9145 | 0.46296 | 2.4407 | 1.875 | 2
| 9146 | 0.48148 | 3.4915 | 0.78125 | 2.0504
| 9147 | 0.56481 | 2.8475 | 0.6875 | 2.1176
| 9148 | 0.5 | 3.2034 | 1.25 | 2.3193
| 9149 | 0.46296 | 2.7797 | 1.1875 | 2
| 9150 | 0.40741 | 3.0678 | 1.5312 | 2.105
| 9151 | 0.34259 | 2.5593 | 2.25 | 2.1303
| 9152 | 0.46296 | 2.8814 | 1.4375 | 2.0126
| 9153 | 0.32407 | 2.661 | 1.125 | 2.3824
| 9154 | 0.5 | 2.4746 | 1.8438 | 2.1218
| 9155 | 0.41667 | 2.9661 | 1.625 | 1.8824
| 9156 | 0.36111 | 2.5254 | 1.2812 | 2.0504
| 9157 | 0.39815 | 2.4237 | 2.4688 | 2.1597
| 9158 | 0.50926 | 2.9661 | 1.1562 | 2.0966
| 9159 | 0.40741 | 2.3051 | 1.5625 | 2.0084
| 9160 | 0.2963 | 3.1017 | 1.625 | 2.0672
| 9161 | 0.42593 | 2.6441 | 0.9375 | 1.8866
| 9162 | 0.58333 | 2.4068 | 2.0625 | 2.2437
| 9163 | 0.34259 | 2.3051 | 1.9062 | 1.916
| 9164 | 0.36111 | 2.6949 | 1.3125 | 1.9664
| 9165 | 0.26852 | 3.3898 | 1.3125 | 2.0924
| 9166 | 0.36111 | 3.2034 | 0.8125 | 2.3025
| 9167 | 0.44444 | 2.9492 | 1.0312 | 2.042
| 9168 | 0.43519 | 2.4576 | 0.9375 | 2.2269
| 9169 | 0.43519 | 3.0169 | 1.6875 | 2.2353
| 9170 | 0.37037 | 2.9153 | 2 | 1.7395
| 9171 | 0.44444 | 3.3729 | 0.9375 | 2.4034
| 9172 | 0.27778 | 2.8983 | 1.9062 | 1.8782
| 9173 | 0.4537 | 2.6949 | 1.5 | 1.9748
| 9174 | 0.36111 | 2.7966 | 1.4688 | 2.3739
| 9175 | 0.48148 | 3.1864 | 1.7188 | 1.8613
| 9176 | 0.31481 | 2.5593 | 1.875 | 2.0924
| 9177 | 0.38889 | 3.1695 | 1.1875 | 2.1765
| 9178 | 0.41667 | 3.1695 | 1.1562 | 1.9874
| 9179 | 0.30556 | 2.5254 | 1.4062 | 2.2185
| 9180 | 0.31481 | 2.7119 | 1.3125 | 2.6555
| 9181 | 0.42593 | 2.339 | 0.90625 | 2.1639
| 9182 | 0.4537 | 2.661 | 1.4688 | 1.9874
| 9183 | 0.36111 | 2.8136 | 1.0625 | 2.1765
| 9184 | 0.39815 | 3.5932 | 1.0625 | 2.2143
| 9185 | 0.33333 | 2.5424 | 2.0938 | 2.0504
| 9186 | 0.33333 | 1.7966 | 1.7188 | 1.8739
| 9187 | 0.38889 | 2.5593 | 2 | 2.042
| 9188 | 0.43519 | 2.9831 | 1.2812 | 1.8025
| 9189 | 0.48148 | 2.8136 | 1.875 | 2.5
| 9190 | 0.37037 | 2.2542 | 1.1875 | 1.8277
| 9191 | 0.38889 | 3.1525 | 1.0625 | 2.3277
| 9192 | 0.34259 | 2.4237 | 0.9375 | 1.9916
| 9193 | 0.49074 | 2.5085 | 1.5 | 1.958
| 9194 | 0.32407 | 2.8475 | 1 | 2.1723
| 9195 | 0.25 | 2.5593 | 0.9375 | 2.4202
| 9196 | 0.48148 | 2.4915 | 1.7188 | 1.8908
| 9197 | 0.53704 | 2.4746 | 1.0312 | 2.2479
| 9198 | 0.46296 | 3.1017 | 1.3438 | 2.3235
| 9199 | 0.39815 | 2.5763 | 1.1875 | 1.8908
| 9200 | 0.55556 | 3.1864 | 1.125 | 2.4076
| 9201 | 0.46296 | 3.4068 | 0.9375 | 2.0546
| 9202 | 0.44444 | 2.7288 | 1.375 | 1.8697
| 9203 | 0.36111 | 2.5932 | 1.0625 | 2.2059
| 9204 | 0.39815 | 3.2034 | 1.0625 | 2.5336
| 9205 | 0.32407 | 3.0169 | 1.4375 | 1.8025
| 9206 | 0.38889 | 2.2712 | 1.5938 | 2.3445
| 9207 | 0.42593 | 2.3729 | 0.8125 | 1.7689
| 9208 | 0.36111 | 2.9661 | 2.0625 | 2.1933
| 9209 | 0.34259 | 3.1525 | 1.1875 | 1.9454
| 9210 | 0.42593 | 2.9492 | 1.3125 | 2.3109
| 9211 | 0.5 | 2.678 | 1.8125 | 2.3193
| 9212 | 0.42593 | 2.4746 | 1.3438 | 2.1849
| 9213 | 0.2963 | 2.2712 | 1.25 | 2.3067
| 9214 | 0.37963 | 2.339 | 1.9688 | 2.084
| 9215 | 0.55556 | 2.5254 | 1.5 | 1.9076
| 9216 | 0.22222 | 2.5424 | 0.96875 | 2.1807
| 9217 | 0.33333 | 3.339 | 1.6562 | 1.7983
| 9218 | 0.37963 | 3.0169 | 1.5625 | 1.916
| 9219 | 0.37037 | 1.6102 | 1.875 | 2.3655
| 9220 | 0.31481 | 2.8983 | 1.5625 | 2.1471
| 9221 | 0.37037 | 2.6949 | 0.8125 | 2.2395
| 9222 | 0.30556 | 2.3051 | 1.5312 | 2.1387
| 9223 | 0.49074 | 2.8305 | 1.5 | 2.1218
| 9224 | 0.37037 | 3.0847 | 1.1875 | 1.9118
| 9225 | 0.37963 | 2.5593 | 1.0938 | 1.9286
| 9226 | 0.37037 | 1.8814 | 0.9375 | 2.1471
| 9227 | 0.35185 | 2.5254 | 1.1562 | 1.979
| 9228 | 0.42593 | 2.2203 | 1.8438 | 2.2143
| 9229 | 0.33333 | 3.1864 | 1.4688 | 1.9412
| 9230 | 0.36111 | 3.2542 | 1.4375 | 1.9286
| 9231 | 0.37037 | 2.5763 | 1.6875 | 2.0378
| 9232 | 0.32407 | 2.5085 | 1.8125 | 2.0924
| 9233 | 0.42593 | 3.8305 | 1.3438 | 2.2899
| 9234 | 0.5 | 2.8644 | 1.3438 | 2.2857
| 9235 | 0.4537 | 2.5593 | 0.96875 | 1.9412
| 9236 | 0.39815 | 2.6271 | 2 | 2.0462
| 9237 | 0.37037 | 2.7797 | 1.625 | 1.9874
| 9238 | 0.33333 | 2.5254 | 1.75 | 2.1387
| 9239 | 0.43519 | 3.0169 | 1.2188 | 2.2941
| 9240 | 0.47222 | 2.2542 | 1.6562 | 2.0462
| 9241 | 0.25926 | 3.3898 | 1.5312 | 2.1176
| 9242 | 0.26852 | 2.0678 | 1.0625 | 2.2311
| 9243 | 0.26852 | 2.5763 | 0.84375 | 1.7521
| 9244 | 0.47222 | 2.8814 | 2 | 2.0378
| 9245 | 0.49074 | 2.1356 | 2.0625 | 2.1092
| 9246 | 0.55556 | 3.5593 | 2.25 | 2.0966
| 9247 | 0.37037 | 2.5254 | 0.90625 | 2.2773
| 9248 | 0.42593 | 2.678 | 1.5938 | 2.2395
| 9249 | 0.38889 | 2.9831 | 1.1875 | 2.0672
| 9250 | 0.63889 | 2.2203 | 0.6875 | 2.1513
| 9251 | 0.38889 | 2.2542 | 1.0312 | 2.4076
| 9252 | 0.38889 | 2.7797 | 1.4062 | 2.4748
| 9253 | 0.43519 | 2.1356 | 1.375 | 2.0504
| 9254 | 0.53704 | 2.3898 | 1.4688 | 2.3067
| 9255 | 0.37963 | 2.322 | 2.1562 | 2.0378
| 9256 | 0.31481 | 2.5424 | 0.8125 | 2.2311
| 9257 | 0.48148 | 3.0508 | 1 | 2.0546
| 9258 | 0.36111 | 2.9492 | 0.875 | 2.437
| 9259 | 0.35185 | 2.1525 | 1.1875 | 2.084
| 9260 | 0.43519 | 3.4576 | 1.25 | 2.0756
| 9261 | 0.58333 | 2.5424 | 0.6875 | 2.084
| 9262 | 0.39815 | 3.1017 | 2.125 | 1.8529
| 9263 | 0.51852 | 2.0508 | 1.375 | 1.8025
| 9264 | 0.31481 | 2.5424 | 0.90625 | 1.8613
| 9265 | 0.39815 | 3.2373 | 1.2812 | 1.9496
| 9266 | 0.42593 | 2.678 | 1.8125 | 2.1639
| 9267 | 0.5 | 2.9492 | 0.8125 | 2.042
| 9268 | 0.49074 | 2.7627 | 1.6562 | 1.916
| 9269 | 0.53704 | 2.1017 | 1.625 | 2.3067
| 9270 | 0.34259 | 3.0339 | 1.0625 | 2.1849
| 9271 | 0.32407 | 2.9492 | 1.1875 | 2.1513
| 9272 | 0.32407 | 3.2034 | 1.6562 | 1.8277
| 9273 | 0.5 | 3.3559 | 1.1562 | 2.0672
| 9274 | 0.51852 | 2.322 | 1.625 | 1.9244
| 9275 | 0.27778 | 2.8644 | 1.1875 | 2.0378
| 9276 | 0.52778 | 2.2203 | 2.125 | 1.937
| 9277 | 0.47222 | 2.661 | 1 | 1.8697
| 9278 | 0.50926 | 3.1356 | 0.9375 | 2.2647
| 9279 | 0.2963 | 2.7966 | 1.25 | 1.8824
| 9280 | 0.41667 | 2.9322 | 1.375 | 2.2563
| 9281 | 0.35185 | 2.2712 | 1.1562 | 2.3571
| 9282 | 0.37037 | 2.1525 | 1.1875 | 1.9748
| 9283 | 0.41667 | 2.2542 | 0.96875 | 2.1681
| 9284 | 0.40741 | 2.3729 | 1.5 | 2.0252
| 9285 | 0.26852 | 2.6102 | 1.4375 | 2.063
| 9286 | 0.55556 | 2.4915 | 1.5 | 2.1597
| 9287 | 0.48148 | 3.0678 | 1.0938 | 2.0714
| 9288 | 0.25 | 2.5424 | 1.9062 | 1.9874
| 9289 | 0.40741 | 3.0678 | 0.71875 | 2.0462
| 9290 | 0.39815 | 2.4576 | 1.1562 | 2
| 9291 | 0.2963 | 2.5085 | 1.125 | 2.3655
| 9292 | 0.46296 | 3.3051 | 1.75 | 1.8782
| 9293 | 0.49074 | 2.1525 | 1.75 | 2.2101
| 9294 | 0.32407 | 2.5593 | 1.625 | 2.1681
| 9295 | 0.46296 | 2.9153 | 1.0312 | 2.1471
| 9296 | 0.5 | 3.0169 | 1.2188 | 1.979
| 9297 | 0.40741 | 2.6102 | 1.5 | 2.2143
| 9298 | 0.43519 | 2.678 | 1.8125 | 2.0924
| 9299 | 0.4537 | 2.3729 | 1.9688 | 2.0504
| 9300 | 0.4537 | 2.4746 | 1.75 | 1.6387
| 9301 | 0.46296 | 3.4068 | 1.3438 | 1.9454
| 9302 | 0.4537 | 3.7288 | 1.3125 | 1.895
| 9303 | 0.42593 | 2.661 | 1.9375 | 2.0672
| 9304 | 0.37037 | 3.5254 | 1.9375 | 1.6765
| 9305 | 0.51852 | 2.2542 | 0.65625 | 2.2185
| 9306 | 0.40741 | 2.2373 | 1.125 | 1.916
| 9307 | 0.37037 | 2.3898 | 1.3438 | 2.1933
| 9308 | 0.44444 | 2.8305 | 1.6562 | 1.8025
| 9309 | 0.5 | 2.3559 | 1.9688 | 2.0588
| 9310 | 0.39815 | 2.6949 | 1.5938 | 1.8992
| 9311 | 0.25 | 2.1695 | 2.1562 | 2.1134
| 9312 | 0.43519 | 2.9322 | 1.2812 | 2.437
| 9313 | 0.46296 | 2.7797 | 1.4062 | 1.8992
| 9314 | 0.2963 | 2.5254 | 1.6562 | 2.542
| 9315 | 0.39815 | 2.4068 | 1.1875 | 2.1387
| 9316 | 0.42593 | 3.2712 | 1.2188 | 2.1429
| 9317 | 0.42593 | 3.2034 | 1.25 | 2.2941
| 9318 | 0.38889 | 2.7119 | 1.8438 | 2.0588
| 9319 | 0.46296 | 2.2881 | 1.25 | 1.8277
| 9320 | 0.36111 | 2.4576 | 1.2812 | 1.9454
| 9321 | 0.36111 | 3.5763 | 1.625 | 2.1387
| 9322 | 0.2963 | 2.4576 | 1.375 | 1.8739
| 9323 | 0.41667 | 3.339 | 1.8125 | 2.0672
| 9324 | 0.37963 | 2.1186 | 1.875 | 2.4916
| 9325 | 0.40741 | 3.4746 | 1.0312 | 2.1176
| 9326 | 0.34259 | 2.2373 | 1.1562 | 2.0882
| 9327 | 0.50926 | 2.5424 | 1.3438 | 2.0168
| 9328 | 0.31481 | 2.3559 | 1.1562 | 1.9832
| 9329 | 0.46296 | 2.6949 | 1.125 | 1.916
| 9330 | 0.5463 | 2.4746 | 1.4062 | 2.0168
| 9331 | 0.49074 | 2.2203 | 0.71875 | 1.8067
| 9332 | 0.4537 | 2.7966 | 0.78125 | 2.0588
| 9333 | 0.40741 | 2.7458 | 1.6562 | 1.9832
| 9334 | 0.32407 | 3.4237 | 1.625 | 1.9244
| 9335 | 0.49074 | 2.5932 | 0.90625 | 2.0378
| 9336 | 0.58333 | 3.2034 | 1.7188 | 2.395
| 9337 | 0.44444 | 1.9492 | 1.6562 | 2.1176
| 9338 | 0.39815 | 2.5763 | 0.875 | 1.9118
| 9339 | 0.50926 | 3.6949 | 2.0312 | 1.8782
| 9340 | 0.37963 | 2.5424 | 1.3438 | 2.3908
| 9341 | 0.48148 | 3.2034 | 1.1875 | 2.1639
| 9342 | 0.25 | 2.8644 | 1.5312 | 1.8235
| 9343 | 0.34259 | 2.4407 | 1.3438 | 1.8992
| 9344 | 0.41667 | 2.7288 | 1.25 | 1.9748
| 9345 | 0.35185 | 3.2034 | 0.84375 | 1.8571
| 9346 | 0.43519 | 3.1356 | 1.4375 | 2.1218
| 9347 | 0.30556 | 2.6102 | 1.25 | 2.0672
| 9348 | 0.40741 | 2.678 | 1.75 | 1.958
| 9349 | 0.43519 | 3.1017 | 2.0312 | 2.021
| 9350 | 0.47222 | 2.6271 | 1.7812 | 2.4286
| 9351 | 0.32407 | 1.9153 | 1.2812 | 1.8866
| 9352 | 0.41667 | 2.4576 | 2.7188 | 1.7899
| 9353 | 0.4537 | 3.2203 | 1.1562 | 2.1765
| 9354 | 0.37963 | 2.6271 | 2.1562 | 2.063
| 9355 | 0.67593 | 2.4407 | 1.2812 | 1.9412
| 9356 | 0.66667 | 2.9831 | 1.7812 | 2.1639
| 9357 | 0.30556 | 2.678 | 1.4062 | 1.8655
| 9358 | 0.49074 | 2.1864 | 1.5 | 2.1218
| 9359 | 0.38889 | 2.0678 | 1.3438 | 2.1597
| 9360 | 0.27778 | 2.4746 | 1.75 | 2.2647
| 9361 | 0.49074 | 3.2373 | 1.875 | 2.3235
| 9362 | 0.37963 | 2.7797 | 1.0312 | 1.9034
| 9363 | 0.43519 | 2.1017 | 1.4062 | 2.5378
| 9364 | 0.40741 | 2.8475 | 1.5938 | 1.9202
| 9365 | 0.24074 | 2.9661 | 0.96875 | 2.1134
| 9366 | 0.5463 | 2.5593 | 1.125 | 2.3109
| 9367 | 0.42593 | 2.9661 | 0.90625 | 2.0672
| 9368 | 0.44444 | 3.4915 | 1.5938 | 2.1387
| 9369 | 0.37963 | 2.2203 | 1.25 | 2.1555
| 9370 | 0.50926 | 2.2203 | 1.5312 | 2.0294
| 9371 | 0.33333 | 3.0678 | 2.1562 | 2.0588
| 9372 | 0.31481 | 2.7288 | 2.2812 | 1.9286
| 9373 | 0.41667 | 3.0847 | 1.4375 | 2.0798
| 9374 | 0.57407 | 3.5424 | 2.2812 | 1.8992
| 9375 | 0.39815 | 2.5085 | 1.125 | 1.8025
| 9376 | 0.34259 | 2.1695 | 1.3438 | 2.042
| 9377 | 0.35185 | 2.4237 | 1.375 | 2.2101
| 9378 | 0.42593 | 2.322 | 1.1875 | 2.2731
| 9379 | 0.36111 | 2.1525 | 1.2188 | 1.7563
| 9380 | 0.34259 | 2.6441 | 1.0312 | 1.8361
| 9381 | 0.34259 | 2.4915 | 2.1562 | 2.084
| 9382 | 0.66667 | 3.0678 | 1.875 | 2.7311
| 9383 | 0.31481 | 2.322 | 1.5625 | 2.4748
| 9384 | 0.40741 | 3.4068 | 1.5312 | 2.3403
| 9385 | 0.33333 | 2.1695 | 1.7812 | 2.2269
| 9386 | 0.38889 | 1.7458 | 1.0625 | 1.8992
| 9387 | 0.25926 | 3.322 | 1.5625 | 2.4748
| 9388 | 0.40741 | 2.7288 | 1.125 | 2.1597
| 9389 | 0.37037 | 3 | 1.3125 | 1.9412
| 9390 | 0.21296 | 2.8305 | 1.625 | 2.0042
| 9391 | 0.43519 | 2.3051 | 1.3125 | 2.0042
| 9392 | 0.40741 | 3.0847 | 2.0312 | 1.9706
| 9393 | 0.26852 | 2.2373 | 1 | 1.8067
| 9394 | 0.39815 | 2.8644 | 1.125 | 2.0882
| 9395 | 0.42593 | 2.4068 | 1.6562 | 2.4076
| 9396 | 0.5463 | 2.5254 | 1.6875 | 2.1387
| 9397 | 0.49074 | 2.4407 | 1.2812 | 2.2899
| 9398 | 0.42593 | 2.5085 | 0.9375 | 2.042
| 9399 | 0.41667 | 3 | 1.2188 | 2.1555
| 9400 | 0.28704 | 2.4068 | 1.4062 | 2.1681
| 9401 | 0.53704 | 2.9661 | 1.3438 | 1.9706
| 9402 | 0.5463 | 3.2203 | 1.5625 | 2.3319
| 9403 | 0.50926 | 2.9322 | 0.90625 | 2.1218
| 9404 | 0.42593 | 2.7288 | 0.78125 | 1.9706
| 9405 | 0.40741 | 2.8983 | 1.4062 | 1.8908
| 9406 | 0.37963 | 2.9661 | 1.9375 | 2.0588
| 9407 | 0.42593 | 2.9831 | 1.8125 | 1.979
| 9408 | 0.30556 | 2.6271 | 0.8125 | 2.4118
| 9409 | 0.47222 | 3.1017 | 1.875 | 2.0546
| 9410 | 0.52778 | 2.8814 | 1 | 2.1513
| 9411 | 0.37037 | 2.2881 | 0.90625 | 2.2521
| 9412 | 0.4537 | 2.5424 | 2.1875 | 2.584
| 9413 | 0.49074 | 2.4068 | 1.375 | 1.9832
| 9414 | 0.44444 | 2.0508 | 1.0312 | 2.1092
| 9415 | 0.35185 | 2.2373 | 1.6875 | 2.1555
| 9416 | 0.5 | 3.2542 | 1.75 | 2.042
| 9417 | 0.31481 | 3.3051 | 1.5 | 2.0168
| 9418 | 0.40741 | 3.322 | 1.5625 | 2.0504
| 9419 | 0.34259 | 2.661 | 0.875 | 2.1765
| 9420 | 0.42593 | 2.678 | 0.84375 | 1.9748
| 9421 | 0.39815 | 2.4237 | 2.0938 | 1.8025
| 9422 | 0.40741 | 3.2712 | 1.2188 | 1.7311
| 9423 | 0.4537 | 2.6271 | 1.5 | 1.9916
| 9424 | 0.47222 | 3.1017 | 1.8438 | 2.2269
| 9425 | 0.37037 | 2.4746 | 1 | 1.916
| 9426 | 0.37963 | 2.1356 | 1.375 | 1.9664
| 9427 | 0.37037 | 2.7797 | 1.5625 | 2.8403
| 9428 | 0.5 | 3.4746 | 1.75 | 2.3067
| 9429 | 0.55556 | 2.9492 | 1.3125 | 1.916
| 9430 | 0.5463 | 2.5254 | 1.8438 | 2.0336
| 9431 | 0.37037 | 2.6271 | 1.8438 | 2.1849
| 9432 | 0.52778 | 1.661 | 1.7188 | 2.2941
| 9433 | 0.47222 | 3.3051 | 1.25 | 2.1933
| 9434 | 0.34259 | 2.3729 | 1.8125 | 2.2059
| 9435 | 0.38889 | 2.2542 | 0.96875 | 2.3529
| 9436 | 0.40741 | 2.5085 | 1.4375 | 1.7101
| 9437 | 0.57407 | 2.7627 | 1.6875 | 2.4496
| 9438 | 0.37963 | 2.4576 | 1.375 | 2.0378
| 9439 | 0.51852 | 1.7288 | 1.2812 | 2.3193
| 9440 | 0.37963 | 2.6271 | 1.0938 | 2.0378
| 9441 | 0.25 | 3.2712 | 1.375 | 2.1597
| 9442 | 0.55556 | 2.5424 | 2.125 | 2.063
| 9443 | 0.32407 | 2.0678 | 1.8438 | 2.2731
| 9444 | 0.34259 | 2.6441 | 1.375 | 2.3992
| 9445 | 0.61111 | 2.4915 | 2.5312 | 2.1723
| 9446 | 0.47222 | 2.5932 | 1.7812 | 2.3529
| 9447 | 0.39815 | 2.0339 | 1.6875 | 2.2773
| 9448 | 0.4537 | 2.339 | 1.25 | 1.7479
| 9449 | 0.44444 | 1.8136 | 1.4375 | 2.2395
| 9450 | 0.43519 | 2.2373 | 1.25 | 1.937
| 9451 | 0.27778 | 2.9322 | 1.25 | 2.2269
| 9452 | 0.37037 | 1.7458 | 1.3438 | 2.2941
| 9453 | 0.37963 | 2.8983 | 1.1875 | 1.937
| 9454 | 0.4537 | 2.8136 | 2.375 | 2.042
| 9455 | 0.42593 | 2.5424 | 1.0312 | 1.9664
| 9456 | 0.33333 | 3.0339 | 1.125 | 2.0462
| 9457 | 0.33333 | 3.2542 | 1.7812 | 2
| 9458 | 0.41667 | 2.5763 | 1.0312 | 1.8655
| 9459 | 0.4537 | 2.4576 | 1.25 | 1.9832
| 9460 | 0.25926 | 2.1356 | 0.375 | 2.1176
| 9461 | 0.5 | 2.4237 | 1.4688 | 2.084
| 9462 | 0.37963 | 2.2881 | 0.90625 | 2.2185
| 9463 | 0.42593 | 3.4237 | 2 | 2.1681
| 9464 | 0.39815 | 2.8983 | 1.0938 | 2.3193
| 9465 | 0.35185 | 1.9492 | 1.2812 | 2.3151
| 9466 | 0.39815 | 2.7458 | 1.1875 | 2.1261
| 9467 | 0.42593 | 2.8136 | 1.875 | 2.0924
| 9468 | 0.40741 | 2.4407 | 2.0625 | 1.8613
| 9469 | 0.43519 | 2.4068 | 1.6562 | 2.1555
| 9470 | 0.51852 | 2.5424 | 0.6875 | 1.8319
| 9471 | 0.44444 | 3.0169 | 1.5312 | 1.9454
| 9472 | 0.4537 | 2.5085 | 0.875 | 2.3782
| 9473 | 0.38889 | 2.6441 | 1.0625 | 2.084
| 9474 | 0.40741 | 2.4746 | 1.3125 | 1.9412
| 9475 | 0.48148 | 3.5932 | 1 | 2.0084
| 9476 | 0.43519 | 2.5424 | 1.375 | 2.1387
| 9477 | 0.52778 | 2.3559 | 0.75 | 2.2059
| 9478 | 0.32407 | 1.9322 | 2.125 | 2.3655
| 9479 | 0.30556 | 3.2712 | 1.25 | 2.395
| 9480 | 0.5463 | 3.0339 | 1 | 2.1176
| 9481 | 0.42593 | 2.3051 | 1.2812 | 2.4496
| 9482 | 0.48148 | 2.1695 | 1.5625 | 1.7143
| 9483 | 0.40741 | 3.2203 | 1.2188 | 2.3571
| 9484 | 0.47222 | 2.4915 | 1.2188 | 2.3235
| 9485 | 0.43519 | 3.1864 | 1.4375 | 2.0546
| 9486 | 0.36111 | 2.1695 | 1.5 | 2.2059
| 9487 | 0.44444 | 2.6102 | 1.5938 | 1.8319
| 9488 | 0.35185 | 2.661 | 1.4688 | 2.1218
| 9489 | 0.43519 | 2.4407 | 2.5938 | 2.0756
| 9490 | 0.39815 | 2.2712 | 1.4062 | 1.9706
| 9491 | 0.49074 | 2.3729 | 1.6875 | 2.0924
| 9492 | 0.56481 | 2.1525 | 1.2812 | 2.0882
| 9493 | 0.32407 | 2.9661 | 1.5312 | 2.1513
| 9494 | 0.42593 | 2.8644 | 1.0625 | 2.521
| 9495 | 0.49074 | 2.678 | 0.96875 | 1.7899
| 9496 | 0.34259 | 2.8814 | 1.5938 | 1.6933
| 9497 | 0.4537 | 3.4576 | 1.7188 | 2.0168
| 9498 | 0.50926 | 3.2542 | 1.3125 | 2.2059
| 9499 | 0.41667 | 2.8814 | 1.1875 | 2.2689
| 9500 | 0.37037 | 2.5424 | 2.4688 | 2.0756
| 9501 | 0.37963 | 2.8983 | 1.25 | 2.1807
| 9502 | 0.48148 | 2.0169 | 2.0312 | 2.0924
| 9503 | 0.5463 | 2.3729 | 1.5625 | 2.1513
| 9504 | 0.4537 | 2.7119 | 0.9375 | 2.0042
| 9505 | 0.37037 | 2.8305 | 1.9375 | 2.105
| 9506 | 0.43519 | 3.3559 | 1 | 1.8529
| 9507 | 0.4537 | 2.9322 | 1.875 | 1.9328
| 9508 | 0.61111 | 2.4915 | 1.6562 | 2.1849
| 9509 | 0.28704 | 2.4915 | 1.9375 | 2
| 9510 | 0.42593 | 2.3051 | 1.9062 | 1.9454
| 9511 | 0.40741 | 2.678 | 1.5625 | 2.0966
| 9512 | 0.41667 | 2.1186 | 0.90625 | 2.0378
| 9513 | 0.49074 | 2.5932 | 2.25 | 1.9748
| 9514 | 0.37037 | 2.8814 | 1.3125 | 2.1176
| 9515 | 0.26852 | 2.4576 | 1.4062 | 1.9412
| 9516 | 0.41667 | 2.6271 | 0.6875 | 2.2941
| 9517 | 0.35185 | 3.661 | 0.59375 | 2.1933
| 9518 | 0.49074 | 2.661 | 1.3438 | 1.8403
| 9519 | 0.36111 | 2.6441 | 0.875 | 1.8782
| 9520 | 0.46296 | 3.1017 | 1.5625 | 2.2773
| 9521 | 0.46296 | 3.1525 | 1.8438 | 2.2437
| 9522 | 0.26852 | 2.3559 | 1.125 | 1.9118
| 9523 | 0.5 | 2.5763 | 1.3125 | 2.3109
| 9524 | 0.32407 | 1.8305 | 1.4688 | 2.0378
| 9525 | 0.62963 | 2.4068 | 1.7812 | 2.4286
| 9526 | 0.32407 | 2.5424 | 1.125 | 2.0756
| 9527 | 0.25 | 2.1356 | 1.4688 | 2.0798
| 9528 | 0.5463 | 2.1695 | 1.25 | 2.1471
| 9529 | 0.37963 | 2.6949 | 1.625 | 2.4244
| 9530 | 0.39815 | 2.8644 | 1.4062 | 1.9622
| 9531 | 0.32407 | 2.5254 | 1.1875 | 2.1176
| 9532 | 0.64815 | 2.4407 | 0.90625 | 2.458
| 9533 | 0.47222 | 2.7119 | 1.4062 | 1.9244
| 9534 | 0.2963 | 2.8644 | 1.6875 | 2.2269
| 9535 | 0.42593 | 3.9153 | 1.5938 | 1.958
| 9536 | 0.35185 | 3.2542 | 1.75 | 1.8403
| 9537 | 0.28704 | 3.5424 | 1.1562 | 2.3403
| 9538 | 0.39815 | 3.4746 | 1.3438 | 2.2185
| 9539 | 0.61111 | 2.9492 | 0.875 | 1.9118
| 9540 | 0.62963 | 2.9322 | 1.6562 | 1.8992
| 9541 | 0.41667 | 2.9492 | 1.8125 | 1.8235
| 9542 | 0.2963 | 3.5085 | 1.25 | 2.042
| 9543 | 0.38889 | 2.9492 | 1.1875 | 2.1345
| 9544 | 0.34259 | 2.9831 | 1.2812 | 2.0462
| 9545 | 0.46296 | 2.5932 | 1.1562 | 2.1134
| 9546 | 0.27778 | 2.9153 | 1.25 | 1.958
| 9547 | 0.38889 | 2.4576 | 1.875 | 1.8319
| 9548 | 0.37037 | 2.5593 | 1.4375 | 2.3992
| 9549 | 0.37963 | 2.4576 | 1.0625 | 2.0714
| 9550 | 0.33333 | 3.0678 | 1.5625 | 3.0336
| 9551 | 0.43519 | 2.3729 | 1.4375 | 2.2521
| 9552 | 0.44444 | 3.1186 | 1.9688 | 2.3529
| 9553 | 0.43519 | 2.0678 | 1.4375 | 2.4118
| 9554 | 0.43519 | 2.4746 | 1.3125 | 2.0966
| 9555 | 0.42593 | 2.0508 | 1.6562 | 2.1681
| 9556 | 0.28704 | 2.9492 | 1.5938 | 1.979
| 9557 | 0.39815 | 2.1695 | 1.5 | 2.2017
| 9558 | 0.51852 | 3.0847 | 0.75 | 2.2059
| 9559 | 0.42593 | 2.4068 | 1.6562 | 1.9244
| 9560 | 0.26852 | 2.322 | 1.1875 | 2.1345
| 9561 | 0.44444 | 2.2712 | 1.0625 | 2.3782
| 9562 | 0.40741 | 2.9831 | 1.7812 | 1.8487
| 9563 | 0.34259 | 2.6949 | 1.1562 | 2.2731
| 9564 | 0.46296 | 3.3051 | 1.8125 | 1.9202
| 9565 | 0.50926 | 2.4915 | 1 | 2.1681
| 9566 | 0.41667 | 2.0847 | 0.875 | 2.4496
| 9567 | 0.34259 | 3.0169 | 0.6875 | 1.8151
| 9568 | 0.27778 | 2.6949 | 0.875 | 1.9958
| 9569 | 0.42593 | 2.2712 | 1.0625 | 2.1387
| 9570 | 0.5463 | 2.5085 | 1.3438 | 2.0504
| 9571 | 0.53704 | 2.3559 | 1.9375 | 2.0588
| 9572 | 0.4537 | 2.0847 | 1.875 | 2.5966
| 9573 | 0.41667 | 2.9661 | 0.71875 | 2.1555
| 9574 | 0.37037 | 2.6949 | 1.5312 | 1.9244
| 9575 | 0.30556 | 2.1356 | 0.84375 | 1.7857
| 9576 | 0.46296 | 2.339 | 2.0312 | 2.0042
| 9577 | 0.52778 | 2.8644 | 1.9688 | 1.8403
| 9578 | 0.36111 | 3.1695 | 1.0312 | 2.1765
| 9579 | 0.41667 | 2.5085 | 0.96875 | 2.0924
| 9580 | 0.64815 | 2.3729 | 1.25 | 2.0252
| 9581 | 0.34259 | 2.3051 | 0.875 | 1.916
| 9582 | 0.4537 | 2.2034 | 0.9375 | 2.3025
| 9583 | 0.4537 | 2.4407 | 2.0938 | 1.8277
| 9584 | 0.44444 | 2.9492 | 1.3438 | 2.1387
| 9585 | 0.38889 | 2.1864 | 1.7188 | 2.1471
| 9586 | 0.32407 | 2.7966 | 0.8125 | 1.8655
| 9587 | 0.49074 | 2.5424 | 1.0312 | 1.9706
| 9588 | 0.24074 | 3.0678 | 1.3438 | 2.1975
| 9589 | 0.46296 | 2.1356 | 1.2812 | 1.8487
| 9590 | 0.37037 | 2.8136 | 1.375 | 2.1176
| 9591 | 0.30556 | 2.322 | 1.625 | 2.0924
| 9592 | 0.62037 | 2.3559 | 1.625 | 2.5042
| 9593 | 0.2963 | 2.1017 | 1.5625 | 2.021
| 9594 | 0.60185 | 2.9492 | 1.3125 | 1.937
| 9595 | 0.40741 | 2.678 | 1.6562 | 2.0084
| 9596 | 0.5 | 2.2034 | 1.5312 | 1.8782
| 9597 | 0.25926 | 2.4068 | 0.75 | 1.9706
| 9598 | 0.50926 | 3.0847 | 0.8125 | 1.8529
| 9599 | 0.58333 | 3.2034 | 1.3125 | 1.8487
| 9600 | 0.31481 | 2.2373 | 1.1562 | 1.8655
| 9601 | 0.58333 | 3.3559 | 0.96875 | 2.3445
| 9602 | 0.31481 | 2.4915 | 1 | 2.1849
| 9603 | 0.25 | 3.5424 | 1.1562 | 2.1387
| 9604 | 0.40741 | 3.1695 | 2.75 | 1.7899
| 9605 | 0.37963 | 2.1356 | 2.125 | 2.2815
| 9606 | 0.2963 | 2.5593 | 2.3125 | 2.0126
| 9607 | 0.41667 | 3.5424 | 1 | 1.958
| 9608 | 0.52778 | 2.7627 | 1.7188 | 1.7983
| 9609 | 0.37963 | 2.5424 | 2.1875 | 1.7857
| 9610 | 0.25 | 2.0508 | 1.4375 | 2.1387
| 9611 | 0.48148 | 3.3559 | 1.5312 | 1.9874
| 9612 | 0.41667 | 2.4237 | 1.25 | 2.2143
| 9613 | 0.36111 | 3.2034 | 0.78125 | 2.0168
| 9614 | 0.39815 | 3.322 | 0.8125 | 2.2437
| 9615 | 0.2963 | 2.4746 | 1.375 | 1.8319
| 9616 | 0.40741 | 2.2203 | 1.7188 | 2.2941
| 9617 | 0.48148 | 3.4068 | 1.0625 | 1.9202
| 9618 | 0.35185 | 2.1525 | 1.625 | 2.0756
| 9619 | 0.27778 | 2.339 | 1.4375 | 2.042
| 9620 | 0.37037 | 2.8644 | 1.625 | 2.0126
| 9621 | 0.2963 | 2.3559 | 1.4688 | 1.8445
| 9622 | 0.56481 | 2.9153 | 1.5 | 2.1555
| 9623 | 0.31481 | 2.3729 | 1.875 | 2.2269
| 9624 | 0.5 | 2.9153 | 1.5625 | 2.0924
| 9625 | 0.33333 | 2.5593 | 2.7188 | 2.2143
| 9626 | 0.40741 | 2.2881 | 1.3125 | 1.9874
| 9627 | 0.43519 | 3 | 0.6875 | 2.1218
| 9628 | 0.36111 | 2.5424 | 1.4062 | 2.1975
| 9629 | 0.39815 | 3.5085 | 2.8438 | 1.9706
| 9630 | 0.47222 | 2.5932 | 1.7188 | 2.2017
| 9631 | 0.56481 | 3.0847 | 1.4062 | 1.979
| 9632 | 0.31481 | 2.1864 | 0.8125 | 1.6933
| 9633 | 0.46296 | 2.3051 | 0.875 | 2.3361
| 9634 | 0.44444 | 2.5932 | 2.875 | 2.1513
| 9635 | 0.33333 | 3.1356 | 1.7188 | 1.6807
| 9636 | 0.27778 | 2.7966 | 1.5312 | 2.1218
| 9637 | 0.40741 | 2.5932 | 1.2188 | 2.1849
| 9638 | 0.41667 | 2.2034 | 0.6875 | 2.2899
| 9639 | 0.34259 | 2.2542 | 0.59375 | 2.084
| 9640 | 0.49074 | 2.8814 | 1.3438 | 1.8403
| 9641 | 0.5 | 2.9322 | 2.375 | 1.9622
| 9642 | 0.5463 | 3.0678 | 1.75 | 2.1303
| 9643 | 0.43519 | 1.8983 | 1.4062 | 1.6639
| 9644 | 0.40741 | 2.9831 | 1.7812 | 2.3782
| 9645 | 0.38889 | 3.7458 | 1.4375 | 2.1639
| 9646 | 0.43519 | 3.0508 | 1.1875 | 2.3277
| 9647 | 0.64815 | 2.4068 | 1.0938 | 1.8319
| 9648 | 0.41667 | 2.7119 | 1 | 2.1513
| 9649 | 0.31481 | 3.2542 | 1.5938 | 2.3277
| 9650 | 0.37037 | 2.7119 | 1.1562 | 1.9328
| 9651 | 0.24074 | 2.5254 | 1.0312 | 2.2857
| 9652 | 0.39815 | 3.0508 | 1 | 2.2941
| 9653 | 0.4537 | 2.7119 | 1.5625 | 2.084
| 9654 | 0.40741 | 2.0508 | 2.0625 | 1.8487
| 9655 | 0.52778 | 2.7966 | 1.2812 | 1.9622
| 9656 | 0.73148 | 2.1186 | 1.375 | 2.1008
| 9657 | 0.57407 | 1.6949 | 0.8125 | 1.9622
| 9658 | 0.35185 | 3.1356 | 1.5625 | 2.1975
| 9659 | 0.40741 | 2.5763 | 1.3438 | 2.1891
| 9660 | 0.27778 | 2.4068 | 1.5625 | 2.3487
| 9661 | 0.50926 | 3.4576 | 1.0938 | 1.9244
| 9662 | 0.34259 | 2.4237 | 1.8438 | 2.5
| 9663 | 0.52778 | 2 | 0.71875 | 1.937
| 9664 | 0.50926 | 2.6441 | 1.625 | 2.1681
| 9665 | 0.35185 | 2.8983 | 1.5938 | 2.2479
| 9666 | 0.2963 | 2.8644 | 1.125 | 2.1933
| 9667 | 0.28704 | 2.5932 | 0.875 | 2.0504
| 9668 | 0.38889 | 2.5763 | 1.25 | 2.0168
| 9669 | 0.32407 | 2.6949 | 1.9375 | 1.916
| 9670 | 0.37037 | 1.6441 | 1.6875 | 2.3361
| 9671 | 0.40741 | 2.4068 | 1.2812 | 2.1218
| 9672 | 0.39815 | 2.7966 | 0.90625 | 2.021
| 9673 | 0.47222 | 3.0508 | 1.4375 | 2.1134
| 9674 | 0.37963 | 3.3898 | 1.0938 | 2.2353
| 9675 | 0.36111 | 2.8305 | 2.3438 | 2.1092
| 9676 | 0.2963 | 2.7627 | 1.8125 | 1.8571
| 9677 | 0.37963 | 2.4576 | 1.3125 | 2.0252
| 9678 | 0.31481 | 2.1356 | 1.9375 | 1.7479
| 9679 | 0.59259 | 2.678 | 0.96875 | 1.9874
| 9680 | 0.40741 | 3.2712 | 1.4375 | 2.1639
| 9681 | 0.37037 | 2.5424 | 1.8125 | 2.0966
| 9682 | 0.32407 | 2.6102 | 1.75 | 2.3613
| 9683 | 0.53704 | 2.5932 | 1 | 2.0042
| 9684 | 0.42593 | 2.9661 | 1.125 | 1.958
| 9685 | 0.43519 | 2.8475 | 1.7188 | 1.9496
| 9686 | 0.27778 | 2.4237 | 1.1562 | 1.9916
| 9687 | 0.31481 | 3 | 2.5312 | 2.1429
| 9688 | 0.46296 | 3.2542 | 1.625 | 2.1092
| 9689 | 0.38889 | 2.8136 | 1.0312 | 1.8613
| 9690 | 0.55556 | 2.5085 | 1.6875 | 1.8697
| 9691 | 0.44444 | 3.2034 | 2.6875 | 2.1261
| 9692 | 0.40741 | 2.0339 | 0.625 | 1.979
| 9693 | 0.50926 | 2.7966 | 1.5938 | 2.0504
| 9694 | 0.51852 | 2.9661 | 1.0312 | 2.3571
| 9695 | 0.32407 | 2.339 | 1.9688 | 2.042
| 9696 | 0.46296 | 2.1864 | 1.1875 | 2.2227
| 9697 | 0.44444 | 2.7458 | 1.7812 | 1.916
| 9698 | 0.52778 | 2.322 | 2.25 | 2.1134
| 9699 | 0.55556 | 2.4237 | 2.0938 | 2.0378
| 9700 | 0.44444 | 2.2542 | 0.8125 | 2.3319
| 9701 | 0.25 | 2.1864 | 1.4688 | 2.2437
| 9702 | 0.42593 | 2.9661 | 1.0625 | 1.9916
| 9703 | 0.42593 | 2.7458 | 1.4688 | 1.7269
| 9704 | 0.38889 | 2.5254 | 1.0312 | 2.1134
| 9705 | 0.25 | 2.661 | 1.3125 | 1.9202
| 9706 | 0.2963 | 3.1186 | 1.375 | 2.2143
| 9707 | 0.48148 | 2.2881 | 1.4688 | 2.0756
| 9708 | 0.32407 | 2.4746 | 1.8438 | 2.3235
| 9709 | 0.47222 | 3 | 0.8125 | 2.0462
| 9710 | 0.32407 | 2.5424 | 1.0625 | 2.2437
| 9711 | 0.28704 | 2.4237 | 1.7812 | 2.1176
| 9712 | 0.42593 | 1.8644 | 1.75 | 2.0042
| 9713 | 0.55556 | 2.7627 | 0.9375 | 1.9034
| 9714 | 0.33333 | 2.7797 | 1.4062 | 1.7647
| 9715 | 0.36111 | 2.4407 | 1.4062 | 1.8319
| 9716 | 0.5 | 2.6949 | 1.1875 | 2.1555
| 9717 | 0.34259 | 2.7458 | 1.7812 | 2.0168
| 9718 | 0.43519 | 3.7119 | 0.8125 | 2.0084
| 9719 | 0.36111 | 2.9831 | 0.4375 | 2.6092
| 9720 | 0.40741 | 2.1525 | 1.5312 | 2.2773
| 9721 | 0.33333 | 2.9831 | 0.78125 | 2.479
| 9722 | 0.37963 | 2.2712 | 2.3438 | 2.0714
| 9723 | 0.46296 | 2.9153 | 1.9688 | 1.9034
| 9724 | 0.27778 | 3.9153 | 2 | 1.937
| 9725 | 0.35185 | 2.4237 | 1.7188 | 2.0168
| 9726 | 0.2963 | 1.9492 | 1.2812 | 1.8319
| 9727 | 0.37963 | 2.8814 | 1.1875 | 2.3824
| 9728 | 0.38889 | 2.2542 | 0.84375 | 1.895
| 9729 | 0.37963 | 2.3729 | 1.2812 | 2.0294
| 9730 | 0.33333 | 3.0169 | 0.84375 | 2.3361
| 9731 | 0.55556 | 3.0678 | 1.2812 | 1.9328
| 9732 | 0.37037 | 2.6949 | 1.625 | 2.3109
| 9733 | 0.52778 | 3.2203 | 1.2812 | 2.0756
| 9734 | 0.28704 | 2.0508 | 1.0625 | 2.0588
| 9735 | 0.35185 | 2.6441 | 1.4062 | 2.1513
| 9736 | 0.46296 | 3.3051 | 1.25 | 2.2983
| 9737 | 0.42593 | 2.7288 | 1.5 | 2.1765
| 9738 | 0.44444 | 2.6441 | 1.3125 | 2.1723
| 9739 | 0.37037 | 2.6102 | 1.1562 | 2
| 9740 | 0.33333 | 3.3051 | 1 | 1.8193
| 9741 | 0.4537 | 2.8475 | 1.2188 | 1.8109
| 9742 | 0.28704 | 2.8475 | 1.25 | 2.4748
| 9743 | 0.50926 | 2.339 | 1.3125 | 2.1723
| 9744 | 0.55556 | 3.2712 | 1.7812 | 1.9622
| 9745 | 0.37963 | 2.3898 | 2 | 1.916
| 9746 | 0.63889 | 3.0678 | 1.0938 | 2.0504
| 9747 | 0.49074 | 2.2542 | 1.4062 | 1.8445
| 9748 | 0.48148 | 2.8983 | 1.3125 | 1.9244
| 9749 | 0.64815 | 1.8305 | 1.4375 | 2.1765
| 9750 | 0.58333 | 2.1864 | 1.25 | 1.8361
| 9751 | 0.41667 | 2.8983 | 1.5 | 2.2395
| 9752 | 0.41667 | 2.7627 | 1.75 | 2.2143
| 9753 | 0.30556 | 2.8644 | 1 | 2.4832
| 9754 | 0.46296 | 2.4915 | 1.3438 | 2.4916
| 9755 | 0.5463 | 3.1864 | 1.1875 | 1.7563
| 9756 | 0.2963 | 2.4576 | 1.6875 | 2.1429
| 9757 | 0.58333 | 3.1525 | 1.2188 | 2.2815
| 9758 | 0.41667 | 2.5763 | 1.9062 | 2.1513
| 9759 | 0.43519 | 2.9153 | 1.7812 | 2.1891
| 9760 | 0.55556 | 3.1525 | 1.5 | 2.2395
| 9761 | 0.34259 | 2.5932 | 1.4375 | 2.0924
| 9762 | 0.25926 | 2.5593 | 1.0312 | 1.9202
| 9763 | 0.52778 | 2.7966 | 1.5625 | 2.2395
| 9764 | 0.37037 | 2.5085 | 1.5 | 2.1891
| 9765 | 0.34259 | 2.8305 | 1.3125 | 2.3277
| 9766 | 0.31481 | 2.6441 | 2.125 | 1.8487
| 9767 | 0.63889 | 3 | 1.0312 | 1.8445
| 9768 | 0.30556 | 2.1017 | 1.0938 | 2.0756
| 9769 | 0.50926 | 2.2034 | 1.0938 | 2.1261
| 9770 | 0.48148 | 3.0169 | 0.875 | 2.2521
| 9771 | 0.41667 | 3.1356 | 1.8125 | 2.0084
| 9772 | 0.5 | 1.9831 | 1.875 | 2.1597
| 9773 | 0.37037 | 3.2373 | 1.0938 | 1.9958
| 9774 | 0.46296 | 2.5593 | 1.2188 | 1.9538
| 9775 | 0.55556 | 2.3051 | 1.3125 | 1.8866
| 9776 | 0.49074 | 3.1356 | 1.4688 | 2.3908
| 9777 | 0.68519 | 3.4576 | 1.5938 | 1.7983
| 9778 | 0.40741 | 3.8305 | 1.3438 | 2.2185
| 9779 | 0.37037 | 3.1864 | 0.8125 | 2.3908
| 9780 | 0.34259 | 2.5763 | 1.1875 | 2.105
| 9781 | 0.31481 | 2.1186 | 1 | 1.9454
| 9782 | 0.49074 | 2.7119 | 1.4688 | 1.8824
| 9783 | 0.53704 | 2.5932 | 1.6875 | 2.1345
| 9784 | 0.37963 | 3.4576 | 1.0938 | 2.1345
| 9785 | 0.5463 | 2.1864 | 1.4688 | 2.3908
| 9786 | 0.32407 | 2.322 | 1.75 | 2.063
| 9787 | 0.31481 | 2.2712 | 1 | 2.0714
| 9788 | 0.49074 | 2.9322 | 0.6875 | 2.1429
| 9789 | 0.57407 | 1.2881 | 1.75 | 2.2941
| 9790 | 0.30556 | 2.7797 | 1.25 | 2.3824
| 9791 | 0.39815 | 2.6441 | 1.3125 | 2.1639
| 9792 | 0.37037 | 2.7966 | 1.6562 | 1.7857
| 9793 | 0.48148 | 2.6949 | 0.8125 | 2.437
| 9794 | 0.47222 | 2.8475 | 0.90625 | 2.0168
| 9795 | 0.39815 | 1.9153 | 1.125 | 1.7941
| 9796 | 0.46296 | 2.1017 | 1.3438 | 2.0336
| 9797 | 0.48148 | 2.8305 | 0.96875 | 1.979
| 9798 | 0.47222 | 1.8305 | 1.2812 | 2.0966
| 9799 | 0.39815 | 1.9492 | 1.9375 | 2.4328
| 9800 | 0.39815 | 3.2373 | 1.1562 | 2.1723
| 9801 | 0.44444 | 2.2712 | 1.0312 | 1.9664
| 9802 | 0.46296 | 3 | 2 | 1.9538
| 9803 | 0.31481 | 2.5254 | 1 | 1.9832
| 9804 | 0.34259 | 2.6441 | 0.9375 | 2.1092
| 9805 | 0.43519 | 2.2373 | 1.6875 | 2.2143
| 9806 | 0.43519 | 2.7119 | 0.90625 | 2.021
| 9807 | 0.53704 | 2.5932 | 1.7812 | 2.021
| 9808 | 0.25926 | 3.4746 | 1.8438 | 2.1345
| 9809 | 0.37963 | 2.0678 | 1.4375 | 1.9454
| 9810 | 0.47222 | 1.9322 | 1.0938 | 1.9958
| 9811 | 0.42593 | 2.9492 | 1.1562 | 2.0126
| 9812 | 0.46296 | 3.3051 | 1.6875 | 2.3109
| 9813 | 0.43519 | 2.1695 | 2.0625 | 2.1387
| 9814 | 0.42593 | 2.9661 | 1.3125 | 2
| 9815 | 0.47222 | 2.6271 | 2.0625 | 2.3319
| 9816 | 0.40741 | 2.7288 | 1.6562 | 2.0378
| 9817 | 0.5 | 3.0847 | 0.90625 | 2.1471
| 9818 | 0.27778 | 2.7119 | 1.5312 | 2.1218
| 9819 | 0.41667 | 2.0847 | 1.9375 | 2.0084
| 9820 | 0.47222 | 2.4915 | 1.0625 | 2.1261
| 9821 | 0.50926 | 3.0508 | 1.0938 | 2.2857
| 9822 | 0.57407 | 3.1017 | 1.4375 | 1.9832
| 9823 | 0.2963 | 3.3898 | 1.2812 | 2.1387
| 9824 | 0.46296 | 2.5254 | 2.0312 | 2.1429
| 9825 | 0.50926 | 2.661 | 1.1875 | 2.5378
| 9826 | 0.32407 | 2.7797 | 0.8125 | 2.0588
| 9827 | 0.26852 | 2.2712 | 0.90625 | 1.8487
| 9828 | 0.39815 | 2.5424 | 1.2188 | 2.1639
| 9829 | 0.47222 | 2.8814 | 1.9062 | 2.1891
| 9830 | 0.46296 | 2.4915 | 1.5312 | 2
| 9831 | 0.46296 | 2.4407 | 1.875 | 2.2479
| 9832 | 0.2963 | 3.3729 | 1.625 | 1.8655
| 9833 | 0.43519 | 2.9322 | 2.0938 | 2.2689
| 9834 | 0.50926 | 2.5932 | 0.90625 | 1.8235
| 9835 | 0.38889 | 2.5593 | 1.7188 | 2.0168
| 9836 | 0.31481 | 2.7627 | 1.4062 | 1.7773
| 9837 | 0.37963 | 2.5932 | 1.1562 | 2.0336
| 9838 | 0.50926 | 2.4915 | 0.90625 | 2.063
| 9839 | 0.62963 | 2.1525 | 2.125 | 2.2899
| 9840 | 0.38889 | 2.4068 | 2.1562 | 2.2479
| 9841 | 0.44444 | 2.2542 | 1.25 | 2.0756
| 9842 | 0.49074 | 2.4576 | 0.96875 | 1.916
| 9843 | 0.46296 | 2.8814 | 1.2812 | 2.0882
| 9844 | 0.5463 | 2.3898 | 1.9688 | 1.9748
| 9845 | 0.2963 | 1.8644 | 1.8438 | 2.0546
| 9846 | 0.35185 | 2.7966 | 1.3125 | 2.0798
| 9847 | 0.40741 | 2.2034 | 2.5938 | 2.1092
| 9848 | 0.40741 | 3.1356 | 1.0312 | 1.9832
| 9849 | 0.41667 | 2.4746 | 1.875 | 2.0336
| 9850 | 0.56481 | 3.9492 | 1.6562 | 2.0336
| 9851 | 0.33333 | 3.8136 | 1.5312 | 2.3487
| 9852 | 0.63889 | 3.6271 | 1.3125 | 2.2647
| 9853 | 0.33333 | 2.8983 | 1.5 | 2.1218
| 9854 | 0.42593 | 2.2712 | 1.4375 | 2.0882
| 9855 | 0.53704 | 3 | 1.8125 | 2.2563
| 9856 | 0.62037 | 3.2881 | 1.125 | 1.8403
| 9857 | 0.43519 | 3.3559 | 1.6562 | 1.9958
| 9858 | 0.34259 | 2.3051 | 1.5938 | 2.1891
| 9859 | 0.37963 | 2.5763 | 1 | 1.7731
| 9860 | 0.35185 | 1.9153 | 1 | 2.1513
| 9861 | 0.32407 | 3.1525 | 1.2812 | 1.9454
| 9862 | 0.52778 | 2.8136 | 1.6562 | 2.1891
| 9863 | 0.43519 | 2.5763 | 1.5 | 2.3487
| 9864 | 0.47222 | 2.8814 | 1.125 | 1.9202
| 9865 | 0.49074 | 3.4407 | 2.1875 | 2.1513
| 9866 | 0.42593 | 3.0339 | 1.4375 | 1.937
| 9867 | 0.33333 | 2.3051 | 1.0938 | 2.1975
| 9868 | 0.52778 | 3.3729 | 1.9375 | 2.0126
| 9869 | 0.32407 | 2.661 | 0.71875 | 2.1849
| 9870 | 0.39815 | 3.3559 | 1.875 | 1.8277
| 9871 | 0.59259 | 3.6271 | 1.5938 | 1.8697
| 9872 | 0.40741 | 2.7797 | 1.3125 | 2.3487
| 9873 | 0.25 | 2.8983 | 1.5312 | 2.3403
| 9874 | 0.36111 | 3.1695 | 1.0625 | 1.8319
| 9875 | 0.44444 | 3.1356 | 1.25 | 1.7857
| 9876 | 0.34259 | 2.7627 | 1.3438 | 1.8739
| 9877 | 0.32407 | 1.9153 | 1.8438 | 2.021
| 9878 | 0.42593 | 2.2881 | 1.3438 | 2.2815
| 9879 | 0.44444 | 2.7288 | 1.5938 | 1.9328
| 9880 | 0.36111 | 2.4746 | 1.4688 | 2.5756
| 9881 | 0.32407 | 2.7966 | 1.4062 | 2.0462
| 9882 | 0.38889 | 2.5763 | 1.0625 | 2.2605
| 9883 | 0.38889 | 3.3559 | 1.1562 | 1.9832
| 9884 | 0.32407 | 2.1017 | 1.3125 | 2.0882
| 9885 | 0.43519 | 2.678 | 2.1875 | 2.1681
| 9886 | 0.40741 | 3 | 0.90625 | 2.2983
| 9887 | 0.4537 | 2.9322 | 1.9062 | 2.3193
| 9888 | 0.32407 | 2.8644 | 1.3438 | 2.0378
| 9889 | 0.41667 | 2.5763 | 1.6875 | 2.1303
| 9890 | 0.41667 | 3.7627 | 1.125 | 2.2815
| 9891 | 0.32407 | 2.9153 | 1.1562 | 2.0084
| 9892 | 0.30556 | 1.5932 | 1 | 2.0378
| 9893 | 0.43519 | 2.4068 | 2.1562 | 2.0924
| 9894 | 0.43519 | 3.0847 | 1 | 2.1807
| 9895 | 0.5 | 2.8136 | 1.875 | 1.6555
| 9896 | 0.5463 | 2.1864 | 1.7188 | 2.0462
| 9897 | 0.39815 | 3 | 1.375 | 2.1639
| 9898 | 0.52778 | 2.4068 | 1.3125 | 2.2563
| 9899 | 0.40741 | 2.5763 | 1.6875 | 2.1471
| 9900 | 0.41667 | 2.8644 | 1.4062 | 2.0546
| 9901 | 0.48148 | 2.661 | 1.1562 | 1.8151
| 9902 | 0.52778 | 3.1356 | 1.7188 | 2.479
| 9903 | 0.49074 | 2.3051 | 1.25 | 2.1681
| 9904 | 0.37963 | 3.4068 | 0.78125 | 1.8025
| 9905 | 0.40741 | 2.1017 | 1.25 | 2.3613
| 9906 | 0.38889 | 2.5254 | 1.7812 | 1.9118
| 9907 | 0.37963 | 2.7627 | 1.75 | 2.6471
| 9908 | 0.41667 | 2.7627 | 1.2188 | 2.0378
| 9909 | 0.38889 | 3.3051 | 1.1562 | 2.4958
| 9910 | 0.37037 | 2.2881 | 0.6875 | 1.7899
| 9911 | 0.37963 | 2.2881 | 0.8125 | 2.0168
| 9912 | 0.47222 | 2.9322 | 1.5625 | 2.2353
| 9913 | 0.44444 | 2.2373 | 1.625 | 1.979
| 9914 | 0.37963 | 2.4237 | 1.4062 | 2.1681
| 9915 | 0.50926 | 3.1864 | 1.1875 | 1.9874
| 9916 | 0.48148 | 2.1356 | 1.5312 | 2.3109
| 9917 | 0.63889 | 2.678 | 2.125 | 2.1261
| 9918 | 0.33333 | 2.2712 | 1.375 | 2.0672
| 9919 | 0.37037 | 3.0847 | 0.9375 | 2.0126
| 9920 | 0.32407 | 2.9492 | 1.75 | 2.3403
| 9921 | 0.2963 | 2.6271 | 1.9688 | 1.9916
| 9922 | 0.37963 | 2.1525 | 0.71875 | 2.0168
| 9923 | 0.35185 | 1.8475 | 1.6562 | 2.084
| 9924 | 0.51852 | 2.6102 | 1.5312 | 2.0084
| 9925 | 0.22222 | 2.7288 | 2.0625 | 1.8739
| 9926 | 0.41667 | 2.5254 | 1.0938 | 2.0966
| 9927 | 0.62963 | 2.3051 | 1.5938 | 2.0672
| 9928 | 0.33333 | 2.0508 | 0.625 | 2.2017
| 9929 | 0.33333 | 2.0339 | 0.84375 | 2.2521
| 9930 | 0.4537 | 2.2881 | 1.1875 | 1.9202
| 9931 | 0.39815 | 2.2881 | 1.6562 | 1.979
| 9932 | 0.47222 | 1.8983 | 1.8438 | 1.8235
| 9933 | 0.57407 | 3 | 1.875 | 2.1513
| 9934 | 0.56481 | 2.4746 | 1.2812 | 1.7521
| 9935 | 0.40741 | 2.4407 | 0.96875 | 2.1765
| 9936 | 0.44444 | 2.4237 | 0.65625 | 2.1176
| 9937 | 0.4537 | 3.6949 | 0.71875 | 2.2059
| 9938 | 0.33333 | 2.678 | 1.5625 | 2.2311
| 9939 | 0.41667 | 2.678 | 1.4688 | 1.8235
| 9940 | 0.41667 | 2.339 | 2.1562 | 1.895
| 9941 | 0.41667 | 2.1695 | 1.4062 | 1.8025
| 9942 | 0.49074 | 2.4746 | 1 | 2.0714
| 9943 | 0.39815 | 2.5254 | 1.9062 | 2.0546
| 9944 | 0.4537 | 2.2542 | 1.5312 | 2.1092
| 9945 | 0.53704 | 2 | 1.625 | 2.1008
| 9946 | 0.31481 | 3.5593 | 1.8125 | 1.9244
| 9947 | 0.38889 | 3.0508 | 1.5938 | 1.7899
| 9948 | 0.57407 | 2.8814 | 1.3125 | 2.395
| 9949 | 0.47222 | 2.7627 | 0.375 | 2.2941
| 9950 | 0.33333 | 2.678 | 1.5625 | 2.0168
| 9951 | 0.52778 | 2.5932 | 1.7188 | 2.3908
| 9952 | 0.40741 | 3.339 | 0.875 | 1.9832
| 9953 | 0.55556 | 2.2034 | 1.2812 | 1.8403
| 9954 | 0.33333 | 3.1186 | 1.8125 | 2.2437
| 9955 | 0.42593 | 2.5763 | 2.125 | 2.0042
| 9956 | 0.42593 | 2.8305 | 0.90625 | 2.1597
| 9957 | 0.32407 | 2.5593 | 2.125 | 2.1134
| 9958 | 0.43519 | 2.0508 | 1.125 | 2.0126
| 9959 | 0.30556 | 2.1695 | 1.3125 | 2.042
| 9960 | 0.41667 | 3.1525 | 1.9375 | 2.2143
| 9961 | 0.30556 | 2.4407 | 1.1875 | 2
| 9962 | 0.34259 | 2.8814 | 1.5 | 2.3613
| 9963 | 0.37963 | 3.2203 | 1.125 | 2.063
| 9964 | 0.31481 | 2.678 | 1.2188 | 1.8193
| 9965 | 0.41667 | 1.7627 | 1.1562 | 2.1975
| 9966 | 0.56481 | 2.7458 | 1.6562 | 1.8613
| 9967 | 0.61111 | 2.4237 | 1.1562 | 2.2479
| 9968 | 0.49074 | 2.5593 | 0.96875 | 2.1345
| 9969 | 0.36111 | 1.9322 | 1.4062 | 2.021
| 9970 | 0.42593 | 1.8814 | 2.4062 | 2.1134
| 9971 | 0.31481 | 2.6102 | 2 | 2.0462
| 9972 | 0.25 | 2.2034 | 1.6875 | 2.1681
| 9973 | 0.44444 | 2.6441 | 1.625 | 2.0672
| 9974 | 0.38889 | 2.4746 | 1.2812 | 1.8403
| 9975 | 0.44444 | 2.9492 | 2.75 | 2.0294
| 9976 | 0.5463 | 3.0169 | 1.25 | 2.2101
| 9977 | 0.41667 | 2.7458 | 1.4375 | 2.4958
| 9978 | 0.23148 | 3.2712 | 1.3125 | 2.0756
| 9979 | 0.42593 | 2.2881 | 1.3125 | 1.8277
| 9980 | 0.44444 | 2.3051 | 1.2188 | 2
| 9981 | 0.34259 | 2.7288 | 2.625 | 2.0378
| 9982 | 0.23148 | 2.5254 | 1.5625 | 2.2899
| 9983 | 0.47222 | 2.4068 | 2.0625 | 2.2395
| 9984 | 0.37037 | 2.5763 | 1.125 | 2.1134
| 9985 | 0.39815 | 3.1695 | 1.2812 | 1.8277
| 9986 | 0.31481 | 2.9153 | 1.7188 | 1.8445
| 9987 | 0.47222 | 3.1864 | 1.4062 | 1.9874
| 9988 | 0.36111 | 2.5932 | 0.65625 | 2.4832
| 9989 | 0.73148 | 2.4915 | 1.4688 | 2.2773
| 9990 | 0.37963 | 1.8814 | 1.5938 | 2.3277
| 9991 | 0.50926 | 2.3729 | 1.125 | 2.3866
| 9992 | 0.46296 | 2.9831 | 1.875 | 1.9958
| 9993 | 0.38889 | 2.5932 | 1.75 | 1.8487
| 9994 | 0.40741 | 2.8644 | 1.875 | 2.105
| 9995 | 0.36111 | 2.0678 | 1.75 | 2.2059
| 9996 | 0.43519 | 2.1017 | 1 | 2.3067
| 9997 | 0.34259 | 2.8475 | 1.5312 | 1.8529
| 9998 | 0.48148 | 2.6102 | 2.25 | 2.1555
| 9999 | 0.44444 | 2.7966 | 1.0938 | 2.5126
| 10000 | 0.40741 | 2.9831 | 0.96875 | 2.1345

## PMTable
1 | Generated with the SIPmath™ Modeler Tools from ProbabilityManagement.org
| Index | Resampled_TH_C | Delivery_time_C | Delivery_time_L1 | Project_Delivery_time_PLAN | Delivery_time_L2 | Delivery_time_L3 | Resampled_TH_A | Delivery_time_A | Resampled_TH_O | Delivery_time_O | Project_Delivery_time_ACTUAL
| Values | 1.2 | 3.3333 | 11.4894 | 19.8491 | 2.7126 | 5.6471 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 1 | 1 | 4 | 11.4894 | 19.8491 | 2.7126 | 5.6471 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 2 | 0.6 | 6.6667 | 11.7391 | 21.6812 | 3.085 | 6.8571 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 3 | 0.6 | 6.6667 | 11.25 | 17.4881 | 2.8095 | 3.4286 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 4 | 1 | 4 | 10.1887 | 17.3179 | 3.2109 | 3.9184 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 5 | 1.2 | 3.3333 | 11.0204 | 17.262 | 1.9749 | 4.2667 | 0.4 | 12.5 | 0.2 | 10 | 25.8333
| 6 | 0.8 | 5 | 14.5946 | 21.6809 | 3.776 | 3.3103 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 7 | 0.4 | 10 | 7.7143 | 16.8589 | 3.6589 | 5.4857 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 8 | 1.2 | 3.3333 | 13.1707 | 22.1788 | 3.5224 | 5.4857 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 9 | 0.8 | 5 | 15.4286 | 24.259 | 2.6369 | 6.1935 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 10 | 1 | 4 | 15 | 23.8791 | 2.2584 | 6.6207 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 11 | 0.6 | 6.6667 | 13.1707 | 20.351 | 2.9136 | 4.2667 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 12 | 0.6 | 6.6667 | 10.3846 | 17.916 | 3.1678 | 4.3636 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 13 | 0.6 | 6.6667 | 14.2105 | 22.5409 | 3.2778 | 5.0526 | 1 | 5 | 0.2 | 10 | 21.6667
| 14 | 1.4 | 2.8571 | 16.875 | 23.5823 | 2.6222 | 4.0851 | 1 | 5 | 0.2 | 10 | 17.8571
| 15 | 1 | 4 | 16.3636 | 22.5844 | 2.3024 | 3.9184 | 1 | 5 | 0.4 | 5 | 14
| 16 | 0.8 | 5 | 16.3636 | 26.0471 | 2.8263 | 6.8571 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 17 | 0.4 | 10 | 9.4737 | 18.1182 | 2.8263 | 5.8182 | 1 | 5 | 0.2 | 10 | 25
| 18 | 0.8 | 5 | 20 | 25.901 | 3.4706 | 2.4304 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 19 | 0.8 | 5 | 14.2105 | 20.6313 | 3.7165 | 2.7042 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 20 | 0.8 | 5 | 12.2727 | 22.1252 | 3.6589 | 6.1935 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 21 | 0.8 | 5 | 12.2727 | 20.664 | 2.7442 | 5.6471 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 22 | 0.4 | 10 | 19.2857 | 26.3582 | 2.9873 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 23 | 1.2 | 3.3333 | 12.8571 | 21.1994 | 2.5241 | 5.8182 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 24 | 1 | 4 | 10.8 | 22.4718 | 3.3239 | 8.3478 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 25 | 0.6 | 6.6667 | 13.8462 | 22.8326 | 2.7929 | 6.1935 | 0.2 | 25 | 0.4 | 5 | 36.6667
| 26 | 1.6 | 2.5 | 9.3103 | 16.196 | 2.4205 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 13.75
| 27 | 0.8 | 5 | 11.25 | 20.4359 | 2.5652 | 6.6207 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 28 | 1 | 4 | 9.4737 | 19.0911 | 2.7602 | 6.8571 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 29 | 0.8 | 5 | 14.2105 | 21.7389 | 2.7283 | 4.8 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 30 | 0.4 | 10 | 10.8 | 20.5239 | 3.3239 | 6.4 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 31 | 1.2 | 3.3333 | 14.5946 | 32.9905 | 2.3959 | 16 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 32 | 0.6 | 6.6667 | 12.5581 | 18.8579 | 2.7442 | 3.5556 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 33 | 1.2 | 3.3333 | 9.1525 | 16.3716 | 3.3007 | 3.9184 | 1 | 5 | 0.2 | 10 | 18.3333
| 34 | 0.1 | 40 | 11.4894 | 17.4818 | 2.8957 | 3.0968 | 0.4 | 12.5 | 0.2 | 10 | 62.5
| 35 | 1 | 4 | 10.8 | 16.7758 | 3.5758 | 2.4 | 1 | 5 | 0.4 | 5 | 14
| 36 | 1.2 | 3.3333 | 11.25 | 18.3967 | 3.1467 | 4 | 1 | 5 | 0.4 | 5 | 13.3333
| 37 | 0.6 | 6.6667 | 13.8462 | 22.6758 | 3.4963 | 5.3333 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 38 | 0.6 | 6.6667 | 11.25 | 17.8346 | 3.6308 | 2.9538 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 39 | 1 | 4 | 12.2727 | 18.6055 | 2.2476 | 4.0851 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 40 | 0.8 | 5 | 11.4894 | 24.5082 | 2.9136 | 10.1053 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 41 | 1 | 4 | 8.7097 | 16.0104 | 3.3007 | 4 | 1 | 5 | 0.1 | 20 | 29
| 42 | 0.8 | 5 | 21.6 | 29.8418 | 3.1892 | 5.0526 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 43 | 0.6 | 6.6667 | 13.8462 | 24.0625 | 3.1053 | 7.1111 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 44 | 1 | 4 | 11.0204 | 19.5108 | 2.8434 | 5.6471 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 45 | 0.8 | 5 | 9.6429 | 16.1579 | 3.1467 | 3.3684 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 46 | 1.6 | 2.5 | 10.1887 | 16.4736 | 3.085 | 3.2 | 1 | 5 | 0.6 | 3.3333 | 10.8333
| 47 | 1 | 4 | 12.5581 | 19.8717 | 3.5489 | 3.7647 | 1 | 5 | 0.2 | 10 | 19
| 48 | 0.8 | 5 | 10.8 | 18.1106 | 3.4706 | 3.84 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 49 | 0.6 | 6.6667 | 9.4737 | 16.8973 | 3.6589 | 3.7647 | 0.6 | 8.3333 | 0.1 | 20 | 35
| 50 | 0.4 | 10 | 9 | 16.1024 | 2.3024 | 4.8 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 51 | 1 | 4 | 18 | 28.0913 | 3.4706 | 6.6207 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 52 | 0.4 | 10 | 18 | 27.1782 | 4.4952 | 4.6829 | 1 | 5 | 0.1 | 20 | 35
| 53 | 0.8 | 5 | 10.5882 | 18.3852 | 2.6077 | 5.1892 | 1 | 5 | 0.1 | 20 | 30
| 54 | 0.6 | 6.6667 | 11.7391 | 17.6452 | 2.5376 | 3.3684 | 1 | 5 | 0.6 | 3.3333 | 15
| 55 | 1.4 | 2.8571 | 16.3636 | 25.7072 | 4.2909 | 5.0526 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 56 | 1.6 | 2.5 | 10.3846 | 18.825 | 2.6222 | 5.8182 | 0.8 | 6.25 | 0.8 | 2.5 | 11.25
| 57 | 0.4 | 10 | 14.2105 | 23.1875 | 4.177 | 4.8 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 58 | 1 | 4 | 11.25 | 18.6425 | 3.1258 | 4.2667 | 1.6 | 3.125 | 0.2 | 10 | 17.125
| 59 | 0.6 | 6.6667 | 12 | 19.3598 | 3.8689 | 3.4909 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 60 | 0.8 | 5 | 15.4286 | 22.8174 | 3.5489 | 3.84 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 61 | 0.4 | 10 | 12.2727 | 19.6762 | 2.0702 | 5.3333 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 62 | 0.8 | 5 | 12 | 19.5965 | 3.2329 | 4.3636 | 1 | 5 | 1 | 2 | 12
| 63 | 1.2 | 3.3333 | 8.8525 | 16.2816 | 3.8065 | 3.6226 | 1.4 | 3.5714 | 0.8 | 2.5 | 9.4048
| 64 | 1 | 4 | 18.6207 | 27.3856 | 3.5758 | 5.1892 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 65 | 1 | 4 | 9.8182 | 19.5697 | 3.9333 | 5.8182 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 66 | 1 | 4 | 9.4737 | 17.9328 | 3.1258 | 5.3333 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 67 | 1.2 | 3.3333 | 13.1707 | 21.9149 | 2.7442 | 6 | 1 | 5 | 0.1 | 20 | 28.3333
| 68 | 1.6 | 2.5 | 13.8462 | 21.9937 | 3.3475 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 11.6667
| 69 | 1 | 4 | 10.8 | 18.1719 | 3.1053 | 4.2667 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 70 | 0.4 | 10 | 10.8 | 18.8098 | 2.5241 | 5.4857 | 0.4 | 12.5 | 0.4 | 5 | 27.5
| 71 | 0.6 | 6.6667 | 12 | 19.698 | 3.2329 | 4.4651 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 72 | 0.6 | 6.6667 | 13.8462 | 23.057 | 3.2109 | 6 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 73 | 0.8 | 5 | 13.8462 | 23.2075 | 3.1678 | 6.1935 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 74 | 1 | 4 | 10.1887 | 18.3671 | 3.1258 | 5.0526 | 1.4 | 3.5714 | 0.1 | 20 | 27.5714
| 75 | 1.2 | 3.3333 | 16.875 | 27.4389 | 4.3704 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 76 | 1 | 4 | 9.8182 | 16.0182 | 2.36 | 3.84 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 77 | 0.6 | 6.6667 | 16.3636 | 24.5748 | 3.746 | 4.4651 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 78 | 0.4 | 10 | 11.25 | 17.5234 | 3.1258 | 3.1475 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 79 | 0.8 | 5 | 11.7391 | 19.0013 | 2.5792 | 4.6829 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 80 | 1.2 | 3.3333 | 18 | 23.4825 | 3.3007 | 2.1818 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 81 | 0.6 | 6.6667 | 16.3636 | 25.77 | 3.0064 | 6.4 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 82 | 1 | 4 | 14.2105 | 20.7466 | 3.0452 | 3.4909 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 83 | 0.8 | 5 | 12.2727 | 19.2428 | 3.2778 | 3.6923 | 1 | 5 | 0.4 | 5 | 15
| 84 | 0.8 | 5 | 13.5 | 19.8053 | 3.1053 | 3.2 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 85 | 1 | 4 | 15.8824 | 23.0819 | 3.0256 | 4.1739 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 86 | 1.2 | 3.3333 | 10.5882 | 19.0056 | 2.9317 | 5.4857 | 1.6 | 3.125 | 0.4 | 5 | 11.4583
| 87 | 1.2 | 3.3333 | 18.6207 | 28.0072 | 3.9008 | 5.4857 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.1667
| 88 | 0.4 | 10 | 11.0204 | 18.8121 | 2.4583 | 5.3333 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 89 | 0.6 | 6.6667 | 15 | 23.9136 | 2.9136 | 6 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 90 | 0.6 | 6.6667 | 11.7391 | 19.1249 | 3.3007 | 4.0851 | 1 | 5 | 0.6 | 3.3333 | 15
| 91 | 0.6 | 6.6667 | 12.8571 | 19.1756 | 2.95 | 3.3684 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 92 | 0.6 | 6.6667 | 14.2105 | 23.664 | 3.8065 | 5.6471 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 93 | 0.8 | 5 | 9.1525 | 18.0006 | 3.6589 | 5.1892 | 1 | 5 | 0.4 | 5 | 15
| 94 | 0.4 | 10 | 18 | 27.852 | 5.4884 | 4.3636 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 95 | 0.8 | 5 | 13.1707 | 19.5803 | 4.2523 | 2.1573 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 96 | 1 | 4 | 14.5946 | 22.0917 | 2.6971 | 4.8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 97 | 0.8 | 5 | 11.7391 | 20.3884 | 3.9664 | 4.6829 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 98 | 0.8 | 5 | 15.8824 | 25.5829 | 2.8434 | 6.8571 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 99 | 0.6 | 6.6667 | 7.8261 | 15.8401 | 3.5489 | 4.4651 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 100 | 1 | 4 | 11.7391 | 20.4709 | 2.9136 | 5.8182 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 101 | 0.8 | 5 | 10.3846 | 21.3331 | 3.8374 | 7.1111 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 102 | 0.2 | 20 | 9.8182 | 17.6793 | 3.776 | 4.0851 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 103 | 0.6 | 6.6667 | 12.5581 | 20.1513 | 3.9008 | 3.6923 | 1.4 | 3.5714 | 0.8 | 2.5 | 12.7381
| 104 | 0.4 | 10 | 12.8571 | 19.7821 | 3.085 | 3.84 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 105 | 1.2 | 3.3333 | 11.25 | 20.735 | 3.085 | 6.4 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 106 | 1 | 4 | 12 | 20.1597 | 2.8263 | 5.3333 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 107 | 1 | 4 | 16.3636 | 24.6272 | 3.2109 | 5.0526 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 108 | 0.4 | 10 | 15.8824 | 24.2997 | 2.9317 | 5.4857 | 1 | 5 | 0.4 | 5 | 20
| 109 | 0.6 | 6.6667 | 8.7097 | 16.8323 | 2.6369 | 5.4857 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 110 | 0.4 | 10 | 13.1707 | 21.0812 | 2.9873 | 4.9231 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 111 | 0.6 | 6.6667 | 12.2727 | 20.6364 | 4 | 4.3636 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 112 | 0.8 | 5 | 11.25 | 18.9929 | 3.2778 | 4.4651 | 1 | 5 | 0.2 | 10 | 20
| 113 | 0.8 | 5 | 15 | 22.9873 | 4.069 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 114 | 0.4 | 10 | 9.4737 | 16.0681 | 2.4205 | 4.1739 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 115 | 1 | 4 | 13.5 | 21.0224 | 3.5224 | 4 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 116 | 1.2 | 3.3333 | 12.8571 | 21.2687 | 2.5934 | 5.8182 | 1 | 5 | 0.4 | 5 | 13.3333
| 117 | 0.2 | 20 | 11.25 | 18.3415 | 3.0064 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 118 | 0.6 | 6.6667 | 11.4894 | 21.9792 | 3.1053 | 7.3846 | 1 | 5 | 0.6 | 3.3333 | 15
| 119 | 1.2 | 3.3333 | 11.25 | 19.9462 | 2.878 | 5.8182 | 1 | 5 | 0.1 | 20 | 28.3333
| 120 | 0.6 | 6.6667 | 25.7143 | 32.3512 | 2.6369 | 4 | 1.8 | 2.7778 | 0.4 | 5 | 14.4444
| 121 | 0.4 | 10 | 9.3103 | 15.4672 | 2.7283 | 3.4286 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 122 | 0.4 | 10 | 15 | 20.8447 | 2.6971 | 3.1475 | 1 | 5 | 0.2 | 10 | 25
| 123 | 1 | 4 | 13.8462 | 22.6474 | 2.6077 | 6.1935 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 124 | 1.4 | 2.8571 | 15 | 23.0109 | 3.2109 | 4.8 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 125 | 1.2 | 3.3333 | 13.5 | 20.0432 | 3.3957 | 3.1475 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 126 | 0.4 | 10 | 17.4194 | 24.5713 | 4.1043 | 3.0476 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 127 | 0.6 | 6.6667 | 11.7391 | 18.4069 | 3.0452 | 3.6226 | 1 | 5 | 0.2 | 10 | 21.6667
| 128 | 1.2 | 3.3333 | 11.4894 | 19.2905 | 2.878 | 4.9231 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 129 | 1 | 4 | 17.4194 | 23.9359 | 3.0256 | 3.4909 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 130 | 0.6 | 6.6667 | 10 | 17.1686 | 4.5385 | 2.6301 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 131 | 0.6 | 6.6667 | 10.1887 | 18.3871 | 2.5514 | 5.6471 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 132 | 1.2 | 3.3333 | 9.6429 | 17.2594 | 3.0452 | 4.5714 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 133 | 1 | 4 | 12.2727 | 19.8011 | 2.7283 | 4.8 | 1 | 5 | 0.4 | 5 | 14
| 134 | 1 | 4 | 10.3846 | 17.1221 | 3.0452 | 3.6923 | 1.6 | 3.125 | 0.6 | 3.3333 | 10.4583
| 135 | 0.6 | 6.6667 | 10.8 | 18.1943 | 2.4712 | 4.9231 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 136 | 0.8 | 5 | 12 | 21.5404 | 5.0753 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 137 | 0.8 | 5 | 12 | 20.7536 | 3.4203 | 5.3333 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 138 | 0.2 | 20 | 11.4894 | 17.6469 | 2.6667 | 3.4909 | 1 | 5 | 0.2 | 10 | 35
| 139 | 0.4 | 10 | 11.7391 | 20.0788 | 3.0064 | 5.3333 | 1 | 5 | 0.2 | 10 | 25
| 140 | 0.8 | 5 | 19.2857 | 25.8821 | 3.1678 | 3.4286 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 141 | 0.8 | 5 | 12.8571 | 18.831 | 2.8263 | 3.1475 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 142 | 0.8 | 5 | 14.2105 | 21.3057 | 3.2552 | 3.84 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 143 | 0.8 | 5 | 10 | 18.8097 | 3.3239 | 5.4857 | 1 | 5 | 0.2 | 10 | 20
| 144 | 0.6 | 6.6667 | 12.2727 | 20.6297 | 3.1678 | 5.1892 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 145 | 0.6 | 6.6667 | 15 | 21.4465 | 2.6818 | 3.7647 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 146 | 0.8 | 5 | 10.1887 | 17.5955 | 3.2329 | 4.1739 | 1.2 | 4.1667 | 1 | 2 | 11.1667
| 147 | 0.6 | 6.6667 | 13.5 | 21.1329 | 2.95 | 4.6829 | 1 | 5 | 0.2 | 10 | 21.6667
| 148 | 0.6 | 6.6667 | 10 | 17.2529 | 3.1678 | 4.0851 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 149 | 0.6 | 6.6667 | 10 | 16.8141 | 2.8957 | 3.9184 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 150 | 0.8 | 5 | 10.3846 | 18.0627 | 2.878 | 4.8 | 1.4 | 3.5714 | 0.8 | 2.5 | 11.0714
| 151 | 0.6 | 6.6667 | 9.8182 | 15.9933 | 2.1751 | 4 | 1 | 5 | 0.6 | 3.3333 | 15
| 152 | 0.4 | 10 | 22.5 | 28.499 | 3.0452 | 2.9538 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 153 | 0.8 | 5 | 15.4286 | 24.9984 | 2.7126 | 6.8571 | 1 | 5 | 0.8 | 2.5 | 12.5
| 154 | 0.8 | 5 | 13.8462 | 20.6642 | 2.5514 | 4.2667 | 1.4 | 3.5714 | 1 | 2 | 10.5714
| 155 | 0.6 | 6.6667 | 12.5581 | 19.8687 | 3.4706 | 3.84 | 1 | 5 | 0.6 | 3.3333 | 15
| 156 | 1.2 | 3.3333 | 9.6429 | 16.5052 | 3.3714 | 3.4909 | 1 | 5 | 0.1 | 20 | 28.3333
| 157 | 0.6 | 6.6667 | 15.8824 | 22.6103 | 3.1053 | 3.6226 | 1 | 5 | 0.1 | 20 | 31.6667
| 158 | 0.8 | 5 | 12.5581 | 18.0432 | 2.1166 | 3.3684 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 159 | 0.8 | 5 | 11.0204 | 20.2096 | 4 | 5.1892 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 160 | 1.2 | 3.3333 | 13.1707 | 20.351 | 2.9136 | 4.2667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 161 | 0.6 | 6.6667 | 12.5581 | 20.5652 | 2.36 | 5.6471 | 1.6 | 3.125 | 0.4 | 5 | 14.7917
| 162 | 0.8 | 5 | 11.25 | 20.9833 | 2.6222 | 7.1111 | 1.6 | 3.125 | 0.1 | 20 | 28.125
| 163 | 0.8 | 5 | 13.1707 | 21.2324 | 2.7283 | 5.3333 | 1 | 5 | 0.4 | 5 | 15
| 164 | 0.2 | 20 | 21.6 | 28.1812 | 3.0256 | 3.5556 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 165 | 0.8 | 5 | 9 | 17.1179 | 4.4952 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 166 | 1.4 | 2.8571 | 10 | 15.7709 | 3.2109 | 2.56 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 167 | 1 | 4 | 14.5946 | 20.9456 | 2.7283 | 3.6226 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 168 | 1.4 | 2.8571 | 9.4737 | 17.827 | 3.3007 | 5.0526 | 1.2 | 4.1667 | 0.1 | 20 | 27.0238
| 169 | 1.2 | 3.3333 | 9.8182 | 16.1906 | 2.6077 | 3.7647 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.1667
| 170 | 0.8 | 5 | 10 | 17.5103 | 3.0452 | 4.4651 | 1 | 5 | 0.2 | 10 | 20
| 171 | 0.6 | 6.6667 | 12.5581 | 21.3678 | 3.3239 | 5.4857 | 1 | 5 | 0.2 | 10 | 21.6667
| 172 | 0.8 | 5 | 9.6429 | 14.9294 | 2.7602 | 2.5263 | 0.4 | 12.5 | 0.6 | 3.3333 | 20.8333
| 173 | 1 | 4 | 12 | 22.878 | 2.878 | 8 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 174 | 1.4 | 2.8571 | 12.5581 | 17.0165 | 2.4583 | 2 | 1 | 5 | 0.4 | 5 | 12.8571
| 175 | 0.8 | 5 | 14.5946 | 21.9126 | 3.2329 | 4.0851 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 176 | 1.2 | 3.3333 | 10.3846 | 18.9541 | 4.1043 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 177 | 0.8 | 5 | 13.5 | 21.0224 | 3.5224 | 4 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 178 | 0.4 | 10 | 9 | 15.7063 | 3.2778 | 3.4286 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 179 | 0.6 | 6.6667 | 13.1707 | 22.8208 | 2.7929 | 6.8571 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 180 | 1.4 | 2.8571 | 14.5946 | 21.6106 | 2.216 | 4.8 | 0.6 | 8.3333 | 0.6 | 3.3333 | 14.5238
| 181 | 1.2 | 3.3333 | 14.5946 | 21.2202 | 3.7165 | 2.9091 | 1 | 5 | 0.4 | 5 | 13.3333
| 182 | 1.2 | 3.3333 | 16.3636 | 24.0531 | 2.6369 | 5.0526 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 183 | 1 | 4 | 8.8525 | 14.3716 | 3.0256 | 2.4935 | 1.8 | 2.7778 | 0.6 | 3.3333 | 10.1111
| 184 | 1 | 4 | 10.3846 | 15.8776 | 2.8263 | 2.6667 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 185 | 1 | 4 | 13.1707 | 19.1772 | 2.3838 | 3.6226 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 186 | 0.8 | 5 | 13.1707 | 23.1776 | 2.6222 | 7.3846 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 187 | 1.4 | 2.8571 | 12.5581 | 19.0355 | 2.7126 | 3.7647 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 188 | 0.8 | 5 | 17.4194 | 24.1967 | 2.5106 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 189 | 0.6 | 6.6667 | 23.4783 | 30.2572 | 2.8606 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 190 | 1.2 | 3.3333 | 14.5946 | 20.6204 | 3.3957 | 2.6301 | 1.6 | 3.125 | 0.2 | 10 | 16.4583
| 191 | 0.8 | 5 | 10.8 | 18.6291 | 2.7765 | 5.0526 | 1.6 | 3.125 | 0.1 | 20 | 28.125
| 192 | 1.2 | 3.3333 | 13.5 | 19.3855 | 2.9317 | 2.9538 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 193 | 0.6 | 6.6667 | 12 | 18.2125 | 3.0649 | 3.1475 | 1.4 | 3.5714 | 0.8 | 2.5 | 12.7381
| 194 | 1.2 | 3.3333 | 18 | 24.3786 | 2.95 | 3.4286 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 195 | 1 | 4 | 13.5 | 19.8048 | 3.3957 | 2.9091 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 196 | 0.8 | 5 | 12.2727 | 20.3032 | 3.3475 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 197 | 1 | 4 | 12 | 20.6391 | 2.4456 | 6.1935 | 1 | 5 | 0.2 | 10 | 19
| 198 | 0.6 | 6.6667 | 7.7143 | 15.7468 | 2.8434 | 5.1892 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 199 | 1.8 | 2.2222 | 12.8571 | 23.2171 | 2.36 | 8 | 1 | 5 | 0.1 | 20 | 27.2222
| 200 | 1 | 4 | 10.5882 | 16.9964 | 2.4082 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 201 | 0.8 | 5 | 7.9412 | 16.9442 | 2.8095 | 6.1935 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 202 | 0.8 | 5 | 8.3077 | 14.8053 | 2.5792 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 203 | 1.2 | 3.3333 | 12.2727 | 19.8315 | 4.4112 | 3.1475 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 204 | 0.8 | 5 | 12.2727 | 20.7916 | 4.2523 | 4.2667 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 205 | 1.2 | 3.3333 | 11.25 | 19.3709 | 2.9317 | 5.1892 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 206 | 0.4 | 10 | 12.8571 | 20.4835 | 2.8263 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 207 | 0.4 | 10 | 8.4375 | 15.1668 | 3.3007 | 3.4286 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 208 | 1.4 | 2.8571 | 20 | 26.4109 | 3.2109 | 3.2 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 209 | 1.2 | 3.3333 | 9.8182 | 16.6654 | 4.1043 | 2.7429 | 1.2 | 4.1667 | 0.1 | 20 | 27.5
| 210 | 1 | 4 | 8.4375 | 17.6267 | 4 | 5.1892 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 211 | 1.4 | 2.8571 | 12.5581 | 18.9234 | 2.2802 | 4.0851 | 1.6 | 3.125 | 0.4 | 5 | 10.9821
| 212 | 0.8 | 5 | 7.2 | 16.5686 | 2.9686 | 6.4 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 213 | 0.2 | 20 | 11.7391 | 19.4797 | 2.5514 | 5.1892 | 0.4 | 12.5 | 0.2 | 10 | 42.5
| 214 | 0.6 | 6.6667 | 15.4286 | 22.1351 | 3.6589 | 3.0476 | 0.4 | 12.5 | 0.2 | 10 | 29.1667
| 215 | 1 | 4 | 12 | 18.1367 | 2.8263 | 3.3103 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 216 | 0.6 | 6.6667 | 10.8 | 18.0871 | 3.5224 | 3.7647 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 217 | 1.2 | 3.3333 | 11.7391 | 17.2826 | 2.3959 | 3.1475 | 1 | 5 | 0.4 | 5 | 13.3333
| 218 | 1.2 | 3.3333 | 8.7097 | 14.9387 | 2.8606 | 3.3684 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 219 | 1 | 4 | 9.4737 | 16.55 | 2.7126 | 4.3636 | 1 | 5 | 0.8 | 2.5 | 11.5
| 220 | 1 | 4 | 14.2105 | 20.4333 | 2.9686 | 3.2542 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 221 | 0.6 | 6.6667 | 11.25 | 20.2186 | 2.9686 | 6 | 0.4 | 12.5 | 0.6 | 3.3333 | 22.5
| 222 | 0.8 | 5 | 14.5946 | 24.0435 | 3.6308 | 5.8182 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 223 | 0.6 | 6.6667 | 9.6429 | 15.5184 | 2.5652 | 3.3103 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 224 | 0.4 | 10 | 11.4894 | 17.208 | 2.8095 | 2.9091 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 225 | 1.4 | 2.8571 | 14.5946 | 20.9273 | 2.2476 | 4.0851 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 226 | 0.6 | 6.6667 | 11.7391 | 27.1735 | 4.7677 | 10.6667 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 227 | 0.6 | 6.6667 | 15 | 21.1817 | 3.085 | 3.0968 | 1.4 | 3.5714 | 0.8 | 2.5 | 12.7381
| 228 | 0.2 | 20 | 15.4286 | 22.1592 | 3.4203 | 3.3103 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 229 | 1 | 4 | 13.5 | 21.3374 | 3.8374 | 4 | 1 | 5 | 0.4 | 5 | 14
| 230 | 0.8 | 5 | 9.8182 | 16.2547 | 2.7442 | 3.6923 | 1 | 5 | 0.4 | 5 | 15
| 231 | 0.6 | 6.6667 | 11.25 | 19.2392 | 3.1892 | 4.8 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 232 | 0.4 | 10 | 16.3636 | 23.0262 | 2.7442 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 233 | 1 | 4 | 15.8824 | 24.773 | 2.6971 | 6.1935 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 234 | 0.4 | 10 | 11.4894 | 19.9293 | 2.7929 | 5.6471 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 235 | 0.2 | 20 | 8.0597 | 15.0641 | 2.433 | 4.5714 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 236 | 0.8 | 5 | 8.5714 | 15.5003 | 2.5652 | 4.3636 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 237 | 1 | 4 | 14.5946 | 21.8055 | 3.2109 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 238 | 1 | 4 | 11.0204 | 20.4013 | 2.7602 | 6.6207 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 239 | 1.4 | 2.8571 | 13.5 | 20.3459 | 2.5792 | 4.2667 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 240 | 1.2 | 3.3333 | 17.4194 | 26.8843 | 3.0649 | 6.4 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 241 | 1 | 4 | 12.2727 | 21.2437 | 3.3239 | 5.6471 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 242 | 0.6 | 6.6667 | 19.2857 | 27.1309 | 3.0452 | 4.8 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 243 | 1.2 | 3.3333 | 13.5 | 24.3049 | 3.4203 | 7.3846 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 244 | 0.4 | 10 | 14.2105 | 22.2317 | 2.9686 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 245 | 0.4 | 10 | 18.6207 | 25.1225 | 2.8095 | 3.6923 | 1 | 5 | 0.4 | 5 | 20
| 246 | 0.8 | 5 | 15 | 22.093 | 2.8263 | 4.2667 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 247 | 1 | 4 | 12.8571 | 19.4191 | 3.0064 | 3.5556 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 248 | 0.8 | 5 | 16.875 | 23.3989 | 3.3239 | 3.2 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 249 | 1.2 | 3.3333 | 15.4286 | 21.3923 | 2.4082 | 3.5556 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 250 | 0.6 | 6.6667 | 8.8525 | 16.6082 | 3.8374 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 251 | 0.8 | 5 | 12 | 18.8856 | 2.4205 | 4.4651 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 252 | 0.8 | 5 | 15.4286 | 24.1968 | 2.95 | 5.8182 | 1 | 5 | 0.4 | 5 | 15
| 253 | 1.2 | 3.3333 | 18 | 25.7479 | 3.0649 | 4.6829 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 254 | 0.8 | 5 | 12.2727 | 18.9391 | 2.8263 | 3.84 | 1 | 5 | 0.4 | 5 | 15
| 255 | 1.2 | 3.3333 | 16.875 | 22.799 | 2.7765 | 3.1475 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 256 | 1.2 | 3.3333 | 12.5581 | 19.5056 | 3.2552 | 3.6923 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 257 | 0.4 | 10 | 10.8 | 17.9107 | 3.0256 | 4.0851 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 258 | 0.6 | 6.6667 | 10.8 | 18.1432 | 2.878 | 4.4651 | 1 | 5 | 0.2 | 10 | 21.6667
| 259 | 1.4 | 2.8571 | 10.5882 | 20.3042 | 3.5224 | 6.1935 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 260 | 0.6 | 6.6667 | 15 | 21.3158 | 2.7602 | 3.5556 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 261 | 1 | 4 | 12.5581 | 20.8885 | 3.2778 | 5.0526 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 262 | 0.4 | 10 | 9 | 16.0005 | 2.6369 | 4.3636 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 263 | 1 | 4 | 12 | 20.357 | 3.1678 | 5.1892 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 264 | 0.8 | 5 | 12.8571 | 18.9039 | 2.95 | 3.0968 | 1 | 5 | 0.4 | 5 | 15
| 265 | 0.6 | 6.6667 | 16.3636 | 23.1744 | 2.6369 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 266 | 0.8 | 5 | 13.1707 | 19.2357 | 3.0649 | 3 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 267 | 0.8 | 5 | 7.2973 | 16.4408 | 2.95 | 6.1935 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 268 | 0.8 | 5 | 10.3846 | 20.8951 | 3.1258 | 7.3846 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 269 | 0.8 | 5 | 14.2105 | 21.1819 | 2.6077 | 4.3636 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 270 | 1.4 | 2.8571 | 9.4737 | 18.7931 | 3.1258 | 6.1935 | 1 | 5 | 0.4 | 5 | 12.8571
| 271 | 0.2 | 20 | 10.8 | 16.3761 | 2.6222 | 2.9538 | 1 | 5 | 0.4 | 5 | 30
| 272 | 1 | 4 | 15 | 22.9821 | 2.7929 | 5.1892 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 273 | 0.4 | 10 | 15.8824 | 24.995 | 2.7126 | 6.4 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 274 | 0.6 | 6.6667 | 11.4894 | 18.4518 | 2.4974 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 275 | 1 | 4 | 10.8 | 16.4507 | 3.1892 | 2.4615 | 0.2 | 25 | 0.4 | 5 | 34
| 276 | 1 | 4 | 15.4286 | 21.2342 | 2.5514 | 3.2542 | 1 | 5 | 0.2 | 10 | 19
| 277 | 0.6 | 6.6667 | 15.4286 | 23.3144 | 4.3303 | 3.5556 | 0.6 | 8.3333 | 1 | 2 | 17
| 278 | 0.8 | 5 | 13.8462 | 19.3909 | 2.878 | 2.6667 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 279 | 1 | 4 | 16.3636 | 22.8089 | 3.4453 | 3 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 280 | 0.4 | 10 | 15.4286 | 23.1155 | 3.4203 | 4.2667 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 281 | 0.8 | 5 | 10 | 16.8601 | 2.5934 | 4.2667 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 282 | 1.6 | 2.5 | 14.5946 | 21.7446 | 3.0649 | 4.0851 | 0.8 | 6.25 | 0.2 | 10 | 18.75
| 283 | 0.8 | 5 | 10.3846 | 20.3206 | 2.5514 | 7.3846 | 1 | 5 | 0.2 | 10 | 20
| 284 | 0.8 | 5 | 11.7391 | 20.2997 | 3.3714 | 5.1892 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 285 | 0.6 | 6.6667 | 18 | 25.6142 | 3.3475 | 4.2667 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 286 | 0.8 | 5 | 13.5 | 20.3866 | 2.7126 | 4.1739 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 287 | 0.4 | 10 | 17.4194 | 27.4262 | 2.8957 | 7.1111 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 288 | 0.4 | 10 | 11.0204 | 18.8532 | 3.6589 | 4.1739 | 1.6 | 3.125 | 0.4 | 5 | 18.125
| 289 | 0.2 | 20 | 15.4286 | 21.386 | 2.8606 | 3.0968 | 1 | 5 | 0.2 | 10 | 35
| 290 | 0.2 | 20 | 12.5581 | 21.0181 | 4.7677 | 3.6923 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 291 | 1 | 4 | 13.8462 | 20.2064 | 2.9317 | 3.4286 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 292 | 0.2 | 20 | 10 | 17.5263 | 2.8434 | 4.6829 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 293 | 1 | 4 | 8.7097 | 14.6995 | 3.4963 | 2.4935 | 1 | 5 | 0.2 | 10 | 19
| 294 | 1.2 | 3.3333 | 11.7391 | 20.453 | 2.8957 | 5.8182 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 295 | 0.8 | 5 | 11.25 | 17.9522 | 3.1467 | 3.5556 | 1 | 5 | 0.1 | 20 | 30
| 296 | 0.6 | 6.6667 | 13.1707 | 21.6517 | 4.2143 | 4.2667 | 1 | 5 | 0.1 | 20 | 31.6667
| 297 | 0.4 | 10 | 10 | 15.2139 | 2.3483 | 2.8657 | 1 | 5 | 0.4 | 5 | 20
| 298 | 0.6 | 6.6667 | 16.875 | 23.9857 | 3.0256 | 4.0851 | 1 | 5 | 0.1 | 20 | 31.6667
| 299 | 1 | 4 | 13.5 | 21.0023 | 2.5792 | 4.9231 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 300 | 1.2 | 3.3333 | 9.6429 | 20.0029 | 2.36 | 8 | 0.4 | 12.5 | 0.4 | 5 | 20.8333
| 301 | 0.2 | 20 | 12.8571 | 19.3309 | 3.0452 | 3.4286 | 1 | 5 | 0.4 | 5 | 30
| 302 | 0.8 | 5 | 18 | 29.0039 | 3.3239 | 7.68 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 303 | 1 | 4 | 8.1818 | 14.4186 | 3.1892 | 3.0476 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 304 | 1 | 4 | 11.4894 | 19.6322 | 2.8095 | 5.3333 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 305 | 1 | 4 | 16.3636 | 25.7395 | 4.4528 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 306 | 1.6 | 2.5 | 11.0204 | 17.3181 | 2.9873 | 3.3103 | 1 | 5 | 0.6 | 3.3333 | 10.8333
| 307 | 1.6 | 2.5 | 7.9412 | 15.9399 | 2.8095 | 5.1892 | 1 | 5 | 0.4 | 5 | 12.5
| 308 | 0.4 | 10 | 15.8824 | 25.0544 | 2.5514 | 6.6207 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 309 | 1 | 4 | 12.2727 | 19.9242 | 2.9686 | 4.6829 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 310 | 0.6 | 6.6667 | 15 | 22.15 | 3.0649 | 4.0851 | 1 | 5 | 0.6 | 3.3333 | 15
| 311 | 1 | 4 | 13.1707 | 22.7414 | 2.95 | 6.6207 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 312 | 0.8 | 5 | 8.1818 | 16.4456 | 2.4456 | 5.8182 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 313 | 0.8 | 5 | 12.5581 | 20.4706 | 3.5489 | 4.3636 | 1 | 5 | 0.1 | 20 | 30
| 314 | 0.6 | 6.6667 | 15.4286 | 20.8078 | 3.1467 | 2.2326 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 315 | 0.6 | 6.6667 | 16.875 | 24.5314 | 3.085 | 4.5714 | 1 | 5 | 0.2 | 10 | 21.6667
| 316 | 0.6 | 6.6667 | 10 | 17.0269 | 3.7165 | 3.3103 | 1 | 5 | 0.4 | 5 | 16.6667
| 317 | 0.8 | 5 | 13.1707 | 21.2714 | 3.3007 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 318 | 0.6 | 6.6667 | 10.5882 | 16.3145 | 2.8606 | 2.8657 | 1 | 5 | 0.2 | 10 | 21.6667
| 319 | 0.8 | 5 | 13.5 | 20.8085 | 2.8434 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 320 | 0.6 | 6.6667 | 14.2105 | 20.6262 | 2.4974 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 321 | 1.4 | 2.8571 | 12.5581 | 24.183 | 4.7677 | 6.8571 | 1 | 5 | 0.1 | 20 | 27.8571
| 322 | 1 | 4 | 8.1818 | 14.6809 | 2.3251 | 4.1739 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 323 | 1 | 4 | 14.5946 | 21.6966 | 2.6369 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 324 | 1 | 4 | 12.8571 | 23.2974 | 2.7602 | 7.68 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 325 | 1 | 4 | 12.5581 | 20.9015 | 3.4203 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 326 | 1.6 | 2.5 | 13.5 | 22.3362 | 3.1892 | 5.6471 | 1.2 | 4.1667 | 0.2 | 10 | 16.6667
| 327 | 0.4 | 10 | 10.1887 | 15.844 | 2.6077 | 3.0476 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 328 | 1 | 4 | 13.1707 | 19.0075 | 2.4082 | 3.4286 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 329 | 0.8 | 5 | 9.8182 | 15.9439 | 2.6971 | 3.4286 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 330 | 0.8 | 5 | 11.25 | 18.8102 | 2.7602 | 4.8 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 331 | 0.8 | 5 | 15.8824 | 29.3555 | 4.3303 | 9.1429 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 332 | 0.2 | 20 | 9.4737 | 17.0494 | 3.5758 | 4 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 333 | 0.8 | 5 | 15 | 21.8118 | 3.1892 | 3.6226 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 334 | 0.2 | 20 | 15 | 23.2204 | 3.1678 | 5.0526 | 0.6 | 8.3333 | 0.1 | 20 | 48.3333
| 335 | 1.2 | 3.3333 | 10.8 | 19.5499 | 2.9317 | 5.8182 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 336 | 0.4 | 10 | 13.8462 | 21.8673 | 2.9686 | 5.0526 | 1 | 5 | 0.2 | 10 | 25
| 337 | 0.8 | 5 | 11.0204 | 17.6666 | 3.2778 | 3.3684 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 338 | 0.6 | 6.6667 | 15.4286 | 22.8263 | 2.8263 | 4.5714 | 1 | 5 | 0.2 | 10 | 21.6667
| 339 | 0.4 | 10 | 11.0204 | 17.9997 | 2.7126 | 4.2667 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 340 | 1.2 | 3.3333 | 8.8525 | 16.4583 | 3.6875 | 3.9184 | 1 | 5 | 0.2 | 10 | 18.3333
| 341 | 0.4 | 10 | 15 | 22.3223 | 1.8366 | 5.4857 | 1 | 5 | 0.4 | 5 | 20
| 342 | 1.2 | 3.3333 | 10.1887 | 19.8943 | 3.085 | 6.6207 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.1667
| 343 | 1 | 4 | 15.4286 | 21.4826 | 3.0064 | 3.0476 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 344 | 0.6 | 6.6667 | 18.6207 | 24.5736 | 3.746 | 2.2069 | 1 | 5 | 0.4 | 5 | 16.6667
| 345 | 1 | 4 | 14.2105 | 19.9553 | 2.6971 | 3.0476 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 346 | 1 | 4 | 10.1887 | 18.7 | 3.0256 | 5.4857 | 0.4 | 12.5 | 0.2 | 10 | 26.5
| 347 | 0.6 | 6.6667 | 15 | 22.3363 | 3.4963 | 3.84 | 0.6 | 8.3333 | 1 | 2 | 17
| 348 | 0.6 | 6.6667 | 18 | 26.7176 | 2.5241 | 6.1935 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 349 | 1 | 4 | 10.1887 | 19.0321 | 2.8434 | 6 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 350 | 1.2 | 3.3333 | 15.4286 | 26.0952 | 2.6667 | 8 | 1.4 | 3.5714 | 0.8 | 2.5 | 9.4048
| 351 | 0.8 | 5 | 11.7391 | 18.4378 | 3.0064 | 3.6923 | 1 | 5 | 0.8 | 2.5 | 12.5
| 352 | 0.6 | 6.6667 | 10 | 17.4147 | 3.4963 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 353 | 0.6 | 6.6667 | 12 | 16.9879 | 2.878 | 2.1099 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 354 | 0.4 | 10 | 13.1707 | 20.8152 | 3.4706 | 4.1739 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 355 | 1 | 4 | 13.5 | 24.4578 | 3.2778 | 7.68 | 1 | 5 | 0.4 | 5 | 14
| 356 | 1.2 | 3.3333 | 13.1707 | 19.1857 | 2.5241 | 3.4909 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 357 | 0.4 | 10 | 11.7391 | 21.5927 | 3.2329 | 6.6207 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 358 | 0.6 | 6.6667 | 14.2105 | 21.7606 | 3.085 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 359 | 1 | 4 | 15.4286 | 22.3521 | 3.776 | 3.1475 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 360 | 1 | 4 | 13.5 | 20.0339 | 2.36 | 4.1739 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 361 | 1.4 | 2.8571 | 15 | 23.8814 | 3.3957 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 362 | 0.4 | 10 | 14.5946 | 22.1442 | 4.4528 | 3.0968 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 363 | 0.4 | 10 | 13.1707 | 18.7616 | 2.3366 | 3.2542 | 1 | 5 | 0.4 | 5 | 20
| 364 | 1 | 4 | 9.6429 | 17.79 | 3.5758 | 4.5714 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 365 | 1 | 4 | 12.5581 | 20.7282 | 3.8065 | 4.3636 | 1 | 5 | 0.2 | 10 | 19
| 366 | 1.2 | 3.3333 | 7.5 | 14.2717 | 2.9317 | 3.84 | 1 | 5 | 0.4 | 5 | 13.3333
| 367 | 1.2 | 3.3333 | 9.8182 | 17.0373 | 3.0452 | 4.1739 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 368 | 0.4 | 10 | 11.0204 | 19.5513 | 3.0452 | 5.4857 | 1 | 5 | 0.8 | 2.5 | 17.5
| 369 | 1.4 | 2.8571 | 12.5581 | 18.673 | 2.8606 | 3.2542 | 1.8 | 2.7778 | 0.2 | 10 | 15.6349
| 370 | 1 | 4 | 11.7391 | 18.2342 | 3.3475 | 3.1475 | 1 | 5 | 0.4 | 5 | 14
| 371 | 0.8 | 5 | 16.3636 | 22.5315 | 2.9136 | 3.2542 | 1 | 5 | 0.4 | 5 | 15
| 372 | 0.6 | 6.6667 | 13.8462 | 20.2951 | 2.8263 | 3.6226 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 373 | 0.2 | 20 | 9.8182 | 16.7487 | 2.2476 | 4.6829 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 374 | 0.4 | 10 | 11.4894 | 18.2411 | 2.6667 | 4.0851 | 1 | 5 | 0.2 | 10 | 25
| 375 | 0.6 | 6.6667 | 11.0204 | 19.0951 | 3.9008 | 4.1739 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 376 | 0.8 | 5 | 11.0204 | 23.8222 | 3.6589 | 9.1429 | 1 | 5 | 0.2 | 10 | 20
| 377 | 0.6 | 6.6667 | 13.1707 | 22.2498 | 2.4583 | 6.6207 | 1 | 5 | 0.2 | 10 | 21.6667
| 378 | 0.2 | 20 | 10.3846 | 16.2743 | 2.7929 | 3.0968 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 379 | 0.4 | 10 | 15.8824 | 21.8257 | 2.8957 | 3.0476 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 380 | 0.4 | 10 | 12 | 19.6952 | 4.4952 | 3.2 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 381 | 0.6 | 6.6667 | 13.1707 | 19.8713 | 2.8606 | 3.84 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 382 | 0.6 | 6.6667 | 9.8182 | 17.5301 | 3.4453 | 4.2667 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 383 | 0.8 | 5 | 12 | 22.5817 | 3.4706 | 7.1111 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 384 | 0.4 | 10 | 12.8571 | 22.5749 | 2.8606 | 6.8571 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 385 | 1.4 | 2.8571 | 12.2727 | 17.3699 | 2.6971 | 2.4 | 1.4 | 3.5714 | 0.4 | 5 | 11.4286
| 386 | 1.2 | 3.3333 | 9 | 15.1888 | 2.7602 | 3.4286 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 387 | 0.6 | 6.6667 | 8.0597 | 14.6111 | 2.5514 | 4 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 388 | 1.4 | 2.8571 | 12 | 18.2329 | 3.2329 | 3 | 1 | 5 | 0.2 | 10 | 17.8571
| 389 | 0.6 | 6.6667 | 11.7391 | 18.7394 | 2.8263 | 4.1739 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 390 | 1 | 4 | 11.4894 | 19.0422 | 3.1892 | 4.3636 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 391 | 0.8 | 5 | 12 | 20.7024 | 2.3024 | 6.4 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 392 | 1 | 4 | 12.2727 | 19.7942 | 3.3475 | 4.1739 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 393 | 0.8 | 5 | 15.4286 | 24.1768 | 2.3483 | 6.4 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 394 | 1 | 4 | 11.7391 | 20.1374 | 3.0649 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 395 | 1 | 4 | 14.2105 | 22.5502 | 3.0064 | 5.3333 | 1 | 5 | 0.2 | 10 | 19
| 396 | 0.6 | 6.6667 | 10.5882 | 20.5375 | 2.2692 | 7.68 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 397 | 1.2 | 3.3333 | 13.5 | 20.0619 | 3.0064 | 3.5556 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 398 | 0.8 | 5 | 15.4286 | 22.6186 | 2.8263 | 4.3636 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 399 | 1.2 | 3.3333 | 12.5581 | 21.1693 | 3.2778 | 5.3333 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 400 | 0.8 | 5 | 12.5581 | 19.8897 | 3.0649 | 4.2667 | 1.2 | 4.1667 | 1 | 2 | 11.1667
| 401 | 0.8 | 5 | 13.1707 | 20.5336 | 3.2778 | 4.0851 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 402 | 1 | 4 | 12 | 20.0026 | 2.95 | 5.0526 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.8333
| 403 | 0.8 | 5 | 11.25 | 21.4952 | 2.8606 | 7.3846 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 404 | 1.2 | 3.3333 | 14.5946 | 21.9333 | 3.4203 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 405 | 0.8 | 5 | 12.2727 | 18.4467 | 2.5514 | 3.6226 | 1 | 5 | 0.2 | 10 | 20
| 406 | 1 | 4 | 8.8525 | 16.0428 | 3.1053 | 4.0851 | 1 | 5 | 0.2 | 10 | 19
| 407 | 1 | 4 | 13.8462 | 22.3184 | 3.9008 | 4.5714 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.8333
| 408 | 0.8 | 5 | 15 | 22.4708 | 3.6308 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 409 | 1 | 4 | 8.7097 | 16.4597 | 2.95 | 4.8 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 410 | 0.6 | 6.6667 | 10.8 | 19.3376 | 2.5376 | 6 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 411 | 0.6 | 6.6667 | 10.5882 | 16.5375 | 2.4583 | 3.4909 | 1 | 5 | 0.6 | 3.3333 | 15
| 412 | 0.6 | 6.6667 | 11.4894 | 19.2776 | 3.1053 | 4.6829 | 1 | 5 | 0.2 | 10 | 21.6667
| 413 | 1 | 4 | 15.4286 | 21.7001 | 2.5792 | 3.6923 | 1 | 5 | 0.4 | 5 | 14
| 414 | 0.6 | 6.6667 | 10.5882 | 17.8479 | 2.3366 | 4.9231 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 415 | 0.4 | 10 | 14.5946 | 21.8095 | 2.0258 | 5.1892 | 1 | 5 | 0.4 | 5 | 20
| 416 | 1.2 | 3.3333 | 10.8 | 22.7524 | 2.8095 | 9.1429 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 417 | 1 | 4 | 11.25 | 17.5985 | 2.7929 | 3.5556 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 418 | 0.8 | 5 | 15.8824 | 20.6821 | 2.4583 | 2.3415 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 419 | 0.8 | 5 | 10.5882 | 18.1734 | 2.3959 | 5.1892 | 1 | 5 | 0.8 | 2.5 | 12.5
| 420 | 0.8 | 5 | 12.8571 | 23.7707 | 2.9136 | 8 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 421 | 1 | 4 | 14.2105 | 20.7477 | 2.6971 | 3.84 | 1.6 | 3.125 | 0.6 | 3.3333 | 10.4583
| 422 | 1 | 4 | 11.25 | 18.0906 | 2.6667 | 4.1739 | 1 | 5 | 0.2 | 10 | 19
| 423 | 1.2 | 3.3333 | 16.3636 | 25.1271 | 3.2778 | 5.4857 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 424 | 1.4 | 2.8571 | 12 | 19.5971 | 3.0256 | 4.5714 | 1.4 | 3.5714 | 0.4 | 5 | 11.4286
| 425 | 0.1 | 40 | 8.7097 | 17.4414 | 2.9136 | 5.8182 | 1 | 5 | 0.6 | 3.3333 | 48.3333
| 426 | 1.4 | 2.8571 | 16.3636 | 22.9903 | 2.36 | 4.2667 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 427 | 1.2 | 3.3333 | 15 | 19.7982 | 2.3366 | 2.4615 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 428 | 1 | 4 | 12.8571 | 22.0038 | 3.1467 | 6 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 429 | 0.8 | 5 | 8.1818 | 14.8619 | 3.1892 | 3.4909 | 1 | 5 | 0.2 | 10 | 20
| 430 | 1 | 4 | 9.4737 | 16.2845 | 2.6369 | 4.1739 | 1 | 5 | 0.4 | 5 | 14
| 431 | 1.4 | 2.8571 | 12.8571 | 20.1335 | 2.5934 | 4.6829 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 432 | 0.6 | 6.6667 | 9.8182 | 17.1053 | 3.5224 | 3.7647 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 433 | 1.6 | 2.5 | 11.7391 | 20.8705 | 2.5106 | 6.6207 | 1.4 | 3.5714 | 0.4 | 5 | 11.0714
| 434 | 0.8 | 5 | 8.5714 | 17.9214 | 2.95 | 6.4 | 1 | 5 | 0.2 | 10 | 20
| 435 | 1.2 | 3.3333 | 27 | 35.0934 | 2.6077 | 5.4857 | 1 | 5 | 0.2 | 10 | 18.3333
| 436 | 0.6 | 6.6667 | 13.8462 | 22.0021 | 3.2329 | 4.9231 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 437 | 1.2 | 3.3333 | 12.8571 | 19.6956 | 3.3475 | 3.4909 | 1 | 5 | 0.2 | 10 | 18.3333
| 438 | 0.6 | 6.6667 | 13.1707 | 20.0743 | 2.6369 | 4.2667 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 439 | 0.6 | 6.6667 | 16.875 | 25.45 | 3.5224 | 5.0526 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 440 | 0.6 | 6.6667 | 12 | 20.2645 | 3.9008 | 4.3636 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 441 | 0.8 | 5 | 13.1707 | 18.5459 | 2.9136 | 2.4615 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 442 | 1.2 | 3.3333 | 10.1887 | 17.192 | 3.085 | 3.9184 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 443 | 1.2 | 3.3333 | 13.8462 | 21.5357 | 2.6369 | 5.0526 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 444 | 0.8 | 5 | 11.4894 | 18.0587 | 2.4842 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 445 | 0.4 | 10 | 8.0597 | 15.269 | 2.7442 | 4.4651 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 446 | 1 | 4 | 10.1887 | 15.9606 | 3.1053 | 2.6667 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 447 | 1.2 | 3.3333 | 13.5 | 22.2312 | 2.5376 | 6.1935 | 1 | 5 | 0.4 | 5 | 13.3333
| 448 | 0.8 | 5 | 14.5946 | 22.9083 | 2.6667 | 5.6471 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 449 | 0.6 | 6.6667 | 15.4286 | 22.1466 | 2.878 | 3.84 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 450 | 0.6 | 6.6667 | 15 | 23.2009 | 3.2778 | 4.9231 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 451 | 0.2 | 20 | 10 | 16.2641 | 2.8957 | 3.3684 | 1 | 5 | 0.1 | 20 | 45
| 452 | 0.2 | 20 | 11.7391 | 18.0191 | 3.5758 | 2.7042 | 1 | 5 | 0.2 | 10 | 35
| 453 | 0.6 | 6.6667 | 13.1707 | 21.8456 | 3.1892 | 5.4857 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 454 | 0.6 | 6.6667 | 16.875 | 24.1093 | 2.5514 | 4.6829 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 455 | 0.8 | 5 | 10.1887 | 15.9574 | 2.4583 | 3.3103 | 1 | 5 | 0.4 | 5 | 15
| 456 | 0.1 | 40 | 9.4737 | 17.3386 | 3.0649 | 4.8 | 1.4 | 3.5714 | 0.8 | 2.5 | 46.0714
| 457 | 1.4 | 2.8571 | 11.4894 | 17.9255 | 3.1258 | 3.3103 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 458 | 0.2 | 20 | 13.1707 | 19.9607 | 2.95 | 3.84 | 1 | 5 | 0.2 | 10 | 35
| 459 | 0.8 | 5 | 11.0204 | 17.5155 | 3.3475 | 3.1475 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 460 | 1.2 | 3.3333 | 13.8462 | 19.75 | 2.3483 | 3.5556 | 1 | 5 | 0.4 | 5 | 13.3333
| 461 | 1.2 | 3.3333 | 10 | 16.5183 | 2.8957 | 3.6226 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 462 | 1.2 | 3.3333 | 11.7391 | 19.94 | 3.2778 | 4.9231 | 1 | 5 | 0.4 | 5 | 13.3333
| 463 | 0.4 | 10 | 10.5882 | 18.6684 | 3.7165 | 4.3636 | 1 | 5 | 0.4 | 5 | 20
| 464 | 0.6 | 6.6667 | 16.875 | 25.6847 | 3.3239 | 5.4857 | 1 | 5 | 0.1 | 20 | 31.6667
| 465 | 0.8 | 5 | 15.4286 | 26.1728 | 2.7442 | 8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 466 | 0.8 | 5 | 9.8182 | 17.0296 | 3.3714 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 467 | 1 | 4 | 16.3636 | 23.3093 | 2.8606 | 4.0851 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 468 | 0.8 | 5 | 12.8571 | 22.7399 | 3.0256 | 6.8571 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 469 | 1.2 | 3.3333 | 10.8 | 18.2982 | 2.4456 | 5.0526 | 1 | 5 | 1 | 2 | 10.3333
| 470 | 1.4 | 2.8571 | 10 | 17.4895 | 3.1258 | 4.3636 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 471 | 0.8 | 5 | 14.2105 | 21.2699 | 3.6308 | 3.4286 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 472 | 0.6 | 6.6667 | 10 | 18.5535 | 2.36 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 15
| 473 | 0.8 | 5 | 11.25 | 20.2434 | 2.5934 | 6.4 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 474 | 1.4 | 2.8571 | 12.8571 | 18.556 | 2.5514 | 3.1475 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 475 | 0.6 | 6.6667 | 11.7391 | 17.5015 | 3.1678 | 2.5946 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 476 | 1 | 4 | 13.1707 | 19.0964 | 2.878 | 3.0476 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 477 | 0.4 | 10 | 14.2105 | 21.862 | 2.9686 | 4.6829 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 478 | 1.4 | 2.8571 | 11.0204 | 18.7701 | 3.5758 | 4.1739 | 1 | 5 | 0.4 | 5 | 12.8571
| 479 | 0.6 | 6.6667 | 7.9412 | 19.0169 | 3.3957 | 7.68 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 480 | 0.8 | 5 | 16.875 | 26.3114 | 2.5792 | 6.8571 | 1 | 5 | 0.2 | 10 | 20
| 481 | 1.6 | 2.5 | 9.3103 | 19.6085 | 2.9136 | 7.3846 | 0.8 | 6.25 | 0.2 | 10 | 18.75
| 482 | 1.2 | 3.3333 | 12.5581 | 20.3418 | 2.8606 | 4.9231 | 1.6 | 3.125 | 0.4 | 5 | 11.4583
| 483 | 0.4 | 10 | 11.7391 | 20.3301 | 3.1053 | 5.4857 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 484 | 1.8 | 2.2222 | 12.8571 | 19.29 | 3.2329 | 3.2 | 0.8 | 6.25 | 0.6 | 3.3333 | 11.8056
| 485 | 1 | 4 | 12 | 19.5778 | 3.0064 | 4.5714 | 1 | 5 | 0.4 | 5 | 14
| 486 | 0.6 | 6.6667 | 11.25 | 17.0548 | 2.8957 | 2.9091 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 487 | 1 | 4 | 19.2857 | 25.7191 | 2.3483 | 4.0851 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 488 | 0.8 | 5 | 10 | 23.5759 | 3.4706 | 10.1053 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 489 | 1.4 | 2.8571 | 12.8571 | 21.1031 | 2.7602 | 5.4857 | 1.4 | 3.5714 | 0.1 | 20 | 26.4286
| 490 | 0.8 | 5 | 10.8 | 16.7392 | 2.5106 | 3.4286 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 491 | 1 | 4 | 13.1707 | 19.4708 | 2.9317 | 3.3684 | 1 | 5 | 0.2 | 10 | 19
| 492 | 0.4 | 10 | 14.5946 | 21.3069 | 2.4456 | 4.2667 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 493 | 1.2 | 3.3333 | 15.8824 | 24.2483 | 3.9008 | 4.4651 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 494 | 1.4 | 2.8571 | 12.5581 | 20.4671 | 4.069 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 495 | 0.8 | 5 | 8.5714 | 19.5127 | 2.5934 | 8.3478 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 496 | 0.6 | 6.6667 | 8.4375 | 17.8089 | 3.3714 | 6 | 1 | 5 | 0.4 | 5 | 16.6667
| 497 | 0.6 | 6.6667 | 17.4194 | 27.0328 | 3.9664 | 5.6471 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 498 | 2 | 2 | 14.2105 | 19.4774 | 2.5241 | 2.7429 | 1 | 5 | 0.4 | 5 | 12
| 499 | 1.2 | 3.3333 | 15.8824 | 27.1601 | 3.2778 | 8 | 1 | 5 | 0.2 | 10 | 18.3333
| 500 | 0.4 | 10 | 7.1053 | 13.8722 | 2.6818 | 4.0851 | 1 | 5 | 0.4 | 5 | 20
| 501 | 0.6 | 6.6667 | 8.1818 | 16.3221 | 3.9664 | 4.1739 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 502 | 0.6 | 6.6667 | 12.2727 | 22.2366 | 2.5792 | 7.3846 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 503 | 0.8 | 5 | 16.875 | 22.8142 | 2.5106 | 3.4286 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 504 | 1 | 4 | 18 | 23.8917 | 2.7442 | 3.1475 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 505 | 1 | 4 | 11.25 | 19.3427 | 2.4456 | 5.6471 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 506 | 0.6 | 6.6667 | 11.0204 | 18.2007 | 2.9136 | 4.2667 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 507 | 1 | 4 | 13.5 | 20.932 | 2.8606 | 4.5714 | 1 | 5 | 0.2 | 10 | 19
| 508 | 0.4 | 10 | 10.8 | 17.1221 | 2.237 | 4.0851 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 509 | 0.6 | 6.6667 | 15.8824 | 22.3696 | 2.9317 | 3.5556 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 510 | 1 | 4 | 15.4286 | 22.5454 | 2.6517 | 4.4651 | 1.6 | 3.125 | 0.6 | 3.3333 | 10.4583
| 511 | 0.6 | 6.6667 | 12.8571 | 21.3302 | 2.9873 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 512 | 0.4 | 10 | 10.5882 | 20.156 | 3.1678 | 6.4 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 513 | 0.4 | 10 | 9.6429 | 17.3773 | 2.6818 | 5.0526 | 1 | 5 | 0.8 | 2.5 | 17.5
| 514 | 0.4 | 10 | 10.5882 | 16.1816 | 2.5934 | 3 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 515 | 0.6 | 6.6667 | 11.4894 | 18.821 | 2.7602 | 4.5714 | 1 | 5 | 0.4 | 5 | 16.6667
| 516 | 1.4 | 2.8571 | 14.2105 | 20.5944 | 2.3838 | 4 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 517 | 1 | 4 | 9.8182 | 17.6055 | 2.9873 | 4.8 | 1 | 5 | 0.4 | 5 | 14
| 518 | 1 | 4 | 11.25 | 22.0562 | 2.4583 | 8.3478 | 1 | 5 | 0.2 | 10 | 19
| 519 | 1 | 4 | 12 | 20.1829 | 2.6971 | 5.4857 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 520 | 1 | 4 | 15.8824 | 22.2339 | 2.8606 | 3.4909 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 521 | 0.6 | 6.6667 | 10.5882 | 16.2091 | 2.5241 | 3.0968 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 522 | 1.2 | 3.3333 | 14.5946 | 21.1952 | 2.237 | 4.3636 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 523 | 0.2 | 20 | 11.7391 | 18.4099 | 2.2056 | 4.4651 | 1.2 | 4.1667 | 0.1 | 20 | 44.1667
| 524 | 1 | 4 | 9 | 15.8778 | 3.2552 | 3.6226 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 525 | 1 | 4 | 11.7391 | 21.1755 | 2.5792 | 6.8571 | 1 | 5 | 0.2 | 10 | 19
| 526 | 1 | 4 | 10.5882 | 16.9176 | 3.4203 | 2.9091 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 527 | 0.6 | 6.6667 | 11.0204 | 18.2616 | 3.5489 | 3.6923 | 1.6 | 3.125 | 0.8 | 2.5 | 12.2917
| 528 | 1.2 | 3.3333 | 10 | 15.4974 | 2.4974 | 3 | 1.4 | 3.5714 | 0.1 | 20 | 26.9048
| 529 | 0.6 | 6.6667 | 14.2105 | 20.1188 | 2.8606 | 3.0476 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 530 | 0.8 | 5 | 20.7692 | 28.927 | 2.9686 | 5.1892 | 1 | 5 | 0.4 | 5 | 15
| 531 | 0.4 | 10 | 16.875 | 22.9819 | 2.4842 | 3.6226 | 1 | 5 | 0.2 | 10 | 25
| 532 | 0.4 | 10 | 10 | 15.962 | 2.6517 | 3.3103 | 1 | 5 | 0.8 | 2.5 | 17.5
| 533 | 0.8 | 5 | 14.5946 | 22.9858 | 2.7442 | 5.6471 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 534 | 1 | 4 | 10.3846 | 18.7134 | 2.5106 | 5.8182 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 535 | 0.6 | 6.6667 | 12.5581 | 20.3769 | 2.8957 | 4.9231 | 1 | 5 | 0.4 | 5 | 16.6667
| 536 | 1.2 | 3.3333 | 17.4194 | 26.5851 | 3.3475 | 5.8182 | 1 | 5 | 0.1 | 20 | 28.3333
| 537 | 0.8 | 5 | 13.1707 | 20.3439 | 2.8095 | 4.3636 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 538 | 0.6 | 6.6667 | 13.5 | 19.1552 | 3.2552 | 2.4 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 539 | 0.4 | 10 | 16.3636 | 24.9752 | 3.1258 | 5.4857 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 540 | 1.4 | 2.8571 | 13.8462 | 19.8848 | 2.7283 | 3.3103 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 541 | 0.6 | 6.6667 | 14.2105 | 21.1644 | 3.1892 | 3.7647 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 542 | 1 | 4 | 11.0204 | 16.9718 | 2.6971 | 3.2542 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 543 | 0.6 | 6.6667 | 11.7391 | 19.9981 | 3.6875 | 4.5714 | 1 | 5 | 0.2 | 10 | 21.6667
| 544 | 0.8 | 5 | 10.3846 | 16.8789 | 3.1258 | 3.3684 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 545 | 1.4 | 2.8571 | 10.3846 | 20.2299 | 3.4453 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 546 | 0.8 | 5 | 11.25 | 19.8615 | 3.1258 | 5.4857 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 547 | 1.2 | 3.3333 | 12.8571 | 19.4966 | 3.2109 | 3.4286 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 548 | 0.8 | 5 | 11.4894 | 18.5002 | 2.7442 | 4.2667 | 0.8 | 6.25 | 1 | 2 | 13.25
| 549 | 1 | 4 | 16.3636 | 23.2194 | 2.6818 | 4.1739 | 1 | 5 | 0.1 | 20 | 29
| 550 | 1.6 | 2.5 | 9.8182 | 23.1126 | 3.1892 | 10.1053 | 1.4 | 3.5714 | 0.6 | 3.3333 | 9.4048
| 551 | 0.8 | 5 | 18 | 24.2839 | 2.7283 | 3.5556 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 552 | 0.6 | 6.6667 | 10 | 18.7115 | 3.6589 | 5.0526 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 553 | 0.2 | 20 | 15.4286 | 25.5409 | 3.2552 | 6.8571 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 554 | 1 | 4 | 10.3846 | 17.644 | 2.8957 | 4.3636 | 1 | 5 | 0.2 | 10 | 19
| 555 | 0.8 | 5 | 9 | 19.1563 | 3.0452 | 7.1111 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 556 | 0.6 | 6.6667 | 11.0204 | 18.9903 | 2.4842 | 5.4857 | 1 | 5 | 0.4 | 5 | 16.6667
| 557 | 0.8 | 5 | 12.2727 | 20.3032 | 2.6971 | 5.3333 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 558 | 0.6 | 6.6667 | 10 | 17.9832 | 3.7165 | 4.2667 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 559 | 0.4 | 10 | 14.5946 | 21.2315 | 2.6369 | 4 | 1 | 5 | 0.2 | 10 | 25
| 560 | 0.6 | 6.6667 | 11.4894 | 17.9867 | 2.4974 | 4 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 561 | 1.2 | 3.3333 | 14.5946 | 23.658 | 4.1404 | 4.9231 | 1 | 5 | 0.2 | 10 | 18.3333
| 562 | 0.6 | 6.6667 | 12 | 16.797 | 2.237 | 2.56 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 563 | 0.8 | 5 | 9.3103 | 18.3184 | 3.5224 | 5.4857 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 564 | 0.8 | 5 | 14.5946 | 20.8555 | 3.6308 | 2.6301 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 565 | 1.4 | 2.8571 | 12.2727 | 20.4119 | 2.95 | 5.1892 | 1 | 5 | 0.2 | 10 | 17.8571
| 566 | 1 | 4 | 8.8525 | 15.6788 | 2.8263 | 4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 567 | 1.2 | 3.3333 | 10.8 | 19.1638 | 2.878 | 5.4857 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 568 | 0.6 | 6.6667 | 8.3077 | 15.1733 | 3.0256 | 3.84 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 569 | 0.4 | 10 | 15.8824 | 25.004 | 4.069 | 5.0526 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 570 | 1 | 4 | 13.5 | 22.3438 | 3.0256 | 5.8182 | 1 | 5 | 0.2 | 10 | 19
| 571 | 0.6 | 6.6667 | 14.5946 | 21.755 | 3.3957 | 3.7647 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 572 | 0.2 | 20 | 10.1887 | 16.6942 | 2.95 | 3.5556 | 1.4 | 3.5714 | 0.2 | 10 | 33.5714
| 573 | 1 | 4 | 9.1525 | 16.7377 | 2.3959 | 5.1892 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 574 | 0.6 | 6.6667 | 10.3846 | 18.2971 | 3.5489 | 4.3636 | 1 | 5 | 0.2 | 10 | 21.6667
| 575 | 1.2 | 3.3333 | 13.8462 | 20.7497 | 2.6369 | 4.2667 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 576 | 0.2 | 20 | 11.7391 | 18.0135 | 2.6517 | 3.6226 | 1.4 | 3.5714 | 0.2 | 10 | 33.5714
| 577 | 0.6 | 6.6667 | 16.3636 | 22.8747 | 3.6875 | 2.8235 | 1 | 5 | 0.1 | 20 | 31.6667
| 578 | 1 | 4 | 9 | 14.6249 | 3.0649 | 2.56 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 579 | 0.6 | 6.6667 | 16.3636 | 26.0796 | 3.5224 | 6.1935 | 1 | 5 | 0.2 | 10 | 21.6667
| 580 | 0.8 | 5 | 15.8824 | 25.2017 | 3.1258 | 6.1935 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 581 | 1.4 | 2.8571 | 10.5882 | 17.3785 | 2.3251 | 4.4651 | 0.6 | 8.3333 | 0.4 | 5 | 16.1905
| 582 | 1 | 4 | 20 | 27.4222 | 2.6222 | 4.8 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 583 | 0.6 | 6.6667 | 12.8571 | 18.622 | 2.5106 | 3.2542 | 1 | 5 | 0.2 | 10 | 21.6667
| 584 | 0.2 | 20 | 12 | 18.3167 | 3.0064 | 3.3103 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 585 | 0.8 | 5 | 9.1525 | 15.7084 | 3.0649 | 3.4909 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 586 | 1 | 4 | 9.3103 | 18.4329 | 3.9333 | 5.1892 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 587 | 0.8 | 5 | 14.5946 | 20.8327 | 2.8095 | 3.4286 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 588 | 0.6 | 6.6667 | 10.5882 | 19.1589 | 3.085 | 5.4857 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 589 | 0.8 | 5 | 15.4286 | 23.7406 | 2.8263 | 5.4857 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 590 | 1 | 4 | 11.7391 | 18.4091 | 3.5224 | 3.1475 | 1 | 5 | 0.4 | 5 | 14
| 591 | 0.4 | 10 | 8.7097 | 17.9875 | 3.2778 | 6 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 592 | 0.8 | 5 | 15 | 23.2469 | 2.9136 | 5.3333 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 593 | 1 | 4 | 10.3846 | 18.0452 | 2.8606 | 4.8 | 1 | 5 | 0.4 | 5 | 14
| 594 | 0.4 | 10 | 20 | 27.2603 | 3.4203 | 3.84 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 595 | 1 | 4 | 15.8824 | 22.3313 | 2.8263 | 3.6226 | 1 | 5 | 0.4 | 5 | 14
| 596 | 0.8 | 5 | 10.5882 | 18.0368 | 3.085 | 4.3636 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 597 | 1 | 4 | 13.5 | 21.2228 | 3.5489 | 4.1739 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 598 | 1.2 | 3.3333 | 11.7391 | 18.4572 | 2.878 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 599 | 0.6 | 6.6667 | 12.2727 | 19.3516 | 2.3959 | 4.6829 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 600 | 1 | 4 | 10.8 | 19.3261 | 3.6031 | 4.9231 | 1 | 5 | 0.1 | 20 | 29
| 601 | 0.6 | 6.6667 | 10 | 15.3674 | 2.4583 | 2.9091 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 602 | 1 | 4 | 15.8824 | 24.7128 | 2.6369 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 603 | 0.6 | 6.6667 | 21.6 | 27.0195 | 2.3719 | 3.0476 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 604 | 0.8 | 5 | 11.7391 | 18.7559 | 2.9317 | 4.0851 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 605 | 1 | 4 | 10.3846 | 16.5532 | 2.9686 | 3.2 | 1 | 5 | 0.2 | 10 | 19
| 606 | 1 | 4 | 10.8 | 18.8498 | 2.8606 | 5.1892 | 1.4 | 3.5714 | 0.1 | 20 | 27.5714
| 607 | 0.6 | 6.6667 | 13.1707 | 21.3911 | 3.1678 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 608 | 0.4 | 10 | 12.8571 | 23.3067 | 3.0649 | 7.3846 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 609 | 0.6 | 6.6667 | 9.3103 | 17.4012 | 3.1678 | 4.9231 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 610 | 0.4 | 10 | 9.8182 | 18.905 | 4.0342 | 5.0526 | 0.6 | 8.3333 | 0.8 | 2.5 | 20.8333
| 611 | 0.8 | 5 | 11.7391 | 18.4355 | 2.9317 | 3.7647 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 612 | 0.8 | 5 | 9.8182 | 16.799 | 2.8957 | 4.0851 | 1 | 5 | 0.2 | 10 | 20
| 613 | 1.2 | 3.3333 | 11.25 | 18.3739 | 2.7602 | 4.3636 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 614 | 1.4 | 2.8571 | 11.4894 | 19.6741 | 2.5376 | 5.6471 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 615 | 0.8 | 5 | 12 | 21.1435 | 2.95 | 6.1935 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 616 | 0.8 | 5 | 13.1707 | 18.7789 | 3.1467 | 2.4615 | 1 | 5 | 0.2 | 10 | 20
| 617 | 1.2 | 3.3333 | 15 | 22.7494 | 2.8263 | 4.9231 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 618 | 0.4 | 10 | 13.8462 | 19.6871 | 2.7442 | 3.0968 | 1 | 5 | 0.2 | 10 | 25
| 619 | 1 | 4 | 11.4894 | 18.4227 | 2.6667 | 4.2667 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 620 | 1 | 4 | 9 | 15.5576 | 2.7929 | 3.7647 | 1 | 5 | 0.4 | 5 | 14
| 621 | 0.8 | 5 | 11.7391 | 20.0336 | 3.1053 | 5.1892 | 1.2 | 4.1667 | 1 | 2 | 11.1667
| 622 | 1.4 | 2.8571 | 7.9412 | 13.5922 | 2.6971 | 2.9538 | 0.6 | 8.3333 | 0.8 | 2.5 | 13.6905
| 623 | 0.6 | 6.6667 | 18 | 27.1398 | 3.8065 | 5.3333 | 1 | 5 | 0.4 | 5 | 16.6667
| 624 | 0.6 | 6.6667 | 15.8824 | 23.9128 | 3.3475 | 4.6829 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 625 | 1.4 | 2.8571 | 11.7391 | 18.5208 | 2.6077 | 4.1739 | 0.6 | 8.3333 | 0.2 | 10 | 21.1905
| 626 | 1 | 4 | 11.7391 | 18.2763 | 2.6971 | 3.84 | 1 | 5 | 0.4 | 5 | 14
| 627 | 0.4 | 10 | 11.25 | 19.0807 | 2.4974 | 5.3333 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 628 | 1 | 4 | 10.1887 | 20.1925 | 3.1467 | 6.8571 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 629 | 0.6 | 6.6667 | 10.3846 | 16.6214 | 3.1892 | 3.0476 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 630 | 1 | 4 | 11.4894 | 20.2009 | 3.6589 | 5.0526 | 0.6 | 8.3333 | 1 | 2 | 14.3333
| 631 | 1.4 | 2.8571 | 10.5882 | 21.1652 | 4.177 | 6.4 | 1 | 5 | 0.2 | 10 | 17.8571
| 632 | 0.4 | 10 | 10.5882 | 20.7461 | 3.3007 | 6.8571 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 633 | 0.8 | 5 | 9.4737 | 15.9613 | 2.3137 | 4.1739 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 634 | 1.2 | 3.3333 | 11.25 | 16.2676 | 2.5241 | 2.4935 | 1 | 5 | 0.2 | 10 | 18.3333
| 635 | 0.6 | 6.6667 | 13.1707 | 20.8168 | 2.5934 | 5.0526 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 636 | 0.8 | 5 | 9.8182 | 17.3968 | 2.8957 | 4.6829 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 637 | 0.6 | 6.6667 | 13.5 | 21.6706 | 4.2523 | 3.9184 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 638 | 1.2 | 3.3333 | 9 | 14.7303 | 2.7765 | 2.9538 | 0.4 | 12.5 | 0.4 | 5 | 20.8333
| 639 | 0.8 | 5 | 12.8571 | 25.0256 | 3.0256 | 9.1429 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 640 | 1.2 | 3.3333 | 10.1887 | 21.015 | 2.8263 | 8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 641 | 0.6 | 6.6667 | 13.8462 | 22.4249 | 2.9317 | 5.6471 | 1.6 | 3.125 | 0.2 | 10 | 19.7917
| 642 | 0.1 | 40 | 12.5581 | 19.6512 | 2.8263 | 4.2667 | 0.4 | 12.5 | 0.4 | 5 | 57.5
| 643 | 0.4 | 10 | 11.25 | 19.6136 | 4 | 4.3636 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 644 | 0.8 | 5 | 10.5882 | 17.1762 | 2.8957 | 3.6923 | 0.2 | 25 | 0.4 | 5 | 35
| 645 | 0.8 | 5 | 14.5946 | 20.8297 | 2.7442 | 3.4909 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 646 | 0.8 | 5 | 11.7391 | 22.4694 | 4.3303 | 6.4 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 647 | 1 | 4 | 9.6429 | 16.1579 | 3.1467 | 3.3684 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 648 | 0.8 | 5 | 14.2105 | 23.0707 | 2.6667 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 649 | 0.6 | 6.6667 | 10.8 | 17.042 | 2.9317 | 3.3103 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 650 | 0.8 | 5 | 9.4737 | 18.2117 | 3.5489 | 5.1892 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 651 | 0.6 | 6.6667 | 18.6207 | 25.0989 | 2.9873 | 3.4909 | 1 | 5 | 0.4 | 5 | 16.6667
| 652 | 0.6 | 6.6667 | 9.4737 | 15.8523 | 2.95 | 3.4286 | 0.4 | 12.5 | 0.6 | 3.3333 | 22.5
| 653 | 0.4 | 10 | 11.7391 | 18.9461 | 2.8434 | 4.3636 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 654 | 0.8 | 5 | 10.5882 | 23.3619 | 3.6308 | 9.1429 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 655 | 0.2 | 20 | 11.4894 | 18.5155 | 3.4706 | 3.5556 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 656 | 0.8 | 5 | 14.5946 | 21.2874 | 2.6077 | 4.0851 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 657 | 0.2 | 20 | 10.1887 | 17.7665 | 3.0064 | 4.5714 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 658 | 1.2 | 3.3333 | 11.7391 | 17.5618 | 2.9136 | 2.9091 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 659 | 0.4 | 10 | 15 | 23.1239 | 3.3239 | 4.8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 660 | 0.8 | 5 | 11.7391 | 22.147 | 4.2143 | 6.1935 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 661 | 1.2 | 3.3333 | 12.8571 | 20.2464 | 3.0256 | 4.3636 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 662 | 0.4 | 10 | 9.4737 | 19.3958 | 3.0649 | 6.8571 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 663 | 0.8 | 5 | 14.2105 | 22.7414 | 3.0452 | 5.4857 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 664 | 0.8 | 5 | 11.25 | 18.5732 | 4.069 | 3.2542 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 665 | 1.2 | 3.3333 | 12.8571 | 19.3992 | 3.4453 | 3.0968 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 666 | 0.8 | 5 | 12 | 19.8916 | 3.8065 | 4.0851 | 1 | 5 | 0.2 | 10 | 20
| 667 | 1 | 4 | 12.2727 | 19.4723 | 3.0256 | 4.1739 | 1 | 5 | 0.2 | 10 | 19
| 668 | 0.8 | 5 | 10.1887 | 19.2177 | 3.2109 | 5.8182 | 1 | 5 | 0.1 | 20 | 30
| 669 | 1.2 | 3.3333 | 11.4894 | 17.8267 | 2.4974 | 3.84 | 1.2 | 4.1667 | 0.1 | 20 | 27.5
| 670 | 1 | 4 | 11.25 | 18.7953 | 2.6222 | 4.9231 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.8333
| 671 | 0.6 | 6.6667 | 13.8462 | 20.1317 | 2.4456 | 3.84 | 1 | 5 | 0.4 | 5 | 16.6667
| 672 | 0.8 | 5 | 14.2105 | 20.653 | 2.5241 | 3.9184 | 1 | 5 | 0.2 | 10 | 20
| 673 | 1 | 4 | 18.6207 | 25.7654 | 2.878 | 4.2667 | 1.4 | 3.5714 | 0.8 | 2.5 | 10.0714
| 674 | 1 | 4 | 13.5 | 20.0007 | 3.3007 | 3.2 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 675 | 0.8 | 5 | 13.1707 | 19.0517 | 2.2584 | 3.6226 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 676 | 0.8 | 5 | 16.3636 | 23.8561 | 2.8095 | 4.6829 | 1 | 5 | 0.1 | 20 | 30
| 677 | 0.2 | 20 | 15.8824 | 26.6273 | 3.0649 | 7.68 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 678 | 0.6 | 6.6667 | 18 | 28.0068 | 2.8957 | 7.1111 | 1 | 5 | 0.2 | 10 | 21.6667
| 679 | 0.8 | 5 | 7.9412 | 13.3642 | 2.7929 | 2.6301 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 680 | 0.6 | 6.6667 | 38.5714 | 44.4316 | 2.7126 | 3.1475 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 681 | 1 | 4 | 14.5946 | 24.3912 | 3.6031 | 6.1935 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 682 | 0.4 | 10 | 9.3103 | 17.7324 | 3.2329 | 5.1892 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 683 | 0.8 | 5 | 8.7097 | 17.5034 | 3.1467 | 5.6471 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 684 | 1.2 | 3.3333 | 13.1707 | 20.2938 | 3.8689 | 3.2542 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 685 | 0.6 | 6.6667 | 11.4894 | 19.8081 | 3.3957 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 686 | 0.8 | 5 | 12.2727 | 18.1297 | 2.7602 | 3.0968 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 687 | 0.6 | 6.6667 | 12.8571 | 20.169 | 3.0452 | 4.2667 | 1 | 5 | 0.4 | 5 | 16.6667
| 688 | 1 | 4 | 8.4375 | 13.6113 | 2.5792 | 2.5946 | 1 | 5 | 0.2 | 10 | 19
| 689 | 0.8 | 5 | 16.3636 | 23.6639 | 2.2476 | 5.0526 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 690 | 0.4 | 10 | 20 | 28.1007 | 3.3007 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 691 | 0.4 | 10 | 15.8824 | 23.099 | 2.95 | 4.2667 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 692 | 0.4 | 10 | 13.1707 | 19.5203 | 3.3957 | 2.9538 | 1 | 5 | 0.2 | 10 | 25
| 693 | 1 | 4 | 11.4894 | 19.9251 | 2.95 | 5.4857 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 694 | 0.8 | 5 | 9.3103 | 17.9852 | 3.1892 | 5.4857 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 695 | 0.6 | 6.6667 | 13.5 | 21.2392 | 3.1678 | 4.5714 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 696 | 1.4 | 2.8571 | 11.25 | 18.2942 | 3.1258 | 3.9184 | 1 | 5 | 0.4 | 5 | 12.8571
| 697 | 0.6 | 6.6667 | 11.4894 | 17.8853 | 2.3959 | 4 | 1 | 5 | 0.4 | 5 | 16.6667
| 698 | 0.8 | 5 | 13.5 | 24.5275 | 3.3475 | 7.68 | 1 | 5 | 0.4 | 5 | 15
| 699 | 1.2 | 3.3333 | 12.5581 | 20.8287 | 3.4706 | 4.8 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 700 | 0.4 | 10 | 8.8525 | 16.3739 | 2.95 | 4.5714 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 701 | 0.4 | 10 | 11.7391 | 18.372 | 2.7929 | 3.84 | 1 | 5 | 0.4 | 5 | 20
| 702 | 1 | 4 | 14.2105 | 21.5422 | 2.7602 | 4.5714 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 703 | 1.6 | 2.5 | 12.2727 | 18.3179 | 3.0452 | 3 | 1.4 | 3.5714 | 0.2 | 10 | 16.0714
| 704 | 0.4 | 10 | 15.4286 | 22.9895 | 2.878 | 4.6829 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 705 | 1.2 | 3.3333 | 13.8462 | 25.818 | 2.3719 | 9.6 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 706 | 0.4 | 10 | 10.8 | 18.4876 | 3.3239 | 4.3636 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 707 | 1.2 | 3.3333 | 12.2727 | 17.7554 | 3.3957 | 2.087 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 708 | 0.8 | 5 | 9.8182 | 15.9318 | 2.9136 | 3.2 | 1.4 | 3.5714 | 0.1 | 20 | 28.5714
| 709 | 0.8 | 5 | 12.8571 | 20.3088 | 3.2778 | 4.1739 | 1 | 5 | 0.4 | 5 | 15
| 710 | 0.8 | 5 | 12 | 18.4027 | 3.2552 | 3.1475 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 711 | 0.6 | 6.6667 | 16.3636 | 22.7352 | 3.3239 | 3.0476 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 712 | 0.4 | 10 | 16.875 | 28.3203 | 3.4453 | 8 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 713 | 1.2 | 3.3333 | 13.5 | 20.5608 | 2.6971 | 4.3636 | 1 | 5 | 0.2 | 10 | 18.3333
| 714 | 1.4 | 2.8571 | 11.0204 | 21.6411 | 4 | 6.6207 | 1 | 5 | 0.4 | 5 | 12.8571
| 715 | 0.6 | 6.6667 | 15.4286 | 23.1202 | 4.069 | 3.6226 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 716 | 1 | 4 | 9.6429 | 15.9267 | 2.7283 | 3.5556 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 717 | 1.8 | 2.2222 | 14.2105 | 20.9108 | 2.3366 | 4.3636 | 1 | 5 | 0.6 | 3.3333 | 10.5556
| 718 | 0.8 | 5 | 13.8462 | 22.0664 | 3.4203 | 4.8 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 719 | 1.2 | 3.3333 | 13.8462 | 21.207 | 2.8957 | 4.4651 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 720 | 1.4 | 2.8571 | 11.25 | 18.6986 | 3.085 | 4.3636 | 0.6 | 8.3333 | 0.4 | 5 | 16.1905
| 721 | 1 | 4 | 12.5581 | 19.569 | 2.7442 | 4.2667 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 722 | 1.4 | 2.8571 | 10 | 17.0915 | 3.0064 | 4.0851 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 723 | 0.4 | 10 | 15 | 21.5339 | 2.36 | 4.1739 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 724 | 0.2 | 20 | 10.3846 | 18.8745 | 3.3007 | 5.1892 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 725 | 1.2 | 3.3333 | 15.4286 | 24.4713 | 3.3957 | 5.6471 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 726 | 0.8 | 5 | 13.1707 | 19.4999 | 2.6369 | 3.6923 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 727 | 1 | 4 | 12.2727 | 21.3377 | 3.0649 | 6 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 728 | 0.8 | 5 | 13.5 | 21.5283 | 3.1053 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 729 | 0.8 | 5 | 8.1818 | 15.5264 | 4.0342 | 3.3103 | 1 | 5 | 0.2 | 10 | 20
| 730 | 1.4 | 2.8571 | 18 | 28.558 | 2.878 | 7.68 | 0.4 | 12.5 | 0.4 | 5 | 20.3571
| 731 | 0.8 | 5 | 12.8571 | 18.665 | 2.7602 | 3.0476 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 732 | 0.6 | 6.6667 | 14.2105 | 22.4574 | 2.9136 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 733 | 1.2 | 3.3333 | 16.875 | 24.0833 | 2.6369 | 4.5714 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 734 | 0.8 | 5 | 13.1707 | 21.1816 | 3.2109 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 735 | 1 | 4 | 8.8525 | 18.2939 | 4.2523 | 5.1892 | 1 | 5 | 0.4 | 5 | 14
| 736 | 0.4 | 10 | 14.5946 | 22.3769 | 3.2109 | 4.5714 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 737 | 1 | 4 | 11.0204 | 18.6114 | 3.1258 | 4.4651 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 738 | 1.2 | 3.3333 | 9.1525 | 18.2058 | 4.3704 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 739 | 0.8 | 5 | 10 | 19.4487 | 3.2552 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 740 | 0.6 | 6.6667 | 12 | 17.037 | 2.6667 | 2.3704 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 741 | 1 | 4 | 12.8571 | 21.4518 | 2.7765 | 5.8182 | 1 | 5 | 0.4 | 5 | 14
| 742 | 0.6 | 6.6667 | 14.5946 | 21.698 | 2.4205 | 4.6829 | 0.4 | 12.5 | 0.2 | 10 | 29.1667
| 743 | 0.8 | 5 | 11.7391 | 19.6698 | 2.878 | 5.0526 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 744 | 1.2 | 3.3333 | 10.1887 | 17.5564 | 3.6031 | 3.7647 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 745 | 1.2 | 3.3333 | 11.7391 | 23.2281 | 4.1043 | 7.3846 | 0.4 | 12.5 | 0.4 | 5 | 20.8333
| 746 | 0.6 | 6.6667 | 15.8824 | 23.8082 | 3.1258 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 747 | 1 | 4 | 14.2105 | 20.8107 | 2.6818 | 3.9184 | 1 | 5 | 0.4 | 5 | 14
| 748 | 0.8 | 5 | 11.7391 | 18.2763 | 2.6971 | 3.84 | 1 | 5 | 0.4 | 5 | 15
| 749 | 0.8 | 5 | 13.5 | 21.5509 | 2.5652 | 5.4857 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 750 | 0.4 | 10 | 13.1707 | 18.5576 | 2.433 | 2.9538 | 1 | 5 | 0.4 | 5 | 20
| 751 | 0.6 | 6.6667 | 10.5882 | 16.2315 | 2.8606 | 2.7826 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 752 | 0.6 | 6.6667 | 13.5 | 23.6165 | 3.7165 | 6.4 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 753 | 0.6 | 6.6667 | 13.1707 | 25.4525 | 2.6818 | 9.6 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 754 | 0.8 | 5 | 12.2727 | 20.0222 | 2.8263 | 4.9231 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 755 | 1 | 4 | 11.4894 | 17.4048 | 3.0064 | 2.9091 | 1.4 | 3.5714 | 0.8 | 2.5 | 10.0714
| 756 | 0.8 | 5 | 10.8 | 18.1631 | 3.1892 | 4.1739 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 757 | 0.8 | 5 | 10 | 17.5314 | 3.1678 | 4.3636 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 758 | 0.4 | 10 | 7.8261 | 15.3232 | 2.6971 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 759 | 1 | 4 | 11.4894 | 17.6871 | 2.433 | 3.7647 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 760 | 1 | 4 | 11.4894 | 23.0143 | 4.1404 | 7.3846 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 761 | 0.8 | 5 | 14.2105 | 21.9735 | 3.4963 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 762 | 0.4 | 10 | 15.8824 | 22.0704 | 2.6971 | 3.4909 | 1 | 5 | 0.8 | 2.5 | 17.5
| 763 | 0.1 | 40 | 18.6207 | 27.7372 | 3.6308 | 5.4857 | 0.8 | 6.25 | 0.6 | 3.3333 | 49.5833
| 764 | 0.4 | 10 | 8.7097 | 15.5877 | 2.7929 | 4.0851 | 1 | 5 | 0.2 | 10 | 25
| 765 | 0.6 | 6.6667 | 14.2105 | 21.7715 | 2.878 | 4.6829 | 1 | 5 | 0.1 | 20 | 31.6667
| 766 | 0.6 | 6.6667 | 13.8462 | 19.5764 | 2.9873 | 2.7429 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 767 | 1 | 4 | 9 | 16.8548 | 2.9317 | 4.9231 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 768 | 1 | 4 | 16.3636 | 29.9439 | 2.9136 | 10.6667 | 1 | 5 | 0.2 | 10 | 19
| 769 | 0.8 | 5 | 14.5946 | 21.4538 | 3.5489 | 3.3103 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 770 | 0.6 | 6.6667 | 12 | 19.4148 | 2.8434 | 4.5714 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 771 | 1 | 4 | 12 | 18.9651 | 2.1651 | 4.8 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 772 | 0.4 | 10 | 11.7391 | 21.5634 | 3.6308 | 6.1935 | 1.6 | 3.125 | 0.4 | 5 | 18.125
| 773 | 0.6 | 6.6667 | 19.2857 | 30.8346 | 3.5489 | 8 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 774 | 0.6 | 6.6667 | 9.6429 | 19.9745 | 2.6517 | 7.68 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 775 | 0.6 | 6.6667 | 12.8571 | 20.7063 | 3.2778 | 4.5714 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 776 | 1 | 4 | 11.7391 | 19.5567 | 2.4842 | 5.3333 | 1 | 5 | 0.4 | 5 | 14
| 777 | 1 | 4 | 13.5 | 20.7109 | 3.2109 | 4 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 778 | 0.6 | 6.6667 | 13.8462 | 23.722 | 3.2552 | 6.6207 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 779 | 0.8 | 5 | 14.5946 | 22.3735 | 2.4456 | 5.3333 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 780 | 0.8 | 5 | 10.5882 | 18.8722 | 2.6369 | 5.6471 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 781 | 0.6 | 6.6667 | 11.0204 | 20.6845 | 3.4706 | 6.1935 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 782 | 1.4 | 2.8571 | 10 | 15.1835 | 2.36 | 2.8235 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 783 | 1.4 | 2.8571 | 12.5581 | 20.5253 | 3.3957 | 4.5714 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 784 | 0.6 | 6.6667 | 13.5 | 21.5543 | 4.2143 | 3.84 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 785 | 0.8 | 5 | 12.2727 | 19.3638 | 2.4082 | 4.6829 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 786 | 0.4 | 10 | 12 | 21.4377 | 4.1043 | 5.3333 | 0.4 | 12.5 | 0.4 | 5 | 27.5
| 787 | 0.8 | 5 | 12 | 18.4872 | 2.9317 | 3.5556 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 788 | 0.6 | 6.6667 | 11.4894 | 18.1288 | 3.2109 | 3.4286 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 789 | 1.2 | 3.3333 | 11.25 | 25.1375 | 2.5934 | 11.2941 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 790 | 1 | 4 | 9 | 17.3785 | 4.5385 | 3.84 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 791 | 1 | 4 | 14.2105 | 19.573 | 2.0522 | 3.3103 | 1 | 5 | 0.2 | 10 | 19
| 792 | 1 | 4 | 12.5581 | 18.2178 | 2.2913 | 3.3684 | 1 | 5 | 0.4 | 5 | 14
| 793 | 0.4 | 10 | 12.8571 | 21.395 | 3.9664 | 4.5714 | 1 | 5 | 0.2 | 10 | 25
| 794 | 0.8 | 5 | 14.5946 | 22.3057 | 3.3475 | 4.3636 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 795 | 0.8 | 5 | 12.2727 | 19.403 | 3.0452 | 4.0851 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 796 | 1.4 | 2.8571 | 12.8571 | 23.6424 | 3.1053 | 7.68 | 1 | 5 | 0.2 | 10 | 17.8571
| 797 | 0.2 | 20 | 12.8571 | 19.1596 | 2.3024 | 4 | 1 | 5 | 0.4 | 5 | 30
| 798 | 0.4 | 10 | 10.5882 | 19.5963 | 3.5224 | 5.4857 | 1.6 | 3.125 | 0.4 | 5 | 18.125
| 799 | 1.2 | 3.3333 | 9.6429 | 19.4527 | 3.1892 | 6.6207 | 1 | 5 | 0.4 | 5 | 13.3333
| 800 | 1 | 4 | 18 | 24.1148 | 2.8606 | 3.2542 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 801 | 0.6 | 6.6667 | 14.5946 | 22.3828 | 3.1053 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 802 | 0.4 | 10 | 15.8824 | 23.1893 | 2.3838 | 4.9231 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 803 | 0.8 | 5 | 11.7391 | 19.3362 | 3.0256 | 4.5714 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 804 | 0.6 | 6.6667 | 14.5946 | 22.3194 | 3.8065 | 3.9184 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 805 | 0.4 | 10 | 14.5946 | 22.0721 | 3.2109 | 4.2667 | 1.6 | 3.125 | 0.4 | 5 | 18.125
| 806 | 0.6 | 6.6667 | 14.2105 | 19.9542 | 2.878 | 2.8657 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 807 | 0.6 | 6.6667 | 12 | 20.3359 | 3.1467 | 5.1892 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 808 | 0.8 | 5 | 13.8462 | 21.2254 | 2.5792 | 4.8 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 809 | 0.2 | 20 | 12 | 17.6962 | 2.9136 | 2.7826 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 810 | 0.8 | 5 | 13.1707 | 20.2106 | 3.3475 | 3.6923 | 1.8 | 2.7778 | 0.4 | 5 | 12.7778
| 811 | 1 | 4 | 13.8462 | 21.4976 | 2.9686 | 4.6829 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 812 | 0.4 | 10 | 15.4286 | 27.8549 | 2.8263 | 9.6 | 1 | 5 | 1 | 2 | 17
| 813 | 0.1 | 40 | 11.0204 | 18.9598 | 3.5758 | 4.3636 | 0.8 | 6.25 | 0.1 | 20 | 66.25
| 814 | 0.4 | 10 | 13.1707 | 19.2477 | 2.237 | 3.84 | 1 | 5 | 0.4 | 5 | 20
| 815 | 1.2 | 3.3333 | 13.5 | 19.0067 | 3.0452 | 2.4615 | 1.2 | 4.1667 | 0.1 | 20 | 27.5
| 816 | 0.2 | 20 | 8.8525 | 18.5684 | 3.5224 | 6.1935 | 0.6 | 8.3333 | 0.8 | 2.5 | 30.8333
| 817 | 1.4 | 2.8571 | 12 | 20.134 | 3.2109 | 4.9231 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 818 | 0.4 | 10 | 16.875 | 21.5689 | 2.4082 | 2.2857 | 1.6 | 3.125 | 0.8 | 2.5 | 15.625
| 819 | 0.8 | 5 | 15 | 23.124 | 3.6589 | 4.4651 | 1 | 5 | 0.2 | 10 | 20
| 820 | 0.4 | 10 | 13.8462 | 20.6595 | 2.3483 | 4.4651 | 1.6 | 3.125 | 0.2 | 10 | 23.125
| 821 | 0.6 | 6.6667 | 13.5 | 23.1552 | 3.2552 | 6.4 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 822 | 0.6 | 6.6667 | 9.4737 | 16.1759 | 3.1467 | 3.5556 | 1 | 5 | 0.4 | 5 | 16.6667
| 823 | 0.6 | 6.6667 | 10.5882 | 17.8425 | 4 | 3.2542 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 824 | 1.2 | 3.3333 | 9 | 16.5251 | 4.0342 | 3.4909 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 825 | 0.4 | 10 | 12.2727 | 21.2587 | 3.1678 | 5.8182 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 826 | 1 | 4 | 11.0204 | 21.2573 | 3.1258 | 7.1111 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 827 | 0.4 | 10 | 10.8 | 18.8556 | 4.2909 | 3.7647 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 828 | 1 | 4 | 13.1707 | 21.8991 | 2.7283 | 6 | 1 | 5 | 0.2 | 10 | 19
| 829 | 0.8 | 5 | 18 | 26.0978 | 3.0452 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 830 | 0.4 | 10 | 11.25 | 21.5582 | 3.6875 | 6.6207 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 831 | 1.2 | 3.3333 | 13.8462 | 22.1766 | 3.2778 | 5.0526 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 832 | 0.6 | 6.6667 | 14.5946 | 20.9299 | 2.7126 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 833 | 0.8 | 5 | 11.25 | 19.1699 | 3.746 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 834 | 0.8 | 5 | 8.3077 | 19.3196 | 3.9008 | 7.1111 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 835 | 0.4 | 10 | 17.4194 | 23.1745 | 3.4963 | 2.2588 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 836 | 0.6 | 6.6667 | 12 | 18.9774 | 3.5489 | 3.4286 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 837 | 0.8 | 5 | 11.7391 | 25.3134 | 2.2802 | 11.2941 | 1.8 | 2.7778 | 0.8 | 2.5 | 10.2778
| 838 | 0.6 | 6.6667 | 10.1887 | 19.6736 | 3.085 | 6.4 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 839 | 1.4 | 2.8571 | 11.25 | 18.1377 | 2.5241 | 4.3636 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 840 | 0.6 | 6.6667 | 18.6207 | 25.0922 | 3.3239 | 3.1475 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 841 | 0.8 | 5 | 13.5 | 21.8719 | 2.3719 | 6 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 842 | 0.2 | 20 | 12.2727 | 18.8661 | 2.5934 | 4 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 843 | 0.8 | 5 | 13.1707 | 21.6296 | 3.6589 | 4.8 | 1 | 5 | 0.1 | 20 | 30
| 844 | 1 | 4 | 10.3846 | 20.1929 | 2.6971 | 7.1111 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 845 | 0.4 | 10 | 10.8 | 18.7664 | 3.9664 | 4 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 846 | 0.8 | 5 | 10.1887 | 17.5564 | 3.6031 | 3.7647 | 0.4 | 12.5 | 0.1 | 20 | 37.5
| 847 | 1.2 | 3.3333 | 12.2727 | 19.2167 | 3.0256 | 3.9184 | 0.8 | 6.25 | 0.8 | 2.5 | 12.0833
| 848 | 1 | 4 | 12 | 19.4988 | 3.8065 | 3.6923 | 1 | 5 | 0.2 | 10 | 19
| 849 | 0.6 | 6.6667 | 10.5882 | 22.0827 | 3.1467 | 8.3478 | 1 | 5 | 0.6 | 3.3333 | 15
| 850 | 1 | 4 | 16.875 | 22.663 | 3.0452 | 2.7429 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 851 | 0.2 | 20 | 8.4375 | 16.125 | 3.6875 | 4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 27.5
| 852 | 0.6 | 6.6667 | 10 | 18.9009 | 2.2802 | 6.6207 | 1 | 5 | 0.2 | 10 | 21.6667
| 853 | 1.2 | 3.3333 | 11.25 | 18.9316 | 2.3483 | 5.3333 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 854 | 0.4 | 10 | 12.2727 | 21.398 | 2.9317 | 6.1935 | 0.6 | 8.3333 | 0.1 | 20 | 38.3333
| 855 | 0.6 | 6.6667 | 9.3103 | 16.9467 | 3.0649 | 4.5714 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 856 | 0.4 | 10 | 11.25 | 18.6837 | 2.9686 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 857 | 1 | 4 | 12 | 19.0196 | 2.3366 | 4.6829 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 858 | 0.2 | 20 | 8.1818 | 14.9151 | 2.9686 | 3.7647 | 0.4 | 12.5 | 0.8 | 2.5 | 35
| 859 | 1.2 | 3.3333 | 9.6429 | 20.9224 | 2.9317 | 8.3478 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 860 | 0.2 | 20 | 10.1887 | 17.5209 | 2.9686 | 4.3636 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 861 | 0.6 | 6.6667 | 12.8571 | 19.667 | 3.0452 | 3.7647 | 1.6 | 3.125 | 0.2 | 10 | 19.7917
| 862 | 0.6 | 6.6667 | 16.3636 | 21.6921 | 3.1467 | 2.1818 | 1 | 5 | 0.6 | 3.3333 | 15
| 863 | 1.2 | 3.3333 | 13.8462 | 21.261 | 2.8434 | 4.5714 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 864 | 0.6 | 6.6667 | 12.2727 | 21.4011 | 2.7283 | 6.4 | 1 | 5 | 0.4 | 5 | 16.6667
| 865 | 0.4 | 10 | 18 | 26.0697 | 3.1467 | 4.9231 | 1 | 5 | 0.2 | 10 | 25
| 866 | 0.8 | 5 | 12.2727 | 20.1424 | 3.6031 | 4.2667 | 1.6 | 3.125 | 0.6 | 3.3333 | 11.4583
| 867 | 0.1 | 40 | 8.7097 | 15.2468 | 2.6971 | 3.84 | 0.6 | 8.3333 | 0.6 | 3.3333 | 51.6667
| 868 | 0.6 | 6.6667 | 16.3636 | 23.8303 | 2.6667 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 869 | 1.2 | 3.3333 | 16.875 | 22.1418 | 2.4842 | 2.7826 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 870 | 1 | 4 | 13.1707 | 20.1393 | 2.9686 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 871 | 0.6 | 6.6667 | 11.0204 | 18.7993 | 2.4456 | 5.3333 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 872 | 0.6 | 6.6667 | 15.4286 | 22.9412 | 2.7126 | 4.8 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 873 | 0.6 | 6.6667 | 12.2727 | 18.8166 | 3.4963 | 3.0476 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 874 | 1.4 | 2.8571 | 13.8462 | 24.4254 | 2.5792 | 8 | 0.6 | 8.3333 | 0.6 | 3.3333 | 14.5238
| 875 | 0.6 | 6.6667 | 14.2105 | 20.5458 | 2.7126 | 3.6226 | 0.4 | 12.5 | 0.6 | 3.3333 | 22.5
| 876 | 0.4 | 10 | 10 | 16.3514 | 2.433 | 3.9184 | 1 | 5 | 0.4 | 5 | 20
| 877 | 0.8 | 5 | 9.1525 | 15.6095 | 2.3719 | 4.0851 | 1 | 5 | 0.2 | 10 | 20
| 878 | 0.6 | 6.6667 | 13.1707 | 22.5752 | 3.2109 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 879 | 0.8 | 5 | 9.8182 | 16.9068 | 3.3239 | 3.7647 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 880 | 1.2 | 3.3333 | 12.5581 | 19.1545 | 3.1678 | 3.4286 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 881 | 0.8 | 5 | 15 | 20.872 | 3.1678 | 2.7042 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 882 | 0.6 | 6.6667 | 11.25 | 20.1071 | 3.3714 | 5.4857 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 883 | 0.6 | 6.6667 | 12.2727 | 22.3857 | 2.7283 | 7.3846 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 884 | 0.8 | 5 | 13.1707 | 25.5288 | 3.6308 | 8.7273 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 885 | 1.6 | 2.5 | 11.4894 | 21.8266 | 3.7165 | 6.6207 | 0.6 | 8.3333 | 0.2 | 10 | 20.8333
| 886 | 0.4 | 10 | 12.8571 | 20.0471 | 2.8263 | 4.3636 | 0.4 | 12.5 | 0.1 | 20 | 42.5
| 887 | 0.6 | 6.6667 | 18.6207 | 29.797 | 3.4963 | 7.68 | 1 | 5 | 0.4 | 5 | 16.6667
| 888 | 0.8 | 5 | 10 | 19.9624 | 3.1053 | 6.8571 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 889 | 1.2 | 3.3333 | 11.25 | 22.873 | 2.8957 | 8.7273 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 890 | 0.6 | 6.6667 | 13.8462 | 21.1848 | 3.4203 | 3.9184 | 1 | 5 | 0.4 | 5 | 16.6667
| 891 | 1 | 4 | 13.5 | 22.3097 | 3.3239 | 5.4857 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 892 | 1.2 | 3.3333 | 11.7391 | 21.1436 | 3.2109 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 893 | 1 | 4 | 12.8571 | 21.571 | 2.8957 | 5.8182 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 894 | 1.2 | 3.3333 | 9 | 16.4895 | 3.1258 | 4.3636 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 895 | 1.2 | 3.3333 | 12.8571 | 19.8084 | 3.3957 | 3.5556 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 896 | 0.6 | 6.6667 | 11.4894 | 20.543 | 2.433 | 6.6207 | 1 | 5 | 0.4 | 5 | 16.6667
| 897 | 1 | 4 | 18 | 25.2974 | 3.8065 | 3.4909 | 0.2 | 25 | 0.8 | 2.5 | 31.5
| 898 | 1.2 | 3.3333 | 8.7097 | 15.3156 | 2.9136 | 3.6923 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 899 | 0.8 | 5 | 15.4286 | 23.4426 | 3.5489 | 4.4651 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 900 | 0.8 | 5 | 15 | 21.3 | 2.6077 | 3.6923 | 0.6 | 8.3333 | 0.1 | 20 | 33.3333
| 901 | 0.8 | 5 | 10.1887 | 15.7681 | 2.0885 | 3.4909 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 902 | 0.6 | 6.6667 | 12.2727 | 18.718 | 3.4453 | 3 | 1 | 5 | 0.6 | 3.3333 | 15
| 903 | 0.2 | 20 | 15 | 22.2593 | 2.8957 | 4.3636 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 904 | 0.6 | 6.6667 | 15 | 21.995 | 2.7283 | 4.2667 | 1 | 5 | 0.4 | 5 | 16.6667
| 905 | 0.6 | 6.6667 | 12.8571 | 24.6883 | 4.72 | 7.1111 | 1 | 5 | 0.6 | 3.3333 | 15
| 906 | 0.6 | 6.6667 | 13.8462 | 21.0193 | 2.8095 | 4.3636 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 907 | 0.4 | 10 | 10.8 | 18.7126 | 2.5792 | 5.3333 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 908 | 0.2 | 20 | 9.1525 | 16.4218 | 3.9008 | 3.3684 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 909 | 0.4 | 10 | 16.875 | 25.4178 | 2.8957 | 5.6471 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 910 | 0.4 | 10 | 11.7391 | 19.5161 | 2.2913 | 5.4857 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 911 | 0.8 | 5 | 9.8182 | 16.8438 | 3.0256 | 4 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 912 | 1.4 | 2.8571 | 11.4894 | 18.2797 | 3.0256 | 3.7647 | 1 | 5 | 0.4 | 5 | 12.8571
| 913 | 0.6 | 6.6667 | 11.0204 | 18.1507 | 3.0452 | 4.0851 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 914 | 1.2 | 3.3333 | 11.7391 | 19.5273 | 2.3024 | 5.4857 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 915 | 1 | 4 | 12.5581 | 17.5818 | 2.4974 | 2.5263 | 1 | 5 | 0.4 | 5 | 14
| 916 | 0.4 | 10 | 10.3846 | 15.8872 | 2.6369 | 2.8657 | 0.6 | 8.3333 | 0.8 | 2.5 | 20.8333
| 917 | 0.6 | 6.6667 | 13.8462 | 22.2031 | 3.1678 | 5.1892 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 918 | 0.6 | 6.6667 | 15.4286 | 21.8275 | 2.8434 | 3.5556 | 1 | 5 | 0.4 | 5 | 16.6667
| 919 | 1 | 4 | 15.4286 | 22.4834 | 2.3719 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 920 | 1.2 | 3.3333 | 11.0204 | 19.799 | 3.4453 | 5.3333 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 921 | 0.6 | 6.6667 | 18.6207 | 24.955 | 2.8434 | 3.4909 | 1 | 5 | 0.2 | 10 | 21.6667
| 922 | 1 | 4 | 10 | 19.0836 | 4.72 | 4.3636 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 923 | 0.6 | 6.6667 | 16.3636 | 25.5176 | 4.5825 | 4.5714 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 924 | 0.4 | 10 | 9 | 15.3353 | 2.7126 | 3.6226 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 925 | 0.4 | 10 | 12.5581 | 17.9647 | 2.7765 | 2.6301 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 926 | 0.8 | 5 | 10 | 17.4594 | 2.7765 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 927 | 0.6 | 6.6667 | 10.3846 | 16.383 | 2.7442 | 3.2542 | 1.8 | 2.7778 | 0.4 | 5 | 14.4444
| 928 | 1 | 4 | 10 | 15.9306 | 3.0649 | 2.8657 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 929 | 0.6 | 6.6667 | 14.5946 | 23.2057 | 2.7929 | 5.8182 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 930 | 0.6 | 6.6667 | 13.1707 | 25.2821 | 2.9686 | 9.1429 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 931 | 0.8 | 5 | 12.8571 | 21.607 | 2.9317 | 5.8182 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 932 | 0.6 | 6.6667 | 13.8462 | 20.3338 | 2.3137 | 4.1739 | 1 | 5 | 0.4 | 5 | 16.6667
| 933 | 1.2 | 3.3333 | 15.4286 | 20.8454 | 2.7126 | 2.7042 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 934 | 1 | 4 | 14.2105 | 26.4474 | 2.6369 | 9.6 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 935 | 0.6 | 6.6667 | 9.4737 | 16.491 | 2.8434 | 4.1739 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 936 | 0.6 | 6.6667 | 14.2105 | 21.9663 | 3.8374 | 3.9184 | 0.4 | 12.5 | 0.2 | 10 | 29.1667
| 937 | 0.8 | 5 | 9.3103 | 16.5895 | 3.1053 | 4.1739 | 1 | 5 | 0.1 | 20 | 30
| 938 | 0.2 | 20 | 12 | 19.5906 | 3.3239 | 4.2667 | 0.8 | 6.25 | 0.2 | 10 | 36.25
| 939 | 0.8 | 5 | 13.8462 | 25.6557 | 2.6667 | 9.1429 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 940 | 1.8 | 2.2222 | 8.7097 | 16.2004 | 3.0256 | 4.4651 | 1.2 | 4.1667 | 0.8 | 2.5 | 8.8889
| 941 | 0.2 | 20 | 8.3077 | 15.338 | 2.5652 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 942 | 1 | 4 | 10.5882 | 17.4383 | 2.9317 | 3.9184 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 943 | 0.6 | 6.6667 | 10.5882 | 17.3767 | 3.2329 | 3.5556 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 944 | 0.4 | 10 | 10.8 | 16.799 | 3.0452 | 2.9538 | 1 | 5 | 0.4 | 5 | 20
| 945 | 0.8 | 5 | 12.8571 | 22.2249 | 2.5106 | 6.8571 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 946 | 0.4 | 10 | 9.8182 | 18.2636 | 3.5224 | 4.9231 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 947 | 0.8 | 5 | 12 | 18.078 | 2.878 | 3.2 | 1 | 5 | 0.4 | 5 | 15
| 948 | 1 | 4 | 9.8182 | 17.7121 | 2.4082 | 5.4857 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 949 | 1 | 4 | 12.5581 | 20.9697 | 2.5934 | 5.8182 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 950 | 0.8 | 5 | 11.0204 | 16.2298 | 2.5792 | 2.6301 | 1 | 5 | 0.8 | 2.5 | 12.5
| 951 | 0.8 | 5 | 12 | 20.8095 | 2.8095 | 6 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 952 | 0.8 | 5 | 18 | 25.5602 | 2.7602 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 953 | 0.8 | 5 | 11.25 | 17.1563 | 2.8095 | 3.0968 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 954 | 1.2 | 3.3333 | 8.3077 | 14.6469 | 3.085 | 3.2542 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 955 | 1 | 4 | 12.8571 | 20.2979 | 3.5224 | 3.9184 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 956 | 0.8 | 5 | 15.8824 | 23.719 | 2.9136 | 4.9231 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 957 | 1.2 | 3.3333 | 12.8571 | 20.948 | 3.1678 | 4.9231 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 958 | 0.8 | 5 | 19.2857 | 26.5451 | 2.8957 | 4.3636 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 959 | 1 | 4 | 8.1818 | 16.6829 | 3.1678 | 5.3333 | 1 | 5 | 0.1 | 20 | 29
| 960 | 1.2 | 3.3333 | 11.7391 | 23.2761 | 3.1892 | 8.3478 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 961 | 1.4 | 2.8571 | 12.5581 | 18.12 | 2.9317 | 2.6301 | 1.6 | 3.125 | 0.4 | 5 | 10.9821
| 962 | 1 | 4 | 10.3846 | 19.2178 | 3.3475 | 5.4857 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 963 | 0.4 | 10 | 14.2105 | 21.4272 | 2.95 | 4.2667 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 964 | 0.2 | 20 | 11.4894 | 21.2601 | 2.9136 | 6.8571 | 0.6 | 8.3333 | 0.6 | 3.3333 | 31.6667
| 965 | 1.2 | 3.3333 | 13.5 | 20.9113 | 2.7283 | 4.6829 | 0.4 | 12.5 | 0.4 | 5 | 20.8333
| 966 | 0.8 | 5 | 15.4286 | 23.2894 | 3.3957 | 4.4651 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 967 | 1.2 | 3.3333 | 8.8525 | 16.5875 | 3.3714 | 4.3636 | 1 | 5 | 0.4 | 5 | 13.3333
| 968 | 0.8 | 5 | 10.1887 | 17.1136 | 3.085 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 969 | 1 | 4 | 9.1525 | 18.3822 | 4.177 | 5.0526 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 970 | 1.4 | 2.8571 | 12.2727 | 20.7701 | 2.4974 | 6 | 1.4 | 3.5714 | 0.4 | 5 | 11.4286
| 971 | 0.6 | 6.6667 | 11.7391 | 19.8329 | 3.5224 | 4.5714 | 1.6 | 3.125 | 0.2 | 10 | 19.7917
| 972 | 1 | 4 | 9.8182 | 16.9821 | 3.3239 | 3.84 | 1 | 5 | 0.2 | 10 | 19
| 973 | 1 | 4 | 10.5882 | 19.2417 | 3.1678 | 5.4857 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 974 | 0.6 | 6.6667 | 12.2727 | 19.5144 | 2.878 | 4.3636 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 975 | 1 | 4 | 14.2105 | 25.6558 | 3.4453 | 8 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 976 | 0.8 | 5 | 16.875 | 27.2853 | 3.0256 | 7.3846 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 977 | 0.6 | 6.6667 | 7.9412 | 15.1521 | 3.2109 | 4 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 978 | 0.6 | 6.6667 | 14.5946 | 21.5082 | 2.9136 | 4 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 979 | 0.6 | 6.6667 | 9.1525 | 17.9207 | 2.95 | 5.8182 | 1 | 5 | 0.4 | 5 | 16.6667
| 980 | 1 | 4 | 12.2727 | 18.2489 | 2.6077 | 3.3684 | 1 | 5 | 0.2 | 10 | 19
| 981 | 0.8 | 5 | 10.5882 | 20.9102 | 3.2109 | 7.1111 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 982 | 0.8 | 5 | 12.8571 | 20.5114 | 3.1892 | 4.4651 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 983 | 0.6 | 6.6667 | 12 | 20.1209 | 2.9317 | 5.1892 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 984 | 0.4 | 10 | 15.4286 | 23.9086 | 3.1467 | 5.3333 | 0.8 | 6.25 | 1 | 2 | 18.25
| 985 | 0.4 | 10 | 17.4194 | 26.6385 | 3.0256 | 6.1935 | 1 | 5 | 0.4 | 5 | 20
| 986 | 0.2 | 20 | 20.7692 | 27.8572 | 3.3957 | 3.6923 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 987 | 0.8 | 5 | 8.7097 | 17.1639 | 2.9686 | 5.4857 | 1 | 5 | 0.4 | 5 | 15
| 988 | 1.2 | 3.3333 | 11.0204 | 17.5271 | 2.6667 | 3.84 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 989 | 0.4 | 10 | 9 | 15.9758 | 3.4203 | 3.5556 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 990 | 0.8 | 5 | 13.1707 | 22.7738 | 3.6031 | 6 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 991 | 0.2 | 20 | 12.5581 | 17.2243 | 2.5792 | 2.087 | 0.4 | 12.5 | 0.4 | 5 | 37.5
| 992 | 0.8 | 5 | 10.1887 | 19.7741 | 2.7283 | 6.8571 | 1.2 | 4.1667 | 1 | 2 | 11.1667
| 993 | 0.6 | 6.6667 | 15 | 21.2359 | 2.4712 | 3.7647 | 1 | 5 | 0.4 | 5 | 16.6667
| 994 | 0.8 | 5 | 10.8 | 16.0719 | 2.1751 | 3.0968 | 1 | 5 | 0.2 | 10 | 20
| 995 | 0.6 | 6.6667 | 13.8462 | 23.1469 | 3.3007 | 6 | 1 | 5 | 0.4 | 5 | 16.6667
| 996 | 0.4 | 10 | 15.8824 | 22.4258 | 2.4583 | 4.0851 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 997 | 0.2 | 20 | 12.8571 | 21.8431 | 3.1678 | 5.8182 | 1 | 5 | 0.2 | 10 | 35
| 998 | 1.4 | 2.8571 | 15.8824 | 22.2719 | 2.4712 | 3.9184 | 1 | 5 | 0.2 | 10 | 17.8571
| 999 | 0.6 | 6.6667 | 10.5882 | 19.1633 | 3.5224 | 5.0526 | 1 | 5 | 0.4 | 5 | 16.6667
| 1000 | 0.4 | 10 | 14.5946 | 20.4831 | 3.0649 | 2.8235 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 1001 | 0.6 | 6.6667 | 14.5946 | 21.1129 | 2.8957 | 3.6226 | 1 | 5 | 0.2 | 10 | 21.6667
| 1002 | 1 | 4 | 14.5946 | 20.7798 | 2.4205 | 3.7647 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 1003 | 0.2 | 20 | 25.7143 | 32.3548 | 3.085 | 3.5556 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 1004 | 1 | 4 | 13.8462 | 20.323 | 2.6369 | 3.84 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 1005 | 0.6 | 6.6667 | 15.8824 | 26.4562 | 3.1892 | 7.3846 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 1006 | 1 | 4 | 17.4194 | 27.8544 | 3.3239 | 7.1111 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 1007 | 0.8 | 5 | 14.2105 | 19.5909 | 2.1261 | 3.2542 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 1008 | 1 | 4 | 10.8 | 19.7478 | 3.3007 | 5.6471 | 1 | 5 | 0.4 | 5 | 14
| 1009 | 1.2 | 3.3333 | 12 | 18.61 | 2.9873 | 3.6226 | 1 | 5 | 0.2 | 10 | 18.3333
| 1010 | 0.6 | 6.6667 | 12.5581 | 18.8473 | 2.8606 | 3.4286 | 1 | 5 | 1 | 2 | 13.6667
| 1011 | 0.8 | 5 | 9.1525 | 15.7901 | 3.1467 | 3.4909 | 1 | 5 | 0.4 | 5 | 15
| 1012 | 0.4 | 10 | 9.6429 | 17.3195 | 3.1053 | 4.5714 | 1 | 5 | 0.4 | 5 | 20
| 1013 | 1.2 | 3.3333 | 15 | 21.0653 | 2.9686 | 3.0968 | 0.8 | 6.25 | 0.8 | 2.5 | 12.0833
| 1014 | 0.6 | 6.6667 | 14.5946 | 23.8731 | 3.085 | 6.1935 | 1 | 5 | 0.4 | 5 | 16.6667
| 1015 | 1.2 | 3.3333 | 18.6207 | 27.2484 | 2.8095 | 5.8182 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 1016 | 1 | 4 | 12.5581 | 18.6717 | 2.9136 | 3.2 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 1017 | 0.2 | 20 | 14.2105 | 21.1255 | 2.5514 | 4.3636 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 1018 | 1.2 | 3.3333 | 10.8 | 18.1893 | 3.0256 | 4.3636 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 1019 | 1 | 4 | 12.5581 | 20.3211 | 3.4963 | 4.2667 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 1020 | 1 | 4 | 14.5946 | 22.5884 | 5.3636 | 2.6301 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 1021 | 0.6 | 6.6667 | 9.6429 | 15.4072 | 2.3959 | 3.3684 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 1022 | 0.8 | 5 | 12.2727 | 17.6637 | 3.1053 | 2.2857 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1023 | 1 | 4 | 13.5 | 20.3335 | 3.2109 | 3.6226 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 1024 | 1.4 | 2.8571 | 15.8824 | 22.3605 | 3.1678 | 3.3103 | 1.4 | 3.5714 | 0.2 | 10 | 16.4286
| 1025 | 1.2 | 3.3333 | 9.6429 | 18.3947 | 4.069 | 4.6829 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 1026 | 0.8 | 5 | 12.8571 | 21.0098 | 3.6875 | 4.4651 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 1027 | 0.6 | 6.6667 | 12 | 19.7891 | 3.5224 | 4.2667 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 1028 | 0.6 | 6.6667 | 12.8571 | 20.1486 | 2.8263 | 4.4651 | 0.6 | 8.3333 | 0.8 | 2.5 | 17.5
| 1029 | 0.6 | 6.6667 | 21.6 | 27.7817 | 3.085 | 3.0968 | 1 | 5 | 0.4 | 5 | 16.6667
| 1030 | 1 | 4 | 10.3846 | 18.3915 | 3.3239 | 4.6829 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 1031 | 1 | 4 | 12.2727 | 21.025 | 3.1053 | 5.6471 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 1032 | 0.4 | 10 | 12.2727 | 23.5558 | 3.6031 | 7.68 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 1033 | 0.4 | 10 | 10.5882 | 22.4282 | 2.6971 | 9.1429 | 1.6 | 3.125 | 0.2 | 10 | 23.125
| 1034 | 1.4 | 2.8571 | 10.8 | 19.6158 | 2.6222 | 6.1935 | 1.6 | 3.125 | 0.2 | 10 | 15.9821
| 1035 | 0.8 | 5 | 13.5 | 19.7511 | 2.7602 | 3.4909 | 1 | 5 | 0.2 | 10 | 20
| 1036 | 0.4 | 10 | 11.25 | 18.7206 | 3.4706 | 4 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 1037 | 1.2 | 3.3333 | 13.8462 | 22.9859 | 3.8065 | 5.3333 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 1038 | 0.4 | 10 | 13.8462 | 21.5065 | 2.4712 | 5.1892 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 1039 | 1.2 | 3.3333 | 11.0204 | 18.0648 | 2.5792 | 4.4651 | 1 | 5 | 0.4 | 5 | 13.3333
| 1040 | 0.8 | 5 | 8.5714 | 14.9655 | 3.0256 | 3.3684 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 1041 | 0.6 | 6.6667 | 12 | 19.744 | 3.6589 | 4.0851 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 1042 | 0.8 | 5 | 11.4894 | 21.41 | 2.8095 | 7.1111 | 1.6 | 3.125 | 0.2 | 10 | 18.125
| 1043 | 1 | 4 | 10.5882 | 17.5458 | 2.0345 | 4.9231 | 1 | 5 | 0.8 | 2.5 | 11.5
| 1044 | 0.8 | 5 | 16.3636 | 24.2286 | 3.0649 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1045 | 1 | 4 | 12.2727 | 19.956 | 2.7602 | 4.9231 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 1046 | 0.6 | 6.6667 | 8.1818 | 14.6108 | 2.5106 | 3.9184 | 0.6 | 8.3333 | 0.8 | 2.5 | 17.5
| 1047 | 0.1 | 40 | 12.2727 | 19.6427 | 3.0064 | 4.3636 | 0.6 | 8.3333 | 0.6 | 3.3333 | 51.6667
| 1048 | 0.8 | 5 | 10.8 | 18.5281 | 3.0452 | 4.6829 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1049 | 0.2 | 20 | 13.5 | 22.7234 | 4.0342 | 5.1892 | 1 | 5 | 0.4 | 5 | 30
| 1050 | 0.8 | 5 | 13.8462 | 21.5627 | 3.7165 | 4 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 1051 | 0.4 | 10 | 12.2727 | 20.257 | 2.9317 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 1052 | 1 | 4 | 14.2105 | 21.6988 | 2.5652 | 4.9231 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 1053 | 0.8 | 5 | 12.8571 | 19.5535 | 2.9317 | 3.7647 | 1 | 5 | 0.4 | 5 | 15
| 1054 | 0.4 | 10 | 12.5581 | 20.8202 | 4.177 | 4.0851 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 1055 | 0.6 | 6.6667 | 9.3103 | 14.7847 | 2.5652 | 2.9091 | 1 | 5 | 0.4 | 5 | 16.6667
| 1056 | 0.8 | 5 | 13.5 | 21.0308 | 2.6077 | 4.9231 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 1057 | 0.8 | 5 | 15 | 22.1313 | 3.5758 | 3.5556 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 1058 | 0.2 | 20 | 15 | 23.3418 | 3.6589 | 4.6829 | 0.6 | 8.3333 | 0.2 | 10 | 38.3333
| 1059 | 1 | 4 | 12.2727 | 21.3264 | 2.433 | 6.6207 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 1060 | 0.8 | 5 | 20 | 28.1939 | 2.8606 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1061 | 1.2 | 3.3333 | 8.8525 | 15.8828 | 2.6667 | 4.3636 | 1.6 | 3.125 | 0.2 | 10 | 16.4583
| 1062 | 1 | 4 | 8.7097 | 15.8709 | 2.9873 | 4.1739 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 1063 | 1 | 4 | 16.3636 | 23.5706 | 2.8434 | 4.3636 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 1064 | 0.4 | 10 | 19.2857 | 25.4535 | 2.9136 | 3.2542 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 1065 | 1 | 4 | 12.2727 | 19.7974 | 4.2143 | 3.3103 | 1 | 5 | 0.4 | 5 | 14
| 1066 | 1 | 4 | 9.3103 | 16.4465 | 3.3714 | 3.7647 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 1067 | 1 | 4 | 16.3636 | 23.5632 | 3.0256 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 1068 | 0.8 | 5 | 9.8182 | 14.9965 | 2.2692 | 2.9091 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 1069 | 0.6 | 6.6667 | 12.2727 | 20.0222 | 2.8263 | 4.9231 | 1 | 5 | 0.4 | 5 | 16.6667
| 1070 | 1.6 | 2.5 | 12.2727 | 18.9512 | 2.5934 | 4.0851 | 0.8 | 6.25 | 0.4 | 5 | 13.75
| 1071 | 0.6 | 6.6667 | 18.6207 | 25.9994 | 2.9136 | 4.4651 | 1 | 5 | 0.4 | 5 | 16.6667
| 1072 | 0.8 | 5 | 10.3846 | 20.4398 | 4.866 | 5.1892 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1073 | 0.6 | 6.6667 | 10 | 16.4974 | 2.4974 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 1074 | 0.8 | 5 | 8.4375 | 15.2165 | 2.8606 | 3.9184 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 1075 | 0.8 | 5 | 11.4894 | 19.2784 | 3.5224 | 4.2667 | 1 | 5 | 0.4 | 5 | 15
| 1076 | 1.2 | 3.3333 | 11.7391 | 19.1022 | 3.1892 | 4.1739 | 1.2 | 4.1667 | 0.1 | 20 | 27.5
| 1077 | 0.4 | 10 | 12.5581 | 20.1277 | 3.3957 | 4.1739 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 1078 | 0.2 | 20 | 11.25 | 18.7801 | 3.0649 | 4.4651 | 1 | 5 | 0.4 | 5 | 30
| 1079 | 0.6 | 6.6667 | 12 | 19.5597 | 2.2264 | 5.3333 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 1080 | 0.4 | 10 | 12 | 21.2888 | 3.4706 | 5.8182 | 1 | 5 | 0.8 | 2.5 | 17.5
| 1081 | 1.4 | 2.8571 | 17.4194 | 24.5996 | 3.0064 | 4.1739 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 1082 | 0.2 | 20 | 9.6429 | 15.0826 | 3.2329 | 2.2069 | 1 | 5 | 0.4 | 5 | 30
| 1083 | 1.4 | 2.8571 | 14.2105 | 22.2514 | 3.5758 | 4.4651 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 1084 | 1.4 | 2.8571 | 13.5 | 22.9649 | 3.0649 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 1085 | 1.2 | 3.3333 | 9.6429 | 17.5723 | 3.0064 | 4.9231 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 1086 | 0.2 | 20 | 16.875 | 22.663 | 3.0452 | 2.7429 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 1087 | 0.4 | 10 | 13.1707 | 19.5471 | 2.2913 | 4.0851 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 1088 | 1 | 4 | 15 | 29.8263 | 2.8263 | 12 | 1 | 5 | 0.8 | 2.5 | 11.5
| 1089 | 0.6 | 6.6667 | 10.5882 | 18.1383 | 3.085 | 4.4651 | 1 | 5 | 0.4 | 5 | 16.6667
| 1090 | 0.6 | 6.6667 | 10.5882 | 17.4566 | 2.95 | 3.9184 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 1091 | 0.8 | 5 | 10 | 16.5189 | 3.776 | 2.7429 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 1092 | 0.4 | 10 | 14.5946 | 23.7875 | 2.7929 | 6.4 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 1093 | 1 | 4 | 14.2105 | 22.382 | 3.3714 | 4.8 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 1094 | 0.6 | 6.6667 | 12.2727 | 20.2222 | 2.7602 | 5.1892 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 1095 | 0.8 | 5 | 8.4375 | 15.3103 | 3.776 | 3.0968 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 1096 | 0.6 | 6.6667 | 15.4286 | 21.6315 | 2.5106 | 3.6923 | 1 | 5 | 0.2 | 10 | 21.6667
| 1097 | 1.2 | 3.3333 | 12.2727 | 18.3796 | 2.5514 | 3.5556 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 1098 | 1 | 4 | 13.5 | 20.8787 | 2.9136 | 4.4651 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 1099 | 1 | 4 | 18.6207 | 27.0127 | 5.2444 | 3.1475 | 1 | 5 | 0.2 | 10 | 19
| 1100 | 1 | 4 | 12.8571 | 28.8516 | 2.2802 | 13.7143 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 1101 | 0.6 | 6.6667 | 12 | 17.6357 | 2.6818 | 2.9538 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 1102 | 0.4 | 10 | 13.1707 | 19.8771 | 3.2778 | 3.4286 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 1103 | 0.8 | 5 | 13.8462 | 20.7965 | 2.7765 | 4.1739 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 1104 | 1 | 4 | 9.1525 | 14.433 | 2.5376 | 2.7429 | 1 | 5 | 0.4 | 5 | 14
| 1105 | 0.8 | 5 | 12.8571 | 20.8422 | 2.6517 | 5.3333 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 1106 | 1 | 4 | 14.5946 | 23.8834 | 3.4706 | 5.8182 | 1 | 5 | 0.4 | 5 | 14
| 1107 | 0.8 | 5 | 8.5714 | 16.4889 | 2.7283 | 5.1892 | 1 | 5 | 0.4 | 5 | 15
| 1108 | 0.6 | 6.6667 | 12.2727 | 20.3755 | 2.9136 | 5.1892 | 1 | 5 | 0.4 | 5 | 16.6667
| 1109 | 0.4 | 10 | 13.1707 | 19.0117 | 2.7442 | 3.0968 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 1110 | 0.8 | 5 | 16.875 | 23.8913 | 3.3239 | 3.6923 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 1111 | 0.8 | 5 | 10.1887 | 17.8867 | 3.2329 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 1112 | 1.4 | 2.8571 | 13.5 | 25.2336 | 3.0064 | 8.7273 | 1 | 5 | 0.2 | 10 | 17.8571
| 1113 | 0.1 | 40 | 12.2727 | 17.8945 | 2.7126 | 2.9091 | 0.8 | 6.25 | 0.4 | 5 | 51.25
| 1114 | 1.2 | 3.3333 | 10.5882 | 17.9399 | 3.085 | 4.2667 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 1115 | 1 | 4 | 21.6 | 28.6763 | 2.7126 | 4.3636 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 1116 | 0.8 | 5 | 11.7391 | 19.7906 | 3.9664 | 4.0851 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 1117 | 1 | 4 | 12.8571 | 20.5215 | 3.746 | 3.9184 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 1118 | 0.6 | 6.6667 | 13.1707 | 19.1446 | 2.8263 | 3.1475 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 1119 | 0.8 | 5 | 14.2105 | 25.001 | 3.9333 | 6.8571 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 1120 | 0.8 | 5 | 11.25 | 19.0626 | 3.3475 | 4.4651 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 1121 | 0.8 | 5 | 12.5581 | 18.265 | 2.216 | 3.4909 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 1122 | 0.8 | 5 | 13.1707 | 20.406 | 2.9686 | 4.2667 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1123 | 0.2 | 20 | 12 | 19.5974 | 2.4082 | 5.1892 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 1124 | 0.8 | 5 | 11.4894 | 18.5412 | 3.4963 | 3.5556 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 1125 | 0.6 | 6.6667 | 12.8571 | 19.4736 | 2.7765 | 3.84 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 1126 | 1.2 | 3.3333 | 12 | 18.3073 | 3.6031 | 2.7042 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 1127 | 0.8 | 5 | 10 | 18.4174 | 2.9317 | 5.4857 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 1128 | 0.8 | 5 | 9.8182 | 15.4724 | 2.95 | 2.7042 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 1129 | 0.8 | 5 | 11.7391 | 19.4572 | 3.1467 | 4.5714 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 1130 | 0.6 | 6.6667 | 8.5714 | 16.484 | 2.5792 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 1131 | 0.6 | 6.6667 | 8.3077 | 16.6736 | 3.9008 | 4.4651 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 1132 | 0.6 | 6.6667 | 15.4286 | 23.0195 | 3.1258 | 4.4651 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 1133 | 1 | 4 | 16.875 | 27.3629 | 3.6308 | 6.8571 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 1134 | 0.2 | 20 | 11.7391 | 16.8287 | 2.1357 | 2.9538 | 1 | 5 | 0.4 | 5 | 30
| 1135 | 0.4 | 10 | 15 | 24.3873 | 2.9873 | 6.4 | 1 | 5 | 0.4 | 5 | 20
| 1136 | 0.2 | 20 | 14.5946 | 24.9109 | 2.9317 | 7.3846 | 1 | 5 | 0.4 | 5 | 30
| 1137 | 1.2 | 3.3333 | 8.7097 | 16.0955 | 3.3007 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 1138 | 1 | 4 | 12.2727 | 22.4501 | 2.4974 | 7.68 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 1139 | 0.1 | 40 | 16.3636 | 24.5429 | 3.4963 | 4.6829 | 1 | 5 | 0.2 | 10 | 55
| 1140 | 1 | 4 | 7.5 | 15.0103 | 3.0452 | 4.4651 | 1 | 5 | 0.2 | 10 | 19
| 1141 | 0.4 | 10 | 11.4894 | 18.2419 | 3.3239 | 3.4286 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 1142 | 1.4 | 2.8571 | 12.2727 | 17.9913 | 2.8095 | 2.9091 | 1.4 | 3.5714 | 0.2 | 10 | 16.4286
| 1143 | 1.2 | 3.3333 | 15.4286 | 22.0596 | 2.7126 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 1144 | 1 | 4 | 11.25 | 19.3231 | 3.8065 | 4.2667 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 1145 | 0.2 | 20 | 11.4894 | 18.636 | 3.1467 | 4 | 0.6 | 8.3333 | 0.6 | 3.3333 | 31.6667
| 1146 | 0.6 | 6.6667 | 11.0204 | 17.2246 | 2.95 | 3.2542 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 1147 | 0.8 | 5 | 11.7391 | 19.5513 | 2.1651 | 5.6471 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 1148 | 0.8 | 5 | 11.7391 | 17.9937 | 3.3007 | 2.9538 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 1149 | 1.4 | 2.8571 | 9.3103 | 15.0747 | 2.3959 | 3.3684 | 1 | 5 | 0.4 | 5 | 12.8571
| 1150 | 1 | 4 | 12.8571 | 23.269 | 3.3007 | 7.1111 | 1 | 5 | 0.2 | 10 | 19
| 1151 | 1.6 | 2.5 | 15.4286 | 23.7969 | 3.4453 | 4.9231 | 1.4 | 3.5714 | 0.6 | 3.3333 | 9.4048
| 1152 | 1.2 | 3.3333 | 11.7391 | 17.5997 | 2.8606 | 3 | 1.6 | 3.125 | 0.4 | 5 | 11.4583
| 1153 | 0.8 | 5 | 8.7097 | 16.3263 | 3.0452 | 4.5714 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 1154 | 0.6 | 6.6667 | 15.4286 | 21.3888 | 3.0064 | 2.9538 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 1155 | 1.2 | 3.3333 | 9.4737 | 18.955 | 2.8606 | 6.6207 | 1 | 5 | 0.2 | 10 | 18.3333
| 1156 | 0.6 | 6.6667 | 11.7391 | 21.3943 | 3.2552 | 6.4 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 1157 | 0.8 | 5 | 15 | 24.3873 | 2.9873 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1158 | 0.8 | 5 | 9.1525 | 17.6076 | 2.6369 | 5.8182 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 1159 | 0.8 | 5 | 9.4737 | 17.3789 | 3.1053 | 4.8 | 1 | 5 | 0.2 | 10 | 20
| 1160 | 0.1 | 40 | 18 | 26.1239 | 3.3239 | 4.8 | 1 | 5 | 0.8 | 2.5 | 47.5
| 1161 | 1 | 4 | 25.7143 | 32.6428 | 2.8434 | 4.0851 | 1 | 5 | 0.8 | 2.5 | 11.5
| 1162 | 0.4 | 10 | 12 | 20.6344 | 3.4453 | 5.1892 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 1163 | 1 | 4 | 10 | 17.3719 | 3.1053 | 4.2667 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 1164 | 1.2 | 3.3333 | 10.5882 | 17.9771 | 3.5489 | 3.84 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 1165 | 0.8 | 5 | 11.4894 | 17.807 | 3.6875 | 2.6301 | 1 | 5 | 0.4 | 5 | 15
| 1166 | 0.6 | 6.6667 | 13.8462 | 20.279 | 3.2329 | 3.2 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 1167 | 1 | 4 | 11.7391 | 20.2523 | 3.3239 | 5.1892 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 1168 | 1.2 | 3.3333 | 14.5946 | 22.993 | 3.9333 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 1169 | 1 | 4 | 12.5581 | 20.6456 | 2.2692 | 5.8182 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 1170 | 0.6 | 6.6667 | 10.1887 | 24.738 | 3.2552 | 11.2941 | 1 | 5 | 0.6 | 3.3333 | 15
| 1171 | 1.4 | 2.8571 | 11.7391 | 21.248 | 2.6517 | 6.8571 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 1172 | 0.6 | 6.6667 | 17.4194 | 23.9872 | 3.4203 | 3.1475 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 1173 | 1 | 4 | 12 | 19.1239 | 2.95 | 4.1739 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 1174 | 1.2 | 3.3333 | 14.2105 | 20.987 | 2.7765 | 4 | 1 | 5 | 0.4 | 5 | 13.3333
| 1175 | 0.8 | 5 | 7.1053 | 14.0044 | 3.4706 | 3.4286 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 1176 | 1 | 4 | 10.8 | 15.6263 | 2.3959 | 2.4304 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 1177 | 1 | 4 | 9.4737 | 16.5896 | 2.433 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 1178 | 0.2 | 20 | 8.4375 | 13.647 | 2.8095 | 2.4 | 0.6 | 8.3333 | 0.4 | 5 | 33.3333
| 1179 | 1 | 4 | 8.7097 | 13.4015 | 2.433 | 2.2588 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 1180 | 0.4 | 10 | 12 | 22.2056 | 2.2056 | 8 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 1181 | 0.8 | 5 | 12.8571 | 20.219 | 3.9333 | 3.4286 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 1182 | 0.6 | 6.6667 | 12.5581 | 20.6171 | 3.0064 | 5.0526 | 1 | 5 | 0.6 | 3.3333 | 15
| 1183 | 0.2 | 20 | 9.6429 | 19.1077 | 2.6077 | 6.8571 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 1184 | 0.6 | 6.6667 | 14.2105 | 20.9473 | 2.6517 | 4.0851 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 1185 | 0.8 | 5 | 12.5581 | 22.3057 | 3.3475 | 6.4 | 1 | 5 | 0.4 | 5 | 15
| 1186 | 1 | 4 | 16.3636 | 24.501 | 2.6517 | 5.4857 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 1187 | 0.6 | 6.6667 | 15 | 21.2641 | 2.8957 | 3.3684 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 1188 | 1.4 | 2.8571 | 12.8571 | 20.5764 | 2.6667 | 5.0526 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 1189 | 1.4 | 2.8571 | 12.5581 | 19.1584 | 2.7602 | 3.84 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 1190 | 1 | 4 | 11.4894 | 18.3769 | 3.6875 | 3.2 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 1191 | 0.8 | 5 | 12.2727 | 19.9057 | 2.95 | 4.6829 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 1192 | 0.8 | 5 | 15 | 25.0944 | 3.9008 | 6.1935 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 1193 | 0.4 | 10 | 15.4286 | 23.1965 | 3.085 | 4.6829 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 1194 | 1.2 | 3.3333 | 9.3103 | 19.7164 | 3.5489 | 6.8571 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 1195 | 0.2 | 20 | 10.3846 | 16.5955 | 3.2109 | 3 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 1196 | 1 | 4 | 12.5581 | 21.2948 | 2.3366 | 6.4 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 1197 | 0.8 | 5 | 8.8525 | 14.6158 | 2.8095 | 2.9538 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 1198 | 1.4 | 2.8571 | 12.8571 | 23.2674 | 3.0256 | 7.3846 | 0.8 | 6.25 | 0.1 | 20 | 29.1071
| 1199 | 1.4 | 2.8571 | 8.4375 | 16.5601 | 2.6369 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 1200 | 1.2 | 3.3333 | 13.1707 | 19.7136 | 2.9873 | 3.5556 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 1201 | 1.8 | 2.2222 | 15.4286 | 21.8776 | 2.8263 | 3.6226 | 1.2 | 4.1667 | 0.6 | 3.3333 | 9.7222
| 1202 | 0.4 | 10 | 12.5581 | 18.6283 | 2.5792 | 3.4909 | 1 | 5 | 0.2 | 10 | 25
| 1203 | 0.4 | 10 | 12.2727 | 20.1437 | 2.6818 | 5.1892 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 1204 | 0.4 | 10 | 11.7391 | 17.8194 | 2.6517 | 3.4286 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 1205 | 1.2 | 3.3333 | 11.25 | 21.1328 | 3.0256 | 6.8571 | 1 | 5 | 0.2 | 10 | 18.3333
| 1206 | 1.2 | 3.3333 | 11.0204 | 17.0405 | 2.6517 | 3.3684 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 1207 | 0.4 | 10 | 9.3103 | 15.4196 | 2.2692 | 3.84 | 1 | 5 | 0.8 | 2.5 | 17.5
| 1208 | 0.6 | 6.6667 | 15.8824 | 23.6229 | 2.5514 | 5.1892 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 1209 | 0.8 | 5 | 14.2105 | 23.7572 | 3.1467 | 6.4 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 1210 | 0.8 | 5 | 11.7391 | 19.2199 | 3.3957 | 4.0851 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 1211 | 1 | 4 | 12 | 19.3376 | 2.5376 | 4.8 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 1212 | 0.6 | 6.6667 | 12.8571 | 21.4322 | 3.5224 | 5.0526 | 1 | 5 | 0.2 | 10 | 21.6667
| 1213 | 1 | 4 | 9.4737 | 16.9961 | 3.5224 | 4 | 0.6 | 8.3333 | 0.1 | 20 | 32.3333
| 1214 | 0.4 | 10 | 14.2105 | 27.7361 | 3.4203 | 10.1053 | 0.6 | 8.3333 | 0.1 | 20 | 38.3333
| 1215 | 0.4 | 10 | 15 | 20.2535 | 2.5106 | 2.7429 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 1216 | 0.6 | 6.6667 | 12 | 19.8328 | 3.6589 | 4.1739 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 1217 | 0.8 | 5 | 9 | 16.0425 | 3.2778 | 3.7647 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 1218 | 0.4 | 10 | 12.8571 | 20.5453 | 3.6031 | 4.0851 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 1219 | 0.2 | 20 | 13.8462 | 25.0262 | 4.069 | 7.1111 | 0.4 | 12.5 | 0.4 | 5 | 37.5
| 1220 | 1.2 | 3.3333 | 10 | 16.8589 | 3.6589 | 3.2 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 1221 | 0.4 | 10 | 10.1887 | 18.4628 | 3.085 | 5.1892 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 1222 | 1 | 4 | 10.1887 | 16.018 | 2.6818 | 3.1475 | 1 | 5 | 0.4 | 5 | 14
| 1223 | 1 | 4 | 11.25 | 17.6822 | 2.8095 | 3.6226 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 1224 | 1 | 4 | 9.3103 | 16.5357 | 2.7602 | 4.4651 | 1 | 5 | 0.4 | 5 | 14
| 1225 | 0.4 | 10 | 11.7391 | 21.1594 | 3.4203 | 6 | 1 | 5 | 0.2 | 10 | 25
| 1226 | 1 | 4 | 15 | 22.1239 | 2.7602 | 4.3636 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 1227 | 0.6 | 6.6667 | 16.3636 | 23.2583 | 2.8095 | 4.0851 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 1228 | 1 | 4 | 14.5946 | 20.4537 | 2.95 | 2.9091 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 1229 | 1 | 4 | 12.2727 | 20.672 | 2.9136 | 5.4857 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 1230 | 0.4 | 10 | 14.2105 | 20.3591 | 2.3838 | 3.7647 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 1231 | 1.2 | 3.3333 | 14.5946 | 20.623 | 2.9317 | 3.0968 | 0.4 | 12.5 | 0.4 | 5 | 20.8333
| 1232 | 1 | 4 | 10.8 | 17.256 | 2.5376 | 3.9184 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 1233 | 1.2 | 3.3333 | 10.3846 | 15.6664 | 2.6517 | 2.6301 | 1 | 5 | 0.2 | 10 | 18.3333
| 1234 | 0.4 | 10 | 11.25 | 20.5076 | 2.6369 | 6.6207 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 1235 | 1 | 4 | 14.5946 | 21.8606 | 3.8374 | 3.4286 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 1236 | 1 | 4 | 11.7391 | 19.7603 | 2.9686 | 5.0526 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 1237 | 0.8 | 5 | 12.5581 | 19.8324 | 3.1892 | 4.0851 | 1 | 5 | 0.8 | 2.5 | 12.5
| 1238 | 0.2 | 20 | 12.8571 | 18.7468 | 2.7929 | 3.0968 | 1 | 5 | 0.4 | 5 | 30
| 1239 | 0.6 | 6.6667 | 17.4194 | 25.9967 | 2.3838 | 6.1935 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 1240 | 1.2 | 3.3333 | 13.8462 | 21.8673 | 2.9686 | 5.0526 | 1.6 | 3.125 | 0.2 | 10 | 16.4583
| 1241 | 1.2 | 3.3333 | 10.1887 | 17.7644 | 3.5758 | 4 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 1242 | 0.6 | 6.6667 | 12 | 20.9686 | 2.9686 | 6 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 1243 | 0.4 | 10 | 19.2857 | 26.9943 | 3.0256 | 4.6829 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 1244 | 1 | 4 | 17.4194 | 23.9377 | 2.8957 | 3.6226 | 1 | 5 | 0.2 | 10 | 19
| 1245 | 1 | 4 | 11.0204 | 17.7657 | 2.2802 | 4.4651 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 1246 | 0.6 | 6.6667 | 13.8462 | 20.3502 | 3.8374 | 2.6667 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 1247 | 1 | 4 | 9.3103 | 17.0733 | 3.4963 | 4.2667 | 1 | 5 | 0.2 | 10 | 19
| 1248 | 0.4 | 10 | 13.1707 | 20.0992 | 2.8434 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 1249 | 1.2 | 3.3333 | 12.8571 | 19.8463 | 2.5241 | 4.4651 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 1250 | 0.6 | 6.6667 | 9.1525 | 16.1724 | 3.2552 | 3.7647 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 1251 | 1.2 | 3.3333 | 8.0597 | 16.8383 | 3.4453 | 5.3333 | 1 | 5 | 0.4 | 5 | 13.3333
| 1252 | 0.8 | 5 | 13.5 | 20.9088 | 3.0452 | 4.3636 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 1253 | 0.6 | 6.6667 | 9.8182 | 16.6509 | 3.5224 | 3.3103 | 1 | 5 | 0.4 | 5 | 16.6667
| 1254 | 1 | 4 | 7.7143 | 15.4308 | 3.7165 | 4 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 1255 | 0.4 | 10 | 11.25 | 17.7761 | 2.6077 | 3.9184 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 1256 | 0.8 | 5 | 11.25 | 17.6042 | 3.6875 | 2.6667 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1257 | 0.6 | 6.6667 | 13.5 | 20.8136 | 3.5489 | 3.7647 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 1258 | 1 | 4 | 13.1707 | 21.5948 | 3.3714 | 5.0526 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 1259 | 1 | 4 | 13.1707 | 20.1125 | 3.6875 | 3.2542 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 1260 | 0.8 | 5 | 13.8462 | 22.6501 | 3.4706 | 5.3333 | 1.6 | 3.125 | 0.2 | 10 | 18.125
| 1261 | 0.6 | 6.6667 | 14.5946 | 21.8787 | 2.7126 | 4.5714 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 1262 | 0.8 | 5 | 15 | 21.6069 | 2.433 | 4.1739 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 1263 | 0.8 | 5 | 12.5581 | 19.1125 | 3.1258 | 3.4286 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1264 | 0.8 | 5 | 12.8571 | 21.0107 | 3.4706 | 4.6829 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 1265 | 0.4 | 10 | 11.4894 | 19.212 | 2.237 | 5.4857 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 1266 | 1 | 4 | 12.5581 | 22.0352 | 3.6589 | 5.8182 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 1267 | 0.8 | 5 | 12.5581 | 19.6455 | 2.6222 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1268 | 0.8 | 5 | 13.1707 | 21.6686 | 3.4453 | 5.0526 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 1269 | 0.8 | 5 | 11.7391 | 20.4354 | 2.878 | 5.8182 | 1 | 5 | 0.4 | 5 | 15
| 1270 | 0.8 | 5 | 15.4286 | 22.3308 | 2.7283 | 4.1739 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 1271 | 1.2 | 3.3333 | 12.5581 | 19.6501 | 2.7283 | 4.3636 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 1272 | 1.2 | 3.3333 | 12.2727 | 18.9371 | 2.5792 | 4.0851 | 1 | 5 | 0.4 | 5 | 13.3333
| 1273 | 0.2 | 20 | 8.3077 | 17.6271 | 3.1258 | 6.1935 | 1.2 | 4.1667 | 1 | 2 | 26.1667
| 1274 | 0.4 | 10 | 10 | 24.3575 | 4.2523 | 10.1053 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 1275 | 1.4 | 2.8571 | 12.5581 | 21.0948 | 3.3475 | 5.1892 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 1276 | 1.2 | 3.3333 | 8.4375 | 15.8861 | 3.085 | 4.3636 | 0.4 | 12.5 | 0.2 | 10 | 25.8333
| 1277 | 0.8 | 5 | 15.8824 | 25.0675 | 4.72 | 4.4651 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 1278 | 0.4 | 10 | 8.7097 | 17.0084 | 2.6517 | 5.6471 | 0.8 | 6.25 | 1 | 2 | 18.25
| 1279 | 1 | 4 | 10.5882 | 18.0765 | 2.5652 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 1280 | 0.4 | 10 | 9.8182 | 18.0137 | 3.0064 | 5.1892 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 1281 | 1 | 4 | 13.1707 | 22.6348 | 2.8434 | 6.6207 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 1282 | 0.2 | 20 | 11.25 | 18.8692 | 3.4453 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 1283 | 1 | 4 | 12.2727 | 24.9179 | 3.0452 | 9.6 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 1284 | 0.2 | 20 | 10 | 18.0109 | 3.2109 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 1285 | 0.8 | 5 | 8.8525 | 16.1782 | 2.8606 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1286 | 0.8 | 5 | 9.4737 | 16.2016 | 2.8095 | 3.9184 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 1287 | 0.6 | 6.6667 | 9.8182 | 20.0291 | 2.8263 | 7.3846 | 1 | 5 | 0.2 | 10 | 21.6667
| 1288 | 0.8 | 5 | 8.7097 | 16.1621 | 2.9873 | 4.4651 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 1289 | 0.8 | 5 | 10.5882 | 20.3211 | 2.3483 | 7.3846 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 1290 | 1.2 | 3.3333 | 14.5946 | 22.4386 | 2.5106 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 1291 | 1 | 4 | 10.1887 | 17.1339 | 3.1053 | 3.84 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 1292 | 0.6 | 6.6667 | 9.3103 | 14.9802 | 2.6222 | 3.0476 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 1293 | 0.8 | 5 | 7.013 | 13.7648 | 2.6667 | 4.0851 | 1 | 5 | 0.4 | 5 | 15
| 1294 | 0.8 | 5 | 12.5581 | 18.3473 | 3.085 | 2.7042 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 1295 | 1 | 4 | 11.4894 | 17.7901 | 3.3007 | 3 | 1 | 5 | 0.4 | 5 | 14
| 1296 | 0.8 | 5 | 14.2105 | 21.1286 | 2.7442 | 4.1739 | 1 | 5 | 0.8 | 2.5 | 12.5
| 1297 | 0.4 | 10 | 15 | 21.0252 | 2.1852 | 3.84 | 1 | 5 | 0.4 | 5 | 20
| 1298 | 0.4 | 10 | 15.8824 | 22.4244 | 3.4453 | 3.0968 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 1299 | 0.6 | 6.6667 | 15.8824 | 22.5262 | 3.4963 | 3.1475 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 1300 | 0.6 | 6.6667 | 12 | 19.3439 | 2.2913 | 5.0526 | 1 | 5 | 0.2 | 10 | 21.6667
| 1301 | 1 | 4 | 13.5 | 19.1869 | 2.2584 | 3.4286 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 1302 | 0.6 | 6.6667 | 12.8571 | 21.6221 | 3.5758 | 5.1892 | 1 | 5 | 0.6 | 3.3333 | 15
| 1303 | 0.4 | 10 | 20.7692 | 28.059 | 3.3714 | 3.9184 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 1304 | 1.2 | 3.3333 | 8.7097 | 15.0355 | 3.1258 | 3.2 | 0.4 | 12.5 | 0.2 | 10 | 25.8333
| 1305 | 0.8 | 5 | 12 | 21.3402 | 3.1467 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 1306 | 0.6 | 6.6667 | 12.8571 | 21.672 | 3.1678 | 5.6471 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 1307 | 0.6 | 6.6667 | 11.25 | 19.1193 | 4.177 | 3.6923 | 1 | 5 | 0.4 | 5 | 16.6667
| 1308 | 1 | 4 | 12.2727 | 21.9887 | 3.5224 | 6.1935 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 1309 | 1 | 4 | 12.8571 | 19.5535 | 2.9317 | 3.7647 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 1310 | 1.2 | 3.3333 | 18 | 24.3741 | 2.6818 | 3.6923 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 1311 | 1 | 4 | 12.5581 | 18.9232 | 2.8095 | 3.5556 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 1312 | 0.6 | 6.6667 | 14.5946 | 22.3772 | 2.5934 | 5.1892 | 1 | 5 | 0.2 | 10 | 21.6667
| 1313 | 0.8 | 5 | 10.5882 | 18.1183 | 3.0649 | 4.4651 | 1 | 5 | 0.1 | 20 | 30
| 1314 | 0.4 | 10 | 10.8 | 20.4835 | 2.8263 | 6.8571 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 1315 | 0.6 | 6.6667 | 17.4194 | 24.8327 | 3.1467 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 15
| 1316 | 0.8 | 5 | 7.5 | 13.642 | 3.2329 | 2.9091 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 1317 | 1.2 | 3.3333 | 8.7097 | 14.7108 | 2.4456 | 3.5556 | 1.4 | 3.5714 | 0.1 | 20 | 26.9048
| 1318 | 0.8 | 5 | 11.7391 | 20.2296 | 2.8434 | 5.6471 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1319 | 0.8 | 5 | 11.4894 | 18.283 | 3.746 | 3.0476 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 1320 | 0.4 | 10 | 15.8824 | 22.7828 | 3.2778 | 3.6226 | 1 | 5 | 0.2 | 10 | 25
| 1321 | 0.8 | 5 | 9.8182 | 17.1096 | 2.8263 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 1322 | 0.6 | 6.6667 | 10 | 18.8814 | 3.3957 | 5.4857 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 1323 | 1.2 | 3.3333 | 12 | 20.5153 | 2.6971 | 5.8182 | 0.4 | 12.5 | 0.4 | 5 | 20.8333
| 1324 | 1 | 4 | 19.2857 | 27.1033 | 2.4842 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 1325 | 0.8 | 5 | 10.1887 | 26.5107 | 2.6077 | 13.7143 | 1 | 5 | 0.4 | 5 | 15
| 1326 | 0.6 | 6.6667 | 11.7391 | 19.2097 | 3.4706 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 1327 | 1 | 4 | 14.2105 | 20.7947 | 2.7442 | 3.84 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 1328 | 0.8 | 5 | 15 | 24.8706 | 3.4706 | 6.4 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 1329 | 0.6 | 6.6667 | 14.2105 | 20.1411 | 3.0649 | 2.8657 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 1330 | 0.8 | 5 | 11.7391 | 18.9004 | 2.9873 | 4.1739 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 1331 | 0.6 | 6.6667 | 11.4894 | 20.156 | 2.6667 | 6 | 1 | 5 | 0.4 | 5 | 16.6667
| 1332 | 0.6 | 6.6667 | 20 | 26.8118 | 3.1892 | 3.6226 | 1 | 5 | 0.4 | 5 | 16.6667
| 1333 | 1 | 4 | 9.8182 | 16.8767 | 2.5934 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 1334 | 1 | 4 | 12.8571 | 19.7685 | 3.1467 | 3.7647 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 1335 | 0.8 | 5 | 19.2857 | 27.6447 | 3.0256 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1336 | 1 | 4 | 20.7692 | 29.2096 | 2.6222 | 5.8182 | 1 | 5 | 0.8 | 2.5 | 11.5
| 1337 | 1 | 4 | 14.2105 | 22.2331 | 3.6589 | 4.3636 | 1 | 5 | 0.4 | 5 | 14
| 1338 | 1 | 4 | 13.5 | 19.9336 | 2.878 | 3.5556 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 1339 | 0.8 | 5 | 11.0204 | 24.5214 | 3.3957 | 10.1053 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 1340 | 0.6 | 6.6667 | 13.8462 | 19.7203 | 2.4456 | 3.4286 | 1 | 5 | 0.4 | 5 | 16.6667
| 1341 | 0.4 | 10 | 11.7391 | 19.8486 | 2.2913 | 5.8182 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 1342 | 1 | 4 | 11.25 | 18.7942 | 2.7442 | 4.8 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 1343 | 0.4 | 10 | 18 | 25.7228 | 3.5489 | 4.1739 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 1344 | 0.8 | 5 | 18 | 28.5161 | 3.6589 | 6.8571 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1345 | 0.8 | 5 | 13.8462 | 24.8737 | 3.3475 | 7.68 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 1346 | 0.8 | 5 | 10.1887 | 19.1102 | 3.8689 | 5.0526 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 1347 | 0.6 | 6.6667 | 11.0204 | 17.9704 | 2.95 | 4 | 1.6 | 3.125 | 0.6 | 3.3333 | 13.125
| 1348 | 0.8 | 5 | 11.7391 | 18.7199 | 2.8957 | 4.0851 | 0.4 | 12.5 | 0.6 | 3.3333 | 20.8333
| 1349 | 0.8 | 5 | 10 | 16.1506 | 2.4583 | 3.6923 | 1.4 | 3.5714 | 0.1 | 20 | 28.5714
| 1350 | 0.8 | 5 | 12.2727 | 19.6949 | 2.6222 | 4.8 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 1351 | 0.8 | 5 | 12.2727 | 17.999 | 2.8606 | 2.8657 | 1 | 5 | 0.4 | 5 | 15
| 1352 | 0.4 | 10 | 11.25 | 18.4284 | 3.6875 | 3.4909 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 1353 | 0.4 | 10 | 11.0204 | 17.9473 | 4.72 | 2.2069 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 1354 | 0.2 | 20 | 11.25 | 20.1267 | 3.6875 | 5.1892 | 1.2 | 4.1667 | 0.6 | 3.3333 | 27.5
| 1355 | 0.6 | 6.6667 | 14.2105 | 23.8962 | 3.0649 | 6.6207 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 1356 | 0.6 | 6.6667 | 10.8 | 17.2162 | 2.8606 | 3.5556 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 1357 | 1 | 4 | 10.3846 | 18.4637 | 2.5934 | 5.4857 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 1358 | 1 | 4 | 10.5882 | 17.312 | 3.2329 | 3.4909 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 1359 | 0.6 | 6.6667 | 10.5882 | 17.4913 | 3.3475 | 3.5556 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 1360 | 1.6 | 2.5 | 13.1707 | 19.995 | 3.3957 | 3.4286 | 1.2 | 4.1667 | 0.8 | 2.5 | 9.1667
| 1361 | 0.6 | 6.6667 | 13.8462 | 25.5404 | 2.5514 | 9.1429 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 1362 | 0.4 | 10 | 14.2105 | 20.8186 | 2.8434 | 3.7647 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 1363 | 0.8 | 5 | 20.7692 | 26.8126 | 2.8434 | 3.2 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 1364 | 1 | 4 | 11.0204 | 17.6206 | 2.7602 | 3.84 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 1365 | 0.6 | 6.6667 | 13.8462 | 20.2625 | 2.6517 | 3.7647 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 1366 | 1.2 | 3.3333 | 14.5946 | 24.1145 | 4.0342 | 5.4857 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 1367 | 1.4 | 2.8571 | 9.1525 | 17.1051 | 4.0342 | 3.9184 | 0.6 | 8.3333 | 0.2 | 10 | 21.1905
| 1368 | 1.2 | 3.3333 | 10.8 | 18.2369 | 2.6369 | 4.8 | 1.6 | 3.125 | 0.2 | 10 | 16.4583
| 1369 | 0.8 | 5 | 10 | 15.5173 | 2.4205 | 3.0968 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 1370 | 0.6 | 6.6667 | 12.8571 | 19.0592 | 3.1053 | 3.0968 | 1 | 5 | 0.4 | 5 | 16.6667
| 1371 | 0.2 | 20 | 11.7391 | 18.1443 | 2.5652 | 3.84 | 1.6 | 3.125 | 0.2 | 10 | 33.125
| 1372 | 1 | 4 | 10.5882 | 17.4771 | 2.6222 | 4.2667 | 1 | 5 | 0.8 | 2.5 | 11.5
| 1373 | 1.2 | 3.3333 | 27 | 35.0778 | 3.2778 | 4.8 | 1 | 5 | 0.2 | 10 | 18.3333
| 1374 | 0.6 | 6.6667 | 11.0204 | 21.4502 | 3.0452 | 7.3846 | 1 | 5 | 0.2 | 10 | 21.6667
| 1375 | 0.6 | 6.6667 | 12.5581 | 19.3677 | 2.8095 | 4 | 1.4 | 3.5714 | 0.8 | 2.5 | 12.7381
| 1376 | 0.6 | 6.6667 | 12.2727 | 20.9515 | 2.8606 | 5.8182 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 1377 | 0.4 | 10 | 12.2727 | 18.6308 | 2.5934 | 3.7647 | 1 | 5 | 0.8 | 2.5 | 17.5
| 1378 | 1 | 4 | 12.8571 | 20.5352 | 2.878 | 4.8 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 1379 | 1 | 4 | 7.8261 | 15.6387 | 3.3475 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 1380 | 1.4 | 2.8571 | 16.875 | 23.2942 | 2.5792 | 3.84 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 1381 | 0.8 | 5 | 10 | 17.8614 | 3.6875 | 4.1739 | 1 | 5 | 0.2 | 10 | 20
| 1382 | 0.4 | 10 | 11.0204 | 17.6671 | 2.7283 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 1383 | 0.4 | 10 | 12.8571 | 19.0439 | 3.2329 | 2.9538 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 1384 | 1 | 4 | 12.2727 | 19.5209 | 2.5652 | 4.6829 | 1 | 5 | 0.8 | 2.5 | 11.5
| 1385 | 0.2 | 20 | 11.25 | 18.6178 | 3.6031 | 3.7647 | 1.2 | 4.1667 | 0.1 | 20 | 44.1667
| 1386 | 1.6 | 2.5 | 11.7391 | 19.6005 | 3.6875 | 4.1739 | 1 | 5 | 0.1 | 20 | 27.5
| 1387 | 1.2 | 3.3333 | 8.5714 | 16.0929 | 2.95 | 4.5714 | 0.4 | 12.5 | 0.1 | 20 | 35.8333
| 1388 | 0.8 | 5 | 10.8 | 19.2001 | 3.3475 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 1389 | 0.4 | 10 | 11.25 | 18.5741 | 2.5241 | 4.8 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 1390 | 0.6 | 6.6667 | 12.5581 | 19.8787 | 3.1467 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 1391 | 1 | 4 | 8.4375 | 14.4719 | 3.2109 | 2.8235 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 1392 | 0.6 | 6.6667 | 10.8 | 18.3054 | 3.4203 | 4.0851 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 1393 | 0.4 | 10 | 12.2727 | 19.9351 | 3.3957 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 1394 | 1.4 | 2.8571 | 15.4286 | 23.3968 | 3.0452 | 4.9231 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 1395 | 0.2 | 20 | 10.8 | 18.7821 | 2.7929 | 5.1892 | 1 | 5 | 0.2 | 10 | 35
| 1396 | 1 | 4 | 12.5581 | 24.4058 | 2.2476 | 9.6 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 1397 | 0.2 | 20 | 16.875 | 24.8412 | 2.9136 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 1398 | 0.2 | 20 | 12.2727 | 20.1917 | 3.3475 | 4.5714 | 1.4 | 3.5714 | 0.2 | 10 | 33.5714
| 1399 | 1.2 | 3.3333 | 12 | 18.8656 | 3.0256 | 3.84 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 1400 | 1 | 4 | 11.25 | 20.1133 | 3.0452 | 5.8182 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 1401 | 0.8 | 5 | 12 | 21.5698 | 2.1852 | 7.3846 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 1402 | 0.8 | 5 | 9.4737 | 14.7669 | 2.5106 | 2.7826 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 1403 | 0.4 | 10 | 11.7391 | 17.5014 | 3.3007 | 2.4615 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 1404 | 0.8 | 5 | 12.5581 | 22.5619 | 3.1467 | 6.8571 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 1405 | 0.6 | 6.6667 | 15.4286 | 22.5514 | 2.5514 | 4.5714 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 1406 | 1.2 | 3.3333 | 15.4286 | 22.3761 | 3.2552 | 3.6923 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 1407 | 0.8 | 5 | 12.8571 | 20.1976 | 3.5758 | 3.7647 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1408 | 0.8 | 5 | 10.1887 | 16.2049 | 2.9686 | 3.0476 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1409 | 0.8 | 5 | 13.5 | 21.9174 | 2.9317 | 5.4857 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 1410 | 1 | 4 | 16.3636 | 22.7221 | 3.2109 | 3.1475 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 1411 | 0.4 | 10 | 13.5 | 22.1065 | 3.8065 | 4.8 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 1412 | 1 | 4 | 9.6429 | 17.2402 | 2.4082 | 5.1892 | 0.8 | 6.25 | 1 | 2 | 12.25
| 1413 | 0.8 | 5 | 11.25 | 18.04 | 2.95 | 3.84 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 1414 | 0.8 | 5 | 10.1887 | 17.6409 | 4.2523 | 3.2 | 1 | 5 | 0.8 | 2.5 | 12.5
| 1415 | 1.4 | 2.8571 | 9.3103 | 18.5275 | 2.36 | 6.8571 | 0.6 | 8.3333 | 0.6 | 3.3333 | 14.5238
| 1416 | 0.4 | 10 | 14.5946 | 23.6526 | 3.8689 | 5.1892 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 1417 | 0.4 | 10 | 10.3846 | 16.3193 | 3.0256 | 2.9091 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 1418 | 1 | 4 | 9.8182 | 17.9947 | 2.9873 | 5.1892 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 1419 | 1 | 4 | 12.5581 | 19.8262 | 3.5758 | 3.6923 | 1 | 5 | 0.4 | 5 | 14
| 1420 | 1 | 4 | 11.4894 | 19.3615 | 3.1892 | 4.6829 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 1421 | 1.2 | 3.3333 | 8.8525 | 17.4014 | 3.4963 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 1422 | 0.4 | 10 | 11.4894 | 19.2523 | 3.4963 | 4.2667 | 1 | 5 | 0.2 | 10 | 25
| 1423 | 0.4 | 10 | 13.1707 | 22.3667 | 3.5489 | 5.6471 | 1.4 | 3.5714 | 0.1 | 20 | 33.5714
| 1424 | 0.4 | 10 | 11.0204 | 18.2313 | 3.1258 | 4.0851 | 0.6 | 8.3333 | 0.8 | 2.5 | 20.8333
| 1425 | 1 | 4 | 8.4375 | 15.2259 | 3.2329 | 3.5556 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 1426 | 1 | 4 | 13.5 | 23.0258 | 3.1258 | 6.4 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 1427 | 0.8 | 5 | 8.0597 | 14.6301 | 2.878 | 3.6923 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 1428 | 0.4 | 10 | 13.1707 | 20.4714 | 3.3007 | 4 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 1429 | 0.6 | 6.6667 | 9.8182 | 17.3275 | 2.8263 | 4.6829 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 1430 | 0.8 | 5 | 10.8 | 19.304 | 4.1404 | 4.3636 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 1431 | 1.6 | 2.5 | 13.8462 | 20.2436 | 3.3007 | 3.0968 | 0.6 | 8.3333 | 0.4 | 5 | 15.8333
| 1432 | 0.4 | 10 | 20 | 24.9909 | 2.4974 | 2.4935 | 0.4 | 12.5 | 0.8 | 2.5 | 25
| 1433 | 0.4 | 10 | 15.4286 | 22.7126 | 2.7126 | 4.5714 | 0.4 | 12.5 | 0.2 | 10 | 32.5
| 1434 | 0.6 | 6.6667 | 12 | 18.7018 | 3.2109 | 3.4909 | 1 | 5 | 0.2 | 10 | 21.6667
| 1435 | 0.4 | 10 | 9.8182 | 22.0869 | 3.1258 | 9.1429 | 1 | 5 | 0.1 | 20 | 35
| 1436 | 1.2 | 3.3333 | 12.5581 | 20.0067 | 3.085 | 4.3636 | 1 | 5 | 0.4 | 5 | 13.3333
| 1437 | 0.8 | 5 | 11.4894 | 21.2153 | 3.1053 | 6.6207 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 1438 | 1.6 | 2.5 | 14.5946 | 22.0654 | 3.6308 | 3.84 | 1 | 5 | 0.4 | 5 | 12.5
| 1439 | 0.8 | 5 | 13.5 | 22.849 | 2.7283 | 6.6207 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 1440 | 0.8 | 5 | 7.6056 | 19.4796 | 3.1467 | 8.7273 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 1441 | 0.6 | 6.6667 | 12.5581 | 19.0064 | 3.3007 | 3.1475 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 1442 | 0.2 | 20 | 7.8261 | 15.667 | 2.6517 | 5.1892 | 0.8 | 6.25 | 0.1 | 20 | 46.25
| 1443 | 1.4 | 2.8571 | 17.4194 | 25.3527 | 2.7442 | 5.1892 | 1.4 | 3.5714 | 0.1 | 20 | 26.4286
| 1444 | 0.8 | 5 | 12.5581 | 20.3042 | 3.746 | 4 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1445 | 0.8 | 5 | 14.5946 | 22.6497 | 2.237 | 5.8182 | 1 | 5 | 0.8 | 2.5 | 12.5
| 1446 | 0.8 | 5 | 11.4894 | 18.141 | 2.6517 | 4 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 1447 | 0.6 | 6.6667 | 12 | 20.4456 | 2.4456 | 6 | 1 | 5 | 0.4 | 5 | 16.6667
| 1448 | 0.8 | 5 | 14.2105 | 23.4772 | 3.9333 | 5.3333 | 0.4 | 12.5 | 0.1 | 20 | 37.5
| 1449 | 1.6 | 2.5 | 13.5 | 19.6817 | 3.085 | 3.0968 | 1.6 | 3.125 | 0.6 | 3.3333 | 8.9583
| 1450 | 1.2 | 3.3333 | 11.4894 | 19.4571 | 3.1678 | 4.8 | 0.8 | 6.25 | 1 | 2 | 11.5833
| 1451 | 1 | 4 | 8.7097 | 15.3559 | 3.2778 | 3.3684 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 1452 | 1 | 4 | 10.5882 | 17.7866 | 3.5758 | 3.6226 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 1453 | 0.8 | 5 | 16.875 | 23.4715 | 3.5489 | 3.0476 | 0.8 | 6.25 | 1 | 2 | 13.25
| 1454 | 0.2 | 20 | 8.1818 | 15.1143 | 3.1678 | 3.7647 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 1455 | 0.4 | 10 | 10.8 | 17.1555 | 3.0452 | 3.3103 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 1456 | 0.2 | 20 | 11.7391 | 18.759 | 3.2552 | 3.7647 | 1 | 5 | 0.4 | 5 | 30
| 1457 | 0.6 | 6.6667 | 11.4894 | 17.3995 | 2.1455 | 3.7647 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 1458 | 0.8 | 5 | 12.2727 | 19.1411 | 2.95 | 3.9184 | 1.6 | 3.125 | 0.6 | 3.3333 | 11.4583
| 1459 | 1.2 | 3.3333 | 11.4894 | 18.9876 | 2.4456 | 5.0526 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 1460 | 1.2 | 3.3333 | 13.8462 | 27.135 | 2.6222 | 10.6667 | 1 | 5 | 0.4 | 5 | 13.3333
| 1461 | 0.8 | 5 | 15.4286 | 21.4221 | 3.2109 | 2.7826 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 1462 | 0.2 | 20 | 20 | 31.6773 | 2.95 | 8.7273 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 1463 | 1 | 4 | 12.5581 | 19.4833 | 3.2329 | 3.6923 | 1 | 5 | 0.2 | 10 | 19
| 1464 | 0.4 | 10 | 11.25 | 18.0763 | 2.8263 | 4 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 1465 | 1.2 | 3.3333 | 8.1818 | 15.8791 | 3.1258 | 4.5714 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 1466 | 0.8 | 5 | 12 | 20.1579 | 3.1053 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 1467 | 0.6 | 6.6667 | 10.3846 | 19.5294 | 2.5241 | 6.6207 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 1468 | 1 | 4 | 10.1887 | 18.0342 | 2.7929 | 5.0526 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 1469 | 0.8 | 5 | 16.875 | 22.9006 | 3.0256 | 3 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1470 | 1 | 4 | 8.4375 | 13.4916 | 2.7126 | 2.3415 | 0.6 | 8.3333 | 1 | 2 | 14.3333
| 1471 | 0.8 | 5 | 12.5581 | 21.4538 | 2.8957 | 6 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 1472 | 1 | 4 | 13.8462 | 20.2668 | 2.7283 | 3.6923 | 0.6 | 8.3333 | 1 | 2 | 14.3333
| 1473 | 1 | 4 | 13.5 | 21.5783 | 3.0256 | 5.0526 | 1 | 5 | 0.4 | 5 | 14
| 1474 | 0.2 | 20 | 15 | 22.1333 | 3.9333 | 3.2 | 1 | 5 | 0.4 | 5 | 30
| 1475 | 0.6 | 6.6667 | 15.8824 | 25.2055 | 3.8374 | 5.4857 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 1476 | 1.2 | 3.3333 | 11.4894 | 19.8198 | 3.2778 | 5.0526 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 1477 | 0.4 | 10 | 8.7097 | 13.9005 | 2.3251 | 2.8657 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 1478 | 1 | 4 | 11.4894 | 20.2949 | 2.9873 | 5.8182 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 1479 | 0.8 | 5 | 14.5946 | 21.3923 | 2.7126 | 4.0851 | 1 | 5 | 0.2 | 10 | 20
| 1480 | 1 | 4 | 14.2105 | 20.5455 | 3.6308 | 2.7042 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 1481 | 0.4 | 10 | 10 | 19.9446 | 3.3239 | 6.6207 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 1482 | 0.8 | 5 | 13.1707 | 21.8755 | 3.3714 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1483 | 1 | 4 | 9.6429 | 17.7211 | 3.0256 | 5.0526 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 1484 | 0.4 | 10 | 18.6207 | 26.325 | 2.6517 | 5.0526 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 1485 | 0.8 | 5 | 13.8462 | 23.7821 | 2.5514 | 7.3846 | 1 | 5 | 0.4 | 5 | 15
| 1486 | 0.6 | 6.6667 | 8.5714 | 15.2176 | 3.2778 | 3.3684 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 1487 | 0.6 | 6.6667 | 12.5581 | 20.0571 | 3.6589 | 3.84 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 1488 | 0.8 | 5 | 10.1887 | 16.6547 | 2.8434 | 3.6226 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 1489 | 1 | 4 | 9.4737 | 15.5391 | 2.6369 | 3.4286 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 1490 | 0.6 | 6.6667 | 11.7391 | 17.7611 | 2.5934 | 3.4286 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 1491 | 1 | 4 | 10.3846 | 16.7632 | 2.95 | 3.4286 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 1492 | 0.4 | 10 | 13.8462 | 20.8731 | 2.7602 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 1493 | 1 | 4 | 11.25 | 19.9107 | 4.9684 | 3.6923 | 1 | 5 | 0.4 | 5 | 14
| 1494 | 0.8 | 5 | 10.8 | 17.3406 | 2.6222 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1495 | 0.2 | 20 | 10.1887 | 19.176 | 2.9873 | 6 | 1 | 5 | 0.4 | 5 | 30
| 1496 | 0.4 | 10 | 19.2857 | 27.5175 | 3.5489 | 4.6829 | 1 | 5 | 0.4 | 5 | 20
| 1497 | 0.6 | 6.6667 | 13.5 | 18.6012 | 2.6077 | 2.4935 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 1498 | 0.8 | 5 | 10 | 18.1526 | 3.6875 | 4.4651 | 1 | 5 | 0.1 | 20 | 30
| 1499 | 1 | 4 | 8.8525 | 17.229 | 3.3239 | 5.0526 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 1500 | 0.8 | 5 | 16.3636 | 23.6489 | 3.4453 | 3.84 | 1 | 5 | 0.2 | 10 | 20
| 1501 | 0.6 | 6.6667 | 12.2727 | 17.6212 | 2.6818 | 2.6667 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 1502 | 0.4 | 10 | 13.8462 | 21.2752 | 3.2552 | 4.1739 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 1503 | 1 | 4 | 14.2105 | 28.6561 | 2.4456 | 12 | 1 | 5 | 0.2 | 10 | 19
| 1504 | 0.8 | 5 | 20.7692 | 28.4 | 3.6308 | 4 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 1505 | 0.8 | 5 | 10 | 16.1859 | 2.9317 | 3.2542 | 1.6 | 3.125 | 0.2 | 10 | 18.125
| 1506 | 0.6 | 6.6667 | 15.8824 | 22.8264 | 3.0256 | 3.9184 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 1507 | 1.4 | 2.8571 | 15 | 22.0861 | 4.177 | 2.9091 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 1508 | 1 | 4 | 11.0204 | 18.4094 | 3.4706 | 3.9184 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 1509 | 1.2 | 3.3333 | 9.8182 | 15.9214 | 2.7929 | 3.3103 | 1 | 5 | 0.4 | 5 | 13.3333
| 1510 | 1 | 4 | 11.7391 | 20.5487 | 2.8095 | 6 | 1 | 5 | 0.4 | 5 | 14
| 1511 | 0.6 | 6.6667 | 11.7391 | 18.0545 | 3.1678 | 3.1475 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 1512 | 0.4 | 10 | 10.5882 | 18.6936 | 2.4583 | 5.6471 | 1.6 | 3.125 | 0.2 | 10 | 23.125
| 1513 | 0.8 | 5 | 8.7097 | 14.9422 | 3.085 | 3.1475 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 1514 | 0.8 | 5 | 11.0204 | 20.2989 | 3.085 | 6.1935 | 1 | 5 | 0.2 | 10 | 20
| 1515 | 0.8 | 5 | 10.5882 | 20.4085 | 3.4203 | 6.4 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 1516 | 0.1 | 40 | 14.5946 | 21.9932 | 3.776 | 3.6226 | 1 | 5 | 0.4 | 5 | 50
| 1517 | 1 | 4 | 16.875 | 27.2368 | 2.6818 | 7.68 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 1518 | 1.2 | 3.3333 | 13.5 | 21.1059 | 3.6875 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 1519 | 0.8 | 5 | 16.3636 | 25.7285 | 2.7442 | 6.6207 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1520 | 0.6 | 6.6667 | 15 | 22.2167 | 2.95 | 4.2667 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 1521 | 1 | 4 | 13.5 | 20.1483 | 3.0256 | 3.6226 | 1 | 5 | 0.4 | 5 | 14
| 1522 | 0.2 | 20 | 12.8571 | 19.9624 | 3.1053 | 4 | 1 | 5 | 0.4 | 5 | 30
| 1523 | 0.6 | 6.6667 | 9.6429 | 16.2719 | 3.0064 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 1524 | 0.6 | 6.6667 | 13.5 | 21.6765 | 2.9873 | 5.1892 | 1 | 5 | 0.6 | 3.3333 | 15
| 1525 | 1.4 | 2.8571 | 11.7391 | 21.9906 | 3.6308 | 6.6207 | 1 | 5 | 0.2 | 10 | 17.8571
| 1526 | 1 | 4 | 13.1707 | 19.7947 | 2.9317 | 3.6923 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 1527 | 0.8 | 5 | 9.8182 | 16.2374 | 2.5792 | 3.84 | 1 | 5 | 0.2 | 10 | 20
| 1528 | 1.2 | 3.3333 | 12.2727 | 18.76 | 2.9317 | 3.5556 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 1529 | 0.4 | 10 | 9 | 19.3333 | 3.9333 | 6.4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 1530 | 0.6 | 6.6667 | 9.8182 | 17.1053 | 3.5224 | 3.7647 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 1531 | 0.6 | 6.6667 | 12 | 21.5467 | 3.1467 | 6.4 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 1532 | 0.4 | 10 | 9.8182 | 18.4716 | 3.0064 | 5.6471 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 1533 | 0.4 | 10 | 10 | 22.3106 | 3.1678 | 9.1429 | 1.2 | 4.1667 | 0.1 | 20 | 34.1667
| 1534 | 0.4 | 10 | 14.2105 | 24.6686 | 3.8374 | 6.6207 | 1 | 5 | 0.4 | 5 | 20
| 1535 | 0.6 | 6.6667 | 10.5882 | 16.5382 | 2.95 | 3 | 1 | 5 | 0.4 | 5 | 16.6667
| 1536 | 1 | 4 | 12.5581 | 21.8717 | 2.9136 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 1537 | 1.6 | 2.5 | 11.7391 | 20.1051 | 3.9008 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 11.6667
| 1538 | 1 | 4 | 10.5882 | 20.5774 | 2.878 | 7.1111 | 1 | 5 | 0.4 | 5 | 14
| 1539 | 0.8 | 5 | 11.25 | 18.6736 | 3.6589 | 3.7647 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1540 | 1.6 | 2.5 | 12.8571 | 18.5317 | 2.9317 | 2.7429 | 1.4 | 3.5714 | 0.1 | 20 | 26.0714
| 1541 | 0.8 | 5 | 10.5882 | 19.3938 | 2.9873 | 5.8182 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 1542 | 0.2 | 20 | 13.5 | 21.1995 | 2.7765 | 4.9231 | 1 | 5 | 0.4 | 5 | 30
| 1543 | 1 | 4 | 8.8525 | 16.5169 | 3.746 | 3.9184 | 1 | 5 | 0.4 | 5 | 14
| 1544 | 1 | 4 | 12.8571 | 18.7173 | 2.7126 | 3.1475 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 1545 | 1 | 4 | 12.8571 | 19.0204 | 2.6077 | 3.5556 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 1546 | 0.8 | 5 | 10 | 17.7351 | 3.3714 | 4.3636 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 1547 | 0.6 | 6.6667 | 10.8 | 20.149 | 2.7283 | 6.6207 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 1548 | 0.8 | 5 | 10.3846 | 18.7053 | 2.9873 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1549 | 0.6 | 6.6667 | 12.8571 | 19.8734 | 3.3239 | 3.6923 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 1550 | 1.2 | 3.3333 | 11.0204 | 20.2789 | 3.0649 | 6.1935 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 1551 | 1 | 4 | 11.0204 | 20.164 | 2.95 | 6.1935 | 0.4 | 12.5 | 0.1 | 20 | 36.5
| 1552 | 0.6 | 6.6667 | 12.5581 | 20.391 | 3.6589 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 1553 | 1 | 4 | 15.4286 | 25.6246 | 3.085 | 7.1111 | 1.8 | 2.7778 | 0.4 | 5 | 11.7778
| 1554 | 0.6 | 6.6667 | 11.0204 | 18.7888 | 2.5792 | 5.1892 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 1555 | 0.8 | 5 | 9.8182 | 16.6646 | 3.0064 | 3.84 | 1 | 5 | 0.2 | 10 | 20
| 1556 | 1.2 | 3.3333 | 9.1525 | 17.6758 | 3.4706 | 5.0526 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 1557 | 0.4 | 10 | 10.8 | 18.9548 | 2.3366 | 5.8182 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 1558 | 0.4 | 10 | 9.4737 | 18.3504 | 3.6875 | 5.1892 | 1 | 5 | 0.4 | 5 | 20
| 1559 | 1 | 4 | 15.4286 | 24.5205 | 2.4712 | 6.6207 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 1560 | 0.6 | 6.6667 | 13.5 | 20.6239 | 2.95 | 4.1739 | 1 | 5 | 0.4 | 5 | 16.6667
| 1561 | 0.4 | 10 | 11.7391 | 17.7012 | 2.4712 | 3.4909 | 1 | 5 | 0.2 | 10 | 25
| 1562 | 0.8 | 5 | 16.875 | 24.1522 | 2.9136 | 4.3636 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1563 | 0.8 | 5 | 15 | 21.6706 | 3.4706 | 3.2 | 1 | 5 | 0.2 | 10 | 20
| 1564 | 0.8 | 5 | 9.3103 | 16.6613 | 2.9873 | 4.3636 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 1565 | 0.8 | 5 | 11.4894 | 18.3517 | 3.3714 | 3.4909 | 1 | 5 | 0.8 | 2.5 | 12.5
| 1566 | 1.2 | 3.3333 | 20.7692 | 26.6843 | 3.2109 | 2.7042 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 1567 | 0.4 | 10 | 15.4286 | 21.3066 | 2.878 | 3 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 1568 | 1 | 4 | 11.0204 | 18.8628 | 3.5758 | 4.2667 | 1 | 5 | 0.4 | 5 | 14
| 1569 | 1.2 | 3.3333 | 13.1707 | 20.9122 | 2.4082 | 5.3333 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 1570 | 0.6 | 6.6667 | 13.5 | 21.7855 | 3.2329 | 5.0526 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 1571 | 1.4 | 2.8571 | 12.5581 | 22.9021 | 3.2329 | 7.1111 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 1572 | 0.8 | 5 | 9.1525 | 16.587 | 3.1678 | 4.2667 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1573 | 0.2 | 20 | 12.5581 | 19.9715 | 3.1467 | 4.2667 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 1574 | 1 | 4 | 9.8182 | 17.1613 | 2.878 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 1575 | 1.2 | 3.3333 | 8.8525 | 20.1302 | 3.2778 | 8 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 1576 | 0.8 | 5 | 12.5581 | 18.1387 | 2.433 | 3.1475 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1577 | 1 | 4 | 12.5581 | 21.2127 | 4.2909 | 4.3636 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 1578 | 0.6 | 6.6667 | 9.4737 | 17.3863 | 2.5792 | 5.3333 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 1579 | 0.2 | 20 | 9.8182 | 17.2612 | 3.6031 | 3.84 | 0.8 | 6.25 | 0.8 | 2.5 | 28.75
| 1580 | 1.2 | 3.3333 | 12.5581 | 19.1393 | 3.0256 | 3.5556 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 1581 | 0.8 | 5 | 12.8571 | 21.0047 | 3.3475 | 4.8 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 1582 | 0.8 | 5 | 15 | 24.6463 | 3.0256 | 6.6207 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 1583 | 1 | 4 | 11.4894 | 18.6696 | 2.9136 | 4.2667 | 1 | 5 | 0.4 | 5 | 14
| 1584 | 0.6 | 6.6667 | 11.0204 | 17.7965 | 3.3475 | 3.4286 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 1585 | 1.2 | 3.3333 | 12 | 23.2795 | 2.9317 | 8.3478 | 1.4 | 3.5714 | 0.8 | 2.5 | 9.4048
| 1586 | 0.4 | 10 | 10 | 16.3115 | 2.2264 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 1587 | 0.4 | 10 | 25.7143 | 34.9777 | 3.4453 | 5.8182 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 1588 | 1.6 | 2.5 | 15.8824 | 24.2114 | 2.8434 | 5.4857 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.0833
| 1589 | 0.2 | 20 | 11.0204 | 17.1491 | 2.7602 | 3.3684 | 1.2 | 4.1667 | 0.8 | 2.5 | 26.6667
| 1590 | 0.6 | 6.6667 | 12.8571 | 20.0363 | 2.6077 | 4.5714 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 1591 | 0.8 | 5 | 11.25 | 20.8987 | 2.5376 | 7.1111 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 1592 | 1 | 4 | 12.2727 | 19.2677 | 2.7283 | 4.2667 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 1593 | 0.8 | 5 | 13.8462 | 20.4914 | 3.4453 | 3.2 | 1 | 5 | 0.1 | 20 | 30
| 1594 | 1 | 4 | 13.5 | 18.8067 | 2.5241 | 2.7826 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 1595 | 0.6 | 6.6667 | 18.6207 | 24.6675 | 2.95 | 3.0968 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 1596 | 1.2 | 3.3333 | 9 | 16.4594 | 2.7765 | 4.6829 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 1597 | 0.8 | 5 | 11.4894 | 17.5361 | 2.95 | 3.0968 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 1598 | 1.2 | 3.3333 | 10.1887 | 18.8742 | 3.4963 | 5.1892 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 1599 | 0.8 | 5 | 12.8571 | 19.9167 | 2.7929 | 4.2667 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 1600 | 0.2 | 20 | 16.3636 | 24.6774 | 2.6667 | 5.6471 | 0.8 | 6.25 | 0.8 | 2.5 | 28.75
| 1601 | 0.2 | 20 | 10 | 18.4483 | 3.3957 | 5.0526 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 1602 | 1.4 | 2.8571 | 10.5882 | 16.9122 | 3.3239 | 3 | 1 | 5 | 0.2 | 10 | 17.8571
| 1603 | 0.4 | 10 | 13.1707 | 20.4667 | 3.2109 | 4.0851 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 1604 | 0.4 | 10 | 14.5946 | 21.8627 | 3.5758 | 3.6923 | 1 | 5 | 0.4 | 5 | 20
| 1605 | 0.1 | 40 | 12.2727 | 18.7253 | 2.7602 | 3.6923 | 0.8 | 6.25 | 0.2 | 10 | 56.25
| 1606 | 0.8 | 5 | 9.1525 | 16.8112 | 3.9664 | 3.6923 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 1607 | 0.4 | 10 | 12 | 23.1453 | 4.0342 | 7.1111 | 1 | 5 | 0.8 | 2.5 | 17.5
| 1608 | 1.2 | 3.3333 | 11.4894 | 17.6242 | 2.9873 | 3.1475 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 1609 | 1.6 | 2.5 | 10 | 20.391 | 3.0064 | 7.3846 | 1 | 5 | 0.6 | 3.3333 | 10.8333
| 1610 | 0.6 | 6.6667 | 9.3103 | 15.848 | 2.5376 | 4 | 1 | 5 | 0.2 | 10 | 21.6667
| 1611 | 1 | 4 | 15 | 22.7344 | 2.6818 | 5.0526 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 1612 | 0.4 | 10 | 15.8824 | 22.7379 | 3.2329 | 3.6226 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 1613 | 1.6 | 2.5 | 10.8 | 21.7578 | 3.2778 | 7.68 | 1.4 | 3.5714 | 0.2 | 10 | 16.0714
| 1614 | 1 | 4 | 14.2105 | 20.3612 | 2.4583 | 3.6923 | 1 | 5 | 0.8 | 2.5 | 11.5
| 1615 | 0.4 | 10 | 12.2727 | 20.2061 | 2.7442 | 5.1892 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 1616 | 0.8 | 5 | 8.5714 | 14.3793 | 2.1852 | 3.6226 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1617 | 1.2 | 3.3333 | 16.3636 | 24.8135 | 5.0213 | 3.4286 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 1618 | 1.2 | 3.3333 | 12 | 18.6609 | 2.9686 | 3.6923 | 1 | 5 | 0.2 | 10 | 18.3333
| 1619 | 0.6 | 6.6667 | 16.3636 | 22.4853 | 3.1678 | 2.9538 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 1620 | 0.6 | 6.6667 | 11.4894 | 18.6186 | 3.2109 | 3.9184 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 1621 | 1.2 | 3.3333 | 18 | 25.5492 | 2.36 | 5.1892 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 1622 | 0.8 | 5 | 14.5946 | 20.3606 | 3.3957 | 2.3704 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 1623 | 0.6 | 6.6667 | 20 | 26.8095 | 2.8095 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 1624 | 0.4 | 10 | 12 | 19.0593 | 3.6308 | 3.4286 | 0.4 | 12.5 | 0.2 | 10 | 32.5
| 1625 | 0.8 | 5 | 12.5581 | 18.8691 | 3.4453 | 2.8657 | 1 | 5 | 0.2 | 10 | 20
| 1626 | 0.8 | 5 | 12.5581 | 20.0254 | 3.5489 | 3.9184 | 1 | 5 | 0.4 | 5 | 15
| 1627 | 1.4 | 2.8571 | 18.6207 | 24.8095 | 2.7602 | 3.4286 | 1 | 5 | 0.8 | 2.5 | 10.3571
| 1628 | 0.8 | 5 | 13.1707 | 21.9307 | 2.36 | 6.4 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 1629 | 1.4 | 2.8571 | 15 | 20.6582 | 2.5106 | 3.1475 | 0.8 | 6.25 | 0.8 | 2.5 | 11.6071
| 1630 | 0.4 | 10 | 12.8571 | 18.9304 | 3.0256 | 3.0476 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 1631 | 1.4 | 2.8571 | 18.6207 | 25.4696 | 3.4203 | 3.4286 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 1632 | 0.8 | 5 | 9.6429 | 18.1322 | 3.8065 | 4.6829 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 1633 | 0.4 | 10 | 13.1707 | 18.9626 | 2.5376 | 3.2542 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 1634 | 1 | 4 | 9.8182 | 19.0074 | 4 | 5.1892 | 1 | 5 | 0.4 | 5 | 14
| 1635 | 1.2 | 3.3333 | 12.5581 | 20.7521 | 2.8606 | 5.3333 | 0.4 | 12.5 | 0.8 | 2.5 | 18.3333
| 1636 | 0.8 | 5 | 16.3636 | 24.0722 | 3.0256 | 4.6829 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 1637 | 0.8 | 5 | 16.3636 | 25.8984 | 3.7165 | 5.8182 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 1638 | 1.4 | 2.8571 | 10.3846 | 19.378 | 2.5934 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 1639 | 1.2 | 3.3333 | 15.8824 | 26.5104 | 2.2802 | 8.3478 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 1640 | 1.2 | 3.3333 | 12.2727 | 21.3904 | 3.4706 | 5.6471 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 1641 | 1 | 4 | 10.1887 | 17.954 | 2.7126 | 5.0526 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 1642 | 1.2 | 3.3333 | 12.8571 | 20.8408 | 4.6733 | 3.3103 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 1643 | 0.8 | 5 | 14.5946 | 20.4903 | 2.8957 | 3 | 1.4 | 3.5714 | 0.1 | 20 | 28.5714
| 1644 | 0.6 | 6.6667 | 9.8182 | 16.8112 | 3.3007 | 3.6923 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 1645 | 1.2 | 3.3333 | 14.2105 | 22.0529 | 2.1953 | 5.6471 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 1646 | 0.8 | 5 | 12 | 19.207 | 2.5241 | 4.6829 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1647 | 0.8 | 5 | 11.0204 | 19.5664 | 3.746 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1648 | 0.6 | 6.6667 | 14.5946 | 23.6764 | 2.6818 | 6.4 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 1649 | 0.8 | 5 | 17.4194 | 26.1595 | 3.6875 | 5.0526 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 1650 | 0.6 | 6.6667 | 13.1707 | 24.9891 | 3.4706 | 8.3478 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 1651 | 1.2 | 3.3333 | 14.5946 | 20.1877 | 2.4456 | 3.1475 | 1.6 | 3.125 | 0.4 | 5 | 11.4583
| 1652 | 1.2 | 3.3333 | 10.3846 | 16.6562 | 2.5792 | 3.6923 | 1.6 | 3.125 | 0.4 | 5 | 11.4583
| 1653 | 0.6 | 6.6667 | 11.0204 | 19.8817 | 5.0213 | 3.84 | 1 | 5 | 0.4 | 5 | 16.6667
| 1654 | 1 | 4 | 10.5882 | 18.8145 | 2.5792 | 5.6471 | 0.4 | 12.5 | 0.8 | 2.5 | 19
| 1655 | 0.6 | 6.6667 | 13.5 | 21.8463 | 2.8606 | 5.4857 | 1 | 5 | 0.4 | 5 | 16.6667
| 1656 | 0.6 | 6.6667 | 11.4894 | 17.7224 | 3.3239 | 2.9091 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 1657 | 0.6 | 6.6667 | 12.8571 | 22.1352 | 2.878 | 6.4 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 1658 | 0.4 | 10 | 9.3103 | 19.3353 | 3.1678 | 6.8571 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 1659 | 0.8 | 5 | 12.2727 | 20.4493 | 2.9873 | 5.1892 | 1.4 | 3.5714 | 0.1 | 20 | 28.5714
| 1660 | 0.8 | 5 | 15.4286 | 21.6446 | 2.5934 | 3.6226 | 1 | 5 | 0.4 | 5 | 15
| 1661 | 0.8 | 5 | 11.4894 | 21.6654 | 3.0649 | 7.1111 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 1662 | 1 | 4 | 11.7391 | 20.8704 | 4.7677 | 4.3636 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 1663 | 0.6 | 6.6667 | 11.7391 | 19.4224 | 2.7602 | 4.9231 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 1664 | 0.4 | 10 | 10.5882 | 18.9998 | 2.5934 | 5.8182 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 1665 | 0.6 | 6.6667 | 15.4286 | 22.8 | 3.3714 | 4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 1666 | 1 | 4 | 11.7391 | 20.0686 | 5.0753 | 3.2542 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 1667 | 0.8 | 5 | 12.2727 | 19.0868 | 2.8957 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1668 | 0.8 | 5 | 13.8462 | 20.7627 | 3.7165 | 3.2 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1669 | 1 | 4 | 10.8 | 17.3726 | 2.95 | 3.6226 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 1670 | 1 | 4 | 13.8462 | 22.5757 | 3.8065 | 4.9231 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 1671 | 0.8 | 5 | 11.7391 | 18.2051 | 2.8434 | 3.6226 | 1 | 5 | 0.4 | 5 | 15
| 1672 | 0.6 | 6.6667 | 9.8182 | 17.4445 | 2.8263 | 4.8 | 1.6 | 3.125 | 0.4 | 5 | 14.7917
| 1673 | 1.2 | 3.3333 | 14.5946 | 23.9492 | 3.8689 | 5.4857 | 1.6 | 3.125 | 0.8 | 2.5 | 8.9583
| 1674 | 1 | 4 | 18 | 25.2871 | 3.5224 | 3.7647 | 1 | 5 | 0.4 | 5 | 14
| 1675 | 0.4 | 10 | 13.5 | 19.109 | 2.8263 | 2.7826 | 1 | 5 | 0.4 | 5 | 20
| 1676 | 0.8 | 5 | 7.9412 | 15.0007 | 2.7929 | 4.2667 | 1.6 | 3.125 | 0.8 | 2.5 | 10.625
| 1677 | 1 | 4 | 18.6207 | 25.6406 | 3.2552 | 3.7647 | 1 | 5 | 0.8 | 2.5 | 11.5
| 1678 | 0.8 | 5 | 10.8 | 17.4376 | 3.1467 | 3.4909 | 1 | 5 | 0.1 | 20 | 30
| 1679 | 1.2 | 3.3333 | 15 | 24.1809 | 2.9873 | 6.1935 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 1680 | 0.4 | 10 | 12.2727 | 21.1818 | 3.5758 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 1681 | 1.2 | 3.3333 | 10.5882 | 18.7597 | 3.3714 | 4.8 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 1682 | 1 | 4 | 10 | 17.1498 | 3.6589 | 3.4909 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 1683 | 0.8 | 5 | 8.5714 | 16.0564 | 2.9136 | 4.5714 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 1684 | 1.2 | 3.3333 | 13.1707 | 19.4075 | 3.1892 | 3.0476 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 1685 | 0.4 | 10 | 10 | 16.2585 | 3.2109 | 3.0476 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 1686 | 0.8 | 5 | 9.3103 | 16.5007 | 3.1053 | 4.0851 | 1 | 5 | 0.1 | 20 | 30
| 1687 | 1.6 | 2.5 | 9.6429 | 17.7611 | 2.4712 | 5.6471 | 0.8 | 6.25 | 0.8 | 2.5 | 11.25
| 1688 | 1.2 | 3.3333 | 25.7143 | 33.4535 | 3.1678 | 4.5714 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 1689 | 0.8 | 5 | 7.9412 | 13.6314 | 2.5934 | 3.0968 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1690 | 1.2 | 3.3333 | 12.5581 | 19.6361 | 3.5224 | 3.5556 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 1691 | 0.8 | 5 | 12.5581 | 20.8544 | 3.4963 | 4.8 | 1 | 5 | 0.2 | 10 | 20
| 1692 | 1 | 4 | 10.5882 | 19.7059 | 3.4706 | 5.6471 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 1693 | 1.2 | 3.3333 | 9 | 17.5662 | 3.2329 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 1694 | 1.6 | 2.5 | 11.7391 | 21.6766 | 2.8263 | 7.1111 | 1 | 5 | 0.4 | 5 | 12.5
| 1695 | 0.6 | 6.6667 | 16.3636 | 21.9109 | 2.5934 | 2.9538 | 1 | 5 | 0.2 | 10 | 21.6667
| 1696 | 0.6 | 6.6667 | 15.8824 | 24.3536 | 2.4712 | 6 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 1697 | 1 | 4 | 12.5581 | 22.5355 | 4.3303 | 5.6471 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 1698 | 0.8 | 5 | 12.8571 | 20.379 | 3.2552 | 4.2667 | 1 | 5 | 0.2 | 10 | 20
| 1699 | 1.2 | 3.3333 | 11.25 | 20.7553 | 3.1053 | 6.4 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 1700 | 0.8 | 5 | 11.25 | 21.61 | 2.36 | 8 | 1 | 5 | 0.2 | 10 | 20
| 1701 | 1.2 | 3.3333 | 11.4894 | 17.1566 | 1.9749 | 3.6923 | 1 | 5 | 0.2 | 10 | 18.3333
| 1702 | 0.8 | 5 | 11.4894 | 20.2498 | 3.8374 | 4.9231 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 1703 | 0.4 | 10 | 10.3846 | 17.4676 | 4.4528 | 2.6301 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 1704 | 0.4 | 10 | 12.2727 | 19.6878 | 2.95 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 1705 | 1.2 | 3.3333 | 10.8 | 18.6507 | 3.1678 | 4.6829 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 1706 | 1 | 4 | 14.2105 | 19.5948 | 2.3366 | 3.0476 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 1707 | 0.6 | 6.6667 | 15 | 25.2734 | 2.5934 | 7.68 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 1708 | 1.4 | 2.8571 | 23.4783 | 28.7053 | 2.4842 | 2.7429 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 1709 | 0.2 | 20 | 11.4894 | 21.5141 | 2.9136 | 7.1111 | 1 | 5 | 0.2 | 10 | 35
| 1710 | 0.6 | 6.6667 | 11.4894 | 19.6133 | 3.3239 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 1711 | 0.4 | 10 | 16.3636 | 23.5249 | 2.9873 | 4.1739 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 1712 | 0.6 | 6.6667 | 11.25 | 20.9141 | 3.4706 | 6.1935 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 1713 | 1 | 4 | 14.2105 | 22.6828 | 3.9008 | 4.5714 | 1 | 5 | 0.2 | 10 | 19
| 1714 | 0.8 | 5 | 10.5882 | 18.4496 | 3.6875 | 4.1739 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 1715 | 0.6 | 6.6667 | 9.4737 | 15.2988 | 2.7283 | 3.0968 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 1716 | 1.2 | 3.3333 | 11.25 | 19.8349 | 3.3957 | 5.1892 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 1717 | 0.2 | 20 | 13.1707 | 20.9365 | 3.3007 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 1718 | 0.8 | 5 | 15.8824 | 28.447 | 3.8374 | 8.7273 | 1 | 5 | 0.4 | 5 | 15
| 1719 | 1.4 | 2.8571 | 11.0204 | 24.9649 | 3.2778 | 10.6667 | 1.6 | 3.125 | 0.4 | 5 | 10.9821
| 1720 | 1.4 | 2.8571 | 10 | 18.4894 | 3.8065 | 4.6829 | 0.6 | 8.3333 | 0.1 | 20 | 31.1905
| 1721 | 0.4 | 10 | 13.5 | 21.0674 | 3.3007 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 1722 | 1.4 | 2.8571 | 14.2105 | 20.8805 | 3.5224 | 3.1475 | 1.2 | 4.1667 | 0.1 | 20 | 27.0238
| 1723 | 1 | 4 | 14.5946 | 23.5298 | 3.746 | 5.1892 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 1724 | 1.4 | 2.8571 | 11.0204 | 17.4941 | 3.1053 | 3.3684 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 1725 | 0.8 | 5 | 14.2105 | 22.5765 | 3.9008 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 1726 | 0.1 | 40 | 13.8462 | 21.5068 | 2.8606 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 51.25
| 1727 | 0.2 | 20 | 12 | 20.2963 | 3.4963 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 1728 | 1 | 4 | 12.8571 | 18.8493 | 2.6818 | 3.3103 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 1729 | 1 | 4 | 10.5882 | 17.2339 | 3.5489 | 3.0968 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 1730 | 1.2 | 3.3333 | 8.8525 | 14.3662 | 2.3137 | 3.2 | 1.6 | 3.125 | 0.6 | 3.3333 | 9.7917
| 1731 | 0.2 | 20 | 14.5946 | 20.8947 | 2.9317 | 3.3684 | 1.4 | 3.5714 | 0.8 | 2.5 | 26.0714
| 1732 | 0.2 | 20 | 12.5581 | 21.9409 | 3.1892 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 1733 | 0.8 | 5 | 12 | 19.7325 | 4.177 | 3.5556 | 1.4 | 3.5714 | 0.8 | 2.5 | 11.0714
| 1734 | 0.4 | 10 | 10.1887 | 16.3962 | 3.746 | 2.4615 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 1735 | 1 | 4 | 7.9412 | 14.5839 | 2.878 | 3.7647 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 1736 | 0.2 | 20 | 11.7391 | 20.0566 | 3.746 | 4.5714 | 0.8 | 6.25 | 0.1 | 20 | 46.25
| 1737 | 0.8 | 5 | 9.8182 | 15.1374 | 2.7929 | 2.5263 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 1738 | 0.1 | 40 | 9.8182 | 17.3624 | 2.7442 | 4.8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 47.5
| 1739 | 0.8 | 5 | 10.5882 | 18.119 | 2.6077 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1740 | 1 | 4 | 16.3636 | 22.934 | 2.878 | 3.6923 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 1741 | 0.6 | 6.6667 | 12.5581 | 21.5772 | 3.9664 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 1742 | 0.8 | 5 | 12 | 20.2009 | 3.2778 | 4.9231 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 1743 | 1 | 4 | 16.875 | 24.1528 | 3.2778 | 4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 1744 | 0.2 | 20 | 14.5946 | 21.3022 | 3.085 | 3.6226 | 1.4 | 3.5714 | 0.2 | 10 | 33.5714
| 1745 | 0.6 | 6.6667 | 8.5714 | 15.0256 | 3.0256 | 3.4286 | 1 | 5 | 0.4 | 5 | 16.6667
| 1746 | 1 | 4 | 12.5581 | 19.4613 | 3.2109 | 3.6923 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 1747 | 0.6 | 6.6667 | 14.2105 | 23.4001 | 3.3714 | 5.8182 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 1748 | 0.4 | 10 | 12.2727 | 19.7013 | 3.0649 | 4.3636 | 1 | 5 | 0.1 | 20 | 35
| 1749 | 1.2 | 3.3333 | 9.8182 | 18.0485 | 3.6589 | 4.5714 | 1 | 5 | 0.4 | 5 | 13.3333
| 1750 | 0.6 | 6.6667 | 16.875 | 23.6836 | 2.9686 | 3.84 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 1751 | 1.4 | 2.8571 | 14.5946 | 20.9189 | 2.8957 | 3.4286 | 0.6 | 8.3333 | 0.4 | 5 | 16.1905
| 1752 | 0.8 | 5 | 12.5581 | 20.5022 | 2.4583 | 5.4857 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 1753 | 0.8 | 5 | 11.4894 | 16.8372 | 2.5652 | 2.7826 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1754 | 1 | 4 | 8.7097 | 18.7777 | 3.2109 | 6.8571 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 1755 | 1.2 | 3.3333 | 12 | 19.351 | 2.9873 | 4.3636 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 1756 | 0.4 | 10 | 11.25 | 18.0595 | 2.8095 | 4 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 1757 | 1.4 | 2.8571 | 12.2727 | 18.9726 | 3.746 | 2.9538 | 1 | 5 | 0.8 | 2.5 | 10.3571
| 1758 | 1 | 4 | 9.3103 | 17.7277 | 2.9317 | 5.4857 | 1 | 5 | 0.4 | 5 | 14
| 1759 | 1.4 | 2.8571 | 12 | 18.1449 | 2.7765 | 3.3684 | 0.4 | 12.5 | 0.4 | 5 | 20.3571
| 1760 | 1.2 | 3.3333 | 11.7391 | 22.4651 | 3.8689 | 6.8571 | 1 | 5 | 0.2 | 10 | 18.3333
| 1761 | 0.2 | 20 | 11.7391 | 20.7325 | 2.5934 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 1762 | 0.6 | 6.6667 | 11.0204 | 22.3312 | 3.6308 | 7.68 | 1 | 5 | 0.6 | 3.3333 | 15
| 1763 | 1 | 4 | 10.3846 | 17.2166 | 2.9136 | 3.9184 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 1764 | 0.4 | 10 | 14.2105 | 20.0406 | 3.1258 | 2.7042 | 1.2 | 4.1667 | 1 | 2 | 16.1667
| 1765 | 0.6 | 6.6667 | 18.6207 | 26.9087 | 3.7165 | 4.5714 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 1766 | 0.6 | 6.6667 | 9.4737 | 16.5246 | 3.2109 | 3.84 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 1767 | 0.8 | 5 | 15 | 23.0544 | 3.3714 | 4.6829 | 0.6 | 8.3333 | 0.1 | 20 | 33.3333
| 1768 | 0.4 | 10 | 9.3103 | 18.2503 | 4.6733 | 4.2667 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 1769 | 1 | 4 | 10.1887 | 17.2962 | 3.1892 | 3.9184 | 1.6 | 3.125 | 0.2 | 10 | 17.125
| 1770 | 1 | 4 | 12.8571 | 20.3265 | 2.2802 | 5.1892 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 1771 | 1.2 | 3.3333 | 14.5946 | 21.5516 | 2.5934 | 4.3636 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 1772 | 1 | 4 | 9.4737 | 15.9388 | 3.2109 | 3.2542 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 1773 | 0.8 | 5 | 18.6207 | 28.1885 | 3.1678 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1774 | 1.2 | 3.3333 | 18 | 28.2286 | 3.3714 | 6.8571 | 1.6 | 3.125 | 0.2 | 10 | 16.4583
| 1775 | 1 | 4 | 11.4894 | 19.1866 | 3.1258 | 4.5714 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 1776 | 0.8 | 5 | 15.4286 | 23.6053 | 2.8434 | 5.3333 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 1777 | 1 | 4 | 18 | 24.8319 | 2.9136 | 3.9184 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 1778 | 1.2 | 3.3333 | 11.4894 | 21.9223 | 3.5758 | 6.8571 | 1 | 5 | 0.4 | 5 | 13.3333
| 1779 | 0.8 | 5 | 10.3846 | 19.0513 | 2.6667 | 6 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 1780 | 0.2 | 20 | 11.25 | 17.2209 | 3.1053 | 2.8657 | 1 | 5 | 0.1 | 20 | 45
| 1781 | 1 | 4 | 12.2727 | 17.7639 | 2.237 | 3.2542 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.8333
| 1782 | 0.4 | 10 | 9.8182 | 17.1733 | 2.3024 | 5.0526 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 1783 | 1 | 4 | 11.0204 | 18.6971 | 3.1053 | 4.5714 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 1784 | 0.6 | 6.6667 | 15.8824 | 21.1996 | 2.4082 | 2.9091 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 1785 | 1 | 4 | 11.25 | 18.41 | 2.36 | 4.8 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 1786 | 1.2 | 3.3333 | 11.7391 | 18.4675 | 2.7283 | 4 | 1.2 | 4.1667 | 1 | 2 | 9.5
| 1787 | 1 | 4 | 16.3636 | 22.58 | 2.5241 | 3.6923 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 1788 | 0.8 | 5 | 12 | 22.3003 | 3.1892 | 7.1111 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 1789 | 0.6 | 6.6667 | 13.5 | 20.2964 | 2.878 | 3.9184 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 1790 | 0.6 | 6.6667 | 11.7391 | 21.992 | 3.3957 | 6.8571 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 1791 | 1.2 | 3.3333 | 15.4286 | 20.8542 | 3.0256 | 2.4 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 1792 | 1.6 | 2.5 | 18 | 25.7726 | 3.6875 | 4.0851 | 1.2 | 4.1667 | 0.2 | 10 | 16.6667
| 1793 | 0.6 | 6.6667 | 15 | 22.5909 | 3.1258 | 4.4651 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 1794 | 0.6 | 6.6667 | 10.8 | 17.7285 | 2.8434 | 4.0851 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 1795 | 0.6 | 6.6667 | 25.7143 | 32.0496 | 2.7126 | 3.6226 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 1796 | 1.8 | 2.2222 | 11.4894 | 18.8608 | 3.3714 | 4 | 1.4 | 3.5714 | 0.2 | 10 | 15.7937
| 1797 | 1.2 | 3.3333 | 11.4894 | 19.326 | 2.9136 | 4.9231 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 1798 | 0.8 | 5 | 13.1707 | 19.5871 | 2.6517 | 3.7647 | 0.6 | 8.3333 | 0.1 | 20 | 33.3333
| 1799 | 0.2 | 20 | 19.2857 | 27.7116 | 2.6077 | 5.8182 | 0.8 | 6.25 | 0.2 | 10 | 36.25
| 1800 | 1.6 | 2.5 | 15.8824 | 22.0859 | 2.7126 | 3.4909 | 0.8 | 6.25 | 0.2 | 10 | 18.75
| 1801 | 0.8 | 5 | 11.25 | 18.7718 | 3.2552 | 4.2667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 1802 | 0.8 | 5 | 13.8462 | 20.6547 | 2.9686 | 3.84 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 1803 | 0.8 | 5 | 19.2857 | 24.2112 | 2.6667 | 2.2588 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 1804 | 0.8 | 5 | 12 | 21.0143 | 4.2143 | 4.8 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 1805 | 0.6 | 6.6667 | 15 | 21.3028 | 3.2552 | 3.0476 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 1806 | 0.8 | 5 | 10.5882 | 17.211 | 2.5376 | 4.0851 | 1 | 5 | 0.1 | 20 | 30
| 1807 | 0.6 | 6.6667 | 7.9412 | 14.2774 | 3.4706 | 2.8657 | 1 | 5 | 0.2 | 10 | 21.6667
| 1808 | 0.4 | 10 | 13.5 | 22.9275 | 4.6275 | 4.8 | 1 | 5 | 0.2 | 10 | 25
| 1809 | 1 | 4 | 8.1818 | 15.6384 | 3.3714 | 4.0851 | 1 | 5 | 0.2 | 10 | 19
| 1810 | 1.2 | 3.3333 | 10.1887 | 17.3986 | 3.4453 | 3.7647 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 1811 | 0.1 | 40 | 11.4894 | 22.945 | 2.7283 | 8.7273 | 0.6 | 8.3333 | 0.1 | 20 | 68.3333
| 1812 | 1.4 | 2.8571 | 10 | 17.5492 | 2.36 | 5.1892 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 1813 | 1.2 | 3.3333 | 12.2727 | 22.5461 | 2.5934 | 7.68 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 1814 | 1.2 | 3.3333 | 10.5882 | 18.5719 | 3.3007 | 4.6829 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 1815 | 0.8 | 5 | 10 | 17.1228 | 2.5514 | 4.5714 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1816 | 1 | 4 | 13.8462 | 21.2806 | 3.1678 | 4.2667 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 1817 | 0.6 | 6.6667 | 12 | 18.5514 | 2.5514 | 4 | 0.6 | 8.3333 | 0.8 | 2.5 | 17.5
| 1818 | 0.8 | 5 | 11.4894 | 18.7637 | 3.1892 | 4.0851 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 1819 | 1.4 | 2.8571 | 10 | 17.5054 | 3.4203 | 4.0851 | 1 | 5 | 0.2 | 10 | 17.8571
| 1820 | 0.6 | 6.6667 | 13.8462 | 20.5337 | 3.6875 | 3 | 1 | 5 | 0.6 | 3.3333 | 15
| 1821 | 1 | 4 | 12 | 20.0552 | 3.2552 | 4.8 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 1822 | 0.4 | 10 | 9.1525 | 15.5392 | 2.8957 | 3.4909 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 1823 | 0.8 | 5 | 12.5581 | 21.9127 | 3.8689 | 5.4857 | 1 | 5 | 0.2 | 10 | 20
| 1824 | 1.2 | 3.3333 | 10.1887 | 19.6829 | 3.3007 | 6.1935 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 1825 | 0.6 | 6.6667 | 13.1707 | 19.7079 | 2.6971 | 3.84 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 1826 | 1 | 4 | 14.2105 | 20.3718 | 2.7929 | 3.3684 | 1 | 5 | 0.1 | 20 | 29
| 1827 | 0.6 | 6.6667 | 15.8824 | 22.3879 | 2.95 | 3.5556 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 1828 | 0.6 | 6.6667 | 11.7391 | 17.9069 | 3.1678 | 3 | 1 | 5 | 0.4 | 5 | 16.6667
| 1829 | 0.2 | 20 | 18 | 27.1556 | 3.9664 | 5.1892 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 1830 | 0.2 | 20 | 12.2727 | 17.5145 | 2.6818 | 2.56 | 1.2 | 4.1667 | 0.8 | 2.5 | 26.6667
| 1831 | 1.4 | 2.8571 | 10.5882 | 19.9027 | 3.4963 | 5.8182 | 1 | 5 | 0.4 | 5 | 12.8571
| 1832 | 0.6 | 6.6667 | 8.0597 | 15.2828 | 2.6517 | 4.5714 | 1 | 5 | 0.4 | 5 | 16.6667
| 1833 | 0.6 | 6.6667 | 11.25 | 17.7741 | 2.9686 | 3.5556 | 1.8 | 2.7778 | 0.6 | 3.3333 | 12.7778
| 1834 | 0.8 | 5 | 8.3077 | 15.4755 | 3.1678 | 4 | 1 | 5 | 0.2 | 10 | 20
| 1835 | 0.2 | 20 | 16.875 | 23.9928 | 3.2778 | 3.84 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 1836 | 0.6 | 6.6667 | 12.8571 | 19.5727 | 3.8065 | 2.9091 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 1837 | 0.8 | 5 | 9.4737 | 15.8212 | 3.3475 | 3 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 1838 | 1.2 | 3.3333 | 12.8571 | 21.1222 | 2.9317 | 5.3333 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 1839 | 0.4 | 10 | 13.5 | 19.4177 | 3.6589 | 2.2588 | 1.8 | 2.7778 | 0.4 | 5 | 17.7778
| 1840 | 1 | 4 | 10.8 | 17.4587 | 3.1678 | 3.4909 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 1841 | 1 | 4 | 10 | 15.1434 | 2.6818 | 2.4615 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 1842 | 1.2 | 3.3333 | 13.1707 | 22.1785 | 2.6077 | 6.4 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 1843 | 1 | 4 | 16.3636 | 23.9414 | 3.0064 | 4.5714 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 1844 | 0.6 | 6.6667 | 14.2105 | 21.7919 | 3.4963 | 4.0851 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 1845 | 0.6 | 6.6667 | 14.5946 | 21.3072 | 2.7126 | 4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 1846 | 0.8 | 5 | 15 | 23.1956 | 3.0064 | 5.1892 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 1847 | 1.2 | 3.3333 | 12.8571 | 19.2764 | 2.5792 | 3.84 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 1848 | 0.2 | 20 | 12.8571 | 18.5516 | 3.2329 | 2.4615 | 1 | 5 | 0.4 | 5 | 30
| 1849 | 0.6 | 6.6667 | 13.1707 | 25.1065 | 2.7929 | 9.1429 | 1.2 | 4.1667 | 1 | 2 | 12.8333
| 1850 | 0.8 | 5 | 12 | 17.5207 | 2.6971 | 2.8235 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 1851 | 1.8 | 2.2222 | 10.1887 | 18.5231 | 1.9344 | 6.4 | 1.4 | 3.5714 | 0.6 | 3.3333 | 9.127
| 1852 | 1.2 | 3.3333 | 12.8571 | 18.995 | 2.4456 | 3.6923 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 1853 | 0.6 | 6.6667 | 8.5714 | 14.5472 | 3.2329 | 2.7429 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 1854 | 0.6 | 6.6667 | 15 | 21.5683 | 2.7283 | 3.84 | 1 | 5 | 0.6 | 3.3333 | 15
| 1855 | 1 | 4 | 13.1707 | 19.5759 | 2.5652 | 3.84 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 1856 | 1 | 4 | 9.8182 | 16.2435 | 3.2778 | 3.1475 | 1 | 5 | 0.1 | 20 | 29
| 1857 | 0.6 | 6.6667 | 11.25 | 18.9495 | 2.7765 | 4.9231 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 1858 | 1.2 | 3.3333 | 14.2105 | 21.8566 | 2.5934 | 5.0526 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 1859 | 0.4 | 10 | 23.4783 | 30.4124 | 2.7602 | 4.1739 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 1860 | 1 | 4 | 13.8462 | 20.963 | 2.6517 | 4.4651 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 1861 | 0.6 | 6.6667 | 12.2727 | 18.7193 | 2.6818 | 3.7647 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 1862 | 0.6 | 6.6667 | 7.8261 | 14.1604 | 2.8434 | 3.4909 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 1863 | 0.8 | 5 | 12.2727 | 18.3133 | 2.3483 | 3.6923 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 1864 | 0.4 | 10 | 17.4194 | 26.7879 | 2.9686 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 1865 | 0.6 | 6.6667 | 13.1707 | 24.8296 | 3.6589 | 8 | 1 | 5 | 0.1 | 20 | 31.6667
| 1866 | 0.8 | 5 | 11.25 | 20.4934 | 2.8434 | 6.4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 1867 | 1.2 | 3.3333 | 22.5 | 30.385 | 3.085 | 4.8 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 1868 | 1 | 4 | 15.4286 | 22.8557 | 2.7442 | 4.6829 | 1 | 5 | 0.4 | 5 | 14
| 1869 | 0.8 | 5 | 11.25 | 18.8088 | 2.9873 | 4.5714 | 1 | 5 | 0.4 | 5 | 15
| 1870 | 0.6 | 6.6667 | 12.5581 | 19.8779 | 2.6369 | 4.6829 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 1871 | 1.2 | 3.3333 | 12.8571 | 24.2699 | 3.0649 | 8.3478 | 1 | 5 | 0.4 | 5 | 13.3333
| 1872 | 0.8 | 5 | 15.4286 | 23.0892 | 2.8606 | 4.8 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 1873 | 1.2 | 3.3333 | 8.4375 | 16.9026 | 4 | 4.4651 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 1874 | 0.8 | 5 | 13.8462 | 19.9113 | 3.4706 | 2.5946 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 1875 | 1 | 4 | 10.5882 | 17.4593 | 2.6971 | 4.1739 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 1876 | 1.4 | 2.8571 | 13.5 | 25.0758 | 3.5758 | 8 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 1877 | 1 | 4 | 12 | 18.9941 | 3.3714 | 3.6226 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 1878 | 1 | 4 | 11.7391 | 19.8731 | 3.2109 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 1879 | 1 | 4 | 10.5882 | 19.7166 | 2.7283 | 6.4 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 1880 | 0.2 | 20 | 13.1707 | 22.2888 | 2.4974 | 6.6207 | 1.2 | 4.1667 | 1 | 2 | 26.1667
| 1881 | 0.6 | 6.6667 | 9.3103 | 17.6048 | 3.1053 | 5.1892 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 1882 | 0.8 | 5 | 11.7391 | 18.4571 | 3.0256 | 3.6923 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 1883 | 0.6 | 6.6667 | 12.8571 | 21.5426 | 3.4963 | 5.1892 | 1 | 5 | 0.2 | 10 | 21.6667
| 1884 | 0.4 | 10 | 12.2727 | 19.7459 | 2.4205 | 5.0526 | 1.4 | 3.5714 | 0.1 | 20 | 33.5714
| 1885 | 1.4 | 2.8571 | 11.4894 | 21.8233 | 4.1404 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 1886 | 0.8 | 5 | 12.5581 | 24.579 | 2.878 | 9.1429 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1887 | 0.8 | 5 | 13.1707 | 19.5075 | 3.1892 | 3.1475 | 1 | 5 | 0.2 | 10 | 20
| 1888 | 0.4 | 10 | 12 | 20.0677 | 3.4963 | 4.5714 | 1 | 5 | 0.2 | 10 | 25
| 1889 | 0.4 | 10 | 16.875 | 25.5792 | 2.5106 | 6.1935 | 1 | 5 | 0.4 | 5 | 20
| 1890 | 1 | 4 | 18 | 25.1239 | 2.95 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 1891 | 1 | 4 | 12.5581 | 19.0765 | 2.8957 | 3.6226 | 1 | 5 | 0.4 | 5 | 14
| 1892 | 1.6 | 2.5 | 15 | 20.5983 | 2.9317 | 2.6667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10
| 1893 | 0.8 | 5 | 13.5 | 21.8784 | 3.1892 | 5.1892 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 1894 | 1 | 4 | 11.4894 | 17.636 | 3.1467 | 3 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 1895 | 0.6 | 6.6667 | 14.5946 | 23.012 | 2.9317 | 5.4857 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 1896 | 0.6 | 6.6667 | 15 | 23.2945 | 3.3714 | 4.9231 | 1 | 5 | 0.4 | 5 | 16.6667
| 1897 | 1.2 | 3.3333 | 11.25 | 19.135 | 3.085 | 4.8 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 1898 | 0.6 | 6.6667 | 9.1525 | 16.8851 | 2.8095 | 4.9231 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 1899 | 1.2 | 3.3333 | 14.2105 | 20.6756 | 3.2109 | 3.2542 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 1900 | 1.2 | 3.3333 | 12.5581 | 20.5662 | 3.085 | 4.9231 | 1.4 | 3.5714 | 0.8 | 2.5 | 9.4048
| 1901 | 0.8 | 5 | 12.8571 | 20.2774 | 3.4203 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1902 | 0.8 | 5 | 13.8462 | 20.4142 | 3.6589 | 2.9091 | 1 | 5 | 0.2 | 10 | 20
| 1903 | 0.8 | 5 | 10.8 | 20.8 | 4 | 6 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 1904 | 0.4 | 10 | 12.2727 | 19.662 | 3.0256 | 4.3636 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 1905 | 0.1 | 40 | 14.2105 | 20.5359 | 3.2778 | 3.0476 | 1.6 | 3.125 | 0.4 | 5 | 48.125
| 1906 | 1.2 | 3.3333 | 10.5882 | 16.1056 | 2.6517 | 2.8657 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 1907 | 0.6 | 6.6667 | 9.6429 | 15.759 | 2.9686 | 3.1475 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 1908 | 0.4 | 10 | 12.8571 | 19.4649 | 2.6077 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 1909 | 1 | 4 | 10.8 | 19.8185 | 3.3714 | 5.6471 | 1 | 5 | 0.4 | 5 | 14
| 1910 | 0.2 | 20 | 9.8182 | 18.2252 | 4.1404 | 4.2667 | 0.6 | 8.3333 | 0.4 | 5 | 33.3333
| 1911 | 0.4 | 10 | 11.7391 | 18.0537 | 2.6222 | 3.6923 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 1912 | 0.8 | 5 | 12 | 19.3118 | 3.0452 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1913 | 1.2 | 3.3333 | 12 | 19.1664 | 3.9664 | 3.2 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 1914 | 1 | 4 | 12.8571 | 21.0148 | 2.5106 | 5.6471 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 1915 | 1.2 | 3.3333 | 12.8571 | 20.6883 | 3.746 | 4.0851 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.1667
| 1916 | 0.6 | 6.6667 | 15.4286 | 23.24 | 2.6222 | 5.1892 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 1917 | 0.8 | 5 | 11.25 | 17.6319 | 2.8263 | 3.5556 | 1 | 5 | 0.4 | 5 | 15
| 1918 | 0.2 | 20 | 16.875 | 30.7745 | 3.2329 | 10.6667 | 1 | 5 | 0.4 | 5 | 30
| 1919 | 1.2 | 3.3333 | 9.3103 | 15.7057 | 3.085 | 3.3103 | 0.8 | 6.25 | 0.8 | 2.5 | 12.0833
| 1920 | 0.8 | 5 | 12.5581 | 19.436 | 3.2552 | 3.6226 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1921 | 0.6 | 6.6667 | 11.0204 | 16.7983 | 3.3475 | 2.4304 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 1922 | 0.6 | 6.6667 | 20 | 26.4451 | 2.36 | 4.0851 | 1.6 | 3.125 | 0.6 | 3.3333 | 13.125
| 1923 | 0.6 | 6.6667 | 12 | 19.9678 | 3.1678 | 4.8 | 1 | 5 | 0.6 | 3.3333 | 15
| 1924 | 1.4 | 2.8571 | 9.6429 | 17.6416 | 2.8095 | 5.1892 | 1.6 | 3.125 | 0.4 | 5 | 10.9821
| 1925 | 1.4 | 2.8571 | 16.875 | 23.5768 | 3.2109 | 3.4909 | 1 | 5 | 0.1 | 20 | 27.8571
| 1926 | 0.6 | 6.6667 | 10.5882 | 17.766 | 2.7126 | 4.4651 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 1927 | 0.6 | 6.6667 | 9.8182 | 19.8105 | 2.6077 | 7.3846 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 1928 | 1.2 | 3.3333 | 12.5581 | 18.2365 | 2.8957 | 2.7826 | 0.8 | 6.25 | 0.8 | 2.5 | 12.0833
| 1929 | 0.4 | 10 | 15.4286 | 25.96 | 3.4203 | 7.1111 | 0.4 | 12.5 | 0.4 | 5 | 27.5
| 1930 | 1 | 4 | 8.4375 | 13.7906 | 2.2056 | 3.1475 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 1931 | 0.6 | 6.6667 | 12.5581 | 18.2555 | 2.4974 | 3.2 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 1932 | 0.8 | 5 | 12.8571 | 21.2572 | 3.2109 | 5.1892 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1933 | 1 | 4 | 13.8462 | 24.3774 | 3.1467 | 7.3846 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 1934 | 1.4 | 2.8571 | 10.5882 | 18.6282 | 2.9873 | 5.0526 | 1 | 5 | 0.1 | 20 | 27.8571
| 1935 | 1 | 4 | 15 | 23.1475 | 3.3475 | 4.8 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 1936 | 1 | 4 | 12.2727 | 18.1343 | 2.433 | 3.4286 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 1937 | 0.6 | 6.6667 | 13.5 | 20.8629 | 3.2778 | 4.0851 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 1938 | 0.6 | 6.6667 | 14.2105 | 21.9784 | 3.085 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 1939 | 0.8 | 5 | 11.7391 | 17.3735 | 2.5376 | 3.0968 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 1940 | 0.6 | 6.6667 | 10.8 | 17.5766 | 3.5224 | 3.2542 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 1941 | 0.6 | 6.6667 | 10.8 | 21.8154 | 3.6308 | 7.3846 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 1942 | 1.4 | 2.8571 | 12.5581 | 18.2504 | 3.0256 | 2.6667 | 0.6 | 8.3333 | 0.2 | 10 | 21.1905
| 1943 | 0.8 | 5 | 13.1707 | 20.1771 | 3.0064 | 4 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 1944 | 0.8 | 5 | 14.2105 | 23.1815 | 3.3239 | 5.6471 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 1945 | 1.4 | 2.8571 | 11.4894 | 18.6571 | 3.1678 | 4 | 0.4 | 12.5 | 0.2 | 10 | 25.3571
| 1946 | 0.6 | 6.6667 | 15 | 21.6999 | 3.746 | 2.9538 | 1 | 5 | 0.6 | 3.3333 | 15
| 1947 | 1.4 | 2.8571 | 18.6207 | 27.0237 | 3.6031 | 4.8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 1948 | 0.6 | 6.6667 | 10.3846 | 20.0175 | 3.2329 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 1949 | 0.4 | 10 | 10.3846 | 19.1382 | 3.4203 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 1950 | 1.2 | 3.3333 | 8.7097 | 15.843 | 3.9333 | 3.2 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 1951 | 0.8 | 5 | 16.3636 | 25.1135 | 2.9317 | 5.8182 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 1952 | 0.8 | 5 | 12.2727 | 18.0493 | 2.4082 | 3.3684 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 1953 | 0.6 | 6.6667 | 10.3846 | 17.7924 | 2.6077 | 4.8 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 1954 | 1 | 4 | 14.2105 | 23.8764 | 3.0452 | 6.6207 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 1955 | 1.2 | 3.3333 | 8.0597 | 17.3622 | 2.6818 | 6.6207 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 1956 | 1.4 | 2.8571 | 11.0204 | 16.4154 | 2.7283 | 2.6667 | 1 | 5 | 0.2 | 10 | 17.8571
| 1957 | 0.6 | 6.6667 | 12.5581 | 19.4182 | 3.1678 | 3.6923 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 1958 | 1 | 4 | 9.1525 | 14.6844 | 2.4842 | 3.0476 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 1959 | 0.8 | 5 | 11.25 | 20.1331 | 3.0649 | 5.8182 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1960 | 1.2 | 3.3333 | 9.8182 | 19.6706 | 3.6589 | 6.1935 | 1.6 | 3.125 | 0.8 | 2.5 | 8.9583
| 1961 | 0.6 | 6.6667 | 12.5581 | 17.8286 | 2.7442 | 2.5263 | 1 | 5 | 0.6 | 3.3333 | 15
| 1962 | 0.6 | 6.6667 | 20 | 31.8247 | 2.6818 | 9.1429 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 1963 | 0.6 | 6.6667 | 13.1707 | 21.416 | 3.4453 | 4.8 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 1964 | 0.1 | 40 | 16.875 | 23.8067 | 2.9317 | 4 | 1.4 | 3.5714 | 0.4 | 5 | 48.5714
| 1965 | 0.8 | 5 | 11.7391 | 18.0444 | 3.1053 | 3.2 | 1 | 5 | 0.4 | 5 | 15
| 1966 | 1 | 4 | 9.1525 | 19.3285 | 3.776 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 1967 | 1 | 4 | 14.2105 | 21.8201 | 2.8095 | 4.8 | 1 | 5 | 0.1 | 20 | 29
| 1968 | 1 | 4 | 13.8462 | 23.1013 | 3.2552 | 6 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 1969 | 0.4 | 10 | 11.0204 | 20.1462 | 3.1258 | 6 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 1970 | 1.2 | 3.3333 | 14.5946 | 22.7349 | 3.9664 | 4.1739 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 1971 | 0.6 | 6.6667 | 12.5581 | 22.6246 | 2.6818 | 7.3846 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 1972 | 0.8 | 5 | 10.3846 | 18.3705 | 3.9008 | 4.0851 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 1973 | 1.6 | 2.5 | 11.0204 | 20.9749 | 2.8434 | 7.1111 | 1.2 | 4.1667 | 0.4 | 5 | 11.6667
| 1974 | 1 | 4 | 9 | 19.63 | 2.95 | 7.68 | 1 | 5 | 0.4 | 5 | 14
| 1975 | 0.1 | 40 | 11.25 | 18.0634 | 2.3483 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 48.3333
| 1976 | 0.4 | 10 | 11.25 | 19.884 | 3.3007 | 5.3333 | 1.4 | 3.5714 | 0.1 | 20 | 33.5714
| 1977 | 0.8 | 5 | 11.0204 | 17.2294 | 3.2552 | 2.9538 | 1 | 5 | 0.2 | 10 | 20
| 1978 | 1.6 | 2.5 | 14.5946 | 21.3477 | 2.5792 | 4.1739 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10
| 1979 | 1.2 | 3.3333 | 11.4894 | 18.1116 | 2.6222 | 4 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 1980 | 1 | 4 | 9.3103 | 17.1958 | 3.4203 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 1981 | 1.6 | 2.5 | 10.1887 | 17.0497 | 2.4974 | 4.3636 | 0.8 | 6.25 | 0.4 | 5 | 13.75
| 1982 | 0.6 | 6.6667 | 11.4894 | 20.995 | 3.6875 | 5.8182 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 1983 | 0.6 | 6.6667 | 13.5 | 20.1964 | 2.9317 | 3.7647 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 1984 | 0.6 | 6.6667 | 11.7391 | 17.5726 | 2.5792 | 3.2542 | 1.4 | 3.5714 | 0.1 | 20 | 30.2381
| 1985 | 0.8 | 5 | 12.8571 | 19.6332 | 3.3475 | 3.4286 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 1986 | 0.6 | 6.6667 | 14.5946 | 22.0097 | 2.95 | 4.4651 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 1987 | 0.4 | 10 | 13.1707 | 20.1735 | 2.5376 | 4.4651 | 1.6 | 3.125 | 0.6 | 3.3333 | 16.4583
| 1988 | 0.4 | 10 | 20.7692 | 28.9252 | 3.2329 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 1989 | 1 | 4 | 12.5581 | 19.4397 | 1.9585 | 4.9231 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 1990 | 0.6 | 6.6667 | 12.8571 | 23.1024 | 2.8606 | 7.3846 | 1 | 5 | 0.4 | 5 | 16.6667
| 1991 | 0.8 | 5 | 9.8182 | 17.3164 | 2.4456 | 5.0526 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 1992 | 0.8 | 5 | 9.1525 | 16.0966 | 3.0256 | 3.9184 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 1993 | 1 | 4 | 11.4894 | 20.9707 | 2.8606 | 6.6207 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 1994 | 0.8 | 5 | 10.8 | 17.5179 | 3.0256 | 3.6923 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 1995 | 1 | 4 | 10.1887 | 16.4255 | 3.1892 | 3.0476 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 1996 | 1 | 4 | 20 | 27.2206 | 3.9664 | 3.2542 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 1997 | 0.4 | 10 | 19.2857 | 30.014 | 2.7283 | 8 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 1998 | 1.6 | 2.5 | 14.5946 | 21.1688 | 2.8095 | 3.7647 | 0.6 | 8.3333 | 0.4 | 5 | 15.8333
| 1999 | 1.2 | 3.3333 | 10.8 | 17.4626 | 2.3959 | 4.2667 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 2000 | 0.2 | 20 | 8.7097 | 15.4061 | 3.5489 | 3.1475 | 1.2 | 4.1667 | 1 | 2 | 26.1667
| 2001 | 1.2 | 3.3333 | 9.3103 | 16.4669 | 2.7929 | 4.3636 | 1 | 5 | 0.2 | 10 | 18.3333
| 2002 | 0.2 | 20 | 9 | 17.5442 | 3.2109 | 5.3333 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 2003 | 1 | 4 | 10.3846 | 19.3223 | 2.7442 | 6.1935 | 1 | 5 | 0.2 | 10 | 19
| 2004 | 0.8 | 5 | 15.4286 | 23.4706 | 3.4706 | 4.5714 | 1 | 5 | 0.4 | 5 | 15
| 2005 | 0.4 | 10 | 20 | 25.8759 | 2.7283 | 3.1475 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 2006 | 1.2 | 3.3333 | 9.6429 | 18.448 | 4.5385 | 4.2667 | 1 | 5 | 0.2 | 10 | 18.3333
| 2007 | 1 | 4 | 11.25 | 17.8928 | 2.878 | 3.7647 | 1 | 5 | 0.4 | 5 | 14
| 2008 | 0.6 | 6.6667 | 16.875 | 26.7275 | 3.6589 | 6.1935 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 2009 | 0.6 | 6.6667 | 10.1887 | 18.557 | 3.4453 | 4.9231 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 2010 | 0.6 | 6.6667 | 11.25 | 18.8945 | 3.4706 | 4.1739 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 2011 | 0.8 | 5 | 15 | 21.9181 | 2.7442 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2012 | 0.8 | 5 | 13.8462 | 19.5043 | 2.5106 | 3.1475 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2013 | 0.8 | 5 | 12.2727 | 19.4178 | 3.5224 | 3.6226 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2014 | 0.8 | 5 | 13.1707 | 19.1645 | 2.5652 | 3.4286 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 2015 | 1.2 | 3.3333 | 12 | 18.7556 | 3.4453 | 3.3103 | 1 | 5 | 0.4 | 5 | 13.3333
| 2016 | 0.1 | 40 | 15.4286 | 22.4589 | 2.6667 | 4.3636 | 0.6 | 8.3333 | 0.1 | 20 | 68.3333
| 2017 | 0.6 | 6.6667 | 11.0204 | 20.9418 | 3.3007 | 6.6207 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 2018 | 0.8 | 5 | 12 | 17.7442 | 2.7442 | 3 | 0.2 | 25 | 0.6 | 3.3333 | 33.3333
| 2019 | 0.8 | 5 | 11.25 | 18.4917 | 2.878 | 4.3636 | 1 | 5 | 0.2 | 10 | 20
| 2020 | 1 | 4 | 10 | 17.3608 | 2.8957 | 4.4651 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 2021 | 0.4 | 10 | 8.3077 | 18.7806 | 2.7929 | 7.68 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 2022 | 0.6 | 6.6667 | 11.4894 | 21.6829 | 4 | 6.1935 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 2023 | 0.8 | 5 | 18 | 25.5093 | 2.8263 | 4.6829 | 1 | 5 | 0.4 | 5 | 15
| 2024 | 1.2 | 3.3333 | 16.3636 | 24.2258 | 2.8095 | 5.0526 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 2025 | 0.8 | 5 | 16.3636 | 25.9528 | 3.1892 | 6.4 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 2026 | 1 | 4 | 16.3636 | 22.6936 | 2.5652 | 3.7647 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 2027 | 1.2 | 3.3333 | 13.5 | 20.0701 | 2.6517 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 2028 | 0.4 | 10 | 11.0204 | 20.2096 | 3.1892 | 6 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 2029 | 0.6 | 6.6667 | 10.5882 | 18.3541 | 3.3007 | 4.4651 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 2030 | 0.6 | 6.6667 | 14.2105 | 27.8105 | 4 | 9.6 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 2031 | 0.4 | 10 | 12.8571 | 20.0019 | 2.878 | 4.2667 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 2032 | 0.8 | 5 | 9.4737 | 19.7819 | 3.6875 | 6.6207 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 2033 | 0.8 | 5 | 13.1707 | 19.6578 | 3.2329 | 3.2542 | 1 | 5 | 0.4 | 5 | 15
| 2034 | 0.6 | 6.6667 | 16.875 | 24.5356 | 2.8606 | 4.8 | 1 | 5 | 0.4 | 5 | 16.6667
| 2035 | 1.4 | 2.8571 | 9.8182 | 16.5713 | 2.5792 | 4.1739 | 0.8 | 6.25 | 0.1 | 20 | 29.1071
| 2036 | 0.6 | 6.6667 | 11.0204 | 16.8946 | 2.4456 | 3.4286 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 2037 | 1.4 | 2.8571 | 13.5 | 20.2076 | 3.085 | 3.6226 | 0.6 | 8.3333 | 0.2 | 10 | 21.1905
| 2038 | 0.6 | 6.6667 | 15.4286 | 23.4116 | 2.4974 | 5.4857 | 1 | 5 | 0.6 | 3.3333 | 15
| 2039 | 1 | 4 | 12.8571 | 18.4513 | 2.4974 | 3.0968 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 2040 | 1 | 4 | 15.8824 | 22.7213 | 3.1467 | 3.6923 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 2041 | 1.2 | 3.3333 | 13.8462 | 23.4679 | 2.5106 | 7.1111 | 1.2 | 4.1667 | 0.1 | 20 | 27.5
| 2042 | 0.8 | 5 | 13.5 | 23.1552 | 3.2552 | 6.4 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 2043 | 0.4 | 10 | 9.1525 | 15.9592 | 3.4963 | 3.3103 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 2044 | 1.2 | 3.3333 | 12.2727 | 19.03 | 3.0649 | 3.6923 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 2045 | 0.6 | 6.6667 | 13.1707 | 20.8988 | 3.0452 | 4.6829 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 2046 | 0.4 | 10 | 13.8462 | 20.7118 | 3.0256 | 3.84 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 2047 | 0.6 | 6.6667 | 15.8824 | 26.912 | 2.6818 | 8.3478 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 2048 | 1 | 4 | 14.5946 | 23.3264 | 2.9136 | 5.8182 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 2049 | 1 | 4 | 11.4894 | 19.9436 | 2.9686 | 5.4857 | 1 | 5 | 0.4 | 5 | 14
| 2050 | 0.4 | 10 | 10.8 | 18.5392 | 3.1678 | 4.5714 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 2051 | 1 | 4 | 9.8182 | 16.7204 | 2.7283 | 4.1739 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 2052 | 0.4 | 10 | 20.7692 | 28.9068 | 3.085 | 5.0526 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 2053 | 1.2 | 3.3333 | 16.3636 | 21.7563 | 3.2109 | 2.1818 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 2054 | 1 | 4 | 10 | 20.3926 | 2.7126 | 7.68 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 2055 | 0.4 | 10 | 10.3846 | 17.0425 | 3.3475 | 3.3103 | 1 | 5 | 1 | 2 | 17
| 2056 | 0.6 | 6.6667 | 11.0204 | 15.7756 | 2.7126 | 2.0426 | 1 | 5 | 0.2 | 10 | 21.6667
| 2057 | 0.4 | 10 | 9.8182 | 17.5597 | 2.4082 | 5.3333 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 2058 | 0.4 | 10 | 8.7097 | 16.8862 | 2.9873 | 5.1892 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 2059 | 1.2 | 3.3333 | 12.8571 | 20.3886 | 3.1678 | 4.3636 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 2060 | 1.4 | 2.8571 | 12.5581 | 18.9573 | 2.7765 | 3.6226 | 1 | 5 | 0.4 | 5 | 12.8571
| 2061 | 0.8 | 5 | 12.5581 | 20.0431 | 2.9136 | 4.5714 | 1 | 5 | 0.1 | 20 | 30
| 2062 | 0.2 | 20 | 12.8571 | 21.63 | 3.1258 | 5.6471 | 1.2 | 4.1667 | 0.8 | 2.5 | 26.6667
| 2063 | 1.4 | 2.8571 | 11.4894 | 16.0396 | 2.237 | 2.3133 | 1 | 5 | 0.4 | 5 | 12.8571
| 2064 | 0.6 | 6.6667 | 14.2105 | 22.4755 | 2.9317 | 5.3333 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 2065 | 0.8 | 5 | 10.8 | 17.3965 | 3.5489 | 3.0476 | 1 | 5 | 0.2 | 10 | 20
| 2066 | 1 | 4 | 10.3846 | 18.6552 | 3.4706 | 4.8 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 2067 | 1.2 | 3.3333 | 10.1887 | 16.5382 | 3.3957 | 2.9538 | 0.4 | 12.5 | 0.2 | 10 | 25.8333
| 2068 | 0.2 | 20 | 15 | 24.5467 | 3.1467 | 6.4 | 0.4 | 12.5 | 1 | 2 | 34.5
| 2069 | 0.6 | 6.6667 | 12 | 18.7773 | 3.085 | 3.6923 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 2070 | 1.2 | 3.3333 | 12.2727 | 20.1437 | 2.6818 | 5.1892 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 2071 | 1 | 4 | 10.8 | 15.7376 | 2.5376 | 2.4 | 1 | 5 | 0.4 | 5 | 14
| 2072 | 0.8 | 5 | 14.2105 | 22.2888 | 3.0256 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 2073 | 1 | 4 | 14.5946 | 23.014 | 3.4963 | 4.9231 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 2074 | 1 | 4 | 12.5581 | 19.6601 | 2.6369 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 2075 | 1.4 | 2.8571 | 18.6207 | 26.1185 | 3.3239 | 4.1739 | 0.4 | 12.5 | 0.4 | 5 | 20.3571
| 2076 | 1.4 | 2.8571 | 13.1707 | 19.7872 | 2.7765 | 3.84 | 1 | 5 | 0.2 | 10 | 17.8571
| 2077 | 0.8 | 5 | 11.7391 | 21.0176 | 3.085 | 6.1935 | 1 | 5 | 0.2 | 10 | 20
| 2078 | 1 | 4 | 10.5882 | 19.8668 | 3.085 | 6.1935 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 2079 | 0.8 | 5 | 9.8182 | 16.0421 | 2.9136 | 3.3103 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2080 | 1.4 | 2.8571 | 9 | 15.6503 | 2.5652 | 4.0851 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 2081 | 0.8 | 5 | 14.2105 | 21.5336 | 3.6308 | 3.6923 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 2082 | 0.4 | 10 | 13.1707 | 18.8401 | 2.7602 | 2.9091 | 1 | 5 | 0.2 | 10 | 25
| 2083 | 0.8 | 5 | 12.8571 | 18.9697 | 2.7442 | 3.3684 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 2084 | 1.2 | 3.3333 | 7.6056 | 16.934 | 2.4712 | 6.8571 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 2085 | 0.8 | 5 | 12.2727 | 19.0792 | 3.6589 | 3.1475 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 2086 | 0.6 | 6.6667 | 8.5714 | 17.3728 | 4.6275 | 4.1739 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 2087 | 1 | 4 | 11.4894 | 19.4786 | 3.1892 | 4.8 | 1 | 5 | 0.4 | 5 | 14
| 2088 | 1.4 | 2.8571 | 10.8 | 16.0057 | 2.7442 | 2.4615 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 2089 | 1.2 | 3.3333 | 11.7391 | 18.5983 | 3.5489 | 3.3103 | 1.2 | 4.1667 | 0.1 | 20 | 27.5
| 2090 | 0.8 | 5 | 10.8 | 16.8351 | 2.6667 | 3.3684 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 2091 | 0.8 | 5 | 10 | 16.9976 | 3.9008 | 3.0968 | 1 | 5 | 0.8 | 2.5 | 12.5
| 2092 | 0.2 | 20 | 9.6429 | 19.0964 | 3.8065 | 5.6471 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 2093 | 0.6 | 6.6667 | 15 | 26.2109 | 3.2109 | 8 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 2094 | 1.2 | 3.3333 | 12 | 20.4952 | 4.4952 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 2095 | 1.2 | 3.3333 | 20 | 26.2893 | 2.6667 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 2096 | 0.4 | 10 | 13.5 | 19.6606 | 2.3959 | 3.7647 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 2097 | 0.8 | 5 | 13.8462 | 19.3797 | 2.1651 | 3.3684 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 2098 | 1 | 4 | 16.3636 | 22.5672 | 2.7126 | 3.4909 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 2099 | 0.8 | 5 | 11.7391 | 17.6796 | 2.7929 | 3.1475 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2100 | 0.8 | 5 | 18.6207 | 27.2363 | 2.9686 | 5.6471 | 1 | 5 | 0.2 | 10 | 20
| 2101 | 0.6 | 6.6667 | 18 | 23.982 | 3.2778 | 2.7042 | 1 | 5 | 0.6 | 3.3333 | 15
| 2102 | 1 | 4 | 11.4894 | 19.221 | 2.9317 | 4.8 | 0.2 | 25 | 0.1 | 20 | 49
| 2103 | 0.6 | 6.6667 | 10.3846 | 17.3705 | 2.6222 | 4.3636 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 2104 | 0.4 | 10 | 12.2727 | 18.0427 | 2.9873 | 2.7826 | 0.6 | 8.3333 | 0.1 | 20 | 38.3333
| 2105 | 1.6 | 2.5 | 12.2727 | 24.2795 | 3.6589 | 8.3478 | 0.6 | 8.3333 | 0.6 | 3.3333 | 14.1667
| 2106 | 1 | 4 | 11.0204 | 18.6664 | 2.5934 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 2107 | 0.6 | 6.6667 | 14.2105 | 20.7632 | 2.7126 | 3.84 | 1 | 5 | 0.6 | 3.3333 | 15
| 2108 | 0.6 | 6.6667 | 17.4194 | 26.7855 | 4.177 | 5.1892 | 1 | 5 | 0.4 | 5 | 16.6667
| 2109 | 0.4 | 10 | 13.8462 | 24.208 | 2.6818 | 7.68 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 2110 | 1 | 4 | 13.1707 | 20.868 | 3.1258 | 4.5714 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 2111 | 0.2 | 20 | 9.4737 | 17.3468 | 2.95 | 4.9231 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 2112 | 0.4 | 10 | 12.5581 | 18.7233 | 2.3251 | 3.84 | 1.4 | 3.5714 | 0.1 | 20 | 33.5714
| 2113 | 1.2 | 3.3333 | 12.5581 | 20.2315 | 2.4842 | 5.1892 | 1 | 5 | 0.2 | 10 | 18.3333
| 2114 | 0.6 | 6.6667 | 10 | 19.0222 | 2.6222 | 6.4 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 2115 | 1.2 | 3.3333 | 18 | 25.3714 | 3.3714 | 4 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 2116 | 0.8 | 5 | 15.4286 | 22.7614 | 2.2802 | 5.0526 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 2117 | 1.2 | 3.3333 | 13.1707 | 22.8466 | 2.2913 | 7.3846 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 2118 | 0.6 | 6.6667 | 13.5 | 18.7935 | 1.9832 | 3.3103 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 2119 | 0.4 | 10 | 12 | 18.149 | 2.5934 | 3.5556 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 2120 | 0.8 | 5 | 13.8462 | 21.8959 | 2.8606 | 5.1892 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 2121 | 0.6 | 6.6667 | 10 | 20.0664 | 2.6818 | 7.3846 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 2122 | 0.6 | 6.6667 | 15 | 20.438 | 2.878 | 2.56 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 2123 | 0.8 | 5 | 16.875 | 22.6552 | 2.8263 | 2.9538 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 2124 | 0.2 | 20 | 8.8525 | 15.2288 | 2.2913 | 4.0851 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 2125 | 1 | 4 | 11.4894 | 21.1738 | 4.4952 | 5.1892 | 1 | 5 | 0.8 | 2.5 | 11.5
| 2126 | 1.2 | 3.3333 | 12.5581 | 19.0319 | 3.0452 | 3.4286 | 1 | 5 | 0.4 | 5 | 13.3333
| 2127 | 0.8 | 5 | 11.0204 | 18.4871 | 2.6667 | 4.8 | 1 | 5 | 0.4 | 5 | 15
| 2128 | 0.6 | 6.6667 | 12.5581 | 28.484 | 3.1258 | 12.8 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 2129 | 0.8 | 5 | 13.1707 | 19.816 | 3.4453 | 3.2 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 2130 | 1.6 | 2.5 | 13.5 | 20.6803 | 3.0064 | 4.1739 | 1 | 5 | 0.4 | 5 | 12.5
| 2131 | 0.6 | 6.6667 | 10 | 16.5678 | 3.4203 | 3.1475 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 2132 | 0.6 | 6.6667 | 12 | 19.9678 | 3.1678 | 4.8 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 2133 | 0.4 | 10 | 15.4286 | 22.379 | 2.7765 | 4.1739 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 2134 | 0.4 | 10 | 12.2727 | 17.004 | 2.4456 | 2.2857 | 1 | 5 | 0.4 | 5 | 20
| 2135 | 0.2 | 20 | 12.5581 | 18.52 | 2.5934 | 3.3684 | 1 | 5 | 0.4 | 5 | 30
| 2136 | 1 | 4 | 24.5455 | 30.9499 | 2.9136 | 3.4909 | 1.4 | 3.5714 | 0.8 | 2.5 | 10.0714
| 2137 | 0.4 | 10 | 15.4286 | 24.5462 | 3.4706 | 5.6471 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 2138 | 1 | 4 | 10.8 | 17.1741 | 2.6818 | 3.6923 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 2139 | 0.6 | 6.6667 | 11.7391 | 18.9536 | 3.6589 | 3.5556 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 2140 | 0.6 | 6.6667 | 11.4894 | 17.3889 | 3.2329 | 2.6667 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 2141 | 1.4 | 2.8571 | 8.4375 | 15.1038 | 2.8263 | 3.84 | 1 | 5 | 1 | 2 | 9.8571
| 2142 | 1 | 4 | 11.0204 | 18.5952 | 2.6517 | 4.9231 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 2143 | 0.8 | 5 | 9.8182 | 15.6321 | 2.2584 | 3.5556 | 1 | 5 | 0.4 | 5 | 15
| 2144 | 1 | 4 | 12.2727 | 20.3654 | 2.4456 | 5.6471 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 2145 | 0.6 | 6.6667 | 10.5882 | 17.1724 | 2.7442 | 3.84 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 2146 | 1.4 | 2.8571 | 12.2727 | 20.1219 | 3.2778 | 4.5714 | 0.4 | 12.5 | 0.4 | 5 | 20.3571
| 2147 | 0.8 | 5 | 12.8571 | 18.2475 | 2.6077 | 2.7826 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 2148 | 0.6 | 6.6667 | 8.8525 | 17.1114 | 3.6875 | 4.5714 | 1.4 | 3.5714 | 0.1 | 20 | 30.2381
| 2149 | 0.1 | 40 | 12.5581 | 19.2834 | 2.5514 | 4.1739 | 0.6 | 8.3333 | 0.6 | 3.3333 | 51.6667
| 2150 | 1 | 4 | 20.7692 | 28.0378 | 2.6971 | 4.5714 | 0.2 | 25 | 0.6 | 3.3333 | 32.3333
| 2151 | 0.6 | 6.6667 | 12 | 20.0978 | 3.0452 | 5.0526 | 1 | 5 | 0.6 | 3.3333 | 15
| 2152 | 0.4 | 10 | 14.2105 | 21.1447 | 2.7602 | 4.1739 | 1 | 5 | 0.4 | 5 | 20
| 2153 | 0.6 | 6.6667 | 10 | 18.288 | 3.7165 | 4.5714 | 1 | 5 | 0.6 | 3.3333 | 15
| 2154 | 1.4 | 2.8571 | 14.2105 | 21.635 | 2.3719 | 5.0526 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 2155 | 1.6 | 2.5 | 8.3077 | 18.6354 | 3.4706 | 6.8571 | 0.8 | 6.25 | 0.2 | 10 | 18.75
| 2156 | 1 | 4 | 11.0204 | 18.2435 | 2.6517 | 4.5714 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 2157 | 0.6 | 6.6667 | 12.2727 | 21.9584 | 3.0649 | 6.6207 | 1 | 5 | 0.2 | 10 | 21.6667
| 2158 | 0.2 | 20 | 12.8571 | 21.0593 | 3.6308 | 4.5714 | 1.2 | 4.1667 | 0.1 | 20 | 44.1667
| 2159 | 1.2 | 3.3333 | 12 | 18.4192 | 2.5792 | 3.84 | 1 | 5 | 0.4 | 5 | 13.3333
| 2160 | 0.8 | 5 | 15.8824 | 22.3258 | 3.1892 | 3.2542 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 2161 | 0.6 | 6.6667 | 12.2727 | 19.5316 | 3.085 | 4.1739 | 1 | 5 | 0.2 | 10 | 21.6667
| 2162 | 0.8 | 5 | 11.7391 | 22.6527 | 2.9136 | 8 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 2163 | 0.6 | 6.6667 | 11.0204 | 18.8752 | 2.9317 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 15
| 2164 | 1 | 4 | 11.4894 | 18.3075 | 3.1258 | 3.6923 | 1 | 5 | 0.2 | 10 | 19
| 2165 | 1 | 4 | 11.25 | 18.3553 | 3.1053 | 4 | 1 | 5 | 0.4 | 5 | 14
| 2166 | 0.6 | 6.6667 | 11.4894 | 18.1121 | 2.5376 | 4.0851 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 2167 | 0.6 | 6.6667 | 13.8462 | 22.0602 | 2.7283 | 5.4857 | 1 | 5 | 0.1 | 20 | 31.6667
| 2168 | 1.2 | 3.3333 | 12.5581 | 21.9666 | 2.5514 | 6.8571 | 0.6 | 8.3333 | 0.1 | 20 | 31.6667
| 2169 | 0.6 | 6.6667 | 7.9412 | 14.6929 | 2.6667 | 4.0851 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 2170 | 1 | 4 | 15.8824 | 21.3665 | 2.3366 | 3.1475 | 1 | 5 | 0.8 | 2.5 | 11.5
| 2171 | 1 | 4 | 13.5 | 21.5778 | 3.2778 | 4.8 | 1 | 5 | 0.8 | 2.5 | 11.5
| 2172 | 0.4 | 10 | 11.7391 | 17.3068 | 2.7442 | 2.8235 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 2173 | 1.2 | 3.3333 | 13.8462 | 20.1205 | 2.6517 | 3.6226 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 2174 | 1.2 | 3.3333 | 11.25 | 17.0322 | 2.2913 | 3.4909 | 1.6 | 3.125 | 0.4 | 5 | 11.4583
| 2175 | 1 | 4 | 15 | 24.3239 | 3.3239 | 6 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 2176 | 0.4 | 10 | 8.3077 | 16.9299 | 2.6222 | 6 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 2177 | 1 | 4 | 13.8462 | 21.4876 | 3.2778 | 4.3636 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 2178 | 0.1 | 40 | 11.4894 | 17.6383 | 2.5934 | 3.5556 | 1 | 5 | 0.8 | 2.5 | 47.5
| 2179 | 0.6 | 6.6667 | 12.8571 | 18.0013 | 2.7442 | 2.4 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 2180 | 1 | 4 | 11.25 | 17.4427 | 3.0452 | 3.1475 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 2181 | 0.6 | 6.6667 | 15 | 21.4336 | 2.878 | 3.5556 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 2182 | 1 | 4 | 17.4194 | 25.5976 | 3.2552 | 4.9231 | 1 | 5 | 0.4 | 5 | 14
| 2183 | 1 | 4 | 13.5 | 22.5909 | 4.2909 | 4.8 | 1.4 | 3.5714 | 0.1 | 20 | 27.5714
| 2184 | 0.8 | 5 | 14.5946 | 23.7624 | 3.1678 | 6 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 2185 | 0.6 | 6.6667 | 11.25 | 19.9901 | 3.6875 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 2186 | 0.6 | 6.6667 | 9 | 17.156 | 3.2329 | 4.9231 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 2187 | 1.2 | 3.3333 | 11.7391 | 21.6376 | 3.2778 | 6.6207 | 0.4 | 12.5 | 0.1 | 20 | 35.8333
| 2188 | 0.8 | 5 | 8.3077 | 15.3273 | 2.3366 | 4.6829 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2189 | 0.8 | 5 | 12.5581 | 18.7119 | 2.8434 | 3.3103 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2190 | 1.2 | 3.3333 | 16.3636 | 22.4035 | 3.4453 | 2.5946 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 2191 | 0.8 | 5 | 10.5882 | 18.5069 | 2.433 | 5.4857 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 2192 | 0.8 | 5 | 10.1887 | 18.9982 | 2.8095 | 6 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 2193 | 1.2 | 3.3333 | 11.0204 | 18.4138 | 2.5934 | 4.8 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 2194 | 1.2 | 3.3333 | 9.3103 | 19.4047 | 3.9008 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 2195 | 0.8 | 5 | 15.4286 | 22.9193 | 3.0256 | 4.4651 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 2196 | 0.2 | 20 | 12.2727 | 18.8241 | 2.5514 | 4 | 0.6 | 8.3333 | 0.6 | 3.3333 | 31.6667
| 2197 | 1.2 | 3.3333 | 10.1887 | 16.3596 | 2.8606 | 3.3103 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 2198 | 0.2 | 20 | 9.8182 | 17.9885 | 4.3303 | 3.84 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 2199 | 0.8 | 5 | 12 | 19.3624 | 3.5224 | 3.84 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 2200 | 1.2 | 3.3333 | 9.1525 | 16.0482 | 2.8957 | 4 | 1 | 5 | 0.2 | 10 | 18.3333
| 2201 | 0.6 | 6.6667 | 11.0204 | 17.0511 | 2.7765 | 3.2542 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 2202 | 0.6 | 6.6667 | 15 | 25.7442 | 2.7442 | 8 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 2203 | 1 | 4 | 28.4211 | 38.4835 | 3.8689 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 2204 | 1.4 | 2.8571 | 17.4194 | 24.757 | 2.5376 | 4.8 | 1 | 5 | 0.4 | 5 | 12.8571
| 2205 | 0.6 | 6.6667 | 9.6429 | 15.8356 | 3.0452 | 3.1475 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 2206 | 0.6 | 6.6667 | 13.5 | 22.2048 | 3.3714 | 5.3333 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 2207 | 0.8 | 5 | 11.25 | 18.0633 | 3.7165 | 3.0968 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 2208 | 0.6 | 6.6667 | 9.1525 | 15.4947 | 2.9136 | 3.4286 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 2209 | 1 | 4 | 9.6429 | 17.0506 | 2.6077 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 2210 | 1 | 4 | 11.0204 | 16.7763 | 2.4456 | 3.3103 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 2211 | 0.2 | 20 | 17.4194 | 23.3707 | 2.6971 | 3.2542 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 2212 | 1 | 4 | 12 | 17.3288 | 2.9873 | 2.3415 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 2213 | 0.8 | 5 | 13.8462 | 22.2777 | 3.9664 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2214 | 1 | 4 | 13.1707 | 19.1109 | 2.8434 | 3.0968 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 2215 | 0.4 | 10 | 13.1707 | 18.5721 | 2.6971 | 2.7042 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 2216 | 1 | 4 | 10.1887 | 16.8109 | 2.6222 | 4 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 2217 | 1 | 4 | 11.0204 | 19.5108 | 2.8434 | 5.6471 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 2218 | 1 | 4 | 11.4894 | 18.6964 | 2.5241 | 4.6829 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 2219 | 0.6 | 6.6667 | 11.4894 | 17.8214 | 2.7765 | 3.5556 | 1 | 5 | 0.4 | 5 | 16.6667
| 2220 | 0.2 | 20 | 14.5946 | 22.7956 | 3.8374 | 4.3636 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 2221 | 1 | 4 | 13.8462 | 22.4371 | 3.1053 | 5.4857 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 2222 | 0.8 | 5 | 10.5882 | 18.1251 | 2.4842 | 5.0526 | 1 | 5 | 0.2 | 10 | 20
| 2223 | 1 | 4 | 10 | 16.8606 | 2.8606 | 4 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 2224 | 1 | 4 | 12 | 19.006 | 4.1404 | 2.8657 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 2225 | 0.1 | 40 | 10.5882 | 18.0872 | 3.6589 | 3.84 | 1 | 5 | 0.2 | 10 | 55
| 2226 | 0.2 | 20 | 14.5946 | 21.4689 | 2.5106 | 4.3636 | 1 | 5 | 0.2 | 10 | 35
| 2227 | 0.8 | 5 | 11.7391 | 17.1597 | 2.8606 | 2.56 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 2228 | 0.6 | 6.6667 | 9.1525 | 17.9207 | 2.95 | 5.8182 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 2229 | 0.6 | 6.6667 | 8.8525 | 17.2637 | 4.4112 | 4 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 2230 | 1 | 4 | 14.2105 | 21.0402 | 3.0649 | 3.7647 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 2231 | 0.1 | 40 | 11.7391 | 19.505 | 2.2802 | 5.4857 | 1 | 5 | 1 | 2 | 47
| 2232 | 0.8 | 5 | 9.4737 | 16.375 | 2.5376 | 4.3636 | 1 | 5 | 0.8 | 2.5 | 12.5
| 2233 | 0.4 | 10 | 8.4375 | 14.9247 | 2.9317 | 3.5556 | 1.6 | 3.125 | 0.4 | 5 | 18.125
| 2234 | 0.8 | 5 | 12.2727 | 21.5114 | 3.0452 | 6.1935 | 1 | 5 | 0.4 | 5 | 15
| 2235 | 1.2 | 3.3333 | 12.5581 | 17.8538 | 2.8957 | 2.4 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 2236 | 1 | 4 | 7.013 | 13.3725 | 3.1053 | 3.2542 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 2237 | 1 | 4 | 10.5882 | 16.8992 | 3.4453 | 2.8657 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 2238 | 0.4 | 10 | 12 | 20.2303 | 3.6589 | 4.5714 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 2239 | 0.4 | 10 | 9.4737 | 17.1252 | 2.9686 | 4.6829 | 1 | 5 | 0.4 | 5 | 20
| 2240 | 1 | 4 | 12.2727 | 19.6044 | 2.7602 | 4.5714 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 2241 | 1.2 | 3.3333 | 10.1887 | 17.6578 | 2.1357 | 5.3333 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 2242 | 1 | 4 | 12.5581 | 20.3842 | 2.6369 | 5.1892 | 1 | 5 | 0.4 | 5 | 14
| 2243 | 0.6 | 6.6667 | 12.5581 | 18.9101 | 3.2552 | 3.0968 | 1 | 5 | 0.4 | 5 | 16.6667
| 2244 | 0.8 | 5 | 11.7391 | 18.4035 | 2.5792 | 4.0851 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 2245 | 1 | 4 | 11.4894 | 18.8982 | 3.0452 | 4.3636 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 2246 | 1 | 4 | 8.5714 | 17.2403 | 3.8689 | 4.8 | 1 | 5 | 0.2 | 10 | 19
| 2247 | 0.6 | 6.6667 | 10.8 | 21.3871 | 3.9664 | 6.6207 | 1.8 | 2.7778 | 0.2 | 10 | 19.4444
| 2248 | 0.6 | 6.6667 | 14.2105 | 25.4017 | 2.8434 | 8.3478 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 2249 | 0.4 | 10 | 9.1525 | 16.9791 | 3.2552 | 4.5714 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 2250 | 0.4 | 10 | 9.4737 | 18.0843 | 3.6875 | 4.9231 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 2251 | 1 | 4 | 18 | 25.3403 | 3.2552 | 4.0851 | 1 | 5 | 0.4 | 5 | 14
| 2252 | 0.6 | 6.6667 | 18 | 26.9792 | 2.5792 | 6.4 | 1 | 5 | 0.4 | 5 | 16.6667
| 2253 | 0.2 | 20 | 11.4894 | 18.4433 | 3.1892 | 3.7647 | 1 | 5 | 0.2 | 10 | 35
| 2254 | 0.8 | 5 | 15 | 21.8407 | 2.2692 | 4.5714 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2255 | 0.1 | 40 | 12.5581 | 19.0765 | 2.8957 | 3.6226 | 1.4 | 3.5714 | 0.2 | 10 | 53.5714
| 2256 | 1.2 | 3.3333 | 15.4286 | 21.5127 | 2.9873 | 3.0968 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 2257 | 0.6 | 6.6667 | 10.5882 | 17.2854 | 2.6971 | 4 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 2258 | 0.2 | 20 | 13.8462 | 20.2238 | 2.5376 | 3.84 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 2259 | 0.4 | 10 | 13.1707 | 19.5583 | 2.3024 | 4.0851 | 1 | 5 | 0.4 | 5 | 20
| 2260 | 1.4 | 2.8571 | 13.5 | 20.5585 | 2.5934 | 4.4651 | 0.6 | 8.3333 | 1 | 2 | 13.1905
| 2261 | 0.6 | 6.6667 | 11.25 | 18.546 | 3.2109 | 4.0851 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 2262 | 0.8 | 5 | 10.3846 | 15.8401 | 2.7126 | 2.7429 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 2263 | 0.8 | 5 | 13.1707 | 23.0933 | 4.1043 | 5.8182 | 1.8 | 2.7778 | 0.6 | 3.3333 | 11.1111
| 2264 | 0.6 | 6.6667 | 13.8462 | 20.4039 | 2.3838 | 4.1739 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 2265 | 0.4 | 10 | 9.8182 | 17.9464 | 3.4453 | 4.6829 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 2266 | 1.4 | 2.8571 | 13.8462 | 20.5425 | 3.4963 | 3.2 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 2267 | 0.4 | 10 | 13.5 | 20.7416 | 2.7765 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 2268 | 1 | 4 | 11.7391 | 16.9559 | 2.6222 | 2.5946 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 2269 | 1 | 4 | 10.1887 | 17.9279 | 3.1678 | 4.5714 | 1 | 5 | 0.2 | 10 | 19
| 2270 | 1 | 4 | 20 | 26.242 | 2.9317 | 3.3103 | 1 | 5 | 0.4 | 5 | 14
| 2271 | 0.6 | 6.6667 | 14.5946 | 20.6398 | 3.0452 | 3 | 1 | 5 | 0.4 | 5 | 16.6667
| 2272 | 0.8 | 5 | 13.8462 | 22.1649 | 3.3957 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2273 | 0.6 | 6.6667 | 10.3846 | 16.0797 | 3.0649 | 2.6301 | 1.6 | 3.125 | 0.4 | 5 | 14.7917
| 2274 | 0.8 | 5 | 10.1887 | 17.316 | 2.8606 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2275 | 0.8 | 5 | 20.7692 | 28.1485 | 2.5792 | 4.8 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 2276 | 0.8 | 5 | 11.0204 | 22.8126 | 3.0649 | 8.7273 | 0.8 | 6.25 | 1 | 2 | 13.25
| 2277 | 0.6 | 6.6667 | 13.5 | 22.7022 | 3.7165 | 5.4857 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 2278 | 0.6 | 6.6667 | 12.8571 | 20.6305 | 3.9333 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 2279 | 0.6 | 6.6667 | 10.3846 | 16.4047 | 2.6517 | 3.3684 | 1 | 5 | 0.4 | 5 | 16.6667
| 2280 | 0.8 | 5 | 15.4286 | 22.0136 | 2.6667 | 3.9184 | 1 | 5 | 0.8 | 2.5 | 12.5
| 2281 | 0.8 | 5 | 10.5882 | 20.0613 | 2.0885 | 7.3846 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 2282 | 1 | 4 | 9.3103 | 15.554 | 2.5514 | 3.6923 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 2283 | 1 | 4 | 12.2727 | 19.4613 | 3.4963 | 3.6923 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 2284 | 0.4 | 10 | 12.5581 | 27.8523 | 4.6275 | 10.6667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 2285 | 0.2 | 20 | 13.1707 | 19.0498 | 2.5106 | 3.3684 | 1.4 | 3.5714 | 0.2 | 10 | 33.5714
| 2286 | 1 | 4 | 9.1525 | 15.9859 | 3.2778 | 3.5556 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 2287 | 0.8 | 5 | 12 | 19.1076 | 3.1892 | 3.9184 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 2288 | 1 | 4 | 12.8571 | 20.4611 | 2.5514 | 5.0526 | 1 | 5 | 0.1 | 20 | 29
| 2289 | 1.2 | 3.3333 | 10 | 19.9446 | 3.3239 | 6.6207 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 2290 | 0.6 | 6.6667 | 9.3103 | 17.2935 | 3.7165 | 4.2667 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 2291 | 0.8 | 5 | 11.0204 | 20.0024 | 3.4963 | 5.4857 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 2292 | 1.4 | 2.8571 | 10 | 18.156 | 3.2329 | 4.9231 | 1 | 5 | 0.4 | 5 | 12.8571
| 2293 | 0.8 | 5 | 11.4894 | 16.9361 | 2.5376 | 2.9091 | 1 | 5 | 0.2 | 10 | 20
| 2294 | 0.4 | 10 | 9.8182 | 22.3803 | 4.2143 | 8.3478 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 2295 | 0.2 | 20 | 8.8525 | 16.2312 | 2.9136 | 4.4651 | 0.6 | 8.3333 | 0.6 | 3.3333 | 31.6667
| 2296 | 1 | 4 | 8.8525 | 16.4221 | 3.3957 | 4.1739 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 2297 | 0.4 | 10 | 12 | 19.3392 | 3.7165 | 3.6226 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 2298 | 1 | 4 | 14.5946 | 22.1694 | 2.6517 | 4.9231 | 0.4 | 12.5 | 0.1 | 20 | 36.5
| 2299 | 0.2 | 20 | 15 | 22.2998 | 2.7283 | 4.5714 | 0.6 | 8.3333 | 0.8 | 2.5 | 30.8333
| 2300 | 1.4 | 2.8571 | 17.4194 | 26.491 | 2.878 | 6.1935 | 1.4 | 3.5714 | 0.6 | 3.3333 | 9.7619
| 2301 | 0.6 | 6.6667 | 15.8824 | 23.315 | 3.3475 | 4.0851 | 1 | 5 | 0.2 | 10 | 21.6667
| 2302 | 1 | 4 | 14.2105 | 24.0308 | 3.4203 | 6.4 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 2303 | 1.4 | 2.8571 | 18 | 25.7498 | 2.6971 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 2304 | 0.8 | 5 | 10.1887 | 17.3428 | 2.4712 | 4.6829 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 2305 | 0.6 | 6.6667 | 13.5 | 21.1957 | 2.8957 | 4.8 | 1.4 | 3.5714 | 0.1 | 20 | 30.2381
| 2306 | 1 | 4 | 12 | 19.3561 | 2.433 | 4.9231 | 1.8 | 2.7778 | 0.1 | 20 | 26.7778
| 2307 | 0.6 | 6.6667 | 16.3636 | 23.7041 | 3.5758 | 3.7647 | 1 | 5 | 0.4 | 5 | 16.6667
| 2308 | 1.2 | 3.3333 | 10.1887 | 15.7243 | 3.1053 | 2.4304 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 2309 | 0.8 | 5 | 14.5946 | 23.0489 | 2.9686 | 5.4857 | 1 | 5 | 0.4 | 5 | 15
| 2310 | 0.6 | 6.6667 | 14.2105 | 20.6793 | 2.7765 | 3.6923 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 2311 | 0.4 | 10 | 11.0204 | 17.2085 | 2.6971 | 3.4909 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 2312 | 1 | 4 | 15 | 21.5792 | 2.5792 | 4 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.8333
| 2313 | 0.6 | 6.6667 | 16.875 | 23.9194 | 2.5792 | 4.4651 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 2314 | 1.2 | 3.3333 | 9.6429 | 17.1424 | 3.2329 | 4.2667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 2315 | 0.6 | 6.6667 | 11.0204 | 16.3541 | 2.237 | 3.0968 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 2316 | 0.8 | 5 | 13.8462 | 21.1385 | 3.0256 | 4.2667 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 2317 | 1.2 | 3.3333 | 19.2857 | 24.8537 | 2.3137 | 3.2542 | 1 | 5 | 0.2 | 10 | 18.3333
| 2318 | 0.4 | 10 | 11.4894 | 18.821 | 2.7602 | 4.5714 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 2319 | 0.2 | 20 | 10 | 17.8016 | 3.7165 | 4.0851 | 0.4 | 12.5 | 0.1 | 20 | 52.5
| 2320 | 0.6 | 6.6667 | 14.2105 | 21.4699 | 2.8957 | 4.3636 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 2321 | 0.8 | 5 | 12.5581 | 18.764 | 3.5758 | 2.6301 | 1 | 5 | 0.1 | 20 | 30
| 2322 | 1 | 4 | 12.8571 | 21.3938 | 3.3475 | 5.1892 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 2323 | 0.6 | 6.6667 | 11.7391 | 19.4364 | 3.1258 | 4.5714 | 1 | 5 | 0.2 | 10 | 21.6667
| 2324 | 0.6 | 6.6667 | 12.5581 | 20.773 | 3.0256 | 5.1892 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 2325 | 0.8 | 5 | 9.6429 | 16.3913 | 3.1258 | 3.6226 | 1 | 5 | 0.4 | 5 | 15
| 2326 | 0.8 | 5 | 13.8462 | 21.1208 | 2.8095 | 4.4651 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 2327 | 0.2 | 20 | 12.8571 | 21.3492 | 3.0064 | 5.4857 | 0.4 | 12.5 | 0.2 | 10 | 42.5
| 2328 | 1.4 | 2.8571 | 12 | 18.0053 | 2.6369 | 3.3684 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 2329 | 1 | 4 | 10.1887 | 17.207 | 3.3957 | 3.6226 | 1 | 5 | 0.4 | 5 | 14
| 2330 | 0.2 | 20 | 12.8571 | 18.9697 | 3.0649 | 3.0476 | 0.8 | 6.25 | 0.8 | 2.5 | 28.75
| 2331 | 0.4 | 10 | 10.5882 | 17.4488 | 2.8606 | 4 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 2332 | 0.8 | 5 | 14.2105 | 21.7662 | 3.4706 | 4.0851 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 2333 | 1 | 4 | 13.5 | 20.1609 | 3.8374 | 2.8235 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 2334 | 0.8 | 5 | 15.8824 | 23.8118 | 3.0064 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 2335 | 0.8 | 5 | 13.8462 | 19.933 | 2.7765 | 3.3103 | 1 | 5 | 0.2 | 10 | 20
| 2336 | 0.6 | 6.6667 | 17.4194 | 26.3904 | 3.3239 | 5.6471 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 2337 | 0.8 | 5 | 10.8 | 18.7381 | 3.2552 | 4.6829 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 2338 | 0.6 | 6.6667 | 12.5581 | 18.8301 | 2.8434 | 3.4286 | 1 | 5 | 0.1 | 20 | 31.6667
| 2339 | 0.4 | 10 | 15 | 24.9921 | 3.3714 | 6.6207 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 2340 | 1 | 4 | 13.5 | 21.488 | 3.0649 | 4.9231 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 2341 | 0.6 | 6.6667 | 15.4286 | 23.9392 | 2.5106 | 6 | 1.6 | 3.125 | 0.4 | 5 | 14.7917
| 2342 | 1 | 4 | 16.875 | 29.2898 | 3.6875 | 8.7273 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 2343 | 1.6 | 2.5 | 12.5581 | 23.4015 | 2.8434 | 8 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.0833
| 2344 | 1 | 4 | 9.3103 | 19.7599 | 3.0649 | 7.3846 | 1 | 5 | 0.1 | 20 | 29
| 2345 | 0.6 | 6.6667 | 12.2727 | 19.8485 | 3.5758 | 4 | 1.4 | 3.5714 | 0.8 | 2.5 | 12.7381
| 2346 | 1.2 | 3.3333 | 9 | 15.5056 | 2.95 | 3.5556 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 2347 | 0.4 | 10 | 7.2973 | 15.3824 | 4 | 4.0851 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 2348 | 0.6 | 6.6667 | 9.6429 | 17.6091 | 2.9136 | 5.0526 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 2349 | 0.6 | 6.6667 | 12 | 19.296 | 3.2109 | 4.0851 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 2350 | 1 | 4 | 15 | 20.9078 | 2.7602 | 3.1475 | 1 | 5 | 0.4 | 5 | 14
| 2351 | 0.8 | 5 | 11.7391 | 19.3637 | 2.2913 | 5.3333 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 2352 | 0.1 | 40 | 10.5882 | 15.6767 | 2.4583 | 2.6301 | 1.2 | 4.1667 | 0.4 | 5 | 49.1667
| 2353 | 1 | 4 | 12 | 18.8563 | 3.3007 | 3.5556 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 2354 | 0.8 | 5 | 11.7391 | 19.3487 | 2.8095 | 4.8 | 1 | 5 | 0.1 | 20 | 30
| 2355 | 0.6 | 6.6667 | 18 | 26.214 | 2.7283 | 5.4857 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 2356 | 1.2 | 3.3333 | 13.1707 | 19.2915 | 2.5652 | 3.5556 | 1 | 5 | 0.4 | 5 | 13.3333
| 2357 | 0.4 | 10 | 14.2105 | 21.017 | 3.8065 | 3 | 1 | 5 | 0.4 | 5 | 20
| 2358 | 1 | 4 | 10.1887 | 17.3387 | 3.0649 | 4.0851 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 2359 | 0.4 | 10 | 10.8 | 20.5057 | 3.085 | 6.6207 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 2360 | 0.4 | 10 | 15.8824 | 24.3044 | 3.2329 | 5.1892 | 1 | 5 | 0.2 | 10 | 25
| 2361 | 1 | 4 | 16.875 | 26.5079 | 3.2329 | 6.4 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 2362 | 0.8 | 5 | 10.1887 | 18.557 | 3.4453 | 4.9231 | 1 | 5 | 0.4 | 5 | 15
| 2363 | 1 | 4 | 12.8571 | 21.494 | 2.6369 | 6 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 2364 | 0.8 | 5 | 12.5581 | 24.6271 | 4.069 | 8 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 2365 | 0.4 | 10 | 11.7391 | 17.8758 | 2.8263 | 3.3103 | 1 | 5 | 0.2 | 10 | 25
| 2366 | 0.8 | 5 | 13.1707 | 19.0216 | 2.36 | 3.4909 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 2367 | 0.6 | 6.6667 | 13.8462 | 20.3597 | 3.085 | 3.4286 | 0.6 | 8.3333 | 0.1 | 20 | 35
| 2368 | 1 | 4 | 10.1887 | 20.6237 | 3.3239 | 7.1111 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 2369 | 0.6 | 6.6667 | 10.3846 | 16.8066 | 3.1678 | 3.2542 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 2370 | 1.2 | 3.3333 | 14.5946 | 23.1374 | 2.8957 | 5.6471 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 2371 | 0.6 | 6.6667 | 14.5946 | 21.0516 | 3.1467 | 3.3103 | 1 | 5 | 0.6 | 3.3333 | 15
| 2372 | 0.2 | 20 | 12.8571 | 19.2324 | 3.0649 | 3.3103 | 1 | 5 | 0.4 | 5 | 30
| 2373 | 1.2 | 3.3333 | 10 | 16.0344 | 3.2109 | 2.8235 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 2374 | 0.8 | 5 | 11.4894 | 19.649 | 2.8263 | 5.3333 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 2375 | 0.4 | 10 | 20 | 24.8291 | 2.6222 | 2.2069 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 2376 | 0.8 | 5 | 14.2105 | 21.1979 | 2.9873 | 4 | 1 | 5 | 0.1 | 20 | 30
| 2377 | 0.6 | 6.6667 | 11.4894 | 22.7407 | 2.5241 | 8.7273 | 1 | 5 | 0.2 | 10 | 21.6667
| 2378 | 0.8 | 5 | 8.1818 | 13.8869 | 2.3366 | 3.3684 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 2379 | 1.4 | 2.8571 | 10.5882 | 18.1374 | 3.6308 | 3.9184 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 2380 | 1.2 | 3.3333 | 11.7391 | 20.1565 | 2.9317 | 5.4857 | 1 | 5 | 0.4 | 5 | 13.3333
| 2381 | 0.6 | 6.6667 | 14.2105 | 21.5537 | 2.878 | 4.4651 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 2382 | 1.2 | 3.3333 | 11.25 | 19.6437 | 3.4706 | 4.9231 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 2383 | 1.2 | 3.3333 | 10.3846 | 16.8763 | 2.6517 | 3.84 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 2384 | 1 | 4 | 12.5581 | 21.0581 | 2.6818 | 5.8182 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 2385 | 0.6 | 6.6667 | 15.8824 | 23.3389 | 3.3714 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 2386 | 0.4 | 10 | 16.875 | 24.5931 | 3.1467 | 4.5714 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 2387 | 0.2 | 20 | 15 | 22.2503 | 2.0611 | 5.1892 | 0.6 | 8.3333 | 0.2 | 10 | 38.3333
| 2388 | 1.6 | 2.5 | 10.5882 | 16.9607 | 2.6077 | 3.7647 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10
| 2389 | 0.8 | 5 | 12.8571 | 21.8436 | 2.7929 | 6.1935 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 2390 | 0.8 | 5 | 11.0204 | 21.1767 | 3.0452 | 7.1111 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 2391 | 1.4 | 2.8571 | 14.5946 | 22.241 | 3.8065 | 3.84 | 1.4 | 3.5714 | 0.4 | 5 | 11.4286
| 2392 | 0.6 | 6.6667 | 9.6429 | 19.5803 | 2.8263 | 7.1111 | 1.4 | 3.5714 | 0.8 | 2.5 | 12.7381
| 2393 | 0.8 | 5 | 12.2727 | 17.4317 | 3.0256 | 2.1333 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2394 | 0.4 | 10 | 12 | 22 | 4 | 6 | 0.4 | 12.5 | 0.4 | 5 | 27.5
| 2395 | 0.6 | 6.6667 | 12.2727 | 18.4053 | 3.085 | 3.0476 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 2396 | 0.8 | 5 | 12.5581 | 19.501 | 2.5792 | 4.3636 | 0.4 | 12.5 | 1 | 2 | 19.5
| 2397 | 0.8 | 5 | 12.8571 | 20.3454 | 2.5652 | 4.9231 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 2398 | 1.2 | 3.3333 | 13.5 | 22.6225 | 3.9333 | 5.1892 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.1667
| 2399 | 0.8 | 5 | 12.2727 | 19.3246 | 3.4963 | 3.5556 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 2400 | 0.6 | 6.6667 | 11.25 | 17.3705 | 3.6589 | 2.4615 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 2401 | 0.8 | 5 | 9.3103 | 21.1815 | 2.7283 | 9.1429 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 2402 | 1.2 | 3.3333 | 9.6429 | 18.1582 | 2.6971 | 5.8182 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 2403 | 0.8 | 5 | 10 | 18.0672 | 2.878 | 5.1892 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 2404 | 1.2 | 3.3333 | 11.7391 | 20.2909 | 3.8689 | 4.6829 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 2405 | 0.8 | 5 | 15 | 23.7929 | 2.7929 | 6 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2406 | 0.4 | 10 | 10.3846 | 17.3359 | 3.3957 | 3.5556 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 2407 | 1 | 4 | 13.5 | 23.7369 | 3.1258 | 7.1111 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 2408 | 0.6 | 6.6667 | 17.4194 | 25.9846 | 2.5652 | 6 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 2409 | 0.8 | 5 | 13.1707 | 20.7143 | 2.8606 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 2410 | 0.6 | 6.6667 | 11.25 | 18.6301 | 2.6971 | 4.6829 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 2411 | 0.8 | 5 | 12.5581 | 22.7392 | 3.3239 | 6.8571 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 2412 | 1.4 | 2.8571 | 10.1887 | 17.2232 | 2.8606 | 4.1739 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 2413 | 0.6 | 6.6667 | 6.75 | 15.5422 | 3.6031 | 5.1892 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 2414 | 1.2 | 3.3333 | 15 | 23.2945 | 3.1053 | 5.1892 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 2415 | 0.4 | 10 | 11.25 | 18.6219 | 3.1053 | 4.2667 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 2416 | 0.6 | 6.6667 | 10.3846 | 18.5055 | 2.9317 | 5.1892 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 2417 | 1.4 | 2.8571 | 14.5946 | 21.3502 | 3.4453 | 3.3103 | 1.4 | 3.5714 | 0.4 | 5 | 11.4286
| 2418 | 0.6 | 6.6667 | 11.25 | 16.904 | 2.9873 | 2.6667 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 2419 | 0.1 | 40 | 10.8 | 19.2174 | 2.9317 | 5.4857 | 1.6 | 3.125 | 0.2 | 10 | 53.125
| 2420 | 0.8 | 5 | 9.8182 | 16.1784 | 2.9317 | 3.4286 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2421 | 1.4 | 2.8571 | 10.5882 | 18.0476 | 2.7765 | 4.6829 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 2422 | 1 | 4 | 10 | 15.999 | 3.0452 | 2.9538 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 2423 | 0.6 | 6.6667 | 12 | 18.9341 | 2.7602 | 4.1739 | 1 | 5 | 0.6 | 3.3333 | 15
| 2424 | 0.8 | 5 | 11.0204 | 17.5347 | 2.2476 | 4.2667 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 2425 | 0.6 | 6.6667 | 10.3846 | 16.6899 | 3.1053 | 3.2 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 2426 | 1 | 4 | 15.4286 | 23.1915 | 3.4963 | 4.2667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 2427 | 0.6 | 6.6667 | 9.6429 | 17.7364 | 2.7602 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 2428 | 1 | 4 | 11.25 | 16.8761 | 2.3719 | 3.2542 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 2429 | 0.4 | 10 | 7.2 | 15.4459 | 2.7602 | 5.4857 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 2430 | 1.2 | 3.3333 | 13.5 | 20.2461 | 3.2552 | 3.4909 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 2431 | 1.2 | 3.3333 | 14.2105 | 21.3392 | 2.2056 | 4.9231 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.1667
| 2432 | 0.8 | 5 | 14.5946 | 21.5954 | 3.4453 | 3.5556 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 2433 | 0.6 | 6.6667 | 12.2727 | 19.9236 | 2.1651 | 5.4857 | 1 | 5 | 0.2 | 10 | 21.6667
| 2434 | 0.6 | 6.6667 | 8.4375 | 14.1928 | 2.6077 | 3.1475 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 2435 | 0.6 | 6.6667 | 10.5882 | 19.7778 | 3.3714 | 5.8182 | 1 | 5 | 0.1 | 20 | 31.6667
| 2436 | 1 | 4 | 12.8571 | 21.3015 | 3.2552 | 5.1892 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 2437 | 0.4 | 10 | 15 | 21.7293 | 3.3007 | 3.4286 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 2438 | 0.8 | 5 | 9.6429 | 15.8656 | 2.9686 | 3.2542 | 1 | 5 | 0.2 | 10 | 20
| 2439 | 0.1 | 40 | 9.1525 | 16.6628 | 3.0452 | 4.4651 | 1 | 5 | 0.4 | 5 | 50
| 2440 | 0.8 | 5 | 10.8 | 19.1993 | 2.9136 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 2441 | 0.8 | 5 | 12.8571 | 20.0175 | 3.3957 | 3.7647 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 2442 | 0.8 | 5 | 13.1707 | 20.0135 | 3.746 | 3.0968 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 2443 | 0.8 | 5 | 12 | 18.3011 | 2.0345 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2444 | 0.6 | 6.6667 | 13.8462 | 25.0897 | 2.8957 | 8.3478 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 2445 | 1 | 4 | 11.7391 | 21.9151 | 3.776 | 6.4 | 1.4 | 3.5714 | 0.8 | 2.5 | 10.0714
| 2446 | 0.6 | 6.6667 | 15.4286 | 21.5096 | 2.7126 | 3.3684 | 1 | 5 | 0.4 | 5 | 16.6667
| 2447 | 0.6 | 6.6667 | 9.3103 | 16.0379 | 3.6308 | 3.0968 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 2448 | 1.2 | 3.3333 | 13.1707 | 23.508 | 3.7165 | 6.6207 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 2449 | 0.6 | 6.6667 | 12.8571 | 19.2587 | 2.6369 | 3.7647 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 2450 | 0.4 | 10 | 12 | 20.1939 | 2.8606 | 5.3333 | 1.6 | 3.125 | 0.2 | 10 | 23.125
| 2451 | 0.6 | 6.6667 | 10.5882 | 20.7052 | 3.4963 | 6.6207 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 2452 | 0.8 | 5 | 10.1887 | 24.2756 | 3.4203 | 10.6667 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 2453 | 1.4 | 2.8571 | 12.8571 | 21.5619 | 3.3714 | 5.3333 | 0.8 | 6.25 | 0.8 | 2.5 | 11.6071
| 2454 | 1 | 4 | 12.2727 | 20.3518 | 2.5934 | 5.4857 | 1.6 | 3.125 | 0.2 | 10 | 17.125
| 2455 | 0.8 | 5 | 10.8 | 19.3838 | 3.9008 | 4.6829 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 2456 | 0.4 | 10 | 12.8571 | 22.0013 | 2.7442 | 6.4 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 2457 | 1 | 4 | 11.25 | 16.5863 | 2.5934 | 2.7429 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 2458 | 1.2 | 3.3333 | 13.5 | 21.2112 | 3.3475 | 4.3636 | 1 | 5 | 0.2 | 10 | 18.3333
| 2459 | 0.6 | 6.6667 | 10 | 16.1727 | 2.6818 | 3.4909 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 2460 | 1.2 | 3.3333 | 20 | 29.3714 | 3.3714 | 6 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 2461 | 0.2 | 20 | 14.5946 | 24.6356 | 3.4203 | 6.6207 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 2462 | 1.6 | 2.5 | 15.4286 | 21.65 | 2.7929 | 3.4286 | 0.4 | 12.5 | 0.4 | 5 | 20
| 2463 | 0.8 | 5 | 9.8182 | 19.6385 | 3.4203 | 6.4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 2464 | 0.1 | 40 | 12.5581 | 19.0675 | 3.2552 | 3.2542 | 0.8 | 6.25 | 0.6 | 3.3333 | 49.5833
| 2465 | 0.6 | 6.6667 | 9.4737 | 15.5713 | 2.8434 | 3.2542 | 1 | 5 | 0.1 | 20 | 31.6667
| 2466 | 0.4 | 10 | 11.25 | 16.8051 | 2.4583 | 3.0968 | 1 | 5 | 0.2 | 10 | 25
| 2467 | 1 | 4 | 10.8 | 20.3057 | 3.6875 | 5.8182 | 0.4 | 12.5 | 0.2 | 10 | 26.5
| 2468 | 1 | 4 | 7.9412 | 15.7091 | 3.085 | 4.6829 | 1 | 5 | 0.1 | 20 | 29
| 2469 | 0.6 | 6.6667 | 17.4194 | 23.5921 | 2.7442 | 3.4286 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 2470 | 1.8 | 2.2222 | 10.8 | 20.4641 | 3.4706 | 6.1935 | 0.6 | 8.3333 | 0.4 | 5 | 15.5556
| 2471 | 0.8 | 5 | 12 | 18.3343 | 2.8434 | 3.4909 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 2472 | 0.8 | 5 | 9.6429 | 15.9613 | 2.95 | 3.3684 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 2473 | 1 | 4 | 12.2727 | 19.1916 | 4.2523 | 2.6667 | 1 | 5 | 0.8 | 2.5 | 11.5
| 2474 | 1.2 | 3.3333 | 11.4894 | 19.8887 | 2.9136 | 5.4857 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 2475 | 1 | 4 | 22.5 | 29.1343 | 3.3239 | 3.3103 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 2476 | 0.6 | 6.6667 | 9 | 15.4513 | 2.8957 | 3.5556 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 2477 | 0.4 | 10 | 15.8824 | 22.8327 | 2.7765 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 2478 | 0.6 | 6.6667 | 10.8 | 17.3742 | 2.8095 | 3.7647 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 2479 | 0.4 | 10 | 14.2105 | 19.9657 | 2.9317 | 2.8235 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 2480 | 1.6 | 2.5 | 12 | 21.0256 | 3.0256 | 6 | 1.2 | 4.1667 | 0.2 | 10 | 16.6667
| 2481 | 0.4 | 10 | 15.4286 | 21.5129 | 2.5934 | 3.4909 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 2482 | 1 | 4 | 11.0204 | 18.3991 | 2.9136 | 4.4651 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 2483 | 0.8 | 5 | 12 | 18.0806 | 2.8263 | 3.2542 | 1 | 5 | 0.8 | 2.5 | 12.5
| 2484 | 1.2 | 3.3333 | 10.1887 | 17.5696 | 2.8095 | 4.5714 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 2485 | 0.4 | 10 | 16.3636 | 24.4188 | 3.2552 | 4.8 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 2486 | 1.2 | 3.3333 | 12.8571 | 21.0364 | 3.4963 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 2487 | 0.8 | 5 | 11.4894 | 17.7497 | 2.95 | 3.3103 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 2488 | 0.4 | 10 | 13.8462 | 22.3027 | 2.8095 | 5.6471 | 1 | 5 | 0.2 | 10 | 25
| 2489 | 0.8 | 5 | 13.5 | 19.9322 | 2.8095 | 3.6226 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 2490 | 0.8 | 5 | 14.5946 | 24.2409 | 3.0256 | 6.6207 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 2491 | 0.6 | 6.6667 | 13.8462 | 21.377 | 2.6077 | 4.9231 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 2492 | 0.8 | 5 | 13.1707 | 20.8351 | 3.3007 | 4.3636 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 2493 | 0.4 | 10 | 13.5 | 20.6076 | 3.1892 | 3.9184 | 1.2 | 4.1667 | 0.1 | 20 | 34.1667
| 2494 | 1.2 | 3.3333 | 9.6429 | 16.2578 | 2.3483 | 4.2667 | 1 | 5 | 0.2 | 10 | 18.3333
| 2495 | 0.4 | 10 | 7.5 | 15.3409 | 2.6517 | 5.1892 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 2496 | 0.8 | 5 | 11.0204 | 18.7184 | 3.2329 | 4.4651 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 2497 | 0.4 | 10 | 12.5581 | 18.3141 | 2.4456 | 3.3103 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 2498 | 1.4 | 2.8571 | 12 | 20.8 | 4 | 4.8 | 1.4 | 3.5714 | 0.4 | 5 | 11.4286
| 2499 | 0.2 | 20 | 15.8824 | 25.4466 | 3.746 | 5.8182 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 2500 | 1.4 | 2.8571 | 13.5 | 23.248 | 2.6369 | 7.1111 | 0.6 | 8.3333 | 0.4 | 5 | 16.1905
| 2501 | 1 | 4 | 15 | 21.8877 | 2.5241 | 4.3636 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 2502 | 1 | 4 | 12.8571 | 19.0662 | 3.2552 | 2.9538 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 2503 | 0.8 | 5 | 12 | 19.4995 | 3.2329 | 4.2667 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 2504 | 1.2 | 3.3333 | 15.8824 | 25.429 | 3.1467 | 6.4 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 2505 | 0.4 | 10 | 10 | 21.7681 | 3.4203 | 8.3478 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 2506 | 1.4 | 2.8571 | 16.875 | 23.5178 | 2.878 | 3.7647 | 1.6 | 3.125 | 0.6 | 3.3333 | 9.3155
| 2507 | 0.6 | 6.6667 | 16.3636 | 22.5739 | 2.4456 | 3.7647 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 2508 | 0.2 | 20 | 12.5581 | 18.2597 | 2.878 | 2.8235 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 2509 | 0.4 | 10 | 10.5882 | 17.8136 | 2.7602 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 2510 | 0.8 | 5 | 11.25 | 17.7495 | 3.1892 | 3.3103 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 2511 | 0.6 | 6.6667 | 10.1887 | 20.6382 | 3.0649 | 7.3846 | 1 | 5 | 0.2 | 10 | 21.6667
| 2512 | 1.2 | 3.3333 | 13.1707 | 19.6142 | 3.1892 | 3.2542 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 2513 | 0.1 | 40 | 9.4737 | 16.3728 | 3.4706 | 3.4286 | 0.8 | 6.25 | 0.4 | 5 | 51.25
| 2514 | 0.6 | 6.6667 | 15.4286 | 24.8159 | 2.9873 | 6.4 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 2515 | 0.4 | 10 | 15.4286 | 27.8215 | 2.7929 | 9.6 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 2516 | 0.6 | 6.6667 | 11.25 | 18.395 | 3.5224 | 3.6226 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 2517 | 1.2 | 3.3333 | 21.6 | 27.9989 | 2.8434 | 3.5556 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 2518 | 1 | 4 | 12.2727 | 20.7914 | 2.3251 | 6.1935 | 0.2 | 25 | 0.6 | 3.3333 | 32.3333
| 2519 | 1 | 4 | 13.1707 | 20.2732 | 2.3024 | 4.8 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 2520 | 1.2 | 3.3333 | 13.1707 | 22.6213 | 2.5934 | 6.8571 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 2521 | 0.6 | 6.6667 | 13.1707 | 19.8986 | 3.1053 | 3.6226 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 2522 | 1.4 | 2.8571 | 12 | 18.4433 | 3.3957 | 3.0476 | 0.4 | 12.5 | 0.2 | 10 | 25.3571
| 2523 | 1 | 4 | 10.5882 | 17.2285 | 2.1751 | 4.4651 | 1 | 5 | 0.4 | 5 | 14
| 2524 | 0.6 | 6.6667 | 10.8 | 17.3362 | 2.9136 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 2525 | 1.2 | 3.3333 | 12.8571 | 21.2971 | 2.7929 | 5.6471 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 2526 | 0.6 | 6.6667 | 13.1707 | 20.499 | 3.8374 | 3.4909 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 2527 | 1.6 | 2.5 | 9.6429 | 18.4366 | 3.1467 | 5.6471 | 0.6 | 8.3333 | 0.4 | 5 | 15.8333
| 2528 | 1 | 4 | 15.8824 | 25.2002 | 2.6971 | 6.6207 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 2529 | 1.2 | 3.3333 | 15.4286 | 22.2985 | 3.1053 | 3.7647 | 1 | 5 | 0.4 | 5 | 13.3333
| 2530 | 0.4 | 10 | 18.6207 | 24.5721 | 2.6971 | 3.2542 | 1 | 5 | 0.4 | 5 | 20
| 2531 | 0.6 | 6.6667 | 14.2105 | 21.4486 | 2.6667 | 4.5714 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 2532 | 0.8 | 5 | 12 | 22.0875 | 3.6875 | 6.4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 2533 | 0.6 | 6.6667 | 10.3846 | 18.5279 | 2.3251 | 5.8182 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 2534 | 0.6 | 6.6667 | 16.875 | 23.4532 | 3.3239 | 3.2542 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 2535 | 1 | 4 | 15 | 23.2855 | 3.2329 | 5.0526 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 2536 | 1.4 | 2.8571 | 7.7143 | 14.6901 | 3.4203 | 3.5556 | 0.8 | 6.25 | 0.1 | 20 | 29.1071
| 2537 | 0.4 | 10 | 30 | 36.3595 | 3.1053 | 3.2542 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 2538 | 0.8 | 5 | 12.2727 | 18.4202 | 3.3239 | 2.8235 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 2539 | 0.8 | 5 | 12.2727 | 19.6815 | 3.0452 | 4.3636 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 2540 | 0.8 | 5 | 18.6207 | 26.5057 | 3.085 | 4.8 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 2541 | 1 | 4 | 12.8571 | 18.0365 | 2.3137 | 2.8657 | 1 | 5 | 0.4 | 5 | 14
| 2542 | 1 | 4 | 15 | 23.2009 | 3.2778 | 4.9231 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 2543 | 0.6 | 6.6667 | 11.7391 | 20.1934 | 2.9686 | 5.4857 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 2544 | 1 | 4 | 15.4286 | 26.036 | 3.4963 | 7.1111 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 2545 | 1 | 4 | 14.2105 | 22.3497 | 2.95 | 5.1892 | 1 | 5 | 0.1 | 20 | 29
| 2546 | 0.6 | 6.6667 | 16.875 | 25.4765 | 3.5489 | 5.0526 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 2547 | 1.2 | 3.3333 | 9.4737 | 16.0932 | 2.4456 | 4.1739 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 2548 | 0.2 | 20 | 13.1707 | 21.1511 | 3.8065 | 4.1739 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 2549 | 0.4 | 10 | 13.1707 | 23.785 | 4.2143 | 6.4 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 2550 | 0.8 | 5 | 11.4894 | 17.2948 | 3.2109 | 2.5946 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 2551 | 1.2 | 3.3333 | 18 | 26.7126 | 2.7126 | 6 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 2552 | 1 | 4 | 12.5581 | 20.7366 | 3.1258 | 5.0526 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 2553 | 0.8 | 5 | 10.1887 | 17.8782 | 2.6369 | 5.0526 | 1 | 5 | 0.8 | 2.5 | 12.5
| 2554 | 0.8 | 5 | 10.3846 | 17.8828 | 2.4456 | 5.0526 | 1.4 | 3.5714 | 0.1 | 20 | 28.5714
| 2555 | 1.6 | 2.5 | 11.0204 | 19.4205 | 3.2109 | 5.1892 | 0.6 | 8.3333 | 0.2 | 10 | 20.8333
| 2556 | 1 | 4 | 10.5882 | 17.272 | 3.2552 | 3.4286 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 2557 | 0.8 | 5 | 10.1887 | 16.1499 | 2.9136 | 3.0476 | 1 | 5 | 0.4 | 5 | 15
| 2558 | 0.2 | 20 | 12.8571 | 19.0445 | 2.9873 | 3.2 | 1 | 5 | 0.2 | 10 | 35
| 2559 | 0.8 | 5 | 15.8824 | 22.4517 | 2.4842 | 4.0851 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 2560 | 0.8 | 5 | 9.3103 | 15.6998 | 2.6971 | 3.6923 | 1 | 5 | 0.4 | 5 | 15
| 2561 | 1 | 4 | 17.4194 | 26.3707 | 2.5514 | 6.4 | 0.4 | 12.5 | 0.2 | 10 | 26.5
| 2562 | 1 | 4 | 11.4894 | 18.532 | 4.177 | 2.8657 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 2563 | 0.8 | 5 | 11.4894 | 18.047 | 2.7929 | 3.7647 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 2564 | 1.2 | 3.3333 | 13.5 | 20.5452 | 3.0452 | 4 | 1.6 | 3.125 | 0.8 | 2.5 | 8.9583
| 2565 | 1.2 | 3.3333 | 16.3636 | 26.3083 | 3.3239 | 6.6207 | 1 | 5 | 0.4 | 5 | 13.3333
| 2566 | 0.8 | 5 | 15 | 21.0049 | 3.3007 | 2.7042 | 1 | 5 | 0.4 | 5 | 15
| 2567 | 0.2 | 20 | 14.2105 | 22.1124 | 2.7126 | 5.1892 | 0.6 | 8.3333 | 0.2 | 10 | 38.3333
| 2568 | 0.4 | 10 | 16.875 | 22.7341 | 2.95 | 2.9091 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 2569 | 0.8 | 5 | 10 | 17.581 | 2.2476 | 5.3333 | 1 | 5 | 0.4 | 5 | 15
| 2570 | 1 | 4 | 15.8824 | 21.9629 | 2.8263 | 3.2542 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 2571 | 1.4 | 2.8571 | 13.5 | 22.3602 | 2.6667 | 6.1935 | 1.4 | 3.5714 | 0.1 | 20 | 26.4286
| 2572 | 0.8 | 5 | 12.2727 | 19.4785 | 3.8374 | 3.3684 | 1 | 5 | 0.4 | 5 | 15
| 2573 | 0.8 | 5 | 13.1707 | 18.1385 | 2.1852 | 2.7826 | 1 | 5 | 0.2 | 10 | 20
| 2574 | 1.4 | 2.8571 | 10.5882 | 17.9269 | 3.4203 | 3.9184 | 0.4 | 12.5 | 0.2 | 10 | 25.3571
| 2575 | 0.6 | 6.6667 | 12.5581 | 21.0381 | 3.1467 | 5.3333 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 2576 | 0.4 | 10 | 12.8571 | 18.1828 | 2.3719 | 2.9538 | 0.6 | 8.3333 | 0.1 | 20 | 38.3333
| 2577 | 1 | 4 | 12.8571 | 21.9416 | 5.2444 | 3.84 | 1 | 5 | 0.2 | 10 | 19
| 2578 | 0.6 | 6.6667 | 11.25 | 19.9901 | 3.6875 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 2579 | 0.8 | 5 | 10.5882 | 16.0214 | 2.5241 | 2.9091 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 2580 | 0.4 | 10 | 11.25 | 17.374 | 2.2056 | 3.9184 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 2581 | 1.2 | 3.3333 | 14.2105 | 21.3691 | 3.6031 | 3.5556 | 1.2 | 4.1667 | 0.1 | 20 | 27.5
| 2582 | 1 | 4 | 12.8571 | 20.1302 | 3.0064 | 4.2667 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 2583 | 0.8 | 5 | 8.8525 | 19.9538 | 1.9585 | 9.1429 | 1 | 5 | 0.1 | 20 | 30
| 2584 | 0.2 | 20 | 19.2857 | 26.4308 | 3.7165 | 3.4286 | 1 | 5 | 0.2 | 10 | 35
| 2585 | 0.4 | 10 | 13.8462 | 20.2706 | 3.4706 | 2.9538 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 2586 | 0.6 | 6.6667 | 12.8571 | 19.7271 | 3.1053 | 3.7647 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 2587 | 1 | 4 | 16.875 | 27.021 | 3.746 | 6.4 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 2588 | 0.6 | 6.6667 | 11.0204 | 18.4675 | 2.5241 | 4.9231 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 2589 | 0.6 | 6.6667 | 12 | 20.7922 | 3.6031 | 5.1892 | 0.4 | 12.5 | 0.2 | 10 | 29.1667
| 2590 | 0.6 | 6.6667 | 12.8571 | 21.5689 | 4.1404 | 4.5714 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 2591 | 0.8 | 5 | 12 | 18.8243 | 3.3957 | 3.4286 | 1 | 5 | 0.2 | 10 | 20
| 2592 | 0.6 | 6.6667 | 12.5581 | 18.8779 | 2.6971 | 3.6226 | 1 | 5 | 0.1 | 20 | 31.6667
| 2593 | 0.6 | 6.6667 | 19.2857 | 26.3592 | 4.2909 | 2.7826 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 2594 | 0.4 | 10 | 10.8 | 16.8999 | 3.3957 | 2.7042 | 1 | 5 | 0.2 | 10 | 25
| 2595 | 0.8 | 5 | 12.8571 | 22.2445 | 2.9873 | 6.4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 2596 | 0.8 | 5 | 13.8462 | 23.4679 | 2.5106 | 7.1111 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 2597 | 0.8 | 5 | 11.25 | 17.9613 | 2.7929 | 3.9184 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 2598 | 1 | 4 | 10 | 18.5077 | 2.8606 | 5.6471 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 2599 | 0.4 | 10 | 12.5581 | 21.373 | 3.1678 | 5.6471 | 1 | 5 | 0.4 | 5 | 20
| 2600 | 0.8 | 5 | 11.0204 | 16.7617 | 3.1467 | 2.5946 | 1 | 5 | 0.4 | 5 | 15
| 2601 | 0.4 | 10 | 9.6429 | 18.898 | 3.2552 | 6 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 2602 | 1 | 4 | 11.7391 | 17.8858 | 2.5241 | 3.6226 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 2603 | 0.6 | 6.6667 | 10 | 17.8721 | 3.1892 | 4.6829 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 2604 | 1.2 | 3.3333 | 12 | 25.7653 | 2.4712 | 11.2941 | 1 | 5 | 0.4 | 5 | 13.3333
| 2605 | 1.2 | 3.3333 | 14.5946 | 19.9826 | 2.2913 | 3.0968 | 1.2 | 4.1667 | 0.1 | 20 | 27.5
| 2606 | 0.8 | 5 | 10.1887 | 20.3254 | 3.0256 | 7.1111 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 2607 | 0.4 | 10 | 11.0204 | 19.6761 | 3.6031 | 5.0526 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 2608 | 0.4 | 10 | 11.4894 | 18.1116 | 2.6222 | 4 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 2609 | 1 | 4 | 8.8525 | 14.8319 | 3.0256 | 2.9538 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 2610 | 0.8 | 5 | 10 | 17.3328 | 2.2802 | 5.0526 | 1 | 5 | 0.1 | 20 | 30
| 2611 | 1 | 4 | 9.1525 | 15.0267 | 2.4456 | 3.4286 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 2612 | 0.8 | 5 | 7.8261 | 16.8446 | 3.3714 | 5.6471 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 2613 | 0.8 | 5 | 11.0204 | 19.6992 | 2.8606 | 5.8182 | 1 | 5 | 0.2 | 10 | 20
| 2614 | 0.8 | 5 | 12.5581 | 20.6844 | 2.7929 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 2615 | 1.2 | 3.3333 | 13.5 | 22.2366 | 2.3366 | 6.4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 2616 | 1.2 | 3.3333 | 11.0204 | 16.7747 | 3.3239 | 2.4304 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 2617 | 1.4 | 2.8571 | 12.5581 | 20.1939 | 2.7126 | 4.9231 | 1 | 5 | 0.4 | 5 | 12.8571
| 2618 | 0.8 | 5 | 13.1707 | 20.4681 | 3.8065 | 3.4909 | 1 | 5 | 0.4 | 5 | 15
| 2619 | 0.4 | 10 | 14.5946 | 24.4822 | 2.7765 | 7.1111 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 2620 | 1 | 4 | 22.5 | 30.8754 | 2.7283 | 5.6471 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 2621 | 1 | 4 | 10.5882 | 19.8535 | 2.4082 | 6.8571 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 2622 | 0.2 | 20 | 10.3846 | 22.828 | 2.8434 | 9.6 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 2623 | 0.6 | 6.6667 | 12.8571 | 18.4463 | 3.1892 | 2.4 | 0.6 | 8.3333 | 0.8 | 2.5 | 17.5
| 2624 | 0.2 | 20 | 9.4737 | 19.4628 | 2.878 | 7.1111 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 2625 | 0.4 | 10 | 12.5581 | 18.5519 | 2.5652 | 3.4286 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 2626 | 1 | 4 | 14.5946 | 21.5129 | 2.6517 | 4.2667 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 2627 | 0.8 | 5 | 8.7097 | 16.9812 | 3.8065 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 2628 | 1 | 4 | 15 | 22.6357 | 2.7126 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 2629 | 0.6 | 6.6667 | 12.5581 | 24.5581 | 4 | 8 | 1 | 5 | 0.2 | 10 | 21.6667
| 2630 | 1 | 4 | 10.1887 | 17.9619 | 2.1261 | 5.6471 | 1 | 5 | 0.4 | 5 | 14
| 2631 | 0.8 | 5 | 16.3636 | 25.5978 | 3.9008 | 5.3333 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 2632 | 0.8 | 5 | 12.2727 | 19.0217 | 3.9664 | 2.7826 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 2633 | 0.4 | 10 | 10.5882 | 17.7818 | 2.5106 | 4.6829 | 1 | 5 | 0.4 | 5 | 20
| 2634 | 1 | 4 | 10.8 | 20.0778 | 3.6308 | 5.6471 | 1 | 5 | 0.4 | 5 | 14
| 2635 | 0.1 | 40 | 18.6207 | 25.2434 | 2.5376 | 4.0851 | 0.6 | 8.3333 | 0.2 | 10 | 58.3333
| 2636 | 1 | 4 | 12 | 20.1376 | 3.085 | 5.0526 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 2637 | 1.4 | 2.8571 | 12 | 17.1738 | 2.5792 | 2.5946 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 2638 | 0.4 | 10 | 13.5 | 19.957 | 3.1467 | 3.3103 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 2639 | 0.6 | 6.6667 | 8.1818 | 14.1189 | 3.2329 | 2.7042 | 1 | 5 | 0.6 | 3.3333 | 15
| 2640 | 0.8 | 5 | 12.8571 | 19.1599 | 3.2552 | 3.0476 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 2641 | 0.6 | 6.6667 | 13.5 | 20.4032 | 3.2109 | 3.6923 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 2642 | 0.4 | 10 | 11.4894 | 18.8325 | 2.878 | 4.4651 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 2643 | 0.2 | 20 | 12.5581 | 19.5838 | 3.0256 | 4 | 0.8 | 6.25 | 0.1 | 20 | 46.25
| 2644 | 0.8 | 5 | 12.8571 | 21.641 | 2.3838 | 6.4 | 1 | 5 | 0.2 | 10 | 20
| 2645 | 0.4 | 10 | 12.5581 | 19.2719 | 4.2523 | 2.4615 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 2646 | 0.6 | 6.6667 | 12.5581 | 23.9784 | 3.4203 | 8 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 2647 | 0.4 | 10 | 10.1887 | 21.3145 | 3.1258 | 8 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 2648 | 0.4 | 10 | 8.4375 | 18.1835 | 3.746 | 6 | 0.6 | 8.3333 | 0.8 | 2.5 | 20.8333
| 2649 | 1.2 | 3.3333 | 10.3846 | 19.6747 | 2.433 | 6.8571 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 2650 | 0.4 | 10 | 8.5714 | 14.626 | 2.7442 | 3.3103 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 2651 | 1 | 4 | 11.7391 | 18.1257 | 2.8957 | 3.4909 | 1 | 5 | 0.4 | 5 | 14
| 2652 | 0.2 | 20 | 12 | 19.2082 | 2.4082 | 4.8 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 2653 | 0.4 | 10 | 14.2105 | 23.387 | 2.7765 | 6.4 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 2654 | 1 | 4 | 12.2727 | 16.9123 | 2.2692 | 2.3704 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 2655 | 0.6 | 6.6667 | 11.25 | 17.399 | 2.5934 | 3.5556 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 2656 | 1.4 | 2.8571 | 12.5581 | 20.8702 | 2.8263 | 5.4857 | 1 | 5 | 0.8 | 2.5 | 10.3571
| 2657 | 0.8 | 5 | 12 | 18.1449 | 2.7765 | 3.3684 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2658 | 1 | 4 | 12.8571 | 21.8085 | 2.5514 | 6.4 | 1 | 5 | 0.4 | 5 | 14
| 2659 | 0.6 | 6.6667 | 12 | 22.3339 | 4.1404 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 15
| 2660 | 1.4 | 2.8571 | 11.7391 | 21.6202 | 3.6875 | 6.1935 | 1.2 | 4.1667 | 0.8 | 2.5 | 9.5238
| 2661 | 0.8 | 5 | 13.8462 | 20.3642 | 2.433 | 4.0851 | 1 | 5 | 0.4 | 5 | 15
| 2662 | 1.4 | 2.8571 | 13.5 | 20.6624 | 2.8957 | 4.2667 | 1 | 5 | 0.2 | 10 | 17.8571
| 2663 | 0.6 | 6.6667 | 8.3077 | 15.2109 | 3.2109 | 3.6923 | 1 | 5 | 0.4 | 5 | 16.6667
| 2664 | 1 | 4 | 18.6207 | 25.2758 | 3.746 | 2.9091 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 2665 | 0.6 | 6.6667 | 18 | 26.3785 | 3.0452 | 5.3333 | 0.4 | 12.5 | 0.2 | 10 | 29.1667
| 2666 | 0.6 | 6.6667 | 10 | 18.2009 | 3.2778 | 4.9231 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 2667 | 1.2 | 3.3333 | 13.5 | 20.685 | 3.4203 | 3.7647 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 2668 | 0.6 | 6.6667 | 14.5946 | 21.048 | 3.085 | 3.3684 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 2669 | 0.4 | 10 | 15 | 24.4104 | 2.0258 | 7.3846 | 1 | 5 | 0.2 | 10 | 25
| 2670 | 0.6 | 6.6667 | 11.4894 | 18.0851 | 2.5106 | 4.0851 | 1 | 5 | 0.4 | 5 | 16.6667
| 2671 | 1 | 4 | 12.5581 | 22.5828 | 2.9136 | 7.1111 | 0.6 | 8.3333 | 0.1 | 20 | 32.3333
| 2672 | 0.6 | 6.6667 | 10.3846 | 17.7222 | 2.5376 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 2673 | 0.6 | 6.6667 | 10.5882 | 18.079 | 3.0256 | 4.4651 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 2674 | 0.1 | 40 | 16.875 | 24.6942 | 3.9008 | 3.9184 | 0.6 | 8.3333 | 0.4 | 5 | 53.3333
| 2675 | 0.4 | 10 | 16.3636 | 29.4189 | 2.95 | 10.1053 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 2676 | 0.8 | 5 | 13.5 | 23.9586 | 3.3475 | 7.1111 | 1 | 5 | 0.2 | 10 | 20
| 2677 | 0.4 | 10 | 13.1707 | 19.1648 | 3.085 | 2.9091 | 1 | 5 | 0.2 | 10 | 25
| 2678 | 1.2 | 3.3333 | 12.2727 | 18.6237 | 2.7283 | 3.6226 | 0.8 | 6.25 | 0.8 | 2.5 | 12.0833
| 2679 | 0.2 | 20 | 11.4894 | 19.0651 | 3.5758 | 4 | 1.6 | 3.125 | 0.6 | 3.3333 | 26.4583
| 2680 | 1.6 | 2.5 | 8.7097 | 18.8545 | 2.7602 | 7.3846 | 1.4 | 3.5714 | 0.8 | 2.5 | 8.5714
| 2681 | 1.2 | 3.3333 | 13.1707 | 20.0577 | 2.9686 | 3.9184 | 1 | 5 | 0.4 | 5 | 13.3333
| 2682 | 0.6 | 6.6667 | 10.5882 | 16.8321 | 3.4203 | 2.8235 | 1 | 5 | 0.2 | 10 | 21.6667
| 2683 | 1 | 4 | 12.8571 | 24.406 | 3.8689 | 7.68 | 1 | 5 | 0.8 | 2.5 | 11.5
| 2684 | 1.2 | 3.3333 | 11.0204 | 19.8443 | 3.9008 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 2685 | 0.6 | 6.6667 | 10 | 18.7139 | 2.8957 | 5.8182 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 2686 | 0.8 | 5 | 13.5 | 19.8161 | 2.5514 | 3.7647 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 2687 | 1.6 | 2.5 | 11.25 | 22.4229 | 2.4456 | 8.7273 | 1 | 5 | 0.8 | 2.5 | 10
| 2688 | 0.8 | 5 | 9.8182 | 18.2851 | 3.2778 | 5.1892 | 1.2 | 4.1667 | 1 | 2 | 11.1667
| 2689 | 0.8 | 5 | 15.4286 | 22.0713 | 2.878 | 3.7647 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 2690 | 1 | 4 | 12 | 18.2019 | 2.5792 | 3.6226 | 1 | 5 | 0.4 | 5 | 14
| 2691 | 1.2 | 3.3333 | 12 | 21.0074 | 3.1892 | 5.8182 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 2692 | 1.2 | 3.3333 | 12.8571 | 20.355 | 3.3239 | 4.1739 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 2693 | 0.4 | 10 | 14.5946 | 23.3062 | 3.5224 | 5.1892 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 2694 | 0.8 | 5 | 14.2105 | 20.5494 | 2.4205 | 3.9184 | 1 | 5 | 0.2 | 10 | 20
| 2695 | 0.6 | 6.6667 | 11.4894 | 23.5279 | 2.8957 | 9.1429 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 2696 | 0.8 | 5 | 12 | 18.054 | 3.0064 | 3.0476 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 2697 | 0.8 | 5 | 12.5581 | 17.9325 | 2.7442 | 2.6301 | 1 | 5 | 0.4 | 5 | 15
| 2698 | 0.8 | 5 | 14.5946 | 21.64 | 2.6818 | 4.3636 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 2699 | 0.8 | 5 | 9.3103 | 15.9729 | 2.7442 | 3.9184 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 2700 | 1 | 4 | 11.25 | 17.3292 | 2.9317 | 3.1475 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 2701 | 1 | 4 | 10.8 | 19.0009 | 3.2778 | 4.9231 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 2702 | 0.6 | 6.6667 | 11.4894 | 21.4723 | 3.1258 | 6.8571 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 2703 | 1 | 4 | 11.7391 | 20.6292 | 3.8374 | 5.0526 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 2704 | 0.4 | 10 | 10.3846 | 16.6844 | 2.7442 | 3.5556 | 0.4 | 12.5 | 0.4 | 5 | 27.5
| 2705 | 1 | 4 | 11.25 | 18.4178 | 3.1678 | 4 | 1 | 5 | 0.2 | 10 | 19
| 2706 | 0.8 | 5 | 12.8571 | 20.7079 | 3.1678 | 4.6829 | 1 | 5 | 0.4 | 5 | 15
| 2707 | 0.4 | 10 | 11.25 | 20.006 | 4.2909 | 4.4651 | 1 | 5 | 0.2 | 10 | 25
| 2708 | 1.2 | 3.3333 | 9.4737 | 16.4973 | 3.1053 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 2709 | 1.2 | 3.3333 | 16.3636 | 23.8851 | 3.3475 | 4.1739 | 0.8 | 6.25 | 0.8 | 2.5 | 12.0833
| 2710 | 0.8 | 5 | 10.3846 | 18.9606 | 3.776 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 2711 | 0.8 | 5 | 12.2727 | 19.0026 | 3.776 | 2.9538 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 2712 | 1.4 | 2.8571 | 15 | 23.0184 | 3.9333 | 4.0851 | 0.6 | 8.3333 | 0.4 | 5 | 16.1905
| 2713 | 1.2 | 3.3333 | 12.8571 | 20.584 | 2.5376 | 5.1892 | 1 | 5 | 0.4 | 5 | 13.3333
| 2714 | 0.6 | 6.6667 | 10.1887 | 17.1588 | 3.3475 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 2715 | 0.6 | 6.6667 | 12.5581 | 19.4638 | 2.9873 | 3.9184 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 2716 | 0.8 | 5 | 12.5581 | 18.2671 | 3.3957 | 2.3133 | 1 | 5 | 0.4 | 5 | 15
| 2717 | 0.8 | 5 | 11.4894 | 17.2453 | 3.1258 | 2.6301 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 2718 | 0.6 | 6.6667 | 15.4286 | 24.2877 | 3.8065 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 2719 | 0.8 | 5 | 9.3103 | 17.2718 | 3.4963 | 4.4651 | 1 | 5 | 0.2 | 10 | 20
| 2720 | 1.2 | 3.3333 | 12 | 17.8855 | 2.9317 | 2.9538 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 2721 | 0.4 | 10 | 12.5581 | 17.9911 | 2.433 | 3 | 0.6 | 8.3333 | 0.1 | 20 | 38.3333
| 2722 | 1.2 | 3.3333 | 8.5714 | 14.8203 | 2.4842 | 3.7647 | 1 | 5 | 0.4 | 5 | 13.3333
| 2723 | 1 | 4 | 11.4894 | 20.7278 | 3.4203 | 5.8182 | 1 | 5 | 0.4 | 5 | 14
| 2724 | 0.6 | 6.6667 | 13.1707 | 19.3825 | 2.8434 | 3.3684 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 2725 | 1 | 4 | 12.2727 | 18.9602 | 3.6875 | 3 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 2726 | 1 | 4 | 13.5 | 23.8618 | 2.6818 | 7.68 | 1 | 5 | 0.4 | 5 | 14
| 2727 | 0.6 | 6.6667 | 13.5 | 20.2966 | 2.433 | 4.3636 | 1 | 5 | 0.4 | 5 | 16.6667
| 2728 | 1.4 | 2.8571 | 9.3103 | 16.7389 | 4 | 3.4286 | 1 | 5 | 0.4 | 5 | 12.8571
| 2729 | 0.6 | 6.6667 | 14.5946 | 21.4552 | 2.8606 | 4 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 2730 | 1.4 | 2.8571 | 11.4894 | 19.1937 | 2.6517 | 5.0526 | 1.8 | 2.7778 | 0.4 | 5 | 10.6349
| 2731 | 0.8 | 5 | 12.2727 | 18.6947 | 3.1678 | 3.2542 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 2732 | 0.6 | 6.6667 | 9.3103 | 15.1922 | 2.6818 | 3.2 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 2733 | 0.2 | 20 | 12.2727 | 17.79 | 2.4205 | 3.0968 | 0.6 | 8.3333 | 0.4 | 5 | 33.3333
| 2734 | 1 | 4 | 9.1525 | 17.6758 | 3.4706 | 5.0526 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 2735 | 0.4 | 10 | 10.8 | 17.639 | 3.1467 | 3.6923 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 2736 | 1 | 4 | 9.4737 | 16.5168 | 2.7765 | 4.2667 | 1.6 | 3.125 | 0.6 | 3.3333 | 10.4583
| 2737 | 0.8 | 5 | 16.3636 | 22.282 | 2 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 2738 | 1 | 4 | 11.4894 | 18.8742 | 3.2109 | 4.1739 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 2739 | 0.2 | 20 | 14.2105 | 29.787 | 2.7765 | 12.8 | 0.6 | 8.3333 | 0.4 | 5 | 33.3333
| 2740 | 0.4 | 10 | 15 | 26.393 | 3.0452 | 8.3478 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 2741 | 1 | 4 | 11.4894 | 17.1111 | 2.7126 | 2.9091 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 2742 | 0.8 | 5 | 10 | 16.7518 | 2.6667 | 4.0851 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 2743 | 1.2 | 3.3333 | 15.8824 | 23.8217 | 3.5758 | 4.3636 | 1 | 5 | 0.2 | 10 | 18.3333
| 2744 | 0.8 | 5 | 10.3846 | 17.4608 | 2.8095 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 2745 | 1.2 | 3.3333 | 12.2727 | 22.6447 | 2.9873 | 7.3846 | 1 | 5 | 0.4 | 5 | 13.3333
| 2746 | 1 | 4 | 10.8 | 17.4167 | 3.1258 | 3.4909 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 2747 | 0.8 | 5 | 12 | 20.5885 | 3.2552 | 5.3333 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 2748 | 0.8 | 5 | 14.5946 | 21.0389 | 3.3475 | 3.0968 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2749 | 0.8 | 5 | 13.5 | 21.788 | 3.7165 | 4.5714 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 2750 | 0.8 | 5 | 13.5 | 21.7512 | 4.4112 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 2751 | 1.4 | 2.8571 | 11.0204 | 18.9648 | 4.1043 | 3.84 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 2752 | 0.8 | 5 | 13.5 | 20.0361 | 3.0452 | 3.4909 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 2753 | 0.8 | 5 | 10.5882 | 19.2166 | 3.5758 | 5.0526 | 1 | 5 | 0.4 | 5 | 15
| 2754 | 1.4 | 2.8571 | 12.2727 | 18.179 | 2.8095 | 3.0968 | 1 | 5 | 0.4 | 5 | 12.8571
| 2755 | 0.8 | 5 | 10.8 | 19.885 | 3.085 | 6 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 2756 | 1.2 | 3.3333 | 16.3636 | 24.2553 | 2.9686 | 4.9231 | 0.6 | 8.3333 | 0.1 | 20 | 31.6667
| 2757 | 1.2 | 3.3333 | 14.2105 | 22.974 | 3.2778 | 5.4857 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 2758 | 1 | 4 | 10.5882 | 15.7062 | 2.7765 | 2.3415 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 2759 | 0.2 | 20 | 12.8571 | 18.9604 | 2.7929 | 3.3103 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 2760 | 0.8 | 5 | 13.8462 | 19.6606 | 2.8606 | 2.9538 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 2761 | 1 | 4 | 13.1707 | 22.3277 | 4.1043 | 5.0526 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 2762 | 1 | 4 | 11.7391 | 18.2243 | 2.7929 | 3.6923 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.8333
| 2763 | 0.8 | 5 | 12 | 21.4987 | 2.878 | 6.6207 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 2764 | 1 | 4 | 10.5882 | 23.1844 | 3.8689 | 8.7273 | 1 | 5 | 0.4 | 5 | 14
| 2765 | 0.8 | 5 | 10.3846 | 17.429 | 2.5792 | 4.4651 | 0.4 | 12.5 | 0.2 | 10 | 27.5
| 2766 | 0.2 | 20 | 15.4286 | 26.1735 | 3.0649 | 7.68 | 1.2 | 4.1667 | 0.1 | 20 | 44.1667
| 2767 | 0.8 | 5 | 12 | 20.5792 | 2.5792 | 6 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 2768 | 0.6 | 6.6667 | 8.8525 | 17.1549 | 2.3024 | 6 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 2769 | 0.1 | 40 | 9.1525 | 16.5373 | 3.2109 | 4.1739 | 1 | 5 | 0.8 | 2.5 | 47.5
| 2770 | 0.6 | 6.6667 | 13.8462 | 21.7447 | 2.5652 | 5.3333 | 1 | 5 | 0.4 | 5 | 16.6667
| 2771 | 0.4 | 10 | 10.1887 | 16.8474 | 3.1678 | 3.4909 | 0.4 | 12.5 | 0.8 | 2.5 | 25
| 2772 | 1.4 | 2.8571 | 8.8525 | 15.2684 | 2.9873 | 3.4286 | 1.6 | 3.125 | 0.2 | 10 | 15.9821
| 2773 | 1.4 | 2.8571 | 11.4894 | 19.0597 | 3.1053 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 2774 | 0.8 | 5 | 11.7391 | 19.7321 | 4.3704 | 3.6226 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 2775 | 1.4 | 2.8571 | 11.0204 | 20.6422 | 2.5106 | 7.1111 | 1.2 | 4.1667 | 0.8 | 2.5 | 9.5238
| 2776 | 0.8 | 5 | 13.8462 | 21.5051 | 3.6589 | 4 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 2777 | 1.8 | 2.2222 | 10.5882 | 17.9491 | 2.8957 | 4.4651 | 0.8 | 6.25 | 0.2 | 10 | 18.4722
| 2778 | 0.8 | 5 | 23.4783 | 29.1901 | 3.0452 | 2.6667 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 2779 | 0.4 | 10 | 11.7391 | 25.451 | 3.0452 | 10.6667 | 0.4 | 12.5 | 0.8 | 2.5 | 25
| 2780 | 1.2 | 3.3333 | 11.4894 | 20.1865 | 2.6971 | 6 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 2781 | 0.8 | 5 | 12.5581 | 19.9728 | 3.4963 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2782 | 1 | 4 | 13.8462 | 22.8335 | 2.9873 | 6 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 2783 | 1.2 | 3.3333 | 11.7391 | 19.5434 | 3.2329 | 4.5714 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.1667
| 2784 | 0.4 | 10 | 9.6429 | 19.232 | 3.1892 | 6.4 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 2785 | 1 | 4 | 14.2105 | 19.1318 | 2.0978 | 2.8235 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 2786 | 0.8 | 5 | 7.8261 | 13.5232 | 2.6971 | 3 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 2787 | 0.6 | 6.6667 | 9.6429 | 16.7742 | 3.5758 | 3.5556 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 2788 | 1 | 4 | 12 | 19.8608 | 3.3957 | 4.4651 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 2789 | 0.8 | 5 | 18 | 24.6192 | 3.5224 | 3.0968 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 2790 | 1 | 4 | 11.0204 | 18.72 | 2.7765 | 4.9231 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 2791 | 0.8 | 5 | 18.6207 | 26.0297 | 3.3239 | 4.0851 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 2792 | 1.6 | 2.5 | 14.5946 | 25.4855 | 3.2109 | 7.68 | 0.8 | 6.25 | 0.4 | 5 | 13.75
| 2793 | 1.4 | 2.8571 | 12.8571 | 20.169 | 3.0452 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 2794 | 1 | 4 | 12.8571 | 19.5197 | 2.7442 | 3.9184 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 2795 | 1.2 | 3.3333 | 10.8 | 16.822 | 2.5934 | 3.4286 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 2796 | 0.8 | 5 | 13.5 | 21.4199 | 3.746 | 4.1739 | 1.6 | 3.125 | 0.2 | 10 | 18.125
| 2797 | 1 | 4 | 10.1887 | 17.1518 | 2.878 | 4.0851 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 2798 | 0.4 | 10 | 10.3846 | 24.3907 | 3.9008 | 10.1053 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 2799 | 1.2 | 3.3333 | 13.1707 | 21.6719 | 3.1678 | 5.3333 | 1 | 5 | 0.4 | 5 | 13.3333
| 2800 | 0.8 | 5 | 12 | 19.0537 | 2.9686 | 4.0851 | 1 | 5 | 0.4 | 5 | 15
| 2801 | 1 | 4 | 13.5 | 21.8489 | 3.5489 | 4.8 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 2802 | 0.2 | 20 | 11.4894 | 18.8848 | 3.6308 | 3.7647 | 0.6 | 8.3333 | 0.2 | 10 | 38.3333
| 2803 | 1 | 4 | 13.5 | 21.7204 | 3.1678 | 5.0526 | 1 | 5 | 0.4 | 5 | 14
| 2804 | 0.8 | 5 | 14.2105 | 23.2998 | 2.8957 | 6.1935 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2805 | 0.6 | 6.6667 | 11.4894 | 19.5685 | 2.5934 | 5.4857 | 1 | 5 | 0.6 | 3.3333 | 15
| 2806 | 0.4 | 10 | 12.5581 | 18.5074 | 2.4583 | 3.4909 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 2807 | 1.2 | 3.3333 | 11.7391 | 20.3736 | 3.4453 | 5.1892 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 2808 | 0.6 | 6.6667 | 10.5882 | 16.763 | 3.4706 | 2.7042 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 2809 | 0.8 | 5 | 10.8 | 19.0204 | 3.1678 | 5.0526 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 2810 | 0.6 | 6.6667 | 13.1707 | 24.271 | 3.4203 | 7.68 | 1 | 5 | 0.6 | 3.3333 | 15
| 2811 | 0.6 | 6.6667 | 9 | 15.5912 | 2.9686 | 3.6226 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 2812 | 0.4 | 10 | 13.8462 | 21.8124 | 2.9136 | 5.0526 | 1.6 | 3.125 | 0.6 | 3.3333 | 16.4583
| 2813 | 0.4 | 10 | 9.4737 | 16.6243 | 2.5792 | 4.5714 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 2814 | 1 | 4 | 15.4286 | 21.4435 | 2.5241 | 3.4909 | 1 | 5 | 1 | 2 | 11
| 2815 | 0.6 | 6.6667 | 9.3103 | 15.6599 | 3.3957 | 2.9538 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 2816 | 0.6 | 6.6667 | 14.5946 | 22.6872 | 2.4456 | 5.6471 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 2817 | 0.1 | 40 | 12.5581 | 21.239 | 3.3475 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 49.1667
| 2818 | 0.8 | 5 | 12 | 19.9051 | 4.1404 | 3.7647 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 2819 | 1.2 | 3.3333 | 12.5581 | 21.9391 | 2.7602 | 6.6207 | 1.8 | 2.7778 | 0.2 | 10 | 16.1111
| 2820 | 1.4 | 2.8571 | 11.25 | 19.136 | 3.5224 | 4.3636 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 2821 | 0.6 | 6.6667 | 14.2105 | 20.5512 | 3.746 | 2.5946 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 2822 | 1.4 | 2.8571 | 12.8571 | 19.334 | 2.6369 | 3.84 | 0.6 | 8.3333 | 0.6 | 3.3333 | 14.5238
| 2823 | 0.8 | 5 | 12.5581 | 23.1319 | 3.1892 | 7.3846 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 2824 | 0.4 | 10 | 12.2727 | 20.4472 | 3.6031 | 4.5714 | 1 | 5 | 0.2 | 10 | 25
| 2825 | 1.2 | 3.3333 | 11.25 | 20.5285 | 3.085 | 6.1935 | 1 | 5 | 0.4 | 5 | 13.3333
| 2826 | 1.4 | 2.8571 | 14.5946 | 21.1856 | 2.8263 | 3.7647 | 0.8 | 6.25 | 0.1 | 20 | 29.1071
| 2827 | 0.8 | 5 | 12.8571 | 21.5494 | 3.0452 | 5.6471 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 2828 | 1 | 4 | 11.25 | 16.243 | 2.433 | 2.56 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 2829 | 0.8 | 5 | 12 | 20.2833 | 2.95 | 5.3333 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 2830 | 0.8 | 5 | 10.3846 | 23.1305 | 3.6031 | 9.1429 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 2831 | 0.6 | 6.6667 | 13.5 | 21.1643 | 3.3007 | 4.3636 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 2832 | 0.4 | 10 | 10.8 | 20.5424 | 3.5489 | 6.1935 | 1 | 5 | 0.4 | 5 | 20
| 2833 | 0.8 | 5 | 17.4194 | 26.8646 | 3.4453 | 6 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 2834 | 1 | 4 | 12 | 18.9013 | 2.5376 | 4.3636 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 2835 | 1.6 | 2.5 | 12 | 17.633 | 2.433 | 3.2 | 0.8 | 6.25 | 0.2 | 10 | 18.75
| 2836 | 1.4 | 2.8571 | 12.5581 | 20.788 | 2.7442 | 5.4857 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 2837 | 0.6 | 6.6667 | 11.4894 | 18.2511 | 2.8434 | 3.9184 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 2838 | 0.6 | 6.6667 | 11.7391 | 19.2221 | 4.8163 | 2.6667 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 2839 | 1 | 4 | 11.0204 | 16.9168 | 2.9873 | 2.9091 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 2840 | 0.6 | 6.6667 | 12.2727 | 17.9743 | 2.878 | 2.8235 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 2841 | 0.2 | 20 | 9.8182 | 15.9721 | 3.0064 | 3.1475 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 2842 | 1.4 | 2.8571 | 9.8182 | 18.6815 | 3.0452 | 5.8182 | 1 | 5 | 0.4 | 5 | 12.8571
| 2843 | 0.2 | 20 | 10.5882 | 17.7506 | 2.8957 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 2844 | 0.6 | 6.6667 | 12 | 21.4638 | 4.4112 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 2845 | 0.8 | 5 | 12.2727 | 17.6946 | 2.3251 | 3.0968 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 2846 | 1.2 | 3.3333 | 13.1707 | 21.6437 | 3.4203 | 5.0526 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.1667
| 2847 | 0.4 | 10 | 13.8462 | 19.738 | 2.2692 | 3.6226 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 2848 | 0.8 | 5 | 9.4737 | 17.4654 | 3.4203 | 4.5714 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 2849 | 0.6 | 6.6667 | 14.5946 | 23.227 | 3.1467 | 5.4857 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 2850 | 0.2 | 20 | 10 | 17.2354 | 4.4528 | 2.7826 | 0.6 | 8.3333 | 0.2 | 10 | 38.3333
| 2851 | 1.6 | 2.5 | 14.5946 | 20.2987 | 3.4453 | 2.2588 | 0.6 | 8.3333 | 0.4 | 5 | 15.8333
| 2852 | 1 | 4 | 8.7097 | 15.2248 | 3.1467 | 3.3684 | 1 | 5 | 0.2 | 10 | 19
| 2853 | 1.6 | 2.5 | 9.8182 | 17.8879 | 3.1467 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 10.8333
| 2854 | 1.2 | 3.3333 | 12 | 21.7 | 4.2143 | 5.4857 | 1.2 | 4.1667 | 0.1 | 20 | 27.5
| 2855 | 0.6 | 6.6667 | 12.5581 | 21.8775 | 3.1258 | 6.1935 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 2856 | 1.2 | 3.3333 | 9.1525 | 15.9061 | 2.9136 | 3.84 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 2857 | 0.4 | 10 | 13.1707 | 19.6471 | 2.3024 | 4.1739 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 2858 | 0.6 | 6.6667 | 15 | 22.4672 | 3.5489 | 3.9184 | 1 | 5 | 0.2 | 10 | 21.6667
| 2859 | 1 | 4 | 11.0204 | 20.0125 | 4.069 | 4.9231 | 1 | 5 | 0.4 | 5 | 14
| 2860 | 0.6 | 6.6667 | 10.3846 | 18.3944 | 2.5241 | 5.4857 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 2861 | 0.2 | 20 | 12 | 21.0941 | 4.4112 | 4.6829 | 1.4 | 3.5714 | 0.1 | 20 | 43.5714
| 2862 | 0.8 | 5 | 11.0204 | 19.3989 | 4.5385 | 3.84 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 2863 | 0.6 | 6.6667 | 18 | 25.8576 | 2.3719 | 5.4857 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 2864 | 0.6 | 6.6667 | 10.5882 | 17.8805 | 3.0256 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 2865 | 0.6 | 6.6667 | 12.5581 | 18.6014 | 2.8957 | 3.1475 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 2866 | 0.8 | 5 | 12 | 19.0028 | 2.5376 | 4.4651 | 1 | 5 | 0.4 | 5 | 15
| 2867 | 0.6 | 6.6667 | 11.4894 | 18.319 | 3.0649 | 3.7647 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 2868 | 0.8 | 5 | 10.5882 | 19.2691 | 3.3475 | 5.3333 | 1 | 5 | 0.2 | 10 | 20
| 2869 | 1 | 4 | 11.0204 | 17.8885 | 2.1852 | 4.6829 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 2870 | 0.8 | 5 | 9.1525 | 21.8306 | 4.3303 | 8.3478 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 2871 | 0.4 | 10 | 17.4194 | 23.2684 | 3.8065 | 2.0426 | 1 | 5 | 0.2 | 10 | 25
| 2872 | 0.4 | 10 | 11.4894 | 18.6964 | 2.8434 | 4.3636 | 0.4 | 12.5 | 0.4 | 5 | 27.5
| 2873 | 0.6 | 6.6667 | 13.8462 | 20.7172 | 2.6971 | 4.1739 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 2874 | 1.2 | 3.3333 | 8.8525 | 15.2106 | 2.5934 | 3.7647 | 0.4 | 12.5 | 0.4 | 5 | 20.8333
| 2875 | 0.4 | 10 | 10.3846 | 20.3226 | 4.2909 | 5.6471 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 2876 | 1.2 | 3.3333 | 11.0204 | 26.6133 | 2.7929 | 12.8 | 1.2 | 4.1667 | 0.1 | 20 | 27.5
| 2877 | 0.6 | 6.6667 | 11.7391 | 19.4619 | 3.5489 | 4.1739 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 2878 | 0.4 | 10 | 16.875 | 22.4588 | 2.3838 | 3.2 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 2879 | 0.8 | 5 | 9.8182 | 17.4854 | 2.7442 | 4.9231 | 1 | 5 | 0.2 | 10 | 20
| 2880 | 0.6 | 6.6667 | 13.1707 | 19.8017 | 2.7126 | 3.9184 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 2881 | 0.8 | 5 | 14.5946 | 21.2027 | 2.8434 | 3.7647 | 1 | 5 | 0.2 | 10 | 20
| 2882 | 0.6 | 6.6667 | 9.3103 | 15.8579 | 3.3475 | 3.2 | 1 | 5 | 0.1 | 20 | 31.6667
| 2883 | 0.6 | 6.6667 | 10.1887 | 18.2376 | 3.1258 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 15
| 2884 | 0.6 | 6.6667 | 9.3103 | 18.1026 | 3.6031 | 5.1892 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 2885 | 1 | 4 | 10.8 | 18.4774 | 3.8374 | 3.84 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 2886 | 1.2 | 3.3333 | 11.25 | 17.609 | 2.6667 | 3.6923 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 2887 | 0.2 | 20 | 9.8182 | 17.6803 | 2.8095 | 5.0526 | 0.6 | 8.3333 | 0.2 | 10 | 38.3333
| 2888 | 1 | 4 | 12.5581 | 20.5371 | 4.2143 | 3.7647 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 2889 | 0.2 | 20 | 12.8571 | 18.6056 | 2.6517 | 3.0968 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 2890 | 1.2 | 3.3333 | 18.6207 | 25.8009 | 2.9136 | 4.2667 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 2891 | 0.8 | 5 | 11.0204 | 18.576 | 4 | 3.5556 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 2892 | 0.8 | 5 | 13.1707 | 21.4357 | 2.9317 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2893 | 1.4 | 2.8571 | 12.8571 | 21.2765 | 3.4963 | 4.9231 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 2894 | 0.8 | 5 | 11.4894 | 21.3652 | 3.2552 | 6.6207 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 2895 | 0.4 | 10 | 10.8 | 19.1912 | 2.7442 | 5.6471 | 1 | 5 | 0.4 | 5 | 20
| 2896 | 0.6 | 6.6667 | 16.875 | 25.0864 | 2.878 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 2897 | 0.6 | 6.6667 | 10.5882 | 18.3541 | 3.3007 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 2898 | 1.4 | 2.8571 | 9.1525 | 15.0745 | 3.3957 | 2.5263 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 2899 | 0.2 | 20 | 9.1525 | 16.7416 | 3.9664 | 3.6226 | 0.6 | 8.3333 | 0.1 | 20 | 48.3333
| 2900 | 1 | 4 | 9.4737 | 17.9537 | 3.1467 | 5.3333 | 1 | 5 | 0.4 | 5 | 14
| 2901 | 0.6 | 6.6667 | 11.25 | 20.5875 | 2.2264 | 7.1111 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 2902 | 0.4 | 10 | 9.8182 | 19.1515 | 2.7126 | 6.6207 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 2903 | 1 | 4 | 13.8462 | 20.3702 | 2.5241 | 4 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 2904 | 1.6 | 2.5 | 12.5581 | 20.2254 | 2.7442 | 4.9231 | 0.6 | 8.3333 | 0.2 | 10 | 20.8333
| 2905 | 1.4 | 2.8571 | 12.8571 | 19.4805 | 3.5758 | 3.0476 | 1.4 | 3.5714 | 0.8 | 2.5 | 8.9286
| 2906 | 1 | 4 | 11.4894 | 20.3674 | 2.878 | 6 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 2907 | 1.2 | 3.3333 | 9.8182 | 19.1657 | 3.3475 | 6 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 2908 | 1.2 | 3.3333 | 11.25 | 17.2768 | 2.4712 | 3.5556 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 2909 | 0.4 | 10 | 10 | 16.0517 | 3.3475 | 2.7042 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 2910 | 1 | 4 | 13.8462 | 20.3645 | 2.8957 | 3.6226 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 2911 | 0.6 | 6.6667 | 11.0204 | 19.8795 | 3.8065 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 2912 | 0.6 | 6.6667 | 19.2857 | 27.7051 | 3.4963 | 4.9231 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 2913 | 0.6 | 6.6667 | 9.6429 | 16.8388 | 2.3959 | 4.8 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 2914 | 1 | 4 | 15.4286 | 24.4959 | 3.4203 | 5.6471 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 2915 | 0.6 | 6.6667 | 12.8571 | 19.8012 | 3.0256 | 3.9184 | 1 | 5 | 0.2 | 10 | 21.6667
| 2916 | 0.8 | 5 | 10 | 17.1715 | 3.5489 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 2917 | 0.4 | 10 | 10 | 16.5401 | 3.7165 | 2.8235 | 1 | 5 | 0.8 | 2.5 | 17.5
| 2918 | 0.8 | 5 | 11.7391 | 17.7931 | 3.0064 | 3.0476 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 2919 | 1 | 4 | 11.7391 | 19.0827 | 2.4205 | 4.9231 | 1 | 5 | 0.4 | 5 | 14
| 2920 | 0.2 | 20 | 13.5 | 22.0442 | 3.2109 | 5.3333 | 1.4 | 3.5714 | 0.2 | 10 | 33.5714
| 2921 | 0.6 | 6.6667 | 13.5 | 21.4859 | 3.9008 | 4.0851 | 1.6 | 3.125 | 0.1 | 20 | 29.7917
| 2922 | 0.6 | 6.6667 | 9.4737 | 17.1951 | 1.9032 | 5.8182 | 1 | 5 | 0.4 | 5 | 16.6667
| 2923 | 1.4 | 2.8571 | 9.8182 | 17.6524 | 3.4706 | 4.3636 | 0.4 | 12.5 | 0.2 | 10 | 25.3571
| 2924 | 1.2 | 3.3333 | 15.4286 | 22.7126 | 2.7126 | 4.5714 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.1667
| 2925 | 1 | 4 | 12.8571 | 22.9815 | 5.5529 | 4.5714 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 2926 | 0.4 | 10 | 11.4894 | 24.1053 | 2.5106 | 10.1053 | 1 | 5 | 0.2 | 10 | 25
| 2927 | 1.2 | 3.3333 | 10.8 | 22.1007 | 3.3007 | 8 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 2928 | 0.4 | 10 | 20.7692 | 29.3354 | 3.2329 | 5.3333 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 2929 | 1 | 4 | 21.6 | 31.7578 | 3.3007 | 6.8571 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 2930 | 1 | 4 | 15 | 23.5406 | 4.177 | 4.3636 | 0.4 | 12.5 | 0.2 | 10 | 26.5
| 2931 | 0.2 | 20 | 10.5882 | 19.631 | 3.3957 | 5.6471 | 1.8 | 2.7778 | 0.2 | 10 | 32.7778
| 2932 | 1 | 4 | 14.2105 | 25.6737 | 6.1299 | 5.3333 | 1 | 5 | 0.2 | 10 | 19
| 2933 | 0.8 | 5 | 9.4737 | 17.6818 | 4.0342 | 4.1739 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 2934 | 1.2 | 3.3333 | 13.1707 | 23.0771 | 2.2264 | 7.68 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 2935 | 0.6 | 6.6667 | 11.7391 | 17.094 | 2.7602 | 2.5946 | 1 | 5 | 0.4 | 5 | 16.6667
| 2936 | 0.8 | 5 | 11.4894 | 19.0191 | 3.8374 | 3.6923 | 1 | 5 | 0.4 | 5 | 15
| 2937 | 0.8 | 5 | 16.875 | 23.4476 | 2.95 | 3.6226 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 2938 | 0.8 | 5 | 13.8462 | 19.777 | 3.3007 | 2.6301 | 1 | 5 | 0.4 | 5 | 15
| 2939 | 1 | 4 | 12.2727 | 21.1622 | 3.9664 | 4.9231 | 1.4 | 3.5714 | 0.1 | 20 | 27.5714
| 2940 | 1 | 4 | 10 | 17.885 | 3.085 | 4.8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 2941 | 0.4 | 10 | 8.4375 | 15.2197 | 2.6971 | 4.0851 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 2942 | 1 | 4 | 13.8462 | 23.5051 | 3.6589 | 6 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 2943 | 0.8 | 5 | 8.5714 | 16.5071 | 3.4706 | 4.4651 | 1 | 5 | 0.4 | 5 | 15
| 2944 | 1 | 4 | 12.5581 | 20.4535 | 3.3239 | 4.5714 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 2945 | 1 | 4 | 10 | 16.3602 | 2.9317 | 3.4286 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 2946 | 0.8 | 5 | 11.4894 | 20.3248 | 4.3704 | 4.4651 | 1 | 5 | 0.4 | 5 | 15
| 2947 | 0.4 | 10 | 9.4737 | 15.7536 | 3.0256 | 3.2542 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 2948 | 1 | 4 | 12.8571 | 21.7478 | 2.6971 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 2949 | 0.6 | 6.6667 | 18 | 26.4444 | 3.2552 | 5.1892 | 1 | 5 | 0.6 | 3.3333 | 15
| 2950 | 0.6 | 6.6667 | 9.4737 | 15.917 | 3.3957 | 3.0476 | 1 | 5 | 0.6 | 3.3333 | 15
| 2951 | 0.4 | 10 | 14.2105 | 21.3481 | 3.4453 | 3.6923 | 1.8 | 2.7778 | 0.2 | 10 | 22.7778
| 2952 | 1.2 | 3.3333 | 9.8182 | 17.2131 | 3.9664 | 3.4286 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 2953 | 1 | 4 | 10.5882 | 18.3705 | 3.2109 | 4.5714 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 2954 | 1.2 | 3.3333 | 9.8182 | 18.0769 | 3.5758 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 2955 | 0.2 | 20 | 9.1525 | 17.5766 | 3.3714 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 2956 | 0.6 | 6.6667 | 10.8 | 19.3838 | 3.9008 | 4.6829 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 2957 | 0.8 | 5 | 11.7391 | 22.0737 | 2.95 | 7.3846 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 2958 | 1 | 4 | 12.8571 | 19.9435 | 3.776 | 3.3103 | 1 | 5 | 0.8 | 2.5 | 11.5
| 2959 | 0.8 | 5 | 11.25 | 16.3342 | 2.1751 | 2.9091 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 2960 | 0.4 | 10 | 11.25 | 19.5206 | 3.3475 | 4.9231 | 1 | 5 | 0.4 | 5 | 20
| 2961 | 1 | 4 | 12.8571 | 21.2105 | 3.3007 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 2962 | 0.8 | 5 | 15.8824 | 24.4538 | 4 | 4.5714 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 2963 | 0.6 | 6.6667 | 12.2727 | 21.106 | 3.3475 | 5.4857 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 2964 | 0.2 | 20 | 10.1887 | 16.2358 | 2.7929 | 3.2542 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 2965 | 1 | 4 | 12.2727 | 18.5505 | 3.2778 | 3 | 1 | 5 | 0.4 | 5 | 14
| 2966 | 0.8 | 5 | 12 | 20.4628 | 2.2692 | 6.1935 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 2967 | 1.6 | 2.5 | 10.8 | 18.181 | 2.8095 | 4.5714 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.0833
| 2968 | 0.4 | 10 | 15.8824 | 24.8472 | 3.1467 | 5.8182 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 2969 | 1.2 | 3.3333 | 10.8 | 16.7084 | 3.1258 | 2.7826 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 2970 | 1 | 4 | 20.7692 | 32.5417 | 3.0452 | 8.7273 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 2971 | 1 | 4 | 10 | 19.2901 | 2.433 | 6.8571 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 2972 | 0.8 | 5 | 9.4737 | 15.5294 | 3.1467 | 2.9091 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 2973 | 1.2 | 3.3333 | 9.8182 | 17.1818 | 3.4453 | 3.9184 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 2974 | 0.2 | 20 | 14.5946 | 21.9152 | 3.1467 | 4.1739 | 1 | 5 | 0.8 | 2.5 | 27.5
| 2975 | 1 | 4 | 11.4894 | 19.106 | 3.0452 | 4.5714 | 1 | 5 | 0.4 | 5 | 14
| 2976 | 0.8 | 5 | 11.25 | 17.2169 | 2.7126 | 3.2542 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 2977 | 0.8 | 5 | 10.5882 | 18.2353 | 2.3137 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2978 | 0.6 | 6.6667 | 14.5946 | 26.8633 | 3.1258 | 9.1429 | 1 | 5 | 0.2 | 10 | 21.6667
| 2979 | 0.4 | 10 | 12 | 19.6364 | 3.0649 | 4.5714 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 2980 | 0.6 | 6.6667 | 19.2857 | 26.8076 | 3.2552 | 4.2667 | 1 | 5 | 0.4 | 5 | 16.6667
| 2981 | 1 | 4 | 11.4894 | 18.5348 | 2.6818 | 4.3636 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 2982 | 1 | 4 | 14.5946 | 22.0617 | 2.8957 | 4.5714 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 2983 | 1.2 | 3.3333 | 10.1887 | 21.6702 | 4.3704 | 7.1111 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 2984 | 0.4 | 10 | 10.5882 | 17.196 | 2.6077 | 4 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 2985 | 0.4 | 10 | 18 | 26.156 | 3.2329 | 4.9231 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 2986 | 0.8 | 5 | 10 | 16.8815 | 3.1892 | 3.6923 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 2987 | 1.4 | 2.8571 | 12 | 19.4594 | 2.7765 | 4.6829 | 1.4 | 3.5714 | 0.6 | 3.3333 | 9.7619
| 2988 | 0.8 | 5 | 15.8824 | 23.1587 | 2.5934 | 4.6829 | 1 | 5 | 0.4 | 5 | 15
| 2989 | 0.2 | 20 | 10.3846 | 16.622 | 3.8374 | 2.4 | 1.8 | 2.7778 | 0.6 | 3.3333 | 26.1111
| 2990 | 0.4 | 10 | 12.8571 | 19.7172 | 3.1678 | 3.6923 | 1.2 | 4.1667 | 0.1 | 20 | 34.1667
| 2991 | 1.2 | 3.3333 | 12.8571 | 20.0952 | 2.6667 | 4.5714 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 2992 | 0.6 | 6.6667 | 10.8 | 16.2115 | 2.95 | 2.4615 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 2993 | 1.4 | 2.8571 | 10.1887 | 16.2683 | 2.5241 | 3.5556 | 1 | 5 | 0.1 | 20 | 27.8571
| 2994 | 0.6 | 6.6667 | 9.8182 | 17.5341 | 3.6308 | 4.0851 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 2995 | 0.8 | 5 | 11.25 | 20.1557 | 3.7165 | 5.1892 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 2996 | 0.8 | 5 | 9.8182 | 16.63 | 3.1892 | 3.6226 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 2997 | 1 | 4 | 13.5 | 22.06 | 4.72 | 3.84 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 2998 | 1 | 4 | 14.5946 | 20.9747 | 3.1258 | 3.2542 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 2999 | 0.6 | 6.6667 | 10.8 | 18.4734 | 2.4842 | 5.1892 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 3000 | 1 | 4 | 10.1887 | 16.5602 | 3.3239 | 3.0476 | 1 | 5 | 0.4 | 5 | 14
| 3001 | 0.8 | 5 | 18.6207 | 25.7922 | 3.5489 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 3002 | 1.4 | 2.8571 | 11.4894 | 18.2604 | 3.0064 | 3.7647 | 1.6 | 3.125 | 0.2 | 10 | 15.9821
| 3003 | 0.4 | 10 | 11.4894 | 21.2671 | 2.6667 | 7.1111 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 3004 | 0.2 | 20 | 10.1887 | 20.0332 | 2.9873 | 6.8571 | 1.4 | 3.5714 | 0.1 | 20 | 43.5714
| 3005 | 0.4 | 10 | 18.6207 | 31.1544 | 3.8065 | 8.7273 | 1.2 | 4.1667 | 0.1 | 20 | 34.1667
| 3006 | 0.4 | 10 | 14.5946 | 20.4639 | 2.3137 | 3.5556 | 1 | 5 | 0.4 | 5 | 20
| 3007 | 0.6 | 6.6667 | 12.2727 | 19.482 | 2.7442 | 4.4651 | 1.6 | 3.125 | 0.2 | 10 | 19.7917
| 3008 | 1.4 | 2.8571 | 11.0204 | 18.1769 | 2.7929 | 4.3636 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 3009 | 1 | 4 | 7.9412 | 14.8156 | 2.6077 | 4.2667 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 3010 | 0.8 | 5 | 9.3103 | 16.7792 | 3.1053 | 4.3636 | 1 | 5 | 0.8 | 2.5 | 12.5
| 3011 | 0.6 | 6.6667 | 9.1525 | 15.5278 | 3.0649 | 3.3103 | 1 | 5 | 0.2 | 10 | 21.6667
| 3012 | 1.6 | 2.5 | 11.7391 | 19.208 | 3.1053 | 4.3636 | 1.2 | 4.1667 | 0.2 | 10 | 16.6667
| 3013 | 0.4 | 10 | 7.9412 | 16.1864 | 3.4453 | 4.8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 3014 | 0.8 | 5 | 9.6429 | 18.0517 | 3.8374 | 4.5714 | 1.4 | 3.5714 | 0.8 | 2.5 | 11.0714
| 3015 | 1 | 4 | 13.5 | 20.4233 | 3.3007 | 3.6226 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 3016 | 0.8 | 5 | 17.4194 | 24.0783 | 3.6589 | 3 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 3017 | 0.4 | 10 | 10.5882 | 18.9346 | 2.8606 | 5.4857 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 3018 | 0.6 | 6.6667 | 11.0204 | 17.9566 | 3.4453 | 3.4909 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 3019 | 0.6 | 6.6667 | 14.5946 | 22.0432 | 3.085 | 4.3636 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 3020 | 0.8 | 5 | 7.6056 | 13.9248 | 3.0649 | 3.2542 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 3021 | 0.6 | 6.6667 | 12.8571 | 18.6357 | 2.6818 | 3.0968 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 3022 | 1 | 4 | 17.4194 | 24.9358 | 2.5934 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 3023 | 0.6 | 6.6667 | 15.8824 | 21.543 | 2.878 | 2.7826 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 3024 | 1 | 4 | 10.1887 | 17.9068 | 3.1467 | 4.5714 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 3025 | 0.8 | 5 | 10.5882 | 17.2192 | 2.7126 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 3026 | 0.6 | 6.6667 | 13.5 | 19.9832 | 2.8606 | 3.6226 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 3027 | 0.4 | 10 | 12 | 18.4622 | 2.6222 | 3.84 | 1 | 5 | 0.2 | 10 | 25
| 3028 | 0.8 | 5 | 14.5946 | 21.7444 | 3.6589 | 3.4909 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 3029 | 0.4 | 10 | 8.3077 | 17.6904 | 3.1892 | 6.1935 | 1 | 5 | 0.4 | 5 | 20
| 3030 | 0.6 | 6.6667 | 13.1707 | 20.0265 | 2.6818 | 4.1739 | 1 | 5 | 0.2 | 10 | 21.6667
| 3031 | 0.6 | 6.6667 | 12.5581 | 22.0524 | 3.3007 | 6.1935 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 3032 | 0.4 | 10 | 11.25 | 19.3351 | 4 | 4.0851 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 3033 | 0.6 | 6.6667 | 10.5882 | 17.8594 | 2.4712 | 4.8 | 1 | 5 | 0.1 | 20 | 31.6667
| 3034 | 1 | 4 | 10 | 17.5557 | 3.4706 | 4.0851 | 1 | 5 | 0.4 | 5 | 14
| 3035 | 1.2 | 3.3333 | 14.2105 | 24.2618 | 2.6667 | 7.3846 | 1.4 | 3.5714 | 0.8 | 2.5 | 9.4048
| 3036 | 0.8 | 5 | 12 | 20.8097 | 3.3239 | 5.4857 | 1 | 5 | 0.2 | 10 | 20
| 3037 | 0.8 | 5 | 11.4894 | 17.8451 | 2.9873 | 3.3684 | 1 | 5 | 0.4 | 5 | 15
| 3038 | 0.8 | 5 | 10.5882 | 18.2862 | 3.2329 | 4.4651 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 3039 | 0.6 | 6.6667 | 11.0204 | 19.6931 | 3.0256 | 5.6471 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 3040 | 1.2 | 3.3333 | 13.8462 | 19.808 | 2.5934 | 3.3684 | 1 | 5 | 0.2 | 10 | 18.3333
| 3041 | 0.6 | 6.6667 | 11.25 | 16.5657 | 3.3957 | 1.92 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 3042 | 0.8 | 5 | 9 | 15.2941 | 3.4706 | 2.8235 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 3043 | 0.2 | 20 | 11.7391 | 20.5549 | 2.6222 | 6.1935 | 1.2 | 4.1667 | 0.6 | 3.3333 | 27.5
| 3044 | 0.6 | 6.6667 | 12.5581 | 23.0815 | 2.8434 | 7.68 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 3045 | 0.8 | 5 | 19.2857 | 24.8303 | 2.95 | 2.5946 | 0.8 | 6.25 | 1 | 2 | 13.25
| 3046 | 0.2 | 20 | 11.0204 | 17.3043 | 2.7283 | 3.5556 | 1 | 5 | 0.4 | 5 | 30
| 3047 | 0.4 | 10 | 10.3846 | 17.2803 | 2.8957 | 4 | 1 | 5 | 0.2 | 10 | 25
| 3048 | 0.6 | 6.6667 | 20 | 26.1617 | 3.0649 | 3.0968 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 3049 | 0.4 | 10 | 10.1887 | 17.4508 | 2.5792 | 4.6829 | 1.6 | 3.125 | 0.4 | 5 | 18.125
| 3050 | 0.6 | 6.6667 | 13.5 | 22.6707 | 3.8374 | 5.3333 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 3051 | 1.2 | 3.3333 | 14.5946 | 22.8289 | 3.0452 | 5.1892 | 0.4 | 12.5 | 0.1 | 20 | 35.8333
| 3052 | 1.2 | 3.3333 | 13.5 | 20.4493 | 2.4842 | 4.4651 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 3053 | 1.4 | 2.8571 | 12.5581 | 19.1432 | 2.6667 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 3054 | 1.2 | 3.3333 | 18.6207 | 26.5501 | 3.0064 | 4.9231 | 0.4 | 12.5 | 0.2 | 10 | 25.8333
| 3055 | 0.2 | 20 | 11.0204 | 19.466 | 2.4456 | 6 | 1 | 5 | 0.4 | 5 | 30
| 3056 | 0.6 | 6.6667 | 10 | 18.732 | 3.085 | 5.6471 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 3057 | 0.6 | 6.6667 | 10.5882 | 16.6164 | 3.3239 | 2.7042 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 3058 | 1.4 | 2.8571 | 15.8824 | 26.7999 | 3.8065 | 7.1111 | 1 | 5 | 0.4 | 5 | 12.8571
| 3059 | 1.4 | 2.8571 | 13.1707 | 21.084 | 2.8606 | 5.0526 | 1 | 5 | 0.4 | 5 | 12.8571
| 3060 | 0.6 | 6.6667 | 13.1707 | 19.962 | 3.8374 | 2.9538 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 3061 | 0.8 | 5 | 9.3103 | 15.6828 | 2.6077 | 3.7647 | 1 | 5 | 0.1 | 20 | 30
| 3062 | 0.6 | 6.6667 | 14.5946 | 22.3106 | 2.7929 | 4.9231 | 1 | 5 | 0.4 | 5 | 16.6667
| 3063 | 1.8 | 2.2222 | 10.3846 | 17.8535 | 3.1053 | 4.3636 | 1 | 5 | 0.4 | 5 | 12.2222
| 3064 | 0.6 | 6.6667 | 12 | 19.0455 | 2.6818 | 4.3636 | 1 | 5 | 0.2 | 10 | 21.6667
| 3065 | 0.8 | 5 | 11.0204 | 17.5763 | 3.0649 | 3.4909 | 1 | 5 | 0.4 | 5 | 15
| 3066 | 0.4 | 10 | 12.5581 | 18.9787 | 2.4205 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 3067 | 0.4 | 10 | 11.0204 | 20.3092 | 3.4706 | 5.8182 | 1 | 5 | 0.4 | 5 | 20
| 3068 | 1 | 4 | 13.5 | 20.2617 | 2.8434 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 3069 | 0.2 | 20 | 10.5882 | 17.4626 | 2.6077 | 4.2667 | 0.6 | 8.3333 | 0.6 | 3.3333 | 31.6667
| 3070 | 0.6 | 6.6667 | 9.4737 | 14.5707 | 2.6667 | 2.4304 | 1 | 5 | 0.2 | 10 | 21.6667
| 3071 | 1 | 4 | 10 | 17.0444 | 2.5792 | 4.4651 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 3072 | 0.4 | 10 | 13.1707 | 23.473 | 2.6222 | 7.68 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 3073 | 0.4 | 10 | 12.5581 | 18.6485 | 3.3475 | 2.7429 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 3074 | 0.4 | 10 | 10.5882 | 17.399 | 3.2552 | 3.5556 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 3075 | 0.6 | 6.6667 | 11.4894 | 21.0749 | 4.2523 | 5.3333 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 3076 | 1.6 | 2.5 | 12.5581 | 18.6781 | 2.4974 | 3.6226 | 1.4 | 3.5714 | 0.8 | 2.5 | 8.5714
| 3077 | 0.6 | 6.6667 | 15.4286 | 22.4481 | 2.3366 | 4.6829 | 1 | 5 | 0.2 | 10 | 21.6667
| 3078 | 0.6 | 6.6667 | 12.2727 | 18.6021 | 3.4203 | 2.9091 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 3079 | 0.8 | 5 | 11.7391 | 20.0988 | 2.7126 | 5.6471 | 1 | 5 | 0.8 | 2.5 | 12.5
| 3080 | 1 | 4 | 11.25 | 19.0589 | 3.4453 | 4.3636 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 3081 | 1.2 | 3.3333 | 9 | 22.8182 | 2.5241 | 11.2941 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 3082 | 0.8 | 5 | 12.2727 | 19.4128 | 2.7765 | 4.3636 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 3083 | 0.8 | 5 | 15 | 23.357 | 3.1678 | 5.1892 | 1.4 | 3.5714 | 0.1 | 20 | 28.5714
| 3084 | 0.8 | 5 | 11.4894 | 22.8369 | 3.3475 | 8 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 3085 | 0.8 | 5 | 10 | 22.5961 | 3.8689 | 8.7273 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 3086 | 0.6 | 6.6667 | 8.5714 | 17.8148 | 2.8434 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 3087 | 0.8 | 5 | 13.5 | 20.415 | 2.5514 | 4.3636 | 1 | 5 | 0.4 | 5 | 15
| 3088 | 0.2 | 20 | 9.4737 | 18.2828 | 5.9 | 2.9091 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 3089 | 1 | 4 | 11.4894 | 18.578 | 3.3239 | 3.7647 | 1 | 5 | 0.8 | 2.5 | 11.5
| 3090 | 1 | 4 | 12.8571 | 20.2639 | 3.2329 | 4.1739 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 3091 | 0.6 | 6.6667 | 10.5882 | 18.3568 | 2.9686 | 4.8 | 1 | 5 | 0.4 | 5 | 16.6667
| 3092 | 1.6 | 2.5 | 9.1525 | 14.7174 | 2.8606 | 2.7042 | 0.8 | 6.25 | 0.2 | 10 | 18.75
| 3093 | 0.4 | 10 | 11.0204 | 18.0191 | 2.9136 | 4.0851 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 3094 | 1 | 4 | 11.7391 | 19.3466 | 3.5224 | 4.0851 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 3095 | 0.4 | 10 | 9.1525 | 16.3509 | 3.5758 | 3.6226 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 3096 | 1 | 4 | 10.8 | 18.7607 | 3.2778 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 3097 | 0.8 | 5 | 12.8571 | 21.6132 | 4.2909 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 3098 | 1.2 | 3.3333 | 10.5882 | 18.0034 | 2.95 | 4.4651 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 3099 | 1.2 | 3.3333 | 10.8 | 17.795 | 2.7283 | 4.2667 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 3100 | 0.8 | 5 | 15.4286 | 21.1158 | 2.433 | 3.2542 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 3101 | 0.8 | 5 | 9.4737 | 15.7895 | 2.7602 | 3.5556 | 1.8 | 2.7778 | 0.4 | 5 | 12.7778
| 3102 | 1.2 | 3.3333 | 9.6429 | 17.4035 | 3.1892 | 4.5714 | 1 | 5 | 0.1 | 20 | 28.3333
| 3103 | 1.2 | 3.3333 | 12.8571 | 20.7282 | 2.6818 | 5.1892 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 3104 | 1 | 4 | 7.8261 | 15.7176 | 3.8065 | 4.0851 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 3105 | 0.8 | 5 | 11.4894 | 19.1082 | 3.2552 | 4.3636 | 1.4 | 3.5714 | 0.8 | 2.5 | 11.0714
| 3106 | 0.8 | 5 | 11.25 | 17.452 | 3.1053 | 3.0968 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 3107 | 1 | 4 | 13.8462 | 22.9311 | 3.085 | 6 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 3108 | 1.4 | 2.8571 | 9.3103 | 14.7503 | 2.6971 | 2.7429 | 1 | 5 | 0.1 | 20 | 27.8571
| 3109 | 0.6 | 6.6667 | 11.7391 | 26.1591 | 3.1258 | 11.2941 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 3110 | 1 | 4 | 15.4286 | 25.4714 | 2.9317 | 7.1111 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 3111 | 0.1 | 40 | 9.8182 | 19.822 | 3.1467 | 6.8571 | 1.2 | 4.1667 | 0.6 | 3.3333 | 47.5
| 3112 | 0.6 | 6.6667 | 13.5 | 22.5274 | 4.1043 | 4.9231 | 1 | 5 | 0.4 | 5 | 16.6667
| 3113 | 0.6 | 6.6667 | 12 | 20.3188 | 3.3957 | 4.9231 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 3114 | 0.6 | 6.6667 | 15 | 22.8611 | 3.776 | 4.0851 | 1 | 5 | 0.2 | 10 | 21.6667
| 3115 | 1 | 4 | 11.25 | 18.0997 | 3.085 | 3.7647 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 3116 | 0.6 | 6.6667 | 13.8462 | 21.9388 | 2.4456 | 5.6471 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 3117 | 0.2 | 20 | 12.5581 | 23.3 | 3.6308 | 7.1111 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 3118 | 1.2 | 3.3333 | 15 | 22.698 | 3.2329 | 4.4651 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 3119 | 0.4 | 10 | 16.875 | 25.825 | 2.95 | 6 | 1.6 | 3.125 | 0.6 | 3.3333 | 16.4583
| 3120 | 0.4 | 10 | 12 | 18.2734 | 3.1258 | 3.1475 | 1 | 5 | 0.8 | 2.5 | 17.5
| 3121 | 0.8 | 5 | 9.1525 | 17.7866 | 3.3007 | 5.3333 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 3122 | 0.6 | 6.6667 | 12 | 18.8 | 3.3714 | 3.4286 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 3123 | 1 | 4 | 14.5946 | 21.7846 | 2.8263 | 4.3636 | 1 | 5 | 0.2 | 10 | 19
| 3124 | 0.8 | 5 | 11.0204 | 18.9906 | 2.6369 | 5.3333 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 3125 | 0.2 | 20 | 8.3077 | 17.1683 | 2.8606 | 6 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 3126 | 0.6 | 6.6667 | 9 | 17.5165 | 3.7165 | 4.8 | 1 | 5 | 0.2 | 10 | 21.6667
| 3127 | 0.6 | 6.6667 | 17.4194 | 24.9629 | 2.8606 | 4.6829 | 1 | 5 | 0.1 | 20 | 31.6667
| 3128 | 1.2 | 3.3333 | 10.1887 | 18.5546 | 3.9008 | 4.4651 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 3129 | 0.4 | 10 | 11.7391 | 17.9464 | 2.6517 | 3.5556 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 3130 | 1 | 4 | 9.8182 | 16.303 | 3.5758 | 2.9091 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 3131 | 1.2 | 3.3333 | 15 | 24.5892 | 3.1892 | 6.4 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 3132 | 0.6 | 6.6667 | 10.5882 | 17.1885 | 2.7602 | 3.84 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 3133 | 0.4 | 10 | 9.8182 | 17.7846 | 3.9664 | 4 | 0.6 | 8.3333 | 0.1 | 20 | 38.3333
| 3134 | 0.8 | 5 | 13.5 | 20.7686 | 2.6971 | 4.5714 | 0.8 | 6.25 | 1 | 2 | 13.25
| 3135 | 0.6 | 6.6667 | 9 | 18.2552 | 3.2552 | 6 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 3136 | 0.6 | 6.6667 | 17.4194 | 23.926 | 2.6667 | 3.84 | 1 | 5 | 0.1 | 20 | 31.6667
| 3137 | 0.8 | 5 | 13.5 | 22.1809 | 3.3475 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 3138 | 0.6 | 6.6667 | 14.5946 | 23.3595 | 3.5758 | 5.1892 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 3139 | 1.2 | 3.3333 | 9.6429 | 17.3745 | 2.9317 | 4.8 | 1.6 | 3.125 | 0.4 | 5 | 11.4583
| 3140 | 0.2 | 20 | 15 | 21.8606 | 2.8606 | 4 | 0.8 | 6.25 | 0.2 | 10 | 36.25
| 3141 | 0.8 | 5 | 8.5714 | 16.0817 | 3.0452 | 4.4651 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 3142 | 0.6 | 6.6667 | 10.1887 | 18.7138 | 2.878 | 5.6471 | 1 | 5 | 0.6 | 3.3333 | 15
| 3143 | 1.2 | 3.3333 | 11.7391 | 25.6387 | 3.2329 | 10.6667 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 3144 | 0.8 | 5 | 12.8571 | 21.4628 | 4.0342 | 4.5714 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 3145 | 1.2 | 3.3333 | 9.6429 | 17.4621 | 3.9008 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 3146 | 1.2 | 3.3333 | 15 | 25.6486 | 2.9686 | 7.68 | 1 | 5 | 0.4 | 5 | 13.3333
| 3147 | 0.4 | 10 | 20 | 25.4489 | 2.9873 | 2.4615 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 3148 | 0.6 | 6.6667 | 8.1818 | 17.8147 | 3.2329 | 6.4 | 1 | 5 | 0.4 | 5 | 16.6667
| 3149 | 0.4 | 10 | 11.25 | 19.1632 | 2.8606 | 5.0526 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 3150 | 0.6 | 6.6667 | 10.1887 | 16.7057 | 3.4203 | 3.0968 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 3151 | 0.8 | 5 | 13.1707 | 19.7438 | 3.8689 | 2.7042 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 3152 | 1 | 4 | 10.3846 | 18.7137 | 2.8434 | 5.4857 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 3153 | 0.8 | 5 | 12 | 18.3353 | 2.7126 | 3.6226 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 3154 | 1.6 | 2.5 | 11.0204 | 18.1084 | 3.3957 | 3.6923 | 1.6 | 3.125 | 0.4 | 5 | 10.625
| 3155 | 1 | 4 | 14.2105 | 22.6656 | 2.6369 | 5.8182 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 3156 | 1.8 | 2.2222 | 14.5946 | 21.9052 | 3.4706 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 11.3889
| 3157 | 0.1 | 40 | 10.5882 | 19.6842 | 3.2778 | 5.8182 | 1.4 | 3.5714 | 0.4 | 5 | 48.5714
| 3158 | 0.8 | 5 | 9.4737 | 19.9971 | 2.8434 | 7.68 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 3159 | 0.6 | 6.6667 | 10.8 | 16.4712 | 2.4712 | 3.2 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 3160 | 0.8 | 5 | 8.0597 | 15.3973 | 2.5376 | 4.8 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 3161 | 0.6 | 6.6667 | 12.8571 | 18.872 | 3.4203 | 2.5946 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 3162 | 0.8 | 5 | 10.8 | 18.4749 | 2.6222 | 5.0526 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 3163 | 0.8 | 5 | 8.8525 | 15.7794 | 3.3714 | 3.5556 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 3164 | 1 | 4 | 13.5 | 21.7959 | 4.6733 | 3.6226 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 3165 | 1 | 4 | 15 | 22.1959 | 2.3959 | 4.8 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 3166 | 0.4 | 10 | 14.2105 | 21.4699 | 2.8957 | 4.3636 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 3167 | 0.8 | 5 | 14.5946 | 20.3875 | 2.7929 | 3 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 3168 | 1.2 | 3.3333 | 10.1887 | 18.3671 | 3.1258 | 5.0526 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 3169 | 0.8 | 5 | 14.2105 | 21.9039 | 2.36 | 5.3333 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 3170 | 0.8 | 5 | 14.2105 | 21.2362 | 3.0256 | 4 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 3171 | 1.2 | 3.3333 | 11.7391 | 19.3755 | 3.0649 | 4.5714 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 3172 | 1.2 | 3.3333 | 10 | 16.344 | 2.6517 | 3.6923 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 3173 | 0.6 | 6.6667 | 12.8571 | 19.5355 | 3.6308 | 3.0476 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 3174 | 1 | 4 | 10.1887 | 18.1045 | 3.2329 | 4.6829 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 3175 | 1 | 4 | 10 | 17.6031 | 3.6031 | 4 | 1.6 | 3.125 | 0.1 | 20 | 27.125
| 3176 | 1 | 4 | 10 | 22.1376 | 2.5376 | 9.6 | 1 | 5 | 0.4 | 5 | 14
| 3177 | 0.4 | 10 | 11.0204 | 16.9913 | 2.3483 | 3.6226 | 1 | 5 | 0.2 | 10 | 25
| 3178 | 0.8 | 5 | 24.5455 | 40.8966 | 2.6369 | 13.7143 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 3179 | 0.4 | 10 | 9.3103 | 15.4252 | 2.8606 | 3.2542 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 3180 | 0.6 | 6.6667 | 11.7391 | 19.2137 | 3.3007 | 4.1739 | 1 | 5 | 0.1 | 20 | 31.6667
| 3181 | 0.6 | 6.6667 | 16.875 | 22.7809 | 2.6517 | 3.2542 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 3182 | 0.8 | 5 | 10.1887 | 19.0183 | 3.4963 | 5.3333 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 3183 | 0.4 | 10 | 12.5581 | 18.7949 | 3.1892 | 3.0476 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 3184 | 1 | 4 | 13.8462 | 21.6222 | 3.776 | 4 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 3185 | 0.6 | 6.6667 | 12.5581 | 20.4671 | 4.069 | 3.84 | 1 | 5 | 0.2 | 10 | 21.6667
| 3186 | 0.8 | 5 | 12 | 19.0484 | 3.9008 | 3.1475 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 3187 | 0.8 | 5 | 10.5882 | 18.0219 | 2.9686 | 4.4651 | 1 | 5 | 0.2 | 10 | 20
| 3188 | 1 | 4 | 15 | 20.7299 | 3.0256 | 2.7042 | 1 | 5 | 0.4 | 5 | 14
| 3189 | 0.4 | 10 | 9.3103 | 19.9039 | 2.9136 | 7.68 | 0.4 | 12.5 | 0.2 | 10 | 32.5
| 3190 | 0.4 | 10 | 10.5882 | 17.8298 | 2.7765 | 4.4651 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 3191 | 0.4 | 10 | 14.5946 | 21.9047 | 3.6875 | 3.6226 | 1 | 5 | 0.4 | 5 | 20
| 3192 | 0.4 | 10 | 15.8824 | 24.1026 | 3.4203 | 4.8 | 0.6 | 8.3333 | 0.8 | 2.5 | 20.8333
| 3193 | 0.4 | 10 | 14.2105 | 21.2084 | 3.6875 | 3.3103 | 1 | 5 | 0.2 | 10 | 25
| 3194 | 0.8 | 5 | 8.7097 | 19.5575 | 3.1678 | 7.68 | 1 | 5 | 0.4 | 5 | 15
| 3195 | 0.6 | 6.6667 | 10 | 18.3638 | 2.878 | 5.4857 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 3196 | 0.8 | 5 | 11.25 | 16.9342 | 2.4842 | 3.2 | 1.8 | 2.7778 | 0.6 | 3.3333 | 11.1111
| 3197 | 1.2 | 3.3333 | 12.5581 | 20.2166 | 2.3251 | 5.3333 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 3198 | 0.8 | 5 | 9.4737 | 18.4275 | 2.7602 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 3199 | 0.2 | 20 | 12 | 24.4206 | 3.2778 | 9.1429 | 0.6 | 8.3333 | 0.2 | 10 | 38.3333
| 3200 | 1.4 | 2.8571 | 13.1707 | 23.0914 | 2.8095 | 7.1111 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 3201 | 0.8 | 5 | 15 | 22.1892 | 3.1892 | 4 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 3202 | 1 | 4 | 13.5 | 21.559 | 3.0064 | 5.0526 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 3203 | 0.4 | 10 | 9.4737 | 16.7806 | 2.3838 | 4.9231 | 1 | 5 | 0.2 | 10 | 25
| 3204 | 0.4 | 10 | 13.1707 | 18.8261 | 2.6077 | 3.0476 | 1 | 5 | 0.4 | 5 | 20
| 3205 | 1 | 4 | 11.7391 | 18.0741 | 3.6308 | 2.7042 | 1 | 5 | 0.2 | 10 | 19
| 3206 | 0.8 | 5 | 12.5581 | 20.3669 | 3.1258 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 3207 | 0.8 | 5 | 14.5946 | 21.518 | 2.4583 | 4.4651 | 1 | 5 | 0.2 | 10 | 20
| 3208 | 1.2 | 3.3333 | 15.4286 | 21.2 | 3.3714 | 2.4 | 0.8 | 6.25 | 0.8 | 2.5 | 12.0833
| 3209 | 0.8 | 5 | 20.7692 | 26.9915 | 2.6667 | 3.5556 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 3210 | 0.8 | 5 | 12.8571 | 20.4793 | 2.433 | 5.1892 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 3211 | 0.4 | 10 | 12.8571 | 18.8064 | 2.4583 | 3.4909 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 3212 | 0.8 | 5 | 10.3846 | 18.5443 | 2.8263 | 5.3333 | 0.6 | 8.3333 | 0.1 | 20 | 33.3333
| 3213 | 0.8 | 5 | 8.5714 | 15.7386 | 2.4842 | 4.6829 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 3214 | 0.4 | 10 | 11.25 | 17.0198 | 2.6222 | 3.1475 | 1 | 5 | 0.4 | 5 | 20
| 3215 | 0.8 | 5 | 12.2727 | 20.2691 | 2.5106 | 5.4857 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 3216 | 1 | 4 | 10.5882 | 18.7442 | 3.2329 | 4.9231 | 1 | 5 | 0.4 | 5 | 14
| 3217 | 0.6 | 6.6667 | 12 | 18.2325 | 3.085 | 3.1475 | 1.6 | 3.125 | 0.6 | 3.3333 | 13.125
| 3218 | 0.6 | 6.6667 | 9.6429 | 15.392 | 3.1892 | 2.56 | 0.4 | 12.5 | 0.6 | 3.3333 | 22.5
| 3219 | 0.6 | 6.6667 | 16.3636 | 23.7727 | 3.3239 | 4.0851 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 3220 | 1.4 | 2.8571 | 16.3636 | 24.8945 | 3.0452 | 5.4857 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 3221 | 0.8 | 5 | 15.8824 | 24.1944 | 2.8263 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 3222 | 1 | 4 | 13.1707 | 19.7411 | 2.878 | 3.6923 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 3223 | 1.2 | 3.3333 | 10 | 16.6663 | 2.8263 | 3.84 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 3224 | 1.2 | 3.3333 | 13.8462 | 20.9325 | 3.776 | 3.3103 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 3225 | 1.2 | 3.3333 | 13.1707 | 21.0577 | 5.0213 | 2.8657 | 1 | 5 | 0.4 | 5 | 13.3333
| 3226 | 0.6 | 6.6667 | 16.875 | 25.1372 | 2.7765 | 5.4857 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 3227 | 1 | 4 | 9.6429 | 18.4674 | 3.0064 | 5.8182 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 3228 | 0.6 | 6.6667 | 10 | 19.3714 | 3.3714 | 6 | 0.6 | 8.3333 | 0.1 | 20 | 35
| 3229 | 1 | 4 | 9.6429 | 16.1523 | 3.2552 | 3.2542 | 1 | 5 | 0.2 | 10 | 19
| 3230 | 1.2 | 3.3333 | 11.7391 | 21.1455 | 3.0064 | 6.4 | 1 | 5 | 0.2 | 10 | 18.3333
| 3231 | 0.4 | 10 | 15 | 22.7839 | 3.4203 | 4.3636 | 1 | 5 | 0.4 | 5 | 20
| 3232 | 1 | 4 | 9.8182 | 17.921 | 2.9136 | 5.1892 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 3233 | 0.8 | 5 | 12 | 22.4329 | 3.5758 | 6.8571 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 3234 | 0.8 | 5 | 9.3103 | 16.9647 | 3.1892 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 3235 | 0.8 | 5 | 11.7391 | 18.7703 | 2.3483 | 4.6829 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 3236 | 0.8 | 5 | 13.1707 | 23.073 | 3.0452 | 6.8571 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 3237 | 0.6 | 6.6667 | 14.2105 | 21.0971 | 3.3957 | 3.4909 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 3238 | 1 | 4 | 11.25 | 18.1436 | 3.746 | 3.1475 | 1 | 5 | 1 | 2 | 11
| 3239 | 0.6 | 6.6667 | 14.5946 | 27.6134 | 2.9136 | 10.1053 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 3240 | 1.4 | 2.8571 | 13.8462 | 21.4907 | 3.4706 | 4.1739 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 3241 | 0.4 | 10 | 13.1707 | 20.8664 | 2.8957 | 4.8 | 1.4 | 3.5714 | 0.8 | 2.5 | 16.0714
| 3242 | 0.6 | 6.6667 | 8.7097 | 15.0457 | 3.0256 | 3.3103 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 3243 | 0.8 | 5 | 13.5 | 23.7374 | 3.8374 | 6.4 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 3244 | 0.6 | 6.6667 | 11.25 | 17.5141 | 2.8957 | 3.3684 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 3245 | 0.4 | 10 | 12.8571 | 18.6564 | 2.6517 | 3.1475 | 1 | 5 | 0.4 | 5 | 20
| 3246 | 1 | 4 | 8.5714 | 15.3047 | 2.9686 | 3.7647 | 1.6 | 3.125 | 0.2 | 10 | 17.125
| 3247 | 0.4 | 10 | 12 | 20.1392 | 2.95 | 5.1892 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 3248 | 1.2 | 3.3333 | 9.8182 | 16.4763 | 2.4842 | 4.1739 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 3249 | 1.2 | 3.3333 | 10.3846 | 18.6316 | 3.3239 | 4.9231 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 3250 | 1.2 | 3.3333 | 20.7692 | 31.4545 | 3.3007 | 7.3846 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 3251 | 1 | 4 | 12.2727 | 21.0362 | 3.2778 | 5.4857 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 3252 | 0.8 | 5 | 9.4737 | 17.6502 | 2.9873 | 5.1892 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 3253 | 0.8 | 5 | 11.7391 | 19.1877 | 3.085 | 4.3636 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 3254 | 0.2 | 20 | 13.8462 | 20.7318 | 2.4205 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 3255 | 0.1 | 40 | 8.1818 | 14.9097 | 3.1053 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 49.1667
| 3256 | 1.2 | 3.3333 | 12.8571 | 21.4014 | 3.2109 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 3257 | 0.8 | 5 | 14.2105 | 22.1942 | 3.3007 | 4.6829 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 3258 | 1 | 4 | 11.0204 | 18.2395 | 3.0452 | 4.1739 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 3259 | 1 | 4 | 15.8824 | 22.2959 | 3.0452 | 3.3684 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 3260 | 1 | 4 | 11.4894 | 19.2005 | 3.3475 | 4.3636 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 3261 | 0.2 | 20 | 10 | 16.4009 | 3.1467 | 3.2542 | 0.8 | 6.25 | 0.8 | 2.5 | 28.75
| 3262 | 0.8 | 5 | 15.8824 | 23.9856 | 3.4203 | 4.6829 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 3263 | 0.1 | 40 | 10.5882 | 19.5382 | 2.95 | 6 | 0.8 | 6.25 | 0.4 | 5 | 51.25
| 3264 | 0.4 | 10 | 13.5 | 22.1056 | 4.0342 | 4.5714 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 3265 | 1 | 4 | 16.3636 | 23.1409 | 3.085 | 3.6923 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 3266 | 1 | 4 | 12.5581 | 17.7898 | 2.4082 | 2.8235 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 3267 | 1 | 4 | 15.8824 | 23.4989 | 3.0452 | 4.5714 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 3268 | 0.4 | 10 | 16.875 | 25.2508 | 3.5758 | 4.8 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 3269 | 1 | 4 | 14.5946 | 22.8184 | 3.3007 | 4.9231 | 1.4 | 3.5714 | 0.1 | 20 | 27.5714
| 3270 | 1.2 | 3.3333 | 12 | 20.7042 | 2.5106 | 6.1935 | 1 | 5 | 0.2 | 10 | 18.3333
| 3271 | 0.8 | 5 | 12.8571 | 21.0774 | 3.4203 | 4.8 | 1 | 5 | 0.4 | 5 | 15
| 3272 | 1.2 | 3.3333 | 14.2105 | 21.3955 | 3.4203 | 3.7647 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 3273 | 0.6 | 6.6667 | 14.5946 | 20.6096 | 2.5241 | 3.4909 | 1.6 | 3.125 | 0.4 | 5 | 14.7917
| 3274 | 0.8 | 5 | 9.8182 | 18.2773 | 3.1258 | 5.3333 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 3275 | 1 | 4 | 11.4894 | 18.9411 | 3.2778 | 4.1739 | 1 | 5 | 0.4 | 5 | 14
| 3276 | 0.4 | 10 | 10.5882 | 17.1288 | 2.6222 | 3.9184 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 3277 | 0.4 | 10 | 11.25 | 17.3833 | 2.5106 | 3.6226 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 3278 | 0.6 | 6.6667 | 12 | 19.4808 | 3.3957 | 4.0851 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 3279 | 0.4 | 10 | 11.0204 | 17.5271 | 2.6667 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 3280 | 0.8 | 5 | 20 | 27.3417 | 3.1678 | 4.1739 | 1 | 5 | 0.2 | 10 | 20
| 3281 | 1 | 4 | 15 | 20.8344 | 2.5241 | 3.3103 | 0.6 | 8.3333 | 0.1 | 20 | 32.3333
| 3282 | 0.6 | 6.6667 | 10.8 | 21.0164 | 3.1053 | 7.1111 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 3283 | 0.6 | 6.6667 | 13.1707 | 24.7963 | 3.2778 | 8.3478 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 3284 | 0.2 | 20 | 11.0204 | 20.9167 | 3.4963 | 6.4 | 1.2 | 4.1667 | 0.8 | 2.5 | 26.6667
| 3285 | 0.8 | 5 | 15 | 20.8245 | 2.3959 | 3.4286 | 1 | 5 | 0.4 | 5 | 15
| 3286 | 0.8 | 5 | 8.8525 | 17.3833 | 3.0452 | 5.4857 | 1 | 5 | 0.4 | 5 | 15
| 3287 | 1.2 | 3.3333 | 16.3636 | 22.8632 | 3.1892 | 3.3103 | 1.2 | 4.1667 | 0.1 | 20 | 27.5
| 3288 | 1 | 4 | 14.5946 | 22.1545 | 2.6369 | 4.9231 | 0.2 | 25 | 0.8 | 2.5 | 31.5
| 3289 | 1 | 4 | 12.2727 | 27.5056 | 3.2329 | 12 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 3290 | 0.6 | 6.6667 | 10.3846 | 18.858 | 2.8263 | 5.6471 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 3291 | 1 | 4 | 11.7391 | 19.1594 | 3.4203 | 4 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 3292 | 1 | 4 | 9.3103 | 15.7148 | 2.9136 | 3.4909 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 3293 | 0.8 | 5 | 12.5581 | 18.6806 | 3.0256 | 3.0968 | 1 | 5 | 0.2 | 10 | 20
| 3294 | 1 | 4 | 8.3077 | 14.3057 | 3.2552 | 2.7429 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 3295 | 1.2 | 3.3333 | 13.1707 | 20.8577 | 3.4203 | 4.2667 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 3296 | 1 | 4 | 11.0204 | 19.739 | 3.2329 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 3297 | 0.2 | 20 | 11.25 | 17.9199 | 3.5224 | 3.1475 | 1.2 | 4.1667 | 0.1 | 20 | 44.1667
| 3298 | 0.8 | 5 | 18.6207 | 27.9613 | 3.5224 | 5.8182 | 1.4 | 3.5714 | 0.8 | 2.5 | 11.0714
| 3299 | 1.6 | 2.5 | 10.1887 | 17.6404 | 3.2778 | 4.1739 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10
| 3300 | 0.2 | 20 | 12.2727 | 19.4134 | 3.3007 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 3301 | 0.6 | 6.6667 | 11.0204 | 20.874 | 3.2329 | 6.6207 | 1 | 5 | 0.2 | 10 | 21.6667
| 3302 | 0.8 | 5 | 14.5946 | 24.7121 | 3.0064 | 7.1111 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 3303 | 0.8 | 5 | 13.5 | 19.3911 | 2.6369 | 3.2542 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 3304 | 1.8 | 2.2222 | 13.8462 | 21.5854 | 3.1678 | 4.5714 | 0.6 | 8.3333 | 0.6 | 3.3333 | 13.8889
| 3305 | 1.2 | 3.3333 | 11.25 | 18.6425 | 3.1258 | 4.2667 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 3306 | 0.8 | 5 | 13.5 | 20.2693 | 3.1467 | 3.6226 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 3307 | 0.8 | 5 | 13.1707 | 19.0279 | 2.8095 | 3.0476 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 3308 | 0.6 | 6.6667 | 10.8 | 22.0552 | 3.2552 | 8 | 1.4 | 3.5714 | 0.1 | 20 | 30.2381
| 3309 | 1.2 | 3.3333 | 10.5882 | 20.6292 | 3.4203 | 6.6207 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 3310 | 0.2 | 20 | 11.7391 | 16.8362 | 2.6667 | 2.4304 | 1 | 5 | 0.2 | 10 | 35
| 3311 | 0.6 | 6.6667 | 10 | 16.8541 | 3.8065 | 3.0476 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 3312 | 0.4 | 10 | 12 | 19.4222 | 2.6222 | 4.8 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 3313 | 0.8 | 5 | 15.8824 | 24.6515 | 3.7165 | 5.0526 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 3314 | 1.2 | 3.3333 | 9.3103 | 15.608 | 2.9873 | 3.3103 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 3315 | 0.8 | 5 | 17.4194 | 25.7484 | 2.8434 | 5.4857 | 1 | 5 | 1 | 2 | 12
| 3316 | 0.8 | 5 | 16.3636 | 24.7629 | 2.9136 | 5.4857 | 1 | 5 | 0.2 | 10 | 20
| 3317 | 0.6 | 6.6667 | 9.8182 | 17.1088 | 2.6077 | 4.6829 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 3318 | 0.2 | 20 | 11.0204 | 19.3064 | 3.6031 | 4.6829 | 0.6 | 8.3333 | 0.2 | 10 | 38.3333
| 3319 | 1.2 | 3.3333 | 11.0204 | 18.9394 | 3.3475 | 4.5714 | 1 | 5 | 0.2 | 10 | 18.3333
| 3320 | 1.4 | 2.8571 | 13.1707 | 20.936 | 2.7126 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 3321 | 1.2 | 3.3333 | 9.6429 | 19.4731 | 2.4456 | 7.3846 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 3322 | 0.6 | 6.6667 | 12 | 17.4452 | 3.0452 | 2.4 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 3323 | 1.2 | 3.3333 | 10.5882 | 17.5717 | 2.8095 | 4.1739 | 1 | 5 | 0.4 | 5 | 13.3333
| 3324 | 0.8 | 5 | 10.3846 | 18.2153 | 2.4974 | 5.3333 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 3325 | 0.8 | 5 | 12.2727 | 19.7096 | 2.6369 | 4.8 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 3326 | 0.4 | 10 | 10 | 18.5376 | 2.5376 | 6 | 1 | 5 | 0.8 | 2.5 | 17.5
| 3327 | 1.2 | 3.3333 | 13.5 | 20.7147 | 3.5224 | 3.6923 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 3328 | 0.4 | 10 | 12.8571 | 19.7603 | 3.2109 | 3.6923 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 3329 | 0.8 | 5 | 12.5581 | 19.6235 | 3.3007 | 3.7647 | 1 | 5 | 0.8 | 2.5 | 12.5
| 3330 | 1.2 | 3.3333 | 11.7391 | 17.1849 | 2.6222 | 2.8235 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 3331 | 0.4 | 10 | 9.6429 | 15.2251 | 2.878 | 2.7042 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 3332 | 0.6 | 6.6667 | 12.5581 | 23.791 | 3.2329 | 8 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 3333 | 1.2 | 3.3333 | 15.8824 | 24.9275 | 3.0452 | 6 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 3334 | 1.2 | 3.3333 | 13.8462 | 20.074 | 3.4453 | 2.7826 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 3335 | 0.8 | 5 | 20 | 26.9475 | 3.2552 | 3.6923 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 3336 | 0.6 | 6.6667 | 12.8571 | 21.2929 | 2.95 | 5.4857 | 1 | 5 | 0.4 | 5 | 16.6667
| 3337 | 1 | 4 | 12.2727 | 17.0583 | 2.8263 | 1.9592 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 3338 | 1 | 4 | 12.5581 | 22.4496 | 4.9684 | 4.9231 | 1.4 | 3.5714 | 0.1 | 20 | 27.5714
| 3339 | 0.4 | 10 | 13.5 | 20.0881 | 3.2778 | 3.3103 | 1.6 | 3.125 | 0.4 | 5 | 18.125
| 3340 | 1.2 | 3.3333 | 10.8 | 20.6561 | 4.3704 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 3341 | 0.8 | 5 | 11.4894 | 19.7405 | 2.433 | 5.8182 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 3342 | 1.4 | 2.8571 | 18 | 27.8635 | 3.0064 | 6.8571 | 1 | 5 | 0.8 | 2.5 | 10.3571
| 3343 | 0.6 | 6.6667 | 11.0204 | 22.5454 | 4.1404 | 7.3846 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 3344 | 0.8 | 5 | 11.0204 | 17.2263 | 3.5758 | 2.6301 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 3345 | 0.4 | 10 | 9.1525 | 19.2503 | 2.0978 | 8 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 3346 | 0.4 | 10 | 8.4375 | 15.5138 | 2.7126 | 4.3636 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 3347 | 1 | 4 | 12.8571 | 18.7142 | 2.7602 | 3.0968 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 3348 | 0.6 | 6.6667 | 12.2727 | 18.7439 | 2.4712 | 4 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 3349 | 0.6 | 6.6667 | 12.8571 | 17.9228 | 1.8656 | 3.2 | 1 | 5 | 0.4 | 5 | 16.6667
| 3350 | 1.2 | 3.3333 | 10.1887 | 17.872 | 2.7602 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 3351 | 0.2 | 20 | 12.2727 | 18.8984 | 3.3714 | 3.2542 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 3352 | 0.8 | 5 | 10.5882 | 20.1775 | 3.3957 | 6.1935 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 3353 | 1 | 4 | 16.875 | 24.4239 | 3.5489 | 4 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.8333
| 3354 | 0.2 | 20 | 12.8571 | 20.7525 | 3.3239 | 4.5714 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 3355 | 1.4 | 2.8571 | 15.8824 | 25.2472 | 2.7442 | 6.6207 | 1.2 | 4.1667 | 0.8 | 2.5 | 9.5238
| 3356 | 0.8 | 5 | 12 | 20.7442 | 2.7442 | 6 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 3357 | 0.4 | 10 | 12 | 18.5619 | 3.0064 | 3.5556 | 1 | 5 | 0.4 | 5 | 20
| 3358 | 1.4 | 2.8571 | 12.2727 | 21.5303 | 2.6369 | 6.6207 | 1.2 | 4.1667 | 0.1 | 20 | 27.0238
| 3359 | 1 | 4 | 11.7391 | 19.5652 | 2.6369 | 5.1892 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 3360 | 1 | 4 | 10.3846 | 18.1499 | 2.7126 | 5.0526 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 3361 | 1.2 | 3.3333 | 9.6429 | 17.8008 | 3.1053 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 3362 | 0.8 | 5 | 13.5 | 26.2186 | 3.5758 | 9.1429 | 1.4 | 3.5714 | 0.8 | 2.5 | 11.0714
| 3363 | 1.2 | 3.3333 | 13.5 | 20.5779 | 4.4112 | 2.6667 | 0.6 | 8.3333 | 0.1 | 20 | 31.6667
| 3364 | 0.6 | 6.6667 | 11.7391 | 20.4511 | 3.0649 | 5.6471 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 3365 | 0.4 | 10 | 15.4286 | 24.3638 | 4.2523 | 4.6829 | 0.6 | 8.3333 | 0.1 | 20 | 38.3333
| 3366 | 0.8 | 5 | 15.4286 | 20.9978 | 2.8263 | 2.7429 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 3367 | 0.6 | 6.6667 | 12.5581 | 18.6894 | 2.2913 | 3.84 | 1 | 5 | 0.4 | 5 | 16.6667
| 3368 | 1 | 4 | 13.8462 | 20.1968 | 2.5106 | 3.84 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 3369 | 0.8 | 5 | 11.7391 | 17.9941 | 2.3366 | 3.9184 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 3370 | 0.8 | 5 | 11.7391 | 18.9648 | 3.6031 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 3371 | 0.6 | 6.6667 | 10 | 17.7538 | 2.4205 | 5.3333 | 1 | 5 | 0.4 | 5 | 16.6667
| 3372 | 1 | 4 | 17.4194 | 25.0627 | 2.8434 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 3373 | 1.2 | 3.3333 | 9.4737 | 19.1361 | 2.5514 | 7.1111 | 1 | 5 | 0.4 | 5 | 13.3333
| 3374 | 0.6 | 6.6667 | 10.8 | 17.1184 | 2.95 | 3.3684 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 3375 | 0.4 | 10 | 15 | 21.5277 | 4.0342 | 2.4935 | 1 | 5 | 0.4 | 5 | 20
| 3376 | 0.6 | 6.6667 | 10 | 17.3889 | 3.5489 | 3.84 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 3377 | 0.6 | 6.6667 | 10.5882 | 18.3041 | 3.6308 | 4.0851 | 1 | 5 | 0.6 | 3.3333 | 15
| 3378 | 1 | 4 | 13.5 | 19.6779 | 2.8095 | 3.3684 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 3379 | 0.8 | 5 | 16.3636 | 22.5205 | 2.7283 | 3.4286 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 3380 | 0.6 | 6.6667 | 11.4894 | 18.905 | 2.2264 | 5.1892 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 3381 | 0.6 | 6.6667 | 10.1887 | 17.0764 | 2.5241 | 4.3636 | 1.8 | 2.7778 | 0.4 | 5 | 14.4444
| 3382 | 0.2 | 20 | 11.0204 | 17.0828 | 3.3957 | 2.6667 | 0.6 | 8.3333 | 0.6 | 3.3333 | 31.6667
| 3383 | 1 | 4 | 9.6429 | 17.2943 | 2.7283 | 4.9231 | 1 | 5 | 0.8 | 2.5 | 11.5
| 3384 | 0.6 | 6.6667 | 12 | 19.8291 | 2.7765 | 5.0526 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 3385 | 1.4 | 2.8571 | 10.5882 | 18.638 | 2.8606 | 5.1892 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 3386 | 0.6 | 6.6667 | 12.5581 | 19.6008 | 2.4712 | 4.5714 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 3387 | 0.6 | 6.6667 | 11.7391 | 19.9533 | 2.3959 | 5.8182 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 3388 | 1 | 4 | 14.2105 | 21.0405 | 3.5758 | 3.2542 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 3389 | 1.2 | 3.3333 | 12.8571 | 18.5355 | 2.8957 | 2.7826 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 3390 | 1.4 | 2.8571 | 8.8525 | 15.266 | 3.0452 | 3.3684 | 0.6 | 8.3333 | 0.4 | 5 | 16.1905
| 3391 | 0.8 | 5 | 8.0597 | 15.0866 | 2.7602 | 4.2667 | 1 | 5 | 1 | 2 | 12
| 3392 | 0.4 | 10 | 12 | 22.322 | 3.2109 | 7.1111 | 1 | 5 | 0.4 | 5 | 20
| 3393 | 0.4 | 10 | 15.4286 | 22.4082 | 2.4082 | 4.5714 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 3394 | 0.2 | 20 | 12.2727 | 19.2836 | 2.7442 | 4.2667 | 0.8 | 6.25 | 0.2 | 10 | 36.25
| 3395 | 0.8 | 5 | 18 | 24.2146 | 1.851 | 4.3636 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 3396 | 1.2 | 3.3333 | 11.7391 | 19.3721 | 2.95 | 4.6829 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 3397 | 0.6 | 6.6667 | 9.4737 | 16.5757 | 2.6369 | 4.4651 | 1 | 5 | 0.2 | 10 | 21.6667
| 3398 | 0.4 | 10 | 12.5581 | 21.9794 | 3.6031 | 5.8182 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 3399 | 1 | 4 | 10 | 18.2299 | 2.7442 | 5.4857 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 3400 | 1.2 | 3.3333 | 10.8 | 17.1485 | 2.7929 | 3.5556 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 3401 | 1 | 4 | 10.5882 | 17.4839 | 2.8957 | 4 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 3402 | 0.6 | 6.6667 | 13.5 | 20.9925 | 2.8095 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 3403 | 0.6 | 6.6667 | 10.5882 | 18.3925 | 3.2329 | 4.5714 | 1 | 5 | 0.4 | 5 | 16.6667
| 3404 | 1 | 4 | 11.7391 | 17.7611 | 2.5934 | 3.4286 | 0.6 | 8.3333 | 1 | 2 | 14.3333
| 3405 | 1.2 | 3.3333 | 10.8 | 17.6108 | 2.6369 | 4.1739 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 3406 | 0.8 | 5 | 8.5714 | 15.1896 | 3.4706 | 3.1475 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 3407 | 1.4 | 2.8571 | 12.5581 | 20.8788 | 2.9873 | 5.3333 | 0.8 | 6.25 | 0.8 | 2.5 | 11.6071
| 3408 | 0.8 | 5 | 7.9412 | 15.3421 | 2.3483 | 5.0526 | 1.6 | 3.125 | 0.6 | 3.3333 | 11.4583
| 3409 | 0.4 | 10 | 10.5882 | 17.0424 | 3.0256 | 3.4286 | 1.6 | 3.125 | 0.6 | 3.3333 | 16.4583
| 3410 | 0.8 | 5 | 24.5455 | 31.2614 | 3.3475 | 3.3684 | 1 | 5 | 0.4 | 5 | 15
| 3411 | 1.4 | 2.8571 | 12.5581 | 18.7457 | 2.2692 | 3.9184 | 1 | 5 | 0.4 | 5 | 12.8571
| 3412 | 0.6 | 6.6667 | 9.8182 | 17.5063 | 3.6031 | 4.0851 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 3413 | 1 | 4 | 12.8571 | 21.2831 | 2.6077 | 5.8182 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 3414 | 0.6 | 6.6667 | 13.1707 | 19.4058 | 2.7442 | 3.4909 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 3415 | 1.4 | 2.8571 | 8.1818 | 14.45 | 2.7126 | 3.5556 | 1.4 | 3.5714 | 0.6 | 3.3333 | 9.7619
| 3416 | 0.8 | 5 | 12.5581 | 21.8248 | 3.9333 | 5.3333 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 3417 | 0.4 | 10 | 15 | 23.0676 | 2.4205 | 5.6471 | 1 | 5 | 0.4 | 5 | 20
| 3418 | 1 | 4 | 13.5 | 22.8136 | 2.9136 | 6.4 | 0.6 | 8.3333 | 0.1 | 20 | 32.3333
| 3419 | 0.6 | 6.6667 | 12.5581 | 19.5531 | 2.7283 | 4.2667 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 3420 | 0.8 | 5 | 13.1707 | 20.333 | 2.6971 | 4.4651 | 1 | 5 | 0.4 | 5 | 15
| 3421 | 0.6 | 6.6667 | 13.5 | 20.707 | 2.8434 | 4.3636 | 1 | 5 | 0.4 | 5 | 16.6667
| 3422 | 0.8 | 5 | 12.8571 | 20.0924 | 2.9686 | 4.2667 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 3423 | 0.4 | 10 | 12.8571 | 22.1156 | 3.0649 | 6.1935 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 3424 | 0.8 | 5 | 14.5946 | 24.5984 | 3.1467 | 6.8571 | 1 | 5 | 0.4 | 5 | 15
| 3425 | 1.2 | 3.3333 | 8.5714 | 15.9865 | 2.95 | 4.4651 | 1 | 5 | 0.2 | 10 | 18.3333
| 3426 | 0.8 | 5 | 10.8 | 17.7553 | 2.3838 | 4.5714 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 3427 | 0.4 | 10 | 15.4286 | 21.5502 | 3.1678 | 2.9538 | 1 | 5 | 0.1 | 20 | 35
| 3428 | 1.2 | 3.3333 | 12.2727 | 19.2429 | 3.3475 | 3.6226 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 3429 | 0.4 | 10 | 23.4783 | 34.1151 | 2.6369 | 8 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 3430 | 1 | 4 | 13.5 | 22.5511 | 3.2329 | 5.8182 | 1.6 | 3.125 | 0.1 | 20 | 27.125
| 3431 | 0.6 | 6.6667 | 9.6429 | 15.6614 | 2.3959 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 3432 | 1 | 4 | 10.1887 | 17.4608 | 3.7165 | 3.5556 | 1 | 5 | 0.4 | 5 | 14
| 3433 | 0.8 | 5 | 8.5714 | 18.9798 | 2.7283 | 7.68 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 3434 | 0.6 | 6.6667 | 11.4894 | 18.6975 | 2.4082 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 3435 | 0.2 | 20 | 17.4194 | 25.1691 | 2.6971 | 5.0526 | 1.8 | 2.7778 | 0.2 | 10 | 32.7778
| 3436 | 0.8 | 5 | 11.25 | 18.948 | 3.2329 | 4.4651 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 3437 | 0.4 | 10 | 9.6429 | 16.9087 | 3.3475 | 3.9184 | 1 | 5 | 0.2 | 10 | 25
| 3438 | 0.4 | 10 | 12.5581 | 21.0555 | 2.4974 | 6 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 3439 | 0.8 | 5 | 12.2727 | 19.3423 | 2.8957 | 4.1739 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 3440 | 0.8 | 5 | 12.5581 | 20.3472 | 3.5224 | 4.2667 | 1.6 | 3.125 | 0.6 | 3.3333 | 11.4583
| 3441 | 0.8 | 5 | 12 | 20.9136 | 2.9136 | 6 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 3442 | 1 | 4 | 17.4194 | 25.5433 | 3.3239 | 4.8 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 3443 | 0.4 | 10 | 14.2105 | 20.9069 | 2.9317 | 3.7647 | 1.4 | 3.5714 | 0.8 | 2.5 | 16.0714
| 3444 | 1 | 4 | 10.1887 | 16.9166 | 3.1053 | 3.6226 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 3445 | 0.6 | 6.6667 | 9.8182 | 17.7286 | 3.4453 | 4.4651 | 1 | 5 | 0.1 | 20 | 31.6667
| 3446 | 0.6 | 6.6667 | 12.5581 | 23.7155 | 2.8095 | 8.3478 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 3447 | 0.8 | 5 | 12.8571 | 21.342 | 2.2913 | 6.1935 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 3448 | 0.6 | 6.6667 | 10 | 18.1579 | 3.1053 | 5.0526 | 1 | 5 | 0.2 | 10 | 21.6667
| 3449 | 1.6 | 2.5 | 15.4286 | 21.7444 | 2.7602 | 3.5556 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.0833
| 3450 | 0.4 | 10 | 10.1887 | 17.5835 | 2.2056 | 5.1892 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 3451 | 0.6 | 6.6667 | 10.1887 | 17.8089 | 2.6971 | 4.9231 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 3452 | 0.6 | 6.6667 | 11.4894 | 18.5928 | 2.4205 | 4.6829 | 1 | 5 | 0.4 | 5 | 16.6667
| 3453 | 1 | 4 | 10 | 15.6357 | 2.6818 | 2.9538 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 3454 | 1.4 | 2.8571 | 8.1818 | 16.3493 | 3.9008 | 4.2667 | 1 | 5 | 0.8 | 2.5 | 10.3571
| 3455 | 1.2 | 3.3333 | 11.7391 | 20.7908 | 2.6517 | 6.4 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 3456 | 0.4 | 10 | 19.2857 | 29.0823 | 3.6031 | 6.1935 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 3457 | 1.4 | 2.8571 | 13.8462 | 22.4371 | 3.1053 | 5.4857 | 1 | 5 | 0.2 | 10 | 17.8571
| 3458 | 0.8 | 5 | 12.2727 | 19.9076 | 3.7165 | 3.9184 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 3459 | 0.6 | 6.6667 | 12.8571 | 18.6284 | 3.2778 | 2.4935 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 3460 | 1 | 4 | 9.6429 | 17.4735 | 2.4974 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 3461 | 0.8 | 5 | 14.2105 | 20.8609 | 2.5652 | 4.0851 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 3462 | 0.8 | 5 | 11.0204 | 17.4249 | 2.9136 | 3.4909 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 3463 | 0.8 | 5 | 11.4894 | 17.6463 | 2.7283 | 3.4286 | 1 | 5 | 0.4 | 5 | 15
| 3464 | 0.6 | 6.6667 | 14.2105 | 22.4726 | 4.177 | 4.0851 | 1 | 5 | 0.4 | 5 | 16.6667
| 3465 | 0.2 | 20 | 15.4286 | 22.3318 | 3.2109 | 3.6923 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 3466 | 0.8 | 5 | 11.0204 | 17.8904 | 3.1053 | 3.7647 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 3467 | 0.6 | 6.6667 | 11.0204 | 19.7324 | 3.0649 | 5.6471 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 3468 | 1.2 | 3.3333 | 15 | 24.4044 | 3.2109 | 6.1935 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 3469 | 1.2 | 3.3333 | 11.4894 | 18.141 | 2.6517 | 4 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 3470 | 0.6 | 6.6667 | 14.5946 | 22.2275 | 3.1678 | 4.4651 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 3471 | 0.8 | 5 | 16.875 | 25.5798 | 3.3714 | 5.3333 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 3472 | 0.8 | 5 | 8.7097 | 16.471 | 4.069 | 3.6923 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 3473 | 1 | 4 | 13.8462 | 22.6694 | 4.1404 | 4.6829 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 3474 | 1.2 | 3.3333 | 9.4737 | 18.4447 | 3.3239 | 5.6471 | 1 | 5 | 0.4 | 5 | 13.3333
| 3475 | 1 | 4 | 14.2105 | 21.6256 | 2.95 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 3476 | 0.4 | 10 | 14.5946 | 22.1642 | 3.3957 | 4.1739 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 3477 | 1.2 | 3.3333 | 11.7391 | 21.6614 | 2.5376 | 7.3846 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 3478 | 0.8 | 5 | 7.9412 | 14.2711 | 2.5652 | 3.7647 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 3479 | 0.6 | 6.6667 | 15.4286 | 21.6026 | 2.5514 | 3.6226 | 1 | 5 | 0.6 | 3.3333 | 15
| 3480 | 0.1 | 40 | 11.7391 | 17.4384 | 2.6517 | 3.0476 | 1.2 | 4.1667 | 0.2 | 10 | 54.1667
| 3481 | 0.8 | 5 | 10.3846 | 21.0021 | 3.2329 | 7.3846 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 3482 | 0.6 | 6.6667 | 18.6207 | 27.8099 | 3.1892 | 6 | 0.6 | 8.3333 | 0.8 | 2.5 | 17.5
| 3483 | 1 | 4 | 10.1887 | 21.1204 | 2.9317 | 8 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 3484 | 0.6 | 6.6667 | 22.5 | 29.1181 | 3.4706 | 3.1475 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 3485 | 0.8 | 5 | 9 | 16.5283 | 2.7283 | 4.8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 3486 | 0.4 | 10 | 13.8462 | 22.2751 | 3.746 | 4.6829 | 0.4 | 12.5 | 0.6 | 3.3333 | 25.8333
| 3487 | 0.8 | 5 | 10 | 17.1629 | 3.4706 | 3.6923 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 3488 | 1.2 | 3.3333 | 9.8182 | 18.8404 | 2.6222 | 6.4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 3489 | 0.8 | 5 | 10.1887 | 18.7112 | 3.1892 | 5.3333 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 3490 | 0.4 | 10 | 20.7692 | 26.3901 | 2.5241 | 3.0968 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 3491 | 0.8 | 5 | 11.0204 | 17.0567 | 2.6077 | 3.4286 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 3492 | 1 | 4 | 15.8824 | 24.2047 | 3.5224 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 3493 | 1 | 4 | 12.2727 | 20.7183 | 2.4456 | 6 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 3494 | 0.6 | 6.6667 | 9.3103 | 16.0284 | 2.878 | 3.84 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 3495 | 0.4 | 10 | 8.8525 | 20.2713 | 4.0342 | 7.3846 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 3496 | 0.6 | 6.6667 | 15.4286 | 27.1428 | 4.0342 | 7.68 | 1 | 5 | 0.1 | 20 | 31.6667
| 3497 | 0.6 | 6.6667 | 9.3103 | 17.7411 | 3.6308 | 4.8 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 3498 | 0.6 | 6.6667 | 12 | 18.5704 | 2.878 | 3.6923 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 3499 | 0.4 | 10 | 13.1707 | 20.5023 | 3.0649 | 4.2667 | 1 | 5 | 0.4 | 5 | 20
| 3500 | 0.2 | 20 | 14.5946 | 22.2909 | 3.5224 | 4.1739 | 1 | 5 | 0.2 | 10 | 35
| 3501 | 0.6 | 6.6667 | 8.5714 | 17.3479 | 2.7765 | 6 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 3502 | 0.8 | 5 | 13.8462 | 20.5982 | 2.9873 | 3.7647 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 3503 | 0.8 | 5 | 19.2857 | 25.8384 | 2.7126 | 3.84 | 1 | 5 | 0.2 | 10 | 20
| 3504 | 1 | 4 | 10.8 | 16.9732 | 3.0256 | 3.1475 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 3505 | 1.6 | 2.5 | 12.8571 | 19.9523 | 3.2552 | 3.84 | 1.2 | 4.1667 | 0.2 | 10 | 16.6667
| 3506 | 1.2 | 3.3333 | 10.3846 | 17.6898 | 2.6222 | 4.6829 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 3507 | 1 | 4 | 19.2857 | 26.4572 | 3.5489 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 3508 | 0.6 | 6.6667 | 12.8571 | 21.7325 | 2.6818 | 6.1935 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 3509 | 1.4 | 2.8571 | 9.1525 | 17.8837 | 2.5376 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 3510 | 1.2 | 3.3333 | 9.6429 | 18.9919 | 2.7283 | 6.6207 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 3511 | 1 | 4 | 12.8571 | 21.1516 | 3.1053 | 5.1892 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 3512 | 1.2 | 3.3333 | 12.8571 | 18.3709 | 2.8095 | 2.7042 | 1 | 5 | 0.4 | 5 | 13.3333
| 3513 | 0.6 | 6.6667 | 11.7391 | 20.3837 | 2.8263 | 5.8182 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 3514 | 0.4 | 10 | 13.8462 | 19.4396 | 2.5934 | 3 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 3515 | 0.6 | 6.6667 | 12.8571 | 20.7839 | 2.5934 | 5.3333 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 3516 | 0.6 | 6.6667 | 11.25 | 17.6552 | 2.5652 | 3.84 | 1 | 5 | 0.2 | 10 | 21.6667
| 3517 | 0.4 | 10 | 11.7391 | 19.1799 | 3.5224 | 3.9184 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 3518 | 1.2 | 3.3333 | 10.3846 | 19.9926 | 2.9873 | 6.6207 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 3519 | 0.6 | 6.6667 | 13.1707 | 24.4588 | 4.177 | 7.1111 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 3520 | 0.8 | 5 | 12.2727 | 20.5197 | 3.3239 | 4.9231 | 1.4 | 3.5714 | 1 | 2 | 10.5714
| 3521 | 1.2 | 3.3333 | 11.25 | 16.8258 | 2.6667 | 2.9091 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 3522 | 0.4 | 10 | 12.8571 | 20.759 | 2.7126 | 5.1892 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 3523 | 1.6 | 2.5 | 13.5 | 19.7475 | 3.6875 | 2.56 | 1.2 | 4.1667 | 0.4 | 5 | 11.6667
| 3524 | 0.8 | 5 | 13.1707 | 20.0957 | 3.085 | 3.84 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 3525 | 0.6 | 6.6667 | 11.7391 | 18.1177 | 2.95 | 3.4286 | 1 | 5 | 0.2 | 10 | 21.6667
| 3526 | 1.4 | 2.8571 | 9.8182 | 15.6277 | 2.8095 | 3 | 1.4 | 3.5714 | 0.6 | 3.3333 | 9.7619
| 3527 | 0.6 | 6.6667 | 12.5581 | 20.7141 | 3.2329 | 4.9231 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 3528 | 1.4 | 2.8571 | 13.1707 | 21.1371 | 3.9664 | 4 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 3529 | 0.2 | 20 | 13.5 | 21.3266 | 3.2552 | 4.5714 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 3530 | 1.2 | 3.3333 | 13.5 | 20.7381 | 2.6667 | 4.5714 | 0.4 | 12.5 | 0.4 | 5 | 20.8333
| 3531 | 1 | 4 | 12.5581 | 17.1084 | 2.237 | 2.3133 | 1.6 | 3.125 | 0.6 | 3.3333 | 10.4583
| 3532 | 0.8 | 5 | 11.7391 | 18.2073 | 3.3714 | 3.0968 | 1 | 5 | 0.4 | 5 | 15
| 3533 | 1 | 4 | 10 | 16.9453 | 3.1053 | 3.84 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 3534 | 0.8 | 5 | 9.4737 | 17.5468 | 3.8065 | 4.2667 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 3535 | 0.2 | 20 | 10.8 | 18.6492 | 3.2778 | 4.5714 | 1.6 | 3.125 | 0.4 | 5 | 28.125
| 3536 | 1 | 4 | 20 | 28.7602 | 2.7602 | 6 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 3537 | 1.2 | 3.3333 | 20 | 26.3422 | 2.9136 | 3.4286 | 1 | 5 | 0.4 | 5 | 13.3333
| 3538 | 1 | 4 | 16.3636 | 21.7513 | 3.2778 | 2.1099 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 3539 | 1.2 | 3.3333 | 13.5 | 18.7315 | 2.6369 | 2.5946 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 3540 | 0.2 | 20 | 13.5 | 22.1535 | 3.1678 | 5.4857 | 1 | 5 | 0.1 | 20 | 45
| 3541 | 1.2 | 3.3333 | 9.6429 | 16.2546 | 3.746 | 2.8657 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 3542 | 1 | 4 | 10.5882 | 17.3158 | 3.6308 | 3.0968 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 3543 | 0.6 | 6.6667 | 10.3846 | 18.1476 | 3.4963 | 4.2667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 3544 | 1 | 4 | 11.7391 | 20.5696 | 2.6369 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 3545 | 0.6 | 6.6667 | 15 | 23.8767 | 3.6875 | 5.1892 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 3546 | 1.2 | 3.3333 | 12.2727 | 17.9149 | 2.7765 | 2.8657 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 3547 | 0.8 | 5 | 13.5 | 22.5909 | 4.2909 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 3548 | 0.6 | 6.6667 | 15.4286 | 22.0386 | 2.9873 | 3.6226 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 3549 | 0.8 | 5 | 14.5946 | 20.6738 | 2.9317 | 3.1475 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 3550 | 1 | 4 | 10.8 | 20.8797 | 2.9686 | 7.1111 | 1 | 5 | 0.4 | 5 | 14
| 3551 | 0.6 | 6.6667 | 12.5581 | 19.0675 | 3.2552 | 3.2542 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 3552 | 0.4 | 10 | 15.4286 | 25.0875 | 3.6589 | 6 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 3553 | 0.4 | 10 | 15 | 22.2997 | 3.1258 | 4.1739 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 3554 | 0.6 | 6.6667 | 9.1525 | 19.7318 | 2.5792 | 8 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 3555 | 1 | 4 | 13.8462 | 21.9469 | 3.3007 | 4.8 | 1.4 | 3.5714 | 0.1 | 20 | 27.5714
| 3556 | 0.2 | 20 | 18 | 24.7572 | 3.0649 | 3.6923 | 1.4 | 3.5714 | 0.8 | 2.5 | 26.0714
| 3557 | 0.6 | 6.6667 | 12.5581 | 22.1595 | 2.7442 | 6.8571 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 3558 | 0.4 | 10 | 12.5581 | 21.6807 | 3.9333 | 5.1892 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 3559 | 0.8 | 5 | 12 | 24.1241 | 2.5241 | 9.6 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 3560 | 1.2 | 3.3333 | 18 | 29.3846 | 4 | 7.3846 | 1 | 5 | 0.4 | 5 | 13.3333
| 3561 | 0.6 | 6.6667 | 17.4194 | 26.4484 | 3.2109 | 5.8182 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 3562 | 0.6 | 6.6667 | 11.7391 | 17.7495 | 2.9136 | 3.0968 | 1 | 5 | 0.6 | 3.3333 | 15
| 3563 | 1.2 | 3.3333 | 12.8571 | 26.1607 | 2.6369 | 10.6667 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 3564 | 0.4 | 10 | 10.8 | 18.8747 | 3.9008 | 4.1739 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 3565 | 1 | 4 | 15.4286 | 23.1451 | 3.7165 | 4 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 3566 | 0.6 | 6.6667 | 12 | 19.432 | 2.8606 | 4.5714 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 3567 | 0.4 | 10 | 11.25 | 21.9642 | 3.6031 | 7.1111 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 3568 | 1.2 | 3.3333 | 12.2727 | 20.8612 | 3.2552 | 5.3333 | 1 | 5 | 0.2 | 10 | 18.3333
| 3569 | 1 | 4 | 12.8571 | 21.1644 | 4.8163 | 3.4909 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 3570 | 1.8 | 2.2222 | 8.8525 | 13.5966 | 2.7442 | 2 | 1 | 5 | 0.2 | 10 | 17.2222
| 3571 | 0.6 | 6.6667 | 13.5 | 19.1075 | 2.1166 | 3.4909 | 1.6 | 3.125 | 0.4 | 5 | 14.7917
| 3572 | 0.8 | 5 | 11.4894 | 17.7966 | 3.6031 | 2.7042 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 3573 | 1 | 4 | 13.8462 | 22.0873 | 3.776 | 4.4651 | 1.4 | 3.5714 | 1 | 2 | 9.5714
| 3574 | 0.8 | 5 | 16.875 | 23.3054 | 3.6875 | 2.7429 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 3575 | 1 | 4 | 11.25 | 20.3393 | 2.8957 | 6.1935 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 3576 | 1 | 4 | 11.4894 | 22.1803 | 4.2909 | 6.4 | 1.6 | 3.125 | 0.6 | 3.3333 | 10.4583
| 3577 | 1.6 | 2.5 | 12.5581 | 19.7221 | 3.3239 | 3.84 | 1.4 | 3.5714 | 0.2 | 10 | 16.0714
| 3578 | 0.8 | 5 | 15 | 25.9136 | 2.9136 | 8 | 1 | 5 | 0.2 | 10 | 20
| 3579 | 1.2 | 3.3333 | 10.8 | 18.6129 | 2.7602 | 5.0526 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 3580 | 1.4 | 2.8571 | 17.4194 | 25.3132 | 3.2109 | 4.6829 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 3581 | 0.8 | 5 | 18.6207 | 26.1426 | 3.9664 | 3.5556 | 1 | 5 | 0.4 | 5 | 15
| 3582 | 0.8 | 5 | 11.7391 | 18.3424 | 2.3366 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 3583 | 0.8 | 5 | 17.4194 | 23.532 | 2.7442 | 3.3684 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 3584 | 1.2 | 3.3333 | 13.1707 | 21.466 | 2.8095 | 5.4857 | 1 | 5 | 0.4 | 5 | 13.3333
| 3585 | 0.8 | 5 | 10.8 | 21.5677 | 4.7677 | 6 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 3586 | 0.4 | 10 | 14.5946 | 22.4885 | 2.4082 | 5.4857 | 1 | 5 | 0.4 | 5 | 20
| 3587 | 0.1 | 40 | 11.4894 | 17.8085 | 3.0649 | 3.2542 | 0.8 | 6.25 | 0.6 | 3.3333 | 49.5833
| 3588 | 1 | 4 | 11.0204 | 17.558 | 2.5376 | 4 | 1 | 5 | 0.4 | 5 | 14
| 3589 | 0.6 | 6.6667 | 12.8571 | 20.7269 | 3.6031 | 4.2667 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 3590 | 0.2 | 20 | 14.5946 | 19.7094 | 2.2913 | 2.8235 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 3591 | 0.6 | 6.6667 | 15.4286 | 20.8315 | 2.0345 | 3.3684 | 0.6 | 8.3333 | 0.1 | 20 | 35
| 3592 | 0.6 | 6.6667 | 10.3846 | 17.5469 | 2.6971 | 4.4651 | 1 | 5 | 0.4 | 5 | 16.6667
| 3593 | 1.2 | 3.3333 | 10.8 | 16.6964 | 2.9873 | 2.9091 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 3594 | 0.2 | 20 | 12 | 20.6991 | 3.776 | 4.9231 | 1.2 | 4.1667 | 0.8 | 2.5 | 26.6667
| 3595 | 0.6 | 6.6667 | 7.2 | 13.4222 | 2.6667 | 3.5556 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 3596 | 1.4 | 2.8571 | 15 | 23.9377 | 2.7442 | 6.1935 | 1 | 5 | 0.2 | 10 | 17.8571
| 3597 | 1.2 | 3.3333 | 13.1707 | 19.7068 | 3.0452 | 3.4909 | 1 | 5 | 0.4 | 5 | 13.3333
| 3598 | 0.4 | 10 | 10.3846 | 17.0833 | 3.0064 | 3.6923 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 3599 | 1.6 | 2.5 | 11.25 | 17.9346 | 2.5106 | 4.1739 | 0.8 | 6.25 | 0.1 | 20 | 28.75
| 3600 | 0.6 | 6.6667 | 11.7391 | 18.6848 | 2.8606 | 4.0851 | 0.4 | 12.5 | 0.2 | 10 | 29.1667
| 3601 | 1 | 4 | 8.4375 | 14.8366 | 3.4453 | 2.9538 | 1 | 5 | 0.4 | 5 | 14
| 3602 | 1 | 4 | 9.1525 | 16.3174 | 2.5934 | 4.5714 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 3603 | 1 | 4 | 12 | 20.5011 | 3.1678 | 5.3333 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 3604 | 0.6 | 6.6667 | 10.8 | 17.4395 | 3.2109 | 3.4286 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 3605 | 1 | 4 | 8.8525 | 17.7482 | 2.8957 | 6 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 3606 | 1.4 | 2.8571 | 13.5 | 20.4715 | 3.6031 | 3.3684 | 1 | 5 | 0.1 | 20 | 27.8571
| 3607 | 1 | 4 | 10 | 17.916 | 2.0978 | 5.8182 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 3608 | 0.8 | 5 | 16.3636 | 23.8005 | 2.6369 | 4.8 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 3609 | 0.2 | 20 | 11.7391 | 20.3015 | 2.7442 | 5.8182 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 3610 | 1.2 | 3.3333 | 20 | 26.1449 | 2.7765 | 3.3684 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 3611 | 1 | 4 | 11.0204 | 19.1182 | 3.0452 | 5.0526 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 3612 | 1.2 | 3.3333 | 11.4894 | 17.4366 | 2.6369 | 3.3103 | 1 | 5 | 0.2 | 10 | 18.3333
| 3613 | 0.6 | 6.6667 | 11.7391 | 19.2099 | 3.6308 | 3.84 | 1 | 5 | 1 | 2 | 13.6667
| 3614 | 0.4 | 10 | 12.8571 | 19.1259 | 3.4453 | 2.8235 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 3615 | 1.4 | 2.8571 | 12.8571 | 21.4409 | 3.9008 | 4.6829 | 1 | 5 | 0.4 | 5 | 12.8571
| 3616 | 1.2 | 3.3333 | 10.8 | 18.2746 | 3.3007 | 4.1739 | 1.2 | 4.1667 | 0.1 | 20 | 27.5
| 3617 | 1 | 4 | 11.0204 | 20.4691 | 3.2552 | 6.1935 | 1 | 5 | 0.1 | 20 | 29
| 3618 | 0.8 | 5 | 11.25 | 20.3553 | 3.1053 | 6 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 3619 | 1.6 | 2.5 | 15.4286 | 22.5106 | 2.5106 | 4.5714 | 1.4 | 3.5714 | 0.2 | 10 | 16.0714
| 3620 | 0.6 | 6.6667 | 13.5 | 20.4873 | 2.9873 | 4 | 1 | 5 | 0.6 | 3.3333 | 15
| 3621 | 1.2 | 3.3333 | 14.2105 | 20.8622 | 2.6517 | 4 | 1 | 5 | 0.4 | 5 | 13.3333
| 3622 | 1 | 4 | 10.8 | 18.6409 | 2.6517 | 5.1892 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 3623 | 0.8 | 5 | 13.1707 | 21.9307 | 2.36 | 6.4 | 1 | 5 | 1 | 2 | 12
| 3624 | 1.4 | 2.8571 | 8.8525 | 14.5218 | 2.7602 | 2.9091 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 3625 | 1 | 4 | 10.1887 | 17.387 | 2.9317 | 4.2667 | 1 | 5 | 0.4 | 5 | 14
| 3626 | 0.6 | 6.6667 | 11.25 | 18.3455 | 2.5241 | 4.5714 | 1 | 5 | 0.6 | 3.3333 | 15
| 3627 | 1 | 4 | 10 | 18.376 | 4.2909 | 4.0851 | 1.2 | 4.1667 | 1 | 2 | 10.1667
| 3628 | 1.2 | 3.3333 | 17.4194 | 24.9408 | 2.95 | 4.5714 | 0.4 | 12.5 | 0.8 | 2.5 | 18.3333
| 3629 | 0.8 | 5 | 16.3636 | 25.1401 | 2.7765 | 6 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 3630 | 1 | 4 | 11.4894 | 18.0971 | 2.6077 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 3631 | 0.8 | 5 | 11.7391 | 19.6558 | 4.9167 | 3 | 1.6 | 3.125 | 0.2 | 10 | 18.125
| 3632 | 0.8 | 5 | 10 | 16.85 | 2.9317 | 3.9184 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 3633 | 1 | 4 | 11.7391 | 17.7153 | 2.6077 | 3.3684 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 3634 | 0.4 | 10 | 12 | 18.4769 | 2.6369 | 3.84 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 3635 | 0.8 | 5 | 14.5946 | 21.4209 | 2.8263 | 4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 3636 | 1 | 4 | 9.4737 | 15.4406 | 2.7126 | 3.2542 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 3637 | 0.6 | 6.6667 | 16.875 | 24.0194 | 3.776 | 3.3684 | 1 | 5 | 0.2 | 10 | 21.6667
| 3638 | 1.4 | 2.8571 | 18.6207 | 25.9448 | 2.5241 | 4.8 | 1.2 | 4.1667 | 0.8 | 2.5 | 9.5238
| 3639 | 0.6 | 6.6667 | 17.4194 | 25.698 | 2.7929 | 5.4857 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 3640 | 0.2 | 20 | 14.2105 | 20.3554 | 2.7765 | 3.3684 | 1.4 | 3.5714 | 0.1 | 20 | 43.5714
| 3641 | 0.8 | 5 | 13.1707 | 18.7925 | 2.7126 | 2.9091 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 3642 | 1 | 4 | 17.4194 | 26.1379 | 3.2329 | 5.4857 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 3643 | 0.4 | 10 | 9 | 16.4895 | 3.1258 | 4.3636 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 3644 | 1.2 | 3.3333 | 10.5882 | 17.9073 | 2.3959 | 4.9231 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 3645 | 0.6 | 6.6667 | 16.3636 | 22.6456 | 2.9136 | 3.3684 | 1 | 5 | 0.6 | 3.3333 | 15
| 3646 | 1 | 4 | 10.5882 | 18.224 | 2.7126 | 4.9231 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 3647 | 0.8 | 5 | 12 | 17.8175 | 3.3239 | 2.4935 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 3648 | 0.4 | 10 | 15 | 26.2552 | 3.2552 | 8 | 1 | 5 | 0.2 | 10 | 25
| 3649 | 0.6 | 6.6667 | 10.5882 | 18.9472 | 3.0256 | 5.3333 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 3650 | 0.6 | 6.6667 | 18 | 24.2666 | 2.3483 | 3.9184 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 3651 | 1.2 | 3.3333 | 13.5 | 21.6597 | 2.8263 | 5.3333 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 3652 | 0.8 | 5 | 8.7097 | 14.8383 | 2.7602 | 3.3684 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 3653 | 1.2 | 3.3333 | 9.4737 | 17.412 | 2.2913 | 5.6471 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 3654 | 0.6 | 6.6667 | 8.7097 | 15.0681 | 3.2109 | 3.1475 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 3655 | 1.4 | 2.8571 | 10.5882 | 16.4673 | 2.5106 | 3.3684 | 0.4 | 12.5 | 0.6 | 3.3333 | 18.6905
| 3656 | 1 | 4 | 11.4894 | 22.063 | 3.7165 | 6.8571 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 3657 | 1.2 | 3.3333 | 10.5882 | 16.8108 | 3.1258 | 3.0968 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 3658 | 1 | 4 | 11.7391 | 19.0407 | 3.746 | 3.5556 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 3659 | 0.6 | 6.6667 | 18 | 22.9356 | 2.5652 | 2.3704 | 1 | 5 | 0.6 | 3.3333 | 15
| 3660 | 1 | 4 | 12.8571 | 24.726 | 3.8689 | 8 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 3661 | 0.6 | 6.6667 | 17.4194 | 28.3455 | 4.069 | 6.8571 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 3662 | 0.8 | 5 | 10.5882 | 16.9835 | 3.085 | 3.3103 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 3663 | 0.8 | 5 | 10.3846 | 19.2429 | 2.4583 | 6.4 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 3664 | 0.8 | 5 | 12.8571 | 19.1914 | 2.8434 | 3.4909 | 1 | 5 | 0.2 | 10 | 20
| 3665 | 1 | 4 | 9.6429 | 17.2747 | 2.5792 | 5.0526 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 3666 | 0.8 | 5 | 11.0204 | 19.8803 | 4.177 | 4.6829 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 3667 | 0.6 | 6.6667 | 13.1707 | 20.7534 | 4.2143 | 3.3684 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 3668 | 0.8 | 5 | 10.5882 | 16.6354 | 2.7929 | 3.2542 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 3669 | 1 | 4 | 9.4737 | 17.9779 | 4.3303 | 4.1739 | 0.6 | 8.3333 | 0.1 | 20 | 32.3333
| 3670 | 1.2 | 3.3333 | 12.8571 | 18.5855 | 2.7283 | 3 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 3671 | 0.6 | 6.6667 | 21.6 | 30.0183 | 3.085 | 5.3333 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 3672 | 0.8 | 5 | 9.1525 | 16.3956 | 3.6875 | 3.5556 | 1.4 | 3.5714 | 0.1 | 20 | 28.5714
| 3673 | 0.4 | 10 | 15.8824 | 24.1413 | 3.6875 | 4.5714 | 1 | 5 | 0.4 | 5 | 20
| 3674 | 0.6 | 6.6667 | 13.8462 | 22.2157 | 2.5514 | 5.8182 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 3675 | 0.2 | 20 | 10 | 18.9136 | 2.9136 | 6 | 1.2 | 4.1667 | 0.8 | 2.5 | 26.6667
| 3676 | 0.6 | 6.6667 | 9.6429 | 16.4907 | 2.4842 | 4.3636 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 3677 | 1 | 4 | 10.8 | 18.232 | 2.8606 | 4.5714 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 3678 | 1.2 | 3.3333 | 9.4737 | 17.4573 | 3.3007 | 4.6829 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 3679 | 0.6 | 6.6667 | 12 | 21.7628 | 2.6517 | 7.1111 | 1 | 5 | 0.6 | 3.3333 | 15
| 3680 | 0.8 | 5 | 12 | 19.37 | 3.0064 | 4.3636 | 1 | 5 | 0.8 | 2.5 | 12.5
| 3681 | 1.6 | 2.5 | 11.7391 | 20.5963 | 3.3714 | 5.4857 | 1.4 | 3.5714 | 0.6 | 3.3333 | 9.4048
| 3682 | 0.8 | 5 | 9.4737 | 16.6337 | 2.237 | 4.9231 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 3683 | 0.4 | 10 | 12.5581 | 18.8248 | 2.3483 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 3684 | 1.2 | 3.3333 | 18 | 27.3714 | 3.3714 | 6 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 3685 | 1 | 4 | 10.8 | 17.1746 | 3.2778 | 3.0968 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 3686 | 0.6 | 6.6667 | 13.5 | 20.7109 | 3.2109 | 4 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 3687 | 0.8 | 5 | 15.8824 | 22.8994 | 2.4456 | 4.5714 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 3688 | 1 | 4 | 11.7391 | 19.772 | 3.2329 | 4.8 | 0.6 | 8.3333 | 0.1 | 20 | 32.3333
| 3689 | 0.4 | 10 | 14.5946 | 24.5279 | 3.9333 | 6 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 3690 | 0.6 | 6.6667 | 13.5 | 20.0726 | 2.95 | 3.6226 | 0.4 | 12.5 | 0.6 | 3.3333 | 22.5
| 3691 | 1 | 4 | 13.5 | 19.9226 | 2.9317 | 3.4909 | 1.6 | 3.125 | 0.6 | 3.3333 | 10.4583
| 3692 | 0.8 | 5 | 8.4375 | 13.6784 | 2.4583 | 2.7826 | 1 | 5 | 0.8 | 2.5 | 12.5
| 3693 | 0.2 | 20 | 12.2727 | 19.9893 | 3.7165 | 4 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 3694 | 1 | 4 | 10.3846 | 18.49 | 2.4583 | 5.6471 | 1.2 | 4.1667 | 1 | 2 | 10.1667
| 3695 | 1.2 | 3.3333 | 13.5 | 19.9976 | 2.5792 | 3.9184 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 3696 | 0.4 | 10 | 14.5946 | 20.7522 | 2.6667 | 3.4909 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 3697 | 1 | 4 | 11.7391 | 23.3403 | 2.4583 | 9.1429 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 3698 | 0.8 | 5 | 12.8571 | 20.0825 | 2.7602 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 3699 | 1 | 4 | 13.1707 | 21.6784 | 2.8606 | 5.6471 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 3700 | 1 | 4 | 10.5882 | 19.5382 | 2.95 | 6 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 3701 | 1 | 4 | 10.5882 | 20.3343 | 3.746 | 6 | 1 | 5 | 0.4 | 5 | 14
| 3702 | 1.4 | 2.8571 | 16.875 | 24.6436 | 2.9686 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 3703 | 1.4 | 2.8571 | 10.1887 | 19.7297 | 3.3475 | 6.1935 | 1 | 5 | 0.4 | 5 | 12.8571
| 3704 | 0.8 | 5 | 11.25 | 16.6752 | 2.9317 | 2.4935 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 3705 | 1.4 | 2.8571 | 11.0204 | 17.3106 | 2.3719 | 3.9184 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 3706 | 1.4 | 2.8571 | 10.5882 | 20.3049 | 4.9167 | 4.8 | 1.4 | 3.5714 | 0.8 | 2.5 | 8.9286
| 3707 | 0.8 | 5 | 11.7391 | 20.4363 | 2.6971 | 6 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 3708 | 1 | 4 | 8.3077 | 15.1577 | 2.9317 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 3709 | 0.6 | 6.6667 | 10.3846 | 18.3345 | 3.776 | 4.1739 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 3710 | 0.8 | 5 | 12.2727 | 19.8824 | 2.4205 | 5.1892 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 3711 | 1 | 4 | 20.7692 | 28.6796 | 3.4453 | 4.4651 | 1 | 5 | 0.2 | 10 | 19
| 3712 | 0.2 | 20 | 10.5882 | 16.9426 | 3.4453 | 2.9091 | 1.4 | 3.5714 | 0.6 | 3.3333 | 26.9048
| 3713 | 0.6 | 6.6667 | 11.25 | 18.2487 | 2.9136 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 3714 | 0.4 | 10 | 9.4737 | 17.1251 | 2.7283 | 4.9231 | 1 | 5 | 0.2 | 10 | 25
| 3715 | 1 | 4 | 12.5581 | 23.1234 | 2.5652 | 8 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 3716 | 0.8 | 5 | 16.3636 | 24.6178 | 3.0649 | 5.1892 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 3717 | 0.8 | 5 | 11.0204 | 18.8721 | 3.9333 | 3.9184 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 3718 | 0.6 | 6.6667 | 11.4894 | 18.4145 | 3.2329 | 3.6923 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 3719 | 0.4 | 10 | 13.8462 | 22.0418 | 3.3957 | 4.8 | 0.2 | 25 | 0.6 | 3.3333 | 38.3333
| 3720 | 0.6 | 6.6667 | 17.4194 | 26.7599 | 3.5224 | 5.8182 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 3721 | 0.8 | 5 | 16.3636 | 27.1903 | 3.1467 | 7.68 | 1 | 5 | 0.4 | 5 | 15
| 3722 | 1 | 4 | 13.8462 | 20.5247 | 2.1071 | 4.5714 | 1 | 5 | 0.2 | 10 | 19
| 3723 | 1 | 4 | 8.0597 | 17.2254 | 3.3475 | 5.8182 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 3724 | 0.8 | 5 | 12 | 18.0843 | 2.5934 | 3.4909 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 3725 | 0.6 | 6.6667 | 14.2105 | 22.4575 | 3.3239 | 4.9231 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 3726 | 1.2 | 3.3333 | 11.0204 | 17.9112 | 3.5224 | 3.3684 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 3727 | 1.6 | 2.5 | 11.25 | 17.7435 | 3.0649 | 3.4286 | 1.2 | 4.1667 | 0.2 | 10 | 16.6667
| 3728 | 0.4 | 10 | 13.8462 | 21.1302 | 2.7126 | 4.5714 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 3729 | 1 | 4 | 10.8 | 19.3489 | 3.4963 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 3730 | 1.8 | 2.2222 | 8.4375 | 19.9962 | 3.2109 | 8.3478 | 1 | 5 | 0.4 | 5 | 12.2222
| 3731 | 1.4 | 2.8571 | 16.875 | 25.1291 | 3.0649 | 5.1892 | 0.8 | 6.25 | 0.8 | 2.5 | 11.6071
| 3732 | 0.8 | 5 | 14.5946 | 20.0289 | 2.6517 | 2.7826 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 3733 | 0.6 | 6.6667 | 11.4894 | 20.3473 | 3.2109 | 5.6471 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 3734 | 0.4 | 10 | 14.5946 | 23.2673 | 3.0256 | 5.6471 | 1 | 5 | 0.8 | 2.5 | 17.5
| 3735 | 0.4 | 10 | 11.25 | 20.673 | 4.3704 | 5.0526 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 3736 | 1.2 | 3.3333 | 12 | 18.457 | 3.1467 | 3.3103 | 1 | 5 | 0.4 | 5 | 13.3333
| 3737 | 0.8 | 5 | 11.0204 | 18.9906 | 2.6369 | 5.3333 | 1 | 5 | 0.2 | 10 | 20
| 3738 | 0.6 | 6.6667 | 15.4286 | 23.7969 | 3.4453 | 4.9231 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 3739 | 1.4 | 2.8571 | 11.4894 | 18.1639 | 3.4203 | 3.2542 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 3740 | 0.8 | 5 | 15 | 24.539 | 2.6818 | 6.8571 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 3741 | 0.8 | 5 | 18.6207 | 25.0556 | 3.0064 | 3.4286 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 3742 | 0.6 | 6.6667 | 9.3103 | 16.16 | 3.085 | 3.7647 | 1 | 5 | 0.6 | 3.3333 | 15
| 3743 | 1 | 4 | 19.2857 | 29.131 | 3.4453 | 6.4 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 3744 | 0.6 | 6.6667 | 10.1887 | 18.2057 | 4.177 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 3745 | 1 | 4 | 13.5 | 21.4832 | 3.7165 | 4.2667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 3746 | 1 | 4 | 12 | 19.6895 | 2.6369 | 5.0526 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 3747 | 0.8 | 5 | 9.3103 | 15.5892 | 2.9686 | 3.3103 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 3748 | 0.6 | 6.6667 | 11.0204 | 17.7877 | 2.5934 | 4.1739 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 3749 | 0.4 | 10 | 14.5946 | 21.4053 | 3.2552 | 3.5556 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 3750 | 0.4 | 10 | 9.4737 | 17.2574 | 2.8606 | 4.9231 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 3751 | 0.8 | 5 | 9.3103 | 15.4782 | 2.9136 | 3.2542 | 1 | 5 | 0.1 | 20 | 30
| 3752 | 1 | 4 | 11.4894 | 21.7174 | 2.8434 | 7.3846 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 3753 | 1 | 4 | 11.0204 | 20.7878 | 3.1467 | 6.6207 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 3754 | 0.4 | 10 | 13.8462 | 26.0314 | 3.8374 | 8.3478 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 3755 | 1 | 4 | 9.3103 | 16.7326 | 2.6222 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 3756 | 0.6 | 6.6667 | 9.3103 | 16.6078 | 3.8689 | 3.4286 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 3757 | 0.6 | 6.6667 | 7.8261 | 15.0165 | 3.1053 | 4.0851 | 1 | 5 | 0.1 | 20 | 31.6667
| 3758 | 0.6 | 6.6667 | 12.5581 | 17.1236 | 2.4082 | 2.1573 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 3759 | 0.4 | 10 | 9.1525 | 20.2778 | 3.4453 | 7.68 | 0.4 | 12.5 | 0.4 | 5 | 27.5
| 3760 | 0.8 | 5 | 15.8824 | 22.4229 | 2.6222 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 3761 | 0.6 | 6.6667 | 13.5 | 20.1834 | 2.8434 | 3.84 | 1 | 5 | 0.4 | 5 | 16.6667
| 3762 | 0.8 | 5 | 12 | 20.3983 | 3.0649 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 3763 | 0.6 | 6.6667 | 10.1887 | 19.2858 | 2.6971 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 3764 | 0.8 | 5 | 14.2105 | 24.473 | 4.069 | 6.1935 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 3765 | 0.4 | 10 | 9.4737 | 14.1103 | 2.1751 | 2.4615 | 1 | 5 | 0.2 | 10 | 25
| 3766 | 1 | 4 | 10.1887 | 18.1494 | 3.2778 | 4.6829 | 1 | 5 | 0.4 | 5 | 14
| 3767 | 0.8 | 5 | 10.5882 | 18.3946 | 3.0064 | 4.8 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 3768 | 0.4 | 10 | 16.875 | 25.5712 | 2.878 | 5.8182 | 0.4 | 12.5 | 0.4 | 5 | 27.5
| 3769 | 1 | 4 | 15.8824 | 25.4854 | 3.6031 | 6 | 1 | 5 | 0.1 | 20 | 29
| 3770 | 0.4 | 10 | 10.5882 | 18.4743 | 3.5224 | 4.3636 | 1 | 5 | 0.4 | 5 | 20
| 3771 | 0.6 | 6.6667 | 18 | 25.4077 | 2.6077 | 4.8 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 3772 | 0.8 | 5 | 8.8525 | 14.6344 | 2.2264 | 3.5556 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 3773 | 0.8 | 5 | 11.25 | 19.4493 | 3.1467 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 3774 | 1.2 | 3.3333 | 11.25 | 22.7989 | 3.5489 | 8 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 3775 | 1.2 | 3.3333 | 16.3636 | 24.1322 | 2.9686 | 4.8 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 3776 | 0.6 | 6.6667 | 10.5882 | 16.5788 | 3.3239 | 2.6667 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 3777 | 1.4 | 2.8571 | 11.4894 | 17.7918 | 2.3024 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 3778 | 1 | 4 | 8.5714 | 15.3676 | 2.6222 | 4.1739 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 3779 | 0.8 | 5 | 13.1707 | 19.6405 | 2.5514 | 3.9184 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 3780 | 0.6 | 6.6667 | 12.5581 | 21.5095 | 2.5514 | 6.4 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 3781 | 1 | 4 | 18 | 24.7884 | 3.2329 | 3.5556 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 3782 | 0.2 | 20 | 8.4375 | 14.697 | 2.6369 | 3.6226 | 1 | 5 | 0.4 | 5 | 30
| 3783 | 0.4 | 10 | 9.6429 | 20.6129 | 2.6222 | 8.3478 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 3784 | 0.6 | 6.6667 | 12.8571 | 22.7795 | 3.5224 | 6.4 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 3785 | 1 | 4 | 15.8824 | 21.3705 | 3.1467 | 2.3415 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 3786 | 1 | 4 | 24.5455 | 32.8813 | 3.1467 | 5.1892 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 3787 | 1.2 | 3.3333 | 9.8182 | 17.4696 | 2.7283 | 4.9231 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 3788 | 0.1 | 40 | 17.4194 | 26.6335 | 2.5934 | 6.6207 | 0.4 | 12.5 | 0.4 | 5 | 57.5
| 3789 | 0.8 | 5 | 14.2105 | 20.3816 | 3.3475 | 2.8235 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 3790 | 0.8 | 5 | 11.25 | 17.9498 | 3.6031 | 3.0968 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 3791 | 1.4 | 2.8571 | 13.1707 | 21.5241 | 3.3007 | 5.0526 | 0.8 | 6.25 | 0.1 | 20 | 29.1071
| 3792 | 0.8 | 5 | 9.8182 | 18.06 | 3.1892 | 5.0526 | 1 | 5 | 0.4 | 5 | 15
| 3793 | 0.6 | 6.6667 | 8.1818 | 17.6192 | 4.866 | 4.5714 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 3794 | 0.2 | 20 | 11.25 | 17.6924 | 2.5241 | 3.9184 | 0.6 | 8.3333 | 0.2 | 10 | 38.3333
| 3795 | 1 | 4 | 8.8525 | 15.6909 | 3.3475 | 3.4909 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 3796 | 1.2 | 3.3333 | 13.8462 | 22.4577 | 3.1258 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 3797 | 0.8 | 5 | 17.4194 | 25.9042 | 2.6667 | 5.8182 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 3798 | 0.6 | 6.6667 | 12.8571 | 22.5416 | 4.4952 | 5.1892 | 1 | 5 | 0.2 | 10 | 21.6667
| 3799 | 1 | 4 | 15 | 23.0731 | 3.8065 | 4.2667 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 3800 | 1 | 4 | 10.1887 | 19.6374 | 3.2552 | 6.1935 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 3801 | 1 | 4 | 15.8824 | 23.8082 | 3.1258 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 3802 | 1 | 4 | 8.8525 | 15.2886 | 3.1258 | 3.3103 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 3803 | 1.8 | 2.2222 | 12.8571 | 18.1961 | 2.9686 | 2.3704 | 1.2 | 4.1667 | 0.2 | 10 | 16.3889
| 3804 | 1.2 | 3.3333 | 12 | 19.4486 | 3.085 | 4.3636 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 3805 | 0.8 | 5 | 11.7391 | 19.509 | 4.2143 | 3.5556 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 3806 | 1 | 4 | 12 | 19.8365 | 3.3714 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 3807 | 2 | 2 | 8.1818 | 17.0775 | 2.8957 | 6 | 1 | 5 | 0.2 | 10 | 17
| 3808 | 0.8 | 5 | 14.5946 | 21.8528 | 2.2056 | 5.0526 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 3809 | 0.6 | 6.6667 | 9.4737 | 16.1188 | 2.4712 | 4.1739 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 3810 | 1.6 | 2.5 | 8.1818 | 24.3058 | 3.3239 | 12.8 | 1 | 5 | 0.8 | 2.5 | 10
| 3811 | 0.6 | 6.6667 | 12 | 19.9429 | 3.3714 | 4.5714 | 1.4 | 3.5714 | 0.8 | 2.5 | 12.7381
| 3812 | 1.2 | 3.3333 | 11.25 | 18.7718 | 3.2552 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 3813 | 0.2 | 20 | 14.2105 | 20.5359 | 3.2778 | 3.0476 | 1 | 5 | 0.4 | 5 | 30
| 3814 | 0.6 | 6.6667 | 7.5 | 17.226 | 3.1053 | 6.6207 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 3815 | 0.8 | 5 | 12.8571 | 19.2996 | 2.5241 | 3.9184 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 3816 | 1 | 4 | 15 | 22.9843 | 2.9317 | 5.0526 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 3817 | 1.4 | 2.8571 | 12.8571 | 19.786 | 2.5652 | 4.3636 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 3818 | 0.8 | 5 | 8.4375 | 15.5071 | 2.8957 | 4.1739 | 1 | 5 | 0.8 | 2.5 | 12.5
| 3819 | 0.4 | 10 | 15 | 23.2963 | 3.4963 | 4.8 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 3820 | 0.6 | 6.6667 | 12 | 19.6604 | 2.6077 | 5.0526 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 3821 | 0.4 | 10 | 14.5946 | 24.3298 | 2.878 | 6.8571 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 3822 | 1 | 4 | 8.1818 | 16.1852 | 2.1852 | 5.8182 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 3823 | 0.6 | 6.6667 | 12.2727 | 20.3903 | 3.0649 | 5.0526 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 3824 | 0.6 | 6.6667 | 12.8571 | 17.9668 | 3.0452 | 2.0645 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 3825 | 1 | 4 | 13.5 | 22.3434 | 2.8434 | 6 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 3826 | 0.4 | 10 | 12.8571 | 18.6206 | 2.6667 | 3.0968 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 3827 | 1 | 4 | 13.1707 | 19.6578 | 3.2329 | 3.2542 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 3828 | 0.4 | 10 | 13.1707 | 19.2357 | 3.0649 | 3 | 0.4 | 12.5 | 0.6 | 3.3333 | 25.8333
| 3829 | 0.8 | 5 | 12 | 18.1131 | 2.6222 | 3.4909 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 3830 | 0.8 | 5 | 9.3103 | 16.7589 | 2.3959 | 5.0526 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 3831 | 1 | 4 | 10.3846 | 17.8554 | 3.6308 | 3.84 | 1.6 | 3.125 | 0.6 | 3.3333 | 10.4583
| 3832 | 0.8 | 5 | 11.25 | 17.3008 | 2.6222 | 3.4286 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 3833 | 0.6 | 6.6667 | 15.4286 | 22.7722 | 2.4205 | 4.9231 | 1 | 5 | 0.1 | 20 | 31.6667
| 3834 | 1.2 | 3.3333 | 12.2727 | 18.1006 | 3.085 | 2.7429 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 3835 | 0.6 | 6.6667 | 11.4894 | 24.5097 | 3.4203 | 9.6 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 3836 | 1 | 4 | 22.5 | 29.7318 | 3.1467 | 4.0851 | 1 | 5 | 0.2 | 10 | 19
| 3837 | 0.6 | 6.6667 | 13.5 | 21.3548 | 2.9317 | 4.9231 | 1 | 5 | 0.2 | 10 | 21.6667
| 3838 | 0.8 | 5 | 10.8 | 20.4487 | 2.5376 | 7.1111 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 3839 | 0.2 | 20 | 10.3846 | 19.1136 | 3.3957 | 5.3333 | 1.6 | 3.125 | 0.8 | 2.5 | 25.625
| 3840 | 0.8 | 5 | 13.1707 | 19.6543 | 2.5652 | 3.9184 | 1 | 5 | 0.1 | 20 | 30
| 3841 | 0.6 | 6.6667 | 10.1887 | 17.4275 | 3.0649 | 4.1739 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 3842 | 0.6 | 6.6667 | 17.4194 | 26.8406 | 3.6031 | 5.8182 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 3843 | 0.4 | 10 | 14.2105 | 23.4034 | 2.7929 | 6.4 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 3844 | 0.4 | 10 | 20 | 27.8223 | 2.3366 | 5.4857 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 3845 | 1.2 | 3.3333 | 10.3846 | 17.6589 | 3.1892 | 4.0851 | 0.8 | 6.25 | 0.8 | 2.5 | 12.0833
| 3846 | 0.6 | 6.6667 | 10.8 | 16.9126 | 2.7442 | 3.3684 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 3847 | 1 | 4 | 12.8571 | 22.3077 | 2.5934 | 6.8571 | 1 | 5 | 0.2 | 10 | 19
| 3848 | 0.1 | 40 | 9.3103 | 18.7591 | 3.2552 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 49.1667
| 3849 | 1.2 | 3.3333 | 13.1707 | 21.9399 | 3.7165 | 5.0526 | 1 | 5 | 0.4 | 5 | 13.3333
| 3850 | 1 | 4 | 10.8 | 18.8552 | 3.2552 | 4.8 | 1 | 5 | 0.4 | 5 | 14
| 3851 | 0.4 | 10 | 13.8462 | 20.7493 | 3.2109 | 3.6923 | 1 | 5 | 0.4 | 5 | 20
| 3852 | 0.8 | 5 | 14.5946 | 20.0054 | 2.7442 | 2.6667 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 3853 | 1 | 4 | 11.7391 | 19.0707 | 3.0649 | 4.2667 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 3854 | 0.8 | 5 | 13.8462 | 21.527 | 4.2523 | 3.4286 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 3855 | 1 | 4 | 16.875 | 23.7675 | 4.069 | 2.8235 | 1 | 5 | 0.2 | 10 | 19
| 3856 | 1.2 | 3.3333 | 13.5 | 23.6855 | 4.5385 | 5.6471 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 3857 | 1.2 | 3.3333 | 11.0204 | 17.7679 | 2.3838 | 4.3636 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 3858 | 1.2 | 3.3333 | 8.5714 | 16.3087 | 3.4706 | 4.2667 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 3859 | 1.4 | 2.8571 | 11.4894 | 20.8767 | 2.9873 | 6.4 | 1 | 5 | 0.4 | 5 | 12.8571
| 3860 | 1.2 | 3.3333 | 12 | 19.8527 | 2.0345 | 5.8182 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 3861 | 0.2 | 20 | 15.4286 | 22.6907 | 2.5792 | 4.6829 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 3862 | 1 | 4 | 10.5882 | 18.9171 | 2.6818 | 5.6471 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 3863 | 0.6 | 6.6667 | 15.8824 | 24.02 | 3.085 | 5.0526 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 3864 | 1.2 | 3.3333 | 16.875 | 27.3333 | 2.4583 | 8 | 1 | 5 | 0.4 | 5 | 13.3333
| 3865 | 1 | 4 | 12.5581 | 20.5981 | 2.9873 | 5.0526 | 1 | 5 | 0.1 | 20 | 29
| 3866 | 0.4 | 10 | 11.7391 | 18.6891 | 2.95 | 4 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 3867 | 0.8 | 5 | 16.875 | 24.1886 | 3.5489 | 3.7647 | 1.8 | 2.7778 | 0.2 | 10 | 17.7778
| 3868 | 0.4 | 10 | 10 | 17.8599 | 3.4963 | 4.3636 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 3869 | 1.6 | 2.5 | 12.8571 | 19.4191 | 3.0064 | 3.5556 | 1 | 5 | 0.4 | 5 | 12.5
| 3870 | 0.8 | 5 | 13.1707 | 19.4712 | 2.8095 | 3.4909 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 3871 | 0.8 | 5 | 10.8 | 18.4192 | 3.4453 | 4.1739 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 3872 | 0.6 | 6.6667 | 14.5946 | 21.5421 | 3.2552 | 3.6923 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 3873 | 0.4 | 10 | 15 | 22.8088 | 3.1258 | 4.6829 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 3874 | 0.6 | 6.6667 | 14.2105 | 20.8805 | 3.5224 | 3.1475 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 3875 | 1.2 | 3.3333 | 19.2857 | 26.9752 | 2.6369 | 5.0526 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 3876 | 0.8 | 5 | 8.7097 | 17.497 | 4.1043 | 4.6829 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 3877 | 0.6 | 6.6667 | 11.4894 | 20.1856 | 2.878 | 5.8182 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 3878 | 0.6 | 6.6667 | 9.6429 | 18.4586 | 2.6222 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 3879 | 0.8 | 5 | 20.7692 | 27.3949 | 3.3714 | 3.2542 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 3880 | 1.4 | 2.8571 | 16.3636 | 23.6793 | 2.7442 | 4.5714 | 0.6 | 8.3333 | 0.4 | 5 | 16.1905
| 3881 | 1 | 4 | 15.8824 | 22.0236 | 2.7126 | 3.4286 | 1 | 5 | 0.4 | 5 | 14
| 3882 | 0.6 | 6.6667 | 12.2727 | 22.0004 | 4.5385 | 5.1892 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 3883 | 1.4 | 2.8571 | 16.3636 | 24.5112 | 3.3475 | 4.8 | 1 | 5 | 0.4 | 5 | 12.8571
| 3884 | 0.8 | 5 | 12.8571 | 21.4794 | 2.6222 | 6 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 3885 | 0.8 | 5 | 9.6429 | 16.6473 | 2.433 | 4.5714 | 1.4 | 3.5714 | 0.8 | 2.5 | 11.0714
| 3886 | 0.6 | 6.6667 | 13.1707 | 18.6681 | 2.4974 | 3 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 3887 | 0.8 | 5 | 8.8525 | 16.5497 | 3.1258 | 4.5714 | 1 | 5 | 0.1 | 20 | 30
| 3888 | 0.6 | 6.6667 | 11.25 | 19.6097 | 2.7126 | 5.6471 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 3889 | 0.6 | 6.6667 | 9.3103 | 19.4552 | 2.7602 | 7.3846 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 3890 | 0.8 | 5 | 12.2727 | 19.7394 | 2.6667 | 4.8 | 1 | 5 | 0.1 | 20 | 30
| 3891 | 1 | 4 | 11.25 | 16.4467 | 2.8263 | 2.3704 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 3892 | 0.8 | 5 | 11.4894 | 18.5056 | 3.3239 | 3.6923 | 1 | 5 | 0.4 | 5 | 15
| 3893 | 0.4 | 10 | 8.7097 | 16.7794 | 3.1467 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 3894 | 0.6 | 6.6667 | 8.1818 | 15.9829 | 2.878 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 3895 | 0.6 | 6.6667 | 10.3846 | 18.3141 | 3.0064 | 4.9231 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 3896 | 1 | 4 | 18 | 26.5662 | 3.2329 | 5.3333 | 0.4 | 12.5 | 0.8 | 2.5 | 19
| 3897 | 1.2 | 3.3333 | 11.0204 | 17.6721 | 2.6517 | 4 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 3898 | 1 | 4 | 16.3636 | 22.4154 | 3.3475 | 2.7042 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 3899 | 1.2 | 3.3333 | 10.8 | 20.3892 | 2.9686 | 6.6207 | 0.4 | 12.5 | 0.8 | 2.5 | 18.3333
| 3900 | 0.4 | 10 | 9.8182 | 18.7546 | 3.6031 | 5.3333 | 1 | 5 | 0.1 | 20 | 35
| 3901 | 0.6 | 6.6667 | 14.2105 | 20.0047 | 3.3007 | 2.4935 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 3902 | 0.4 | 10 | 9.8182 | 16.819 | 3.4453 | 3.5556 | 1 | 5 | 0.4 | 5 | 20
| 3903 | 0.6 | 6.6667 | 13.1707 | 19.274 | 2.7929 | 3.3103 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 3904 | 1 | 4 | 12.5581 | 18.7642 | 2.8957 | 3.3103 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 3905 | 1 | 4 | 11.25 | 18.4843 | 2.5514 | 4.6829 | 1 | 5 | 0.2 | 10 | 19
| 3906 | 0.8 | 5 | 15.4286 | 22.878 | 2.878 | 4.5714 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 3907 | 1.2 | 3.3333 | 10.3846 | 18.0548 | 3.4963 | 4.1739 | 1 | 5 | 0.2 | 10 | 18.3333
| 3908 | 0.4 | 10 | 14.5946 | 24.8928 | 2.9136 | 7.3846 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 3909 | 1 | 4 | 11.7391 | 19.5076 | 2.5792 | 5.1892 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 3910 | 0.8 | 5 | 8.7097 | 19.396 | 3.0064 | 7.68 | 1.4 | 3.5714 | 0.1 | 20 | 28.5714
| 3911 | 1 | 4 | 8.5714 | 15.6837 | 3.3475 | 3.7647 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 3912 | 0.6 | 6.6667 | 8.4375 | 17.6234 | 2.5652 | 6.6207 | 1 | 5 | 0.1 | 20 | 31.6667
| 3913 | 1.8 | 2.2222 | 15 | 22.6146 | 2.9317 | 4.6829 | 1.4 | 3.5714 | 0.4 | 5 | 10.7937
| 3914 | 1 | 4 | 11.7391 | 18.5499 | 2.6369 | 4.1739 | 0.6 | 8.3333 | 0.1 | 20 | 32.3333
| 3915 | 1.4 | 2.8571 | 11.4894 | 19.8872 | 4.0342 | 4.3636 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 3916 | 1.2 | 3.3333 | 18 | 24.5166 | 3.0256 | 3.4909 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 3917 | 0.6 | 6.6667 | 9.3103 | 16.7071 | 2.9317 | 4.4651 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 3918 | 0.8 | 5 | 11.4894 | 19.0708 | 3.4963 | 4.0851 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 3919 | 0.4 | 10 | 9.8182 | 16.5643 | 3.2552 | 3.4909 | 1 | 5 | 0.1 | 20 | 35
| 3920 | 0.8 | 5 | 12.5581 | 19.1889 | 3.6308 | 3 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 3921 | 1.2 | 3.3333 | 12 | 18.7556 | 3.4453 | 3.3103 | 1.6 | 3.125 | 0.1 | 20 | 26.4583
| 3922 | 1.2 | 3.3333 | 13.5 | 22.2409 | 3.2552 | 5.4857 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 3923 | 1.4 | 2.8571 | 11.0204 | 19.8074 | 2.5934 | 6.1935 | 1 | 5 | 0.4 | 5 | 12.8571
| 3924 | 1 | 4 | 9.8182 | 19.2634 | 3.4453 | 6 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 3925 | 0.8 | 5 | 12.8571 | 18.9737 | 2.1166 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 3926 | 0.6 | 6.6667 | 10.3846 | 18.6924 | 3.2552 | 5.0526 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 3927 | 1.2 | 3.3333 | 12.2727 | 23.7592 | 3.8065 | 7.68 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 3928 | 0.8 | 5 | 11.25 | 16.6777 | 2.2802 | 3.1475 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 3929 | 1 | 4 | 10.8 | 17.6319 | 2.9136 | 3.9184 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 3930 | 0.6 | 6.6667 | 10.8 | 17.6134 | 2.3483 | 4.4651 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 3931 | 1.4 | 2.8571 | 12.8571 | 20.6069 | 2.6971 | 5.0526 | 1.4 | 3.5714 | 0.2 | 10 | 16.4286
| 3932 | 1 | 4 | 14.5946 | 21.3093 | 2.95 | 3.7647 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 3933 | 0.4 | 10 | 10.1887 | 21.8383 | 4.5385 | 7.1111 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 3934 | 0.4 | 10 | 13.5 | 20.5779 | 3.5224 | 3.5556 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 3935 | 0.2 | 20 | 18.6207 | 24.9221 | 3.3475 | 2.9538 | 1.2 | 4.1667 | 0.6 | 3.3333 | 27.5
| 3936 | 0.2 | 20 | 15.4286 | 22.9044 | 2.7929 | 4.6829 | 1 | 5 | 1 | 2 | 27
| 3937 | 0.6 | 6.6667 | 11.25 | 18.4124 | 2.8957 | 4.2667 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 3938 | 0.6 | 6.6667 | 14.2105 | 20.2158 | 2.6369 | 3.3684 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 3939 | 0.6 | 6.6667 | 18 | 25.5748 | 2.6517 | 4.9231 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 3940 | 0.2 | 20 | 15 | 23.8799 | 3.2329 | 5.6471 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 3941 | 0.4 | 10 | 8.0597 | 15.8091 | 2.8263 | 4.9231 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 3942 | 0.6 | 6.6667 | 11.7391 | 17.0513 | 3.1053 | 2.2069 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 3943 | 1.4 | 2.8571 | 9.8182 | 15.9187 | 3.1467 | 2.9538 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 3944 | 1 | 4 | 10.3846 | 18.3033 | 2.433 | 5.4857 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 3945 | 0.8 | 5 | 15 | 21.7126 | 2.7126 | 4 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 3946 | 0.6 | 6.6667 | 12.8571 | 19.9624 | 3.1053 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 3947 | 0.8 | 5 | 7.3973 | 13.5608 | 2.4712 | 3.6923 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 3948 | 1.2 | 3.3333 | 12 | 19.5909 | 3.1258 | 4.4651 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 3949 | 1.2 | 3.3333 | 10.1887 | 18.4357 | 3.3239 | 4.9231 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 3950 | 0.6 | 6.6667 | 14.5946 | 22.2713 | 3.1053 | 4.5714 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 3951 | 0.6 | 6.6667 | 10.8 | 20.2713 | 3.2778 | 6.1935 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 3952 | 0.8 | 5 | 11.4894 | 20.1865 | 2.6971 | 6 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 3953 | 1 | 4 | 10 | 18.7126 | 2.7126 | 6 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 3954 | 1.2 | 3.3333 | 9.6429 | 17.2186 | 3.5758 | 4 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 3955 | 1 | 4 | 16.875 | 23.1277 | 2.6971 | 3.5556 | 1 | 5 | 0.2 | 10 | 19
| 3956 | 1.4 | 2.8571 | 13.5 | 19.7351 | 2.7442 | 3.4909 | 1 | 5 | 0.4 | 5 | 12.8571
| 3957 | 1.6 | 2.5 | 10.5882 | 17.2943 | 3.3957 | 3.3103 | 1.2 | 4.1667 | 0.4 | 5 | 11.6667
| 3958 | 1 | 4 | 11.4894 | 19.5392 | 2.8606 | 5.1892 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 3959 | 0.6 | 6.6667 | 11.25 | 22.5565 | 2.5792 | 8.7273 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 3960 | 1.2 | 3.3333 | 10.5882 | 19.9199 | 2.9317 | 6.4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 3961 | 1.2 | 3.3333 | 11.7391 | 18.3805 | 3.6875 | 2.9538 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 3962 | 0.8 | 5 | 11.25 | 18.4303 | 2.4974 | 4.6829 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 3963 | 1 | 4 | 12.8571 | 19.8286 | 3.6031 | 3.3684 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 3964 | 0.2 | 20 | 11.4894 | 20.9723 | 2.3719 | 7.1111 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 3965 | 0.6 | 6.6667 | 14.2105 | 21.6442 | 2.9686 | 4.4651 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 3966 | 1 | 4 | 9.8182 | 16.9399 | 3.6308 | 3.4909 | 1 | 5 | 0.4 | 5 | 14
| 3967 | 0.2 | 20 | 12 | 21.2785 | 3.085 | 6.1935 | 1 | 5 | 0.8 | 2.5 | 27.5
| 3968 | 0.8 | 5 | 12.2727 | 19.4293 | 2.7929 | 4.3636 | 1 | 5 | 0.8 | 2.5 | 12.5
| 3969 | 0.6 | 6.6667 | 12.2727 | 19.2599 | 3.4963 | 3.4909 | 1 | 5 | 0.4 | 5 | 16.6667
| 3970 | 1.2 | 3.3333 | 15.4286 | 21.8237 | 3.8689 | 2.5263 | 1.6 | 3.125 | 0.4 | 5 | 11.4583
| 3971 | 0.4 | 10 | 15.8824 | 24.1961 | 2.6667 | 5.6471 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 3972 | 0.8 | 5 | 12.2727 | 18.7908 | 2.433 | 4.0851 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 3973 | 0.6 | 6.6667 | 11.7391 | 20.7737 | 3.5489 | 5.4857 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 3974 | 0.6 | 6.6667 | 8.8525 | 15.4814 | 4.069 | 2.56 | 1.6 | 3.125 | 0.6 | 3.3333 | 13.125
| 3975 | 1.2 | 3.3333 | 12 | 19.0955 | 2.5241 | 4.5714 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 3976 | 0.2 | 20 | 14.5946 | 21.7312 | 2.3366 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 3977 | 0.6 | 6.6667 | 11.7391 | 18.9994 | 3.4203 | 3.84 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 3978 | 0.4 | 10 | 14.5946 | 25.555 | 3.5758 | 7.3846 | 1 | 5 | 0.2 | 10 | 25
| 3979 | 0.4 | 10 | 11.7391 | 21.5836 | 2.9873 | 6.8571 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 3980 | 0.6 | 6.6667 | 16.875 | 24.8667 | 3.4203 | 4.5714 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 3981 | 0.8 | 5 | 8.8525 | 17.5059 | 3.0064 | 5.6471 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 3982 | 1.4 | 2.8571 | 12.2727 | 18.3195 | 2.95 | 3.0968 | 1.4 | 3.5714 | 0.4 | 5 | 11.4286
| 3983 | 1 | 4 | 12.8571 | 19.3404 | 2.8606 | 3.6226 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 3984 | 1 | 4 | 8.4375 | 16.8858 | 3.3957 | 5.0526 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 3985 | 1.2 | 3.3333 | 11.4894 | 18.7891 | 2.7283 | 4.5714 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 3986 | 0.4 | 10 | 11.0204 | 18.8465 | 2.6369 | 5.1892 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 3987 | 0.4 | 10 | 10 | 17.389 | 3.4706 | 3.9184 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 3988 | 1 | 4 | 16.875 | 23.3523 | 2.7126 | 3.7647 | 1 | 5 | 0.8 | 2.5 | 11.5
| 3989 | 0.8 | 5 | 11.4894 | 17.5178 | 2.9317 | 3.0968 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 3990 | 0.4 | 10 | 15.8824 | 23.8824 | 2.6667 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 3991 | 0.8 | 5 | 16.3636 | 23.7788 | 2.95 | 4.4651 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 3992 | 0.4 | 10 | 10.8 | 19.4111 | 3.2778 | 5.3333 | 1.2 | 4.1667 | 0.1 | 20 | 34.1667
| 3993 | 0.2 | 20 | 16.3636 | 21.9765 | 2.5652 | 3.0476 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 3994 | 1.2 | 3.3333 | 13.5 | 20.4758 | 3.4203 | 3.5556 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 3995 | 1.4 | 2.8571 | 11.7391 | 18.7029 | 2.6971 | 4.2667 | 0.6 | 8.3333 | 0.4 | 5 | 16.1905
| 3996 | 0.8 | 5 | 12.5581 | 23.7493 | 2.8434 | 8.3478 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 3997 | 0.6 | 6.6667 | 14.2105 | 20.0373 | 2.4583 | 3.3684 | 1.4 | 3.5714 | 0.8 | 2.5 | 12.7381
| 3998 | 0.8 | 5 | 13.5 | 19.1035 | 2.8606 | 2.7429 | 1 | 5 | 0.2 | 10 | 20
| 3999 | 1.2 | 3.3333 | 13.1707 | 19.5526 | 2.8263 | 3.5556 | 1 | 5 | 1 | 2 | 10.3333
| 4000 | 0.4 | 10 | 10.3846 | 18.0627 | 2.878 | 4.8 | 0.4 | 12.5 | 0.2 | 10 | 32.5
| 4001 | 1.4 | 2.8571 | 10.8 | 17.1 | 2.6077 | 3.6923 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 4002 | 0.8 | 5 | 12.5581 | 19.2415 | 2.8434 | 3.84 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 4003 | 1.4 | 2.8571 | 12.8571 | 19.2861 | 2.5106 | 3.9184 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 4004 | 1 | 4 | 10.1887 | 17.4427 | 2.9873 | 4.2667 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 4005 | 0.6 | 6.6667 | 9.4737 | 15.2729 | 2.6517 | 3.1475 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 4006 | 0.1 | 40 | 10.5882 | 16.151 | 2.6971 | 2.8657 | 0.6 | 8.3333 | 0.2 | 10 | 58.3333
| 4007 | 0.8 | 5 | 13.5 | 23.4624 | 3.1053 | 6.8571 | 1 | 5 | 0.1 | 20 | 30
| 4008 | 1 | 4 | 12 | 19.3016 | 3.746 | 3.5556 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 4009 | 1.2 | 3.3333 | 12 | 19.2369 | 3.746 | 3.4909 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 4010 | 0.8 | 5 | 9 | 17.8602 | 2.6667 | 6.1935 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 4011 | 0.4 | 10 | 13.5 | 21.3649 | 3.0649 | 4.8 | 1 | 5 | 0.1 | 20 | 35
| 4012 | 0.8 | 5 | 10 | 18.4241 | 3.3714 | 5.0526 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 4013 | 0.8 | 5 | 11.4894 | 18.3709 | 3.1892 | 3.6923 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 4014 | 0.2 | 20 | 8.8525 | 17.9808 | 2.7283 | 6.4 | 1 | 5 | 0.4 | 5 | 30
| 4015 | 1.4 | 2.8571 | 15 | 21.8497 | 3.085 | 3.7647 | 1 | 5 | 0.8 | 2.5 | 10.3571
| 4016 | 0.2 | 20 | 12.8571 | 19.0764 | 2.7283 | 3.4909 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 4017 | 0.4 | 10 | 15.4286 | 23.0829 | 3.1892 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 4018 | 0.8 | 5 | 11.25 | 17.679 | 2.5106 | 3.9184 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 4019 | 0.6 | 6.6667 | 10.3846 | 18.2112 | 3.2552 | 4.5714 | 1 | 5 | 0.2 | 10 | 21.6667
| 4020 | 0.6 | 6.6667 | 13.1707 | 22.2834 | 2.7126 | 6.4 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 4021 | 1.4 | 2.8571 | 13.1707 | 20.201 | 3.776 | 3.2542 | 1 | 5 | 0.4 | 5 | 12.8571
| 4022 | 0.8 | 5 | 12.5581 | 20.1147 | 3.7165 | 3.84 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 4023 | 0.4 | 10 | 9.8182 | 17.5493 | 3.9664 | 3.7647 | 1.6 | 3.125 | 0.1 | 20 | 33.125
| 4024 | 0.6 | 6.6667 | 12.8571 | 21.6934 | 3.1892 | 5.6471 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 4025 | 0.8 | 5 | 12.5581 | 17.9749 | 2.2692 | 3.1475 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 4026 | 0.2 | 20 | 10.1887 | 15.9296 | 2.5934 | 3.1475 | 1.6 | 3.125 | 0.4 | 5 | 28.125
| 4027 | 1.2 | 3.3333 | 11.0204 | 19.1971 | 2.8434 | 5.3333 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 4028 | 0.4 | 10 | 12 | 18.2528 | 3.1053 | 3.1475 | 1 | 5 | 0.4 | 5 | 20
| 4029 | 1 | 4 | 15.4286 | 21.9686 | 3.7165 | 2.8235 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 4030 | 0.4 | 10 | 19.2857 | 27.1431 | 2.5241 | 5.3333 | 1 | 5 | 0.4 | 5 | 20
| 4031 | 0.2 | 20 | 11.7391 | 18.1725 | 2.3483 | 4.0851 | 1 | 5 | 0.2 | 10 | 35
| 4032 | 0.4 | 10 | 11.4894 | 18.1599 | 3.4706 | 3.2 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 4033 | 0.6 | 6.6667 | 13.5 | 21.9194 | 3.4963 | 4.9231 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 4034 | 1.2 | 3.3333 | 17.4194 | 23.2338 | 2.8606 | 2.9538 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 4035 | 0.8 | 5 | 9.4737 | 19.7526 | 3.1678 | 7.1111 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 4036 | 0.6 | 6.6667 | 15 | 26.3495 | 2.6222 | 8.7273 | 1 | 5 | 0.4 | 5 | 16.6667
| 4037 | 1 | 4 | 11.4894 | 21.836 | 2.6667 | 7.68 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 4038 | 0.8 | 5 | 12 | 21.6308 | 3.6308 | 6 | 1 | 5 | 0.2 | 10 | 20
| 4039 | 0.8 | 5 | 12.2727 | 19.7503 | 3.2109 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 4040 | 0.4 | 10 | 13.8462 | 21.4427 | 2.9136 | 4.6829 | 1 | 5 | 0.4 | 5 | 20
| 4041 | 0.4 | 10 | 11.4894 | 17.4767 | 2.9873 | 3 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 4042 | 0.8 | 5 | 10.1887 | 17.1779 | 2.5241 | 4.4651 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 4043 | 0.4 | 10 | 10.3846 | 17.4881 | 2.4205 | 4.6829 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 4044 | 1.4 | 2.8571 | 8.4375 | 18.0711 | 2.7765 | 6.8571 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 4045 | 1 | 4 | 12.5581 | 22.1473 | 3.1892 | 6.4 | 1 | 5 | 0.4 | 5 | 14
| 4046 | 0.2 | 20 | 11.25 | 18.6143 | 2.7929 | 4.5714 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 4047 | 0.4 | 10 | 12.8571 | 20.6257 | 2.9686 | 4.8 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 4048 | 1.4 | 2.8571 | 13.8462 | 20.2623 | 2.8606 | 3.5556 | 1 | 5 | 0.4 | 5 | 12.8571
| 4049 | 0.8 | 5 | 12.5581 | 23.2553 | 2.6971 | 8 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 4050 | 0.8 | 5 | 10 | 16.7976 | 3.1053 | 3.6923 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 4051 | 0.6 | 6.6667 | 8.4375 | 14.5225 | 3.085 | 3 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 4052 | 1 | 4 | 9.8182 | 16.3934 | 3.1467 | 3.4286 | 1 | 5 | 0.2 | 10 | 19
| 4053 | 0.8 | 5 | 15.8824 | 26.3095 | 3.8065 | 6.6207 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 4054 | 0.8 | 5 | 15.8824 | 23.6938 | 2.6222 | 5.1892 | 1 | 5 | 0.4 | 5 | 15
| 4055 | 0.6 | 6.6667 | 20.7692 | 27.4002 | 2.7126 | 3.9184 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 4056 | 0.2 | 20 | 20 | 26.2983 | 2.4583 | 3.84 | 1 | 5 | 0.8 | 2.5 | 27.5
| 4057 | 0.8 | 5 | 17.4194 | 25.7682 | 2.1553 | 6.1935 | 1 | 5 | 0.4 | 5 | 15
| 4058 | 0.6 | 6.6667 | 12.8571 | 19.55 | 2.6077 | 4.0851 | 2 | 2.5 | 0.4 | 5 | 14.1667
| 4059 | 0.4 | 10 | 10 | 20.6549 | 4.0342 | 6.6207 | 1.4 | 3.5714 | 0.8 | 2.5 | 16.0714
| 4060 | 0.8 | 5 | 10 | 17.8697 | 3.6031 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 4061 | 1.4 | 2.8571 | 11.7391 | 19.087 | 2.7765 | 4.5714 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 4062 | 1 | 4 | 9.8182 | 16.6882 | 3.1053 | 3.7647 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 4063 | 0.4 | 10 | 13.1707 | 24.1581 | 2.9873 | 8 | 1 | 5 | 0.4 | 5 | 20
| 4064 | 0.6 | 6.6667 | 14.5946 | 23.6865 | 2.4712 | 6.6207 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 4065 | 0.8 | 5 | 15 | 25.0797 | 2.9686 | 7.1111 | 1 | 5 | 0.2 | 10 | 20
| 4066 | 0.8 | 5 | 12.8571 | 19.2161 | 2.6667 | 3.6923 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 4067 | 0.6 | 6.6667 | 13.5 | 18.1728 | 2.3024 | 2.3704 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 4068 | 0.6 | 6.6667 | 12.2727 | 20.7834 | 2.5106 | 6 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 4069 | 1 | 4 | 12.5581 | 18.711 | 3.1053 | 3.0476 | 1 | 5 | 0.2 | 10 | 19
| 4070 | 0.1 | 40 | 17.4194 | 27.4518 | 4.2143 | 5.8182 | 1.4 | 3.5714 | 0.6 | 3.3333 | 46.9048
| 4071 | 1.6 | 2.5 | 16.3636 | 23.5037 | 2.7765 | 4.3636 | 1.2 | 4.1667 | 0.4 | 5 | 11.6667
| 4072 | 1 | 4 | 8.8525 | 14.511 | 2.7929 | 2.8657 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 4073 | 1.2 | 3.3333 | 9.3103 | 21.1226 | 3.085 | 8.7273 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 4074 | 0.8 | 5 | 12.8571 | 26.0273 | 3.0649 | 10.1053 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 4075 | 0.8 | 5 | 10.5882 | 17.6233 | 2.95 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 4076 | 0.6 | 6.6667 | 15 | 22.2373 | 3.8689 | 3.3684 | 1 | 5 | 0.4 | 5 | 16.6667
| 4077 | 0.8 | 5 | 8.7097 | 15.3614 | 2.6517 | 4 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 4078 | 0.6 | 6.6667 | 13.5 | 20.2773 | 2.5106 | 4.2667 | 1 | 5 | 0.4 | 5 | 16.6667
| 4079 | 0.4 | 10 | 12.2727 | 18.0673 | 2.4842 | 3.3103 | 1 | 5 | 0.2 | 10 | 25
| 4080 | 0.4 | 10 | 20 | 26.7617 | 2.8434 | 3.9184 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 4081 | 0.4 | 10 | 13.5 | 21.4987 | 2.8095 | 5.1892 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 4082 | 0.4 | 10 | 12.5581 | 23.3384 | 3.3957 | 7.3846 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 4083 | 1.2 | 3.3333 | 13.1707 | 22.2206 | 3.7165 | 5.3333 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 4084 | 1 | 4 | 14.5946 | 21.1164 | 2.6818 | 3.84 | 1 | 5 | 0.1 | 20 | 29
| 4085 | 0.8 | 5 | 10.1887 | 18.7647 | 3.776 | 4.8 | 1.6 | 3.125 | 0.2 | 10 | 18.125
| 4086 | 0.6 | 6.6667 | 18.6207 | 27.3993 | 3.4453 | 5.3333 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 4087 | 1.2 | 3.3333 | 12.8571 | 18.3664 | 3.1678 | 2.3415 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 4088 | 0.4 | 10 | 13.8462 | 21.1182 | 3.7165 | 3.5556 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 4089 | 0.4 | 10 | 12.2727 | 20.8477 | 3.5224 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 4090 | 0.4 | 10 | 14.5946 | 23.8934 | 3.1053 | 6.1935 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 4091 | 0.8 | 5 | 19.2857 | 27.2214 | 3.4706 | 4.4651 | 1.6 | 3.125 | 0.6 | 3.3333 | 11.4583
| 4092 | 0.8 | 5 | 10.5882 | 16.454 | 2.4974 | 3.3684 | 1 | 5 | 0.4 | 5 | 15
| 4093 | 0.6 | 6.6667 | 15 | 23.6794 | 4.2143 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 4094 | 1 | 4 | 13.1707 | 22.8171 | 3.0256 | 6.6207 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 4095 | 0.6 | 6.6667 | 13.1707 | 19.7391 | 2.7283 | 3.84 | 1.6 | 3.125 | 0.4 | 5 | 14.7917
| 4096 | 0.8 | 5 | 9.8182 | 18.783 | 3.1467 | 5.8182 | 0.4 | 12.5 | 0.6 | 3.3333 | 20.8333
| 4097 | 0.4 | 10 | 12.5581 | 22.9245 | 3.9664 | 6.4 | 1 | 5 | 0.4 | 5 | 20
| 4098 | 0.6 | 6.6667 | 10.8 | 16.3844 | 2.216 | 3.3684 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 4099 | 0.8 | 5 | 13.1707 | 21.2485 | 3.2778 | 4.8 | 1 | 5 | 0.2 | 10 | 20
| 4100 | 0.8 | 5 | 14.5946 | 26.4501 | 2.7126 | 9.1429 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 4101 | 1.2 | 3.3333 | 12.2727 | 19.2911 | 3.3957 | 3.6226 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 4102 | 0.6 | 6.6667 | 16.3636 | 23.7788 | 2.95 | 4.4651 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 4103 | 0.8 | 5 | 9 | 19.5757 | 2.8957 | 7.68 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 4104 | 0.8 | 5 | 14.5946 | 22.0704 | 2.7929 | 4.6829 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 4105 | 0.8 | 5 | 12.5581 | 20.3921 | 2.3483 | 5.4857 | 1.4 | 3.5714 | 0.1 | 20 | 28.5714
| 4106 | 0.6 | 6.6667 | 11.7391 | 19.3205 | 3.4963 | 4.0851 | 1 | 5 | 0.2 | 10 | 21.6667
| 4107 | 0.6 | 6.6667 | 11.0204 | 18.9818 | 3.4963 | 4.4651 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 4108 | 1.4 | 2.8571 | 11.7391 | 18.4017 | 2.7442 | 3.9184 | 1 | 5 | 0.2 | 10 | 17.8571
| 4109 | 0.6 | 6.6667 | 12 | 18.7018 | 3.2109 | 3.4909 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 4110 | 1.2 | 3.3333 | 13.1707 | 19.1423 | 3.4453 | 2.5263 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 4111 | 1.6 | 2.5 | 12.8571 | 20.5704 | 2.5241 | 5.1892 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.0833
| 4112 | 1 | 4 | 10.5882 | 18.9089 | 2.9873 | 5.3333 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 4113 | 1 | 4 | 12.5581 | 25.969 | 2.7442 | 10.6667 | 1.6 | 3.125 | 0.6 | 3.3333 | 10.4583
| 4114 | 0.2 | 20 | 13.5 | 21.9174 | 2.9317 | 5.4857 | 0.6 | 8.3333 | 0.2 | 10 | 38.3333
| 4115 | 1 | 4 | 9.4737 | 17.8037 | 3.9664 | 4.3636 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 4116 | 0.4 | 10 | 11.0204 | 19.0191 | 2.8095 | 5.1892 | 1.6 | 3.125 | 0.8 | 2.5 | 15.625
| 4117 | 0.8 | 5 | 11.4894 | 18.3898 | 3.2778 | 3.6226 | 0.8 | 6.25 | 1 | 2 | 13.25
| 4118 | 1.4 | 2.8571 | 13.5 | 20.2115 | 2.5376 | 4.1739 | 0.6 | 8.3333 | 0.6 | 3.3333 | 14.5238
| 4119 | 1 | 4 | 15 | 21.8263 | 2.8263 | 4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 4120 | 1.2 | 3.3333 | 9.3103 | 17.6526 | 2.5241 | 5.8182 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 4121 | 1.2 | 3.3333 | 16.875 | 24.0897 | 3.5224 | 3.6923 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 4122 | 0.6 | 6.6667 | 10.1887 | 17.486 | 2.4974 | 4.8 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 4123 | 1 | 4 | 9.6429 | 19.3588 | 3.5224 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 4124 | 0.2 | 20 | 10.3846 | 16.3924 | 2.5792 | 3.4286 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 4125 | 0.6 | 6.6667 | 15.8824 | 20.2783 | 2.3959 | 2 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 4126 | 0.8 | 5 | 12.5581 | 20.1547 | 3.2329 | 4.3636 | 1.4 | 3.5714 | 1 | 2 | 10.5714
| 4127 | 1.2 | 3.3333 | 7.5 | 14.2572 | 3.0649 | 3.6923 | 0.8 | 6.25 | 0.8 | 2.5 | 12.0833
| 4128 | 0.4 | 10 | 23.4783 | 31.1985 | 3.2552 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 4129 | 1.2 | 3.3333 | 10.3846 | 17.2037 | 2.2476 | 4.5714 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 4130 | 0.6 | 6.6667 | 10.8 | 18.3031 | 2.9317 | 4.5714 | 1 | 5 | 0.4 | 5 | 16.6667
| 4131 | 0.4 | 10 | 14.5946 | 24.5628 | 3.3475 | 6.6207 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 4132 | 0.8 | 5 | 10.5882 | 18.5757 | 3.5224 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 4133 | 0.8 | 5 | 14.2105 | 23.8869 | 2.5652 | 7.1111 | 1 | 5 | 0.8 | 2.5 | 12.5
| 4134 | 0.6 | 6.6667 | 13.5 | 21.5627 | 4.3704 | 3.6923 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 4135 | 0.8 | 5 | 14.2105 | 22.304 | 2.6077 | 5.4857 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 4136 | 0.8 | 5 | 14.5946 | 20.4859 | 3.0256 | 2.8657 | 1 | 5 | 0.4 | 5 | 15
| 4137 | 0.2 | 20 | 12.2727 | 20.1665 | 3.2109 | 4.6829 | 0.4 | 12.5 | 0.2 | 10 | 42.5
| 4138 | 0.6 | 6.6667 | 11.0204 | 19.3508 | 3.2778 | 5.0526 | 1 | 5 | 0.6 | 3.3333 | 15
| 4139 | 0.2 | 20 | 11.0204 | 20.4428 | 2.5652 | 6.8571 | 1 | 5 | 0.2 | 10 | 35
| 4140 | 0.4 | 10 | 18.6207 | 25.6041 | 2.8095 | 4.1739 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 4141 | 1 | 4 | 11.4894 | 18.6523 | 3.4706 | 3.6923 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 4142 | 1 | 4 | 10.3846 | 16.7321 | 3.3475 | 3 | 1 | 5 | 0.4 | 5 | 14
| 4143 | 0.4 | 10 | 7.1053 | 14.8016 | 3.5224 | 4.1739 | 1 | 5 | 0.4 | 5 | 20
| 4144 | 0.6 | 6.6667 | 10.3846 | 18.9861 | 3.5489 | 5.0526 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 4145 | 1.2 | 3.3333 | 9 | 16.7968 | 2.7442 | 5.0526 | 1.4 | 3.5714 | 0.8 | 2.5 | 9.4048
| 4146 | 0.8 | 5 | 15.8824 | 24.0402 | 3.1053 | 5.0526 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 4147 | 0.6 | 6.6667 | 7.7143 | 16.1364 | 3.2329 | 5.1892 | 1 | 5 | 0.4 | 5 | 16.6667
| 4148 | 0.6 | 6.6667 | 16.3636 | 22.4949 | 2.2913 | 3.84 | 1 | 5 | 0.2 | 10 | 21.6667
| 4149 | 0.6 | 6.6667 | 12.5581 | 18.2844 | 2.8606 | 2.8657 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 4150 | 0.2 | 20 | 11.25 | 20.1079 | 3.2109 | 5.6471 | 0.8 | 6.25 | 0.1 | 20 | 46.25
| 4151 | 1 | 4 | 16.3636 | 22.5322 | 2.9686 | 3.2 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 4152 | 0.4 | 10 | 9.6429 | 19.5642 | 3.3007 | 6.6207 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 4153 | 1.2 | 3.3333 | 11.25 | 20.858 | 2.9873 | 6.6207 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 4154 | 0.8 | 5 | 15.8824 | 22.4904 | 2.8434 | 3.7647 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 4155 | 0.8 | 5 | 10.8 | 17.1767 | 2.4583 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 4156 | 0.8 | 5 | 13.1707 | 19.3915 | 2.3024 | 3.9184 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 4157 | 0.8 | 5 | 11.7391 | 20.2624 | 3.4706 | 5.0526 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 4158 | 1.2 | 3.3333 | 12 | 20.5624 | 2.7442 | 5.8182 | 1 | 5 | 0.2 | 10 | 18.3333
| 4159 | 1 | 4 | 10.1887 | 17.0543 | 3.0256 | 3.84 | 1 | 5 | 0.4 | 5 | 14
| 4160 | 0.6 | 6.6667 | 11.7391 | 20.0598 | 2.9873 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 4161 | 0.8 | 5 | 11.7391 | 19.7418 | 2.95 | 5.0526 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 4162 | 0.6 | 6.6667 | 13.1707 | 21.2805 | 2.7765 | 5.3333 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 4163 | 0.4 | 10 | 16.875 | 23.977 | 2.6369 | 4.4651 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 4164 | 0.8 | 5 | 15.4286 | 22.1642 | 4.069 | 2.6667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 4165 | 0.6 | 6.6667 | 11.25 | 19.8565 | 3.8065 | 4.8 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 4166 | 1 | 4 | 15 | 22.3479 | 2.7765 | 4.5714 | 1 | 5 | 0.4 | 5 | 14
| 4167 | 0.4 | 10 | 9.8182 | 17.928 | 2.7765 | 5.3333 | 1 | 5 | 0.2 | 10 | 25
| 4168 | 0.4 | 10 | 11.0204 | 19.1596 | 2.95 | 5.1892 | 1.2 | 4.1667 | 1 | 2 | 16.1667
| 4169 | 0.6 | 6.6667 | 8.1818 | 14.4367 | 2.8263 | 3.4286 | 1 | 5 | 0.2 | 10 | 21.6667
| 4170 | 0.6 | 6.6667 | 15.4286 | 22.0166 | 2.8957 | 3.6923 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 4171 | 0.4 | 10 | 17.4194 | 26.491 | 2.878 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 4172 | 0.4 | 10 | 13.5 | 21.8463 | 2.8606 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 4173 | 1 | 4 | 14.2105 | 20.9708 | 2.7602 | 4 | 1 | 5 | 0.4 | 5 | 14
| 4174 | 1 | 4 | 13.8462 | 21.9985 | 2.6667 | 5.4857 | 1 | 5 | 0.4 | 5 | 14
| 4175 | 0.6 | 6.6667 | 12.2727 | 17.7108 | 2.4842 | 2.9538 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 4176 | 1.4 | 2.8571 | 11.4894 | 17.2713 | 2.2264 | 3.5556 | 1 | 5 | 0.8 | 2.5 | 10.3571
| 4177 | 1 | 4 | 10.3846 | 15.9321 | 2.6818 | 2.8657 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 4178 | 1 | 4 | 12.5581 | 19.9669 | 3.0452 | 4.3636 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 4179 | 0.8 | 5 | 8.0597 | 15.1836 | 2.7602 | 4.3636 | 1 | 5 | 0.2 | 10 | 20
| 4180 | 1 | 4 | 15 | 22.4073 | 2.4842 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 4181 | 1.2 | 3.3333 | 10.5882 | 16.8859 | 2.9873 | 3.3103 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 4182 | 1 | 4 | 11.4894 | 18.1537 | 2.5792 | 4.0851 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 4183 | 0.6 | 6.6667 | 14.2105 | 20.9674 | 3.9333 | 2.8235 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 4184 | 1 | 4 | 10.5882 | 18.0571 | 3.1053 | 4.3636 | 1 | 5 | 0.1 | 20 | 29
| 4185 | 0.6 | 6.6667 | 11.4894 | 18.2414 | 2.9873 | 3.7647 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 4186 | 1.2 | 3.3333 | 12.5581 | 20.6863 | 3.4453 | 4.6829 | 1 | 5 | 0.4 | 5 | 13.3333
| 4187 | 1.2 | 3.3333 | 7.9412 | 15.7863 | 3.0452 | 4.8 | 0.4 | 12.5 | 0.4 | 5 | 20.8333
| 4188 | 0.4 | 10 | 11.4894 | 20.3346 | 2.6517 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 4189 | 1 | 4 | 10.3846 | 21.9002 | 3.1678 | 8.3478 | 1 | 5 | 0.8 | 2.5 | 11.5
| 4190 | 0.8 | 5 | 12.2727 | 20.0601 | 2.9873 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 4191 | 0.6 | 6.6667 | 11.0204 | 17.4864 | 2.8434 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 4192 | 0.6 | 6.6667 | 11.0204 | 16.5639 | 2.1751 | 3.3684 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 4193 | 1 | 4 | 7.9412 | 15.4865 | 2.6222 | 4.9231 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 4194 | 1.2 | 3.3333 | 12.8571 | 19.3232 | 2.8434 | 3.6226 | 1 | 5 | 0.2 | 10 | 18.3333
| 4195 | 1.2 | 3.3333 | 9.8182 | 20.8831 | 3.0649 | 8 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 4196 | 0.8 | 5 | 12.5581 | 20.0956 | 2.3483 | 5.1892 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 4197 | 0.4 | 10 | 14.5946 | 22.9543 | 2.7126 | 5.6471 | 1.6 | 3.125 | 0.2 | 10 | 23.125
| 4198 | 0.6 | 6.6667 | 11.0204 | 18.7683 | 3.0649 | 4.6829 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 4199 | 0.4 | 10 | 12.8571 | 21.1517 | 4.866 | 3.4286 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 4200 | 0.6 | 6.6667 | 11.25 | 17.1559 | 2.6517 | 3.2542 | 1 | 5 | 0.4 | 5 | 16.6667
| 4201 | 0.6 | 6.6667 | 10.3846 | 18.3833 | 2.8095 | 5.1892 | 1 | 5 | 0.2 | 10 | 21.6667
| 4202 | 1.6 | 2.5 | 12.2727 | 19.8505 | 3.0064 | 4.5714 | 0.6 | 8.3333 | 0.2 | 10 | 20.8333
| 4203 | 0.8 | 5 | 11.25 | 17.8052 | 2.6369 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 4204 | 0.6 | 6.6667 | 15 | 23.7333 | 3.9333 | 4.8 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 4205 | 0.2 | 20 | 13.8462 | 21.4207 | 3.2109 | 4.3636 | 1.2 | 4.1667 | 0.6 | 3.3333 | 27.5
| 4206 | 0.8 | 5 | 12.8571 | 19.8093 | 2.2692 | 4.6829 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 4207 | 0.6 | 6.6667 | 10.5882 | 18.8342 | 2.7602 | 5.4857 | 1 | 5 | 0.6 | 3.3333 | 15
| 4208 | 0.4 | 10 | 9.1525 | 21.0907 | 3.2109 | 8.7273 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 4209 | 1.2 | 3.3333 | 12.5581 | 19.0532 | 3.3475 | 3.1475 | 1 | 5 | 0.4 | 5 | 13.3333
| 4210 | 0.8 | 5 | 10 | 15.4512 | 2.4974 | 2.9538 | 1 | 5 | 0.8 | 2.5 | 12.5
| 4211 | 1 | 4 | 12.2727 | 18.2254 | 2.5241 | 3.4286 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 4212 | 0.4 | 10 | 13.1707 | 19.6948 | 2.9686 | 3.5556 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 4213 | 1.2 | 3.3333 | 15 | 22.2167 | 2.95 | 4.2667 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 4214 | 0.6 | 6.6667 | 7.7143 | 16.09 | 3.5758 | 4.8 | 1 | 5 | 0.4 | 5 | 16.6667
| 4215 | 0.8 | 5 | 18 | 23.6403 | 3.5758 | 2.0645 | 1 | 5 | 0.4 | 5 | 15
| 4216 | 1 | 4 | 12.5581 | 18.9946 | 2.7442 | 3.6923 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 4217 | 0.8 | 5 | 10.3846 | 16.549 | 2.0793 | 4.0851 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 4218 | 0.1 | 40 | 10.1887 | 17.1023 | 2.9136 | 4 | 0.6 | 8.3333 | 0.6 | 3.3333 | 51.6667
| 4219 | 0.4 | 10 | 18.6207 | 25.6856 | 3.0649 | 4 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 4220 | 0.8 | 5 | 11.25 | 21.6467 | 3.776 | 6.6207 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 4221 | 1 | 4 | 8.7097 | 15.1106 | 3.1467 | 3.2542 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 4222 | 0.6 | 6.6667 | 12 | 23.0721 | 3.6875 | 7.3846 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 4223 | 0.6 | 6.6667 | 8.0597 | 16.5009 | 2.2476 | 6.1935 | 1 | 5 | 0.4 | 5 | 16.6667
| 4224 | 0.8 | 5 | 12.8571 | 18.9183 | 2.9136 | 3.1475 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 4225 | 1.6 | 2.5 | 14.5946 | 21.4053 | 3.2552 | 3.5556 | 1 | 5 | 0.4 | 5 | 12.5
| 4226 | 0.8 | 5 | 9.6429 | 15.4729 | 3.1258 | 2.7042 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 4227 | 1 | 4 | 15.8824 | 23.4588 | 2.7765 | 4.8 | 1 | 5 | 0.8 | 2.5 | 11.5
| 4228 | 0.4 | 10 | 15.4286 | 23.1467 | 3.1467 | 4.5714 | 0.4 | 12.5 | 0.2 | 10 | 32.5
| 4229 | 0.8 | 5 | 10 | 16.6678 | 3.0452 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 4230 | 0.6 | 6.6667 | 10.8 | 16.9148 | 2.8606 | 3.2542 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 4231 | 0.6 | 6.6667 | 10.5882 | 16.9358 | 3.3475 | 3 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 4232 | 0.8 | 5 | 13.1707 | 24.1747 | 3.3239 | 7.68 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 4233 | 0.6 | 6.6667 | 15.8824 | 22.8657 | 3.0649 | 3.9184 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 4234 | 0.6 | 6.6667 | 12.2727 | 21.9626 | 3.4963 | 6.1935 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 4235 | 1.2 | 3.3333 | 10.8 | 19.6097 | 3.3239 | 5.4857 | 0.8 | 6.25 | 1 | 2 | 11.5833
| 4236 | 0.8 | 5 | 16.3636 | 22.2042 | 2.7929 | 3.0476 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 4237 | 0.8 | 5 | 13.8462 | 19.9117 | 2.6971 | 3.3684 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 4238 | 0.4 | 10 | 10 | 22.4059 | 5.0213 | 7.3846 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 4239 | 0.8 | 5 | 12 | 21.3402 | 3.1467 | 6.1935 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 4240 | 0.8 | 5 | 12.5581 | 22.2627 | 2.5934 | 7.1111 | 1.6 | 3.125 | 0.6 | 3.3333 | 11.4583
| 4241 | 1.6 | 2.5 | 11.0204 | 20.1625 | 3.3239 | 5.8182 | 0.8 | 6.25 | 0.4 | 5 | 13.75
| 4242 | 0.6 | 6.6667 | 11.4894 | 18.3504 | 2.4974 | 4.3636 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 4243 | 0.4 | 10 | 13.1707 | 20.0004 | 3.0649 | 3.7647 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 4244 | 0.4 | 10 | 12.2727 | 22.4497 | 4.177 | 6 | 1.4 | 3.5714 | 0.8 | 2.5 | 16.0714
| 4245 | 0.4 | 10 | 9 | 16.8155 | 3.5489 | 4.2667 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 4246 | 1 | 4 | 19.2857 | 24.9306 | 2.4974 | 3.1475 | 1 | 5 | 0.4 | 5 | 14
| 4247 | 0.8 | 5 | 12.5581 | 20.1602 | 3.8374 | 3.7647 | 1.4 | 3.5714 | 0.8 | 2.5 | 11.0714
| 4248 | 0.4 | 10 | 10.1887 | 18.7112 | 3.1892 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 4249 | 0.8 | 5 | 18.6207 | 23.6696 | 3.0064 | 2.0426 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 4250 | 0.6 | 6.6667 | 12 | 20.1176 | 3.0649 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 4251 | 1 | 4 | 11.0204 | 18.7097 | 3.0064 | 4.6829 | 1 | 5 | 0.2 | 10 | 19
| 4252 | 0.6 | 6.6667 | 13.8462 | 21.6508 | 3.6308 | 4.1739 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 4253 | 0.4 | 10 | 14.2105 | 22.2261 | 2.8263 | 5.1892 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 4254 | 1.2 | 3.3333 | 17.4194 | 28.7583 | 3.6589 | 7.68 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 4255 | 0.4 | 10 | 11.4894 | 18.0471 | 2.3838 | 4.1739 | 1 | 5 | 0.2 | 10 | 25
| 4256 | 0.6 | 6.6667 | 10.8 | 19.9258 | 3.1258 | 6 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 4257 | 0.6 | 6.6667 | 9.6429 | 16.3449 | 2.237 | 4.4651 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 4258 | 0.8 | 5 | 10.8 | 20.6536 | 3.2329 | 6.6207 | 1 | 5 | 0.2 | 10 | 20
| 4259 | 0.4 | 10 | 12.8571 | 21.2405 | 2.5652 | 5.8182 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 4260 | 0.6 | 6.6667 | 10.5882 | 16.7534 | 2.3251 | 3.84 | 1.6 | 3.125 | 0.4 | 5 | 14.7917
| 4261 | 0.8 | 5 | 12 | 21.1448 | 2.5241 | 6.6207 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 4262 | 0.6 | 6.6667 | 13.5 | 20.8978 | 2.8263 | 4.5714 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 4263 | 1 | 4 | 7.3973 | 12.7586 | 2.3137 | 3.0476 | 1 | 5 | 0.2 | 10 | 19
| 4264 | 0.6 | 6.6667 | 12.8571 | 19.2587 | 2.6369 | 3.7647 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 4265 | 1 | 4 | 12 | 18.202 | 3.1053 | 3.0968 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 4266 | 0.2 | 20 | 24.5455 | 33.7596 | 2.5934 | 6.6207 | 0.6 | 8.3333 | 0.2 | 10 | 38.3333
| 4267 | 1 | 4 | 8.7097 | 14.529 | 3.1892 | 2.6301 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 4268 | 0.8 | 5 | 10 | 17.1613 | 2.9873 | 4.1739 | 1 | 5 | 0.4 | 5 | 15
| 4269 | 0.6 | 6.6667 | 15.4286 | 24.1425 | 2.8957 | 5.8182 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 4270 | 1 | 4 | 12.2727 | 22.5305 | 3.1467 | 7.1111 | 1 | 5 | 0.2 | 10 | 19
| 4271 | 0.6 | 6.6667 | 7.3973 | 14.0991 | 3.2109 | 3.4909 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 4272 | 1 | 4 | 11.25 | 19.884 | 3.3007 | 5.3333 | 1.6 | 3.125 | 0.2 | 10 | 17.125
| 4273 | 1.2 | 3.3333 | 11.4894 | 19.8531 | 2.878 | 5.4857 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 4274 | 0.6 | 6.6667 | 12.8571 | 19.3578 | 3.3007 | 3.2 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 4275 | 0.2 | 20 | 11.0204 | 20.6982 | 3.2778 | 6.4 | 1 | 5 | 0.4 | 5 | 30
| 4276 | 1 | 4 | 12.2727 | 18.756 | 2.8606 | 3.6226 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 4277 | 1 | 4 | 15.8824 | 23.8704 | 3.0649 | 4.9231 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 4278 | 1.4 | 2.8571 | 9.6429 | 17.9079 | 2.9317 | 5.3333 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 4279 | 0.8 | 5 | 7.9412 | 18.7014 | 2.7602 | 8 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 4280 | 0.6 | 6.6667 | 18 | 27.0615 | 3.5758 | 5.4857 | 1 | 5 | 0.4 | 5 | 16.6667
| 4281 | 1 | 4 | 17.4194 | 26.2627 | 2.8434 | 6 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 4282 | 0.8 | 5 | 8.5714 | 18.4928 | 3.3007 | 6.6207 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 4283 | 0.2 | 20 | 12.8571 | 19.1814 | 2.8957 | 3.4286 | 1.4 | 3.5714 | 0.8 | 2.5 | 26.0714
| 4284 | 1.6 | 2.5 | 12.8571 | 20.0686 | 3.3714 | 3.84 | 0.6 | 8.3333 | 0.2 | 10 | 20.8333
| 4285 | 0.4 | 10 | 10.1887 | 17.1362 | 3.2552 | 3.6923 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 4286 | 1 | 4 | 20 | 27.3848 | 3.2109 | 4.1739 | 1 | 5 | 0.2 | 10 | 19
| 4287 | 0.6 | 6.6667 | 7.3973 | 13.5352 | 2.4456 | 3.6923 | 1 | 5 | 0.4 | 5 | 16.6667
| 4288 | 1 | 4 | 10.8 | 17.0118 | 2.8434 | 3.3684 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 4289 | 0.6 | 6.6667 | 12.5581 | 21.1288 | 3.085 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 4290 | 1.6 | 2.5 | 13.1707 | 20.2808 | 2.8434 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 10.8333
| 4291 | 0.6 | 6.6667 | 12.8571 | 19.4652 | 2.8434 | 3.7647 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 4292 | 1.4 | 2.8571 | 14.5946 | 22.4283 | 4.069 | 3.7647 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 4293 | 0.6 | 6.6667 | 12.2727 | 20.391 | 2.4712 | 5.6471 | 1 | 5 | 0.2 | 10 | 21.6667
| 4294 | 0.8 | 5 | 10.3846 | 17.8552 | 3.4706 | 4 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 4295 | 0.8 | 5 | 10.3846 | 17.9143 | 3.8374 | 3.6923 | 0.4 | 12.5 | 0.6 | 3.3333 | 20.8333
| 4296 | 0.6 | 6.6667 | 12.2727 | 21.0595 | 2.9686 | 5.8182 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 4297 | 0.6 | 6.6667 | 10 | 16.8296 | 3.0649 | 3.7647 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 4298 | 0.4 | 10 | 13.8462 | 21.4976 | 2.9686 | 4.6829 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 4299 | 0.8 | 5 | 10.1887 | 17.9213 | 2.8095 | 4.9231 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 4300 | 1 | 4 | 12 | 19.0425 | 3.2778 | 3.7647 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 4301 | 1 | 4 | 15 | 21.9252 | 3.2329 | 3.6923 | 1 | 5 | 0.2 | 10 | 19
| 4302 | 0.8 | 5 | 12.2727 | 21.1481 | 2.6818 | 6.1935 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 4303 | 0.6 | 6.6667 | 13.5 | 22.6732 | 3.6875 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 4304 | 0.4 | 10 | 15.8824 | 22.6488 | 3.2109 | 3.5556 | 1 | 5 | 0.4 | 5 | 20
| 4305 | 1.4 | 2.8571 | 12.5581 | 19.219 | 3.1053 | 3.5556 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 4306 | 0.8 | 5 | 10.8 | 18.4142 | 3.3475 | 4.2667 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 4307 | 0.6 | 6.6667 | 12.8571 | 18.7162 | 2.95 | 2.9091 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 4308 | 1 | 4 | 16.3636 | 23.931 | 3.3007 | 4.2667 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 4309 | 1 | 4 | 9.6429 | 14.2591 | 2.6369 | 1.9794 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 4310 | 0.4 | 10 | 11.0204 | 17.8311 | 3.2552 | 3.5556 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 4311 | 1.2 | 3.3333 | 9.3103 | 17.5215 | 3.746 | 4.4651 | 1 | 5 | 0.1 | 20 | 28.3333
| 4312 | 0.4 | 10 | 13.5 | 21.6475 | 3.3475 | 4.8 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 4313 | 1 | 4 | 13.8462 | 28.547 | 4.0342 | 10.6667 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 4314 | 0.8 | 5 | 9 | 17.2833 | 2.95 | 5.3333 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 4315 | 0.8 | 5 | 11.25 | 21.8898 | 3.2552 | 7.3846 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 4316 | 1.2 | 3.3333 | 15 | 23.5106 | 2.5106 | 6 | 1 | 5 | 0.4 | 5 | 13.3333
| 4317 | 1 | 4 | 8.4375 | 15.5614 | 2.95 | 4.1739 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 4318 | 1 | 4 | 14.5946 | 23.3229 | 2.7283 | 6 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 4319 | 1 | 4 | 10.5882 | 21.4146 | 2.8263 | 8 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 4320 | 0.8 | 5 | 12 | 23.1111 | 2.3838 | 8.7273 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 4321 | 0.6 | 6.6667 | 10.3846 | 16.9667 | 2.4082 | 4.1739 | 1 | 5 | 0.2 | 10 | 21.6667
| 4322 | 1 | 4 | 12.5581 | 21.0018 | 4.177 | 4.2667 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 4323 | 0.6 | 6.6667 | 13.8462 | 22.5059 | 3.4706 | 5.1892 | 1 | 5 | 0.1 | 20 | 31.6667
| 4324 | 1 | 4 | 10.1887 | 15.1769 | 2.2056 | 2.7826 | 1 | 5 | 0.4 | 5 | 14
| 4325 | 0.4 | 10 | 15 | 22.3636 | 3.4453 | 3.9184 | 1 | 5 | 0.1 | 20 | 35
| 4326 | 1.2 | 3.3333 | 10 | 18.1007 | 3.3007 | 4.8 | 1 | 5 | 0.2 | 10 | 18.3333
| 4327 | 0.1 | 40 | 12.2727 | 17.948 | 3.0452 | 2.6301 | 1.4 | 3.5714 | 0.4 | 5 | 48.5714
| 4328 | 0.6 | 6.6667 | 12.8571 | 19.8346 | 3.5489 | 3.4286 | 1 | 5 | 0.4 | 5 | 16.6667
| 4329 | 0.6 | 6.6667 | 10.1887 | 16.8874 | 3.0064 | 3.6923 | 1 | 5 | 0.4 | 5 | 16.6667
| 4330 | 0.6 | 6.6667 | 9.4737 | 16.6721 | 3.5758 | 3.6226 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 4331 | 1 | 4 | 13.8462 | 22.0021 | 3.2329 | 4.9231 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 4332 | 0.8 | 5 | 11.4894 | 20.2274 | 3.5489 | 5.1892 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 4333 | 1 | 4 | 12.8571 | 22.5628 | 3.085 | 6.6207 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 4334 | 0.6 | 6.6667 | 13.5 | 22.1616 | 2.8434 | 5.8182 | 1 | 5 | 0.6 | 3.3333 | 15
| 4335 | 1 | 4 | 11.0204 | 18.1717 | 3.2329 | 3.9184 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 4336 | 0.6 | 6.6667 | 12 | 17.6481 | 3.2778 | 2.3704 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 4337 | 0.6 | 6.6667 | 13.5 | 27.7424 | 3.5758 | 10.6667 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 4338 | 0.8 | 5 | 22.5 | 32.0642 | 3.746 | 5.8182 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 4339 | 1 | 4 | 13.8462 | 19.2525 | 3.0064 | 2.4 | 1 | 5 | 0.1 | 20 | 29
| 4340 | 0.8 | 5 | 11.0204 | 20.6313 | 3.2109 | 6.4 | 1 | 5 | 0.4 | 5 | 15
| 4341 | 0.2 | 20 | 10.5882 | 18.2845 | 3.5224 | 4.1739 | 1 | 5 | 0.4 | 5 | 30
| 4342 | 0.4 | 10 | 16.875 | 24.1891 | 3.3957 | 3.9184 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 4343 | 0.6 | 6.6667 | 18 | 25.3858 | 3.3007 | 4.0851 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 4344 | 1 | 4 | 14.5946 | 22.9153 | 2.9873 | 5.3333 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 4345 | 0.8 | 5 | 11.4894 | 17.4767 | 2.9873 | 3 | 1 | 5 | 0.8 | 2.5 | 12.5
| 4346 | 0.8 | 5 | 10.1887 | 16.395 | 3.0064 | 3.2 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 4347 | 0.8 | 5 | 13.8462 | 23.715 | 2.4842 | 7.3846 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 4348 | 0.6 | 6.6667 | 10 | 16.6928 | 2.6077 | 4.0851 | 1 | 5 | 0.4 | 5 | 16.6667
| 4349 | 0.2 | 20 | 10.1887 | 17.2762 | 2.9136 | 4.1739 | 0.8 | 6.25 | 0.2 | 10 | 36.25
| 4350 | 0.6 | 6.6667 | 8.8525 | 17.8002 | 3.3007 | 5.6471 | 1 | 5 | 0.4 | 5 | 16.6667
| 4351 | 1.2 | 3.3333 | 9.6429 | 15.4221 | 2.5792 | 3.2 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 4352 | 1 | 4 | 11.7391 | 19.9347 | 3.0064 | 5.1892 | 1.6 | 3.125 | 0.8 | 2.5 | 9.625
| 4353 | 0.8 | 5 | 10.1887 | 19.4472 | 3.0649 | 6.1935 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 4354 | 0.4 | 10 | 11.7391 | 17.8323 | 2.5376 | 3.5556 | 0.4 | 12.5 | 0.4 | 5 | 27.5
| 4355 | 0.8 | 5 | 12.5581 | 20.7695 | 2.878 | 5.3333 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 4356 | 0.6 | 6.6667 | 12.2727 | 19.9543 | 2.3483 | 5.3333 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 4357 | 0.6 | 6.6667 | 12.2727 | 21.675 | 4.069 | 5.3333 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 4358 | 0.4 | 10 | 19.2857 | 25.6752 | 2.6971 | 3.6923 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 4359 | 0.6 | 6.6667 | 12.8571 | 26.1091 | 3.1467 | 10.1053 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 4360 | 0.8 | 5 | 11.25 | 17.7348 | 3.5758 | 2.9091 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 4361 | 1.2 | 3.3333 | 10 | 18.575 | 3.5224 | 5.0526 | 1 | 5 | 0.4 | 5 | 13.3333
| 4362 | 0.6 | 6.6667 | 13.8462 | 23.5559 | 2.3251 | 7.3846 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 4363 | 0.2 | 20 | 11.4894 | 18.8671 | 2.3251 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 4364 | 1 | 4 | 15.8824 | 22.9093 | 2.7602 | 4.2667 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 4365 | 1 | 4 | 13.8462 | 19.9385 | 3.6308 | 2.4615 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 4366 | 0.2 | 20 | 12 | 19.1091 | 2.5376 | 4.5714 | 1 | 5 | 0.2 | 10 | 35
| 4367 | 1.2 | 3.3333 | 12.2727 | 26.1503 | 3.2109 | 10.6667 | 1.4 | 3.5714 | 0.8 | 2.5 | 9.4048
| 4368 | 0.6 | 6.6667 | 11.0204 | 18.2947 | 3.1892 | 4.0851 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 4369 | 0.8 | 5 | 13.1707 | 21.0667 | 2.8434 | 5.0526 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 4370 | 0.6 | 6.6667 | 10 | 18.9686 | 2.9686 | 6 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 4371 | 0.6 | 6.6667 | 13.8462 | 20.9754 | 3.2109 | 3.9184 | 1 | 5 | 0.2 | 10 | 21.6667
| 4372 | 0.8 | 5 | 14.2105 | 20.4327 | 2.6667 | 3.5556 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 4373 | 0.8 | 5 | 11.7391 | 20.3502 | 2.7929 | 5.8182 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 4374 | 0.8 | 5 | 12 | 18.2838 | 2.7929 | 3.4909 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 4375 | 1 | 4 | 13.8462 | 22.2246 | 4.5385 | 3.84 | 1 | 5 | 0.4 | 5 | 14
| 4376 | 1 | 4 | 13.5 | 23.7047 | 3.3475 | 6.8571 | 1 | 5 | 0.4 | 5 | 14
| 4377 | 0.2 | 20 | 13.5 | 23.2188 | 2.6077 | 7.1111 | 1 | 5 | 0.8 | 2.5 | 27.5
| 4378 | 0.6 | 6.6667 | 9.8182 | 18.2497 | 3.9664 | 4.4651 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 4379 | 1 | 4 | 11.4894 | 19.2029 | 2.9136 | 4.8 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 4380 | 0.8 | 5 | 9 | 21.0512 | 3.3239 | 8.7273 | 1.6 | 3.125 | 0.6 | 3.3333 | 11.4583
| 4381 | 1.2 | 3.3333 | 14.2105 | 24.1822 | 2.8606 | 7.1111 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 4382 | 1 | 4 | 12.2727 | 23.2527 | 3.8689 | 7.1111 | 1 | 5 | 0.4 | 5 | 14
| 4383 | 0.4 | 10 | 15.8824 | 25.2651 | 3.1892 | 6.1935 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 4384 | 0.6 | 6.6667 | 15.4286 | 24.4208 | 3.6589 | 5.3333 | 1 | 5 | 0.2 | 10 | 21.6667
| 4385 | 0.4 | 10 | 13.5 | 23.0489 | 3.5489 | 6 | 1 | 5 | 0.2 | 10 | 25
| 4386 | 0.8 | 5 | 8.8525 | 16.4431 | 3.3239 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 4387 | 1.2 | 3.3333 | 11.0204 | 23.244 | 3.4963 | 8.7273 | 1 | 5 | 0.4 | 5 | 13.3333
| 4388 | 0.6 | 6.6667 | 11.4894 | 17.6786 | 3.1892 | 3 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 4389 | 1 | 4 | 11.25 | 19.0382 | 3.1053 | 4.6829 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 4390 | 1 | 4 | 11.7391 | 18.4897 | 3.6031 | 3.1475 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 4391 | 1 | 4 | 13.8462 | 22.7918 | 2.0885 | 6.8571 | 1 | 5 | 0.4 | 5 | 14
| 4392 | 0.6 | 6.6667 | 13.1707 | 22.9592 | 3.1678 | 6.6207 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 4393 | 0.6 | 6.6667 | 7.8261 | 16.646 | 3.6308 | 5.1892 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 4394 | 0.6 | 6.6667 | 16.3636 | 24.717 | 3.3007 | 5.0526 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 4395 | 1.4 | 2.8571 | 8.0597 | 15.9211 | 3.6875 | 4.1739 | 0.6 | 8.3333 | 0.4 | 5 | 16.1905
| 4396 | 1 | 4 | 10.1887 | 18.0486 | 3.4963 | 4.3636 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 4397 | 0.8 | 5 | 9.8182 | 18.7416 | 3.1053 | 5.8182 | 1 | 5 | 0.2 | 10 | 20
| 4398 | 0.8 | 5 | 16.875 | 24.1282 | 2.6818 | 4.5714 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 4399 | 1.2 | 3.3333 | 9.6429 | 19.1069 | 2.8434 | 6.6207 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 4400 | 0.2 | 20 | 8.7097 | 18.0906 | 2.7602 | 6.6207 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 4401 | 1 | 4 | 9.8182 | 19.2671 | 3.6308 | 5.8182 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 4402 | 1.2 | 3.3333 | 14.2105 | 20.5129 | 2.5376 | 3.7647 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 4403 | 1 | 4 | 15 | 21.6203 | 3.4203 | 3.2 | 1 | 5 | 0.4 | 5 | 14
| 4404 | 1 | 4 | 12.5581 | 18.1425 | 2.216 | 3.3684 | 1 | 5 | 0.2 | 10 | 19
| 4405 | 1.4 | 2.8571 | 8.5714 | 19.061 | 3.8689 | 6.6207 | 1.2 | 4.1667 | 1 | 2 | 9.0238
| 4406 | 0.8 | 5 | 10.1887 | 20.0539 | 2.1852 | 7.68 | 1 | 5 | 0.1 | 20 | 30
| 4407 | 1 | 4 | 12 | 19.5491 | 3.6308 | 3.9184 | 1 | 5 | 0.4 | 5 | 14
| 4408 | 0.6 | 6.6667 | 12.5581 | 21.2547 | 3.2109 | 5.4857 | 1 | 5 | 0.4 | 5 | 16.6667
| 4409 | 0.6 | 6.6667 | 15 | 21.1867 | 3.2329 | 2.9538 | 1 | 5 | 0.2 | 10 | 21.6667
| 4410 | 0.8 | 5 | 9.8182 | 20.7252 | 3.5224 | 7.3846 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 4411 | 1 | 4 | 11.4894 | 25.3889 | 3.2329 | 10.6667 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.8333
| 4412 | 0.2 | 20 | 11.7391 | 19.7005 | 3.4963 | 4.4651 | 1.2 | 4.1667 | 0.6 | 3.3333 | 27.5
| 4413 | 1 | 4 | 17.4194 | 26.5246 | 3.1053 | 6 | 0.6 | 8.3333 | 0.1 | 20 | 32.3333
| 4414 | 0.8 | 5 | 11.4894 | 21.41 | 2.8095 | 7.1111 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 4415 | 0.4 | 10 | 14.2105 | 22.0261 | 3.5489 | 4.2667 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 4416 | 0.8 | 5 | 10.1887 | 18.8227 | 3.3007 | 5.3333 | 1 | 5 | 0.4 | 5 | 15
| 4417 | 0.8 | 5 | 9.3103 | 16.6207 | 4 | 3.3103 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 4418 | 0.2 | 20 | 11.25 | 18.315 | 3.1467 | 3.9184 | 1.6 | 3.125 | 0.4 | 5 | 28.125
| 4419 | 1.4 | 2.8571 | 20 | 29.9023 | 3.0452 | 6.8571 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 4420 | 0.8 | 5 | 14.5946 | 23.8934 | 3.1053 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 4421 | 0.1 | 40 | 15.8824 | 24.2589 | 3.3239 | 5.0526 | 1 | 5 | 0.8 | 2.5 | 47.5
| 4422 | 0.6 | 6.6667 | 13.8462 | 21.702 | 2.6667 | 5.1892 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 4423 | 0.8 | 5 | 9.4737 | 17.6451 | 3.3714 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 4424 | 0.8 | 5 | 13.5 | 19.8776 | 2.5376 | 3.84 | 1 | 5 | 0.2 | 10 | 20
| 4425 | 0.8 | 5 | 11.25 | 19.0044 | 2.5652 | 5.1892 | 1 | 5 | 0.2 | 10 | 20
| 4426 | 0.8 | 5 | 15.4286 | 22.866 | 4.069 | 3.3684 | 1 | 5 | 0.2 | 10 | 20
| 4427 | 0.6 | 6.6667 | 10.3846 | 18.8721 | 3.6875 | 4.8 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 4428 | 0.8 | 5 | 12.2727 | 17.1641 | 2.0258 | 2.8657 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 4429 | 0.6 | 6.6667 | 13.5 | 19.0103 | 3.2778 | 2.2326 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 4430 | 0.6 | 6.6667 | 11.0204 | 17.5006 | 3.776 | 2.7042 | 1 | 5 | 0.6 | 3.3333 | 15
| 4431 | 1 | 4 | 15.8824 | 23.8311 | 3.0256 | 4.9231 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 4432 | 0.6 | 6.6667 | 10 | 17.311 | 2.2584 | 5.0526 | 1 | 5 | 0.6 | 3.3333 | 15
| 4433 | 0.6 | 6.6667 | 15 | 22.4895 | 3.1258 | 4.3636 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 4434 | 0.6 | 6.6667 | 11.25 | 17.4164 | 3.3007 | 2.8657 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 4435 | 0.6 | 6.6667 | 10.8 | 18.7917 | 3.4203 | 4.5714 | 0.4 | 12.5 | 0.8 | 2.5 | 21.6667
| 4436 | 0.8 | 5 | 9.1525 | 20.6896 | 3.1892 | 8.3478 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 4437 | 0.6 | 6.6667 | 12 | 18.0976 | 2.8434 | 3.2542 | 1 | 5 | 0.2 | 10 | 21.6667
| 4438 | 0.6 | 6.6667 | 21.6 | 28.6236 | 3.1053 | 3.9184 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 4439 | 1 | 4 | 12.5581 | 19.114 | 3.0649 | 3.4909 | 1 | 5 | 0.2 | 10 | 19
| 4440 | 0.8 | 5 | 9.6429 | 16.1305 | 2.3137 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 4441 | 0.8 | 5 | 13.5 | 19.4506 | 3.085 | 2.8657 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 4442 | 1 | 4 | 15 | 21.3804 | 3.2329 | 3.1475 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 4443 | 0.8 | 5 | 13.8462 | 24.4002 | 3.9333 | 6.6207 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 4444 | 1.2 | 3.3333 | 10.1887 | 16.5322 | 2.2584 | 4.0851 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 4445 | 1 | 4 | 12.5581 | 21.2629 | 3.3714 | 5.3333 | 1 | 5 | 0.2 | 10 | 19
| 4446 | 0.1 | 40 | 11.0204 | 17.7646 | 2.7442 | 4 | 0.8 | 6.25 | 0.4 | 5 | 51.25
| 4447 | 1 | 4 | 11.4894 | 19.7846 | 2.8095 | 5.4857 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 4448 | 0.6 | 6.6667 | 20 | 25.581 | 2.4842 | 3.0968 | 1 | 5 | 0.4 | 5 | 16.6667
| 4449 | 0.6 | 6.6667 | 10.3846 | 22.2093 | 2.6818 | 9.1429 | 1.6 | 3.125 | 0.2 | 10 | 19.7917
| 4450 | 1 | 4 | 8.4375 | 15.0053 | 3.4203 | 3.1475 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 4451 | 0.4 | 10 | 12.8571 | 19.0061 | 2.5934 | 3.5556 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 4452 | 0.8 | 5 | 12.5581 | 21.5804 | 2.6222 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 4453 | 0.8 | 5 | 13.5 | 21.4821 | 2.7929 | 5.1892 | 1 | 5 | 0.4 | 5 | 15
| 4454 | 0.4 | 10 | 9.4737 | 16.9057 | 2.8606 | 4.5714 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 4455 | 0.8 | 5 | 11.0204 | 20.4013 | 2.7602 | 6.6207 | 1.4 | 3.5714 | 0.8 | 2.5 | 11.0714
| 4456 | 0.8 | 5 | 9 | 15.6851 | 3.776 | 2.9091 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 4457 | 0.8 | 5 | 10.3846 | 18.2022 | 2.4842 | 5.3333 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 4458 | 0.6 | 6.6667 | 10 | 17.6923 | 4 | 3.6923 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 4459 | 0.8 | 5 | 14.2105 | 23.8352 | 3.8065 | 5.8182 | 1 | 5 | 0.2 | 10 | 20
| 4460 | 1 | 4 | 10.3846 | 20.7618 | 2.6971 | 7.68 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 4461 | 0.8 | 5 | 14.2105 | 22.0073 | 2.7442 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 4462 | 1.2 | 3.3333 | 8.0597 | 15.331 | 2.3483 | 4.9231 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 4463 | 0.4 | 10 | 17.4194 | 29.4579 | 2.8957 | 9.1429 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 4464 | 0.2 | 20 | 16.3636 | 22.5212 | 2.6667 | 3.4909 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 4465 | 0.6 | 6.6667 | 6.6667 | 13.5528 | 3.5758 | 3.3103 | 1 | 5 | 0.6 | 3.3333 | 15
| 4466 | 0.8 | 5 | 11.7391 | 20.6292 | 3.8374 | 5.0526 | 1 | 5 | 0.4 | 5 | 15
| 4467 | 1 | 4 | 17.4194 | 24.1039 | 2.5106 | 4.1739 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 4468 | 0.6 | 6.6667 | 9 | 15.7279 | 2.8095 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 4469 | 1.2 | 3.3333 | 11.4894 | 18.8971 | 2.6077 | 4.8 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 4470 | 0.8 | 5 | 13.8462 | 19.5002 | 2.9873 | 2.6667 | 1 | 5 | 0.8 | 2.5 | 12.5
| 4471 | 1 | 4 | 13.8462 | 20.2623 | 2.8606 | 3.5556 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 4472 | 0.8 | 5 | 8.5714 | 14.7641 | 3.0452 | 3.1475 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 4473 | 0.8 | 5 | 13.1707 | 20.431 | 3.4203 | 3.84 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 4474 | 1 | 4 | 12.8571 | 20.7624 | 3.1053 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 4475 | 0.4 | 10 | 12.2727 | 19.2413 | 2.9686 | 4 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 4476 | 1 | 4 | 17.4194 | 25.8275 | 2.4082 | 6 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 4477 | 1.2 | 3.3333 | 13.5 | 23.3759 | 3.2552 | 6.6207 | 1.6 | 3.125 | 0.4 | 5 | 11.4583
| 4478 | 0.8 | 5 | 9.3103 | 16.087 | 3.5224 | 3.2542 | 1 | 5 | 0.2 | 10 | 20
| 4479 | 0.2 | 20 | 12.2727 | 19.4711 | 3.5758 | 3.6226 | 1.4 | 3.5714 | 0.2 | 10 | 33.5714
| 4480 | 0.4 | 10 | 13.8462 | 19.5313 | 2.5376 | 3.1475 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 4481 | 0.6 | 6.6667 | 7.6056 | 14.1278 | 2.3483 | 4.1739 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 4482 | 1 | 4 | 18 | 23.1349 | 2.2692 | 2.8657 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 4483 | 0.8 | 5 | 14.5946 | 22.2862 | 4.069 | 3.6226 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 4484 | 0.2 | 20 | 15 | 24.485 | 3.085 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 4485 | 0.2 | 20 | 17.4194 | 26.9417 | 3.5224 | 6 | 1 | 5 | 0.2 | 10 | 35
| 4486 | 0.2 | 20 | 11.0204 | 17.6138 | 2.5934 | 4 | 1.4 | 3.5714 | 0.6 | 3.3333 | 26.9048
| 4487 | 0.6 | 6.6667 | 15 | 26.8374 | 3.8374 | 8 | 1 | 5 | 0.6 | 3.3333 | 15
| 4488 | 0.6 | 6.6667 | 8.4375 | 14.3346 | 2.6971 | 3.2 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 4489 | 1.4 | 2.8571 | 9.1525 | 16.3618 | 2.7442 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 4490 | 0.6 | 6.6667 | 11.4894 | 21.0461 | 2.4456 | 7.1111 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 4491 | 1 | 4 | 10.3846 | 18.8977 | 3.3239 | 5.1892 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 4492 | 0.6 | 6.6667 | 15 | 23.1782 | 3.2552 | 4.9231 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 4493 | 0.8 | 5 | 9.8182 | 17.216 | 2.8263 | 4.5714 | 1 | 5 | 0.2 | 10 | 20
| 4494 | 0.2 | 20 | 11.7391 | 20.5314 | 3.6031 | 5.1892 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 4495 | 1.4 | 2.8571 | 9.1525 | 17.393 | 2.5934 | 5.6471 | 0.6 | 8.3333 | 0.8 | 2.5 | 13.6905
| 4496 | 0.6 | 6.6667 | 14.5946 | 22.1888 | 3.4203 | 4.1739 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 4497 | 0.8 | 5 | 10.8 | 21.3955 | 3.2109 | 7.3846 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 4498 | 0.4 | 10 | 14.5946 | 21.1013 | 2.6667 | 3.84 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 4499 | 1 | 4 | 9.1525 | 15.8505 | 2.5241 | 4.1739 | 1 | 5 | 0.4 | 5 | 14
| 4500 | 0.4 | 10 | 10.3846 | 20.4819 | 2.7126 | 7.3846 | 1 | 5 | 0.4 | 5 | 20
| 4501 | 1 | 4 | 10.5882 | 18.896 | 3.2552 | 5.0526 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 4502 | 1.2 | 3.3333 | 12 | 17.4953 | 2.7126 | 2.7826 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 4503 | 1.2 | 3.3333 | 11.0204 | 19.4398 | 3.4963 | 4.9231 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 4504 | 1 | 4 | 15.8824 | 22.8157 | 2.6667 | 4.2667 | 0.4 | 12.5 | 0.2 | 10 | 26.5
| 4505 | 0.6 | 6.6667 | 10.5882 | 19.2227 | 3.4453 | 5.1892 | 1 | 5 | 0.4 | 5 | 16.6667
| 4506 | 0.6 | 6.6667 | 10.3846 | 19.171 | 3.3007 | 5.4857 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 4507 | 1 | 4 | 17.4194 | 24.5996 | 2.4974 | 4.6829 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 4508 | 0.4 | 10 | 17.4194 | 25.422 | 2.95 | 5.0526 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 4509 | 1 | 4 | 11.4894 | 21.2053 | 3.5224 | 6.1935 | 1.8 | 2.7778 | 0.8 | 2.5 | 9.2778
| 4510 | 1.4 | 2.8571 | 10.5882 | 17.211 | 2.5376 | 4.0851 | 0.6 | 8.3333 | 0.6 | 3.3333 | 14.5238
| 4511 | 0.4 | 10 | 15 | 21.87 | 3.1053 | 3.7647 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 4512 | 0.4 | 10 | 11.0204 | 18.0207 | 2.8263 | 4.1739 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 4513 | 0.8 | 5 | 12.2727 | 19.507 | 2.5514 | 4.6829 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 4514 | 0.8 | 5 | 13.8462 | 23.2418 | 3.3957 | 6 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 4515 | 0.8 | 5 | 13.8462 | 20.4617 | 2.6971 | 3.9184 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 4516 | 0.6 | 6.6667 | 12.2727 | 18.9166 | 3.4963 | 3.1475 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 4517 | 1 | 4 | 11.0204 | 17.2336 | 3.3475 | 2.8657 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 4518 | 0.8 | 5 | 10.3846 | 18.6726 | 3.7165 | 4.5714 | 1 | 5 | 0.4 | 5 | 15
| 4519 | 1.2 | 3.3333 | 13.5 | 20.206 | 3.3957 | 3.3103 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 4520 | 0.4 | 10 | 12 | 19.716 | 2.7929 | 4.9231 | 1.4 | 3.5714 | 1 | 2 | 15.5714
| 4521 | 1.2 | 3.3333 | 17.4194 | 27.5178 | 2.9873 | 7.1111 | 1 | 5 | 0.4 | 5 | 13.3333
| 4522 | 1.2 | 3.3333 | 8.4375 | 15.1176 | 3.1892 | 3.4909 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 4523 | 1 | 4 | 13.1707 | 18.6518 | 3.1678 | 2.3133 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 4524 | 1 | 4 | 11.7391 | 20.3486 | 3.4203 | 5.1892 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 4525 | 1.2 | 3.3333 | 12.8571 | 22.4221 | 3.3714 | 6.1935 | 0.4 | 12.5 | 0.4 | 5 | 20.8333
| 4526 | 0.8 | 5 | 14.2105 | 22.1762 | 2.7765 | 5.1892 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 4527 | 0.8 | 5 | 11.0204 | 19.7524 | 3.085 | 5.6471 | 1 | 5 | 0.1 | 20 | 30
| 4528 | 0.6 | 6.6667 | 8.1818 | 16.6797 | 3.4453 | 5.0526 | 1 | 5 | 0.2 | 10 | 21.6667
| 4529 | 0.4 | 10 | 14.2105 | 20.5473 | 3.1892 | 3.1475 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 4530 | 0.2 | 20 | 10.1887 | 17.2748 | 3.1678 | 3.9184 | 1.2 | 4.1667 | 0.6 | 3.3333 | 27.5
| 4531 | 1 | 4 | 9.3103 | 16.9996 | 3.0064 | 4.6829 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 4532 | 1 | 4 | 11.0204 | 23.6077 | 2.9873 | 9.6 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 4533 | 0.4 | 10 | 13.8462 | 22.1301 | 2.6369 | 5.6471 | 1 | 5 | 0.4 | 5 | 20
| 4534 | 1.4 | 2.8571 | 10.8 | 21.7847 | 2.6369 | 8.3478 | 0.4 | 12.5 | 0.8 | 2.5 | 17.8571
| 4535 | 1.2 | 3.3333 | 13.8462 | 21.9396 | 2.6077 | 5.4857 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 4536 | 0.4 | 10 | 14.2105 | 21.9039 | 2.36 | 5.3333 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 4537 | 0.8 | 5 | 14.2105 | 20.5625 | 3.2552 | 3.0968 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 4538 | 0.4 | 10 | 13.1707 | 17.6101 | 2.1261 | 2.3133 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 4539 | 0.6 | 6.6667 | 8.8525 | 15.7858 | 2.6667 | 4.2667 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 4540 | 0.6 | 6.6667 | 12.8571 | 19.3407 | 2.5652 | 3.9184 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 4541 | 0.4 | 10 | 11.4894 | 18.4636 | 2.2913 | 4.6829 | 1 | 5 | 0.2 | 10 | 25
| 4542 | 0.2 | 20 | 9.3103 | 20.2438 | 3.5489 | 7.3846 | 1 | 5 | 0.8 | 2.5 | 27.5
| 4543 | 0.6 | 6.6667 | 14.5946 | 23.7624 | 3.1678 | 6 | 1.6 | 3.125 | 0.4 | 5 | 14.7917
| 4544 | 0.6 | 6.6667 | 8.3077 | 14.0076 | 3.1053 | 2.5946 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 4545 | 1.2 | 3.3333 | 11.0204 | 23.2721 | 2.6517 | 9.6 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 4546 | 0.6 | 6.6667 | 15 | 23.6809 | 3.3475 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 4547 | 0.4 | 10 | 13.5 | 31.1828 | 2.9136 | 14.7692 | 1 | 5 | 0.2 | 10 | 25
| 4548 | 0.8 | 5 | 9.4737 | 17.6941 | 3.1678 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 4549 | 1 | 4 | 11.4894 | 18.0804 | 2.8263 | 3.7647 | 1.4 | 3.5714 | 0.8 | 2.5 | 10.0714
| 4550 | 0.8 | 5 | 11.0204 | 17.531 | 2.5106 | 4 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 4551 | 1 | 4 | 11.7391 | 17.9986 | 2.6369 | 3.6226 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 4552 | 0.8 | 5 | 10.5882 | 17.6983 | 2.8434 | 4.2667 | 1.4 | 3.5714 | 1 | 2 | 10.5714
| 4553 | 1 | 4 | 12 | 23.2155 | 4.1043 | 7.1111 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 4554 | 1 | 4 | 12 | 18.2306 | 2.1455 | 4.0851 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 4555 | 0.6 | 6.6667 | 11.7391 | 19.2654 | 2.8434 | 4.6829 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 4556 | 0.8 | 5 | 15 | 24.5053 | 3.1053 | 6.4 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 4557 | 1 | 4 | 11.7391 | 18.0037 | 3.1678 | 3.0968 | 1 | 5 | 0.8 | 2.5 | 11.5
| 4558 | 0.6 | 6.6667 | 20.7692 | 27.8882 | 3.4963 | 3.6226 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 4559 | 1 | 4 | 19.2857 | 26.1458 | 2.5934 | 4.2667 | 0.4 | 12.5 | 0.2 | 10 | 26.5
| 4560 | 1.2 | 3.3333 | 16.875 | 23.7071 | 3.9664 | 2.8657 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 4561 | 0.4 | 10 | 16.3636 | 23.0139 | 2.1852 | 4.4651 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 4562 | 0.4 | 10 | 13.1707 | 19.5147 | 2.5792 | 3.7647 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 4563 | 0.6 | 6.6667 | 11.25 | 18.1446 | 2.8095 | 4.0851 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 4564 | 1.2 | 3.3333 | 7.8261 | 14.6022 | 3.3475 | 3.4286 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 4565 | 0.8 | 5 | 15.8824 | 24.3699 | 3.6875 | 4.8 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 4566 | 0.4 | 10 | 14.2105 | 22.845 | 3.4453 | 5.1892 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 4567 | 0.4 | 10 | 13.8462 | 21.5806 | 2.6818 | 5.0526 | 1 | 5 | 0.4 | 5 | 20
| 4568 | 0.8 | 5 | 12.5581 | 19.8903 | 2.9686 | 4.3636 | 1 | 5 | 0.8 | 2.5 | 12.5
| 4569 | 0.8 | 5 | 10 | 16.9035 | 2.6369 | 4.2667 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 4570 | 0.2 | 20 | 20.7692 | 30.068 | 3.1053 | 6.1935 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 4571 | 0.1 | 40 | 10.5882 | 18.2396 | 2.7283 | 4.9231 | 0.8 | 6.25 | 0.1 | 20 | 66.25
| 4572 | 0.2 | 20 | 12 | 20.2405 | 2.5934 | 5.6471 | 1 | 5 | 0.2 | 10 | 35
| 4573 | 0.2 | 20 | 13.5 | 23.6448 | 2.7602 | 7.3846 | 0.4 | 12.5 | 0.4 | 5 | 37.5
| 4574 | 0.4 | 10 | 13.5 | 20.932 | 2.8606 | 4.5714 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 4575 | 0.4 | 10 | 11.25 | 17.7507 | 3.3007 | 3.2 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 4576 | 0.2 | 20 | 8.8525 | 16.2133 | 2.8957 | 4.4651 | 1 | 5 | 0.2 | 10 | 35
| 4577 | 0.6 | 6.6667 | 12.2727 | 17.8278 | 2.4583 | 3.0968 | 1 | 5 | 0.2 | 10 | 21.6667
| 4578 | 1.2 | 3.3333 | 8.4375 | 16.3437 | 2.4205 | 5.4857 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 4579 | 0.8 | 5 | 11.7391 | 18.9474 | 2.6369 | 4.5714 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 4580 | 1 | 4 | 10 | 18.6557 | 3.6031 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 4581 | 1.2 | 3.3333 | 11.0204 | 18.1079 | 2.9136 | 4.1739 | 0.8 | 6.25 | 0.8 | 2.5 | 12.0833
| 4582 | 1 | 4 | 10.3846 | 17.9752 | 3.3239 | 4.2667 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 4583 | 0.4 | 10 | 11.4894 | 19.6678 | 3.1258 | 5.0526 | 1 | 5 | 0.1 | 20 | 35
| 4584 | 1.2 | 3.3333 | 11.7391 | 18.4069 | 3.0452 | 3.6226 | 1 | 5 | 0.2 | 10 | 18.3333
| 4585 | 1 | 4 | 10.8 | 16.5735 | 2.95 | 2.8235 | 1 | 5 | 0.2 | 10 | 19
| 4586 | 1 | 4 | 9.8182 | 18.8551 | 2.8434 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 4587 | 0.8 | 5 | 12.2727 | 18.4615 | 2.7602 | 3.4286 | 1.4 | 3.5714 | 0.8 | 2.5 | 11.0714
| 4588 | 0.8 | 5 | 15.8824 | 25.8581 | 3.5758 | 6.4 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 4589 | 0.2 | 20 | 9.6429 | 16.9938 | 2.9873 | 4.3636 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 4590 | 0.8 | 5 | 10.8 | 19.8452 | 3.0452 | 6 | 1 | 5 | 0.4 | 5 | 15
| 4591 | 0.8 | 5 | 10.3846 | 17.8191 | 3.1678 | 4.2667 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 4592 | 0.4 | 10 | 11.7391 | 18.5391 | 3.3714 | 3.4286 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 4593 | 0.6 | 6.6667 | 9.1525 | 16.4368 | 2.4842 | 4.8 | 1 | 5 | 0.4 | 5 | 16.6667
| 4594 | 0.8 | 5 | 11.0204 | 21.8109 | 3.9333 | 6.8571 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 4595 | 1.2 | 3.3333 | 11.25 | 19.146 | 2.8434 | 5.0526 | 1.4 | 3.5714 | 0.1 | 20 | 26.9048
| 4596 | 0.8 | 5 | 11.0204 | 17.9212 | 3.9008 | 3 | 0.2 | 25 | 0.6 | 3.3333 | 33.3333
| 4597 | 0.8 | 5 | 13.8462 | 21.5867 | 2.5514 | 5.1892 | 0.4 | 12.5 | 0.2 | 10 | 27.5
| 4598 | 0.2 | 20 | 12.2727 | 18.0011 | 2.7283 | 3 | 1 | 5 | 0.2 | 10 | 35
| 4599 | 0.6 | 6.6667 | 10 | 17.8974 | 3.6308 | 4.2667 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 4600 | 0.8 | 5 | 12.2727 | 19.0263 | 2.9136 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 4601 | 0.6 | 6.6667 | 16.3636 | 22.8509 | 2.9317 | 3.5556 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 4602 | 0.6 | 6.6667 | 12.2727 | 20.0413 | 2.9686 | 4.8 | 0.6 | 8.3333 | 0.1 | 20 | 35
| 4603 | 0.6 | 6.6667 | 11.7391 | 20.489 | 2.9317 | 5.8182 | 1 | 5 | 0.6 | 3.3333 | 15
| 4604 | 1.4 | 2.8571 | 12 | 19.1648 | 2.5934 | 4.5714 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 4605 | 0.8 | 5 | 12.5581 | 18.7529 | 2.8263 | 3.3684 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 4606 | 0.8 | 5 | 9.6429 | 17.2031 | 2.7602 | 4.8 | 1 | 5 | 0.4 | 5 | 15
| 4607 | 0.6 | 6.6667 | 24.5455 | 31.062 | 3.0256 | 3.4909 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 4608 | 0.4 | 10 | 15.4286 | 22.7058 | 2.9136 | 4.3636 | 1 | 5 | 0.4 | 5 | 20
| 4609 | 0.8 | 5 | 15.4286 | 25.6863 | 3.1467 | 7.1111 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 4610 | 0.4 | 10 | 11.7391 | 17.6965 | 2.8606 | 3.0968 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 4611 | 0.2 | 20 | 9.8182 | 18.1715 | 3.3007 | 5.0526 | 1 | 5 | 0.4 | 5 | 30
| 4612 | 0.8 | 5 | 15.4286 | 22.6189 | 3.1053 | 4.0851 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 4613 | 1 | 4 | 10.8 | 17.865 | 3.1467 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 4614 | 0.6 | 6.6667 | 13.8462 | 21.4359 | 2.6667 | 4.9231 | 0.4 | 12.5 | 0.8 | 2.5 | 21.6667
| 4615 | 1 | 4 | 11.25 | 19.4611 | 3.746 | 4.4651 | 1.4 | 3.5714 | 0.8 | 2.5 | 10.0714
| 4616 | 0.8 | 5 | 21.6 | 27.7651 | 2.3251 | 3.84 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 4617 | 1.6 | 2.5 | 13.5 | 19.7134 | 3.4706 | 2.7429 | 0.8 | 6.25 | 0.2 | 10 | 18.75
| 4618 | 0.8 | 5 | 10.3846 | 16.5088 | 3.3007 | 2.8235 | 1 | 5 | 0.4 | 5 | 15
| 4619 | 1.2 | 3.3333 | 10.5882 | 16.0478 | 2.7929 | 2.6667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 4620 | 0.4 | 10 | 15.4286 | 21.1999 | 3.2778 | 2.4935 | 1 | 5 | 0.4 | 5 | 20
| 4621 | 1 | 4 | 10 | 20.0875 | 3.6875 | 6.4 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 4622 | 0.6 | 6.6667 | 9.3103 | 17.7646 | 2.9686 | 5.4857 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 4623 | 0.1 | 40 | 15 | 22.8863 | 2.6971 | 5.1892 | 1 | 5 | 0.2 | 10 | 55
| 4624 | 0.6 | 6.6667 | 10.3846 | 19.9524 | 3.1678 | 6.4 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 4625 | 0.6 | 6.6667 | 11.25 | 21.4764 | 5.3034 | 4.9231 | 1 | 5 | 0.4 | 5 | 16.6667
| 4626 | 1.2 | 3.3333 | 9.4737 | 15.8846 | 3.2109 | 3.2 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 4627 | 0.8 | 5 | 9.8182 | 19.3124 | 3.3007 | 6.1935 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 4628 | 1 | 4 | 10.3846 | 17.8278 | 2.7602 | 4.6829 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 4629 | 0.6 | 6.6667 | 11.4894 | 18.8903 | 2.3483 | 5.0526 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 4630 | 0.6 | 6.6667 | 10.8 | 17.2365 | 2.7442 | 3.6923 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 4631 | 0.4 | 10 | 11.4894 | 17.6469 | 2.6667 | 3.4909 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 4632 | 1.2 | 3.3333 | 12.2727 | 18.4608 | 2.6971 | 3.4909 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 4633 | 1 | 4 | 12 | 22.4078 | 4.2143 | 6.1935 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 4634 | 0.6 | 6.6667 | 13.1707 | 20.0015 | 3.6308 | 3.2 | 1 | 5 | 0.6 | 3.3333 | 15
| 4635 | 1.6 | 2.5 | 12 | 19.2093 | 2.7442 | 4.4651 | 0.6 | 8.3333 | 0.4 | 5 | 15.8333
| 4636 | 1.4 | 2.8571 | 11.4894 | 19.5198 | 3.3475 | 4.6829 | 0.6 | 8.3333 | 0.6 | 3.3333 | 14.5238
| 4637 | 0.6 | 6.6667 | 11.0204 | 21.5608 | 4.1404 | 6.4 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 4638 | 1.2 | 3.3333 | 14.2105 | 25.3025 | 2.7442 | 8.3478 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 4639 | 0.6 | 6.6667 | 11.25 | 20.3948 | 2.5241 | 6.6207 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 4640 | 1.4 | 2.8571 | 10.5882 | 18.397 | 3.1258 | 4.6829 | 1 | 5 | 0.4 | 5 | 12.8571
| 4641 | 0.8 | 5 | 14.2105 | 21.5421 | 3.0649 | 4.2667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 4642 | 0.6 | 6.6667 | 10.3846 | 18.6983 | 2.3137 | 6 | 1 | 5 | 0.2 | 10 | 21.6667
| 4643 | 0.2 | 20 | 13.1707 | 20.4776 | 2.3838 | 4.9231 | 1 | 5 | 0.2 | 10 | 35
| 4644 | 1.2 | 3.3333 | 11.4894 | 18.5325 | 2.7765 | 4.2667 | 1.6 | 3.125 | 0.4 | 5 | 11.4583
| 4645 | 0.8 | 5 | 8.8525 | 23.288 | 4.3303 | 10.1053 | 1 | 5 | 0.4 | 5 | 15
| 4646 | 1.2 | 3.3333 | 10.5882 | 17.2888 | 2.8606 | 3.84 | 1 | 5 | 0.4 | 5 | 13.3333
| 4647 | 0.6 | 6.6667 | 10.8 | 17.2534 | 3.085 | 3.3684 | 1 | 5 | 0.4 | 5 | 16.6667
| 4648 | 0.8 | 5 | 17.4194 | 23.9412 | 2.6818 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 4649 | 0.8 | 5 | 12.8571 | 20.6583 | 2.878 | 4.9231 | 1 | 5 | 0.8 | 2.5 | 12.5
| 4650 | 1.2 | 3.3333 | 12.5581 | 19.9694 | 2.7283 | 4.6829 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 4651 | 0.4 | 10 | 10.5882 | 18.1647 | 2.7765 | 4.8 | 1.6 | 3.125 | 0.2 | 10 | 23.125
| 4652 | 0.4 | 10 | 13.8462 | 20.6846 | 3.3475 | 3.4909 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 4653 | 0.8 | 5 | 13.5 | 20.8629 | 3.2778 | 4.0851 | 1 | 5 | 0.2 | 10 | 20
| 4654 | 0.8 | 5 | 10.5882 | 18.6342 | 2.7126 | 5.3333 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 4655 | 0.4 | 10 | 12 | 18.9249 | 3.4963 | 3.4286 | 0.2 | 25 | 0.6 | 3.3333 | 38.3333
| 4656 | 0.8 | 5 | 13.8462 | 20.8765 | 2.6667 | 4.3636 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 4657 | 1 | 4 | 12 | 19.3744 | 2.1852 | 5.1892 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 4658 | 1.2 | 3.3333 | 10.3846 | 17.1122 | 3.6308 | 3.0968 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 4659 | 0.6 | 6.6667 | 15.4286 | 21.8034 | 3.0064 | 3.3684 | 1 | 5 | 0.4 | 5 | 16.6667
| 4660 | 0.8 | 5 | 12.5581 | 18.7807 | 3.1258 | 3.0968 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 4661 | 0.4 | 10 | 15.4286 | 23.3411 | 2.5792 | 5.3333 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 4662 | 0.1 | 40 | 13.5 | 19.4793 | 2.9317 | 3.0476 | 0.8 | 6.25 | 0.1 | 20 | 66.25
| 4663 | 0.4 | 10 | 20.7692 | 30.418 | 2.5376 | 7.1111 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 4664 | 1.2 | 3.3333 | 8.7097 | 18.8857 | 3.0649 | 7.1111 | 1 | 5 | 0.4 | 5 | 13.3333
| 4665 | 0.2 | 20 | 9.6429 | 17.2016 | 2.9873 | 4.5714 | 0.8 | 6.25 | 0.2 | 10 | 36.25
| 4666 | 1 | 4 | 11.7391 | 20.661 | 2.7283 | 6.1935 | 0.6 | 8.3333 | 0.1 | 20 | 32.3333
| 4667 | 0.4 | 10 | 15.8824 | 23.1537 | 2.3483 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 4668 | 0.8 | 5 | 11.4894 | 18.7563 | 3.776 | 3.4909 | 1 | 5 | 0.4 | 5 | 15
| 4669 | 1.6 | 2.5 | 13.5 | 19.6367 | 2.8263 | 3.3103 | 0.6 | 8.3333 | 0.2 | 10 | 20.8333
| 4670 | 0.4 | 10 | 13.8462 | 21.614 | 3.085 | 4.6829 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 4671 | 1 | 4 | 14.2105 | 20.7664 | 3.0649 | 3.4909 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 4672 | 1 | 4 | 15.4286 | 23.7989 | 4.3704 | 4 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 4673 | 0.8 | 5 | 16.3636 | 23.2042 | 2.6667 | 4.1739 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 4674 | 1 | 4 | 15.4286 | 20.8721 | 2.3959 | 3.0476 | 1 | 5 | 0.4 | 5 | 14
| 4675 | 1.2 | 3.3333 | 11.25 | 18.7389 | 3.9333 | 3.5556 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 4676 | 0.6 | 6.6667 | 10.3846 | 18.605 | 3.1678 | 5.0526 | 1 | 5 | 0.1 | 20 | 31.6667
| 4677 | 0.8 | 5 | 15.8824 | 24.7845 | 4.5385 | 4.3636 | 1 | 5 | 0.4 | 5 | 15
| 4678 | 0.4 | 10 | 14.2105 | 23.5299 | 3.1258 | 6.1935 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 4679 | 1.2 | 3.3333 | 15.8824 | 24.0086 | 2.7929 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 4680 | 0.4 | 10 | 15.4286 | 21.1349 | 2.3959 | 3.3103 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 4681 | 1 | 4 | 11.4894 | 18.2173 | 2.8095 | 3.9184 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 4682 | 0.4 | 10 | 12.8571 | 22.1631 | 3.6589 | 5.6471 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 4683 | 0.8 | 5 | 13.1707 | 19.622 | 2.8957 | 3.5556 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 4684 | 0.8 | 5 | 10.3846 | 17.0513 | 2.6667 | 4 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 4685 | 1 | 4 | 10.8 | 21.6871 | 3.776 | 7.1111 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 4686 | 0.2 | 20 | 14.5946 | 23.3264 | 2.9136 | 5.8182 | 0.8 | 6.25 | 0.1 | 20 | 46.25
| 4687 | 1 | 4 | 9.4737 | 17.7911 | 3.746 | 4.5714 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 4688 | 0.8 | 5 | 14.2105 | 21.2408 | 2.6667 | 4.3636 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 4689 | 0.8 | 5 | 11.4894 | 18.7003 | 3.1258 | 4.0851 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 4690 | 0.8 | 5 | 12 | 20.82 | 3.6308 | 5.1892 | 1 | 5 | 0.2 | 10 | 20
| 4691 | 0.6 | 6.6667 | 11.25 | 18.4404 | 3.1053 | 4.0851 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 4692 | 0.8 | 5 | 12.2727 | 19.3159 | 2.7765 | 4.2667 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 4693 | 0.1 | 40 | 14.5946 | 21.2747 | 3.1892 | 3.4909 | 1 | 5 | 0.2 | 10 | 55
| 4694 | 0.8 | 5 | 9 | 16.3436 | 2.4205 | 4.9231 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 4695 | 0.4 | 10 | 15.4286 | 23.2625 | 2.3483 | 5.4857 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 4696 | 0.4 | 10 | 11.7391 | 19.4224 | 2.7602 | 4.9231 | 0.2 | 25 | 0.1 | 20 | 55
| 4697 | 0.6 | 6.6667 | 12.8571 | 20.6759 | 2.8957 | 4.9231 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 4698 | 0.8 | 5 | 12.8571 | 20.7063 | 3.2778 | 4.5714 | 1 | 5 | 0.2 | 10 | 20
| 4699 | 0.8 | 5 | 14.5946 | 20.8724 | 3.2778 | 3 | 1 | 5 | 0.2 | 10 | 20
| 4700 | 1.6 | 2.5 | 12.5581 | 23.2067 | 2.9686 | 7.68 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10
| 4701 | 0.6 | 6.6667 | 9 | 17.1054 | 2.4583 | 5.6471 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 4702 | 1 | 4 | 12.5581 | 22.7012 | 3.5224 | 6.6207 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 4703 | 1.2 | 3.3333 | 10.8 | 22.403 | 3.2552 | 8.3478 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 4704 | 0.4 | 10 | 13.8462 | 20.3517 | 2.95 | 3.5556 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 4705 | 1.6 | 2.5 | 12.2727 | 20.615 | 2.5241 | 5.8182 | 1.2 | 4.1667 | 0.4 | 5 | 11.6667
| 4706 | 0.8 | 5 | 14.2105 | 21.9194 | 3.8689 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 4707 | 1 | 4 | 10.5882 | 17.7486 | 3.3957 | 3.7647 | 1 | 5 | 0.1 | 20 | 29
| 4708 | 0.6 | 6.6667 | 9.8182 | 17.6148 | 4.1043 | 3.6923 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 4709 | 0.8 | 5 | 13.1707 | 18.8681 | 2.4974 | 3.2 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 4710 | 0.4 | 10 | 9.8182 | 16.4385 | 3.4203 | 3.2 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 4711 | 0.6 | 6.6667 | 13.8462 | 22.9897 | 2.95 | 6.1935 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 4712 | 0.4 | 10 | 12.2727 | 21.5279 | 3.2552 | 6 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 4713 | 1 | 4 | 11.7391 | 20.9676 | 2.6077 | 6.6207 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 4714 | 1 | 4 | 12.2727 | 17.3169 | 2.4842 | 2.56 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 4715 | 1 | 4 | 9.3103 | 16.6712 | 2.8957 | 4.4651 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 4716 | 0.4 | 10 | 20 | 25.4399 | 2.9136 | 2.5263 | 1 | 5 | 0.4 | 5 | 20
| 4717 | 1 | 4 | 13.8462 | 25.3022 | 3.776 | 7.68 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 4718 | 0.4 | 10 | 11.7391 | 22.9133 | 2.8263 | 8.3478 | 1.6 | 3.125 | 0.6 | 3.3333 | 16.4583
| 4719 | 0.2 | 20 | 13.5 | 20.322 | 2.4583 | 4.3636 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 4720 | 0.8 | 5 | 10.3846 | 19.9553 | 2.95 | 6.6207 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 4721 | 0.6 | 6.6667 | 7.9412 | 15.1113 | 3.085 | 4.0851 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 4722 | 0.8 | 5 | 9.3103 | 17.7646 | 2.9686 | 5.4857 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 4723 | 1.2 | 3.3333 | 11.7391 | 18.6134 | 2.5106 | 4.3636 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 4724 | 0.8 | 5 | 14.5946 | 23.9819 | 2.9873 | 6.4 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 4725 | 1.4 | 2.8571 | 9.4737 | 15.5961 | 3.0256 | 3.0968 | 1 | 5 | 0.8 | 2.5 | 10.3571
| 4726 | 1.4 | 2.8571 | 11.7391 | 20.2642 | 2.878 | 5.6471 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 4727 | 0.2 | 20 | 14.5946 | 19.7198 | 2.5652 | 2.56 | 0.8 | 6.25 | 0.2 | 10 | 36.25
| 4728 | 0.4 | 10 | 15.8824 | 28.131 | 3.9008 | 8.3478 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 4729 | 1.2 | 3.3333 | 13.8462 | 20.897 | 3.2109 | 3.84 | 0.4 | 12.5 | 0.4 | 5 | 20.8333
| 4730 | 0.6 | 6.6667 | 13.8462 | 19.8386 | 2.8957 | 3.0968 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 4731 | 0.2 | 20 | 9.4737 | 14.3671 | 2.6077 | 2.2857 | 1 | 5 | 0.8 | 2.5 | 27.5
| 4732 | 0.8 | 5 | 20.7692 | 27.8421 | 3.2329 | 3.84 | 1 | 5 | 1 | 2 | 12
| 4733 | 1.2 | 3.3333 | 9 | 15.6783 | 2.9136 | 3.7647 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 4734 | 1.4 | 2.8571 | 18 | 24.5429 | 2.9873 | 3.5556 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 4735 | 0.6 | 6.6667 | 11.25 | 19.7732 | 3.4706 | 5.0526 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 4736 | 1 | 4 | 14.5946 | 21.4724 | 3.2552 | 3.6226 | 1 | 5 | 0.1 | 20 | 29
| 4737 | 0.4 | 10 | 15.8824 | 25.0221 | 3.8065 | 5.3333 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 4738 | 0.8 | 5 | 12 | 18.5693 | 2.4842 | 4.0851 | 1 | 5 | 0.8 | 2.5 | 12.5
| 4739 | 0.4 | 10 | 14.2105 | 20.8528 | 2.95 | 3.6923 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 4740 | 1 | 4 | 9.8182 | 17.3855 | 3.3007 | 4.2667 | 1 | 5 | 0.4 | 5 | 14
| 4741 | 1.6 | 2.5 | 8.8525 | 15.6081 | 3.4453 | 3.3103 | 1 | 5 | 0.6 | 3.3333 | 10.8333
| 4742 | 0.6 | 6.6667 | 12.5581 | 19.8813 | 4.069 | 3.2542 | 1 | 5 | 0.6 | 3.3333 | 15
| 4743 | 1.4 | 2.8571 | 12.5581 | 18.9041 | 3.5224 | 2.8235 | 1.4 | 3.5714 | 0.1 | 20 | 26.4286
| 4744 | 0.6 | 6.6667 | 11.7391 | 23.5833 | 3.4963 | 8.3478 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 4745 | 0.8 | 5 | 9 | 15.722 | 2.6369 | 4.0851 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 4746 | 0.8 | 5 | 9.4737 | 19.8054 | 2.6517 | 7.68 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 4747 | 0.6 | 6.6667 | 13.1707 | 21.0449 | 4.0342 | 3.84 | 1 | 5 | 0.4 | 5 | 16.6667
| 4748 | 1.2 | 3.3333 | 15.8824 | 23.6593 | 3.6031 | 4.1739 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 4749 | 0.6 | 6.6667 | 12.5581 | 20.3624 | 3.2329 | 4.5714 | 1 | 5 | 0.4 | 5 | 16.6667
| 4750 | 0.6 | 6.6667 | 12.2727 | 22.9699 | 2.6971 | 8 | 1 | 5 | 0.6 | 3.3333 | 15
| 4751 | 0.4 | 10 | 9.4737 | 15.5539 | 2.6517 | 3.4286 | 1 | 5 | 0.4 | 5 | 20
| 4752 | 1.4 | 2.8571 | 10.8 | 16.648 | 2.5376 | 3.3103 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 4753 | 1.4 | 2.8571 | 10 | 17.1604 | 3.3957 | 3.7647 | 0.6 | 8.3333 | 0.1 | 20 | 31.1905
| 4754 | 0.8 | 5 | 15.4286 | 23.8043 | 3.5758 | 4.8 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 4755 | 1.2 | 3.3333 | 14.2105 | 21.4009 | 3.1053 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 4756 | 1.4 | 2.8571 | 11.25 | 23.2101 | 3.2329 | 8.7273 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 4757 | 0.6 | 6.6667 | 12.8571 | 20.3834 | 2.8434 | 4.6829 | 1 | 5 | 0.2 | 10 | 21.6667
| 4758 | 0.8 | 5 | 9.4737 | 19.4984 | 2.9136 | 7.1111 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 4759 | 0.8 | 5 | 13.8462 | 22.3802 | 4.069 | 4.4651 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 4760 | 1.2 | 3.3333 | 13.1707 | 19.4257 | 2.3366 | 3.9184 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 4761 | 1.2 | 3.3333 | 10.3846 | 16.2474 | 2.3719 | 3.4909 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 4762 | 1.2 | 3.3333 | 20.7692 | 29.2933 | 2.5241 | 6 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 4763 | 0.8 | 5 | 14.5946 | 21.1435 | 3.5489 | 3 | 1 | 5 | 0.4 | 5 | 15
| 4764 | 0.4 | 10 | 12 | 21.5053 | 3.1053 | 6.4 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 4765 | 0.6 | 6.6667 | 11.0204 | 20.4618 | 4.2523 | 5.1892 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 4766 | 1.4 | 2.8571 | 11.0204 | 20.8728 | 4.0342 | 5.8182 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 4767 | 0.8 | 5 | 13.1707 | 18.9802 | 3.1053 | 2.7042 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 4768 | 1 | 4 | 15.4286 | 24.1409 | 4.5385 | 4.1739 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 4769 | 1 | 4 | 11.0204 | 16.7458 | 2.4712 | 3.2542 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 4770 | 1.2 | 3.3333 | 7.6056 | 15.0764 | 3.6308 | 3.84 | 1 | 5 | 0.2 | 10 | 18.3333
| 4771 | 0.6 | 6.6667 | 13.1707 | 21.7214 | 3.0649 | 5.4857 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 4772 | 0.4 | 10 | 10.1887 | 16.0493 | 2.8606 | 3 | 1 | 5 | 0.4 | 5 | 20
| 4773 | 1.2 | 3.3333 | 13.1707 | 20.0613 | 3.1258 | 3.7647 | 1.4 | 3.5714 | 0.8 | 2.5 | 9.4048
| 4774 | 1.6 | 2.5 | 10.8 | 18.2594 | 2.7765 | 4.6829 | 1.2 | 4.1667 | 0.4 | 5 | 11.6667
| 4775 | 1.4 | 2.8571 | 10.8 | 16.974 | 2.5514 | 3.6226 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 4776 | 0.6 | 6.6667 | 11.4894 | 19.76 | 3.3475 | 4.9231 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 4777 | 0.8 | 5 | 10.5882 | 17.985 | 2.9317 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 4778 | 1.4 | 2.8571 | 11.0204 | 19.5429 | 3.1892 | 5.3333 | 1.2 | 4.1667 | 0.1 | 20 | 27.0238
| 4779 | 0.8 | 5 | 10.1887 | 16.4238 | 2.7442 | 3.4909 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 4780 | 1.2 | 3.3333 | 9.8182 | 16.0246 | 3.0064 | 3.2 | 1 | 5 | 0.2 | 10 | 18.3333
| 4781 | 0.8 | 5 | 17.4194 | 28.4843 | 3.0649 | 8 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 4782 | 0.4 | 10 | 22.5 | 28.7215 | 2.7929 | 3.4286 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 4783 | 1.2 | 3.3333 | 12.5581 | 19.0942 | 3.0452 | 3.4909 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 4784 | 0.4 | 10 | 11.4894 | 18.0446 | 2.6369 | 3.9184 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 4785 | 1 | 4 | 15.4286 | 22.3786 | 2.95 | 4 | 1.8 | 2.7778 | 0.2 | 10 | 16.7778
| 4786 | 1 | 4 | 10.5882 | 17.189 | 3.0452 | 3.5556 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 4787 | 1 | 4 | 14.2105 | 20.9232 | 2.7126 | 4 | 1 | 5 | 0.1 | 20 | 29
| 4788 | 0.6 | 6.6667 | 14.5946 | 25.555 | 3.5758 | 7.3846 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 4789 | 0.6 | 6.6667 | 11.4894 | 18.1606 | 2.4974 | 4.1739 | 1 | 5 | 0.2 | 10 | 21.6667
| 4790 | 0.6 | 6.6667 | 9.3103 | 15.9767 | 2.8263 | 3.84 | 1.4 | 3.5714 | 0.8 | 2.5 | 12.7381
| 4791 | 0.8 | 5 | 8.5714 | 15.9917 | 3.4203 | 4 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 4792 | 1.4 | 2.8571 | 13.5 | 22.0624 | 2.7442 | 5.8182 | 0.6 | 8.3333 | 0.2 | 10 | 21.1905
| 4793 | 0.6 | 6.6667 | 14.5946 | 22.7728 | 2.36 | 5.8182 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 4794 | 1.4 | 2.8571 | 12 | 21.4264 | 3.2329 | 6.1935 | 1.4 | 3.5714 | 0.4 | 5 | 11.4286
| 4795 | 1.2 | 3.3333 | 12 | 17.0033 | 2.3366 | 2.6667 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 4796 | 0.4 | 10 | 9.6429 | 18.3156 | 3.0256 | 5.6471 | 1.6 | 3.125 | 0.2 | 10 | 23.125
| 4797 | 0.4 | 10 | 12.2727 | 19.9501 | 3.8374 | 3.84 | 0.4 | 12.5 | 0.8 | 2.5 | 25
| 4798 | 1 | 4 | 10.5882 | 17.2305 | 2.95 | 3.6923 | 1 | 5 | 0.4 | 5 | 14
| 4799 | 1.2 | 3.3333 | 13.5 | 20.9291 | 3.8065 | 3.6226 | 1.6 | 3.125 | 0.8 | 2.5 | 8.9583
| 4800 | 0.1 | 40 | 11.0204 | 17.5863 | 4.1043 | 2.4615 | 0.2 | 25 | 0.6 | 3.3333 | 68.3333
| 4801 | 1.2 | 3.3333 | 9.8182 | 15.0285 | 3.1678 | 2.0426 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 4802 | 0.2 | 20 | 12.2727 | 22.0826 | 3.1892 | 6.6207 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 4803 | 0.6 | 6.6667 | 14.5946 | 21.6455 | 3.2109 | 3.84 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 4804 | 0.6 | 6.6667 | 12.5581 | 22.1124 | 2.6971 | 6.8571 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 4805 | 1 | 4 | 9 | 17.6962 | 2.878 | 5.8182 | 1 | 5 | 0.4 | 5 | 14
| 4806 | 1.4 | 2.8571 | 10.8 | 19.267 | 3.2778 | 5.1892 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 4807 | 0.8 | 5 | 14.2105 | 21.0021 | 3.3007 | 3.4909 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 4808 | 1 | 4 | 13.5 | 18.8366 | 2.3366 | 3 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 4809 | 1 | 4 | 15.8824 | 24.7276 | 2.6517 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 4810 | 1 | 4 | 10.5882 | 20.6207 | 4.2143 | 5.8182 | 1 | 5 | 0.1 | 20 | 29
| 4811 | 0.6 | 6.6667 | 10.5882 | 17.2846 | 2.9317 | 3.7647 | 1.2 | 4.1667 | 1 | 2 | 12.8333
| 4812 | 1 | 4 | 21.6 | 32.6605 | 2.7126 | 8.3478 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 4813 | 0.8 | 5 | 11.25 | 19.9334 | 3.6308 | 5.0526 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 4814 | 0.4 | 10 | 10.5882 | 19.073 | 2.2913 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 4815 | 1.4 | 2.8571 | 13.1707 | 19.3816 | 3.2109 | 3 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 4816 | 1.2 | 3.3333 | 13.8462 | 19.9154 | 3.5758 | 2.4935 | 1.2 | 4.1667 | 0.1 | 20 | 27.5
| 4817 | 0.6 | 6.6667 | 9.3103 | 16.6904 | 2.6971 | 4.6829 | 1 | 5 | 0.2 | 10 | 21.6667
| 4818 | 0.6 | 6.6667 | 12.8571 | 23.3451 | 3.6308 | 6.8571 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 4819 | 0.6 | 6.6667 | 14.5946 | 22.9134 | 3.3957 | 4.9231 | 1 | 5 | 0.2 | 10 | 21.6667
| 4820 | 1 | 4 | 11.0204 | 16.1201 | 2.433 | 2.6667 | 1 | 5 | 0.1 | 20 | 29
| 4821 | 1 | 4 | 13.5 | 20.7763 | 2.5934 | 4.6829 | 1 | 5 | 0.4 | 5 | 14
| 4822 | 0.6 | 6.6667 | 10.8 | 18.6457 | 2.36 | 5.4857 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 4823 | 1 | 4 | 12.5581 | 19.7327 | 3.746 | 3.4286 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 4824 | 1 | 4 | 10.3846 | 23.7008 | 3.2109 | 10.1053 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 4825 | 0.2 | 20 | 17.4194 | 23.8447 | 3.2778 | 3.1475 | 0.4 | 12.5 | 0.1 | 20 | 52.5
| 4826 | 0.8 | 5 | 10.8 | 21.8145 | 2.6667 | 8.3478 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 4827 | 0.8 | 5 | 18 | 23.5864 | 3.3007 | 2.2857 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 4828 | 0.8 | 5 | 18 | 23.9571 | 2.8095 | 3.1475 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 4829 | 0.8 | 5 | 13.1707 | 21.1014 | 2.878 | 5.0526 | 1 | 5 | 1 | 2 | 12
| 4830 | 0.2 | 20 | 18 | 26.9922 | 3.6589 | 5.3333 | 1 | 5 | 0.2 | 10 | 35
| 4831 | 1 | 4 | 12 | 21.1602 | 2.7602 | 6.4 | 1.4 | 3.5714 | 0.8 | 2.5 | 10.0714
| 4832 | 1.4 | 2.8571 | 10.5882 | 16.3665 | 2.5241 | 3.2542 | 1 | 5 | 0.8 | 2.5 | 10.3571
| 4833 | 1.4 | 2.8571 | 13.8462 | 24.5764 | 4.3303 | 6.4 | 1 | 5 | 0.4 | 5 | 12.8571
| 4834 | 1 | 4 | 8.1818 | 18.0216 | 4.9167 | 4.9231 | 1 | 5 | 0.4 | 5 | 14
| 4835 | 0.8 | 5 | 11.25 | 18.4742 | 2.8606 | 4.3636 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 4836 | 1.2 | 3.3333 | 10.5882 | 18.4334 | 3.0452 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 4837 | 0.4 | 10 | 10.5882 | 18.6665 | 3.0256 | 5.0526 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 4838 | 0.8 | 5 | 15 | 20.5437 | 2.9136 | 2.6301 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 4839 | 1.2 | 3.3333 | 16.3636 | 25.4792 | 2.2584 | 6.8571 | 1 | 5 | 0.4 | 5 | 13.3333
| 4840 | 0.2 | 20 | 16.3636 | 23.4486 | 3.085 | 4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 27.5
| 4841 | 1.2 | 3.3333 | 10.5882 | 16.2927 | 2.6077 | 3.0968 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 4842 | 0.4 | 10 | 13.8462 | 23.311 | 2.6077 | 6.8571 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 4843 | 0.8 | 5 | 15.4286 | 21.3467 | 2.6077 | 3.3103 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 4844 | 1 | 4 | 16.3636 | 26.6718 | 3.6875 | 6.6207 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 4845 | 0.8 | 5 | 12.2727 | 19.051 | 3.6308 | 3.1475 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 4846 | 0.2 | 20 | 12.8571 | 21.0247 | 2.6818 | 5.4857 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 4847 | 1.4 | 2.8571 | 9.6429 | 16.922 | 3.1053 | 4.1739 | 0.6 | 8.3333 | 0.4 | 5 | 16.1905
| 4848 | 0.4 | 10 | 10.1887 | 19.3982 | 2.8095 | 6.4 | 1 | 5 | 0.4 | 5 | 20
| 4849 | 1 | 4 | 11.4894 | 19.0108 | 2.95 | 4.5714 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 4850 | 1 | 4 | 12.2727 | 21.6363 | 3.7165 | 5.6471 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 4851 | 0.6 | 6.6667 | 13.1707 | 20.154 | 3.0649 | 3.9184 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 4852 | 1 | 4 | 10.3846 | 16.0702 | 2.7765 | 2.9091 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 4853 | 0.6 | 6.6667 | 9.1525 | 16.6091 | 3.3714 | 4.0851 | 1.6 | 3.125 | 0.6 | 3.3333 | 13.125
| 4854 | 0.1 | 40 | 14.2105 | 23.272 | 3.5758 | 5.4857 | 0.8 | 6.25 | 0.2 | 10 | 56.25
| 4855 | 0.8 | 5 | 8.3077 | 14.5202 | 3.0649 | 3.1475 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 4856 | 0.6 | 6.6667 | 15 | 23.8957 | 2.8957 | 6 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 4857 | 0.4 | 10 | 13.5 | 20.6168 | 2.6517 | 4.4651 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 4858 | 0.8 | 5 | 20.7692 | 28.3767 | 3.5224 | 4.0851 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 4859 | 0.4 | 10 | 12.8571 | 20.1002 | 3.6875 | 3.5556 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 4860 | 0.8 | 5 | 15.8824 | 25.5375 | 3.2552 | 6.4 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 4861 | 0.2 | 20 | 11.0204 | 18.934 | 4.2909 | 3.6226 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 4862 | 0.6 | 6.6667 | 11.0204 | 18.1571 | 2.5652 | 4.5714 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 4863 | 0.8 | 5 | 10.1887 | 17.0493 | 2.8606 | 4 | 1 | 5 | 0.2 | 10 | 20
| 4864 | 1.2 | 3.3333 | 12 | 21.3972 | 2.7765 | 6.6207 | 1 | 5 | 0.4 | 5 | 13.3333
| 4865 | 0.8 | 5 | 11.7391 | 18.2498 | 2.5106 | 4 | 0.6 | 8.3333 | 0.1 | 20 | 33.3333
| 4866 | 1 | 4 | 12.8571 | 20.783 | 3.1258 | 4.8 | 1 | 5 | 0.2 | 10 | 19
| 4867 | 0.4 | 10 | 9.4737 | 18.4659 | 3.6589 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 4868 | 1 | 4 | 18 | 23.7793 | 2.9136 | 2.8657 | 1 | 5 | 0.4 | 5 | 14
| 4869 | 1.2 | 3.3333 | 13.5 | 19.7256 | 3.0256 | 3.2 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 4870 | 1.2 | 3.3333 | 16.875 | 25.9975 | 3.9333 | 5.1892 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 4871 | 1.2 | 3.3333 | 13.8462 | 20.0902 | 2.0702 | 4.1739 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 4872 | 1 | 4 | 13.5 | 22.6421 | 3.3239 | 5.8182 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 4873 | 1 | 4 | 15.8824 | 22.952 | 2.8957 | 4.1739 | 1 | 5 | 0.4 | 5 | 14
| 4874 | 0.8 | 5 | 9.4737 | 17.6129 | 2.95 | 5.1892 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 4875 | 0.8 | 5 | 11.25 | 18.3096 | 2.7929 | 4.2667 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 4876 | 0.6 | 6.6667 | 11.7391 | 22.1887 | 3.0649 | 7.3846 | 1 | 5 | 0.6 | 3.3333 | 15
| 4877 | 0.4 | 10 | 12.5581 | 18.2014 | 2.8606 | 2.7826 | 1 | 5 | 0.2 | 10 | 25
| 4878 | 0.6 | 6.6667 | 9.3103 | 16.4362 | 3.1258 | 4 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 4879 | 1 | 4 | 12 | 20.6163 | 3.9333 | 4.6829 | 1.4 | 3.5714 | 0.8 | 2.5 | 10.0714
| 4880 | 1.2 | 3.3333 | 11.7391 | 19.5044 | 2.7126 | 5.0526 | 1 | 5 | 0.2 | 10 | 18.3333
| 4881 | 1 | 4 | 11.4894 | 17.9937 | 4.1043 | 2.4 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 4882 | 1.2 | 3.3333 | 11.4894 | 21.8512 | 2.6818 | 7.68 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 4883 | 1.2 | 3.3333 | 10.1887 | 19.7062 | 3.3239 | 6.1935 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 4884 | 1.4 | 2.8571 | 12.2727 | 18.9707 | 2.5241 | 4.1739 | 1 | 5 | 0.4 | 5 | 12.8571
| 4885 | 0.6 | 6.6667 | 15.4286 | 21.1033 | 2.4205 | 3.2542 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 4886 | 0.4 | 10 | 15.8824 | 22.6964 | 2.8957 | 3.9184 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 4887 | 1 | 4 | 22.5 | 30.9528 | 4.4528 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 4888 | 0.2 | 20 | 13.8462 | 21.8069 | 3.2778 | 4.6829 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 4889 | 0.8 | 5 | 16.875 | 24.2113 | 3.4963 | 3.84 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 4890 | 1.2 | 3.3333 | 12.2727 | 18.4438 | 3.3475 | 2.8235 | 1.8 | 2.7778 | 0.4 | 5 | 11.1111
| 4891 | 1.2 | 3.3333 | 9.1525 | 18.2259 | 3.2552 | 5.8182 | 1 | 5 | 0.4 | 5 | 13.3333
| 4892 | 0.6 | 6.6667 | 10 | 17.4812 | 3.7165 | 3.7647 | 0.2 | 25 | 0.2 | 10 | 41.6667
| 4893 | 0.8 | 5 | 12.8571 | 19.014 | 2.7283 | 3.4286 | 1 | 5 | 0.4 | 5 | 15
| 4894 | 0.2 | 20 | 10.1887 | 17.5447 | 2.433 | 4.9231 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 4895 | 0.4 | 10 | 12.8571 | 20.1888 | 2.7602 | 4.5714 | 1 | 5 | 0.2 | 10 | 25
| 4896 | 0.8 | 5 | 12.8571 | 19.552 | 2.7765 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 4897 | 0.8 | 5 | 12.5581 | 18.9835 | 3.2778 | 3.1475 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 4898 | 0.6 | 6.6667 | 10.8 | 18.8127 | 3.746 | 4.2667 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 4899 | 0.6 | 6.6667 | 15.8824 | 22.9698 | 2.9136 | 4.1739 | 1 | 5 | 0.6 | 3.3333 | 15
| 4900 | 0.6 | 6.6667 | 12 | 18.718 | 2.878 | 3.84 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 4901 | 1 | 4 | 13.1707 | 21.8525 | 2.6818 | 6 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 4902 | 0.2 | 20 | 12 | 24.5636 | 2.4583 | 10.1053 | 0.4 | 12.5 | 0.2 | 10 | 42.5
| 4903 | 0.2 | 20 | 10.8 | 20.2364 | 2.5792 | 6.8571 | 1 | 5 | 0.4 | 5 | 30
| 4904 | 0.8 | 5 | 15 | 21.7617 | 2.8434 | 3.9184 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 4905 | 0.6 | 6.6667 | 18 | 24.8099 | 3.9008 | 2.9091 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 4906 | 1.2 | 3.3333 | 9.8182 | 16.3978 | 2.216 | 4.3636 | 1.6 | 3.125 | 0.8 | 2.5 | 8.9583
| 4907 | 1 | 4 | 10.5882 | 17.0046 | 2.6517 | 3.7647 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 4908 | 0.6 | 6.6667 | 13.8462 | 20.2927 | 2.6818 | 3.7647 | 1 | 5 | 0.4 | 5 | 16.6667
| 4909 | 0.6 | 6.6667 | 15.4286 | 23.6745 | 2.7602 | 5.4857 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 4910 | 1.8 | 2.2222 | 11.7391 | 17.8495 | 2.6818 | 3.4286 | 1.4 | 3.5714 | 0.4 | 5 | 10.7937
| 4911 | 0.8 | 5 | 24.5455 | 32.699 | 3.4706 | 4.6829 | 1 | 5 | 0.4 | 5 | 15
| 4912 | 1 | 4 | 14.5946 | 24.0759 | 2.8606 | 6.6207 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 4913 | 0.6 | 6.6667 | 15.8824 | 23.6004 | 3.1467 | 4.5714 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 4914 | 1 | 4 | 9.8182 | 16.4189 | 3.0452 | 3.5556 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 4915 | 0.8 | 5 | 11.7391 | 19.1091 | 3.0064 | 4.3636 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 4916 | 1 | 4 | 9.3103 | 15.9184 | 2.8434 | 3.7647 | 1 | 5 | 0.4 | 5 | 14
| 4917 | 0.8 | 5 | 10.5882 | 19.347 | 2.5652 | 6.1935 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 4918 | 0.8 | 5 | 28.4211 | 35.1231 | 2.237 | 4.4651 | 1.6 | 3.125 | 0.2 | 10 | 18.125
| 4919 | 0.4 | 10 | 10 | 16.6505 | 2.3838 | 4.2667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 4920 | 1.2 | 3.3333 | 15.8824 | 22.9743 | 2.7283 | 4.3636 | 1 | 5 | 0.2 | 10 | 18.3333
| 4921 | 1 | 4 | 13.5 | 24.1673 | 2.9873 | 7.68 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 4922 | 1 | 4 | 8.8525 | 15.6665 | 2.8957 | 3.9184 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 4923 | 0.8 | 5 | 8.8525 | 14.7283 | 2.7283 | 3.1475 | 0.4 | 12.5 | 0.8 | 2.5 | 20
| 4924 | 1 | 4 | 12.2727 | 20.3216 | 3.1258 | 4.9231 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 4925 | 0.6 | 6.6667 | 11.4894 | 19.1775 | 3.6031 | 4.0851 | 1 | 5 | 0.4 | 5 | 16.6667
| 4926 | 1.2 | 3.3333 | 11.25 | 18.0187 | 3.2778 | 3.4909 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 4927 | 1.2 | 3.3333 | 13.5 | 21.4175 | 2.7283 | 5.1892 | 1.4 | 3.5714 | 0.1 | 20 | 26.9048
| 4928 | 0.4 | 10 | 12.2727 | 18.2991 | 2.8263 | 3.2 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 4929 | 1 | 4 | 10.8 | 17.4467 | 2.7283 | 3.9184 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 4930 | 1 | 4 | 11.7391 | 19.2844 | 2.6222 | 4.9231 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 4931 | 0.6 | 6.6667 | 14.5946 | 23.5766 | 3.4963 | 5.4857 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 4932 | 0.6 | 6.6667 | 10 | 16.9976 | 3.2329 | 3.7647 | 1 | 5 | 0.6 | 3.3333 | 15
| 4933 | 1 | 4 | 14.5946 | 21.0082 | 3.0452 | 3.3684 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 4934 | 0.8 | 5 | 8.5714 | 15.0274 | 2.5376 | 3.9184 | 1 | 5 | 0.4 | 5 | 15
| 4935 | 0.8 | 5 | 11.4894 | 19.6678 | 3.1258 | 5.0526 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 4936 | 0.6 | 6.6667 | 12 | 22.832 | 2.4842 | 8.3478 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 4937 | 0.4 | 10 | 9 | 14.5306 | 2.8263 | 2.7042 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 4938 | 0.6 | 6.6667 | 11.4894 | 19.3902 | 3.9008 | 4 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 4939 | 0.8 | 5 | 12 | 17.977 | 2.6667 | 3.3103 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 4940 | 0.6 | 6.6667 | 10.1887 | 18.0434 | 2.9317 | 4.9231 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 4941 | 1 | 4 | 8.5714 | 18.4159 | 2.9873 | 6.8571 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 4942 | 0.8 | 5 | 9.6429 | 16.7935 | 2.5792 | 4.5714 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 4943 | 0.2 | 20 | 11.0204 | 16.8138 | 2.5934 | 3.2 | 1.4 | 3.5714 | 0.6 | 3.3333 | 26.9048
| 4944 | 0.6 | 6.6667 | 12 | 17.7634 | 2.8095 | 2.9538 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 4945 | 1.2 | 3.3333 | 12.2727 | 21.8194 | 3.1467 | 6.4 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 4946 | 1 | 4 | 10.5882 | 16.4569 | 3.1258 | 2.7429 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 4947 | 0.8 | 5 | 10 | 19.447 | 2.8263 | 6.6207 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 4948 | 0.6 | 6.6667 | 15.4286 | 21.247 | 2.1261 | 3.6923 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 4949 | 0.6 | 6.6667 | 12.2727 | 18.9726 | 3.6031 | 3.0968 | 0.6 | 8.3333 | 0.8 | 2.5 | 17.5
| 4950 | 1.4 | 2.8571 | 13.1707 | 20.4329 | 2.5792 | 4.6829 | 1.2 | 4.1667 | 0.1 | 20 | 27.0238
| 4951 | 0.6 | 6.6667 | 10.5882 | 18.4787 | 3.7165 | 4.1739 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 4952 | 0.2 | 20 | 13.8462 | 23.0895 | 2.8434 | 6.4 | 1 | 5 | 0.4 | 5 | 30
| 4953 | 0.8 | 5 | 8.8525 | 18.0912 | 3.0452 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 4954 | 0.8 | 5 | 23.4783 | 31.1746 | 3.5224 | 4.1739 | 0.8 | 6.25 | 1 | 2 | 13.25
| 4955 | 0.6 | 6.6667 | 14.2105 | 19.9041 | 2.3251 | 3.3684 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 4956 | 1 | 4 | 8.5714 | 16.7707 | 3.1467 | 5.0526 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 4957 | 0.8 | 5 | 16.3636 | 21.9985 | 2.0793 | 3.5556 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 4958 | 0.6 | 6.6667 | 12.2727 | 21.8758 | 3.6031 | 6 | 1 | 5 | 0.4 | 5 | 16.6667
| 4959 | 0.8 | 5 | 15.8824 | 22.5939 | 2.5376 | 4.1739 | 1 | 5 | 0.1 | 20 | 30
| 4960 | 0.8 | 5 | 13.8462 | 21.0718 | 3.6031 | 3.6226 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 4961 | 1.4 | 2.8571 | 12.2727 | 23.718 | 2.3024 | 9.1429 | 0.6 | 8.3333 | 0.6 | 3.3333 | 14.5238
| 4962 | 0.8 | 5 | 15 | 20.8405 | 2.7929 | 3.0476 | 0.4 | 12.5 | 0.2 | 10 | 27.5
| 4963 | 0.8 | 5 | 13.5 | 22.2987 | 3.746 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 4964 | 1 | 4 | 15.4286 | 22.6136 | 3.4203 | 3.7647 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 4965 | 0.6 | 6.6667 | 7.2 | 15.3956 | 3.0064 | 5.1892 | 1 | 5 | 0.4 | 5 | 16.6667
| 4966 | 1 | 4 | 11.25 | 18.3793 | 3.2109 | 3.9184 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 4967 | 1.2 | 3.3333 | 15 | 22.2079 | 2.1553 | 5.0526 | 1 | 5 | 0.4 | 5 | 13.3333
| 4968 | 0.6 | 6.6667 | 11.25 | 20.6327 | 3.1892 | 6.1935 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 4969 | 1 | 4 | 12.8571 | 20.7088 | 3.9333 | 3.9184 | 1 | 5 | 0.2 | 10 | 19
| 4970 | 1 | 4 | 11.0204 | 19.4608 | 2.6222 | 5.8182 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 4971 | 0.8 | 5 | 11.4894 | 18.1099 | 3.0649 | 3.5556 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 4972 | 1.2 | 3.3333 | 12 | 18.4852 | 2.7929 | 3.6923 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 4973 | 0.8 | 5 | 8.5714 | 18.0938 | 3.5224 | 6 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 4974 | 1 | 4 | 11.7391 | 20.8351 | 3.2778 | 5.8182 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 4975 | 0.8 | 5 | 15 | 21.6257 | 3.3714 | 3.2542 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 4976 | 1 | 4 | 16.3636 | 23.3981 | 4.3303 | 2.7042 | 0.8 | 6.25 | 1 | 2 | 12.25
| 4977 | 1 | 4 | 14.2105 | 25.2557 | 3.0452 | 8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 4978 | 0.6 | 6.6667 | 13.5 | 23.0911 | 4.5385 | 5.0526 | 1 | 5 | 0.4 | 5 | 16.6667
| 4979 | 0.8 | 5 | 15.8824 | 23.7436 | 4.3704 | 3.4909 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 4980 | 1.2 | 3.3333 | 9.3103 | 17.1662 | 2.6667 | 5.1892 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 4981 | 0.8 | 5 | 10.1887 | 17.0077 | 2.2476 | 4.5714 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 4982 | 0.4 | 10 | 12.8571 | 22.4513 | 3.776 | 5.8182 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 4983 | 1 | 4 | 10.5882 | 21.5877 | 2.6517 | 8.3478 | 1 | 5 | 0.2 | 10 | 19
| 4984 | 0.6 | 6.6667 | 12.5581 | 22.9879 | 3.0452 | 7.3846 | 1 | 5 | 0.4 | 5 | 16.6667
| 4985 | 1.6 | 2.5 | 13.1707 | 18.9625 | 2.7442 | 3.0476 | 0.8 | 6.25 | 0.4 | 5 | 13.75
| 4986 | 0.6 | 6.6667 | 24.5455 | 33.0353 | 3.3007 | 5.1892 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 4987 | 1.2 | 3.3333 | 10.3846 | 16.3682 | 2.2913 | 3.6923 | 1 | 5 | 1 | 2 | 10.3333
| 4988 | 1 | 4 | 15.4286 | 24.5135 | 3.085 | 6 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 4989 | 1.4 | 2.8571 | 16.875 | 27.9993 | 2.7765 | 8.3478 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 4990 | 0.4 | 10 | 9.3103 | 18.3922 | 2.6818 | 6.4 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 4991 | 1.6 | 2.5 | 14.2105 | 25.4129 | 3.5224 | 7.68 | 0.6 | 8.3333 | 0.4 | 5 | 15.8333
| 4992 | 0.6 | 6.6667 | 14.5946 | 22.2859 | 2.2056 | 5.4857 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 4993 | 0.6 | 6.6667 | 10.8 | 20.9941 | 2.8095 | 7.3846 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 4994 | 0.6 | 6.6667 | 13.1707 | 21.6911 | 3.8374 | 4.6829 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 4995 | 0.2 | 20 | 10.8 | 17.1602 | 2.9317 | 3.4286 | 0.8 | 6.25 | 0.2 | 10 | 36.25
| 4996 | 1.2 | 3.3333 | 11.4894 | 19.7131 | 3.3007 | 4.9231 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 4997 | 1.6 | 2.5 | 9.6429 | 16.2319 | 3.8065 | 2.7826 | 1 | 5 | 0.2 | 10 | 17.5
| 4998 | 0.6 | 6.6667 | 15 | 20.8476 | 2.5934 | 3.2542 | 1 | 5 | 0.1 | 20 | 31.6667
| 4999 | 0.6 | 6.6667 | 12.5581 | 23.3023 | 2.7442 | 8 | 1.6 | 3.125 | 0.8 | 2.5 | 12.2917
| 5000 | 1.2 | 3.3333 | 13.8462 | 20.0075 | 2.7929 | 3.3684 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 5001 | 0.6 | 6.6667 | 12.2727 | 21.1541 | 3.3957 | 5.4857 | 1 | 5 | 0.4 | 5 | 16.6667
| 5002 | 0.4 | 10 | 11.25 | 21.2963 | 3.1892 | 6.8571 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 5003 | 0.8 | 5 | 18.6207 | 27.1458 | 2.878 | 5.6471 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 5004 | 0.6 | 6.6667 | 13.5 | 21.146 | 2.5934 | 5.0526 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 5005 | 1.2 | 3.3333 | 15.8824 | 22.0887 | 3.0064 | 3.2 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 5006 | 1 | 4 | 12.5581 | 19.559 | 3.4453 | 3.5556 | 1 | 5 | 0.2 | 10 | 19
| 5007 | 0.2 | 20 | 11.25 | 17.1425 | 2.5241 | 3.3684 | 1 | 5 | 0.1 | 20 | 45
| 5008 | 0.4 | 10 | 11.25 | 27.572 | 2.6077 | 13.7143 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 5009 | 0.8 | 5 | 14.2105 | 28.9077 | 2.6971 | 12 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 5010 | 1 | 4 | 11.4894 | 19.901 | 2.5934 | 5.8182 | 1 | 5 | 0.2 | 10 | 19
| 5011 | 0.8 | 5 | 12 | 20.0672 | 2.878 | 5.1892 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 5012 | 0.8 | 5 | 12 | 19.4746 | 3.3007 | 4.1739 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 5013 | 0.4 | 10 | 14.5946 | 23.7968 | 3.7165 | 5.4857 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 5014 | 1 | 4 | 11.0204 | 17.9076 | 3.9333 | 2.9538 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 5015 | 0.4 | 10 | 14.2105 | 19.6976 | 2.7442 | 2.7429 | 1 | 5 | 0.8 | 2.5 | 17.5
| 5016 | 0.4 | 10 | 12.2727 | 18.5086 | 2.4712 | 3.7647 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 5017 | 0.6 | 6.6667 | 13.5 | 22.7192 | 3.0256 | 6.1935 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 5018 | 1 | 4 | 13.5 | 21.4158 | 3.2329 | 4.6829 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 5019 | 1.2 | 3.3333 | 15.8824 | 22.5251 | 2.878 | 3.7647 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 5020 | 0.8 | 5 | 12.2727 | 20.8565 | 3.9008 | 4.6829 | 1 | 5 | 0.2 | 10 | 20
| 5021 | 0.8 | 5 | 15.8824 | 23.9313 | 3.1258 | 4.9231 | 1 | 5 | 0.1 | 20 | 30
| 5022 | 0.2 | 20 | 16.3636 | 22.5402 | 2.4842 | 3.6923 | 1.2 | 4.1667 | 0.1 | 20 | 44.1667
| 5023 | 0.2 | 20 | 16.875 | 24.5943 | 2.6667 | 5.0526 | 1.2 | 4.1667 | 0.8 | 2.5 | 26.6667
| 5024 | 1.2 | 3.3333 | 15 | 21.1922 | 2.1071 | 4.0851 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 5025 | 0.8 | 5 | 10.5882 | 17.2102 | 2.2584 | 4.3636 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 5026 | 0.6 | 6.6667 | 8.4375 | 15.6542 | 2.95 | 4.2667 | 1 | 5 | 0.2 | 10 | 21.6667
| 5027 | 1.4 | 2.8571 | 12.8571 | 23.6221 | 3.085 | 7.68 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 5028 | 0.8 | 5 | 10.8 | 17.257 | 3.1467 | 3.3103 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 5029 | 1.2 | 3.3333 | 16.3636 | 23.9976 | 3.5489 | 4.0851 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 5030 | 1.2 | 3.3333 | 15 | 22.5329 | 4.1043 | 3.4286 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.1667
| 5031 | 0.6 | 6.6667 | 8.5714 | 16.0737 | 2.5792 | 4.9231 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 5032 | 0.6 | 6.6667 | 10.8 | 16.8952 | 2.6667 | 3.4286 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 5033 | 0.8 | 5 | 15 | 22.351 | 2.9873 | 4.3636 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 5034 | 1.4 | 2.8571 | 16.875 | 25.5094 | 3.4453 | 5.1892 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 5035 | 0.2 | 20 | 18.6207 | 25.1157 | 3.3475 | 3.1475 | 0.8 | 6.25 | 0.2 | 10 | 36.25
| 5036 | 1.4 | 2.8571 | 11.0204 | 18.6169 | 2.9136 | 4.6829 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 5037 | 1 | 4 | 10 | 15.2833 | 2.1357 | 3.1475 | 1 | 5 | 0.2 | 10 | 19
| 5038 | 0.6 | 6.6667 | 9.4737 | 16.3253 | 2.2802 | 4.5714 | 1.4 | 3.5714 | 0.8 | 2.5 | 12.7381
| 5039 | 0.4 | 10 | 16.3636 | 23.131 | 2.5934 | 4.1739 | 1 | 5 | 0.2 | 10 | 25
| 5040 | 0.6 | 6.6667 | 8.4375 | 14.6109 | 3.1258 | 3.0476 | 1 | 5 | 0.2 | 10 | 21.6667
| 5041 | 0.4 | 10 | 12.8571 | 20.7361 | 2.8263 | 5.0526 | 1.4 | 3.5714 | 0.8 | 2.5 | 16.0714
| 5042 | 0.2 | 20 | 10.8 | 17.1651 | 2.8095 | 3.5556 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 5043 | 1 | 4 | 7.7143 | 15.8857 | 3.3714 | 4.8 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 5044 | 0.8 | 5 | 13.1707 | 19.7408 | 2.6517 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 5045 | 1.4 | 2.8571 | 11.25 | 17.9563 | 3.2778 | 3.4286 | 0.8 | 6.25 | 0.8 | 2.5 | 11.6071
| 5046 | 1.4 | 2.8571 | 10.3846 | 19.5599 | 4.2523 | 4.9231 | 0.4 | 12.5 | 0.8 | 2.5 | 17.8571
| 5047 | 1 | 4 | 12.2727 | 24.0911 | 3.4706 | 8.3478 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 5048 | 0.4 | 10 | 9.6429 | 17.4695 | 3.2552 | 4.5714 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 5049 | 0.6 | 6.6667 | 9 | 16.1886 | 3.4963 | 3.6923 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 5050 | 1.2 | 3.3333 | 8.0597 | 17.8363 | 4.2909 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 5051 | 1.6 | 2.5 | 10 | 19.9824 | 2.3024 | 7.68 | 1 | 5 | 0.1 | 20 | 27.5
| 5052 | 0.6 | 6.6667 | 10 | 16.6948 | 2.7765 | 3.9184 | 1 | 5 | 0.2 | 10 | 21.6667
| 5053 | 1.2 | 3.3333 | 11.25 | 19.2392 | 3.1892 | 4.8 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 5054 | 0.6 | 6.6667 | 14.2105 | 20.562 | 2.8606 | 3.4909 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 5055 | 1 | 4 | 13.1707 | 22.2834 | 2.7126 | 6.4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 5056 | 1 | 4 | 9.6429 | 16.2048 | 3.0064 | 3.5556 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 5057 | 0.6 | 6.6667 | 13.8462 | 19.4013 | 2.4583 | 3.0968 | 1 | 5 | 0.6 | 3.3333 | 15
| 5058 | 0.6 | 6.6667 | 10.3846 | 18.0965 | 3.4453 | 4.2667 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 5059 | 0.8 | 5 | 12.8571 | 21.1649 | 3.2552 | 5.0526 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 5060 | 0.4 | 10 | 10.5882 | 20.0335 | 3.4453 | 6 | 1 | 5 | 0.8 | 2.5 | 17.5
| 5061 | 1 | 4 | 12.5581 | 21.0747 | 3.7165 | 4.8 | 1 | 5 | 0.1 | 20 | 29
| 5062 | 0.2 | 20 | 10.5882 | 19.3954 | 5.5529 | 3.2542 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 5063 | 0.8 | 5 | 12 | 23.1478 | 2.4205 | 8.7273 | 0.4 | 12.5 | 0.8 | 2.5 | 20
| 5064 | 0.8 | 5 | 11.7391 | 19.455 | 3.6308 | 4.0851 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 5065 | 1.2 | 3.3333 | 9.3103 | 18.0394 | 3.3957 | 5.3333 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 5066 | 1.2 | 3.3333 | 11.4894 | 19.9965 | 2.1071 | 6.4 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 5067 | 0.4 | 10 | 11.0204 | 18.6322 | 3.1467 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 5068 | 0.6 | 6.6667 | 20 | 28.5506 | 3.0649 | 5.4857 | 1 | 5 | 0.4 | 5 | 16.6667
| 5069 | 0.4 | 10 | 10.1887 | 17.6705 | 2.6818 | 4.8 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 5070 | 1.2 | 3.3333 | 13.5 | 20.8643 | 2.7929 | 4.5714 | 1 | 5 | 0.2 | 10 | 18.3333
| 5071 | 1 | 4 | 9 | 15.8273 | 2.9873 | 3.84 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 5072 | 1 | 4 | 21.6 | 32.4552 | 3.4706 | 7.3846 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 5073 | 0.4 | 10 | 12.5581 | 19.4586 | 3.2778 | 3.6226 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 5074 | 1 | 4 | 19.2857 | 26.5698 | 2.7126 | 4.5714 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 5075 | 1 | 4 | 12 | 23.0064 | 3.0064 | 8 | 1 | 5 | 0.8 | 2.5 | 11.5
| 5076 | 0.6 | 6.6667 | 10 | 16.9115 | 2.8263 | 4.0851 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 5077 | 0.6 | 6.6667 | 8.8525 | 16.3503 | 3.3239 | 4.1739 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 5078 | 0.8 | 5 | 12.2727 | 18.4005 | 2.6369 | 3.4909 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 5079 | 0.4 | 10 | 10.5882 | 15.8692 | 2.3719 | 2.9091 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 5080 | 1 | 4 | 22.5 | 28.705 | 2.7765 | 3.4286 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 5081 | 0.4 | 10 | 12.8571 | 21.0466 | 4.1043 | 4.0851 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 5082 | 0.8 | 5 | 13.1707 | 18.4279 | 2.6971 | 2.56 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 5083 | 0.1 | 40 | 10.5882 | 16.7423 | 3.3714 | 2.7826 | 1 | 5 | 0.4 | 5 | 50
| 5084 | 0.6 | 6.6667 | 23.4783 | 31.6739 | 3.3957 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 5085 | 1.6 | 2.5 | 9.8182 | 16.7332 | 2.5514 | 4.3636 | 0.8 | 6.25 | 0.4 | 5 | 13.75
| 5086 | 0.6 | 6.6667 | 15.4286 | 20.4217 | 2.6517 | 2.3415 | 1.6 | 3.125 | 0.4 | 5 | 14.7917
| 5087 | 1 | 4 | 12.2727 | 19.783 | 3.0452 | 4.4651 | 1 | 5 | 0.4 | 5 | 14
| 5088 | 1 | 4 | 13.5 | 25.0706 | 2.8434 | 8.7273 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 5089 | 1 | 4 | 9.3103 | 17.977 | 2.6667 | 6 | 1 | 5 | 0.2 | 10 | 19
| 5090 | 0.8 | 5 | 13.5 | 18.5706 | 2.5106 | 2.56 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 5091 | 0.4 | 10 | 11.25 | 17.6933 | 3.3957 | 3.0476 | 1 | 5 | 0.4 | 5 | 20
| 5092 | 0.6 | 6.6667 | 10.1887 | 15.6835 | 2.9686 | 2.5263 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 5093 | 0.8 | 5 | 12.2727 | 18.8736 | 2.1357 | 4.4651 | 1 | 5 | 0.4 | 5 | 15
| 5094 | 1.4 | 2.8571 | 13.1707 | 22.1785 | 2.6077 | 6.4 | 1.4 | 3.5714 | 0.4 | 5 | 11.4286
| 5095 | 1 | 4 | 15 | 23.3638 | 2.878 | 5.4857 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 5096 | 0.8 | 5 | 10.8 | 17.3714 | 3.3714 | 3.2 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 5097 | 0.8 | 5 | 15.8824 | 23.7638 | 4.4528 | 3.4286 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 5098 | 1 | 4 | 13.1707 | 21.6582 | 3.6875 | 4.8 | 1 | 5 | 0.4 | 5 | 14
| 5099 | 0.4 | 10 | 13.8462 | 23.6856 | 2.7283 | 7.1111 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 5100 | 0.6 | 6.6667 | 15.4286 | 23.0192 | 3.3239 | 4.2667 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 5101 | 0.6 | 6.6667 | 15 | 21.7398 | 3.3714 | 3.3684 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 5102 | 1.2 | 3.3333 | 10.8 | 15.8505 | 2.3838 | 2.6667 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 5103 | 1 | 4 | 9.4737 | 15.3775 | 2.3483 | 3.5556 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 5104 | 1.4 | 2.8571 | 11.7391 | 23.288 | 3.8689 | 7.68 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 5105 | 1.6 | 2.5 | 12.5581 | 19.7993 | 3.5489 | 3.6923 | 1.2 | 4.1667 | 0.2 | 10 | 16.6667
| 5106 | 1.2 | 3.3333 | 12.8571 | 26.5302 | 3.0064 | 10.6667 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 5107 | 0.6 | 6.6667 | 12.2727 | 19.1186 | 2.5792 | 4.2667 | 1 | 5 | 0.2 | 10 | 21.6667
| 5108 | 1 | 4 | 11.7391 | 20.0981 | 3.0256 | 5.3333 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 5109 | 0.4 | 10 | 11.25 | 16.9017 | 2.6517 | 3 | 1 | 5 | 0.4 | 5 | 20
| 5110 | 1 | 4 | 10.3846 | 18.2821 | 3.6308 | 4.2667 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 5111 | 1.4 | 2.8571 | 11.25 | 18.3739 | 2.95 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 5112 | 0.8 | 5 | 15.4286 | 24.6514 | 3.5758 | 5.6471 | 1 | 5 | 0.4 | 5 | 15
| 5113 | 0.8 | 5 | 14.5946 | 23.014 | 3.4963 | 4.9231 | 1.6 | 3.125 | 0.6 | 3.3333 | 11.4583
| 5114 | 0.8 | 5 | 15.8824 | 26.1101 | 4.0342 | 6.1935 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 5115 | 0.8 | 5 | 11.4894 | 18.6926 | 2.2802 | 4.9231 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 5116 | 0.8 | 5 | 14.2105 | 21.8981 | 3.3239 | 4.3636 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 5117 | 0.8 | 5 | 13.5 | 20.7145 | 3.6589 | 3.5556 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 5118 | 1.2 | 3.3333 | 10.3846 | 21.701 | 2.9686 | 8.3478 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 5119 | 0.2 | 20 | 12.8571 | 19.7823 | 3.2329 | 3.6923 | 1 | 5 | 0.4 | 5 | 30
| 5120 | 0.4 | 10 | 11.25 | 17.5673 | 2.8263 | 3.4909 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 5121 | 0.6 | 6.6667 | 11.0204 | 17.861 | 2.6667 | 4.1739 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 5122 | 0.8 | 5 | 15.8824 | 21.5366 | 2.95 | 2.7042 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 5123 | 0.8 | 5 | 13.1707 | 20.1674 | 2.3137 | 4.6829 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 5124 | 1 | 4 | 15 | 21.0432 | 2.8957 | 3.1475 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 5125 | 1.4 | 2.8571 | 7.2973 | 14.7061 | 3.7165 | 3.6923 | 1.6 | 3.125 | 0.4 | 5 | 10.9821
| 5126 | 1.2 | 3.3333 | 11.0204 | 18.4161 | 3.3957 | 4 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 5127 | 0.6 | 6.6667 | 14.2105 | 23.8434 | 3.2329 | 6.4 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 5128 | 1.2 | 3.3333 | 13.8462 | 22.8025 | 3.4706 | 5.4857 | 1 | 5 | 0.4 | 5 | 13.3333
| 5129 | 0.6 | 6.6667 | 20 | 26.2042 | 2.95 | 3.2542 | 1 | 5 | 0.2 | 10 | 21.6667
| 5130 | 0.6 | 6.6667 | 14.2105 | 21.4764 | 3.3475 | 3.9184 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 5131 | 0.4 | 10 | 12 | 18.3506 | 2.5106 | 3.84 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 5132 | 0.4 | 10 | 9.8182 | 18.4739 | 3.6031 | 5.0526 | 1 | 5 | 0.2 | 10 | 25
| 5133 | 0.6 | 6.6667 | 13.1707 | 19.5288 | 2.5934 | 3.7647 | 1 | 5 | 0.6 | 3.3333 | 15
| 5134 | 1.2 | 3.3333 | 10.8 | 21.016 | 2.216 | 8 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 5135 | 1 | 4 | 9.3103 | 17.0601 | 2.6971 | 5.0526 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 5136 | 0.8 | 5 | 13.5 | 19.1583 | 2.4583 | 3.2 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 5137 | 1 | 4 | 11.4894 | 17.8054 | 2.5514 | 3.7647 | 1 | 5 | 0.2 | 10 | 19
| 5138 | 0.6 | 6.6667 | 11.25 | 19.536 | 3.6031 | 4.6829 | 1 | 5 | 0.6 | 3.3333 | 15
| 5139 | 0.4 | 10 | 14.2105 | 23.6576 | 2.8263 | 6.6207 | 1.6 | 3.125 | 0.6 | 3.3333 | 16.4583
| 5140 | 0.6 | 6.6667 | 10.5882 | 22.5964 | 2.4082 | 9.6 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 5141 | 0.8 | 5 | 12.5581 | 21.0036 | 3.5224 | 4.9231 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 5142 | 0.2 | 20 | 9.3103 | 15.3018 | 3.1258 | 2.8657 | 1.2 | 4.1667 | 0.6 | 3.3333 | 27.5
| 5143 | 0.4 | 10 | 16.875 | 24.5836 | 3.0256 | 4.6829 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 5144 | 0.4 | 10 | 11.4894 | 18.113 | 3.2552 | 3.3684 | 1 | 5 | 0.8 | 2.5 | 17.5
| 5145 | 0.4 | 10 | 17.4194 | 27.9833 | 4.3704 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 5146 | 0.4 | 10 | 7.9412 | 15.9215 | 3.8065 | 4.1739 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 5147 | 0.4 | 10 | 10.5882 | 17.3161 | 3.1053 | 3.6226 | 1 | 5 | 0.2 | 10 | 25
| 5148 | 0.8 | 5 | 9.3103 | 16.9574 | 2.3137 | 5.3333 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 5149 | 0.8 | 5 | 12 | 20.7867 | 2.9686 | 5.8182 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 5150 | 1 | 4 | 11.25 | 17.2844 | 3.2109 | 2.8235 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 5151 | 1.2 | 3.3333 | 9.8182 | 19.4511 | 3.2329 | 6.4 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 5152 | 0.8 | 5 | 15.8824 | 23.7189 | 3.3714 | 4.4651 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 5153 | 0.6 | 6.6667 | 11.0204 | 20.375 | 3.8689 | 5.4857 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 5154 | 0.4 | 10 | 8.5714 | 16.887 | 2.4974 | 5.8182 | 1 | 5 | 0.4 | 5 | 20
| 5155 | 0.8 | 5 | 10 | 22.9957 | 3.3957 | 9.6 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 5156 | 0.4 | 10 | 12 | 20.1535 | 3.4706 | 4.6829 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 5157 | 1 | 4 | 9.4737 | 17.6521 | 3.1258 | 5.0526 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 5158 | 0.8 | 5 | 10.5882 | 17.27 | 3.3714 | 3.3103 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 5159 | 0.8 | 5 | 9.3103 | 18.7478 | 4.866 | 4.5714 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 5160 | 0.4 | 10 | 10.1887 | 16.352 | 2.6077 | 3.5556 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 5161 | 0.8 | 5 | 13.5 | 19.6367 | 2.8263 | 3.3103 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 5162 | 1.2 | 3.3333 | 9.4737 | 17.4569 | 3.7165 | 4.2667 | 0.2 | 25 | 0.2 | 10 | 38.3333
| 5163 | 0.1 | 40 | 11.0204 | 17.2204 | 2.36 | 3.84 | 1.2 | 4.1667 | 0.6 | 3.3333 | 47.5
| 5164 | 0.8 | 5 | 16.875 | 22.849 | 3.0649 | 2.9091 | 1.4 | 3.5714 | 0.8 | 2.5 | 11.0714
| 5165 | 1.2 | 3.3333 | 10.5882 | 16.3375 | 3.0064 | 2.7429 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 5166 | 0.8 | 5 | 14.2105 | 23.4201 | 2.8095 | 6.4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 5167 | 0.8 | 5 | 12.5581 | 25.4563 | 2.7929 | 10.1053 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 5168 | 1 | 4 | 15.4286 | 22.7846 | 2.433 | 4.9231 | 1 | 5 | 0.2 | 10 | 19
| 5169 | 1 | 4 | 13.1707 | 20.2436 | 3.2329 | 3.84 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 5170 | 1.2 | 3.3333 | 15.4286 | 23.4837 | 3.2552 | 4.8 | 1 | 5 | 0.4 | 5 | 13.3333
| 5171 | 0.6 | 6.6667 | 10.5882 | 18.1106 | 3.5224 | 4 | 0.2 | 25 | 0.8 | 2.5 | 34.1667
| 5172 | 0.8 | 5 | 11.4894 | 20.5026 | 4.3303 | 4.6829 | 1.6 | 3.125 | 0.2 | 10 | 18.125
| 5173 | 1 | 4 | 10 | 15.9541 | 3.3239 | 2.6301 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 5174 | 1 | 4 | 12.8571 | 21.6558 | 3.746 | 5.0526 | 1 | 5 | 0.2 | 10 | 19
| 5175 | 1.2 | 3.3333 | 16.3636 | 24.469 | 2.4583 | 5.6471 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 5176 | 0.8 | 5 | 12 | 18.8866 | 2.7126 | 4.1739 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 5177 | 0.6 | 6.6667 | 13.8462 | 20.4542 | 2.8434 | 3.7647 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 5178 | 1 | 4 | 8.3077 | 14.1186 | 2.9873 | 2.8235 | 1.4 | 3.5714 | 0.8 | 2.5 | 10.0714
| 5179 | 0.6 | 6.6667 | 10 | 18.6307 | 4.866 | 3.7647 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 5180 | 0.6 | 6.6667 | 15.4286 | 21.8071 | 2.95 | 3.4286 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 5181 | 1.2 | 3.3333 | 14.2105 | 21.3333 | 2.5514 | 4.5714 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 5182 | 0.4 | 10 | 19.2857 | 26.4486 | 3.4706 | 3.6923 | 0.4 | 12.5 | 0.1 | 20 | 42.5
| 5183 | 0.6 | 6.6667 | 10.8 | 18.8489 | 3.1258 | 4.9231 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 5184 | 1 | 4 | 9.3103 | 16.3533 | 2.36 | 4.6829 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 5185 | 0.8 | 5 | 16.3636 | 23.8309 | 3.5489 | 3.9184 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 5186 | 0.8 | 5 | 11.7391 | 18.8041 | 3.0649 | 4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 5187 | 0.8 | 5 | 15 | 22.4776 | 3.2109 | 4.2667 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 5188 | 0.4 | 10 | 11.4894 | 18.6196 | 3.0452 | 4.0851 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 5189 | 1.4 | 2.8571 | 12.5581 | 19.5843 | 3.4706 | 3.5556 | 0.4 | 12.5 | 0.2 | 10 | 25.3571
| 5190 | 1.4 | 2.8571 | 14.5946 | 23.9177 | 3.8374 | 5.4857 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 5191 | 0.6 | 6.6667 | 10 | 17.6059 | 3.6875 | 3.9184 | 1.6 | 3.125 | 0.8 | 2.5 | 12.2917
| 5192 | 1 | 4 | 13.8462 | 20.4425 | 3.1678 | 3.4286 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 5193 | 0.2 | 20 | 13.1707 | 19.6241 | 3.085 | 3.3684 | 0.8 | 6.25 | 0.2 | 10 | 36.25
| 5194 | 0.6 | 6.6667 | 9.6429 | 16.6509 | 2.3251 | 4.6829 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 5195 | 0.4 | 10 | 10.8 | 18.1945 | 2.0611 | 5.3333 | 1.4 | 3.5714 | 0.1 | 20 | 33.5714
| 5196 | 1 | 4 | 9.3103 | 15.4031 | 3.0452 | 3.0476 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 5197 | 0.8 | 5 | 11.7391 | 18.7628 | 3.1053 | 3.9184 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 5198 | 0.8 | 5 | 15 | 20.2379 | 2.6077 | 2.6301 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 5199 | 0.6 | 6.6667 | 10.1887 | 18.0394 | 3.1678 | 4.6829 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 5200 | 0.6 | 6.6667 | 10 | 17.1091 | 2.5376 | 4.5714 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 5201 | 0.8 | 5 | 9.8182 | 15.9612 | 3.1892 | 2.9538 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 5202 | 1 | 4 | 17.4194 | 23.6141 | 2.8263 | 3.3684 | 1 | 5 | 0.4 | 5 | 14
| 5203 | 1 | 4 | 13.8462 | 20.4924 | 3.2778 | 3.3684 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 5204 | 1 | 4 | 13.8462 | 20.7493 | 3.2109 | 3.6923 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.8333
| 5205 | 1.4 | 2.8571 | 15.4286 | 22.2426 | 2.8957 | 3.9184 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 5206 | 0.8 | 5 | 11.7391 | 19.4527 | 2.9136 | 4.8 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 5207 | 1 | 4 | 11.4894 | 17.4407 | 2.6971 | 3.2542 | 1 | 5 | 0.4 | 5 | 14
| 5208 | 0.1 | 40 | 13.5 | 19.4126 | 2.7126 | 3.2 | 1.2 | 4.1667 | 0.2 | 10 | 54.1667
| 5209 | 1.2 | 3.3333 | 10.1887 | 18.9002 | 3.6589 | 5.0526 | 0.8 | 6.25 | 0.8 | 2.5 | 12.0833
| 5210 | 0.8 | 5 | 13.1707 | 22.0461 | 2.6818 | 6.1935 | 1 | 5 | 0.1 | 20 | 30
| 5211 | 1 | 4 | 12.8571 | 20.4763 | 3.4453 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 5212 | 1.2 | 3.3333 | 11.25 | 17.331 | 2.4583 | 3.6226 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 5213 | 0.4 | 10 | 12.5581 | 19.2587 | 2.8606 | 3.84 | 1 | 5 | 0.4 | 5 | 20
| 5214 | 1 | 4 | 11.4894 | 17.733 | 2.5514 | 3.6923 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 5215 | 0.8 | 5 | 14.2105 | 22.5919 | 2.8957 | 5.4857 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 5216 | 0.6 | 6.6667 | 12.2727 | 18.0804 | 2.4974 | 3.3103 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 5217 | 1 | 4 | 11.7391 | 18.8436 | 3.5489 | 3.5556 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 5218 | 0.2 | 20 | 12.2727 | 18.8639 | 2.9686 | 3.6226 | 0.4 | 12.5 | 0.4 | 5 | 37.5
| 5219 | 1.2 | 3.3333 | 8.5714 | 15.7649 | 2.7283 | 4.4651 | 0.8 | 6.25 | 0.8 | 2.5 | 12.0833
| 5220 | 1.2 | 3.3333 | 10.1887 | 20.5606 | 2.9873 | 7.3846 | 1.6 | 3.125 | 0.6 | 3.3333 | 9.7917
| 5221 | 0.6 | 6.6667 | 13.1707 | 19.5716 | 3.1467 | 3.2542 | 1 | 5 | 0.2 | 10 | 21.6667
| 5222 | 0.6 | 6.6667 | 15 | 21.3167 | 3.0064 | 3.3103 | 1 | 5 | 0.4 | 5 | 16.6667
| 5223 | 0.4 | 10 | 15 | 21.0561 | 2.5652 | 3.4909 | 1 | 5 | 0.2 | 10 | 25
| 5224 | 0.4 | 10 | 14.5946 | 21.3337 | 2.5652 | 4.1739 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 5225 | 0.6 | 6.6667 | 10 | 16.7279 | 2.8095 | 3.9184 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 5226 | 0.4 | 10 | 8.8525 | 15.0392 | 3.2329 | 2.9538 | 1.6 | 3.125 | 0.6 | 3.3333 | 16.4583
| 5227 | 0.8 | 5 | 8.8525 | 15.6235 | 3.0064 | 3.7647 | 1 | 5 | 0.4 | 5 | 15
| 5228 | 0.6 | 6.6667 | 11.7391 | 17.7577 | 2.3959 | 3.6226 | 1 | 5 | 0.2 | 10 | 21.6667
| 5229 | 1.2 | 3.3333 | 14.2105 | 21.6811 | 3.4706 | 4 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 5230 | 1.2 | 3.3333 | 11.0204 | 18.0872 | 2.3838 | 4.6829 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 5231 | 0.6 | 6.6667 | 20 | 27.4776 | 3.2109 | 4.2667 | 1.4 | 3.5714 | 0.1 | 20 | 30.2381
| 5232 | 1.2 | 3.3333 | 18.6207 | 24.7377 | 3.5224 | 2.5946 | 1.6 | 3.125 | 0.4 | 5 | 11.4583
| 5233 | 0.6 | 6.6667 | 9 | 17.4719 | 3.5489 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 5234 | 0.8 | 5 | 12.8571 | 20.7171 | 3.4963 | 4.3636 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 5235 | 1 | 4 | 22.5 | 32.6611 | 2.7765 | 7.3846 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 5236 | 1.2 | 3.3333 | 14.2105 | 19.9621 | 2.4974 | 3.2542 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 5237 | 0.4 | 10 | 10.8 | 20.1671 | 3.5489 | 5.8182 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 5238 | 1 | 4 | 10.5882 | 17.9122 | 3.3239 | 4 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.8333
| 5239 | 0.4 | 10 | 12.2727 | 21.096 | 4.1404 | 4.6829 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 5240 | 1 | 4 | 16.875 | 23.2907 | 2.4974 | 3.9184 | 1 | 5 | 0.4 | 5 | 14
| 5241 | 0.6 | 6.6667 | 17.4194 | 24.7825 | 3.1892 | 4.1739 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 5242 | 0.4 | 10 | 12.5581 | 20.2577 | 2.7765 | 4.9231 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 5243 | 0.8 | 5 | 13.5 | 21.54 | 2.9873 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 5244 | 0.2 | 20 | 12.5581 | 19.4815 | 3.3007 | 3.6226 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 5245 | 1.2 | 3.3333 | 10.5882 | 17.2693 | 2.216 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 5246 | 0.8 | 5 | 9.8182 | 17.1322 | 3.3957 | 3.9184 | 1 | 5 | 0.4 | 5 | 15
| 5247 | 1.2 | 3.3333 | 12.2727 | 20.1234 | 3.1678 | 4.6829 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 5248 | 1.2 | 3.3333 | 15.4286 | 23.1514 | 3.5489 | 4.1739 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 5249 | 0.4 | 10 | 13.8462 | 23.7685 | 3.5224 | 6.4 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 5250 | 0.6 | 6.6667 | 9.8182 | 19.0078 | 3.3714 | 5.8182 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 5251 | 0.6 | 6.6667 | 10.8 | 18.2883 | 2.5652 | 4.9231 | 1 | 5 | 0.4 | 5 | 16.6667
| 5252 | 0.4 | 10 | 18 | 24.2857 | 2.5934 | 3.6923 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 5253 | 1.4 | 2.8571 | 16.3636 | 22.7854 | 2.3366 | 4.0851 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 5254 | 1.2 | 3.3333 | 13.1707 | 19.5174 | 3.7165 | 2.6301 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 5255 | 1 | 4 | 10.5882 | 20.0085 | 3.4203 | 6 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 5256 | 1 | 4 | 18.6207 | 27.0651 | 3.2552 | 5.1892 | 1 | 5 | 0.4 | 5 | 14
| 5257 | 0.6 | 6.6667 | 12.5581 | 21.5267 | 2.9686 | 6 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 5258 | 1.2 | 3.3333 | 15.8824 | 27.9571 | 3.3475 | 8.7273 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 5259 | 1 | 4 | 11.7391 | 21.9356 | 3.5758 | 6.6207 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 5260 | 0.4 | 10 | 11.25 | 16.8705 | 2.6667 | 2.9538 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 5261 | 0.8 | 5 | 8.0597 | 19.5753 | 3.1678 | 8.3478 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 5262 | 1.6 | 2.5 | 8.3077 | 14.6331 | 3.2778 | 3.0476 | 1.4 | 3.5714 | 0.4 | 5 | 11.0714
| 5263 | 0.6 | 6.6667 | 15.4286 | 23.812 | 2.5652 | 5.8182 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 5264 | 0.4 | 10 | 10.1887 | 18.6887 | 2.6818 | 5.8182 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 5265 | 0.2 | 20 | 10 | 16.6796 | 2.9873 | 3.6923 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 5266 | 1.2 | 3.3333 | 11.4894 | 21.0382 | 3.5489 | 6 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 5267 | 1.2 | 3.3333 | 13.8462 | 21.1376 | 2.8263 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 5268 | 0.6 | 6.6667 | 15 | 22.9657 | 2.7765 | 5.1892 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 5269 | 0.6 | 6.6667 | 10 | 16.2368 | 3.1892 | 3.0476 | 1 | 5 | 0.2 | 10 | 21.6667
| 5270 | 0.8 | 5 | 12 | 20.059 | 3.0064 | 5.0526 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 5271 | 0.6 | 6.6667 | 13.5 | 23.2352 | 2.878 | 6.8571 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 5272 | 0.4 | 10 | 15.8824 | 26.5909 | 3.3239 | 7.3846 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 5273 | 1.2 | 3.3333 | 9.1525 | 16.5418 | 2.3366 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 5274 | 1 | 4 | 11.0204 | 16.9819 | 2.2692 | 3.6923 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 5275 | 1.2 | 3.3333 | 8.8525 | 16.7629 | 2.9873 | 4.9231 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 5276 | 0.6 | 6.6667 | 14.2105 | 23.5595 | 2.7283 | 6.6207 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 5277 | 0.2 | 20 | 11.0204 | 29.2099 | 3.4203 | 14.7692 | 0.8 | 6.25 | 0.8 | 2.5 | 28.75
| 5278 | 1 | 4 | 11.4894 | 17.4357 | 3.6875 | 2.2588 | 1.8 | 2.7778 | 0.4 | 5 | 11.7778
| 5279 | 0.6 | 6.6667 | 10.8 | 17.1297 | 3.2329 | 3.0968 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 5280 | 1.6 | 2.5 | 8.1818 | 15.9169 | 3.3714 | 4.3636 | 1.2 | 4.1667 | 0.4 | 5 | 11.6667
| 5281 | 0.6 | 6.6667 | 11.4894 | 19.935 | 2.4456 | 6 | 0.6 | 8.3333 | 0.8 | 2.5 | 17.5
| 5282 | 1 | 4 | 10.8 | 18.2963 | 3.4963 | 4 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 5283 | 0.6 | 6.6667 | 14.2105 | 21.7073 | 4.6733 | 2.8235 | 1 | 5 | 0.2 | 10 | 21.6667
| 5284 | 0.4 | 10 | 13.5 | 19.6779 | 2.8095 | 3.3684 | 1.2 | 4.1667 | 0.1 | 20 | 34.1667
| 5285 | 1 | 4 | 10.1887 | 18.9207 | 3.085 | 5.6471 | 1 | 5 | 0.4 | 5 | 14
| 5286 | 1.2 | 3.3333 | 12.5581 | 22.0924 | 2.9136 | 6.6207 | 1 | 5 | 0.4 | 5 | 13.3333
| 5287 | 1 | 4 | 13.8462 | 23.536 | 3.4963 | 6.1935 | 1 | 5 | 0.2 | 10 | 19
| 5288 | 0.8 | 5 | 12.2727 | 24.525 | 4.2523 | 8 | 1 | 5 | 0.4 | 5 | 15
| 5289 | 0.6 | 6.6667 | 10.8 | 18.9957 | 3.3957 | 4.8 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 5290 | 0.4 | 10 | 10 | 16.6329 | 2.7929 | 3.84 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 5291 | 1 | 4 | 13.8462 | 22.7962 | 2.95 | 6 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 5292 | 1 | 4 | 12 | 19.5304 | 3.4453 | 4.0851 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 5293 | 1.2 | 3.3333 | 14.5946 | 20.1312 | 2.3366 | 3.2 | 1 | 5 | 0.2 | 10 | 18.3333
| 5294 | 0.8 | 5 | 15.4286 | 22.0098 | 3.0256 | 3.5556 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 5295 | 0.6 | 6.6667 | 12.8571 | 22.1597 | 2.6818 | 6.6207 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 5296 | 1.2 | 3.3333 | 11.0204 | 19.5215 | 3.1678 | 5.3333 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 5297 | 1.2 | 3.3333 | 9.4737 | 18.7515 | 3.2778 | 6 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 5298 | 0.8 | 5 | 16.875 | 24.2548 | 3.6875 | 3.6923 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 5299 | 0.8 | 5 | 9.8182 | 16.3189 | 2.878 | 3.6226 | 1 | 5 | 0.4 | 5 | 15
| 5300 | 1.2 | 3.3333 | 12.8571 | 18.978 | 3.2552 | 2.8657 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 5301 | 0.2 | 20 | 13.5 | 20.1451 | 2.4712 | 4.1739 | 1.2 | 4.1667 | 0.6 | 3.3333 | 27.5
| 5302 | 1.4 | 2.8571 | 18 | 25.7658 | 3.3007 | 4.4651 | 1.4 | 3.5714 | 0.4 | 5 | 11.4286
| 5303 | 0.2 | 20 | 12.8571 | 20.8273 | 2.6369 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 5304 | 0.6 | 6.6667 | 13.5 | 19.4873 | 2.9873 | 3 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 5305 | 1.2 | 3.3333 | 7.5 | 17.8663 | 3.2552 | 7.1111 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 5306 | 0.4 | 10 | 13.8462 | 24.2733 | 3.8065 | 6.6207 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 5307 | 0.6 | 6.6667 | 12.2727 | 18.433 | 2.5376 | 3.6226 | 1 | 5 | 0.2 | 10 | 21.6667
| 5308 | 0.6 | 6.6667 | 10.5882 | 16.9835 | 3.085 | 3.3103 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 5309 | 0.4 | 10 | 10.8 | 19.1422 | 2.5241 | 5.8182 | 1 | 5 | 0.4 | 5 | 20
| 5310 | 1.2 | 3.3333 | 13.1707 | 20.5203 | 2.6667 | 4.6829 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 5311 | 0.6 | 6.6667 | 8.4375 | 14.7452 | 3.2109 | 3.0968 | 0.6 | 8.3333 | 0.8 | 2.5 | 17.5
| 5312 | 1 | 4 | 12.5581 | 19.6431 | 3.085 | 4 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 5313 | 0.8 | 5 | 13.1707 | 20.4578 | 3.5224 | 3.7647 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 5314 | 1 | 4 | 9.8182 | 16.6146 | 2.878 | 3.9184 | 1.6 | 3.125 | 0.2 | 10 | 17.125
| 5315 | 0.8 | 5 | 10 | 18.5934 | 2.5934 | 6 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 5316 | 0.6 | 6.6667 | 14.2105 | 20.2095 | 3.0452 | 2.9538 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 5317 | 1 | 4 | 13.1707 | 19.0394 | 3.0452 | 2.8235 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 5318 | 0.4 | 10 | 11.7391 | 21.6354 | 3.4963 | 6.4 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 5319 | 1.2 | 3.3333 | 9.3103 | 16.5644 | 2.9873 | 4.2667 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 5320 | 0.8 | 5 | 12.2727 | 20.6101 | 4.2523 | 4.0851 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 5321 | 0.4 | 10 | 12.5581 | 20.2185 | 2.6077 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 5322 | 0.4 | 10 | 8.1818 | 15.893 | 3.3475 | 4.3636 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 5323 | 0.8 | 5 | 9.8182 | 17.9893 | 2.5241 | 5.6471 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 5324 | 0.6 | 6.6667 | 9.4737 | 16.5322 | 2.5934 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 15
| 5325 | 0.8 | 5 | 13.8462 | 19.7736 | 2.3719 | 3.5556 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 5326 | 1.2 | 3.3333 | 12.8571 | 20.4901 | 2.95 | 4.6829 | 1 | 5 | 0.2 | 10 | 18.3333
| 5327 | 1.4 | 2.8571 | 12.2727 | 19.2964 | 3.1053 | 3.9184 | 1 | 5 | 0.2 | 10 | 17.8571
| 5328 | 0.8 | 5 | 13.8462 | 20.9514 | 3.1053 | 4 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 5329 | 0.8 | 5 | 12 | 17.6632 | 3.8689 | 1.7944 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 5330 | 0.6 | 6.6667 | 10 | 20.1349 | 3.2778 | 6.8571 | 1 | 5 | 0.2 | 10 | 21.6667
| 5331 | 0.2 | 20 | 13.1707 | 22.1738 | 2.8095 | 6.1935 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 5332 | 1 | 4 | 11.0204 | 18.0232 | 2.5376 | 4.4651 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 5333 | 1.4 | 2.8571 | 12.5581 | 19.0269 | 2.7765 | 3.6923 | 1 | 5 | 0.4 | 5 | 12.8571
| 5334 | 0.6 | 6.6667 | 9.6429 | 19.2537 | 3.2109 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 5335 | 1.2 | 3.3333 | 10.3846 | 19.8299 | 3.4453 | 6 | 1 | 5 | 0.1 | 20 | 28.3333
| 5336 | 0.4 | 10 | 11.25 | 19.9034 | 3.0064 | 5.6471 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 5337 | 1.4 | 2.8571 | 10.1887 | 15.8204 | 2.4842 | 3.1475 | 1.6 | 3.125 | 0.1 | 20 | 25.9821
| 5338 | 1.2 | 3.3333 | 12 | 19.3798 | 3.6875 | 3.6923 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 5339 | 0.6 | 6.6667 | 10.3846 | 16.4196 | 2.9873 | 3.0476 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 5340 | 0.6 | 6.6667 | 12.2727 | 21.0264 | 3.4203 | 5.3333 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 5341 | 0.8 | 5 | 14.2105 | 21.9217 | 3.3475 | 4.3636 | 1.6 | 3.125 | 0.1 | 20 | 28.125
| 5342 | 0.8 | 5 | 8.3077 | 21.1737 | 4.866 | 8 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 5343 | 0.8 | 5 | 13.5 | 21.4836 | 3.3007 | 4.6829 | 1 | 5 | 0.1 | 20 | 30
| 5344 | 0.8 | 5 | 15 | 21.7887 | 3.4203 | 3.3684 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 5345 | 0.8 | 5 | 10.1887 | 19.3544 | 3.3475 | 5.8182 | 1 | 5 | 0.2 | 10 | 20
| 5346 | 1 | 4 | 10.3846 | 20.2407 | 4.3704 | 5.4857 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 5347 | 1.2 | 3.3333 | 14.5946 | 23.3229 | 2.7283 | 6 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 5348 | 0.2 | 20 | 10.3846 | 18.2301 | 2.7929 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 5349 | 0.6 | 6.6667 | 15.4286 | 25.8081 | 3.5224 | 6.8571 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 5350 | 1 | 4 | 9.8182 | 18.764 | 2.3251 | 6.6207 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 5351 | 0.8 | 5 | 9.4737 | 17 | 2.8434 | 4.6829 | 1 | 5 | 0.4 | 5 | 15
| 5352 | 1.2 | 3.3333 | 12 | 21.3136 | 2.9136 | 6.4 | 1 | 5 | 0.1 | 20 | 28.3333
| 5353 | 0.8 | 5 | 18 | 26.729 | 3.3957 | 5.3333 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 5354 | 0.8 | 5 | 30 | 37.1996 | 3.0256 | 4.1739 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 5355 | 1.6 | 2.5 | 9.6429 | 17.5159 | 2.95 | 4.9231 | 0.6 | 8.3333 | 0.2 | 10 | 20.8333
| 5356 | 0.6 | 6.6667 | 19.2857 | 26.5998 | 3.3957 | 3.9184 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 5357 | 0.4 | 10 | 9 | 15.698 | 2.5241 | 4.1739 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 5358 | 0.8 | 5 | 11.25 | 19.0837 | 4.069 | 3.7647 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 5359 | 1.4 | 2.8571 | 12 | 20.9686 | 2.9686 | 6 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 5360 | 0.6 | 6.6667 | 16.3636 | 24.562 | 2.7126 | 5.4857 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 5361 | 0.8 | 5 | 12.8571 | 19.2905 | 2.5934 | 3.84 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 5362 | 1.4 | 2.8571 | 11.0204 | 18.3982 | 2.3251 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 5363 | 1.2 | 3.3333 | 10.5882 | 17.1502 | 3.0064 | 3.5556 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 5364 | 0.6 | 6.6667 | 12.5581 | 21.5233 | 3.776 | 5.1892 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 5365 | 0.8 | 5 | 10.3846 | 18.4624 | 3.2778 | 4.8 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 5366 | 0.6 | 6.6667 | 11.4894 | 19.9068 | 2.9317 | 5.4857 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 5367 | 1 | 4 | 11.0204 | 17.5137 | 2.4082 | 4.0851 | 1 | 5 | 0.4 | 5 | 14
| 5368 | 1.2 | 3.3333 | 13.8462 | 19.9827 | 2.3719 | 3.7647 | 0.8 | 6.25 | 0.8 | 2.5 | 12.0833
| 5369 | 1 | 4 | 11.4894 | 18.8092 | 2.6369 | 4.6829 | 1 | 5 | 0.1 | 20 | 29
| 5370 | 0.2 | 20 | 13.5 | 19.869 | 2.878 | 3.4909 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 5371 | 1 | 4 | 14.5946 | 21.8314 | 2.3137 | 4.9231 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 5372 | 0.2 | 20 | 12.2727 | 21.175 | 3.2552 | 5.6471 | 1 | 5 | 0.4 | 5 | 30
| 5373 | 1 | 4 | 23.4783 | 30.9341 | 3.1892 | 4.2667 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 5374 | 1.4 | 2.8571 | 12 | 18.9872 | 3.4963 | 3.4909 | 1 | 5 | 0.1 | 20 | 27.8571
| 5375 | 0.8 | 5 | 10.1887 | 16.7126 | 3.3239 | 3.2 | 1 | 5 | 0.2 | 10 | 20
| 5376 | 0.2 | 20 | 10.5882 | 18.2855 | 3.1258 | 4.5714 | 1.4 | 3.5714 | 0.6 | 3.3333 | 26.9048
| 5377 | 0.6 | 6.6667 | 10.1887 | 18.3654 | 2.8434 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 5378 | 0.4 | 10 | 11.0204 | 18.2738 | 3.6308 | 3.6226 | 1.6 | 3.125 | 0.1 | 20 | 33.125
| 5379 | 0.8 | 5 | 13.1707 | 20.3703 | 3.0256 | 4.1739 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 5380 | 0.6 | 6.6667 | 15.8824 | 21.6713 | 3.0064 | 2.7826 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 5381 | 1.4 | 2.8571 | 14.2105 | 19.6491 | 2.0702 | 3.3684 | 1.4 | 3.5714 | 0.1 | 20 | 26.4286
| 5382 | 1 | 4 | 11.0204 | 18.6719 | 2.9686 | 4.6829 | 1.2 | 4.1667 | 1 | 2 | 10.1667
| 5383 | 0.8 | 5 | 12 | 21.1892 | 3.1892 | 6 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 5384 | 1.2 | 3.3333 | 12 | 18.7506 | 3.6031 | 3.1475 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 5385 | 0.8 | 5 | 10.8 | 17.1143 | 2.3959 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 5386 | 0.8 | 5 | 15 | 22.9256 | 3.6589 | 4.2667 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 5387 | 1.4 | 2.8571 | 15.4286 | 25.5258 | 2.7126 | 7.3846 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 5388 | 0.6 | 6.6667 | 19.2857 | 26.3958 | 2.8434 | 4.2667 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 5389 | 0.8 | 5 | 14.5946 | 20.3087 | 2.7602 | 2.9538 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 5390 | 0.6 | 6.6667 | 18 | 24.87 | 3.1053 | 3.7647 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 5391 | 1.4 | 2.8571 | 11.25 | 20.1071 | 3.3714 | 5.4857 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 5392 | 1.2 | 3.3333 | 8.7097 | 14.7626 | 2.4974 | 3.5556 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 5393 | 1 | 4 | 10.3846 | 17.8363 | 3.2778 | 4.1739 | 1 | 5 | 0.4 | 5 | 14
| 5394 | 0.6 | 6.6667 | 11.25 | 17.1176 | 3.085 | 2.7826 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 5395 | 0.8 | 5 | 11.7391 | 20.6701 | 3.4453 | 5.4857 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 5396 | 0.1 | 40 | 16.875 | 25.234 | 3.0256 | 5.3333 | 1 | 5 | 0.6 | 3.3333 | 48.3333
| 5397 | 1.2 | 3.3333 | 21.6 | 31.3888 | 2.9317 | 6.8571 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 5398 | 1.2 | 3.3333 | 15 | 22.2343 | 2.5514 | 4.6829 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 5399 | 0.4 | 10 | 13.5 | 19.6879 | 2.5652 | 3.6226 | 1.2 | 4.1667 | 1 | 2 | 16.1667
| 5400 | 1 | 4 | 11.4894 | 21.6664 | 4.177 | 6 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 5401 | 0.6 | 6.6667 | 12.5581 | 17.9232 | 2.6222 | 2.7429 | 1 | 5 | 0.6 | 3.3333 | 15
| 5402 | 1.2 | 3.3333 | 12.5581 | 18.5562 | 3.2552 | 2.7429 | 1.6 | 3.125 | 0.4 | 5 | 11.4583
| 5403 | 0.6 | 6.6667 | 9.1525 | 17.1513 | 2.8095 | 5.1892 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 5404 | 1 | 4 | 13.1707 | 22.1408 | 2.7765 | 6.1935 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 5405 | 1 | 4 | 11.0204 | 16.3125 | 2.1953 | 3.0968 | 1.6 | 3.125 | 0.2 | 10 | 17.125
| 5406 | 1 | 4 | 15.4286 | 23.0251 | 3.2329 | 4.3636 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 5407 | 1.2 | 3.3333 | 13.1707 | 18.1165 | 2.4842 | 2.4615 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 5408 | 1.4 | 2.8571 | 12 | 19.1231 | 3.8689 | 3.2542 | 0.6 | 8.3333 | 0.6 | 3.3333 | 14.5238
| 5409 | 1 | 4 | 9.4737 | 17.3103 | 2.9136 | 4.9231 | 0.6 | 8.3333 | 0.1 | 20 | 32.3333
| 5410 | 0.2 | 20 | 10.1887 | 21.2401 | 3.3714 | 7.68 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 5411 | 0.2 | 20 | 10.8 | 18.7556 | 2.6222 | 5.3333 | 0.8 | 6.25 | 0.2 | 10 | 36.25
| 5412 | 0.6 | 6.6667 | 12.5581 | 21.663 | 2.4842 | 6.6207 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 5413 | 0.4 | 10 | 14.5946 | 22.2138 | 3.4453 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 5414 | 0.8 | 5 | 16.3636 | 25.0752 | 3.6589 | 5.0526 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 5415 | 0.2 | 20 | 13.8462 | 22.2462 | 3.2109 | 5.1892 | 1 | 5 | 0.4 | 5 | 30
| 5416 | 1 | 4 | 11.4894 | 19.9882 | 3.5758 | 4.9231 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 5417 | 0.4 | 10 | 9.3103 | 17.2042 | 3.2109 | 4.6829 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 5418 | 0.8 | 5 | 9.4737 | 19.2694 | 3.3957 | 6.4 | 1 | 5 | 0.2 | 10 | 20
| 5419 | 0.4 | 10 | 18.6207 | 30.1577 | 3.1892 | 8.3478 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 5420 | 0.6 | 6.6667 | 10.5882 | 19.8661 | 3.6308 | 5.6471 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 5421 | 0.8 | 5 | 11.7391 | 17.7101 | 3.1053 | 2.8657 | 1.4 | 3.5714 | 1 | 2 | 10.5714
| 5422 | 1 | 4 | 13.8462 | 21.0628 | 2.95 | 4.2667 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 5423 | 0.6 | 6.6667 | 16.875 | 24.2953 | 3.4203 | 4 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 5424 | 0.6 | 6.6667 | 11.0204 | 18.5505 | 3.0649 | 4.4651 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 5425 | 0.8 | 5 | 9.3103 | 18.4525 | 3.3239 | 5.8182 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 5426 | 0.6 | 6.6667 | 11.25 | 20.8822 | 2.2476 | 7.3846 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 5427 | 1 | 4 | 9.1525 | 15.3211 | 2.9686 | 3.2 | 1 | 5 | 0.2 | 10 | 19
| 5428 | 0.4 | 10 | 9 | 18.4085 | 2.5514 | 6.8571 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 5429 | 0.2 | 20 | 11.4894 | 17.6025 | 2.6222 | 3.4909 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 5430 | 0.8 | 5 | 12.2727 | 23.3489 | 2.7283 | 8.3478 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 5431 | 0.6 | 6.6667 | 15 | 21.925 | 3.085 | 3.84 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 5432 | 0.6 | 6.6667 | 10.3846 | 18.3524 | 3.1678 | 4.8 | 1 | 5 | 0.6 | 3.3333 | 15
| 5433 | 0.6 | 6.6667 | 18.6207 | 27.9753 | 3.8689 | 5.4857 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 5434 | 0.6 | 6.6667 | 12 | 19.6349 | 3.7165 | 3.9184 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 5435 | 0.1 | 40 | 12 | 19.9273 | 2.2802 | 5.6471 | 1 | 5 | 0.6 | 3.3333 | 48.3333
| 5436 | 1 | 4 | 10.1887 | 17.4467 | 2.7929 | 4.4651 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 5437 | 0.4 | 10 | 14.5946 | 22.1049 | 3.0452 | 4.4651 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 5438 | 0.6 | 6.6667 | 12.2727 | 19.0656 | 2.7929 | 4 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 5439 | 0.4 | 10 | 13.8462 | 20.2987 | 2.7602 | 3.6923 | 1 | 5 | 0.4 | 5 | 20
| 5440 | 0.6 | 6.6667 | 12 | 18.1224 | 3.0256 | 3.0968 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 5441 | 1.4 | 2.8571 | 9.3103 | 18.4798 | 3.5224 | 5.6471 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 5442 | 0.6 | 6.6667 | 8.5714 | 15.9692 | 2.8263 | 4.5714 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 5443 | 0.6 | 6.6667 | 13.8462 | 18.906 | 2.878 | 2.1818 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 5444 | 0.8 | 5 | 12.8571 | 22.4221 | 3.3714 | 6.1935 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 5445 | 0.4 | 10 | 15.4286 | 21.3136 | 1.9667 | 3.9184 | 1 | 5 | 0.2 | 10 | 25
| 5446 | 0.8 | 5 | 10.5882 | 17.8986 | 4 | 3.3103 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 5447 | 0.6 | 6.6667 | 10.1887 | 18.075 | 2.6971 | 5.1892 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 5448 | 0.8 | 5 | 15.4286 | 23.4437 | 2.6818 | 5.3333 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 5449 | 0.2 | 20 | 10.5882 | 17.9519 | 3.4453 | 3.9184 | 1.4 | 3.5714 | 0.2 | 10 | 33.5714
| 5450 | 0.4 | 10 | 12 | 18.87 | 3.1053 | 3.7647 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 5451 | 1 | 4 | 10.1887 | 17.369 | 3.0064 | 4.1739 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 5452 | 1.2 | 3.3333 | 9.4737 | 17.0832 | 2.8095 | 4.8 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 5453 | 0.2 | 20 | 13.8462 | 20.3153 | 2.9136 | 3.5556 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 5454 | 0.8 | 5 | 15 | 22.9662 | 2.9136 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 5455 | 1.2 | 3.3333 | 19.2857 | 28.1291 | 2.8434 | 6 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.1667
| 5456 | 0.2 | 20 | 15.8824 | 22.6344 | 2.9873 | 3.7647 | 1.2 | 4.1667 | 0.6 | 3.3333 | 27.5
| 5457 | 1 | 4 | 16.875 | 24.9239 | 3.1258 | 4.9231 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 5458 | 0.6 | 6.6667 | 12.8571 | 23.0885 | 2.5514 | 7.68 | 1.6 | 3.125 | 0.2 | 10 | 19.7917
| 5459 | 0.6 | 6.6667 | 15.8824 | 22.4133 | 3.9008 | 2.6301 | 0.4 | 12.5 | 0.8 | 2.5 | 21.6667
| 5460 | 1 | 4 | 13.5 | 21.5552 | 3.2552 | 4.8 | 0.4 | 12.5 | 0.8 | 2.5 | 19
| 5461 | 0.8 | 5 | 9.3103 | 15.9795 | 3.3007 | 3.3684 | 1 | 5 | 0.2 | 10 | 20
| 5462 | 1 | 4 | 9.8182 | 20.4731 | 4.0342 | 6.6207 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 5463 | 0.8 | 5 | 8.8525 | 17.4285 | 3.776 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 5464 | 1.6 | 2.5 | 9.4737 | 16.6184 | 2.878 | 4.2667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10
| 5465 | 1 | 4 | 13.1707 | 18.7707 | 2.7765 | 2.8235 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 5466 | 1.2 | 3.3333 | 12.2727 | 22.0684 | 3.3957 | 6.4 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 5467 | 0.4 | 10 | 9.4737 | 15.7558 | 3.6875 | 2.5946 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 5468 | 0.2 | 20 | 12.2727 | 21.9967 | 3.3239 | 6.4 | 0.2 | 25 | 0.4 | 5 | 50
| 5469 | 0.8 | 5 | 10.3846 | 17.8604 | 2.7929 | 4.6829 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 5470 | 1.4 | 2.8571 | 11.0204 | 18.0012 | 2.8957 | 4.0851 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 5471 | 0.6 | 6.6667 | 9 | 15.2 | 2.36 | 3.84 | 1.6 | 3.125 | 0.4 | 5 | 14.7917
| 5472 | 0.6 | 6.6667 | 10.1887 | 17.0891 | 3.2778 | 3.6226 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 5473 | 0.6 | 6.6667 | 15.4286 | 25.939 | 3.1258 | 7.3846 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 5474 | 0.8 | 5 | 14.2105 | 21.0425 | 2.9136 | 3.9184 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 5475 | 1.4 | 2.8571 | 15 | 21.3256 | 3.6589 | 2.6667 | 1.4 | 3.5714 | 0.2 | 10 | 16.4286
| 5476 | 0.6 | 6.6667 | 12 | 20.8895 | 3.9664 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 5477 | 1 | 4 | 9.8182 | 16.9786 | 3.3957 | 3.7647 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 5478 | 0.6 | 6.6667 | 12.8571 | 20.475 | 2.5652 | 5.0526 | 1 | 5 | 0.2 | 10 | 21.6667
| 5479 | 0.6 | 6.6667 | 11.25 | 19.4986 | 4.3303 | 3.9184 | 1 | 5 | 0.6 | 3.3333 | 15
| 5480 | 0.8 | 5 | 17.4194 | 26.2457 | 2.8263 | 6 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 5481 | 0.6 | 6.6667 | 14.5946 | 21.4726 | 2.7929 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 5482 | 1.2 | 3.3333 | 9.3103 | 17.3592 | 3.1258 | 4.9231 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 5483 | 1 | 4 | 13.5 | 21.3452 | 3.0452 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 5484 | 1.2 | 3.3333 | 8.1818 | 16.9657 | 2.3838 | 6.4 | 1 | 5 | 0.4 | 5 | 13.3333
| 5485 | 0.6 | 6.6667 | 15 | 21.1419 | 3.0452 | 3.0968 | 1 | 5 | 0.1 | 20 | 31.6667
| 5486 | 1 | 4 | 22.5 | 29.0094 | 3.2552 | 3.2542 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 5487 | 1.2 | 3.3333 | 10.8 | 17.1001 | 2.9317 | 3.3684 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 5488 | 0.4 | 10 | 11.4894 | 22.6146 | 3.4453 | 7.68 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 5489 | 0.4 | 10 | 14.5946 | 24.6161 | 2.6369 | 7.3846 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 5490 | 0.6 | 6.6667 | 8.3077 | 15.9666 | 3.6589 | 4 | 1 | 5 | 0.4 | 5 | 16.6667
| 5491 | 1.4 | 2.8571 | 13.5 | 21.1957 | 2.8957 | 4.8 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 5492 | 0.6 | 6.6667 | 15.4286 | 21.7124 | 2.7929 | 3.4909 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 5493 | 1.6 | 2.5 | 13.5 | 20.932 | 2.8606 | 4.5714 | 0.8 | 6.25 | 0.1 | 20 | 28.75
| 5494 | 0.8 | 5 | 14.5946 | 22.5303 | 3.4706 | 4.4651 | 1 | 5 | 0.2 | 10 | 20
| 5495 | 0.4 | 10 | 11.25 | 22.5295 | 2.9317 | 8.3478 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 5496 | 0.4 | 10 | 11.7391 | 19.4717 | 2.8095 | 4.9231 | 0.4 | 12.5 | 0.6 | 3.3333 | 25.8333
| 5497 | 0.1 | 40 | 11.7391 | 18.9873 | 2.5652 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 49.5833
| 5498 | 0.6 | 6.6667 | 15.4286 | 24.9143 | 4 | 5.4857 | 1 | 5 | 0.6 | 3.3333 | 15
| 5499 | 1 | 4 | 12.8571 | 18.524 | 2.8434 | 2.8235 | 1 | 5 | 0.8 | 2.5 | 11.5
| 5500 | 1.2 | 3.3333 | 12.2727 | 20.0053 | 2.8095 | 4.9231 | 1.4 | 3.5714 | 0.1 | 20 | 26.9048
| 5501 | 0.6 | 6.6667 | 15.8824 | 25.8653 | 3.1258 | 6.8571 | 1 | 5 | 0.2 | 10 | 21.6667
| 5502 | 0.6 | 6.6667 | 9.6429 | 19.2765 | 2.7765 | 6.8571 | 1 | 5 | 0.4 | 5 | 16.6667
| 5503 | 1.2 | 3.3333 | 10.5882 | 15.9578 | 2.8095 | 2.56 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 5504 | 1 | 4 | 12.5581 | 18.693 | 2.9873 | 3.1475 | 1 | 5 | 0.4 | 5 | 14
| 5505 | 0.8 | 5 | 15 | 25.4242 | 2.7442 | 7.68 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 5506 | 1 | 4 | 8.0597 | 14.9463 | 2.7126 | 4.1739 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 5507 | 0.6 | 6.6667 | 11.25 | 20.2722 | 2.6222 | 6.4 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 5508 | 0.6 | 6.6667 | 12.2727 | 19.2735 | 3.4453 | 3.5556 | 1 | 5 | 0.4 | 5 | 16.6667
| 5509 | 0.8 | 5 | 11.25 | 23.0151 | 2.6222 | 9.1429 | 1.8 | 2.7778 | 0.4 | 5 | 12.7778
| 5510 | 0.6 | 6.6667 | 13.8462 | 25.6112 | 2.6222 | 9.1429 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 5511 | 0.6 | 6.6667 | 11.7391 | 20.0988 | 2.7126 | 5.6471 | 1 | 5 | 0.2 | 10 | 21.6667
| 5512 | 1.4 | 2.8571 | 18 | 23.9269 | 2.0085 | 3.9184 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 5513 | 1 | 4 | 11.0204 | 23.4372 | 4.069 | 8.3478 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 5514 | 0.6 | 6.6667 | 13.8462 | 20.348 | 2.8095 | 3.6923 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 5515 | 0.8 | 5 | 14.5946 | 22.3599 | 2.7126 | 5.0526 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 5516 | 0.6 | 6.6667 | 10.1887 | 17.5495 | 2.8957 | 4.4651 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 5517 | 0.6 | 6.6667 | 12.2727 | 19.7807 | 4.4112 | 3.0968 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 5518 | 0.8 | 5 | 11.4894 | 17.8193 | 2.5652 | 3.7647 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 5519 | 0.4 | 10 | 14.2105 | 24.063 | 3.6589 | 6.1935 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 5520 | 1 | 4 | 16.3636 | 23.9236 | 2.6369 | 4.9231 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 5521 | 0.8 | 5 | 12.5581 | 18.5096 | 2.3959 | 3.5556 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 5522 | 1 | 4 | 8.5714 | 15.7363 | 2.5934 | 4.5714 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 5523 | 0.8 | 5 | 15.4286 | 21.8574 | 3.8689 | 2.56 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 5524 | 1 | 4 | 10 | 17.5748 | 2.6517 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 5525 | 1 | 4 | 12.5581 | 18.191 | 3.2329 | 2.4 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 5526 | 1 | 4 | 11.0204 | 19.9682 | 3.3007 | 5.6471 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 5527 | 1 | 4 | 11.0204 | 18.5657 | 3.3714 | 4.1739 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 5528 | 0.4 | 10 | 16.875 | 28.4629 | 2.8606 | 8.7273 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 5529 | 1.4 | 2.8571 | 12.8571 | 18.371 | 2.1455 | 3.3684 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 5530 | 1 | 4 | 9.1525 | 18.9955 | 2.4583 | 7.3846 | 1.6 | 3.125 | 0.2 | 10 | 17.125
| 5531 | 1 | 4 | 13.5 | 21.0224 | 3.5224 | 4 | 1 | 5 | 0.1 | 20 | 29
| 5532 | 0.6 | 6.6667 | 15.4286 | 23.8875 | 3.6589 | 4.8 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 5533 | 0.6 | 6.6667 | 10.1887 | 18.6202 | 3.9664 | 4.4651 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 5534 | 1.2 | 3.3333 | 12.2727 | 19.4197 | 2.6818 | 4.4651 | 1 | 5 | 0.2 | 10 | 18.3333
| 5535 | 0.8 | 5 | 11.7391 | 19.4783 | 3.1678 | 4.5714 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 5536 | 1 | 4 | 11.0204 | 18.3305 | 3.6875 | 3.6226 | 1 | 5 | 0.2 | 10 | 19
| 5537 | 0.6 | 6.6667 | 21.6 | 28.4555 | 3.2329 | 3.6226 | 1.6 | 3.125 | 0.2 | 10 | 19.7917
| 5538 | 1.2 | 3.3333 | 19.2857 | 26.5975 | 3.0452 | 4.2667 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 5539 | 1.2 | 3.3333 | 10.5882 | 22.8888 | 2.1953 | 10.1053 | 1 | 5 | 0.4 | 5 | 13.3333
| 5540 | 1 | 4 | 12.2727 | 18.1805 | 2.7602 | 3.1475 | 1 | 5 | 0.2 | 10 | 19
| 5541 | 1 | 4 | 11.25 | 21.0953 | 3.4453 | 6.4 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 5542 | 1 | 4 | 7.7143 | 13.7207 | 3.0064 | 3 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 5543 | 0.8 | 5 | 14.5946 | 23.2917 | 2.6971 | 6 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 5544 | 1 | 4 | 10 | 16.611 | 3.3007 | 3.3103 | 1 | 5 | 0.2 | 10 | 19
| 5545 | 1 | 4 | 7.5 | 18.9399 | 2.7126 | 8.7273 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 5546 | 0.6 | 6.6667 | 13.8462 | 21.8118 | 2.7765 | 5.1892 | 1 | 5 | 0.2 | 10 | 21.6667
| 5547 | 0.4 | 10 | 11.0204 | 16.9521 | 2.9317 | 3 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 5548 | 1 | 4 | 14.5946 | 25.8192 | 2.4974 | 8.7273 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 5549 | 0.8 | 5 | 13.8462 | 21.3554 | 2.8263 | 4.6829 | 1 | 5 | 0.4 | 5 | 15
| 5550 | 0.8 | 5 | 10.5882 | 17.3166 | 2.7283 | 4 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 5551 | 0.4 | 10 | 13.1707 | 19.4599 | 2.8606 | 3.4286 | 0.4 | 12.5 | 0.4 | 5 | 27.5
| 5552 | 1 | 4 | 11.25 | 19.1604 | 2.9873 | 4.9231 | 0.4 | 12.5 | 0.2 | 10 | 26.5
| 5553 | 1.2 | 3.3333 | 14.5946 | 23.4308 | 3.1892 | 5.6471 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 5554 | 1.2 | 3.3333 | 11.7391 | 19.5648 | 3.0256 | 4.8 | 1.8 | 2.7778 | 0.2 | 10 | 16.1111
| 5555 | 0.6 | 6.6667 | 8.5714 | 14.3423 | 3.2109 | 2.56 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 5556 | 1.2 | 3.3333 | 8.8525 | 15.8533 | 3.4453 | 3.5556 | 1 | 5 | 0.4 | 5 | 13.3333
| 5557 | 0.8 | 5 | 12.2727 | 21.8758 | 3.6031 | 6 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 5558 | 1.2 | 3.3333 | 9.6429 | 19.6067 | 2.5792 | 7.3846 | 1 | 5 | 1 | 2 | 10.3333
| 5559 | 0.6 | 6.6667 | 11.4894 | 19.883 | 3.4706 | 4.9231 | 1 | 5 | 0.4 | 5 | 16.6667
| 5560 | 0.4 | 10 | 9 | 15.1199 | 2.8095 | 3.3103 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 5561 | 0.2 | 20 | 9.4737 | 18.8694 | 3.3957 | 6 | 1.6 | 3.125 | 0.4 | 5 | 28.125
| 5562 | 0.2 | 20 | 12.2727 | 20.5752 | 2.3024 | 6 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 5563 | 0.8 | 5 | 13.5 | 25.1141 | 2.4712 | 9.1429 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 5564 | 0.8 | 5 | 10.3846 | 18.045 | 2.6077 | 5.0526 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 5565 | 0.2 | 20 | 12 | 21.8316 | 3.2109 | 6.6207 | 0.6 | 8.3333 | 0.2 | 10 | 38.3333
| 5566 | 0.8 | 5 | 11.7391 | 18.8586 | 4.4528 | 2.6667 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 5567 | 1.4 | 2.8571 | 12 | 21.4487 | 3.2552 | 6.1935 | 1.2 | 4.1667 | 1 | 2 | 9.0238
| 5568 | 1.2 | 3.3333 | 8.1818 | 14.5016 | 2.6971 | 3.6226 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 5569 | 0.8 | 5 | 10.8 | 15.8237 | 2.4974 | 2.5263 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 5570 | 0.4 | 10 | 10.3846 | 17.198 | 2.7283 | 4.0851 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 5571 | 0.8 | 5 | 10.8 | 17.1161 | 2.5514 | 3.7647 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 5572 | 0.6 | 6.6667 | 10 | 16.6222 | 2.6222 | 4 | 1 | 5 | 0.2 | 10 | 21.6667
| 5573 | 0.4 | 10 | 12 | 19.222 | 4.6275 | 2.5946 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 5574 | 1 | 4 | 13.5 | 19.7856 | 2.4456 | 3.84 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 5575 | 0.8 | 5 | 10.8 | 19.1463 | 2.8606 | 5.4857 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 5576 | 0.6 | 6.6667 | 13.1707 | 20.1712 | 2.6369 | 4.3636 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 5577 | 0.4 | 10 | 12.5581 | 19.682 | 2.7602 | 4.3636 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 5578 | 1.2 | 3.3333 | 13.5 | 19.7359 | 2.3959 | 3.84 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 5579 | 0.8 | 5 | 9.1525 | 17.1652 | 3.746 | 4.2667 | 1 | 5 | 0.4 | 5 | 15
| 5580 | 0.2 | 20 | 11.25 | 19.5333 | 2.95 | 5.3333 | 1 | 5 | 0.4 | 5 | 30
| 5581 | 0.4 | 10 | 18 | 25.9053 | 3.1053 | 4.8 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 5582 | 1.2 | 3.3333 | 13.1707 | 23.2171 | 3.1892 | 6.8571 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 5583 | 0.8 | 5 | 12.2727 | 19.0631 | 3.0256 | 3.7647 | 1 | 5 | 0.2 | 10 | 20
| 5584 | 1.4 | 2.8571 | 10 | 17.3118 | 3.0452 | 4.2667 | 1.4 | 3.5714 | 0.6 | 3.3333 | 9.7619
| 5585 | 1 | 4 | 13.5 | 20.7329 | 3.2329 | 4 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 5586 | 0.8 | 5 | 16.3636 | 24.5112 | 3.3475 | 4.8 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 5587 | 1 | 4 | 12.2727 | 22.3545 | 2.6971 | 7.3846 | 1 | 5 | 0.4 | 5 | 14
| 5588 | 0.8 | 5 | 12 | 18.8601 | 3.1678 | 3.6923 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 5589 | 1.4 | 2.8571 | 13.8462 | 22.377 | 2.7126 | 5.8182 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 5590 | 0.6 | 6.6667 | 13.8462 | 19.4814 | 2.9686 | 2.6667 | 1 | 5 | 0.4 | 5 | 16.6667
| 5591 | 1.2 | 3.3333 | 18 | 24.422 | 3.1678 | 3.2542 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 5592 | 0.6 | 6.6667 | 11.0204 | 21.6937 | 4.6733 | 6 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 5593 | 1 | 4 | 9.6429 | 16.8757 | 3.2329 | 4 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 5594 | 0.6 | 6.6667 | 14.2105 | 21.7661 | 4 | 3.5556 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 5595 | 0.8 | 5 | 14.2105 | 22.9693 | 2.5652 | 6.1935 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 5596 | 0.4 | 10 | 13.1707 | 24.5647 | 2.6667 | 8.7273 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 5597 | 0.8 | 5 | 11.25 | 18.9915 | 2.4082 | 5.3333 | 1 | 5 | 0.4 | 5 | 15
| 5598 | 1.2 | 3.3333 | 11.7391 | 19.2979 | 4.4112 | 3.1475 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 5599 | 1.4 | 2.8571 | 10.3846 | 18.1346 | 2.95 | 4.8 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 5600 | 1 | 4 | 11.0204 | 18.262 | 2.7765 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 5601 | 1 | 4 | 14.5946 | 24.2951 | 2.8434 | 6.8571 | 1 | 5 | 0.2 | 10 | 19
| 5602 | 1.2 | 3.3333 | 11.0204 | 20.8757 | 2.7442 | 7.1111 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 5603 | 1.2 | 3.3333 | 14.2105 | 21.2362 | 3.0256 | 4 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 5604 | 0.8 | 5 | 10.1887 | 18.3226 | 3.2109 | 4.9231 | 1 | 5 | 0.4 | 5 | 15
| 5605 | 1 | 4 | 11.25 | 19.0952 | 3.0452 | 4.8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 5606 | 0.4 | 10 | 13.5 | 23.3453 | 3.4453 | 6.4 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 5607 | 0.4 | 10 | 13.1707 | 18.7089 | 3.1678 | 2.3704 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 5608 | 0.8 | 5 | 15 | 23.3434 | 3.4203 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 5609 | 0.4 | 10 | 16.3636 | 22.8259 | 2.6222 | 3.84 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 5610 | 0.6 | 6.6667 | 16.3636 | 23.0342 | 3.4706 | 3.2 | 1 | 5 | 0.2 | 10 | 21.6667
| 5611 | 1.4 | 2.8571 | 16.3636 | 21.6131 | 2.3838 | 2.8657 | 1.8 | 2.7778 | 0.2 | 10 | 15.6349
| 5612 | 1.2 | 3.3333 | 15 | 21.6395 | 3.2109 | 3.4286 | 1 | 5 | 0.4 | 5 | 13.3333
| 5613 | 1 | 4 | 8.4375 | 16.0161 | 2.8957 | 4.6829 | 1.6 | 3.125 | 0.6 | 3.3333 | 10.4583
| 5614 | 1 | 4 | 13.5 | 22.9364 | 2.5792 | 6.8571 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 5615 | 0.8 | 5 | 13.1707 | 19.2646 | 2.4712 | 3.6226 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 5616 | 0.6 | 6.6667 | 15 | 24.079 | 2.4583 | 6.6207 | 1 | 5 | 0.1 | 20 | 31.6667
| 5617 | 0.8 | 5 | 13.8462 | 21.4017 | 4 | 3.5556 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 5618 | 0.4 | 10 | 13.1707 | 19.9082 | 3.0452 | 3.6923 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 5619 | 1.2 | 3.3333 | 14.2105 | 20.457 | 2.878 | 3.3684 | 1 | 5 | 0.4 | 5 | 13.3333
| 5620 | 1.2 | 3.3333 | 13.5 | 22.3606 | 2.8606 | 6 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 5621 | 1.6 | 2.5 | 12 | 19.1732 | 2.8095 | 4.3636 | 0.6 | 8.3333 | 0.2 | 10 | 20.8333
| 5622 | 0.6 | 6.6667 | 11.7391 | 17.3162 | 3.1467 | 2.4304 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 5623 | 1 | 4 | 16.875 | 24.8249 | 3.776 | 4.1739 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 5624 | 1.2 | 3.3333 | 11.25 | 17.5215 | 2.5792 | 3.6923 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 5625 | 0.6 | 6.6667 | 11.25 | 19.4026 | 3.6875 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 15
| 5626 | 0.8 | 5 | 11.7391 | 19.4348 | 2.8957 | 4.8 | 1 | 5 | 0.2 | 10 | 20
| 5627 | 0.8 | 5 | 14.5946 | 21.7114 | 3.8065 | 3.3103 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 5628 | 0.8 | 5 | 10.5882 | 18.4842 | 2.8434 | 5.0526 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 5629 | 1.2 | 3.3333 | 10.5882 | 19.3668 | 3.4453 | 5.3333 | 1 | 5 | 0.2 | 10 | 18.3333
| 5630 | 0.6 | 6.6667 | 12 | 21.6308 | 3.6308 | 6 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 5631 | 0.8 | 5 | 10.8 | 17.6601 | 2.5934 | 4.2667 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 5632 | 0.6 | 6.6667 | 12 | 20.2541 | 3.0649 | 5.1892 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 5633 | 0.8 | 5 | 12.2727 | 21.265 | 3.6589 | 5.3333 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 5634 | 0.4 | 10 | 16.3636 | 24.2486 | 3.085 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 5635 | 1 | 4 | 8.7097 | 17.438 | 2.7283 | 6 | 1.6 | 3.125 | 0.2 | 10 | 17.125
| 5636 | 0.4 | 10 | 10.1887 | 17.0922 | 2.6369 | 4.2667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 5637 | 0.6 | 6.6667 | 12 | 20.1392 | 2.95 | 5.1892 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 5638 | 1.2 | 3.3333 | 12.2727 | 19.5143 | 2.7765 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 5639 | 0.6 | 6.6667 | 8.4375 | 15.5693 | 2.6667 | 4.4651 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 5640 | 1.2 | 3.3333 | 14.5946 | 20.5164 | 3.2552 | 2.6667 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 5641 | 0.8 | 5 | 9 | 15.2299 | 2.5376 | 3.6923 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 5642 | 0.2 | 20 | 11.4894 | 18.9566 | 3.5489 | 3.9184 | 0.6 | 8.3333 | 0.4 | 5 | 33.3333
| 5643 | 0.2 | 20 | 11.0204 | 17.9261 | 2.9873 | 3.9184 | 1 | 5 | 0.2 | 10 | 35
| 5644 | 0.4 | 10 | 10.1887 | 19.3508 | 2.9686 | 6.1935 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 5645 | 1.2 | 3.3333 | 11.7391 | 16.7703 | 2.5376 | 2.4935 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 5646 | 0.4 | 10 | 11.7391 | 19.3024 | 2.5106 | 5.0526 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 5647 | 1 | 4 | 9.8182 | 17.0348 | 2.95 | 4.2667 | 1 | 5 | 0.8 | 2.5 | 11.5
| 5648 | 1 | 4 | 12.8571 | 19.518 | 3.1053 | 3.5556 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 5649 | 0.6 | 6.6667 | 15 | 23.2945 | 3.1053 | 5.1892 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 5650 | 0.6 | 6.6667 | 23.4783 | 31.8976 | 3.4963 | 4.9231 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 5651 | 0.6 | 6.6667 | 10.8 | 17.7173 | 3.5489 | 3.3684 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 5652 | 1.4 | 2.8571 | 9.8182 | 18.0586 | 2.5934 | 5.6471 | 1 | 5 | 0.4 | 5 | 12.8571
| 5653 | 0.2 | 20 | 11.7391 | 19.5044 | 2.7126 | 5.0526 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 5654 | 0.6 | 6.6667 | 15.4286 | 22.2967 | 2.1852 | 4.6829 | 1 | 5 | 0.6 | 3.3333 | 15
| 5655 | 0.6 | 6.6667 | 7.9412 | 15.9255 | 5.0753 | 2.9091 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 5656 | 1.2 | 3.3333 | 13.5 | 21.3938 | 3.2109 | 4.6829 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 5657 | 1.2 | 3.3333 | 16.3636 | 24.6824 | 3.3957 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 5658 | 0.6 | 6.6667 | 13.8462 | 22.6557 | 2.8095 | 6 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 5659 | 1.4 | 2.8571 | 9.4737 | 16.3037 | 3.5758 | 3.2542 | 1 | 5 | 0.4 | 5 | 12.8571
| 5660 | 1.2 | 3.3333 | 16.3636 | 22.8612 | 2.5792 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 5661 | 1 | 4 | 10.1887 | 19.3489 | 2.7602 | 6.4 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 5662 | 0.6 | 6.6667 | 15.8824 | 21.8584 | 2.4205 | 3.5556 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 5663 | 1 | 4 | 16.875 | 24.0257 | 2.5792 | 4.5714 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 5664 | 0.8 | 5 | 13.5 | 22.6421 | 3.3239 | 5.8182 | 1 | 5 | 0.4 | 5 | 15
| 5665 | 1 | 4 | 11.4894 | 19.9521 | 2.2692 | 6.1935 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 5666 | 0.8 | 5 | 11.0204 | 17.6085 | 3.2778 | 3.3103 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 5667 | 0.2 | 20 | 11.7391 | 22.1451 | 3.5489 | 6.8571 | 1 | 5 | 0.4 | 5 | 30
| 5668 | 0.2 | 20 | 11.25 | 20.4763 | 2.8263 | 6.4 | 1 | 5 | 0.1 | 20 | 45
| 5669 | 0.8 | 5 | 12 | 19.2816 | 3.6589 | 3.6226 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 5670 | 0.6 | 6.6667 | 11.4894 | 18.0592 | 2.3959 | 4.1739 | 1 | 5 | 0.4 | 5 | 16.6667
| 5671 | 1.2 | 3.3333 | 14.2105 | 20.5458 | 2.7126 | 3.6226 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 5672 | 0.6 | 6.6667 | 11.0204 | 18.7549 | 2.6818 | 5.0526 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 5673 | 0.8 | 5 | 13.5 | 21.0214 | 3.6031 | 3.9184 | 0.4 | 12.5 | 0.1 | 20 | 37.5
| 5674 | 0.8 | 5 | 11.4894 | 18.5058 | 2.5514 | 4.4651 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 5675 | 1.2 | 3.3333 | 9.6429 | 17.192 | 3.6308 | 3.9184 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 5676 | 1 | 4 | 12.2727 | 18.3081 | 2.1953 | 3.84 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 5677 | 1.4 | 2.8571 | 12 | 19.0607 | 3.8065 | 3.2542 | 1 | 5 | 0.4 | 5 | 12.8571
| 5678 | 0.4 | 10 | 11.7391 | 18.1612 | 3.1678 | 3.2542 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 5679 | 1.6 | 2.5 | 13.8462 | 20.832 | 2.6222 | 4.3636 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10
| 5680 | 0.8 | 5 | 12.8571 | 18.9007 | 3.3007 | 2.7429 | 1 | 5 | 0.2 | 10 | 20
| 5681 | 1 | 4 | 12.8571 | 20.117 | 1.9265 | 5.3333 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 5682 | 1.2 | 3.3333 | 13.5 | 20.5431 | 2.7765 | 4.2667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 5683 | 0.8 | 5 | 16.3636 | 24.5421 | 3.1258 | 5.0526 | 1.4 | 3.5714 | 0.1 | 20 | 28.5714
| 5684 | 0.8 | 5 | 12.5581 | 19.7838 | 3.6031 | 3.6226 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 5685 | 0.6 | 6.6667 | 15.4286 | 21.2527 | 2.7765 | 3.0476 | 1 | 5 | 0.4 | 5 | 16.6667
| 5686 | 0.8 | 5 | 10 | 17.5929 | 2.7929 | 4.8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 5687 | 0.6 | 6.6667 | 12.8571 | 20.3318 | 3.3007 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 5688 | 1 | 4 | 10.1887 | 18.3413 | 3.6875 | 4.4651 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 5689 | 1.2 | 3.3333 | 9.3103 | 16.8135 | 2.9317 | 4.5714 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 5690 | 1.6 | 2.5 | 12.5581 | 19.1234 | 2.5652 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 11.6667
| 5691 | 1.2 | 3.3333 | 9.3103 | 19.2799 | 3.776 | 6.1935 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 5692 | 0.8 | 5 | 13.1707 | 18.9467 | 2.7283 | 3.0476 | 1 | 5 | 0.2 | 10 | 20
| 5693 | 1.2 | 3.3333 | 12 | 20.0676 | 2.4205 | 5.6471 | 1.4 | 3.5714 | 0.8 | 2.5 | 9.4048
| 5694 | 1 | 4 | 9.1525 | 14.4458 | 2.5106 | 2.7826 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 5695 | 1 | 4 | 9.6429 | 18.7162 | 3.2552 | 5.8182 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 5696 | 1 | 4 | 9.4737 | 16.5416 | 3.4453 | 3.6226 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 5697 | 0.6 | 6.6667 | 13.8462 | 19.1726 | 2.6222 | 2.7042 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 5698 | 0.6 | 6.6667 | 10.8 | 17.7115 | 2.8263 | 4.0851 | 0.6 | 8.3333 | 0.1 | 20 | 35
| 5699 | 0.6 | 6.6667 | 11.4894 | 17.6242 | 2.5792 | 3.5556 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 5700 | 1.2 | 3.3333 | 18.6207 | 29.3349 | 3.6031 | 7.1111 | 1 | 5 | 0.1 | 20 | 28.3333
| 5701 | 0.8 | 5 | 12.5581 | 19.6461 | 3.3957 | 3.6923 | 0.4 | 12.5 | 0.2 | 10 | 27.5
| 5702 | 0.8 | 5 | 10.5882 | 18.0203 | 2.8606 | 4.5714 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 5703 | 0.4 | 10 | 9.8182 | 15.1087 | 2.3366 | 2.9538 | 1 | 5 | 0.1 | 20 | 35
| 5704 | 0.8 | 5 | 11.0204 | 17.5693 | 3.5489 | 3 | 1 | 5 | 0.2 | 10 | 20
| 5705 | 0.2 | 20 | 12.8571 | 19.1175 | 2.95 | 3.3103 | 1.2 | 4.1667 | 0.1 | 20 | 44.1667
| 5706 | 0.8 | 5 | 12.8571 | 20.5453 | 3.6031 | 4.0851 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 5707 | 0.8 | 5 | 17.4194 | 23.2773 | 2.3024 | 3.5556 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 5708 | 0.6 | 6.6667 | 14.2105 | 23.0543 | 3.0256 | 5.8182 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 5709 | 1 | 4 | 15.8824 | 23.4797 | 2.4082 | 5.1892 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 5710 | 0.4 | 10 | 12 | 22.3532 | 2.9686 | 7.3846 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 5711 | 1 | 4 | 12.8571 | 19.8443 | 3.4963 | 3.4909 | 1 | 5 | 0.4 | 5 | 14
| 5712 | 0.8 | 5 | 13.1707 | 20.6314 | 2.5376 | 4.9231 | 1 | 5 | 0.4 | 5 | 15
| 5713 | 0.8 | 5 | 15 | 22.8614 | 3.6875 | 4.1739 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 5714 | 0.8 | 5 | 12.2727 | 20.0652 | 2.1455 | 5.6471 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 5715 | 0.6 | 6.6667 | 16.875 | 24.7046 | 3.1467 | 4.6829 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 5716 | 0.8 | 5 | 10.5882 | 18.0251 | 2.6369 | 4.8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 5717 | 0.2 | 20 | 13.1707 | 23.2117 | 3.4203 | 6.6207 | 1 | 5 | 0.4 | 5 | 30
| 5718 | 0.6 | 6.6667 | 13.1707 | 20.9964 | 3.0256 | 4.8 | 1 | 5 | 0.4 | 5 | 16.6667
| 5719 | 0.8 | 5 | 14.5946 | 23.3062 | 3.5224 | 5.1892 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 5720 | 0.4 | 10 | 13.1707 | 21.249 | 3.0256 | 5.0526 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 5721 | 0.8 | 5 | 8.8525 | 17.4459 | 2.5934 | 6 | 1 | 5 | 0.8 | 2.5 | 12.5
| 5722 | 0.8 | 5 | 14.5946 | 24.0999 | 3.1053 | 6.4 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 5723 | 0.6 | 6.6667 | 11.4894 | 18.2249 | 2.3719 | 4.3636 | 0.6 | 8.3333 | 1 | 2 | 17
| 5724 | 0.6 | 6.6667 | 9.8182 | 17.7627 | 4.2523 | 3.6923 | 1 | 5 | 0.4 | 5 | 16.6667
| 5725 | 0.8 | 5 | 18 | 25.7429 | 3.2778 | 4.4651 | 1 | 5 | 0.1 | 20 | 30
| 5726 | 0.6 | 6.6667 | 10.1887 | 16.4047 | 2.5934 | 3.6226 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 5727 | 0.8 | 5 | 9.6429 | 16.3603 | 2.0345 | 4.6829 | 0.4 | 12.5 | 0.1 | 20 | 37.5
| 5728 | 0.4 | 10 | 12 | 21.8689 | 3.8689 | 6 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 5729 | 0.8 | 5 | 15 | 22.8731 | 2.95 | 4.9231 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 5730 | 0.6 | 6.6667 | 13.1707 | 19.2264 | 2.433 | 3.6226 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 5731 | 0.8 | 5 | 11.25 | 19.4097 | 2.8263 | 5.3333 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 5732 | 0.4 | 10 | 12 | 17.4681 | 2.4205 | 3.0476 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 5733 | 1.2 | 3.3333 | 9.3103 | 17.2342 | 4.4952 | 3.4286 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 5734 | 0.4 | 10 | 18.6207 | 28.8493 | 3.3714 | 6.8571 | 1.6 | 3.125 | 0.6 | 3.3333 | 16.4583
| 5735 | 0.6 | 6.6667 | 14.2105 | 21.4869 | 2.5934 | 4.6829 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 5736 | 1.2 | 3.3333 | 16.3636 | 22.9461 | 2.4974 | 4.0851 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 5737 | 0.8 | 5 | 11.4894 | 17.2686 | 2.5792 | 3.2 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 5738 | 1 | 4 | 10.8 | 16.2476 | 2.2476 | 3.2 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.8333
| 5739 | 0.6 | 6.6667 | 11.7391 | 18.5181 | 2.8606 | 3.9184 | 1.6 | 3.125 | 0.4 | 5 | 14.7917
| 5740 | 0.8 | 5 | 12.2727 | 20.1377 | 3.0649 | 4.8 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 5741 | 0.4 | 10 | 10.8 | 20.0228 | 3.5758 | 5.6471 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 5742 | 0.6 | 6.6667 | 10.5882 | 15.8488 | 2.8606 | 2.4 | 1 | 5 | 0.6 | 3.3333 | 15
| 5743 | 1.2 | 3.3333 | 14.5946 | 20.535 | 2.7929 | 3.1475 | 1 | 5 | 0.4 | 5 | 13.3333
| 5744 | 0.6 | 6.6667 | 15 | 21.1013 | 3.2778 | 2.8235 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 5745 | 0.6 | 6.6667 | 12.5581 | 20.2667 | 3.0256 | 4.6829 | 1 | 5 | 0.1 | 20 | 31.6667
| 5746 | 0.6 | 6.6667 | 15.4286 | 21.2175 | 3.0064 | 2.7826 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 5747 | 1.2 | 3.3333 | 7.9412 | 17.6836 | 3.5489 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 5748 | 1 | 4 | 13.5 | 23.6935 | 4 | 6.1935 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 5749 | 0.6 | 6.6667 | 13.5 | 21.0283 | 2.7283 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 5750 | 0.6 | 6.6667 | 9.6429 | 16.2357 | 3.4453 | 3.1475 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 5751 | 0.8 | 5 | 11.0204 | 17.7424 | 2.6369 | 4.0851 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 5752 | 0.8 | 5 | 16.875 | 26.4754 | 4.4112 | 5.1892 | 1 | 5 | 0.1 | 20 | 30
| 5753 | 0.4 | 10 | 13.5 | 20.0544 | 3.1258 | 3.4286 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 5754 | 0.8 | 5 | 12 | 19.4908 | 3.0256 | 4.4651 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 5755 | 0.6 | 6.6667 | 19.2857 | 24.549 | 2.95 | 2.3133 | 1.6 | 3.125 | 0.2 | 10 | 19.7917
| 5756 | 0.8 | 5 | 15.8824 | 25.8037 | 3.3007 | 6.6207 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 5757 | 0.8 | 5 | 9.4737 | 15.2978 | 2.7765 | 3.0476 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 5758 | 0.6 | 6.6667 | 10.3846 | 15.5137 | 2.8434 | 2.2857 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 5759 | 1 | 4 | 13.5 | 21.7303 | 3.6589 | 4.5714 | 1 | 5 | 0.1 | 20 | 29
| 5760 | 1.8 | 2.2222 | 12.8571 | 21.2745 | 2.9317 | 5.4857 | 0.8 | 6.25 | 0.4 | 5 | 13.4722
| 5761 | 0.8 | 5 | 13.8462 | 19.4274 | 3.2109 | 2.3704 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 5762 | 0.8 | 5 | 16.875 | 25.96 | 3.085 | 6 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 5763 | 0.8 | 5 | 12.5581 | 19.1835 | 2.8606 | 3.7647 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 5764 | 0.8 | 5 | 14.2105 | 21.9431 | 2.8095 | 4.9231 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 5765 | 0.8 | 5 | 16.3636 | 23.6742 | 3.4706 | 3.84 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 5766 | 0.8 | 5 | 12.2727 | 18.8099 | 2.6971 | 3.84 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 5767 | 1.2 | 3.3333 | 11.4894 | 18.315 | 2.6517 | 4.1739 | 1 | 5 | 0.2 | 10 | 18.3333
| 5768 | 0.2 | 20 | 13.1707 | 20.5685 | 2.8263 | 4.5714 | 1.6 | 3.125 | 0.2 | 10 | 33.125
| 5769 | 0.8 | 5 | 13.1707 | 19.6485 | 3.2778 | 3.2 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 5770 | 0.6 | 6.6667 | 15 | 21.0031 | 3.6031 | 2.4 | 1 | 5 | 0.2 | 10 | 21.6667
| 5771 | 0.8 | 5 | 15 | 23.732 | 3.085 | 5.6471 | 1 | 5 | 0.2 | 10 | 20
| 5772 | 0.8 | 5 | 9.8182 | 16.2284 | 2.3251 | 4.0851 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 5773 | 0.6 | 6.6667 | 21.6 | 28.6637 | 3.3714 | 3.6923 | 1 | 5 | 0.2 | 10 | 21.6667
| 5774 | 1 | 4 | 13.1707 | 19.1882 | 2.3251 | 3.6923 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 5775 | 1 | 4 | 10.8 | 18.5281 | 3.0452 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 5776 | 1.2 | 3.3333 | 13.5 | 19.5757 | 3.3714 | 2.7042 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 5777 | 1 | 4 | 11.25 | 18.7258 | 2.7929 | 4.6829 | 1.6 | 3.125 | 0.8 | 2.5 | 9.625
| 5778 | 0.8 | 5 | 13.8462 | 19.3041 | 2.9317 | 2.5263 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 5779 | 0.6 | 6.6667 | 13.1707 | 20.5153 | 4.0342 | 3.3103 | 1.4 | 3.5714 | 0.1 | 20 | 30.2381
| 5780 | 0.8 | 5 | 12.2727 | 17.4231 | 2.9686 | 2.1818 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 5781 | 0.4 | 10 | 11.25 | 20.9946 | 2.36 | 7.3846 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 5782 | 1.2 | 3.3333 | 9.3103 | 16.23 | 2.3483 | 4.5714 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 5783 | 0.4 | 10 | 16.3636 | 23.6772 | 3.5489 | 3.7647 | 1 | 5 | 0.2 | 10 | 25
| 5784 | 0.2 | 20 | 13.1707 | 20.9301 | 3.3957 | 4.3636 | 1.8 | 2.7778 | 0.2 | 10 | 32.7778
| 5785 | 1 | 4 | 12.5581 | 19.3971 | 3.1467 | 3.6923 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 5786 | 0.6 | 6.6667 | 10 | 15.7827 | 3.5758 | 2.2069 | 1 | 5 | 0.6 | 3.3333 | 15
| 5787 | 0.1 | 40 | 14.2105 | 20.3591 | 2.3838 | 3.7647 | 1 | 5 | 0.2 | 10 | 55
| 5788 | 0.4 | 10 | 10.5882 | 15.883 | 2.4712 | 2.8235 | 1 | 5 | 0.2 | 10 | 25
| 5789 | 1 | 4 | 12 | 18.2974 | 3.6308 | 2.6667 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 5790 | 0.2 | 20 | 9.1525 | 18.1385 | 3.1678 | 5.8182 | 0.8 | 6.25 | 0.1 | 20 | 46.25
| 5791 | 0.8 | 5 | 10.5882 | 17.2047 | 2.7765 | 3.84 | 1.2 | 4.1667 | 1 | 2 | 11.1667
| 5792 | 0.4 | 10 | 15.8824 | 23.3389 | 3.3714 | 4.0851 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 5793 | 1.4 | 2.8571 | 15.8824 | 24.1849 | 3.8374 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 5794 | 0.4 | 10 | 15.8824 | 21.2252 | 2.1953 | 3.1475 | 1 | 5 | 0.4 | 5 | 20
| 5795 | 0.4 | 10 | 13.8462 | 22.0206 | 3.6031 | 4.5714 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 5796 | 0.6 | 6.6667 | 7.1053 | 15.7587 | 3.0064 | 5.6471 | 1.6 | 3.125 | 0.2 | 10 | 19.7917
| 5797 | 0.8 | 5 | 14.2105 | 22.6259 | 4.3303 | 4.0851 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 5798 | 1 | 4 | 12.2727 | 20.055 | 3.2109 | 4.5714 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 5799 | 0.8 | 5 | 13.5 | 19.9336 | 2.878 | 3.5556 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 5800 | 0.6 | 6.6667 | 15 | 21.4226 | 2.9317 | 3.4909 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 5801 | 1 | 4 | 9.6429 | 16.2797 | 2.6369 | 4 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 5802 | 0.6 | 6.6667 | 12 | 23.1742 | 2.8263 | 8.3478 | 1 | 5 | 0.2 | 10 | 21.6667
| 5803 | 0.8 | 5 | 8.4375 | 14.7094 | 2.8434 | 3.4286 | 1 | 5 | 0.4 | 5 | 15
| 5804 | 0.2 | 20 | 9.3103 | 17.5809 | 3.4706 | 4.8 | 1.4 | 3.5714 | 0.2 | 10 | 33.5714
| 5805 | 1.2 | 3.3333 | 11.25 | 16.3213 | 2.2056 | 2.8657 | 1.6 | 3.125 | 0.2 | 10 | 16.4583
| 5806 | 0.8 | 5 | 12.8571 | 22.9695 | 3.2552 | 6.8571 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 5807 | 1.2 | 3.3333 | 14.2105 | 22.0412 | 2.4974 | 5.3333 | 1 | 5 | 0.4 | 5 | 13.3333
| 5808 | 0.8 | 5 | 14.2105 | 21.0242 | 3.4453 | 3.3684 | 1 | 5 | 0.2 | 10 | 20
| 5809 | 0.8 | 5 | 13.1707 | 19.2985 | 2.6369 | 3.4909 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 5810 | 0.4 | 10 | 12.8571 | 23.4603 | 3.746 | 6.8571 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 5811 | 0.8 | 5 | 12.5581 | 22.4805 | 3.5224 | 6.4 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 5812 | 0.6 | 6.6667 | 12.5581 | 20.484 | 3.1258 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 5813 | 0.8 | 5 | 14.5946 | 21.8298 | 2.9686 | 4.2667 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 5814 | 1 | 4 | 9.8182 | 21.7125 | 4.2143 | 7.68 | 0.4 | 12.5 | 0.2 | 10 | 26.5
| 5815 | 1.4 | 2.8571 | 15.4286 | 24.2223 | 3.1467 | 5.6471 | 1 | 5 | 0.1 | 20 | 27.8571
| 5816 | 0.2 | 20 | 12 | 20.9022 | 3.2552 | 5.6471 | 1 | 5 | 0.2 | 10 | 35
| 5817 | 0.8 | 5 | 15.8824 | 22.0572 | 3.4706 | 2.7042 | 1 | 5 | 0.4 | 5 | 15
| 5818 | 0.8 | 5 | 14.2105 | 21.0369 | 2.8263 | 4 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 5819 | 0.6 | 6.6667 | 16.875 | 28.7452 | 3.5224 | 8.3478 | 0.4 | 12.5 | 0.6 | 3.3333 | 22.5
| 5820 | 1 | 4 | 10.3846 | 16.9373 | 2.7126 | 3.84 | 1 | 5 | 0.4 | 5 | 14
| 5821 | 0.6 | 6.6667 | 9.1525 | 15.4255 | 2.433 | 3.84 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 5822 | 0.6 | 6.6667 | 14.5946 | 23.9559 | 3.1678 | 6.1935 | 1 | 5 | 0.4 | 5 | 16.6667
| 5823 | 0.8 | 5 | 12.5581 | 24.6293 | 2.4712 | 9.6 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 5824 | 0.6 | 6.6667 | 18.6207 | 24.3856 | 2.5106 | 3.2542 | 1 | 5 | 0.2 | 10 | 21.6667
| 5825 | 0.6 | 6.6667 | 16.875 | 25.3194 | 3.2552 | 5.1892 | 0.6 | 8.3333 | 0.8 | 2.5 | 17.5
| 5826 | 0.4 | 10 | 13.5 | 22.4377 | 2.7442 | 6.1935 | 1.6 | 3.125 | 0.2 | 10 | 23.125
| 5827 | 0.6 | 6.6667 | 10.1887 | 16.7799 | 2.9686 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 5828 | 0.8 | 5 | 16.875 | 22.8459 | 2.3483 | 3.6226 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 5829 | 0.6 | 6.6667 | 11.0204 | 18.5467 | 2.8434 | 4.6829 | 1 | 5 | 0.4 | 5 | 16.6667
| 5830 | 0.2 | 20 | 9 | 20.6464 | 3.9664 | 7.68 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 5831 | 0.6 | 6.6667 | 16.3636 | 22.7326 | 2.878 | 3.4909 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 5832 | 1 | 4 | 12 | 18.4009 | 3.1467 | 3.2542 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 5833 | 1.2 | 3.3333 | 15 | 21.1766 | 2.3366 | 3.84 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 5834 | 0.8 | 5 | 12.5581 | 22.8356 | 3.4203 | 6.8571 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 5835 | 1.2 | 3.3333 | 13.1707 | 21.619 | 3.3957 | 5.0526 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 5836 | 0.4 | 10 | 19.2857 | 26.5807 | 2.3719 | 4.9231 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 5837 | 1 | 4 | 12.2727 | 18.4955 | 2.9686 | 3.2542 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 5838 | 0.8 | 5 | 13.5 | 23.6964 | 3.5758 | 6.6207 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 5839 | 1 | 4 | 13.8462 | 21.0885 | 3.3239 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 5840 | 0.8 | 5 | 13.8462 | 23.0849 | 3.0452 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 5841 | 0.6 | 6.6667 | 14.5946 | 22.3539 | 3.3957 | 4.3636 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 5842 | 0.8 | 5 | 20.7692 | 28.8475 | 3.0256 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 5843 | 0.6 | 6.6667 | 12 | 18.5552 | 2.6369 | 3.9184 | 1 | 5 | 0.1 | 20 | 31.6667
| 5844 | 0.6 | 6.6667 | 11.7391 | 18.4897 | 3.4963 | 3.2542 | 1 | 5 | 0.6 | 3.3333 | 15
| 5845 | 0.1 | 40 | 10.3846 | 16.9399 | 2.6369 | 3.9184 | 1.2 | 4.1667 | 0.6 | 3.3333 | 47.5
| 5846 | 0.6 | 6.6667 | 11.0204 | 18.8994 | 2.8263 | 5.0526 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 5847 | 1 | 4 | 14.2105 | 25.7307 | 2.7929 | 8.7273 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 5848 | 0.2 | 20 | 9.6429 | 15.7272 | 2.5934 | 3.4909 | 1 | 5 | 0.1 | 20 | 45
| 5849 | 0.4 | 10 | 12 | 22.3889 | 3.2778 | 7.1111 | 1 | 5 | 0.1 | 20 | 35
| 5850 | 0.8 | 5 | 12 | 20.4357 | 2.95 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 5851 | 1.2 | 3.3333 | 11.25 | 17.8412 | 2.9686 | 3.6226 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 5852 | 0.8 | 5 | 17.4194 | 25.6959 | 2.4583 | 5.8182 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 5853 | 0.6 | 6.6667 | 24.5455 | 32.4371 | 2.9686 | 4.9231 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 5854 | 0.8 | 5 | 15.8824 | 23.7777 | 3.3239 | 4.5714 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 5855 | 0.6 | 6.6667 | 10.1887 | 18.7393 | 3.0649 | 5.4857 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 5856 | 0.8 | 5 | 13.8462 | 21.0917 | 2.4456 | 4.8 | 1 | 5 | 0.4 | 5 | 15
| 5857 | 0.4 | 10 | 12 | 21.4963 | 3.4963 | 6 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 5858 | 1 | 4 | 13.1707 | 22.5321 | 3.1678 | 6.1935 | 1 | 5 | 0.2 | 10 | 19
| 5859 | 0.6 | 6.6667 | 11.0204 | 17.4746 | 3.0256 | 3.4286 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 5860 | 1 | 4 | 15.4286 | 23.0854 | 4.0342 | 3.6226 | 1 | 5 | 0.8 | 2.5 | 11.5
| 5861 | 1.2 | 3.3333 | 14.2105 | 20.7898 | 2.5792 | 4 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 5862 | 0.8 | 5 | 15.8824 | 22.7562 | 3.4453 | 3.4286 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 5863 | 0.4 | 10 | 10 | 17.844 | 2.5106 | 5.3333 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 5864 | 1 | 4 | 11.4894 | 18.0895 | 2.6818 | 3.9184 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 5865 | 1.2 | 3.3333 | 10 | 16.7253 | 2.5514 | 4.1739 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 5866 | 0.8 | 5 | 9.4737 | 18.0832 | 3.4203 | 5.1892 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 5867 | 1.6 | 2.5 | 11.0204 | 21.5268 | 2.8263 | 7.68 | 1 | 5 | 0.8 | 2.5 | 10
| 5868 | 0.8 | 5 | 11.25 | 18.5034 | 3.6308 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 5869 | 0.2 | 20 | 14.5946 | 20.2639 | 2.7602 | 2.9091 | 1.2 | 4.1667 | 0.6 | 3.3333 | 27.5
| 5870 | 0.8 | 5 | 16.3636 | 22.1285 | 2.5106 | 3.2542 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 5871 | 0.8 | 5 | 9 | 16.9429 | 3.3714 | 4.5714 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 5872 | 0.2 | 20 | 12.8571 | 20.9347 | 2.7442 | 5.3333 | 1.2 | 4.1667 | 0.8 | 2.5 | 26.6667
| 5873 | 1 | 4 | 12.8571 | 20.4283 | 3.8065 | 3.7647 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 5874 | 1 | 4 | 11.4894 | 19.8924 | 3.6031 | 4.8 | 1.4 | 3.5714 | 0.1 | 20 | 27.5714
| 5875 | 1.2 | 3.3333 | 11.0204 | 21.1374 | 3.4963 | 6.6207 | 1 | 5 | 0.4 | 5 | 13.3333
| 5876 | 0.6 | 6.6667 | 13.1707 | 22.016 | 2.6517 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 5877 | 1.4 | 2.8571 | 12.5581 | 20.1491 | 3.1258 | 4.4651 | 1.2 | 4.1667 | 0.1 | 20 | 27.0238
| 5878 | 1.2 | 3.3333 | 9.4737 | 17.8996 | 2.6077 | 5.8182 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 5879 | 1 | 4 | 9.8182 | 19.1465 | 2.4712 | 6.8571 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 5880 | 1.2 | 3.3333 | 14.5946 | 20.9189 | 2.8957 | 3.4286 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 5881 | 0.4 | 10 | 13.1707 | 21.4998 | 2.8434 | 5.4857 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 5882 | 1.2 | 3.3333 | 12.5581 | 18.7134 | 2.1553 | 4 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 5883 | 0.6 | 6.6667 | 13.1707 | 19.7862 | 2.6971 | 3.9184 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 5884 | 1 | 4 | 10.8 | 17.4609 | 3.8374 | 2.8235 | 1 | 5 | 0.4 | 5 | 14
| 5885 | 0.6 | 6.6667 | 12.8571 | 20.2549 | 2.8263 | 4.5714 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 5886 | 1.2 | 3.3333 | 11.7391 | 18.6091 | 3.1053 | 3.7647 | 1.4 | 3.5714 | 0.1 | 20 | 26.9048
| 5887 | 1 | 4 | 12 | 18.7018 | 3.2109 | 3.4909 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 5888 | 0.6 | 6.6667 | 11.7391 | 19.3955 | 3.085 | 4.5714 | 1 | 5 | 0.1 | 20 | 31.6667
| 5889 | 0.2 | 20 | 11.0204 | 16.8356 | 3.2552 | 2.56 | 0.2 | 25 | 0.2 | 10 | 55
| 5890 | 0.6 | 6.6667 | 12.8571 | 22.9183 | 2.95 | 7.1111 | 1 | 5 | 0.6 | 3.3333 | 15
| 5891 | 1.6 | 2.5 | 11.7391 | 19.4886 | 2.8263 | 4.9231 | 1 | 5 | 0.4 | 5 | 12.5
| 5892 | 0.6 | 6.6667 | 14.5946 | 25.6221 | 3.3475 | 7.68 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 5893 | 0.8 | 5 | 9.3103 | 18.6039 | 4.1043 | 5.1892 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 5894 | 0.6 | 6.6667 | 13.8462 | 19.277 | 2.5652 | 2.8657 | 1 | 5 | 0.6 | 3.3333 | 15
| 5895 | 1 | 4 | 8.4375 | 15.1362 | 3.0064 | 3.6923 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 5896 | 0.6 | 6.6667 | 13.8462 | 19.5058 | 2.2913 | 3.3684 | 1 | 5 | 1 | 2 | 13.6667
| 5897 | 0.4 | 10 | 9.6429 | 17.6799 | 2.5514 | 5.4857 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 5898 | 0.8 | 5 | 9.4737 | 16.3642 | 3.1258 | 3.7647 | 1 | 5 | 0.2 | 10 | 20
| 5899 | 0.4 | 10 | 13.1707 | 22.616 | 3.4453 | 6 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 5900 | 0.8 | 5 | 10.3846 | 18.6791 | 3.3714 | 4.9231 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 5901 | 0.8 | 5 | 10.1887 | 17.8005 | 3.1467 | 4.4651 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 5902 | 0.8 | 5 | 15.4286 | 23.195 | 2.8434 | 4.9231 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 5903 | 0.8 | 5 | 10.3846 | 17.8664 | 2.6818 | 4.8 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 5904 | 0.6 | 6.6667 | 7.1053 | 14.539 | 2.5106 | 4.9231 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 5905 | 0.8 | 5 | 11.7391 | 20.5488 | 3.3239 | 5.4857 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 5906 | 0.6 | 6.6667 | 14.2105 | 23.2955 | 3.085 | 6 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 5907 | 0.2 | 20 | 7.8261 | 15.3232 | 2.6971 | 4.8 | 1.2 | 4.1667 | 0.1 | 20 | 44.1667
| 5908 | 1 | 4 | 15.4286 | 23.2498 | 4.3303 | 3.4909 | 1 | 5 | 0.4 | 5 | 14
| 5909 | 0.6 | 6.6667 | 12.2727 | 19.6375 | 2.6818 | 4.6829 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 5910 | 1 | 4 | 13.1707 | 24.8507 | 4 | 7.68 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 5911 | 0.8 | 5 | 13.5 | 19.0987 | 2.9686 | 2.6301 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 5912 | 1.2 | 3.3333 | 12.5581 | 19.253 | 2.7765 | 3.9184 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 5913 | 1.6 | 2.5 | 15.4286 | 22.3571 | 2.8434 | 4.0851 | 0.6 | 8.3333 | 0.6 | 3.3333 | 14.1667
| 5914 | 1 | 4 | 14.5946 | 21.892 | 3.8689 | 3.4286 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 5915 | 0.8 | 5 | 9.4737 | 15.0055 | 2.4842 | 3.0476 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 5916 | 1 | 4 | 9.8182 | 24.1772 | 3.0649 | 11.2941 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 5917 | 1.4 | 2.8571 | 11.25 | 18.4104 | 3.3957 | 3.7647 | 0.6 | 8.3333 | 0.6 | 3.3333 | 14.5238
| 5918 | 0.8 | 5 | 9.8182 | 17.3912 | 2.3838 | 5.1892 | 1 | 5 | 0.4 | 5 | 15
| 5919 | 1 | 4 | 10.3846 | 16.3603 | 3.2329 | 2.7429 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 5920 | 1 | 4 | 10.1887 | 23.3657 | 4.0342 | 9.1429 | 1 | 5 | 0.4 | 5 | 14
| 5921 | 0.6 | 6.6667 | 12 | 20.4001 | 3.3475 | 5.0526 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 5922 | 0.6 | 6.6667 | 12 | 21.7714 | 3.3714 | 6.4 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 5923 | 0.4 | 10 | 10.5882 | 18.0628 | 3.3007 | 4.1739 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 5924 | 0.8 | 5 | 13.1707 | 22.1574 | 4.72 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 5925 | 1.2 | 3.3333 | 18 | 25.6049 | 2.6818 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 5926 | 1 | 4 | 13.8462 | 23.2914 | 3.4453 | 6 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 5927 | 1.4 | 2.8571 | 18.6207 | 28.092 | 3.2778 | 6.1935 | 1.4 | 3.5714 | 0.2 | 10 | 16.4286
| 5928 | 0.6 | 6.6667 | 12 | 21.8985 | 3.2778 | 6.6207 | 1 | 5 | 0.4 | 5 | 16.6667
| 5929 | 1.2 | 3.3333 | 20 | 28.3758 | 3.5758 | 4.8 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 5930 | 0.8 | 5 | 9.8182 | 21.8006 | 3.2552 | 8.7273 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 5931 | 0.6 | 6.6667 | 11.25 | 17.2659 | 3.5224 | 2.4935 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 5932 | 0.6 | 6.6667 | 11.7391 | 17.9209 | 3.085 | 3.0968 | 1.6 | 3.125 | 0.6 | 3.3333 | 13.125
| 5933 | 1.4 | 2.8571 | 8.7097 | 15.5072 | 3.1053 | 3.6923 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 5934 | 0.6 | 6.6667 | 19.2857 | 28.3928 | 2.9136 | 6.1935 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 5935 | 0.8 | 5 | 10 | 18.616 | 2.216 | 6.4 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 5936 | 1.6 | 2.5 | 15 | 27.0842 | 2.4842 | 9.6 | 1 | 5 | 0.6 | 3.3333 | 10.8333
| 5937 | 1.2 | 3.3333 | 11.25 | 18.9173 | 2.7442 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 5938 | 0.8 | 5 | 11.0204 | 16.8651 | 2.6971 | 3.1475 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 5939 | 0.6 | 6.6667 | 13.1707 | 20.5112 | 3.5758 | 3.7647 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 5940 | 1.2 | 3.3333 | 9.3103 | 17.4532 | 2.8095 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 5941 | 0.6 | 6.6667 | 11.0204 | 19.4205 | 3.2109 | 5.1892 | 1.4 | 3.5714 | 1 | 2 | 12.2381
| 5942 | 1.4 | 2.8571 | 14.5946 | 21.6531 | 2.5934 | 4.4651 | 1 | 5 | 0.4 | 5 | 12.8571
| 5943 | 0.8 | 5 | 12.2727 | 21.4823 | 2.8095 | 6.4 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 5944 | 1 | 4 | 12.2727 | 19.0835 | 2.6369 | 4.1739 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 5945 | 0.8 | 5 | 15.4286 | 22.4 | 3.6031 | 3.3684 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 5946 | 1.4 | 2.8571 | 10.5882 | 18.2878 | 2.7765 | 4.9231 | 1 | 5 | 0.4 | 5 | 12.8571
| 5947 | 0.6 | 6.6667 | 8.5714 | 16.9499 | 3.0452 | 5.3333 | 1 | 5 | 0.2 | 10 | 21.6667
| 5948 | 0.2 | 20 | 10.8 | 18.2517 | 3.2778 | 4.1739 | 1.4 | 3.5714 | 0.1 | 20 | 43.5714
| 5949 | 0.8 | 5 | 14.2105 | 21.8003 | 2.6667 | 4.9231 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 5950 | 0.8 | 5 | 14.5946 | 21.7569 | 2.6971 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 5951 | 0.4 | 10 | 12.2727 | 19.9723 | 2.7765 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 5952 | 1 | 4 | 11.0204 | 19.7343 | 2.8957 | 5.8182 | 1 | 5 | 0.2 | 10 | 19
| 5953 | 0.6 | 6.6667 | 12.8571 | 19.909 | 3.4963 | 3.5556 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 5954 | 1.2 | 3.3333 | 11.4894 | 18.4896 | 2.8263 | 4.1739 | 1 | 5 | 0.4 | 5 | 13.3333
| 5955 | 0.2 | 20 | 14.5946 | 22.9237 | 2.8434 | 5.4857 | 1 | 5 | 0.2 | 10 | 35
| 5956 | 1.2 | 3.3333 | 8.0597 | 14.5571 | 2.4974 | 4 | 1 | 5 | 0.2 | 10 | 18.3333
| 5957 | 0.8 | 5 | 11.4894 | 16.837 | 2.5241 | 2.8235 | 1 | 5 | 0.4 | 5 | 15
| 5958 | 0.6 | 6.6667 | 11.0204 | 19.9111 | 2.6971 | 6.1935 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 5959 | 0.4 | 10 | 8.3077 | 14.6973 | 2.4712 | 3.9184 | 1 | 5 | 0.8 | 2.5 | 17.5
| 5960 | 0.8 | 5 | 11.25 | 18.4392 | 3.1892 | 4 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 5961 | 0.8 | 5 | 11.7391 | 19.3301 | 3.1258 | 4.4651 | 1 | 5 | 0.4 | 5 | 15
| 5962 | 1 | 4 | 13.1707 | 20.8829 | 2.2264 | 5.4857 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 5963 | 0.6 | 6.6667 | 11.7391 | 16.3 | 2.2476 | 2.3133 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 5964 | 1.2 | 3.3333 | 12.5581 | 19.6957 | 3.4453 | 3.6923 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 5965 | 0.8 | 5 | 11.0204 | 18.4097 | 3.0256 | 4.3636 | 1 | 5 | 0.8 | 2.5 | 12.5
| 5966 | 0.1 | 40 | 16.875 | 23.7602 | 3.0452 | 3.84 | 0.8 | 6.25 | 0.6 | 3.3333 | 49.5833
| 5967 | 1 | 4 | 9.6429 | 19.1499 | 2.3959 | 7.1111 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 5968 | 1 | 4 | 8.5714 | 15.8482 | 3.9664 | 3.3103 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 5969 | 1 | 4 | 12 | 18.4737 | 3.1053 | 3.3684 | 1 | 5 | 0.8 | 2.5 | 11.5
| 5970 | 1 | 4 | 17.4194 | 25.8596 | 3.8689 | 4.5714 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 5971 | 0.8 | 5 | 14.5946 | 22.6729 | 3.0256 | 5.0526 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 5972 | 1 | 4 | 9 | 18.5901 | 4.1043 | 5.4857 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 5973 | 0.6 | 6.6667 | 15.8824 | 22.743 | 2.8606 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 5974 | 0.8 | 5 | 9.3103 | 16.987 | 3.1053 | 4.5714 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 5975 | 1 | 4 | 18.6207 | 28.3366 | 3.5224 | 6.1935 | 0.4 | 12.5 | 0.2 | 10 | 26.5
| 5976 | 1.4 | 2.8571 | 15.8824 | 26.4476 | 2.5652 | 8 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 5977 | 1.2 | 3.3333 | 12.2727 | 19.9236 | 2.1651 | 5.4857 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 5978 | 1.4 | 2.8571 | 10 | 16.9625 | 2.4974 | 4.4651 | 0.6 | 8.3333 | 0.6 | 3.3333 | 14.5238
| 5979 | 0.8 | 5 | 14.5946 | 20.6204 | 3.3957 | 2.6301 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 5980 | 1.2 | 3.3333 | 13.5 | 21.786 | 3.6031 | 4.6829 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 5981 | 0.4 | 10 | 13.5 | 21.1434 | 2.8434 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 5982 | 1.6 | 2.5 | 14.5946 | 23.2223 | 2.8095 | 5.8182 | 1 | 5 | 0.1 | 20 | 27.5
| 5983 | 0.6 | 6.6667 | 8.3077 | 19.2207 | 2.5652 | 8.3478 | 1 | 5 | 0.6 | 3.3333 | 15
| 5984 | 0.8 | 5 | 15.8824 | 22.9581 | 4.2523 | 2.8235 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 5985 | 1.4 | 2.8571 | 7.6056 | 13.6694 | 2.8095 | 3.2542 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 5986 | 1 | 4 | 8.7097 | 18.3953 | 3.0649 | 6.6207 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 5987 | 1.2 | 3.3333 | 11.7391 | 19.3836 | 3.4706 | 4.1739 | 1 | 5 | 0.4 | 5 | 13.3333
| 5988 | 0.4 | 10 | 10.1887 | 19.1327 | 3.1258 | 5.8182 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 5989 | 0.1 | 40 | 14.5946 | 27.5135 | 3.776 | 9.1429 | 1 | 5 | 0.4 | 5 | 50
| 5990 | 0.4 | 10 | 5.8065 | 12.8228 | 3.8689 | 3.1475 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 5991 | 0.8 | 5 | 9.1525 | 15.3189 | 3.3007 | 2.8657 | 1 | 5 | 0.4 | 5 | 15
| 5992 | 0.6 | 6.6667 | 12.8571 | 22.6623 | 2.4205 | 7.3846 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 5993 | 0.6 | 6.6667 | 9.3103 | 15.7259 | 2.7929 | 3.6226 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 5994 | 0.4 | 10 | 9.8182 | 16.1204 | 2.3838 | 3.9184 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 5995 | 0.6 | 6.6667 | 13.5 | 22.4792 | 2.5792 | 6.4 | 0.6 | 8.3333 | 0.1 | 20 | 35
| 5996 | 0.6 | 6.6667 | 10.1887 | 17.5534 | 2.6818 | 4.6829 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 5997 | 0.8 | 5 | 12.5581 | 21.668 | 4.5385 | 4.5714 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 5998 | 1.2 | 3.3333 | 8.7097 | 15.4025 | 2.6077 | 4.0851 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 5999 | 0.6 | 6.6667 | 16.3636 | 25.0155 | 2.4583 | 6.1935 | 1 | 5 | 0.1 | 20 | 31.6667
| 6000 | 0.1 | 40 | 18.6207 | 25.9464 | 2.8606 | 4.4651 | 1.2 | 4.1667 | 0.6 | 3.3333 | 47.5
| 6001 | 1 | 4 | 11.7391 | 17.7535 | 3.1053 | 2.9091 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 6002 | 1.2 | 3.3333 | 14.2105 | 23.0028 | 3.6031 | 5.1892 | 1 | 5 | 0.4 | 5 | 13.3333
| 6003 | 0.4 | 10 | 13.1707 | 19.213 | 2.5514 | 3.4909 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 6004 | 0.8 | 5 | 11.25 | 18.6136 | 3.4453 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 6005 | 0.6 | 6.6667 | 8.4375 | 16.4401 | 2.95 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 6006 | 1 | 4 | 13.8462 | 20.5244 | 2.9136 | 3.7647 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 6007 | 0.6 | 6.6667 | 18.6207 | 28.217 | 4.6733 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 15
| 6008 | 0.4 | 10 | 18.6207 | 24.808 | 2.9873 | 3.2 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 6009 | 0.2 | 20 | 17.4194 | 23.7202 | 3.9008 | 2.4 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 6010 | 0.8 | 5 | 12.2727 | 21.1847 | 2.2913 | 6.6207 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 6011 | 0.8 | 5 | 10.8 | 19.885 | 3.085 | 6 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 6012 | 1 | 4 | 10.1887 | 18.1874 | 2.8095 | 5.1892 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 6013 | 0.4 | 10 | 11.0204 | 19.1905 | 3.8065 | 4.3636 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 6014 | 0.6 | 6.6667 | 11.4894 | 17.4393 | 2.1852 | 3.7647 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 6015 | 0.4 | 10 | 11.25 | 20.2699 | 2.8263 | 6.1935 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 6016 | 0.6 | 6.6667 | 10 | 17.2456 | 2.4456 | 4.8 | 1 | 5 | 0.2 | 10 | 21.6667
| 6017 | 0.2 | 20 | 16.875 | 23.6306 | 3.4453 | 3.3103 | 1.4 | 3.5714 | 0.2 | 10 | 33.5714
| 6018 | 0.6 | 6.6667 | 12.8571 | 19.8969 | 3.5489 | 3.4909 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 6019 | 0.8 | 5 | 12.8571 | 19.2861 | 2.5106 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 6020 | 0.6 | 6.6667 | 19.2857 | 28.3573 | 2.878 | 6.1935 | 1 | 5 | 0.2 | 10 | 21.6667
| 6021 | 0.6 | 6.6667 | 11.0204 | 17.4222 | 3.6589 | 2.7429 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 6022 | 0.6 | 6.6667 | 13.1707 | 21.7369 | 3.2329 | 5.3333 | 1 | 5 | 0.6 | 3.3333 | 15
| 6023 | 0.6 | 6.6667 | 12.2727 | 18.1788 | 2.5376 | 3.3684 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 6024 | 1 | 4 | 14.5946 | 20.3732 | 2.6818 | 3.0968 | 1 | 5 | 0.4 | 5 | 14
| 6025 | 1 | 4 | 10.5882 | 18.2862 | 3.2329 | 4.4651 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 6026 | 0.4 | 10 | 9.1525 | 15.6307 | 3.1678 | 3.3103 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 6027 | 0.8 | 5 | 10 | 18.2584 | 2.2584 | 6 | 1 | 5 | 0.2 | 10 | 20
| 6028 | 0.2 | 20 | 10 | 17.0537 | 2.9686 | 4.0851 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 6029 | 0.2 | 20 | 11.25 | 19.6493 | 2.9136 | 5.4857 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 6030 | 1.4 | 2.8571 | 10.1887 | 17.5023 | 3.5489 | 3.7647 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 6031 | 1.2 | 3.3333 | 12.5581 | 18.8837 | 3.6589 | 2.6667 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 6032 | 0.4 | 10 | 19.2857 | 24.5876 | 1.9916 | 3.3103 | 1 | 5 | 0.4 | 5 | 20
| 6033 | 0.6 | 6.6667 | 11.25 | 16.7234 | 2.6077 | 2.8657 | 1.6 | 3.125 | 0.4 | 5 | 14.7917
| 6034 | 1 | 4 | 13.5 | 19.4938 | 2.5652 | 3.4286 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 6035 | 1 | 4 | 12.8571 | 20.4646 | 3.5224 | 4.0851 | 1 | 5 | 0.4 | 5 | 14
| 6036 | 0.6 | 6.6667 | 16.875 | 25.3316 | 2.8095 | 5.6471 | 1 | 5 | 0.2 | 10 | 21.6667
| 6037 | 0.4 | 10 | 11.7391 | 18.3149 | 3.5758 | 3 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 6038 | 0.8 | 5 | 14.5946 | 20.3425 | 1.9832 | 3.7647 | 1 | 5 | 0.8 | 2.5 | 12.5
| 6039 | 0.6 | 6.6667 | 10.3846 | 16.6298 | 3.0452 | 3.2 | 1 | 5 | 0.6 | 3.3333 | 15
| 6040 | 0.4 | 10 | 11.4894 | 18.375 | 2.4205 | 4.4651 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 6041 | 1.4 | 2.8571 | 16.875 | 26.2386 | 3.7165 | 5.6471 | 1.6 | 3.125 | 0.4 | 5 | 10.9821
| 6042 | 0.6 | 6.6667 | 16.875 | 25.4861 | 3.2778 | 5.3333 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 6043 | 1.4 | 2.8571 | 10.8 | 18.4589 | 3.6589 | 4 | 1 | 5 | 0.2 | 10 | 17.8571
| 6044 | 0.6 | 6.6667 | 12 | 18.282 | 2.9136 | 3.3684 | 1 | 5 | 0.1 | 20 | 31.6667
| 6045 | 1.2 | 3.3333 | 12 | 17.27 | 2.7765 | 2.4935 | 1.8 | 2.7778 | 0.6 | 3.3333 | 9.4444
| 6046 | 0.6 | 6.6667 | 10.5882 | 19.1372 | 3.4963 | 5.0526 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 6047 | 1.2 | 3.3333 | 12.8571 | 20.4835 | 2.8263 | 4.8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 6048 | 1.2 | 3.3333 | 10.5882 | 16.7428 | 3.8689 | 2.2857 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 6049 | 0.4 | 10 | 13.5 | 22.5919 | 2.4712 | 6.6207 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 6050 | 0.6 | 6.6667 | 11.25 | 19.3459 | 3.6308 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 6051 | 1.2 | 3.3333 | 18.6207 | 24.7854 | 3.2109 | 2.9538 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 6052 | 0.6 | 6.6667 | 12.5581 | 20.7603 | 3.6308 | 4.5714 | 1 | 5 | 0.6 | 3.3333 | 15
| 6053 | 0.4 | 10 | 8.7097 | 16.9645 | 2.6077 | 5.6471 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 6054 | 0.4 | 10 | 16.3636 | 23.9893 | 3.9333 | 3.6923 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 6055 | 0.2 | 20 | 12.5581 | 20.2693 | 3.3475 | 4.3636 | 1 | 5 | 0.4 | 5 | 30
| 6056 | 1.4 | 2.8571 | 11.25 | 20.1864 | 3.6031 | 5.3333 | 1 | 5 | 0.1 | 20 | 27.8571
| 6057 | 0.8 | 5 | 11.25 | 17.8411 | 2.8263 | 3.7647 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 6058 | 0.8 | 5 | 12.2727 | 19.3736 | 3.9008 | 3.2 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 6059 | 1 | 4 | 11.7391 | 20.209 | 2.6517 | 5.8182 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 6060 | 0.2 | 20 | 9.3103 | 16.0447 | 2.2692 | 4.4651 | 0.8 | 6.25 | 0.2 | 10 | 36.25
| 6061 | 0.8 | 5 | 9 | 15.0766 | 3.2109 | 2.8657 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 6062 | 0.8 | 5 | 15.4286 | 22.6349 | 2.0171 | 5.1892 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 6063 | 0.8 | 5 | 16.3636 | 23.1703 | 3.4963 | 3.3103 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 6064 | 1.2 | 3.3333 | 18.6207 | 26.2349 | 3.3475 | 4.2667 | 0.4 | 12.5 | 0.2 | 10 | 25.8333
| 6065 | 0.2 | 20 | 12 | 19.5126 | 2.7126 | 4.8 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 6066 | 0.6 | 6.6667 | 11.4894 | 19.3962 | 4.5385 | 3.3684 | 1 | 5 | 0.2 | 10 | 21.6667
| 6067 | 0.6 | 6.6667 | 20 | 26.7279 | 2.8095 | 3.9184 | 1 | 5 | 0.4 | 5 | 16.6667
| 6068 | 0.4 | 10 | 13.8462 | 20.0201 | 2.5514 | 3.6226 | 1 | 5 | 0.2 | 10 | 25
| 6069 | 1 | 4 | 9.4737 | 16.5387 | 3.1467 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 6070 | 0.6 | 6.6667 | 13.5 | 22.287 | 2.5934 | 6.1935 | 1.4 | 3.5714 | 0.1 | 20 | 30.2381
| 6071 | 0.8 | 5 | 10.5882 | 17.5199 | 2.9317 | 4 | 1 | 5 | 0.2 | 10 | 20
| 6072 | 1.2 | 3.3333 | 11.25 | 17.8967 | 2.7283 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 6073 | 0.2 | 20 | 12 | 18.585 | 2.6667 | 3.9184 | 1 | 5 | 0.4 | 5 | 30
| 6074 | 0.8 | 5 | 9.4737 | 16.8626 | 3.5489 | 3.84 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 6075 | 0.8 | 5 | 13.1707 | 19.6367 | 2.8434 | 3.6226 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 6076 | 1.2 | 3.3333 | 12.5581 | 19.0571 | 3.8689 | 2.6301 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 6077 | 0.4 | 10 | 11.25 | 17.4147 | 3.2109 | 2.9538 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 6078 | 0.6 | 6.6667 | 13.5 | 19.6506 | 2.4583 | 3.6923 | 1 | 5 | 0.4 | 5 | 16.6667
| 6079 | 0.2 | 20 | 10.1887 | 18.2054 | 3.4453 | 4.5714 | 0.6 | 8.3333 | 0.6 | 3.3333 | 31.6667
| 6080 | 1.2 | 3.3333 | 12 | 18.5825 | 2.4974 | 4.0851 | 1 | 5 | 1 | 2 | 10.3333
| 6081 | 1.4 | 2.8571 | 8.1818 | 18.427 | 2.8606 | 7.3846 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 6082 | 0.2 | 20 | 9.3103 | 16.624 | 2.95 | 4.3636 | 1.4 | 3.5714 | 0.2 | 10 | 33.5714
| 6083 | 1.2 | 3.3333 | 12.8571 | 19.672 | 3.3239 | 3.4909 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 6084 | 0.2 | 20 | 12.2727 | 17.6061 | 2.6667 | 2.6667 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 6085 | 0.8 | 5 | 11.0204 | 18.352 | 3.0649 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 6086 | 1.2 | 3.3333 | 11.4894 | 17.8694 | 3.1258 | 3.2542 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 6087 | 0.8 | 5 | 10.8 | 19.1489 | 3.5489 | 4.8 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 6088 | 1.4 | 2.8571 | 11.4894 | 18.5824 | 2.8263 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 6089 | 0.4 | 10 | 12.5581 | 19.1976 | 3.2109 | 3.4286 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 6090 | 0.4 | 10 | 15 | 22.8854 | 3.4203 | 4.4651 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 6091 | 0.6 | 6.6667 | 18 | 25.6673 | 2.7442 | 4.9231 | 1.8 | 2.7778 | 0.4 | 5 | 14.4444
| 6092 | 1.2 | 3.3333 | 12 | 19.2033 | 2.2802 | 4.9231 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 6093 | 0.4 | 10 | 13.5 | 21.5026 | 2.95 | 5.0526 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 6094 | 1 | 4 | 8.5714 | 17.6084 | 2.8434 | 6.1935 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 6095 | 1.2 | 3.3333 | 19.2857 | 31.2682 | 3.2552 | 8.7273 | 0.6 | 8.3333 | 0.1 | 20 | 31.6667
| 6096 | 0.4 | 10 | 10.1887 | 16.9137 | 2.4583 | 4.2667 | 1.2 | 4.1667 | 0.1 | 20 | 34.1667
| 6097 | 0.2 | 20 | 12 | 19.678 | 2.878 | 4.8 | 0.6 | 8.3333 | 0.2 | 10 | 38.3333
| 6098 | 1.2 | 3.3333 | 14.2105 | 21.5427 | 2.9686 | 4.3636 | 1 | 5 | 0.4 | 5 | 13.3333
| 6099 | 1.2 | 3.3333 | 8.3077 | 16.074 | 2.433 | 5.3333 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 6100 | 0.8 | 5 | 10.3846 | 19.2803 | 2.8957 | 6 | 0.6 | 8.3333 | 0.1 | 20 | 33.3333
| 6101 | 0.6 | 6.6667 | 11.4894 | 18.5808 | 3.0064 | 4.0851 | 0.6 | 8.3333 | 0.8 | 2.5 | 17.5
| 6102 | 0.4 | 10 | 8.8525 | 19.5161 | 3.8065 | 6.8571 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 6103 | 0.8 | 5 | 14.2105 | 24.2029 | 2.6077 | 7.3846 | 1.4 | 3.5714 | 0.8 | 2.5 | 11.0714
| 6104 | 0.4 | 10 | 10.8 | 18.0378 | 2.1852 | 5.0526 | 0.6 | 8.3333 | 0.1 | 20 | 38.3333
| 6105 | 0.6 | 6.6667 | 12.8571 | 21.1207 | 3.2109 | 5.0526 | 1 | 5 | 0.1 | 20 | 31.6667
| 6106 | 0.8 | 5 | 9.4737 | 15.4752 | 2.5106 | 3.4909 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 6107 | 1.2 | 3.3333 | 11.7391 | 19.6875 | 2.8957 | 5.0526 | 1 | 5 | 0.4 | 5 | 13.3333
| 6108 | 0.8 | 5 | 13.8462 | 24.9573 | 4 | 7.1111 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 6109 | 0.8 | 5 | 12.8571 | 18.9043 | 2.7929 | 3.2542 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 6110 | 1.2 | 3.3333 | 15.8824 | 22.7287 | 3.0064 | 3.84 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 6111 | 1.4 | 2.8571 | 12.5581 | 21.2369 | 2.8606 | 5.8182 | 0.8 | 6.25 | 0.1 | 20 | 29.1071
| 6112 | 1 | 4 | 15.4286 | 20.8456 | 2.5514 | 2.8657 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 6113 | 0.8 | 5 | 20.7692 | 27.4538 | 2.5106 | 4.1739 | 1.2 | 4.1667 | 1 | 2 | 11.1667
| 6114 | 1 | 4 | 10.1887 | 18.0198 | 3.746 | 4.0851 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 6115 | 1 | 4 | 14.2105 | 20.5975 | 2.6222 | 3.7647 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 6116 | 1 | 4 | 12.5581 | 19.9843 | 2.237 | 5.1892 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 6117 | 0.4 | 10 | 13.1707 | 19.6763 | 2.95 | 3.5556 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 6118 | 0.6 | 6.6667 | 11.25 | 17.5103 | 2.95 | 3.3103 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 6119 | 0.2 | 20 | 10.1887 | 16.1127 | 2.7765 | 3.1475 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 6120 | 0.8 | 5 | 11.25 | 18.4857 | 3.3957 | 3.84 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 6121 | 0.6 | 6.6667 | 9.4737 | 16.4054 | 2.9317 | 4 | 1.6 | 3.125 | 0.6 | 3.3333 | 13.125
| 6122 | 1 | 4 | 14.2105 | 20.0792 | 3.1258 | 2.7429 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 6123 | 0.6 | 6.6667 | 17.4194 | 25.7977 | 3.1892 | 5.1892 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 6124 | 0.6 | 6.6667 | 12 | 19.9443 | 2.1261 | 5.8182 | 1 | 5 | 0.4 | 5 | 16.6667
| 6125 | 1 | 4 | 13.5 | 20.6078 | 2.7442 | 4.3636 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 6126 | 0.6 | 6.6667 | 11.7391 | 16.936 | 2.6369 | 2.56 | 1.6 | 3.125 | 0.6 | 3.3333 | 13.125
| 6127 | 0.8 | 5 | 9.6429 | 16.8424 | 3.0256 | 4.1739 | 1 | 5 | 0.2 | 10 | 20
| 6128 | 0.8 | 5 | 12.8571 | 20.0184 | 2.9873 | 4.1739 | 1 | 5 | 0.1 | 20 | 30
| 6129 | 0.4 | 10 | 11.25 | 20.2148 | 3.1467 | 5.8182 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 6130 | 0.6 | 6.6667 | 13.8462 | 23.9845 | 2.4583 | 7.68 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 6131 | 0.8 | 5 | 16.3636 | 22.9814 | 3.1892 | 3.4286 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 6132 | 0.4 | 10 | 15 | 22.4495 | 2.878 | 4.5714 | 1 | 5 | 0.8 | 2.5 | 17.5
| 6133 | 1 | 4 | 12.2727 | 21.855 | 2.4712 | 7.1111 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 6134 | 0.6 | 6.6667 | 10.5882 | 16.3049 | 2.3483 | 3.3684 | 1 | 5 | 0.4 | 5 | 16.6667
| 6135 | 0.8 | 5 | 10.1887 | 15.8705 | 2.6818 | 3 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 6136 | 0.4 | 10 | 12.2727 | 18.9545 | 3.3714 | 3.3103 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 6137 | 0.6 | 6.6667 | 8.0597 | 18.47 | 3.0256 | 7.3846 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 6138 | 1.4 | 2.8571 | 11.25 | 18.8597 | 2.4205 | 5.1892 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 6139 | 1 | 4 | 15 | 21.3299 | 2.5652 | 3.7647 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 6140 | 0.8 | 5 | 14.5946 | 24.0149 | 3.4203 | 6 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 6141 | 0.2 | 20 | 14.2105 | 21.555 | 2.1553 | 5.1892 | 1.2 | 4.1667 | 0.1 | 20 | 44.1667
| 6142 | 1.2 | 3.3333 | 8.1818 | 14.1421 | 2.7602 | 3.2 | 0.8 | 6.25 | 0.8 | 2.5 | 12.0833
| 6143 | 1 | 4 | 9.4737 | 24.4054 | 2.9317 | 12 | 1.4 | 3.5714 | 0.8 | 2.5 | 10.0714
| 6144 | 1.2 | 3.3333 | 9.6429 | 21.3146 | 3.3239 | 8.3478 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 6145 | 0.8 | 5 | 13.5 | 19.7857 | 2.5934 | 3.6923 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 6146 | 0.8 | 5 | 19.2857 | 27.9392 | 3.1678 | 5.4857 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 6147 | 0.4 | 10 | 11.7391 | 19.7062 | 3.3957 | 4.5714 | 1.6 | 3.125 | 0.8 | 2.5 | 15.625
| 6148 | 0.8 | 5 | 16.875 | 30.148 | 3.1678 | 10.1053 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 6149 | 0.4 | 10 | 15 | 22.7684 | 2.5792 | 5.1892 | 1.8 | 2.7778 | 0.4 | 5 | 17.7778
| 6150 | 0.8 | 5 | 11.7391 | 17.5159 | 3.1467 | 2.6301 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 6151 | 1.4 | 2.8571 | 28.4211 | 38.1635 | 3.5489 | 6.1935 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 6152 | 0.6 | 6.6667 | 12.2727 | 18.1257 | 2.9873 | 2.8657 | 1 | 5 | 0.4 | 5 | 16.6667
| 6153 | 1 | 4 | 11.4894 | 18.8782 | 3.5489 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 6154 | 1 | 4 | 13.8462 | 24.099 | 3.3957 | 6.8571 | 1 | 5 | 0.4 | 5 | 14
| 6155 | 0.4 | 10 | 13.8462 | 21.5164 | 3.4963 | 4.1739 | 1 | 5 | 0.8 | 2.5 | 17.5
| 6156 | 0.4 | 10 | 12 | 19.3118 | 3.0452 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 6157 | 0.4 | 10 | 8.8525 | 15.9783 | 3.1258 | 4 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 6158 | 1 | 4 | 11.0204 | 17.4694 | 2.8263 | 3.6226 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 6159 | 1 | 4 | 14.5946 | 23.4308 | 3.1892 | 5.6471 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 6160 | 0.8 | 5 | 9.4737 | 16.3918 | 2.7442 | 4.1739 | 1 | 5 | 0.4 | 5 | 15
| 6161 | 0.4 | 10 | 14.2105 | 24.3875 | 4.177 | 6 | 1 | 5 | 0.8 | 2.5 | 17.5
| 6162 | 1 | 4 | 16.875 | 22.0352 | 2.3366 | 2.8235 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 6163 | 0.4 | 10 | 10.8 | 18.1206 | 3.1467 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 6164 | 0.8 | 5 | 16.3636 | 23.9939 | 1.9832 | 5.6471 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 6165 | 1.2 | 3.3333 | 13.5 | 20.35 | 2.9317 | 3.9184 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 6166 | 0.6 | 6.6667 | 12.8571 | 19.8863 | 3.1892 | 3.84 | 1 | 5 | 0.2 | 10 | 21.6667
| 6167 | 0.6 | 6.6667 | 12.5581 | 19.7384 | 2.4974 | 4.6829 | 1 | 5 | 0.4 | 5 | 16.6667
| 6168 | 1 | 4 | 16.875 | 25.4052 | 2.3366 | 6.1935 | 1 | 5 | 0.4 | 5 | 14
| 6169 | 0.8 | 5 | 11.0204 | 16.9428 | 2.9686 | 2.9538 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 6170 | 1.2 | 3.3333 | 9.6429 | 17.3163 | 2.4842 | 5.1892 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 6171 | 0.8 | 5 | 15.8824 | 23.3318 | 2.878 | 4.5714 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 6172 | 0.4 | 10 | 13.1707 | 21.3554 | 2.5376 | 5.6471 | 1 | 5 | 0.2 | 10 | 25
| 6173 | 1 | 4 | 13.5 | 20.3141 | 2.8957 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 6174 | 0.6 | 6.6667 | 12.2727 | 21.769 | 3.4963 | 6 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 6175 | 1.2 | 3.3333 | 12.2727 | 20.6364 | 4 | 4.3636 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 6176 | 0.4 | 10 | 13.5 | 20.6273 | 2.8606 | 4.2667 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 6177 | 0.2 | 20 | 10.3846 | 17.8842 | 3.2329 | 4.2667 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 6178 | 0.4 | 10 | 11.0204 | 17.5211 | 2.878 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 6179 | 0.6 | 6.6667 | 11.4894 | 20.3925 | 3.085 | 5.8182 | 1 | 5 | 0.4 | 5 | 16.6667
| 6180 | 0.4 | 10 | 12.5581 | 21.5282 | 2.7765 | 6.1935 | 1 | 5 | 0.4 | 5 | 20
| 6181 | 0.8 | 5 | 10.1887 | 21.1372 | 3.8374 | 7.1111 | 1 | 5 | 0.4 | 5 | 15
| 6182 | 0.4 | 10 | 15.4286 | 21.9157 | 3.2329 | 3.2542 | 1 | 5 | 0.4 | 5 | 20
| 6183 | 1 | 4 | 12.5581 | 22.8801 | 3.2109 | 7.1111 | 1 | 5 | 0.4 | 5 | 14
| 6184 | 1.2 | 3.3333 | 12 | 17.1835 | 2.36 | 2.8235 | 1 | 5 | 0.4 | 5 | 13.3333
| 6185 | 1 | 4 | 8.8525 | 21.306 | 2.3483 | 10.1053 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 6186 | 0.8 | 5 | 20.7692 | 33.684 | 2.8095 | 10.1053 | 1 | 5 | 0.2 | 10 | 20
| 6187 | 0.4 | 10 | 11.4894 | 17.1363 | 2.3366 | 3.3103 | 1 | 5 | 0.4 | 5 | 20
| 6188 | 0.6 | 6.6667 | 16.3636 | 23.9965 | 3.1678 | 4.4651 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 6189 | 1 | 4 | 10.5882 | 17.205 | 3.1258 | 3.4909 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 6190 | 0.4 | 10 | 10.1887 | 18.3588 | 3.8065 | 4.3636 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 6191 | 0.6 | 6.6667 | 15.8824 | 26.3365 | 4.9684 | 5.4857 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 6192 | 1.4 | 2.8571 | 11.25 | 19.3892 | 2.95 | 5.1892 | 0.2 | 25 | 0.6 | 3.3333 | 31.1905
| 6193 | 1.4 | 2.8571 | 10.5882 | 21.5011 | 3.2329 | 7.68 | 1 | 5 | 0.2 | 10 | 17.8571
| 6194 | 1.2 | 3.3333 | 9.3103 | 23.382 | 3.9664 | 10.1053 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 6195 | 0.6 | 6.6667 | 20 | 27.3687 | 2.4456 | 4.9231 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 6196 | 0.1 | 40 | 14.5946 | 21.7238 | 3.2109 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 51.25
| 6197 | 0.4 | 10 | 9.6429 | 15.6031 | 3.0064 | 2.9538 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 6198 | 0.8 | 5 | 19.2857 | 29.5095 | 3.6031 | 6.6207 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 6199 | 1.2 | 3.3333 | 10.3846 | 16.2905 | 2.6517 | 3.2542 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 6200 | 1.2 | 3.3333 | 14.2105 | 23.5595 | 2.7283 | 6.6207 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 6201 | 1.2 | 3.3333 | 10.8 | 18.4876 | 3.3239 | 4.3636 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 6202 | 0.6 | 6.6667 | 12 | 18.5018 | 2.8095 | 3.6923 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 6203 | 1 | 4 | 16.875 | 24.6248 | 2.6971 | 5.0526 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 6204 | 0.4 | 10 | 13.1707 | 22.3921 | 4.5385 | 4.6829 | 0.4 | 12.5 | 0.4 | 5 | 27.5
| 6205 | 1.4 | 2.8571 | 10.5882 | 19.3564 | 2.95 | 5.8182 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 6206 | 0.8 | 5 | 11.7391 | 17.4675 | 2.7283 | 3 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 6207 | 0.4 | 10 | 13.1707 | 20.5944 | 3.6589 | 3.7647 | 1 | 5 | 0.4 | 5 | 20
| 6208 | 0.4 | 10 | 9.1525 | 14.9748 | 2.6222 | 3.2 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 6209 | 0.6 | 6.6667 | 12.2727 | 21.3854 | 2.7126 | 6.4 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 6210 | 0.6 | 6.6667 | 7.3973 | 16.0377 | 4.069 | 4.5714 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 6211 | 1 | 4 | 13.8462 | 22.9124 | 2.4456 | 6.6207 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 6212 | 1.4 | 2.8571 | 9.8182 | 21.2581 | 2.7126 | 8.7273 | 1 | 5 | 0.4 | 5 | 12.8571
| 6213 | 1 | 4 | 14.2105 | 22.0561 | 2.7929 | 5.0526 | 1.2 | 4.1667 | 1 | 2 | 10.1667
| 6214 | 1.2 | 3.3333 | 10.3846 | 16.2701 | 2.9317 | 2.9538 | 1 | 5 | 0.4 | 5 | 13.3333
| 6215 | 0.6 | 6.6667 | 7.9412 | 14.2651 | 3.3239 | 3 | 1 | 5 | 0.2 | 10 | 21.6667
| 6216 | 1 | 4 | 15.8824 | 26.8085 | 4.069 | 6.8571 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 6217 | 0.6 | 6.6667 | 15.4286 | 21.2952 | 2.6667 | 3.2 | 1.8 | 2.7778 | 0.6 | 3.3333 | 12.7778
| 6218 | 0.8 | 5 | 11.4894 | 18.2735 | 2.4205 | 4.3636 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 6219 | 1 | 4 | 11.4894 | 21.7057 | 3.1053 | 7.1111 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 6220 | 0.6 | 6.6667 | 15.4286 | 21.7228 | 3.1467 | 3.1475 | 1 | 5 | 0.2 | 10 | 21.6667
| 6221 | 0.4 | 10 | 12.5581 | 18.9163 | 2.5934 | 3.7647 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 6222 | 1.4 | 2.8571 | 12 | 18.8728 | 3.776 | 3.0968 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 6223 | 0.8 | 5 | 9.1525 | 16.842 | 2.6369 | 5.0526 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 6224 | 0.8 | 5 | 17.4194 | 24.5383 | 3.4963 | 3.6226 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 6225 | 0.8 | 5 | 18 | 24.5218 | 2.6818 | 3.84 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 6226 | 0.4 | 10 | 11.0204 | 17.2585 | 2.8095 | 3.4286 | 1 | 5 | 0.1 | 20 | 35
| 6227 | 0.2 | 20 | 10.5882 | 19.2716 | 3.6308 | 5.0526 | 1.4 | 3.5714 | 0.2 | 10 | 33.5714
| 6228 | 0.2 | 20 | 12.2727 | 20.0412 | 2.5792 | 5.1892 | 1.6 | 3.125 | 0.2 | 10 | 33.125
| 6229 | 1.6 | 2.5 | 14.2105 | 25.7261 | 3.1678 | 8.3478 | 0.8 | 6.25 | 0.4 | 5 | 13.75
| 6230 | 0.2 | 20 | 15.4286 | 21.9049 | 2.3024 | 4.1739 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 6231 | 0.8 | 5 | 11.7391 | 19.6524 | 2.8606 | 5.0526 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 6232 | 0.6 | 6.6667 | 12.2727 | 18.2204 | 2.5792 | 3.3684 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 6233 | 0.8 | 5 | 9.8182 | 17.568 | 2.6971 | 5.0526 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 6234 | 0.8 | 5 | 8.0597 | 13.8231 | 2.8095 | 2.9538 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 6235 | 0.4 | 10 | 10.3846 | 16.8302 | 2.4456 | 4 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 6236 | 0.1 | 40 | 13.8462 | 22.8684 | 2.6222 | 6.4 | 1.2 | 4.1667 | 0.4 | 5 | 49.1667
| 6237 | 0.8 | 5 | 12 | 19.0862 | 3.1678 | 3.9184 | 0.4 | 12.5 | 0.6 | 3.3333 | 20.8333
| 6238 | 1.2 | 3.3333 | 8.7097 | 15.2509 | 2.7765 | 3.7647 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 6239 | 1.2 | 3.3333 | 7.2973 | 16.0089 | 3.5224 | 5.1892 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 6240 | 1 | 4 | 11.0204 | 17.6655 | 2.4712 | 4.1739 | 1 | 5 | 0.4 | 5 | 14
| 6241 | 0.4 | 10 | 8.4375 | 16.1355 | 3.2329 | 4.4651 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 6242 | 1 | 4 | 9.6429 | 17.8898 | 2.9136 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 6243 | 0.2 | 20 | 15.8824 | 21.7932 | 3.0452 | 2.8657 | 1.4 | 3.5714 | 0.2 | 10 | 33.5714
| 6244 | 1.2 | 3.3333 | 15 | 27.8552 | 3.2552 | 9.6 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 6245 | 1 | 4 | 11.4894 | 17.75 | 3.0064 | 3.2542 | 1 | 5 | 0.2 | 10 | 19
| 6246 | 1.2 | 3.3333 | 16.3636 | 23.7321 | 4 | 3.3684 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 6247 | 0.8 | 5 | 10.5882 | 17.2948 | 3.6589 | 3.0476 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 6248 | 0.4 | 10 | 13.1707 | 19.0394 | 3.1258 | 2.7429 | 1.4 | 3.5714 | 0.1 | 20 | 33.5714
| 6249 | 0.6 | 6.6667 | 16.3636 | 22.2112 | 3.0649 | 2.7826 | 1 | 5 | 0.4 | 5 | 16.6667
| 6250 | 0.6 | 6.6667 | 15.4286 | 22.2967 | 2.1852 | 4.6829 | 1 | 5 | 0.2 | 10 | 21.6667
| 6251 | 0.2 | 20 | 12.8571 | 19.2905 | 3.0649 | 3.3684 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 6252 | 0.4 | 10 | 10.1887 | 17.3664 | 2.7126 | 4.4651 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 6253 | 1 | 4 | 9.4737 | 17.5041 | 3.3475 | 4.6829 | 1 | 5 | 0.1 | 20 | 29
| 6254 | 0.6 | 6.6667 | 12.5581 | 19.5217 | 3.0452 | 3.9184 | 1.6 | 3.125 | 0.8 | 2.5 | 12.2917
| 6255 | 1.2 | 3.3333 | 15 | 22.5814 | 3.4963 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 6256 | 0.8 | 5 | 13.5 | 21.3814 | 4.4528 | 3.4286 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 6257 | 0.4 | 10 | 17.4194 | 26.3434 | 2.5241 | 6.4 | 1 | 5 | 0.2 | 10 | 25
| 6258 | 1 | 4 | 11.0204 | 21.5518 | 3.4203 | 7.1111 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 6259 | 0.4 | 10 | 11.7391 | 18.3569 | 3.1892 | 3.4286 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 6260 | 1.2 | 3.3333 | 13.1707 | 19.2057 | 3.1258 | 2.9091 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 6261 | 1.2 | 3.3333 | 15 | 23.4308 | 3.6308 | 4.8 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 6262 | 0.4 | 10 | 10 | 16.5094 | 3.2552 | 3.2542 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 6263 | 0.8 | 5 | 12.2727 | 18.3035 | 3.6308 | 2.4 | 0.4 | 12.5 | 0.2 | 10 | 27.5
| 6264 | 0.8 | 5 | 13.1707 | 23.487 | 2.9317 | 7.3846 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 6265 | 0.8 | 5 | 14.5946 | 21.3762 | 2.6077 | 4.1739 | 1 | 5 | 0.1 | 20 | 30
| 6266 | 0.2 | 20 | 13.8462 | 20.8525 | 3.0064 | 4 | 0.6 | 8.3333 | 0.1 | 20 | 48.3333
| 6267 | 1.2 | 3.3333 | 13.8462 | 20.2477 | 2.6369 | 3.7647 | 1 | 5 | 0.4 | 5 | 13.3333
| 6268 | 0.6 | 6.6667 | 16.3636 | 29.0818 | 4.3704 | 8.3478 | 1.4 | 3.5714 | 0.1 | 20 | 30.2381
| 6269 | 0.6 | 6.6667 | 12.5581 | 22.6747 | 3.7165 | 6.4 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 6270 | 0.6 | 6.6667 | 9 | 18.3873 | 2.9873 | 6.4 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 6271 | 1 | 4 | 14.5946 | 23.8552 | 2.8606 | 6.4 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 6272 | 1.2 | 3.3333 | 13.8462 | 24.5325 | 3.0064 | 7.68 | 1 | 5 | 0.2 | 10 | 18.3333
| 6273 | 0.6 | 6.6667 | 11.7391 | 19.5479 | 3.1258 | 4.6829 | 1 | 5 | 0.2 | 10 | 21.6667
| 6274 | 0.8 | 5 | 10.8 | 17.4329 | 2.7929 | 3.84 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 6275 | 1.2 | 3.3333 | 11.7391 | 21.5707 | 3.2109 | 6.6207 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 6276 | 0.8 | 5 | 10.3846 | 16.9803 | 3.3957 | 3.2 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 6277 | 1.4 | 2.8571 | 10.5882 | 17.3001 | 2.3483 | 4.3636 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 6278 | 0.8 | 5 | 11.4894 | 17.7253 | 2.3959 | 3.84 | 0.4 | 12.5 | 0.2 | 10 | 27.5
| 6279 | 0.8 | 5 | 13.1707 | 20.9366 | 2.2802 | 5.4857 | 1 | 5 | 0.2 | 10 | 20
| 6280 | 0.4 | 10 | 11.7391 | 19.3533 | 3.3475 | 4.2667 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 6281 | 0.8 | 5 | 16.3636 | 26.9374 | 3.1892 | 7.3846 | 0.8 | 6.25 | 1 | 2 | 13.25
| 6282 | 0.8 | 5 | 11.7391 | 20.293 | 3.6308 | 4.9231 | 0.6 | 8.3333 | 0.1 | 20 | 33.3333
| 6283 | 0.2 | 20 | 10.1887 | 16.7578 | 2.3024 | 4.2667 | 1 | 5 | 0.4 | 5 | 30
| 6284 | 0.8 | 5 | 10.5882 | 16.4962 | 3.2778 | 2.6301 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 6285 | 0.8 | 5 | 10.3846 | 19.5524 | 3.1678 | 6 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 6286 | 1 | 4 | 12.8571 | 21.5619 | 3.3714 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 6287 | 1 | 4 | 10.1887 | 17.423 | 2.5514 | 4.6829 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 6288 | 0.6 | 6.6667 | 11.25 | 17.4069 | 2.7283 | 3.4286 | 1 | 5 | 0.6 | 3.3333 | 15
| 6289 | 0.4 | 10 | 16.3636 | 23.4762 | 3.4203 | 3.6923 | 1 | 5 | 0.2 | 10 | 25
| 6290 | 0.2 | 20 | 9.6429 | 16.5745 | 2.9317 | 4 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 6291 | 0.6 | 6.6667 | 19.2857 | 27.0515 | 3.3007 | 4.4651 | 0.4 | 12.5 | 0.6 | 3.3333 | 22.5
| 6292 | 0.8 | 5 | 10 | 16.282 | 2.9136 | 3.3684 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 6293 | 0.6 | 6.6667 | 10 | 16.7233 | 3.1678 | 3.5556 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 6294 | 0.6 | 6.6667 | 12.2727 | 22.6194 | 2.6667 | 7.68 | 1.6 | 3.125 | 0.6 | 3.3333 | 13.125
| 6295 | 0.2 | 20 | 15 | 21.9013 | 2.5376 | 4.3636 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 6296 | 0.8 | 5 | 13.8462 | 22.6501 | 3.4706 | 5.3333 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 6297 | 0.4 | 10 | 12.2727 | 21.3096 | 2.6369 | 6.4 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 6298 | 0.8 | 5 | 12 | 20.2429 | 4.069 | 4.1739 | 1 | 5 | 0.1 | 20 | 30
| 6299 | 0.6 | 6.6667 | 14.2105 | 22.2888 | 3.0256 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 6300 | 1 | 4 | 20 | 25.1595 | 2.2056 | 2.9538 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 6301 | 1.4 | 2.8571 | 14.2105 | 20.4944 | 2.7283 | 3.5556 | 0.6 | 8.3333 | 0.2 | 10 | 21.1905
| 6302 | 1.2 | 3.3333 | 12 | 20.0786 | 3.3957 | 4.6829 | 1 | 5 | 0.4 | 5 | 13.3333
| 6303 | 1.2 | 3.3333 | 16.3636 | 22.3298 | 2.5376 | 3.4286 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 6304 | 0.4 | 10 | 12.8571 | 19.0828 | 3.0256 | 3.2 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 6305 | 1.2 | 3.3333 | 13.1707 | 21.2804 | 3.746 | 4.3636 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 6306 | 0.8 | 5 | 9 | 15.6706 | 3.4706 | 3.2 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 6307 | 0.4 | 10 | 10 | 17.9804 | 3.8065 | 4.1739 | 1 | 5 | 0.2 | 10 | 25
| 6308 | 0.2 | 20 | 12.2727 | 20.032 | 3.3957 | 4.3636 | 0.6 | 8.3333 | 0.2 | 10 | 38.3333
| 6309 | 1 | 4 | 11.25 | 21.9397 | 4.069 | 6.6207 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 6310 | 0.1 | 40 | 10.5882 | 17.34 | 2.6667 | 4.0851 | 1.2 | 4.1667 | 0.1 | 20 | 64.1667
| 6311 | 0.6 | 6.6667 | 11.4894 | 17.7732 | 2.7929 | 3.4909 | 1 | 5 | 0.2 | 10 | 21.6667
| 6312 | 1 | 4 | 15 | 20.3897 | 2.5241 | 2.8657 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 6313 | 1.4 | 2.8571 | 12.2727 | 20.9845 | 4.1404 | 4.5714 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 6314 | 0.8 | 5 | 12.8571 | 18.588 | 2.4205 | 3.3103 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 6315 | 1 | 4 | 15.8824 | 22.6271 | 3.1892 | 3.5556 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 6316 | 1 | 4 | 10.5882 | 18.7711 | 2.6971 | 5.4857 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 6317 | 1 | 4 | 15.8824 | 24.1283 | 2.7602 | 5.4857 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 6318 | 1 | 4 | 12.5581 | 21.8726 | 3.4963 | 5.8182 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 6319 | 1.4 | 2.8571 | 11.7391 | 18.9943 | 3.2552 | 4 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 6320 | 0.6 | 6.6667 | 10.5882 | 17.6571 | 3.8689 | 3.2 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 6321 | 1.2 | 3.3333 | 13.1707 | 21.1174 | 3.1467 | 4.8 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 6322 | 0.6 | 6.6667 | 14.5946 | 20.7966 | 3.1053 | 3.0968 | 1 | 5 | 0.4 | 5 | 16.6667
| 6323 | 1 | 4 | 13.8462 | 21.7172 | 2.6818 | 5.1892 | 1 | 5 | 0.1 | 20 | 29
| 6324 | 0.2 | 20 | 12.8571 | 19.6977 | 2.6667 | 4.1739 | 1 | 5 | 0.4 | 5 | 30
| 6325 | 1 | 4 | 11.7391 | 18.7648 | 3.0256 | 4 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 6326 | 1.4 | 2.8571 | 9.1525 | 16.4731 | 3.1467 | 4.1739 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 6327 | 0.4 | 10 | 9.3103 | 23.4846 | 4.069 | 10.1053 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 6328 | 1.2 | 3.3333 | 21.6 | 32.9641 | 2.6369 | 8.7273 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 6329 | 1.2 | 3.3333 | 15.4286 | 21.3864 | 3.4963 | 2.4615 | 1 | 5 | 0.2 | 10 | 18.3333
| 6330 | 0.6 | 6.6667 | 13.8462 | 21.3861 | 2.9686 | 4.5714 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 6331 | 0.4 | 10 | 12 | 19.0442 | 3.1258 | 3.9184 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 6332 | 0.8 | 5 | 11.0204 | 17.5391 | 2.8263 | 3.6923 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 6333 | 0.2 | 20 | 10 | 15.8091 | 3.3475 | 2.4615 | 1 | 5 | 0.2 | 10 | 35
| 6334 | 0.8 | 5 | 11.7391 | 19.9978 | 3.5758 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 6335 | 1 | 4 | 13.1707 | 22.9272 | 2.3719 | 7.3846 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 6336 | 0.8 | 5 | 10.3846 | 16.5055 | 3.2552 | 2.8657 | 1 | 5 | 0.4 | 5 | 15
| 6337 | 1 | 4 | 13.1707 | 19.7912 | 3.0649 | 3.5556 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 6338 | 0.6 | 6.6667 | 11.7391 | 20.5053 | 2.1455 | 6.6207 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 6339 | 1 | 4 | 14.2105 | 22.9797 | 3.7165 | 5.0526 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 6340 | 0.6 | 6.6667 | 14.2105 | 25.3711 | 3.776 | 7.3846 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 6341 | 0.6 | 6.6667 | 12 | 20.4437 | 4.177 | 4.2667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 6342 | 0.8 | 5 | 11.4894 | 18.5325 | 2.7765 | 4.2667 | 1 | 5 | 0.8 | 2.5 | 12.5
| 6343 | 0.8 | 5 | 14.5946 | 21.0634 | 2.7765 | 3.6923 | 1 | 5 | 0.1 | 20 | 30
| 6344 | 1.2 | 3.3333 | 13.5 | 18.9064 | 3.0649 | 2.3415 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 6345 | 1.2 | 3.3333 | 12.2727 | 19.4603 | 3.9333 | 3.2542 | 0.4 | 12.5 | 0.1 | 20 | 35.8333
| 6346 | 1.2 | 3.3333 | 10.1887 | 16.4999 | 2.4712 | 3.84 | 1 | 5 | 0.4 | 5 | 13.3333
| 6347 | 0.6 | 6.6667 | 11.7391 | 18.7554 | 3.3239 | 3.6923 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 6348 | 1.2 | 3.3333 | 9.8182 | 18.7834 | 3.776 | 5.1892 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 6349 | 0.8 | 5 | 15.4286 | 22.3151 | 2.7126 | 4.1739 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 6350 | 0.8 | 5 | 10.5882 | 18.0765 | 2.5652 | 4.9231 | 1 | 5 | 0.2 | 10 | 20
| 6351 | 1 | 4 | 10.8 | 18.6296 | 3.1467 | 4.6829 | 1.8 | 2.7778 | 0.4 | 5 | 11.7778
| 6352 | 0.6 | 6.6667 | 10.8 | 18.6614 | 3.6875 | 4.1739 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 6353 | 0.6 | 6.6667 | 14.2105 | 21.6627 | 3.6875 | 3.7647 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 6354 | 0.4 | 10 | 9.1525 | 15.7606 | 2.8434 | 3.7647 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 6355 | 0.8 | 5 | 10.3846 | 19.017 | 3.1467 | 5.4857 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 6356 | 0.2 | 20 | 13.8462 | 21.7311 | 3.085 | 4.8 | 1 | 5 | 0.2 | 10 | 35
| 6357 | 0.4 | 10 | 13.8462 | 26.4718 | 3.0256 | 9.6 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 6358 | 0.8 | 5 | 23.4783 | 28.5928 | 2.7442 | 2.3704 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 6359 | 0.6 | 6.6667 | 10.8 | 18.8552 | 3.2552 | 4.8 | 1 | 5 | 0.1 | 20 | 31.6667
| 6360 | 1.2 | 3.3333 | 11.4894 | 18.486 | 2.3137 | 4.6829 | 1 | 5 | 0.4 | 5 | 13.3333
| 6361 | 0.6 | 6.6667 | 15.4286 | 24.2869 | 2.4583 | 6.4 | 1 | 5 | 0.6 | 3.3333 | 15
| 6362 | 0.6 | 6.6667 | 9.3103 | 17.3408 | 3.3475 | 4.6829 | 1 | 5 | 0.4 | 5 | 16.6667
| 6363 | 0.4 | 10 | 12.2727 | 20.7804 | 2.8606 | 5.6471 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 6364 | 0.4 | 10 | 9.4737 | 16.1164 | 2.878 | 3.7647 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 6365 | 0.6 | 6.6667 | 13.1707 | 20.7895 | 3.2552 | 4.3636 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 6366 | 0.8 | 5 | 10.3846 | 16.8853 | 2.878 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 6367 | 0.8 | 5 | 13.5 | 21.6675 | 3.9008 | 4.2667 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 6368 | 0.6 | 6.6667 | 12.2727 | 20.9845 | 4.1404 | 4.5714 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 6369 | 1.4 | 2.8571 | 15.4286 | 22.0079 | 3.2109 | 3.3684 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 6370 | 1 | 4 | 16.3636 | 22.4292 | 2.6971 | 3.3684 | 1 | 5 | 0.2 | 10 | 19
| 6371 | 0.2 | 20 | 14.2105 | 21.0021 | 1.9916 | 4.8 | 1.2 | 4.1667 | 0.1 | 20 | 44.1667
| 6372 | 1 | 4 | 9 | 16.1498 | 3.6589 | 3.4909 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 6373 | 1 | 4 | 13.1707 | 21.863 | 3.0452 | 5.6471 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 6374 | 0.8 | 5 | 12.5581 | 19.5206 | 2.4974 | 4.4651 | 1 | 5 | 0.2 | 10 | 20
| 6375 | 0.6 | 6.6667 | 12 | 18.9808 | 2.8957 | 4.0851 | 1 | 5 | 0.6 | 3.3333 | 15
| 6376 | 0.6 | 6.6667 | 12 | 19.4715 | 3.0064 | 4.4651 | 0.4 | 12.5 | 0.2 | 10 | 29.1667
| 6377 | 0.8 | 5 | 14.5946 | 19.7971 | 3.0452 | 2.1573 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 6378 | 1.2 | 3.3333 | 15.4286 | 24.5732 | 3.6589 | 5.4857 | 1 | 5 | 0.2 | 10 | 18.3333
| 6379 | 1 | 4 | 14.2105 | 21.172 | 3.4706 | 3.4909 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 6380 | 1.4 | 2.8571 | 9.3103 | 18.4477 | 4.2143 | 4.9231 | 0.6 | 8.3333 | 0.6 | 3.3333 | 14.5238
| 6381 | 1.4 | 2.8571 | 9 | 15.6626 | 2.3959 | 4.2667 | 0.6 | 8.3333 | 0.8 | 2.5 | 13.6905
| 6382 | 1.2 | 3.3333 | 11.4894 | 21.5574 | 3.2109 | 6.8571 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 6383 | 1 | 4 | 11.4894 | 20.7901 | 3.3007 | 6 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 6384 | 0.6 | 6.6667 | 13.1707 | 22.4695 | 3.1053 | 6.1935 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 6385 | 1.6 | 2.5 | 9.1525 | 15.9046 | 2.9873 | 3.7647 | 1.2 | 4.1667 | 0.8 | 2.5 | 9.1667
| 6386 | 1.2 | 3.3333 | 8.8525 | 15.9411 | 3.3239 | 3.7647 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 6387 | 0.4 | 10 | 12 | 24.55 | 2.95 | 9.6 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 6388 | 0.8 | 5 | 9.3103 | 19.9957 | 3.3007 | 7.3846 | 1 | 5 | 0.4 | 5 | 15
| 6389 | 0.6 | 6.6667 | 20 | 25.5313 | 2.6222 | 2.9091 | 1 | 5 | 1 | 2 | 13.6667
| 6390 | 0.8 | 5 | 11.7391 | 18.1445 | 3.4963 | 2.9091 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 6391 | 0.4 | 10 | 17.4194 | 28.4233 | 3.3239 | 7.68 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 6392 | 0.4 | 10 | 10.5882 | 16.0831 | 2.9686 | 2.5263 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 6393 | 0.8 | 5 | 11.0204 | 16.0459 | 2.7929 | 2.2326 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 6394 | 0.4 | 10 | 12 | 17.6595 | 3.0649 | 2.5946 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 6395 | 1 | 4 | 11.7391 | 18.6661 | 3.3714 | 3.5556 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 6396 | 1.2 | 3.3333 | 13.1707 | 20.4548 | 2.7126 | 4.5714 | 0.4 | 12.5 | 0.2 | 10 | 25.8333
| 6397 | 0.6 | 6.6667 | 12.8571 | 21.2886 | 3.9664 | 4.4651 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 6398 | 0.2 | 20 | 9.4737 | 18.1428 | 3.746 | 4.9231 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 6399 | 0.8 | 5 | 13.5 | 29.6714 | 3.3714 | 12.8 | 1 | 5 | 0.8 | 2.5 | 12.5
| 6400 | 0.6 | 6.6667 | 7.7143 | 22.5872 | 4.7677 | 10.1053 | 1 | 5 | 0.1 | 20 | 31.6667
| 6401 | 1 | 4 | 11.0204 | 17.6382 | 3.1892 | 3.4286 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 6402 | 0.4 | 10 | 12.2727 | 18.7031 | 3.6875 | 2.7429 | 1 | 5 | 0.2 | 10 | 25
| 6403 | 1.4 | 2.8571 | 13.5 | 18.4028 | 2.0793 | 2.8235 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 6404 | 0.6 | 6.6667 | 8.1818 | 12.6956 | 2.4712 | 2.0426 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 6405 | 1 | 4 | 10.5882 | 17.7992 | 3.1258 | 4.0851 | 1 | 5 | 0.4 | 5 | 14
| 6406 | 0.8 | 5 | 16.3636 | 26.9217 | 2.878 | 7.68 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 6407 | 0.6 | 6.6667 | 15.8824 | 24.8058 | 3.1053 | 5.8182 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 6408 | 0.6 | 6.6667 | 13.5 | 20.1002 | 2.6818 | 3.9184 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 6409 | 0.8 | 5 | 15.8824 | 21.4252 | 2.7602 | 2.7826 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 6410 | 0.8 | 5 | 8.4375 | 16.4835 | 2.7126 | 5.3333 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 6411 | 1.4 | 2.8571 | 16.3636 | 24.0593 | 2.8957 | 4.8 | 1 | 5 | 0.4 | 5 | 12.8571
| 6412 | 1 | 4 | 15.4286 | 22.7355 | 2.3838 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 6413 | 0.4 | 10 | 8.7097 | 16.7687 | 3.0064 | 5.0526 | 1 | 5 | 0.2 | 10 | 25
| 6414 | 0.6 | 6.6667 | 15 | 20.8335 | 2.5792 | 3.2542 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 6415 | 0.6 | 6.6667 | 9.1525 | 15.7001 | 3.3475 | 3.2 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 6416 | 0.4 | 10 | 12.5581 | 22.434 | 3.2552 | 6.6207 | 1 | 5 | 0.2 | 10 | 25
| 6417 | 0.4 | 10 | 13.5 | 22.5199 | 2.8263 | 6.1935 | 1 | 5 | 0.4 | 5 | 20
| 6418 | 0.8 | 5 | 10.8 | 17.6606 | 2.8606 | 4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 6419 | 0.6 | 6.6667 | 10.5882 | 19.2428 | 4.2909 | 4.3636 | 0.4 | 12.5 | 0.6 | 3.3333 | 22.5
| 6420 | 1.2 | 3.3333 | 10.5882 | 18.1166 | 2.7283 | 4.8 | 1 | 5 | 0.2 | 10 | 18.3333
| 6421 | 0.4 | 10 | 13.8462 | 20.4423 | 3.1053 | 3.4909 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 6422 | 1 | 4 | 13.5 | 22.5185 | 3.3714 | 5.6471 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 6423 | 0.6 | 6.6667 | 7.7143 | 16.2047 | 2.8434 | 5.6471 | 0.4 | 12.5 | 0.6 | 3.3333 | 22.5
| 6424 | 0.8 | 5 | 9.8182 | 17.3674 | 2.36 | 5.1892 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 6425 | 0.6 | 6.6667 | 10.1887 | 18.5671 | 3.1892 | 5.1892 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 6426 | 0.4 | 10 | 12.8571 | 19.6712 | 2.8957 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 6427 | 1.2 | 3.3333 | 12.8571 | 21.532 | 3.1892 | 5.4857 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 6428 | 0.8 | 5 | 9.3103 | 15.6932 | 2.7602 | 3.6226 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 6429 | 1.4 | 2.8571 | 10 | 19.7352 | 2.878 | 6.8571 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 6430 | 0.2 | 20 | 11.25 | 18.243 | 3.3007 | 3.6923 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 6431 | 0.8 | 5 | 13.1707 | 24.1852 | 2.6667 | 8.3478 | 1 | 5 | 1 | 2 | 12
| 6432 | 0.6 | 6.6667 | 10 | 17.5263 | 2.8434 | 4.6829 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 6433 | 0.6 | 6.6667 | 9.3103 | 15.2744 | 3.4706 | 2.4935 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 6434 | 0.8 | 5 | 12.2727 | 19.2012 | 2.8434 | 4.0851 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 6435 | 0.2 | 20 | 16.3636 | 23.4895 | 3.1258 | 4 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 6436 | 0.6 | 6.6667 | 20 | 25.6364 | 2.1455 | 3.4909 | 1 | 5 | 0.6 | 3.3333 | 15
| 6437 | 0.4 | 10 | 12 | 21.983 | 3.1258 | 6.8571 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 6438 | 0.6 | 6.6667 | 9.3103 | 15.9509 | 3.085 | 3.5556 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 6439 | 0.6 | 6.6667 | 14.2105 | 19.9121 | 2.878 | 2.8235 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 6440 | 0.6 | 6.6667 | 15.4286 | 21.9313 | 3.5489 | 2.9538 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 6441 | 0.8 | 5 | 9.6429 | 16.4609 | 2.5514 | 4.2667 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 6442 | 0.8 | 5 | 18.6207 | 26.9344 | 3.6308 | 4.6829 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 6443 | 0.8 | 5 | 8.7097 | 16.9427 | 3.9664 | 4.2667 | 0.2 | 25 | 0.2 | 10 | 40
| 6444 | 0.6 | 6.6667 | 15 | 24.2778 | 3.6308 | 5.6471 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 6445 | 1.6 | 2.5 | 12 | 21.4362 | 2.3251 | 7.1111 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.0833
| 6446 | 1 | 4 | 13.1707 | 19.079 | 2.8606 | 3.0476 | 1.2 | 4.1667 | 1 | 2 | 10.1667
| 6447 | 0.8 | 5 | 13.8462 | 19.4723 | 2.3719 | 3.2542 | 1 | 5 | 0.8 | 2.5 | 12.5
| 6448 | 0.6 | 6.6667 | 11.7391 | 18.8241 | 3.085 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 6449 | 0.8 | 5 | 10 | 21.8943 | 4.2143 | 7.68 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 6450 | 0.6 | 6.6667 | 14.5946 | 21.8113 | 2.95 | 4.2667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 6451 | 0.4 | 10 | 11.25 | 16.8301 | 2.95 | 2.6301 | 0.4 | 12.5 | 0.2 | 10 | 32.5
| 6452 | 1.6 | 2.5 | 8.8525 | 18.5012 | 2.5376 | 7.1111 | 1.2 | 4.1667 | 0.8 | 2.5 | 9.1667
| 6453 | 0.8 | 5 | 14.5946 | 21.6634 | 2.4974 | 4.5714 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 6454 | 0.8 | 5 | 13.8462 | 19.063 | 2.6222 | 2.5946 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 6455 | 0.4 | 10 | 17.4194 | 26.6627 | 2.8434 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 6456 | 0.6 | 6.6667 | 8.7097 | 15.6554 | 2.8606 | 4.0851 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 6457 | 0.4 | 10 | 12.5581 | 18.6231 | 3.0649 | 3 | 1 | 5 | 0.4 | 5 | 20
| 6458 | 0.6 | 6.6667 | 11.25 | 19.6531 | 3.6031 | 4.8 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 6459 | 0.4 | 10 | 15.8824 | 21.3702 | 2.6222 | 2.8657 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 6460 | 1.2 | 3.3333 | 9.3103 | 14.4191 | 2.0611 | 3.0476 | 1 | 5 | 0.4 | 5 | 13.3333
| 6461 | 0.6 | 6.6667 | 11.4894 | 19.2717 | 3.2109 | 4.5714 | 1 | 5 | 0.4 | 5 | 16.6667
| 6462 | 0.4 | 10 | 9.8182 | 22.2962 | 2.878 | 9.6 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 6463 | 0.4 | 10 | 10.1887 | 16.6042 | 2.7929 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 6464 | 0.6 | 6.6667 | 13.8462 | 20.2433 | 2.9686 | 3.4286 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 6465 | 0.8 | 5 | 12.5581 | 20.6932 | 4.3704 | 3.7647 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 6466 | 0.8 | 5 | 12.2727 | 19.3747 | 2.6369 | 4.4651 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 6467 | 0.8 | 5 | 12 | 19.0915 | 3.0064 | 4.0851 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 6468 | 0.4 | 10 | 14.5946 | 27.6149 | 3.4203 | 9.6 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 6469 | 0.2 | 20 | 8.0597 | 15.7161 | 3.085 | 4.5714 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 6470 | 1 | 4 | 9.4737 | 15.0671 | 2.5934 | 3 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 6471 | 1 | 4 | 10.1887 | 16.4041 | 3.1678 | 3.0476 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 6472 | 1 | 4 | 8.1818 | 15.7792 | 2.4082 | 5.1892 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 6473 | 0.8 | 5 | 17.4194 | 24.1912 | 2.4082 | 4.3636 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 6474 | 1 | 4 | 13.8462 | 20.5066 | 2.8957 | 3.7647 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 6475 | 0.6 | 6.6667 | 14.2105 | 21.5261 | 2.7442 | 4.5714 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 6476 | 0.6 | 6.6667 | 14.2105 | 21.4101 | 3.0256 | 4.1739 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 6477 | 0.2 | 20 | 13.8462 | 20.0688 | 3.1258 | 3.0968 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 6478 | 1 | 4 | 11.4894 | 21.2153 | 3.1053 | 6.6207 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 6479 | 1.4 | 2.8571 | 18.6207 | 24.2206 | 2.8957 | 2.7042 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 6480 | 0.4 | 10 | 11.4894 | 17.2072 | 3.3475 | 2.3704 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 6481 | 1.4 | 2.8571 | 9 | 16.3956 | 2.7126 | 4.6829 | 1 | 5 | 0.4 | 5 | 12.8571
| 6482 | 0.4 | 10 | 9.8182 | 18.3889 | 3.085 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 6483 | 1 | 4 | 10.8 | 18.4465 | 3.8065 | 3.84 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 6484 | 1.2 | 3.3333 | 10 | 19.8453 | 3.4453 | 6.4 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 6485 | 0.2 | 20 | 8.7097 | 16.4278 | 3.1467 | 4.5714 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 6486 | 0.6 | 6.6667 | 11.25 | 23.4778 | 3.085 | 9.1429 | 1 | 5 | 0.6 | 3.3333 | 15
| 6487 | 1 | 4 | 18.6207 | 27.4641 | 2.8434 | 6 | 1.8 | 2.7778 | 0.4 | 5 | 11.7778
| 6488 | 1 | 4 | 16.3636 | 25.959 | 2.4842 | 7.1111 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 6489 | 0.6 | 6.6667 | 13.8462 | 19.9116 | 2.6369 | 3.4286 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 6490 | 1 | 4 | 14.5946 | 21.6796 | 3.7165 | 3.3684 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 6491 | 1 | 4 | 9.3103 | 16.9884 | 2.878 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 6492 | 1.2 | 3.3333 | 9.6429 | 15.8209 | 3.7165 | 2.4615 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 6493 | 1 | 4 | 11.0204 | 16.7689 | 2.6517 | 3.0968 | 0.4 | 12.5 | 0.2 | 10 | 26.5
| 6494 | 1 | 4 | 12.5581 | 22.0524 | 3.3007 | 6.1935 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 6495 | 0.6 | 6.6667 | 11.4894 | 18.8966 | 2.4842 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 15
| 6496 | 0.8 | 5 | 9.4737 | 19.7526 | 3.1678 | 7.1111 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 6497 | 0.8 | 5 | 10.3846 | 17.4866 | 2.6369 | 4.4651 | 0.4 | 12.5 | 0.2 | 10 | 27.5
| 6498 | 1.2 | 3.3333 | 11.4894 | 17.8449 | 3.0452 | 3.3103 | 1.2 | 4.1667 | 0.1 | 20 | 27.5
| 6499 | 0.4 | 10 | 12 | 18.9115 | 2.8263 | 4.0851 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 6500 | 0.6 | 6.6667 | 12.5581 | 18.3015 | 2.433 | 3.3103 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 6501 | 1 | 4 | 20.7692 | 26.9261 | 2.7283 | 3.4286 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 6502 | 0.4 | 10 | 14.5946 | 20.8271 | 3.085 | 3.1475 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 6503 | 1 | 4 | 12.2727 | 20.6816 | 3.8374 | 4.5714 | 1 | 5 | 0.4 | 5 | 14
| 6504 | 0.6 | 6.6667 | 11.25 | 19.6573 | 2.7602 | 5.6471 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 6505 | 0.8 | 5 | 11.4894 | 19.3998 | 2.9873 | 4.9231 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 6506 | 0.6 | 6.6667 | 11.4894 | 19.3411 | 3.9333 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 6507 | 0.8 | 5 | 8.7097 | 17.6961 | 2.7929 | 6.1935 | 1.4 | 3.5714 | 0.8 | 2.5 | 11.0714
| 6508 | 0.8 | 5 | 9.8182 | 17.1288 | 3.4706 | 3.84 | 0.4 | 12.5 | 0.8 | 2.5 | 20
| 6509 | 0.4 | 10 | 11.0204 | 16.8455 | 2.7283 | 3.0968 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 6510 | 1.2 | 3.3333 | 15.4286 | 22.1858 | 3.0649 | 3.6923 | 1.6 | 3.125 | 0.2 | 10 | 16.4583
| 6511 | 0.6 | 6.6667 | 10 | 21.1003 | 3.4203 | 7.68 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 6512 | 1 | 4 | 16.3636 | 23.6059 | 3.3239 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 6513 | 1.4 | 2.8571 | 10.5882 | 17.6958 | 3.1892 | 3.9184 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 6514 | 0.6 | 6.6667 | 12 | 25.8875 | 2.5934 | 11.2941 | 1 | 5 | 0.4 | 5 | 16.6667
| 6515 | 1 | 4 | 9.1525 | 17.9607 | 2.4082 | 6.4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 6516 | 0.1 | 40 | 12.5581 | 19.4528 | 2.8095 | 4.0851 | 0.6 | 8.3333 | 0.4 | 5 | 53.3333
| 6517 | 0.2 | 20 | 12.2727 | 22.3392 | 2.6818 | 7.3846 | 1 | 5 | 0.4 | 5 | 30
| 6518 | 0.6 | 6.6667 | 8.8525 | 15.204 | 2.8606 | 3.4909 | 1 | 5 | 0.2 | 10 | 21.6667
| 6519 | 0.4 | 10 | 10.5882 | 19.0448 | 2.8095 | 5.6471 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 6520 | 0.1 | 40 | 13.8462 | 19.6347 | 2.36 | 3.4286 | 1.4 | 3.5714 | 0.4 | 5 | 48.5714
| 6521 | 1 | 4 | 11.25 | 20.4282 | 4.4952 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 6522 | 0.8 | 5 | 9 | 16.3512 | 3.6589 | 3.6923 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 6523 | 0.8 | 5 | 14.5946 | 20.9134 | 2.0522 | 4.2667 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 6524 | 0.8 | 5 | 10.5882 | 17.4179 | 3.0649 | 3.7647 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 6525 | 0.8 | 5 | 9.8182 | 21.3692 | 2.4082 | 9.1429 | 1 | 5 | 1 | 2 | 12
| 6526 | 0.6 | 6.6667 | 11.7391 | 20.9925 | 4.3303 | 4.9231 | 0.4 | 12.5 | 0.8 | 2.5 | 21.6667
| 6527 | 1.2 | 3.3333 | 10.8 | 17.2974 | 2.4974 | 4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 6528 | 0.8 | 5 | 9.1525 | 17.5359 | 2.5652 | 5.8182 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 6529 | 1.2 | 3.3333 | 11.7391 | 23.6585 | 2.7765 | 9.1429 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 6530 | 1.2 | 3.3333 | 11.0204 | 17.3042 | 2.7929 | 3.4909 | 1 | 5 | 0.2 | 10 | 18.3333
| 6531 | 0.4 | 10 | 8.5714 | 13.7681 | 2.8263 | 2.3704 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 6532 | 0.6 | 6.6667 | 11.7391 | 18.345 | 2.9136 | 3.6923 | 1 | 5 | 0.4 | 5 | 16.6667
| 6533 | 0.4 | 10 | 10.3846 | 19.9926 | 2.9873 | 6.6207 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 6534 | 0.4 | 10 | 7.9412 | 16.4788 | 2.5376 | 6 | 1 | 5 | 0.1 | 20 | 35
| 6535 | 1 | 4 | 13.8462 | 21.2978 | 3.2778 | 4.1739 | 1 | 5 | 0.2 | 10 | 19
| 6536 | 0.6 | 6.6667 | 9.1525 | 15.3756 | 2.4583 | 3.7647 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 6537 | 1 | 4 | 10.1887 | 15.9501 | 2.8957 | 2.8657 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 6538 | 1.2 | 3.3333 | 10 | 19.1071 | 2.9136 | 6.1935 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 6539 | 1.4 | 2.8571 | 15.4286 | 26.0808 | 4.2523 | 6.4 | 0.8 | 6.25 | 0.8 | 2.5 | 11.6071
| 6540 | 0.8 | 5 | 14.5946 | 21.4446 | 2.9317 | 3.9184 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 6541 | 0.6 | 6.6667 | 13.8462 | 19.6819 | 2.2802 | 3.5556 | 1 | 5 | 0.4 | 5 | 16.6667
| 6542 | 0.6 | 6.6667 | 18 | 22.5455 | 2.1751 | 2.3704 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 6543 | 1 | 4 | 13.5 | 20.3656 | 3.0256 | 3.84 | 1 | 5 | 0.4 | 5 | 14
| 6544 | 0.4 | 10 | 16.875 | 22.313 | 2.8434 | 2.5946 | 1 | 5 | 0.4 | 5 | 20
| 6545 | 1 | 4 | 14.5946 | 22.9409 | 2.8606 | 5.4857 | 1 | 5 | 0.2 | 10 | 19
| 6546 | 0.4 | 10 | 16.3636 | 23.7153 | 3.085 | 4.2667 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 6547 | 1.2 | 3.3333 | 16.3636 | 22.9389 | 3.1467 | 3.4286 | 1 | 5 | 0.2 | 10 | 18.3333
| 6548 | 0.6 | 6.6667 | 13.5 | 20.3327 | 3.5224 | 3.3103 | 1 | 5 | 0.2 | 10 | 21.6667
| 6549 | 0.4 | 10 | 11.0204 | 18.2733 | 3.1678 | 4.0851 | 1 | 5 | 0.4 | 5 | 20
| 6550 | 0.6 | 6.6667 | 12.5581 | 20.1552 | 3.0256 | 4.5714 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 6551 | 0.2 | 20 | 9.8182 | 16.0421 | 2.9136 | 3.3103 | 1.4 | 3.5714 | 0.1 | 20 | 43.5714
| 6552 | 0.6 | 6.6667 | 12.8571 | 21.5576 | 5.5529 | 3.1475 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 6553 | 0.4 | 10 | 10.3846 | 18.3726 | 3.0649 | 4.9231 | 1 | 5 | 0.1 | 20 | 35
| 6554 | 0.8 | 5 | 12.2727 | 18.3659 | 2.5376 | 3.5556 | 1.6 | 3.125 | 0.2 | 10 | 18.125
| 6555 | 1.4 | 2.8571 | 14.5946 | 22.452 | 2.5241 | 5.3333 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 6556 | 0.6 | 6.6667 | 9 | 15.5759 | 3.085 | 3.4909 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 6557 | 1.4 | 2.8571 | 17.4194 | 23.5146 | 2.6667 | 3.4286 | 0.6 | 8.3333 | 0.4 | 5 | 16.1905
| 6558 | 1 | 4 | 14.5946 | 24.9166 | 3.2109 | 7.1111 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 6559 | 1.2 | 3.3333 | 10.3846 | 17.5297 | 3.7165 | 3.4286 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 6560 | 0.6 | 6.6667 | 13.8462 | 20.4011 | 3.3007 | 3.2542 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 6561 | 1.2 | 3.3333 | 14.5946 | 24.7831 | 4.3704 | 5.8182 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 6562 | 0.2 | 20 | 10.8 | 17.3151 | 3.1467 | 3.3684 | 1 | 5 | 0.1 | 20 | 45
| 6563 | 0.4 | 10 | 12.2727 | 21.4868 | 2.5934 | 6.6207 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 6564 | 0.6 | 6.6667 | 14.5946 | 21.0436 | 2.8263 | 3.6226 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 6565 | 1.4 | 2.8571 | 18.6207 | 25.3213 | 2.8606 | 3.84 | 0.6 | 8.3333 | 0.4 | 5 | 16.1905
| 6566 | 1 | 4 | 9.4737 | 28.97 | 3.4963 | 16 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 6567 | 1 | 4 | 14.2105 | 22.389 | 3.1258 | 5.0526 | 1 | 5 | 0.4 | 5 | 14
| 6568 | 0.6 | 6.6667 | 12.2727 | 19.8172 | 3.2778 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 6569 | 0.2 | 20 | 19.2857 | 28.1919 | 2.7126 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 6570 | 0.4 | 10 | 9.4737 | 17.4399 | 2.9136 | 5.0526 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 6571 | 0.8 | 5 | 16.875 | 23.819 | 3.0256 | 3.9184 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 6572 | 1.4 | 2.8571 | 10.5882 | 17.4734 | 3.0452 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 6573 | 1.2 | 3.3333 | 9.8182 | 17.0771 | 3.085 | 4.1739 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 6574 | 1 | 4 | 8.1818 | 14.4816 | 2.7442 | 3.5556 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 6575 | 0.4 | 10 | 16.3636 | 23.9202 | 3.7165 | 3.84 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 6576 | 1.4 | 2.8571 | 12.5581 | 19.2207 | 2.7442 | 3.9184 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 6577 | 1.4 | 2.8571 | 8.3077 | 17.4781 | 4.3704 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 6578 | 0.8 | 5 | 16.3636 | 24.0981 | 2.6818 | 5.0526 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 6579 | 0.8 | 5 | 17.4194 | 24.9508 | 3.1678 | 4.3636 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 6580 | 1 | 4 | 14.5946 | 24.3003 | 3.085 | 6.6207 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 6581 | 1 | 4 | 12 | 20.4259 | 2.6077 | 5.8182 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 6582 | 1 | 4 | 14.2105 | 20.9092 | 3.0064 | 3.6923 | 1 | 5 | 0.4 | 5 | 14
| 6583 | 0.1 | 40 | 15.8824 | 22.3754 | 2.7283 | 3.7647 | 1.2 | 4.1667 | 0.2 | 10 | 54.1667
| 6584 | 1 | 4 | 16.875 | 23.4827 | 2.6077 | 4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 6585 | 0.4 | 10 | 10.1887 | 17.4369 | 2.3251 | 4.9231 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 6586 | 1 | 4 | 11.0204 | 31.5201 | 3.0452 | 17.4545 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 6587 | 1 | 4 | 12.5581 | 21.8469 | 3.4706 | 5.8182 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 6588 | 0.6 | 6.6667 | 12.5581 | 23.3384 | 3.3957 | 7.3846 | 1 | 5 | 0.4 | 5 | 16.6667
| 6589 | 0.6 | 6.6667 | 9.3103 | 17.1555 | 3.0452 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 6590 | 1 | 4 | 9.8182 | 15.2855 | 3.1258 | 2.3415 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 6591 | 0.6 | 6.6667 | 15.8824 | 23.9313 | 3.1258 | 4.9231 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 6592 | 1 | 4 | 8.5714 | 16.1685 | 3.0256 | 4.5714 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 6593 | 1.4 | 2.8571 | 13.5 | 20.7997 | 3.1258 | 4.1739 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 6594 | 1.2 | 3.3333 | 10.3846 | 17.7477 | 3.1892 | 4.1739 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 6595 | 0.8 | 5 | 13.5 | 19.3571 | 2.8095 | 3.0476 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 6596 | 0.8 | 5 | 11.4894 | 19.1566 | 2.7442 | 4.9231 | 1 | 5 | 0.2 | 10 | 20
| 6597 | 0.6 | 6.6667 | 11.4894 | 19.4152 | 3.1258 | 4.8 | 1.8 | 2.7778 | 0.4 | 5 | 14.4444
| 6598 | 0.6 | 6.6667 | 10.1887 | 21.609 | 3.4203 | 8 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 6599 | 0.4 | 10 | 14.2105 | 21.3322 | 3.6308 | 3.4909 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 6600 | 1 | 4 | 12.5581 | 20.2026 | 3.4706 | 4.1739 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 6601 | 0.8 | 5 | 14.5946 | 20.3413 | 2.7929 | 2.9538 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 6602 | 1.2 | 3.3333 | 12.8571 | 18.9221 | 3.0649 | 3 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 6603 | 0.6 | 6.6667 | 12.8571 | 19.1121 | 2.8263 | 3.4286 | 1 | 5 | 0.4 | 5 | 16.6667
| 6604 | 0.4 | 10 | 10.5882 | 19.0882 | 2.6818 | 5.8182 | 1.2 | 4.1667 | 0.1 | 20 | 34.1667
| 6605 | 1 | 4 | 11.7391 | 21.549 | 3.1892 | 6.6207 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 6606 | 0.6 | 6.6667 | 12 | 19.5942 | 3.4203 | 4.1739 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 6607 | 1.4 | 2.8571 | 16.3636 | 25.473 | 3.776 | 5.3333 | 0.4 | 12.5 | 0.2 | 10 | 25.3571
| 6608 | 0.8 | 5 | 10.3846 | 18.3872 | 2.95 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 6609 | 0.8 | 5 | 11.25 | 19.1235 | 2.2264 | 5.6471 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 6610 | 1 | 4 | 9.8182 | 18.8762 | 3.8689 | 5.1892 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.8333
| 6611 | 0.8 | 5 | 20 | 26.9233 | 3.3007 | 3.6226 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 6612 | 1.2 | 3.3333 | 13.1707 | 25.2821 | 2.9686 | 9.1429 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 6613 | 0.4 | 10 | 12 | 19.5633 | 2.5106 | 5.0526 | 0.4 | 12.5 | 0.6 | 3.3333 | 25.8333
| 6614 | 0.8 | 5 | 11.0204 | 17.091 | 2.7602 | 3.3103 | 1 | 5 | 0.2 | 10 | 20
| 6615 | 0.2 | 20 | 11.0204 | 19.1163 | 3.6308 | 4.4651 | 0.6 | 8.3333 | 0.6 | 3.3333 | 31.6667
| 6616 | 1 | 4 | 12.5581 | 20.6957 | 3.085 | 5.0526 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 6617 | 0.8 | 5 | 11.0204 | 17.3718 | 2.433 | 3.9184 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 6618 | 0.6 | 6.6667 | 15 | 20.9466 | 3.4203 | 2.5263 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 6619 | 0.6 | 6.6667 | 16.875 | 26.0889 | 3.3957 | 5.8182 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 6620 | 0.4 | 10 | 10.5882 | 17.5916 | 3.085 | 3.9184 | 1 | 5 | 0.2 | 10 | 25
| 6621 | 1.2 | 3.3333 | 12.2727 | 19.2169 | 3.5758 | 3.3684 | 1.8 | 2.7778 | 0.4 | 5 | 11.1111
| 6622 | 1 | 4 | 17.4194 | 30.5682 | 3.5489 | 9.6 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 6623 | 0.6 | 6.6667 | 11.7391 | 17.33 | 2.3366 | 3.2542 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 6624 | 1 | 4 | 12.5581 | 19.4265 | 2.95 | 3.9184 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 6625 | 0.4 | 10 | 11.7391 | 19.0631 | 3.3239 | 4 | 1.6 | 3.125 | 0.8 | 2.5 | 15.625
| 6626 | 1.4 | 2.8571 | 11.25 | 17.1538 | 2.95 | 2.9538 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 6627 | 0.4 | 10 | 12.5581 | 19.0417 | 2.5652 | 3.9184 | 1 | 5 | 0.4 | 5 | 20
| 6628 | 0.6 | 6.6667 | 8.8525 | 17.0269 | 3.6031 | 4.5714 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 6629 | 1 | 4 | 11.4894 | 18.4368 | 3.2552 | 3.6923 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 6630 | 0.8 | 5 | 11.0204 | 18.1844 | 3.3239 | 3.84 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 6631 | 0.8 | 5 | 10.3846 | 16.3928 | 2.8606 | 3.1475 | 1 | 5 | 0.2 | 10 | 20
| 6632 | 0.6 | 6.6667 | 10.5882 | 20.351 | 2.6517 | 7.1111 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 6633 | 0.2 | 20 | 9.8182 | 20.5035 | 3.3007 | 7.3846 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 6634 | 0.4 | 10 | 8.5714 | 17.8004 | 2.3719 | 6.8571 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 6635 | 0.4 | 10 | 12 | 18.6077 | 2.6077 | 4 | 1 | 5 | 0.2 | 10 | 25
| 6636 | 0.8 | 5 | 16.3636 | 23.2226 | 3.6589 | 3.2 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 6637 | 0.2 | 20 | 11.0204 | 18.6985 | 2.878 | 4.8 | 1 | 5 | 1 | 2 | 27
| 6638 | 1.4 | 2.8571 | 12.2727 | 18.6237 | 2.7283 | 3.6226 | 1 | 5 | 0.8 | 2.5 | 10.3571
| 6639 | 1 | 4 | 18.6207 | 26.0156 | 3.9664 | 3.4286 | 1 | 5 | 0.4 | 5 | 14
| 6640 | 0.8 | 5 | 12.5581 | 19.2604 | 3.1467 | 3.5556 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 6641 | 1.2 | 3.3333 | 8.8525 | 16.7032 | 3.1678 | 4.6829 | 1 | 5 | 0.2 | 10 | 18.3333
| 6642 | 0.8 | 5 | 9.8182 | 16.9648 | 3.1467 | 4 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 6643 | 1.2 | 3.3333 | 10.5882 | 18.3852 | 2.6077 | 5.1892 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 6644 | 0.6 | 6.6667 | 15 | 22.0649 | 3.0649 | 4 | 1 | 5 | 0.2 | 10 | 21.6667
| 6645 | 0.6 | 6.6667 | 12.2727 | 18.7509 | 3.1678 | 3.3103 | 1 | 5 | 0.1 | 20 | 31.6667
| 6646 | 0.4 | 10 | 12.5581 | 18.4769 | 2.2264 | 3.6923 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 6647 | 1.2 | 3.3333 | 12.5581 | 18.8131 | 2.8263 | 3.4286 | 1.6 | 3.125 | 0.2 | 10 | 16.4583
| 6648 | 0.8 | 5 | 18 | 25.8611 | 3.776 | 4.0851 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 6649 | 0.6 | 6.6667 | 9.6429 | 16.6431 | 2.8263 | 4.1739 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 6650 | 0.8 | 5 | 12.2727 | 19.6575 | 3.2109 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 6651 | 0.4 | 10 | 16.875 | 25.3479 | 3.4203 | 5.0526 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 6652 | 0.2 | 20 | 12.2727 | 19.8219 | 3.6308 | 3.9184 | 1.4 | 3.5714 | 0.1 | 20 | 43.5714
| 6653 | 0.8 | 5 | 13.1707 | 20.413 | 3.3239 | 3.9184 | 0.4 | 12.5 | 0.1 | 20 | 37.5
| 6654 | 1 | 4 | 10.5882 | 17.3769 | 3.4203 | 3.3684 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 6655 | 0.8 | 5 | 11.25 | 18.9612 | 3.3475 | 4.3636 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 6656 | 1.2 | 3.3333 | 8.8525 | 15.7942 | 3.6875 | 3.2542 | 0.8 | 6.25 | 0.8 | 2.5 | 12.0833
| 6657 | 1 | 4 | 10.5882 | 17.4997 | 2.8263 | 4.0851 | 1.4 | 3.5714 | 0.1 | 20 | 27.5714
| 6658 | 0.8 | 5 | 14.2105 | 21.6432 | 3.3475 | 4.0851 | 1 | 5 | 0.2 | 10 | 20
| 6659 | 0.8 | 5 | 15.4286 | 21.7453 | 3.0064 | 3.3103 | 1 | 5 | 0.4 | 5 | 15
| 6660 | 1 | 4 | 17.4194 | 23.0368 | 2.9873 | 2.6301 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 6661 | 0.8 | 5 | 10.1887 | 17.4801 | 2.8263 | 4.4651 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 6662 | 0.6 | 6.6667 | 9 | 16.4432 | 2.7602 | 4.6829 | 1 | 5 | 0.1 | 20 | 31.6667
| 6663 | 0.6 | 6.6667 | 11.7391 | 19.7335 | 3.6308 | 4.3636 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 6664 | 0.4 | 10 | 11.4894 | 16.5114 | 2.6517 | 2.3704 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 6665 | 1.2 | 3.3333 | 16.875 | 24.1522 | 2.9136 | 4.3636 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 6666 | 1 | 4 | 11.25 | 17.4871 | 3.3714 | 2.8657 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 6667 | 0.8 | 5 | 15 | 21.1635 | 2.4712 | 3.6923 | 1 | 5 | 0.4 | 5 | 15
| 6668 | 0.8 | 5 | 17.4194 | 25.6484 | 2.8957 | 5.3333 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 6669 | 1 | 4 | 12 | 20.4699 | 2.6517 | 5.8182 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 6670 | 0.8 | 5 | 11.7391 | 18.9847 | 2.4456 | 4.8 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 6671 | 1.2 | 3.3333 | 12.2727 | 22.0894 | 4.6275 | 5.1892 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 6672 | 0.6 | 6.6667 | 13.8462 | 20.1944 | 2.3483 | 4 | 1 | 5 | 0.6 | 3.3333 | 15
| 6673 | 1 | 4 | 13.5 | 23.1431 | 4.72 | 4.9231 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 6674 | 0.6 | 6.6667 | 8.5714 | 15.3113 | 3.3714 | 3.3684 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 6675 | 1.2 | 3.3333 | 12.2727 | 20.1286 | 2.6667 | 5.1892 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 6676 | 1.2 | 3.3333 | 10.8 | 19.3077 | 2.8606 | 5.6471 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 6677 | 0.6 | 6.6667 | 11.4894 | 29.3639 | 3.1053 | 14.7692 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 6678 | 0.6 | 6.6667 | 13.8462 | 23.0353 | 3.1892 | 6 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 6679 | 0.4 | 10 | 12.8571 | 18.7822 | 2.3024 | 3.6226 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 6680 | 0.8 | 5 | 16.3636 | 24.2484 | 3.9664 | 3.9184 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 6681 | 0.8 | 5 | 12.5581 | 21.5021 | 3.1258 | 5.8182 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 6682 | 0.6 | 6.6667 | 15.4286 | 24.6673 | 3.0452 | 6.1935 | 1 | 5 | 0.1 | 20 | 31.6667
| 6683 | 0.8 | 5 | 13.1707 | 19.4253 | 3.3007 | 2.9538 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 6684 | 1 | 4 | 13.1707 | 18.0011 | 2.1261 | 2.7042 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 6685 | 1.6 | 2.5 | 12.5581 | 19.6634 | 3.1053 | 4 | 0.8 | 6.25 | 0.2 | 10 | 18.75
| 6686 | 1 | 4 | 14.2105 | 22.7414 | 3.0452 | 5.4857 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.8333
| 6687 | 1.2 | 3.3333 | 11.4894 | 18.833 | 2.4205 | 4.9231 | 1 | 5 | 0.1 | 20 | 28.3333
| 6688 | 0.8 | 5 | 18.6207 | 28.6159 | 4.177 | 5.8182 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 6689 | 0.8 | 5 | 12.2727 | 24.5414 | 3.1258 | 9.1429 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 6690 | 0.4 | 10 | 12.8571 | 18.9304 | 3.0256 | 3.0476 | 1 | 5 | 0.2 | 10 | 25
| 6691 | 0.8 | 5 | 10 | 17.993 | 4.3704 | 3.6226 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 6692 | 0.6 | 6.6667 | 14.2105 | 20.3362 | 2.6971 | 3.4286 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 6693 | 0.8 | 5 | 10.5882 | 18.698 | 2.7765 | 5.3333 | 1 | 5 | 0.4 | 5 | 15
| 6694 | 0.4 | 10 | 11.7391 | 18.0191 | 3.5758 | 2.7042 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 6695 | 1.2 | 3.3333 | 12.8571 | 20.3255 | 3.776 | 3.6923 | 1 | 5 | 0.2 | 10 | 18.3333
| 6696 | 1.2 | 3.3333 | 10.8 | 16.9869 | 3.2778 | 2.9091 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.1667
| 6697 | 0.6 | 6.6667 | 12.5581 | 18.2555 | 2.4974 | 3.2 | 0.4 | 12.5 | 0.8 | 2.5 | 21.6667
| 6698 | 0.6 | 6.6667 | 16.3636 | 20.8876 | 2.7126 | 1.8113 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 6699 | 0.4 | 10 | 8.5714 | 15.1896 | 3.4706 | 3.1475 | 1 | 5 | 0.8 | 2.5 | 17.5
| 6700 | 1.6 | 2.5 | 7.9412 | 16.8852 | 3.1258 | 5.8182 | 1.8 | 2.7778 | 0.2 | 10 | 15.2778
| 6701 | 0.8 | 5 | 12.8571 | 20.9349 | 3.2778 | 4.8 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 6702 | 1 | 4 | 10.8 | 22.7824 | 3.2552 | 8.7273 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 6703 | 0.4 | 10 | 10.1887 | 19.2072 | 3.3714 | 5.6471 | 1 | 5 | 0.4 | 5 | 20
| 6704 | 0.2 | 20 | 12.5581 | 19.9201 | 3.8065 | 3.5556 | 0.4 | 12.5 | 0.6 | 3.3333 | 35.8333
| 6705 | 1 | 4 | 13.5 | 19.5868 | 2.7765 | 3.3103 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 6706 | 1.2 | 3.3333 | 14.5946 | 22.6498 | 3.2552 | 4.8 | 0.4 | 12.5 | 0.4 | 5 | 20.8333
| 6707 | 1 | 4 | 12.8571 | 21.9113 | 2.8606 | 6.1935 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 6708 | 0.8 | 5 | 11.7391 | 22.0669 | 3.4706 | 6.8571 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 6709 | 0.8 | 5 | 16.875 | 24.3853 | 3.0452 | 4.4651 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 6710 | 1 | 4 | 11.7391 | 18.4551 | 3.3475 | 3.3684 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 6711 | 1 | 4 | 11.4894 | 17.9591 | 2.5514 | 3.9184 | 1 | 5 | 0.1 | 20 | 29
| 6712 | 0.6 | 6.6667 | 15 | 22.3392 | 3.7165 | 3.6226 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 6713 | 0.6 | 6.6667 | 12.5581 | 20.565 | 3.3239 | 4.6829 | 1 | 5 | 0.6 | 3.3333 | 15
| 6714 | 0.8 | 5 | 12.2727 | 18.905 | 2.4583 | 4.1739 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 6715 | 1.2 | 3.3333 | 11.7391 | 18.155 | 2.9873 | 3.4286 | 1 | 5 | 0.4 | 5 | 13.3333
| 6716 | 1.2 | 3.3333 | 13.5 | 19.8186 | 3.5758 | 2.7429 | 0.4 | 12.5 | 0.8 | 2.5 | 18.3333
| 6717 | 1.2 | 3.3333 | 10.5882 | 20.7947 | 3.8065 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 6718 | 0.8 | 5 | 13.8462 | 20.7242 | 2.7929 | 4.0851 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 6719 | 0.6 | 6.6667 | 12.2727 | 21.0595 | 2.9686 | 5.8182 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 6720 | 0.8 | 5 | 8.3077 | 15.0535 | 4.2523 | 2.4935 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 6721 | 1 | 4 | 12.5581 | 19.3029 | 2.8263 | 3.9184 | 1 | 5 | 0.1 | 20 | 29
| 6722 | 0.6 | 6.6667 | 15.8824 | 21.9616 | 2.9317 | 3.1475 | 1 | 5 | 0.4 | 5 | 16.6667
| 6723 | 0.6 | 6.6667 | 15 | 19.6782 | 2.4456 | 2.2326 | 1 | 5 | 0.4 | 5 | 16.6667
| 6724 | 0.1 | 40 | 9.4737 | 15.2261 | 2.8434 | 2.9091 | 0.8 | 6.25 | 0.4 | 5 | 51.25
| 6725 | 0.8 | 5 | 13.5 | 18.9807 | 2.7765 | 2.7042 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 6726 | 0.4 | 10 | 13.5 | 20.0526 | 2.7126 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 6727 | 0.8 | 5 | 20.7692 | 29.8408 | 2.878 | 6.1935 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 6728 | 0.6 | 6.6667 | 16.3636 | 23.1172 | 2.9136 | 3.84 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 6729 | 0.8 | 5 | 11.7391 | 20.1846 | 3.5224 | 4.9231 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 6730 | 0.8 | 5 | 16.875 | 23.8067 | 2.9317 | 4 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 6731 | 0.8 | 5 | 15 | 22.1996 | 3.0256 | 4.1739 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 6732 | 0.6 | 6.6667 | 12.8571 | 20.5042 | 2.3137 | 5.3333 | 1 | 5 | 0.2 | 10 | 21.6667
| 6733 | 1 | 4 | 9.4737 | 15.4815 | 2.5792 | 3.4286 | 1 | 5 | 0.4 | 5 | 14
| 6734 | 0.6 | 6.6667 | 10.8 | 17.8654 | 3.3007 | 3.7647 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 6735 | 0.8 | 5 | 15.4286 | 23.7195 | 4.2909 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 6736 | 0.6 | 6.6667 | 15.8824 | 24.7414 | 3.8065 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 6737 | 1.4 | 2.8571 | 14.2105 | 21.283 | 2.9873 | 4.0851 | 1.4 | 3.5714 | 0.2 | 10 | 16.4286
| 6738 | 0.6 | 6.6667 | 10 | 17.273 | 3.0064 | 4.2667 | 1 | 5 | 0.2 | 10 | 21.6667
| 6739 | 0.4 | 10 | 14.5946 | 21.8539 | 2.8957 | 4.3636 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 6740 | 0.8 | 5 | 13.5 | 23.8163 | 2.9317 | 7.3846 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 6741 | 1 | 4 | 13.1707 | 19.8385 | 3.0452 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 6742 | 0.8 | 5 | 12 | 19.0729 | 3.2329 | 3.84 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 6743 | 1 | 4 | 10.5882 | 18.0173 | 3.2552 | 4.1739 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 6744 | 1 | 4 | 10.5882 | 17.8271 | 3.0649 | 4.1739 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 6745 | 1.2 | 3.3333 | 9.6429 | 18.5647 | 2.7283 | 6.1935 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 6746 | 0.6 | 6.6667 | 12.8571 | 18.3703 | 3.4706 | 2.0426 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 6747 | 1.4 | 2.8571 | 11.4894 | 18.1445 | 3.746 | 2.9091 | 1 | 5 | 0.1 | 20 | 27.8571
| 6748 | 0.6 | 6.6667 | 11.4894 | 23.4718 | 3.2552 | 8.7273 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 6749 | 0.4 | 10 | 14.5946 | 21.4265 | 2.9136 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 6750 | 1 | 4 | 10.5882 | 15.9358 | 2.5241 | 2.8235 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 6751 | 0.6 | 6.6667 | 12 | 17.4999 | 3.0064 | 2.4935 | 0.4 | 12.5 | 0.8 | 2.5 | 21.6667
| 6752 | 1.2 | 3.3333 | 11.0204 | 17.3117 | 2.2913 | 4 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 6753 | 0.2 | 20 | 9.8182 | 16.4807 | 2.7442 | 3.9184 | 1 | 5 | 0.4 | 5 | 30
| 6754 | 0.8 | 5 | 10.5882 | 17.2288 | 3.085 | 3.5556 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 6755 | 0.8 | 5 | 9.3103 | 19.8319 | 3.9008 | 6.6207 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 6756 | 1.2 | 3.3333 | 9 | 16.5565 | 3.7165 | 3.84 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 6757 | 0.4 | 10 | 18 | 22.9837 | 2.8263 | 2.1573 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 6758 | 0.6 | 6.6667 | 13.5 | 20.0355 | 3.8689 | 2.6667 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 6759 | 1.4 | 2.8571 | 9.6429 | 18.6374 | 3.3475 | 5.6471 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 6760 | 0.4 | 10 | 11.0204 | 18.0929 | 2.9873 | 4.0851 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 6761 | 0.6 | 6.6667 | 10.1887 | 16.8683 | 2.9873 | 3.6923 | 1.6 | 3.125 | 0.4 | 5 | 14.7917
| 6762 | 1 | 4 | 15 | 19.8638 | 2.2692 | 2.5946 | 1 | 5 | 0.8 | 2.5 | 11.5
| 6763 | 0.8 | 5 | 13.5 | 23.9118 | 3.3007 | 7.1111 | 1 | 5 | 0.4 | 5 | 15
| 6764 | 0.8 | 5 | 13.1707 | 22.7511 | 3.9333 | 5.6471 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 6765 | 0.8 | 5 | 16.875 | 29.9974 | 3.5224 | 9.6 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 6766 | 1.2 | 3.3333 | 7.9412 | 19.374 | 3.085 | 8.3478 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 6767 | 0.6 | 6.6667 | 10.1887 | 17.6882 | 3.2329 | 4.2667 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 6768 | 1 | 4 | 10.3846 | 15.8282 | 2.3959 | 3.0476 | 1 | 5 | 0.2 | 10 | 19
| 6769 | 1.2 | 3.3333 | 11.7391 | 18.9744 | 2.9686 | 4.2667 | 1.4 | 3.5714 | 1 | 2 | 8.9048
| 6770 | 0.8 | 5 | 12 | 21.3194 | 3.1258 | 6.1935 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 6771 | 0.8 | 5 | 11.25 | 19.5452 | 2.8095 | 5.4857 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 6772 | 0.8 | 5 | 12 | 18.779 | 2.8606 | 3.9184 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 6773 | 0.8 | 5 | 9.3103 | 16.9985 | 3.6031 | 4.0851 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 6774 | 0.2 | 20 | 11.7391 | 20.0251 | 3.6031 | 4.6829 | 0.6 | 8.3333 | 0.2 | 10 | 38.3333
| 6775 | 1 | 4 | 10.1887 | 17.9534 | 4 | 3.7647 | 1 | 5 | 0.2 | 10 | 19
| 6776 | 0.1 | 40 | 12 | 19.0729 | 3.2329 | 3.84 | 0.8 | 6.25 | 0.2 | 10 | 56.25
| 6777 | 0.8 | 5 | 10.1887 | 16.2844 | 2.8957 | 3.2 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 6778 | 0.6 | 6.6667 | 9.3103 | 15.301 | 2.6222 | 3.3684 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 6779 | 0.2 | 20 | 11.4894 | 21.1154 | 4.1404 | 5.4857 | 0.6 | 8.3333 | 0.2 | 10 | 38.3333
| 6780 | 0.4 | 10 | 17.4194 | 25.5434 | 3.6589 | 4.4651 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 6781 | 0.6 | 6.6667 | 16.3636 | 21.4153 | 2.6517 | 2.4 | 1 | 5 | 0.4 | 5 | 16.6667
| 6782 | 0.4 | 10 | 18.6207 | 25.217 | 3.1678 | 3.4286 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 6783 | 0.8 | 5 | 12 | 19.4989 | 3.6589 | 3.84 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 6784 | 0.6 | 6.6667 | 10.1887 | 17.4053 | 2.95 | 4.2667 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 6785 | 0.8 | 5 | 10.5882 | 20.1967 | 2.4974 | 7.1111 | 1 | 5 | 0.2 | 10 | 20
| 6786 | 1.2 | 3.3333 | 13.5 | 22.3246 | 3.0064 | 5.8182 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 6787 | 0.2 | 20 | 9.3103 | 16.8418 | 3.1678 | 4.3636 | 1.4 | 3.5714 | 0.6 | 3.3333 | 26.9048
| 6788 | 0.8 | 5 | 11.25 | 17.4448 | 2.8263 | 3.3684 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 6789 | 0.6 | 6.6667 | 11.0204 | 18.2351 | 3.5224 | 3.6923 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 6790 | 0.8 | 5 | 19.2857 | 25.1959 | 2.0702 | 3.84 | 1 | 5 | 0.4 | 5 | 15
| 6791 | 1 | 4 | 9.6429 | 17.8857 | 4.069 | 4.1739 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 6792 | 0.4 | 10 | 13.5 | 27.0256 | 3.4203 | 10.1053 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 6793 | 1.2 | 3.3333 | 14.2105 | 23.0677 | 3.3714 | 5.4857 | 0.4 | 12.5 | 0.4 | 5 | 20.8333
| 6794 | 1.2 | 3.3333 | 15 | 24.1435 | 2.95 | 6.1935 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 6795 | 1 | 4 | 15 | 23.3121 | 2.8263 | 5.4857 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 6796 | 1.2 | 3.3333 | 11.7391 | 23.5313 | 3.0649 | 8.7273 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 6797 | 1.4 | 2.8571 | 10.8 | 18.2088 | 3.0452 | 4.3636 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 6798 | 0.2 | 20 | 12.5581 | 24.8612 | 3.5758 | 8.7273 | 0.8 | 6.25 | 0.2 | 10 | 36.25
| 6799 | 1.2 | 3.3333 | 7.2 | 11.9838 | 2.3838 | 2.4 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 6800 | 0.6 | 6.6667 | 12.8571 | 19.7679 | 2.4456 | 4.4651 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 6801 | 0.6 | 6.6667 | 12 | 18.4052 | 2.5652 | 3.84 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 6802 | 0.4 | 10 | 10.1887 | 17.971 | 3.2109 | 4.5714 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 6803 | 1.6 | 2.5 | 9.8182 | 17.5115 | 2.36 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 11.6667
| 6804 | 0.4 | 10 | 8.7097 | 15.8603 | 2.5792 | 4.5714 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 6805 | 0.8 | 5 | 11.0204 | 19.6578 | 3.8374 | 4.8 | 1 | 5 | 0.4 | 5 | 15
| 6806 | 0.4 | 10 | 12.2727 | 20.1327 | 3.4963 | 4.3636 | 1 | 5 | 0.2 | 10 | 25
| 6807 | 0.8 | 5 | 12.2727 | 19.453 | 3.0064 | 4.1739 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 6808 | 0.8 | 5 | 10 | 17.0452 | 3.0452 | 4 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 6809 | 1 | 4 | 13.1707 | 19.5297 | 2.6667 | 3.6923 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 6810 | 0.6 | 6.6667 | 14.5946 | 28.5373 | 3.8374 | 10.1053 | 1 | 5 | 0.4 | 5 | 16.6667
| 6811 | 1 | 4 | 10.3846 | 19.4388 | 2.8606 | 6.1935 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 6812 | 0.6 | 6.6667 | 19.2857 | 27.943 | 3.3239 | 5.3333 | 1 | 5 | 0.4 | 5 | 16.6667
| 6813 | 0.4 | 10 | 16.875 | 24.3729 | 3.3239 | 4.1739 | 1.6 | 3.125 | 0.2 | 10 | 23.125
| 6814 | 1 | 4 | 12 | 18.8875 | 3.6875 | 3.2 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 6815 | 0.8 | 5 | 11.4894 | 18.8962 | 3.2329 | 4.1739 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 6816 | 0.6 | 6.6667 | 14.5946 | 19.8777 | 3.1258 | 2.1573 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 6817 | 1.8 | 2.2222 | 9.3103 | 18.944 | 2.7765 | 6.8571 | 1 | 5 | 0.1 | 20 | 27.2222
| 6818 | 0.4 | 10 | 13.8462 | 19.9007 | 2.7442 | 3.3103 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 6819 | 0.8 | 5 | 10 | 18.5538 | 3.6308 | 4.9231 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 6820 | 0.6 | 6.6667 | 15.8824 | 24.0227 | 4.1404 | 4 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 6821 | 1.2 | 3.3333 | 9.1525 | 19.8652 | 2.7126 | 8 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 6822 | 0.4 | 10 | 12.2727 | 20.8612 | 3.2552 | 5.3333 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 6823 | 0.8 | 5 | 9.8182 | 16.4472 | 3.0064 | 3.6226 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 6824 | 1 | 4 | 10 | 16.6376 | 3.9333 | 2.7042 | 1.8 | 2.7778 | 0.2 | 10 | 16.7778
| 6825 | 0.8 | 5 | 12.8571 | 20.0243 | 2.4842 | 4.6829 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 6826 | 0.8 | 5 | 17.4194 | 24.132 | 2.7126 | 4 | 1 | 5 | 0.2 | 10 | 20
| 6827 | 0.8 | 5 | 10.5882 | 17.6769 | 3.3239 | 3.7647 | 0.2 | 25 | 0.2 | 10 | 40
| 6828 | 1.2 | 3.3333 | 10 | 18.4729 | 3.4203 | 5.0526 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 6829 | 1 | 4 | 11.4894 | 19.0347 | 2.6222 | 4.9231 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 6830 | 0.6 | 6.6667 | 12.5581 | 18.4506 | 2.5241 | 3.3684 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 6831 | 0.8 | 5 | 11.7391 | 19.4348 | 2.8957 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 6832 | 1.4 | 2.8571 | 12 | 16.8485 | 2.6667 | 2.1818 | 1 | 5 | 0.2 | 10 | 17.8571
| 6833 | 1 | 4 | 9.1525 | 16.3716 | 3.3007 | 3.9184 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 6834 | 1.2 | 3.3333 | 15.8824 | 23.019 | 2.5652 | 4.5714 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 6835 | 1.4 | 2.8571 | 20 | 26.5357 | 2.8434 | 3.6923 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 6836 | 0.6 | 6.6667 | 14.2105 | 19.6265 | 2.216 | 3.2 | 1 | 5 | 0.4 | 5 | 16.6667
| 6837 | 0.8 | 5 | 9.3103 | 16.6361 | 2.8606 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 6838 | 1.2 | 3.3333 | 11.7391 | 18.14 | 3.1467 | 3.2542 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 6839 | 1.2 | 3.3333 | 11.0204 | 18.4447 | 3.9333 | 3.4909 | 0.2 | 25 | 0.6 | 3.3333 | 31.6667
| 6840 | 1 | 4 | 12.2727 | 17.8779 | 3.0452 | 2.56 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 6841 | 1 | 4 | 16.875 | 23.9474 | 2.9873 | 4.0851 | 1 | 5 | 0.1 | 20 | 29
| 6842 | 0.6 | 6.6667 | 12 | 20.3834 | 2.5652 | 5.8182 | 1 | 5 | 0.6 | 3.3333 | 15
| 6843 | 1 | 4 | 15.8824 | 21.5356 | 2.7442 | 2.9091 | 2 | 2.5 | 0.6 | 3.3333 | 9.8333
| 6844 | 0.2 | 20 | 11.4894 | 21.3209 | 3.2109 | 6.6207 | 1 | 5 | 0.2 | 10 | 35
| 6845 | 1 | 4 | 12.2727 | 18.5587 | 3.1892 | 3.0968 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 6846 | 0.6 | 6.6667 | 13.8462 | 22.4235 | 2.3838 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 6847 | 0.6 | 6.6667 | 9.1525 | 17.6776 | 2.878 | 5.6471 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 6848 | 1.4 | 2.8571 | 12.2727 | 20.9325 | 3.4706 | 5.1892 | 1.4 | 3.5714 | 0.8 | 2.5 | 8.9286
| 6849 | 1 | 4 | 9.6429 | 15.9942 | 2.433 | 3.9184 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 6850 | 0.8 | 5 | 11.4894 | 19.568 | 3.3957 | 4.6829 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 6851 | 1.2 | 3.3333 | 10.8 | 16.614 | 2.4456 | 3.3684 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 6852 | 0.2 | 20 | 9.3103 | 15.1246 | 2.6667 | 3.1475 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 6853 | 1.2 | 3.3333 | 14.5946 | 27.1567 | 4.2143 | 8.3478 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 6854 | 0.6 | 6.6667 | 12.5581 | 20.2809 | 3.5489 | 4.1739 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 6855 | 1 | 4 | 12.8571 | 19.9445 | 2.6222 | 4.4651 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 6856 | 0.4 | 10 | 12.2727 | 17.9108 | 2.3838 | 3.2542 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 6857 | 1 | 4 | 8.3077 | 14.3455 | 3.2552 | 2.7826 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 6858 | 0.6 | 6.6667 | 11.4894 | 21.123 | 2.7765 | 6.8571 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 6859 | 0.6 | 6.6667 | 14.5946 | 22.6044 | 2.5241 | 5.4857 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 6860 | 0.2 | 20 | 7.8261 | 15.0136 | 3.3475 | 3.84 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 6861 | 0.4 | 10 | 14.2105 | 20.8358 | 2.8606 | 3.7647 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 6862 | 0.8 | 5 | 9.3103 | 19.1639 | 3.2329 | 6.6207 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 6863 | 1.2 | 3.3333 | 19.2857 | 26.2665 | 2.8957 | 4.0851 | 1 | 5 | 0.2 | 10 | 18.3333
| 6864 | 0.2 | 20 | 11.0204 | 16.6871 | 2.6667 | 3 | 1.6 | 3.125 | 0.6 | 3.3333 | 26.4583
| 6865 | 0.2 | 20 | 14.5946 | 20.9859 | 2.5514 | 3.84 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 6866 | 0.1 | 40 | 15.4286 | 23.2019 | 3.9333 | 3.84 | 1.4 | 3.5714 | 0.4 | 5 | 48.5714
| 6867 | 0.8 | 5 | 12 | 18.3294 | 3.4203 | 2.9091 | 1 | 5 | 0.8 | 2.5 | 12.5
| 6868 | 0.8 | 5 | 14.5946 | 23.9292 | 3.6875 | 5.6471 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 6869 | 1.2 | 3.3333 | 12.8571 | 23.1791 | 3.2109 | 7.1111 | 1.2 | 4.1667 | 0.1 | 20 | 27.5
| 6870 | 0.4 | 10 | 13.1707 | 19.3127 | 3.2329 | 2.9091 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 6871 | 0.4 | 10 | 11.7391 | 19.4742 | 3.3714 | 4.3636 | 1 | 5 | 0.2 | 10 | 25
| 6872 | 0.4 | 10 | 9.8182 | 18.1865 | 3.4453 | 4.9231 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 6873 | 0.6 | 6.6667 | 11.25 | 18.4614 | 3.3714 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 6874 | 0.4 | 10 | 11.0204 | 16.5517 | 2.6222 | 2.9091 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 6875 | 1.2 | 3.3333 | 12.8571 | 19.9739 | 2.6517 | 4.4651 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 6876 | 0.8 | 5 | 9.3103 | 15.6599 | 3.3957 | 2.9538 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 6877 | 0.8 | 5 | 13.8462 | 20.1082 | 2.4974 | 3.7647 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 6878 | 0.2 | 20 | 13.8462 | 20.6758 | 3.0649 | 3.7647 | 1 | 5 | 0.4 | 5 | 30
| 6879 | 1.4 | 2.8571 | 9.6429 | 18.9436 | 3.3007 | 6 | 1 | 5 | 0.2 | 10 | 17.8571
| 6880 | 1 | 4 | 11.4894 | 20.6831 | 2.3366 | 6.8571 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 6881 | 1.2 | 3.3333 | 16.875 | 27.6033 | 2.7283 | 8 | 1 | 5 | 0.2 | 10 | 18.3333
| 6882 | 0.4 | 10 | 12 | 18.9987 | 2.9136 | 4.0851 | 1 | 5 | 0.2 | 10 | 25
| 6883 | 1.2 | 3.3333 | 18.6207 | 24.791 | 3.5758 | 2.5946 | 0.4 | 12.5 | 0.2 | 10 | 25.8333
| 6884 | 1.6 | 2.5 | 16.875 | 25.604 | 3.3957 | 5.3333 | 0.8 | 6.25 | 0.2 | 10 | 18.75
| 6885 | 0.8 | 5 | 18 | 27.1929 | 2.7929 | 6.4 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 6886 | 0.8 | 5 | 13.5 | 23.2475 | 3.3475 | 6.4 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 6887 | 0.8 | 5 | 8.1818 | 16.1698 | 3.0649 | 4.9231 | 1.6 | 3.125 | 0.2 | 10 | 18.125
| 6888 | 1 | 4 | 11.4894 | 21.3131 | 2.7126 | 7.1111 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 6889 | 1.2 | 3.3333 | 11.0204 | 17.8269 | 3.8065 | 3 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 6890 | 0.6 | 6.6667 | 12.8571 | 19.3253 | 3.3714 | 3.0968 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 6891 | 1.2 | 3.3333 | 12 | 20.1376 | 3.085 | 5.0526 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 6892 | 0.6 | 6.6667 | 15 | 25.2065 | 3.8065 | 6.4 | 1 | 5 | 0.2 | 10 | 21.6667
| 6893 | 1.4 | 2.8571 | 9.6429 | 19.0241 | 2.5241 | 6.8571 | 1 | 5 | 0.4 | 5 | 12.8571
| 6894 | 0.8 | 5 | 10.5882 | 17.0089 | 2.7283 | 3.6923 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 6895 | 0.4 | 10 | 13.1707 | 19.9815 | 3.2552 | 3.5556 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 6896 | 0.4 | 10 | 15.4286 | 21.2045 | 2.7283 | 3.0476 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 6897 | 0.8 | 5 | 12.5581 | 24.5581 | 4 | 8 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 6898 | 0.8 | 5 | 8.1818 | 22.2855 | 2.8095 | 11.2941 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 6899 | 0.4 | 10 | 12.8571 | 20.4007 | 2.8606 | 4.6829 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 6900 | 0.8 | 5 | 12.5581 | 20.0067 | 3.085 | 4.3636 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 6901 | 0.4 | 10 | 12.8571 | 20.4171 | 2.6369 | 4.9231 | 1 | 5 | 0.4 | 5 | 20
| 6902 | 0.8 | 5 | 13.1707 | 21.963 | 3.6031 | 5.1892 | 1 | 5 | 0.2 | 10 | 20
| 6903 | 1.2 | 3.3333 | 10.1887 | 17.2057 | 2.4456 | 4.5714 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 6904 | 0.4 | 10 | 13.1707 | 19.8986 | 3.1053 | 3.6226 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 6905 | 1.4 | 2.8571 | 24.5455 | 31.8065 | 3.4963 | 3.7647 | 1 | 5 | 0.4 | 5 | 12.8571
| 6906 | 0.8 | 5 | 12 | 19.698 | 3.2329 | 4.4651 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 6907 | 0.6 | 6.6667 | 11.25 | 17.0492 | 2.6517 | 3.1475 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 6908 | 0.8 | 5 | 22.5 | 29.9291 | 3.2552 | 4.1739 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 6909 | 0.8 | 5 | 12.5581 | 18.5926 | 3.2109 | 2.8235 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 6910 | 0.6 | 6.6667 | 8.0597 | 13.8289 | 3.0649 | 2.7042 | 1 | 5 | 0.6 | 3.3333 | 15
| 6911 | 1.2 | 3.3333 | 15.4286 | 23.0251 | 2.9136 | 4.6829 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 6912 | 1.6 | 2.5 | 12.2727 | 25.1222 | 2.7442 | 10.1053 | 1 | 5 | 0.6 | 3.3333 | 10.8333
| 6913 | 1 | 4 | 9.4737 | 16.202 | 2.7283 | 4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 6914 | 1.2 | 3.3333 | 15 | 22.1366 | 2.5652 | 4.5714 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 6915 | 0.4 | 10 | 12.2727 | 20.6816 | 3.8374 | 4.5714 | 1 | 5 | 0.4 | 5 | 20
| 6916 | 0.8 | 5 | 10.8 | 18.842 | 3.4706 | 4.5714 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 6917 | 1.2 | 3.3333 | 12 | 18.8744 | 2.6077 | 4.2667 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 6918 | 0.4 | 10 | 11.25 | 18.9703 | 3.2552 | 4.4651 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 6919 | 1.6 | 2.5 | 10.5882 | 19.2743 | 4.7677 | 3.9184 | 1.4 | 3.5714 | 0.4 | 5 | 11.0714
| 6920 | 0.8 | 5 | 14.2105 | 20.7511 | 2.6222 | 3.9184 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 6921 | 1 | 4 | 10.3846 | 15.0422 | 2.3719 | 2.2857 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 6922 | 0.1 | 40 | 14.5946 | 25.6221 | 3.3475 | 7.68 | 0.8 | 6.25 | 0.4 | 5 | 51.25
| 6923 | 0.8 | 5 | 10 | 19.5224 | 3.5224 | 6 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 6924 | 0.8 | 5 | 12.5581 | 17.7035 | 2.0978 | 3.0476 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 6925 | 0.4 | 10 | 14.2105 | 22.8059 | 2.1953 | 6.4 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 6926 | 0.8 | 5 | 11.7391 | 18.1106 | 3.3714 | 3 | 1 | 5 | 0.8 | 2.5 | 12.5
| 6927 | 0.4 | 10 | 9.1525 | 22.8449 | 3.0256 | 10.6667 | 1 | 5 | 0.2 | 10 | 25
| 6928 | 0.4 | 10 | 17.4194 | 23.6632 | 3.4203 | 2.8235 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 6929 | 1 | 4 | 12.8571 | 20.8707 | 4.866 | 3.1475 | 1 | 5 | 0.2 | 10 | 19
| 6930 | 0.4 | 10 | 11.7391 | 19.1877 | 3.085 | 4.3636 | 1 | 5 | 0.2 | 10 | 25
| 6931 | 1 | 4 | 13.1707 | 20.0308 | 3.1678 | 3.6923 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 6932 | 0.4 | 10 | 11.0204 | 17.4001 | 3.4706 | 2.9091 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 6933 | 1 | 4 | 16.875 | 23.4088 | 3.1053 | 3.4286 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 6934 | 0.6 | 6.6667 | 11.0204 | 16.8897 | 2.3137 | 3.5556 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 6935 | 1 | 4 | 12.2727 | 20.4684 | 3.3957 | 4.8 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 6936 | 0.8 | 5 | 12 | 19.0163 | 3.3239 | 3.6923 | 1.6 | 3.125 | 0.8 | 2.5 | 10.625
| 6937 | 0.6 | 6.6667 | 9.8182 | 16.1291 | 3.4453 | 2.8657 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 6938 | 1.2 | 3.3333 | 9.4737 | 18.461 | 2.9873 | 6 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 6939 | 0.6 | 6.6667 | 10.1887 | 15.3209 | 2.5376 | 2.5946 | 1 | 5 | 0.6 | 3.3333 | 15
| 6940 | 0.6 | 6.6667 | 13.1707 | 20.5124 | 3.1678 | 4.1739 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 6941 | 1.4 | 2.8571 | 12.2727 | 19.6815 | 3.0452 | 4.3636 | 0.4 | 12.5 | 0.6 | 3.3333 | 18.6905
| 6942 | 1.2 | 3.3333 | 13.8462 | 20.4286 | 2.4974 | 4.0851 | 1 | 5 | 0.2 | 10 | 18.3333
| 6943 | 0.8 | 5 | 9.1525 | 16.0887 | 3.4453 | 3.4909 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 6944 | 0.8 | 5 | 12.8571 | 19.3142 | 3.1467 | 3.3103 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 6945 | 0.8 | 5 | 12.5581 | 20.0896 | 3.1678 | 4.3636 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 6946 | 1 | 4 | 13.1707 | 20.1173 | 3.3239 | 3.6226 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 6947 | 1.2 | 3.3333 | 10.5882 | 17.6334 | 3.0452 | 4 | 1 | 5 | 0.2 | 10 | 18.3333
| 6948 | 0.8 | 5 | 13.8462 | 20.9496 | 2.4205 | 4.6829 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 6949 | 1.2 | 3.3333 | 13.8462 | 24.7962 | 2.95 | 8 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 6950 | 0.8 | 5 | 8.5714 | 16.1418 | 3.1053 | 4.4651 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 6951 | 0.6 | 6.6667 | 11.4894 | 16.9088 | 2.6369 | 2.7826 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 6952 | 0.8 | 5 | 12.5581 | 19.919 | 2.8957 | 4.4651 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 6953 | 0.4 | 10 | 14.5946 | 23.8527 | 4.069 | 5.1892 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 6954 | 1.2 | 3.3333 | 16.3636 | 23.4365 | 2.6077 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 6955 | 0.4 | 10 | 11.7391 | 21.4816 | 3.5489 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 6956 | 1 | 4 | 10.1887 | 16.866 | 2.3137 | 4.3636 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.8333
| 6957 | 0.8 | 5 | 11.0204 | 18.0629 | 3.2778 | 3.7647 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 6958 | 0.8 | 5 | 12.8571 | 23.0618 | 3.3475 | 6.8571 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 6959 | 0.6 | 6.6667 | 11.4894 | 19.5571 | 3.4963 | 4.5714 | 1 | 5 | 0.4 | 5 | 16.6667
| 6960 | 1.2 | 3.3333 | 7.9412 | 14.3165 | 3.0649 | 3.3103 | 0.4 | 12.5 | 0.2 | 10 | 25.8333
| 6961 | 1.4 | 2.8571 | 13.1707 | 20.7465 | 3.5758 | 4 | 0.8 | 6.25 | 0.8 | 2.5 | 11.6071
| 6962 | 0.6 | 6.6667 | 7.5 | 22.8239 | 3.3239 | 12 | 1 | 5 | 0.6 | 3.3333 | 15
| 6963 | 1.4 | 2.8571 | 13.1707 | 24.7592 | 2.4456 | 9.1429 | 1 | 5 | 0.4 | 5 | 12.8571
| 6964 | 1.4 | 2.8571 | 15 | 23.5077 | 2.8606 | 5.6471 | 1 | 5 | 0.8 | 2.5 | 10.3571
| 6965 | 1 | 4 | 11.0204 | 19.881 | 2.8606 | 6 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 6966 | 0.6 | 6.6667 | 11.4894 | 18.0901 | 3.0452 | 3.5556 | 0.6 | 8.3333 | 0.1 | 20 | 35
| 6967 | 0.8 | 5 | 11.4894 | 18.78 | 2.6077 | 4.6829 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 6968 | 1 | 4 | 13.1707 | 20.5124 | 3.1678 | 4.1739 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 6969 | 0.2 | 20 | 9.1525 | 16.0967 | 3.5758 | 3.3684 | 1 | 5 | 0.2 | 10 | 35
| 6970 | 0.8 | 5 | 12.2727 | 19.5958 | 3.6308 | 3.6923 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 6971 | 0.8 | 5 | 11.4894 | 17.4214 | 3.1892 | 2.7429 | 1 | 5 | 0.4 | 5 | 15
| 6972 | 0.6 | 6.6667 | 18 | 25.9132 | 2.8606 | 5.0526 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 6973 | 0.6 | 6.6667 | 15 | 22.7326 | 2.8095 | 4.9231 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 6974 | 0.8 | 5 | 13.5 | 20.1678 | 3.0452 | 3.6226 | 1 | 5 | 0.4 | 5 | 15
| 6975 | 0.6 | 6.6667 | 13.1707 | 18.3461 | 2.6818 | 2.4935 | 1 | 5 | 0.4 | 5 | 16.6667
| 6976 | 0.8 | 5 | 9.8182 | 15.8103 | 2.6818 | 3.3103 | 1 | 5 | 0.2 | 10 | 20
| 6977 | 0.6 | 6.6667 | 10 | 16.4027 | 3.2552 | 3.1475 | 1 | 5 | 0.6 | 3.3333 | 15
| 6978 | 0.4 | 10 | 12 | 21.726 | 3.1053 | 6.6207 | 1 | 5 | 0.4 | 5 | 20
| 6979 | 0.4 | 10 | 10 | 17.988 | 3.0649 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 6980 | 0.6 | 6.6667 | 13.8462 | 21.7183 | 3.3007 | 4.5714 | 0.2 | 25 | 0.4 | 5 | 36.6667
| 6981 | 0.8 | 5 | 12.5581 | 19.6455 | 2.6222 | 4.4651 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 6982 | 0.8 | 5 | 12.5581 | 19.9167 | 4.1043 | 3.2542 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 6983 | 1.4 | 2.8571 | 15 | 21.457 | 3.1467 | 3.3103 | 1.4 | 3.5714 | 0.2 | 10 | 16.4286
| 6984 | 0.8 | 5 | 13.1707 | 21.3285 | 2.9686 | 5.1892 | 1 | 5 | 0.4 | 5 | 15
| 6985 | 1 | 4 | 11.4894 | 18.5836 | 4.1404 | 2.9538 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 6986 | 1.2 | 3.3333 | 9.4737 | 19.4183 | 3.3239 | 6.6207 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 6987 | 1.2 | 3.3333 | 10.1887 | 17.7917 | 3.6031 | 4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 6988 | 1.2 | 3.3333 | 11.7391 | 17.7495 | 3.5489 | 2.4615 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 6989 | 1.2 | 3.3333 | 15.8824 | 23.8768 | 3.6308 | 4.3636 | 0.4 | 12.5 | 0.2 | 10 | 25.8333
| 6990 | 0.6 | 6.6667 | 16.3636 | 25.8554 | 2.1071 | 7.3846 | 1 | 5 | 0.2 | 10 | 21.6667
| 6991 | 1.2 | 3.3333 | 11.0204 | 17.7561 | 2.8957 | 3.84 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 6992 | 0.6 | 6.6667 | 12.2727 | 21.025 | 3.1053 | 5.6471 | 1 | 5 | 0.2 | 10 | 21.6667
| 6993 | 1 | 4 | 12.2727 | 19.9172 | 3.4706 | 4.1739 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 6994 | 0.8 | 5 | 13.1707 | 18.574 | 2.5376 | 2.8657 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 6995 | 0.2 | 20 | 8.8525 | 15.4074 | 3.3007 | 3.2542 | 1 | 5 | 0.4 | 5 | 30
| 6996 | 0.4 | 10 | 9.3103 | 16.6027 | 3.0256 | 4.2667 | 1 | 5 | 0.4 | 5 | 20
| 6997 | 0.8 | 5 | 11.0204 | 18.8333 | 2.7602 | 5.0526 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 6998 | 0.2 | 20 | 9.4737 | 15.6766 | 3.4203 | 2.7826 | 1 | 5 | 0.2 | 10 | 35
| 6999 | 0.4 | 10 | 13.5 | 19.6379 | 2.4456 | 3.6923 | 1.6 | 3.125 | 0.2 | 10 | 23.125
| 7000 | 0.4 | 10 | 14.5946 | 24.4149 | 3.4203 | 6.4 | 1 | 5 | 0.2 | 10 | 25
| 7001 | 1 | 4 | 9.3103 | 15.8316 | 3.2109 | 3.3103 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 7002 | 0.6 | 6.6667 | 14.5946 | 20.7725 | 2.8095 | 3.3684 | 1 | 5 | 0.6 | 3.3333 | 15
| 7003 | 0.6 | 6.6667 | 9.1525 | 20.1867 | 4.177 | 6.8571 | 1 | 5 | 0.2 | 10 | 21.6667
| 7004 | 1.2 | 3.3333 | 9.4737 | 14.8397 | 2.2692 | 3.0968 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 7005 | 0.6 | 6.6667 | 13.1707 | 21.8153 | 2.8263 | 5.8182 | 1 | 5 | 0.2 | 10 | 21.6667
| 7006 | 1 | 4 | 12.8571 | 19.9606 | 2.4205 | 4.6829 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 7007 | 0.8 | 5 | 9.6429 | 16.6537 | 2.7442 | 4.2667 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 7008 | 0.2 | 20 | 12.5581 | 19.8688 | 2.5106 | 4.8 | 0.8 | 6.25 | 0.1 | 20 | 46.25
| 7009 | 0.4 | 10 | 14.2105 | 21.1155 | 3.0649 | 3.84 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 7010 | 1 | 4 | 12.8571 | 18.6979 | 2.9317 | 2.9091 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 7011 | 0.6 | 6.6667 | 16.3636 | 23.07 | 3.2778 | 3.4286 | 1 | 5 | 0.1 | 20 | 31.6667
| 7012 | 0.8 | 5 | 13.5 | 20.2006 | 2.8606 | 3.84 | 1 | 5 | 0.4 | 5 | 15
| 7013 | 1 | 4 | 11.25 | 18.9106 | 2.8606 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7014 | 0.8 | 5 | 9 | 15.8251 | 2.36 | 4.4651 | 1 | 5 | 0.4 | 5 | 15
| 7015 | 0.6 | 6.6667 | 12.2727 | 20.8612 | 3.2552 | 5.3333 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 7016 | 0.6 | 6.6667 | 15.8824 | 22.3555 | 3.8065 | 2.6667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 7017 | 1.4 | 2.8571 | 11.4894 | 22.5408 | 3.3714 | 7.68 | 0.8 | 6.25 | 1 | 2 | 11.1071
| 7018 | 0.8 | 5 | 13.5 | 22.1966 | 3.2109 | 5.4857 | 1 | 5 | 0.1 | 20 | 30
| 7019 | 0.6 | 6.6667 | 10.8 | 15.768 | 2.5376 | 2.4304 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 7020 | 1 | 4 | 12 | 20.2635 | 3.2109 | 5.0526 | 1 | 5 | 0.2 | 10 | 19
| 7021 | 0.8 | 5 | 14.2105 | 20.9077 | 2.6971 | 4 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 7022 | 0.6 | 6.6667 | 10.1887 | 17.2341 | 2.6818 | 4.3636 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 7023 | 0.4 | 10 | 11.0204 | 21.7073 | 3.5758 | 7.1111 | 1 | 5 | 0.2 | 10 | 25
| 7024 | 1 | 4 | 12.2727 | 18.2346 | 2.5934 | 3.3684 | 1 | 5 | 0.1 | 20 | 29
| 7025 | 0.6 | 6.6667 | 10.5882 | 19.3842 | 2.3959 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 7026 | 1 | 4 | 13.8462 | 24.0403 | 2.8095 | 7.3846 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 7027 | 0.8 | 5 | 9.6429 | 16.8412 | 2.9317 | 4.2667 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 7028 | 1.2 | 3.3333 | 12.5581 | 19.87 | 3.0452 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 7029 | 1 | 4 | 15.4286 | 22.1643 | 2.8957 | 3.84 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 7030 | 0.6 | 6.6667 | 20.7692 | 28.0302 | 3.4963 | 3.7647 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 7031 | 0.8 | 5 | 13.1707 | 19.6277 | 3.1467 | 3.3103 | 1 | 5 | 0.4 | 5 | 15
| 7032 | 1 | 4 | 18 | 23.8299 | 3.0064 | 2.8235 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 7033 | 0.8 | 5 | 15.4286 | 23.1843 | 3.8374 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 7034 | 1 | 4 | 10.5882 | 16.7331 | 2.7765 | 3.3684 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 7035 | 0.8 | 5 | 13.8462 | 23.4139 | 3.1678 | 6.4 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 7036 | 1 | 4 | 14.5946 | 24.6557 | 2.95 | 7.1111 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 7037 | 0.1 | 40 | 9.3103 | 17.2587 | 2.8957 | 5.0526 | 1.4 | 3.5714 | 0.4 | 5 | 48.5714
| 7038 | 0.4 | 10 | 10.8 | 19.1359 | 3.1467 | 5.1892 | 1 | 5 | 0.1 | 20 | 35
| 7039 | 0.8 | 5 | 14.5946 | 21.0488 | 3.0256 | 3.4286 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 7040 | 0.4 | 10 | 14.5946 | 22.3969 | 2.1553 | 5.6471 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 7041 | 0.4 | 10 | 9.4737 | 16.9254 | 2.6517 | 4.8 | 1.6 | 3.125 | 0.4 | 5 | 18.125
| 7042 | 0.8 | 5 | 14.2105 | 24.6561 | 2.4456 | 8 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 7043 | 0.6 | 6.6667 | 11.4894 | 22.4933 | 3.3239 | 7.68 | 1 | 5 | 0.2 | 10 | 21.6667
| 7044 | 0.8 | 5 | 12 | 18.6517 | 2.6517 | 4 | 1 | 5 | 0.4 | 5 | 15
| 7045 | 0.4 | 10 | 11.7391 | 19.0344 | 2.9317 | 4.3636 | 1 | 5 | 0.4 | 5 | 20
| 7046 | 1.4 | 2.8571 | 11.25 | 20.6186 | 2.9686 | 6.4 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 7047 | 1.2 | 3.3333 | 10 | 17.2191 | 3.3007 | 3.9184 | 1 | 5 | 0.4 | 5 | 13.3333
| 7048 | 0.8 | 5 | 13.1707 | 18.7967 | 2.8434 | 2.7826 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 7049 | 0.6 | 6.6667 | 10.1887 | 16.7894 | 3.0452 | 3.5556 | 1 | 5 | 1 | 2 | 13.6667
| 7050 | 1.2 | 3.3333 | 15.8824 | 22.7836 | 2.5376 | 4.3636 | 1 | 5 | 0.1 | 20 | 28.3333
| 7051 | 0.4 | 10 | 15 | 22.7823 | 3.2109 | 4.5714 | 0.6 | 8.3333 | 0.1 | 20 | 38.3333
| 7052 | 0.4 | 10 | 11.0204 | 19.9324 | 2.2913 | 6.6207 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 7053 | 0.8 | 5 | 8.7097 | 16.7586 | 3.1258 | 4.9231 | 1 | 5 | 0.2 | 10 | 20
| 7054 | 0.6 | 6.6667 | 15.4286 | 25.3096 | 3.6875 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 7055 | 0.6 | 6.6667 | 16.3636 | 22.4797 | 2.9686 | 3.1475 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 7056 | 1 | 4 | 11.0204 | 17.4694 | 2.8263 | 3.6226 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 7057 | 1 | 4 | 16.875 | 24.3021 | 2.7442 | 4.6829 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7058 | 0.2 | 20 | 12 | 18.777 | 2.2056 | 4.5714 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 7059 | 0.6 | 6.6667 | 15.8824 | 22.881 | 2.9136 | 4.0851 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 7060 | 0.6 | 6.6667 | 8.4375 | 14.5536 | 2.9686 | 3.1475 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 7061 | 0.4 | 10 | 10 | 16.3045 | 2.6818 | 3.6226 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 7062 | 0.8 | 5 | 17.4194 | 26.2974 | 2.878 | 6 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 7063 | 0.8 | 5 | 13.1707 | 24.0006 | 3.4453 | 7.3846 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 7064 | 0.8 | 5 | 8.5714 | 15.9782 | 3.2329 | 4.1739 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 7065 | 0.2 | 20 | 11.0204 | 20.8089 | 3.1678 | 6.6207 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 7066 | 1 | 4 | 15 | 21.6626 | 2.7442 | 3.9184 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.8333
| 7067 | 0.8 | 5 | 11.25 | 19.841 | 3.1053 | 5.4857 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 7068 | 1 | 4 | 12 | 19.3889 | 3.5489 | 3.84 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 7069 | 1.2 | 3.3333 | 10.3846 | 16.6455 | 3.6308 | 2.6301 | 1 | 5 | 0.2 | 10 | 18.3333
| 7070 | 0.8 | 5 | 18 | 23.8911 | 2.6369 | 3.2542 | 1 | 5 | 0.4 | 5 | 15
| 7071 | 0.8 | 5 | 9.6429 | 16.1669 | 2.5241 | 4 | 0.4 | 12.5 | 0.1 | 20 | 37.5
| 7072 | 0.8 | 5 | 12.8571 | 20.8254 | 3.0452 | 4.9231 | 1 | 5 | 0.1 | 20 | 30
| 7073 | 0.4 | 10 | 14.5946 | 21.2742 | 2.9873 | 3.6923 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 7074 | 0.6 | 6.6667 | 10.1887 | 18.388 | 3.1467 | 5.0526 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 7075 | 1 | 4 | 12.8571 | 21.4322 | 3.5224 | 5.0526 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 7076 | 0.2 | 20 | 9.6429 | 17.8276 | 2.5376 | 5.6471 | 0.6 | 8.3333 | 0.4 | 5 | 33.3333
| 7077 | 0.8 | 5 | 10.1887 | 18.7314 | 2.8957 | 5.6471 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 7078 | 0.4 | 10 | 10 | 17.5588 | 2.9873 | 4.5714 | 1 | 5 | 0.2 | 10 | 25
| 7079 | 0.8 | 5 | 15.4286 | 24.6424 | 3.3957 | 5.8182 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 7080 | 1 | 4 | 9.3103 | 24.9347 | 4.3303 | 11.2941 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7081 | 0.8 | 5 | 14.5946 | 23.5509 | 3.4706 | 5.4857 | 1 | 5 | 0.2 | 10 | 20
| 7082 | 1 | 4 | 15 | 22.3687 | 3.746 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7083 | 1 | 4 | 10.5882 | 16.3485 | 2.7602 | 3 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 7084 | 0.8 | 5 | 9 | 17.8472 | 4.6733 | 4.1739 | 1 | 5 | 0.4 | 5 | 15
| 7085 | 0.2 | 20 | 12.5581 | 20.909 | 4.177 | 4.1739 | 1.2 | 4.1667 | 0.6 | 3.3333 | 27.5
| 7086 | 0.6 | 6.6667 | 14.5946 | 24.5869 | 2.6077 | 7.3846 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 7087 | 0.6 | 6.6667 | 7.8261 | 14.7714 | 3.1053 | 3.84 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 7088 | 0.4 | 10 | 13.1707 | 18.5823 | 3.1258 | 2.2857 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 7089 | 0.8 | 5 | 15 | 21.2566 | 3.3475 | 2.9091 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 7090 | 0.6 | 6.6667 | 12.2727 | 19.7486 | 2.7929 | 4.6829 | 1 | 5 | 0.4 | 5 | 16.6667
| 7091 | 0.6 | 6.6667 | 13.8462 | 20.9713 | 2.3251 | 4.8 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 7092 | 0.6 | 6.6667 | 28.4211 | 38.0453 | 4.2909 | 5.3333 | 0.6 | 8.3333 | 0.1 | 20 | 35
| 7093 | 0.6 | 6.6667 | 12.5581 | 20.8274 | 2.6222 | 5.6471 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 7094 | 0.6 | 6.6667 | 21.6 | 27.3929 | 2.7929 | 3 | 1 | 5 | 0.6 | 3.3333 | 15
| 7095 | 0.6 | 6.6667 | 12.2727 | 21.109 | 3.1892 | 5.6471 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 7096 | 0.4 | 10 | 13.8462 | 20.2876 | 3.5758 | 2.8657 | 1.4 | 3.5714 | 0.8 | 2.5 | 16.0714
| 7097 | 0.4 | 10 | 9.4737 | 16.6696 | 2.3959 | 4.8 | 1 | 5 | 0.4 | 5 | 20
| 7098 | 0.8 | 5 | 14.5946 | 20.4633 | 3.0452 | 2.8235 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 7099 | 0.8 | 5 | 13.1707 | 22.2667 | 3.2778 | 5.8182 | 1.6 | 3.125 | 0.6 | 3.3333 | 11.4583
| 7100 | 0.6 | 6.6667 | 12.2727 | 18.353 | 2.6517 | 3.4286 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 7101 | 1 | 4 | 12.8571 | 18.6039 | 2.7929 | 2.9538 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 7102 | 0.6 | 6.6667 | 12.5581 | 19.8884 | 4.3303 | 3 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 7103 | 1 | 4 | 12 | 21.7888 | 2.9317 | 6.8571 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 7104 | 1.4 | 2.8571 | 12.2727 | 18.0175 | 2.6971 | 3.0476 | 1 | 5 | 0.2 | 10 | 17.8571
| 7105 | 1.2 | 3.3333 | 12.8571 | 21.1264 | 2.6222 | 5.6471 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 7106 | 0.6 | 6.6667 | 11.7391 | 18.9004 | 2.9873 | 4.1739 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 7107 | 1 | 4 | 6.8354 | 18.8708 | 3.6875 | 8.3478 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 7108 | 1.4 | 2.8571 | 10.8 | 18.2432 | 2.7602 | 4.6829 | 0.6 | 8.3333 | 0.6 | 3.3333 | 14.5238
| 7109 | 1 | 4 | 14.2105 | 19.7723 | 2.9317 | 2.6301 | 1 | 5 | 0.1 | 20 | 29
| 7110 | 0.6 | 6.6667 | 12.8571 | 20.8 | 3.3714 | 4.5714 | 1 | 5 | 0.6 | 3.3333 | 15
| 7111 | 1 | 4 | 10.8 | 18.058 | 2.7929 | 4.4651 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 7112 | 0.6 | 6.6667 | 10.3846 | 18.2338 | 3.2778 | 4.5714 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 7113 | 0.4 | 10 | 11.7391 | 19.86 | 2.9317 | 5.1892 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 7114 | 1 | 4 | 13.5 | 20.4093 | 2.2264 | 4.6829 | 1 | 5 | 0.4 | 5 | 14
| 7115 | 0.6 | 6.6667 | 6.9231 | 14.1619 | 3.0649 | 4.1739 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 7116 | 1 | 4 | 11.0204 | 16.7652 | 2.6971 | 3.0476 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 7117 | 1.4 | 2.8571 | 16.3636 | 23.2809 | 3.5489 | 3.3684 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 7118 | 1.6 | 2.5 | 12.5581 | 19.0414 | 2.8606 | 3.6226 | 1.2 | 4.1667 | 0.8 | 2.5 | 9.1667
| 7119 | 0.4 | 10 | 12.5581 | 20.4435 | 3.4203 | 4.4651 | 1 | 5 | 0.4 | 5 | 20
| 7120 | 0.8 | 5 | 10.1887 | 18.5094 | 2.9873 | 5.3333 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 7121 | 0.8 | 5 | 11.7391 | 19.7391 | 2.6667 | 5.3333 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 7122 | 0.4 | 10 | 8.8525 | 18.0146 | 2.9686 | 6.1935 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 7123 | 1 | 4 | 10.1887 | 16.814 | 2.8606 | 3.7647 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 7124 | 1 | 4 | 10.5882 | 20.4891 | 3.9008 | 6 | 1 | 5 | 0.4 | 5 | 14
| 7125 | 1.2 | 3.3333 | 9.3103 | 17.6066 | 3.4963 | 4.8 | 1.4 | 3.5714 | 0.1 | 20 | 26.9048
| 7126 | 0.8 | 5 | 13.8462 | 20.1282 | 2.9136 | 3.3684 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 7127 | 0.4 | 10 | 15.4286 | 26.1607 | 3.3475 | 7.3846 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 7128 | 0.6 | 6.6667 | 10.5882 | 19.536 | 3.3007 | 5.6471 | 1 | 5 | 0.1 | 20 | 31.6667
| 7129 | 1.4 | 2.8571 | 15.4286 | 22.4522 | 3.1053 | 3.9184 | 0.8 | 6.25 | 0.1 | 20 | 29.1071
| 7130 | 0.4 | 10 | 10.8 | 17.4614 | 3.2329 | 3.4286 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 7131 | 1.2 | 3.3333 | 12 | 19.4026 | 4.0342 | 3.3684 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 7132 | 1 | 4 | 16.875 | 23.2703 | 3.085 | 3.3103 | 1 | 5 | 0.1 | 20 | 29
| 7133 | 0.8 | 5 | 16.3636 | 22.7103 | 3.7165 | 2.6301 | 1 | 5 | 0.4 | 5 | 15
| 7134 | 0.4 | 10 | 12.5581 | 18.2774 | 2.8957 | 2.8235 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 7135 | 1 | 4 | 10.3846 | 17.2859 | 2.5376 | 4.3636 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 7136 | 1.2 | 3.3333 | 15.4286 | 23.9399 | 3.0256 | 5.4857 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 7137 | 0.6 | 6.6667 | 13.8462 | 22.9311 | 3.085 | 6 | 1 | 5 | 0.6 | 3.3333 | 15
| 7138 | 0.2 | 20 | 12.8571 | 19.5176 | 2.8957 | 3.7647 | 1.4 | 3.5714 | 0.2 | 10 | 33.5714
| 7139 | 1.2 | 3.3333 | 12 | 17.9085 | 3.085 | 2.8235 | 1.2 | 4.1667 | 0.1 | 20 | 27.5
| 7140 | 0.4 | 10 | 14.5946 | 21.0516 | 2.3719 | 4.0851 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 7141 | 0.1 | 40 | 11.25 | 19.9819 | 5.3034 | 3.4286 | 1.4 | 3.5714 | 0.6 | 3.3333 | 46.9048
| 7142 | 1 | 4 | 11.7391 | 19.8567 | 3.0649 | 5.0526 | 1 | 5 | 0.4 | 5 | 14
| 7143 | 1.6 | 2.5 | 9 | 17.1745 | 3.6031 | 4.5714 | 1.2 | 4.1667 | 0.1 | 20 | 26.6667
| 7144 | 0.6 | 6.6667 | 11.0204 | 17.0553 | 3.1258 | 2.9091 | 1.6 | 3.125 | 0.6 | 3.3333 | 13.125
| 7145 | 1 | 4 | 18.6207 | 26.9357 | 3.1258 | 5.1892 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 7146 | 0.8 | 5 | 11.0204 | 22.9975 | 4.866 | 7.1111 | 1 | 5 | 0.4 | 5 | 15
| 7147 | 0.4 | 10 | 15 | 22.988 | 3.0649 | 4.9231 | 1.4 | 3.5714 | 0.1 | 20 | 33.5714
| 7148 | 1.2 | 3.3333 | 14.5946 | 25.1684 | 3.1892 | 7.3846 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 7149 | 1.4 | 2.8571 | 7.1053 | 15.3256 | 3.4203 | 4.8 | 1.2 | 4.1667 | 0.1 | 20 | 27.0238
| 7150 | 0.4 | 10 | 12.2727 | 23.8868 | 2.4712 | 9.1429 | 0.4 | 12.5 | 0.8 | 2.5 | 25
| 7151 | 0.4 | 10 | 14.5946 | 24.9115 | 2.6369 | 7.68 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 7152 | 1.2 | 3.3333 | 12.2727 | 18.2634 | 2.6222 | 3.3684 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 7153 | 1 | 4 | 14.2105 | 22.4558 | 3.4453 | 4.8 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 7154 | 0.8 | 5 | 14.2105 | 21.1468 | 2.4712 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 7155 | 1 | 4 | 10.3846 | 16.6018 | 2.0433 | 4.1739 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 7156 | 0.8 | 5 | 11.25 | 20.6373 | 2.9873 | 6.4 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 7157 | 1.2 | 3.3333 | 12.5581 | 21.351 | 2.7929 | 6 | 1 | 5 | 0.2 | 10 | 18.3333
| 7158 | 0.8 | 5 | 10.5882 | 21.5759 | 3.6031 | 7.3846 | 1 | 5 | 0.4 | 5 | 15
| 7159 | 1 | 4 | 11.7391 | 19.2494 | 3.0452 | 4.4651 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 7160 | 0.4 | 10 | 8.8525 | 14.9556 | 3.0064 | 3.0968 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 7161 | 0.4 | 10 | 15.8824 | 23.614 | 2.9317 | 4.8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 7162 | 1 | 4 | 15.4286 | 22.1131 | 2.5106 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 7163 | 0.2 | 20 | 11.25 | 19.8656 | 2.9686 | 5.6471 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 7164 | 1.2 | 3.3333 | 12.5581 | 23.3142 | 3.3714 | 7.3846 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.1667
| 7165 | 0.8 | 5 | 14.5946 | 22.0102 | 2.2264 | 5.1892 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 7166 | 0.6 | 6.6667 | 9.8182 | 15.7975 | 2.9317 | 3.0476 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 7167 | 1.4 | 2.8571 | 11.0204 | 17.4175 | 2.9686 | 3.4286 | 1.4 | 3.5714 | 0.2 | 10 | 16.4286
| 7168 | 1.4 | 2.8571 | 9.4737 | 15.9744 | 2.878 | 3.6226 | 1 | 5 | 0.4 | 5 | 12.8571
| 7169 | 0.8 | 5 | 11.25 | 21.1259 | 3.2552 | 6.6207 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 7170 | 0.6 | 6.6667 | 12 | 19.3978 | 2.8263 | 4.5714 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 7171 | 1.4 | 2.8571 | 18 | 24.6614 | 3.2329 | 3.4286 | 0.6 | 8.3333 | 0.8 | 2.5 | 13.6905
| 7172 | 0.4 | 10 | 11.0204 | 18.0933 | 3.2329 | 3.84 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 7173 | 0.8 | 5 | 8.1818 | 14.5537 | 2.3719 | 4 | 1 | 5 | 0.1 | 20 | 30
| 7174 | 0.8 | 5 | 12 | 19.3858 | 3.3007 | 4.0851 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 7175 | 0.6 | 6.6667 | 12.8571 | 19.002 | 2.7765 | 3.3684 | 1 | 5 | 0.6 | 3.3333 | 15
| 7176 | 1.2 | 3.3333 | 12.5581 | 18.3097 | 2.4974 | 3.2542 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.1667
| 7177 | 1.2 | 3.3333 | 11.4894 | 17.2542 | 2.5106 | 3.2542 | 0.4 | 12.5 | 0.2 | 10 | 25.8333
| 7178 | 0.8 | 5 | 13.8462 | 19.2505 | 2.878 | 2.5263 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 7179 | 1.2 | 3.3333 | 13.5 | 20.5509 | 3.2109 | 3.84 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 7180 | 1.4 | 2.8571 | 9.3103 | 17.5645 | 3.0649 | 5.1892 | 1 | 5 | 0.1 | 20 | 27.8571
| 7181 | 0.8 | 5 | 11.4894 | 17.8333 | 2.5792 | 3.7647 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 7182 | 0.6 | 6.6667 | 14.5946 | 24.4581 | 3.0064 | 6.8571 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 7183 | 1 | 4 | 12.8571 | 22.9544 | 2.7126 | 7.3846 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 7184 | 0.4 | 10 | 18.6207 | 25.707 | 3.776 | 3.3103 | 1 | 5 | 0.1 | 20 | 35
| 7185 | 0.4 | 10 | 10 | 17.1498 | 3.6589 | 3.4909 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 7186 | 1 | 4 | 12.2727 | 19.3378 | 3.1467 | 3.9184 | 0.4 | 12.5 | 0.2 | 10 | 26.5
| 7187 | 0.8 | 5 | 14.2105 | 22.0664 | 2.6667 | 5.1892 | 1.4 | 3.5714 | 0.1 | 20 | 28.5714
| 7188 | 0.6 | 6.6667 | 8.5714 | 17.5671 | 3.8065 | 5.1892 | 0.4 | 12.5 | 0.6 | 3.3333 | 22.5
| 7189 | 0.6 | 6.6667 | 15 | 23.1745 | 3.6031 | 4.5714 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 7190 | 1.4 | 2.8571 | 19.2857 | 25.3019 | 2.9686 | 3.0476 | 0.6 | 8.3333 | 0.8 | 2.5 | 13.6905
| 7191 | 1.4 | 2.8571 | 9.4737 | 17.8825 | 3.8374 | 4.5714 | 1 | 5 | 0.2 | 10 | 17.8571
| 7192 | 1.2 | 3.3333 | 8.4375 | 16.0278 | 2.5376 | 5.0526 | 1 | 5 | 0.2 | 10 | 18.3333
| 7193 | 0.4 | 10 | 9.4737 | 16.0529 | 2.5792 | 4 | 1 | 5 | 0.4 | 5 | 20
| 7194 | 0.2 | 20 | 9.8182 | 17.5145 | 3.5224 | 4.1739 | 1 | 5 | 0.2 | 10 | 35
| 7195 | 0.4 | 10 | 8.8525 | 17.7743 | 2.7283 | 6.1935 | 1 | 5 | 0.2 | 10 | 25
| 7196 | 1 | 4 | 13.8462 | 22.0002 | 4.069 | 4.0851 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 7197 | 1 | 4 | 10.8 | 17.2336 | 2.878 | 3.5556 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 7198 | 0.4 | 10 | 9.3103 | 16.3287 | 3.3957 | 3.6226 | 0.6 | 8.3333 | 0.1 | 20 | 38.3333
| 7199 | 0.8 | 5 | 11.7391 | 20.6449 | 3.7165 | 5.1892 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 7200 | 0.8 | 5 | 12.5581 | 21.7795 | 4.5385 | 4.6829 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 7201 | 1.4 | 2.8571 | 13.8462 | 20.7277 | 3.1892 | 3.6923 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 7202 | 0.6 | 6.6667 | 12 | 21.2997 | 3.9664 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 7203 | 0.6 | 6.6667 | 12 | 20.3785 | 3.0452 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 7204 | 0.6 | 6.6667 | 13.5 | 19.8073 | 3.6031 | 2.7042 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 7205 | 0.4 | 10 | 11.4894 | 19.3493 | 3.4963 | 4.3636 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 7206 | 1 | 4 | 8.5714 | 14.8246 | 3.4706 | 2.7826 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7207 | 0.8 | 5 | 11.0204 | 17.4927 | 2.2056 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 7208 | 1 | 4 | 10.5882 | 19.1489 | 3.3714 | 5.1892 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 7209 | 0.8 | 5 | 11.25 | 19.1987 | 3.0256 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 7210 | 1.2 | 3.3333 | 10.3846 | 16.8324 | 2.6077 | 3.84 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 7211 | 0.6 | 6.6667 | 16.875 | 26.4457 | 2.95 | 6.6207 | 1 | 5 | 0.2 | 10 | 21.6667
| 7212 | 0.6 | 6.6667 | 13.8462 | 21.7152 | 4.1043 | 3.7647 | 1 | 5 | 0.2 | 10 | 21.6667
| 7213 | 1.2 | 3.3333 | 8.1818 | 15.7042 | 3.5224 | 4 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 7214 | 1.2 | 3.3333 | 11.25 | 16.5362 | 2.4205 | 2.8657 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 7215 | 0.4 | 10 | 15 | 21.1367 | 2.8263 | 3.3103 | 1.4 | 3.5714 | 0.1 | 20 | 33.5714
| 7216 | 1.2 | 3.3333 | 11.25 | 24.8516 | 3.4963 | 10.1053 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 7217 | 0.2 | 20 | 10.8 | 25.9315 | 3.8374 | 11.2941 | 1.2 | 4.1667 | 0.8 | 2.5 | 26.6667
| 7218 | 0.2 | 20 | 12.5581 | 21.3621 | 3.4706 | 5.3333 | 1 | 5 | 0.2 | 10 | 35
| 7219 | 0.6 | 6.6667 | 9.4737 | 17.7681 | 3.1053 | 5.1892 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 7220 | 1.4 | 2.8571 | 12.2727 | 19.7244 | 3.2778 | 4.1739 | 0.8 | 6.25 | 0.8 | 2.5 | 11.6071
| 7221 | 0.2 | 20 | 10.3846 | 17.6013 | 2.95 | 4.2667 | 1.4 | 3.5714 | 0.1 | 20 | 43.5714
| 7222 | 1 | 4 | 13.1707 | 19.6249 | 3.0256 | 3.4286 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 7223 | 1 | 4 | 16.3636 | 24.653 | 2.4712 | 5.8182 | 1 | 5 | 0.8 | 2.5 | 11.5
| 7224 | 0.8 | 5 | 10 | 17.389 | 3.4706 | 3.9184 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 7225 | 0.2 | 20 | 10.1887 | 16.8721 | 2.8434 | 3.84 | 0.6 | 8.3333 | 0.4 | 5 | 33.3333
| 7226 | 1 | 4 | 16.875 | 23.2256 | 2.5106 | 3.84 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 7227 | 1 | 4 | 11.4894 | 19.5198 | 2.6971 | 5.3333 | 1 | 5 | 0.1 | 20 | 29
| 7228 | 0.4 | 10 | 11.7391 | 18.9291 | 2.8263 | 4.3636 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 7229 | 1.2 | 3.3333 | 16.875 | 22.3141 | 3.1258 | 2.3133 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 7230 | 0.8 | 5 | 8.8525 | 17.3714 | 4.2523 | 4.2667 | 1.6 | 3.125 | 0.8 | 2.5 | 10.625
| 7231 | 0.6 | 6.6667 | 13.8462 | 22.1414 | 2.8095 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 7232 | 0.8 | 5 | 10.1887 | 17.0497 | 2.4974 | 4.3636 | 1 | 5 | 0.2 | 10 | 20
| 7233 | 0.8 | 5 | 10.3846 | 17.1221 | 3.0452 | 3.6923 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 7234 | 0.2 | 20 | 13.1707 | 21.5367 | 3.9008 | 4.4651 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 7235 | 1.2 | 3.3333 | 12.5581 | 20.8052 | 3.3239 | 4.9231 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 7236 | 0.8 | 5 | 12.8571 | 22.4012 | 2.433 | 7.1111 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 7237 | 1.2 | 3.3333 | 11.7391 | 19.5648 | 3.0256 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 7238 | 0.4 | 10 | 13.1707 | 22.5083 | 2.2264 | 7.1111 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 7239 | 0.4 | 10 | 8.8525 | 14.5787 | 2.8606 | 2.8657 | 1 | 5 | 0.4 | 5 | 20
| 7240 | 0.2 | 20 | 13.1707 | 21.1625 | 3.4203 | 4.5714 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 7241 | 1 | 4 | 13.1707 | 20.7381 | 3.3007 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 7242 | 0.8 | 5 | 14.2105 | 20.8333 | 2.5376 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 7243 | 1.4 | 2.8571 | 10.8 | 15.9446 | 2.9873 | 2.1573 | 0.4 | 12.5 | 0.4 | 5 | 20.3571
| 7244 | 1.2 | 3.3333 | 8.7097 | 15.5825 | 3.776 | 3.0968 | 1 | 5 | 0.4 | 5 | 13.3333
| 7245 | 1.4 | 2.8571 | 22.5 | 31.046 | 3.746 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 7246 | 1 | 4 | 11.4894 | 20.06 | 3.085 | 5.4857 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 7247 | 0.6 | 6.6667 | 12.8571 | 21.983 | 3.1258 | 6 | 1 | 5 | 0.2 | 10 | 21.6667
| 7248 | 1.2 | 3.3333 | 10.5882 | 16.0282 | 2.6971 | 2.7429 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 7249 | 0.8 | 5 | 12 | 20.6809 | 3.3475 | 5.3333 | 1 | 5 | 0.4 | 5 | 15
| 7250 | 1 | 4 | 10.3846 | 21.3198 | 3.2552 | 7.68 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 7251 | 0.2 | 20 | 10 | 18.3784 | 3.1892 | 5.1892 | 1 | 5 | 0.2 | 10 | 35
| 7252 | 0.6 | 6.6667 | 10.3846 | 17.5547 | 3.085 | 4.0851 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 7253 | 0.8 | 5 | 12.2727 | 18.852 | 3.2109 | 3.3684 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 7254 | 1 | 4 | 13.1707 | 21.9436 | 3.1258 | 5.6471 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7255 | 0.4 | 10 | 20 | 26.7884 | 3.2329 | 3.5556 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 7256 | 1 | 4 | 16.3636 | 23.6489 | 3.4453 | 3.84 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 7257 | 0.8 | 5 | 11.0204 | 21.7022 | 2.6818 | 8 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 7258 | 0.4 | 10 | 10.3846 | 17.751 | 2.3137 | 5.0526 | 1 | 5 | 0.8 | 2.5 | 17.5
| 7259 | 1.4 | 2.8571 | 17.4194 | 24.6011 | 4.0342 | 3.1475 | 1 | 5 | 0.4 | 5 | 12.8571
| 7260 | 0.8 | 5 | 12.8571 | 21.1161 | 3.6875 | 4.5714 | 1 | 5 | 0.1 | 20 | 30
| 7261 | 0.6 | 6.6667 | 11.7391 | 19.6366 | 3.6308 | 4.2667 | 1 | 5 | 0.2 | 10 | 21.6667
| 7262 | 0.2 | 20 | 12.2727 | 19.8216 | 3.5489 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 7263 | 0.8 | 5 | 11.25 | 19.9548 | 3.3714 | 5.3333 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 7264 | 0.4 | 10 | 10.3846 | 16.3183 | 2.5652 | 3.3684 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 7265 | 1 | 4 | 12.2727 | 21.5601 | 2.6667 | 6.6207 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 7266 | 0.8 | 5 | 11.7391 | 23.2928 | 2.8263 | 8.7273 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 7267 | 1.2 | 3.3333 | 18 | 24.023 | 2.7126 | 3.3103 | 1 | 5 | 0.4 | 5 | 13.3333
| 7268 | 0.6 | 6.6667 | 13.1707 | 21.5686 | 4.0342 | 4.3636 | 1 | 5 | 0.4 | 5 | 16.6667
| 7269 | 0.8 | 5 | 9.6429 | 16.1359 | 2.2264 | 4.2667 | 1 | 5 | 0.4 | 5 | 15
| 7270 | 0.6 | 6.6667 | 10.5882 | 19.536 | 3.3007 | 5.6471 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 7271 | 0.6 | 6.6667 | 10.5882 | 16.8286 | 2.1553 | 4.0851 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 7272 | 1 | 4 | 14.5946 | 22.2648 | 3.4963 | 4.1739 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 7273 | 0.1 | 40 | 16.3636 | 25.7938 | 2.8095 | 6.6207 | 0.8 | 6.25 | 0.2 | 10 | 56.25
| 7274 | 0.6 | 6.6667 | 9.6429 | 19.1895 | 3.1467 | 6.4 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 7275 | 1.2 | 3.3333 | 14.5946 | 21.3194 | 3.4706 | 3.2542 | 1 | 5 | 0.2 | 10 | 18.3333
| 7276 | 1 | 4 | 12.5581 | 20.5923 | 4.0342 | 4 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 7277 | 1 | 4 | 9.4737 | 15.3587 | 1.9667 | 3.9184 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 7278 | 0.8 | 5 | 14.5946 | 22.505 | 3.4453 | 4.4651 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 7279 | 0.8 | 5 | 9.6429 | 16.5117 | 3.8689 | 3 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 7280 | 0.6 | 6.6667 | 11.0204 | 17.285 | 3.1678 | 3.0968 | 1.6 | 3.125 | 0.2 | 10 | 19.7917
| 7281 | 1 | 4 | 10.3846 | 15.8906 | 2.4583 | 3.0476 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 7282 | 0.8 | 5 | 7.5 | 15.3452 | 3.0452 | 4.8 | 1.4 | 3.5714 | 0.1 | 20 | 28.5714
| 7283 | 0.6 | 6.6667 | 10.1887 | 16.5141 | 3.2778 | 3.0476 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 7284 | 0.6 | 6.6667 | 11.7391 | 19.882 | 2.8095 | 5.3333 | 1 | 5 | 0.2 | 10 | 21.6667
| 7285 | 1.2 | 3.3333 | 11.25 | 17.3569 | 2.5514 | 3.5556 | 1.6 | 3.125 | 0.2 | 10 | 16.4583
| 7286 | 0.8 | 5 | 13.1707 | 20.1694 | 2.9136 | 4.0851 | 0.4 | 12.5 | 0.8 | 2.5 | 20
| 7287 | 0.8 | 5 | 15.8824 | 22.9513 | 4.069 | 3 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 7288 | 1 | 4 | 12.5581 | 19.2505 | 3.8689 | 2.8235 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7289 | 1.2 | 3.3333 | 15.8824 | 22.4923 | 2.9873 | 3.6226 | 0.4 | 12.5 | 0.4 | 5 | 20.8333
| 7290 | 1.4 | 2.8571 | 12.8571 | 20.3534 | 3.4963 | 4 | 0.4 | 12.5 | 0.6 | 3.3333 | 18.6905
| 7291 | 0.4 | 10 | 14.2105 | 20.5798 | 2.1953 | 4.1739 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 7292 | 0.8 | 5 | 12.5581 | 30.6281 | 3.3007 | 14.7692 | 1 | 5 | 0.1 | 20 | 30
| 7293 | 0.6 | 6.6667 | 11.4894 | 18.2666 | 3.085 | 3.6923 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 7294 | 0.8 | 5 | 18.6207 | 26.8382 | 4.4528 | 3.7647 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 7295 | 1.2 | 3.3333 | 11.7391 | 18.2768 | 2.5376 | 4 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 7296 | 1 | 4 | 10 | 15.0587 | 2.5652 | 2.4935 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 7297 | 0.8 | 5 | 11.7391 | 21.0725 | 4 | 5.3333 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 7298 | 1.2 | 3.3333 | 8.1818 | 21.1293 | 3.3475 | 9.6 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 7299 | 0.8 | 5 | 12 | 19.3678 | 3.6031 | 3.7647 | 0.4 | 12.5 | 0.8 | 2.5 | 20
| 7300 | 0.6 | 6.6667 | 10.8 | 20.4031 | 3.6031 | 6 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 7301 | 0.4 | 10 | 18 | 26.2635 | 3.2109 | 5.0526 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 7302 | 1 | 4 | 14.2105 | 22.9232 | 2.7126 | 6 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 7303 | 0.8 | 5 | 12.8571 | 18.3039 | 2.5376 | 2.9091 | 1 | 5 | 0.4 | 5 | 15
| 7304 | 1.4 | 2.8571 | 12 | 20.504 | 4.1404 | 4.3636 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 7305 | 0.2 | 20 | 13.5 | 20.3434 | 2.8434 | 4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 27.5
| 7306 | 1.2 | 3.3333 | 10.8 | 17.1254 | 3.2778 | 3.0476 | 1 | 5 | 0.2 | 10 | 18.3333
| 7307 | 0.8 | 5 | 10.3846 | 19.9985 | 3.4203 | 6.1935 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 7308 | 0.8 | 5 | 10 | 16.5552 | 2.6369 | 3.9184 | 1 | 5 | 0.4 | 5 | 15
| 7309 | 0.2 | 20 | 13.1707 | 23.1957 | 3.1678 | 6.8571 | 1 | 5 | 0.4 | 5 | 30
| 7310 | 0.2 | 20 | 10.5882 | 17.4252 | 2.3719 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 7311 | 1 | 4 | 10 | 17.9381 | 3.2552 | 4.6829 | 1.4 | 3.5714 | 0.8 | 2.5 | 10.0714
| 7312 | 1 | 4 | 10.5882 | 16.3824 | 3.3007 | 2.4935 | 1 | 5 | 0.4 | 5 | 14
| 7313 | 1 | 4 | 12 | 23.5807 | 3.2329 | 8.3478 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 7314 | 1.2 | 3.3333 | 8.3077 | 14.3606 | 2.4974 | 3.5556 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 7315 | 1 | 4 | 14.5946 | 21.2141 | 2.4456 | 4.1739 | 1 | 5 | 0.4 | 5 | 14
| 7316 | 0.6 | 6.6667 | 11.25 | 20.1091 | 3.8065 | 5.0526 | 0.6 | 8.3333 | 0.1 | 20 | 35
| 7317 | 0.6 | 6.6667 | 10 | 16.3651 | 2.8095 | 3.5556 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 7318 | 0.8 | 5 | 10.5882 | 16.4489 | 3.3007 | 2.56 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 7319 | 1 | 4 | 11.7391 | 18.7524 | 3.5224 | 3.4909 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 7320 | 1.2 | 3.3333 | 16.3636 | 23.2347 | 2.6971 | 4.1739 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 7321 | 0.6 | 6.6667 | 11.4894 | 16.8888 | 2.4456 | 2.9538 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 7322 | 1.2 | 3.3333 | 10.3846 | 17.5347 | 3.0649 | 4.0851 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 7323 | 1 | 4 | 10 | 15.5618 | 2.9317 | 2.6301 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 7324 | 0.6 | 6.6667 | 11.0204 | 17.5753 | 3.3007 | 3.2542 | 0.6 | 8.3333 | 0.8 | 2.5 | 17.5
| 7325 | 1.2 | 3.3333 | 12 | 19.5612 | 3.8689 | 3.6923 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 7326 | 1.2 | 3.3333 | 10.8 | 18.9209 | 2.9317 | 5.1892 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.1667
| 7327 | 0.8 | 5 | 12 | 21.2988 | 3.1053 | 6.1935 | 1 | 5 | 0.2 | 10 | 20
| 7328 | 0.8 | 5 | 10.8 | 15.8777 | 2.5514 | 2.5263 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 7329 | 0.4 | 10 | 15 | 21.3066 | 2.878 | 3.4286 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 7330 | 1.6 | 2.5 | 11.25 | 18.6791 | 3.8065 | 3.6226 | 1 | 5 | 0.4 | 5 | 12.5
| 7331 | 1 | 4 | 18 | 25.4565 | 3.3714 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7332 | 1 | 4 | 8.8525 | 14.9686 | 2.9686 | 3.1475 | 1 | 5 | 0.4 | 5 | 14
| 7333 | 1.2 | 3.3333 | 11.25 | 18.1 | 2.9317 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 7334 | 0.4 | 10 | 12 | 21.3878 | 4.8163 | 4.5714 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 7335 | 0.4 | 10 | 11.25 | 18.0288 | 2.3137 | 4.4651 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 7336 | 0.8 | 5 | 7.6056 | 15.4496 | 2.5106 | 5.3333 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 7337 | 0.6 | 6.6667 | 13.5 | 19.1187 | 2.4712 | 3.1475 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 7338 | 0.8 | 5 | 12.2727 | 19.378 | 3.1053 | 4 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 7339 | 1 | 4 | 16.875 | 26.5391 | 3.4706 | 6.1935 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 7340 | 1.2 | 3.3333 | 8.7097 | 16.944 | 3.0452 | 5.1892 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 7341 | 1.4 | 2.8571 | 15.4286 | 30.9257 | 2.6971 | 12.8 | 0.4 | 12.5 | 0.2 | 10 | 25.3571
| 7342 | 0.6 | 6.6667 | 11.25 | 17.699 | 2.8263 | 3.6226 | 1 | 5 | 0.6 | 3.3333 | 15
| 7343 | 1 | 4 | 9.1525 | 15.8524 | 3.746 | 2.9538 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 7344 | 1 | 4 | 12 | 17.1059 | 3.1467 | 1.9592 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 7345 | 1 | 4 | 11.25 | 18.9543 | 2.6517 | 5.0526 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 7346 | 1.4 | 2.8571 | 14.5946 | 21.5375 | 2.5792 | 4.3636 | 0.4 | 12.5 | 0.4 | 5 | 20.3571
| 7347 | 0.8 | 5 | 12.8571 | 21.6509 | 3.1467 | 5.6471 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 7348 | 0.2 | 20 | 10.8 | 18.6574 | 2.5241 | 5.3333 | 1 | 5 | 0.4 | 5 | 30
| 7349 | 0.4 | 10 | 12.5581 | 18.8381 | 3.5758 | 2.7042 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 7350 | 0.6 | 6.6667 | 15.4286 | 24.1401 | 3.5224 | 5.1892 | 1 | 5 | 0.4 | 5 | 16.6667
| 7351 | 0.6 | 6.6667 | 10.3846 | 18.8087 | 3.3714 | 5.0526 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 7352 | 1 | 4 | 14.2105 | 20.2645 | 3.0064 | 3.0476 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 7353 | 0.6 | 6.6667 | 10.1887 | 17.6223 | 2.9686 | 4.4651 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 7354 | 1.2 | 3.3333 | 11.4894 | 19.7839 | 3.3714 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 7355 | 0.6 | 6.6667 | 14.2105 | 22.2049 | 3.6308 | 4.3636 | 1 | 5 | 0.2 | 10 | 21.6667
| 7356 | 0.6 | 6.6667 | 13.5 | 19.0758 | 2.6667 | 2.9091 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 7357 | 0.4 | 10 | 9.8182 | 16.2547 | 2.7442 | 3.6923 | 1 | 5 | 0.4 | 5 | 20
| 7358 | 1.6 | 2.5 | 13.8462 | 22.2905 | 3.2552 | 5.1892 | 1.6 | 3.125 | 0.4 | 5 | 10.625
| 7359 | 0.8 | 5 | 12.8571 | 21.4085 | 2.5514 | 6 | 1 | 5 | 0.2 | 10 | 20
| 7360 | 0.6 | 6.6667 | 9.4737 | 16.8825 | 3.7165 | 3.6923 | 1 | 5 | 0.4 | 5 | 16.6667
| 7361 | 1 | 4 | 10.8 | 18.5281 | 3.0452 | 4.6829 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 7362 | 1 | 4 | 9.6429 | 15.5297 | 2.3959 | 3.4909 | 1 | 5 | 0.1 | 20 | 29
| 7363 | 0.8 | 5 | 13.8462 | 20.3701 | 3.3239 | 3.2 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 7364 | 0.8 | 5 | 11.4894 | 18.9258 | 2.3838 | 5.0526 | 1 | 5 | 0.8 | 2.5 | 12.5
| 7365 | 1.2 | 3.3333 | 11.7391 | 17.4151 | 2.5792 | 3.0968 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 7366 | 0.4 | 10 | 17.4194 | 26.9843 | 3.3714 | 6.1935 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 7367 | 1 | 4 | 11.0204 | 19.0416 | 2.9686 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 7368 | 1 | 4 | 12.2727 | 20.0385 | 3.3007 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 7369 | 0.6 | 6.6667 | 10 | 18.787 | 2.5934 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 7370 | 1.2 | 3.3333 | 9.4737 | 15.4652 | 3.1258 | 2.8657 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 7371 | 1 | 4 | 12.2727 | 20.3098 | 2.5514 | 5.4857 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 7372 | 1 | 4 | 15 | 21.6205 | 3.0649 | 3.5556 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 7373 | 0.8 | 5 | 10.5882 | 19.733 | 2.5241 | 6.6207 | 1 | 5 | 0.4 | 5 | 15
| 7374 | 0.8 | 5 | 11.7391 | 19.1192 | 2.6971 | 4.6829 | 1.6 | 3.125 | 0.6 | 3.3333 | 11.4583
| 7375 | 1.4 | 2.8571 | 14.2105 | 21.6035 | 3.8374 | 3.5556 | 1 | 5 | 0.8 | 2.5 | 10.3571
| 7376 | 1 | 4 | 11.4894 | 19.9694 | 3.1467 | 5.3333 | 1 | 5 | 0.4 | 5 | 14
| 7377 | 1 | 4 | 15 | 22.2792 | 3.1053 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 7378 | 0.8 | 5 | 12.2727 | 18.587 | 2.3959 | 3.9184 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 7379 | 1 | 4 | 11.25 | 17.9565 | 3.6589 | 3.0476 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 7380 | 0.1 | 40 | 12.5581 | 20.3234 | 2.7126 | 5.0526 | 0.6 | 8.3333 | 0.6 | 3.3333 | 51.6667
| 7381 | 1 | 4 | 12.5581 | 19.2728 | 2.95 | 3.7647 | 1 | 5 | 0.1 | 20 | 29
| 7382 | 1 | 4 | 14.5946 | 20.2445 | 2.8263 | 2.8235 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7383 | 0.6 | 6.6667 | 11.0204 | 17.6132 | 3.4453 | 3.1475 | 1 | 5 | 0.2 | 10 | 21.6667
| 7384 | 0.8 | 5 | 11.7391 | 18.1195 | 3.2329 | 3.1475 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 7385 | 0.8 | 5 | 14.5946 | 20.892 | 3.6308 | 2.6667 | 1 | 5 | 0.4 | 5 | 15
| 7386 | 1 | 4 | 13.8462 | 24.3042 | 3.8374 | 6.6207 | 0.8 | 6.25 | 1 | 2 | 12.25
| 7387 | 0.6 | 6.6667 | 12 | 21.0031 | 2.8095 | 6.1935 | 1 | 5 | 0.2 | 10 | 21.6667
| 7388 | 0.8 | 5 | 10.8 | 20.0317 | 3.746 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 7389 | 0.6 | 6.6667 | 10.5882 | 16.6588 | 2.7602 | 3.3103 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 7390 | 0.6 | 6.6667 | 15 | 22.3136 | 2.95 | 4.3636 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 7391 | 0.8 | 5 | 12.8571 | 25.2667 | 2.8095 | 9.6 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 7392 | 1 | 4 | 12.8571 | 22.7993 | 3.085 | 6.8571 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 7393 | 1 | 4 | 9.6429 | 21.6708 | 3.3007 | 8.7273 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 7394 | 1.2 | 3.3333 | 9 | 16.5758 | 3.5758 | 4 | 1.6 | 3.125 | 0.4 | 5 | 11.4583
| 7395 | 1.2 | 3.3333 | 11.0204 | 16.6786 | 2.5106 | 3.1475 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 7396 | 0.2 | 20 | 11.7391 | 19.772 | 3.2329 | 4.8 | 0.6 | 8.3333 | 0.4 | 5 | 33.3333
| 7397 | 0.4 | 10 | 16.875 | 23.4402 | 2.5652 | 4 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 7398 | 0.4 | 10 | 14.5946 | 22.5433 | 3.0256 | 4.9231 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 7399 | 1.2 | 3.3333 | 18 | 23.7173 | 2.2264 | 3.4909 | 1 | 5 | 0.4 | 5 | 13.3333
| 7400 | 0.2 | 20 | 8.8525 | 19.0762 | 3.6031 | 6.6207 | 1.6 | 3.125 | 0.4 | 5 | 28.125
| 7401 | 1.8 | 2.2222 | 12.5581 | 18.0317 | 2.8434 | 2.6301 | 0.6 | 8.3333 | 0.2 | 10 | 20.5556
| 7402 | 1.2 | 3.3333 | 19.2857 | 26.0761 | 3.0256 | 3.7647 | 1 | 5 | 0.4 | 5 | 13.3333
| 7403 | 0.8 | 5 | 9.8182 | 17.0435 | 2.7602 | 4.4651 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 7404 | 0.2 | 20 | 10.8 | 20.0387 | 3.0452 | 6.1935 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 7405 | 1 | 4 | 15 | 23.3442 | 2.6971 | 5.6471 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 7406 | 1 | 4 | 15.8824 | 25.2459 | 3.7165 | 5.6471 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 7407 | 0.2 | 20 | 11.4894 | 23.6386 | 3.0064 | 9.1429 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 7408 | 1 | 4 | 11.4894 | 16.3403 | 2.9686 | 1.8824 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 7409 | 0.6 | 6.6667 | 7.9412 | 14.7328 | 3.3007 | 3.4909 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 7410 | 1 | 4 | 11.7391 | 23.5072 | 3.4203 | 8.3478 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 7411 | 0.8 | 5 | 10 | 20.2909 | 4.2909 | 6 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 7412 | 1.2 | 3.3333 | 15.8824 | 24.1026 | 3.4203 | 4.8 | 1.6 | 3.125 | 0.8 | 2.5 | 8.9583
| 7413 | 0.6 | 6.6667 | 13.5 | 21.5851 | 4 | 4.0851 | 0.6 | 8.3333 | 0.8 | 2.5 | 17.5
| 7414 | 0.2 | 20 | 14.2105 | 21.9264 | 3.6308 | 4.0851 | 1 | 5 | 0.1 | 20 | 45
| 7415 | 0.8 | 5 | 17.4194 | 26.3408 | 3.8689 | 5.0526 | 1 | 5 | 0.1 | 20 | 30
| 7416 | 1 | 4 | 11.4894 | 19.2238 | 2.6818 | 5.0526 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 7417 | 1.2 | 3.3333 | 11.4894 | 24.9824 | 2.8263 | 10.6667 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 7418 | 0.6 | 6.6667 | 10.8 | 17.9122 | 3.3475 | 3.7647 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 7419 | 1 | 4 | 15.8824 | 22.7214 | 3.4706 | 3.3684 | 1 | 5 | 0.8 | 2.5 | 11.5
| 7420 | 0.2 | 20 | 13.5 | 19.7674 | 2.7765 | 3.4909 | 1 | 5 | 0.2 | 10 | 35
| 7421 | 0.6 | 6.6667 | 14.2105 | 19.5974 | 2.8606 | 2.5263 | 1 | 5 | 0.6 | 3.3333 | 15
| 7422 | 1.2 | 3.3333 | 12 | 18.8936 | 3.746 | 3.1475 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 7423 | 1.2 | 3.3333 | 7.5 | 14.6401 | 2.7765 | 4.3636 | 0.6 | 8.3333 | 0.1 | 20 | 31.6667
| 7424 | 1.2 | 3.3333 | 9.3103 | 17.8329 | 3.1892 | 5.3333 | 0.6 | 8.3333 | 0.1 | 20 | 31.6667
| 7425 | 1.4 | 2.8571 | 10.5882 | 18.9301 | 3.6589 | 4.6829 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 7426 | 1 | 4 | 10.1887 | 20.6289 | 2.7602 | 7.68 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 7427 | 0.4 | 10 | 9.4737 | 15.8485 | 3.0064 | 3.3684 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 7428 | 0.4 | 10 | 12.5581 | 18.8386 | 2.1953 | 4.0851 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 7429 | 1 | 4 | 7.9412 | 14.952 | 2.7442 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 7430 | 1 | 4 | 11.25 | 18.735 | 2.9136 | 4.5714 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 7431 | 0.8 | 5 | 11.4894 | 17.9581 | 2.7765 | 3.6923 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 7432 | 0.4 | 10 | 10.3846 | 16.8779 | 2.4082 | 4.0851 | 0.6 | 8.3333 | 0.1 | 20 | 38.3333
| 7433 | 0.8 | 5 | 15.8824 | 21.8171 | 3.0256 | 2.9091 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 7434 | 0.2 | 20 | 11.0204 | 22.4134 | 3.0452 | 8.3478 | 1 | 5 | 0.2 | 10 | 35
| 7435 | 0.8 | 5 | 12.2727 | 17.2789 | 1.9585 | 3.0476 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 7436 | 1 | 4 | 11.4894 | 19.9251 | 2.95 | 5.4857 | 1 | 5 | 0.4 | 5 | 14
| 7437 | 0.2 | 20 | 15.8824 | 22.9461 | 3.3714 | 3.6923 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 7438 | 0.6 | 6.6667 | 13.8462 | 21.9654 | 4.0342 | 4.0851 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 7439 | 0.4 | 10 | 10.3846 | 22.337 | 2.8095 | 9.1429 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 7440 | 0.4 | 10 | 12.2727 | 22.2102 | 2.8263 | 7.1111 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 7441 | 1 | 4 | 11.25 | 18.8056 | 4 | 3.5556 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 7442 | 0.4 | 10 | 19.2857 | 26.5227 | 3.746 | 3.4909 | 1 | 5 | 0.4 | 5 | 20
| 7443 | 0.2 | 20 | 13.8462 | 21.4937 | 2.4583 | 5.1892 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 7444 | 0.8 | 5 | 13.1707 | 22.5843 | 2.7929 | 6.6207 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 7445 | 1.2 | 3.3333 | 12 | 22.2625 | 4.069 | 6.1935 | 0.6 | 8.3333 | 0.1 | 20 | 31.6667
| 7446 | 0.6 | 6.6667 | 13.1707 | 18.9887 | 2.1953 | 3.6226 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 7447 | 0.8 | 5 | 10 | 17.2659 | 3.3475 | 3.9184 | 1 | 5 | 0.4 | 5 | 15
| 7448 | 0.4 | 10 | 13.1707 | 20.2058 | 2.95 | 4.0851 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 7449 | 0.4 | 10 | 9.3103 | 16.1238 | 2.7283 | 4.0851 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 7450 | 1 | 4 | 11.25 | 18.45 | 4 | 3.2 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 7451 | 0.4 | 10 | 13.8462 | 21.0606 | 3.6589 | 3.5556 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 7452 | 0.6 | 6.6667 | 14.2105 | 21.5544 | 2.2913 | 5.0526 | 1 | 5 | 0.6 | 3.3333 | 15
| 7453 | 1 | 4 | 11.7391 | 20.4357 | 3.2109 | 5.4857 | 1 | 5 | 0.2 | 10 | 19
| 7454 | 1 | 4 | 10 | 19.1892 | 3.1892 | 6 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 7455 | 0.8 | 5 | 10.5882 | 18.9867 | 3.9333 | 4.4651 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 7456 | 1.2 | 3.3333 | 15.4286 | 20.5745 | 2.5514 | 2.5946 | 1 | 5 | 0.2 | 10 | 18.3333
| 7457 | 0.6 | 6.6667 | 16.3636 | 26.1344 | 2.9136 | 6.8571 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 7458 | 1.2 | 3.3333 | 12.2727 | 20.5018 | 2.8957 | 5.3333 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 7459 | 1.4 | 2.8571 | 12.2727 | 19.033 | 2.7602 | 4 | 1 | 5 | 0.4 | 5 | 12.8571
| 7460 | 0.6 | 6.6667 | 12 | 21.4203 | 3.4203 | 6 | 1 | 5 | 0.6 | 3.3333 | 15
| 7461 | 0.6 | 6.6667 | 12.8571 | 23.6174 | 2.7602 | 8 | 1.8 | 2.7778 | 0.2 | 10 | 19.4444
| 7462 | 1 | 4 | 13.1707 | 20.2105 | 3.5489 | 3.4909 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 7463 | 0.2 | 20 | 12 | 19.0345 | 2.8606 | 4.1739 | 1.4 | 3.5714 | 0.6 | 3.3333 | 26.9048
| 7464 | 1 | 4 | 12.2727 | 22.6499 | 2.6971 | 7.68 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 7465 | 1 | 4 | 18 | 27.1959 | 3.5489 | 5.6471 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 7466 | 1.2 | 3.3333 | 10.3846 | 19.789 | 3.2109 | 6.1935 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 7467 | 0.4 | 10 | 11.25 | 24.85 | 4 | 9.6 | 1 | 5 | 0.4 | 5 | 20
| 7468 | 1.2 | 3.3333 | 11.7391 | 17.6994 | 2.7602 | 3.2 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 7469 | 1 | 4 | 10.8 | 19.0512 | 4.4112 | 3.84 | 1 | 5 | 0.4 | 5 | 14
| 7470 | 1 | 4 | 10 | 17.9917 | 3.4203 | 4.5714 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 7471 | 0.1 | 40 | 10.3846 | 16.6017 | 1.9504 | 4.2667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 47.5
| 7472 | 0.6 | 6.6667 | 11.4894 | 21.037 | 4.2143 | 5.3333 | 1 | 5 | 0.4 | 5 | 16.6667
| 7473 | 0.2 | 20 | 13.1707 | 21.5104 | 3.0064 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 7474 | 0.8 | 5 | 15.8824 | 22.1821 | 2.7442 | 3.5556 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 7475 | 1.2 | 3.3333 | 13.1707 | 20.3083 | 3.4453 | 3.6923 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 7476 | 0.4 | 10 | 12.2727 | 20.2061 | 3.9333 | 4 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 7477 | 1 | 4 | 11.25 | 19.2598 | 2.5241 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7478 | 0.6 | 6.6667 | 11.4894 | 19.9114 | 3.2329 | 5.1892 | 0.1 | 50 | 0.6 | 3.3333 | 60
| 7479 | 1 | 4 | 15.8824 | 21.2711 | 2.5652 | 2.8235 | 1 | 5 | 0.4 | 5 | 14
| 7480 | 0.8 | 5 | 11.0204 | 18.5916 | 3.8065 | 3.7647 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 7481 | 1.2 | 3.3333 | 8.8525 | 16.4127 | 2.7602 | 4.8 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 7482 | 0.8 | 5 | 11.4894 | 19.2372 | 3.0649 | 4.6829 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 7483 | 0.2 | 20 | 11.4894 | 17.611 | 3.1678 | 2.9538 | 1.2 | 4.1667 | 0.1 | 20 | 44.1667
| 7484 | 0.4 | 10 | 15.4286 | 22.5386 | 2.8434 | 4.2667 | 1 | 5 | 0.4 | 5 | 20
| 7485 | 1.4 | 2.8571 | 15 | 20.3239 | 3.3239 | 2 | 1 | 5 | 0.4 | 5 | 12.8571
| 7486 | 1 | 4 | 16.3636 | 23.4218 | 4.1043 | 2.9538 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 7487 | 0.4 | 10 | 11.0204 | 17.3626 | 2.9136 | 3.4286 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 7488 | 1.2 | 3.3333 | 11.4894 | 19.0823 | 2.7929 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 7489 | 0.8 | 5 | 15.4286 | 24.5205 | 2.4712 | 6.6207 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 7490 | 0.6 | 6.6667 | 14.2105 | 21.5915 | 2.8095 | 4.5714 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 7491 | 0.2 | 20 | 15.4286 | 21.8856 | 3.1467 | 3.3103 | 1 | 5 | 1 | 2 | 27
| 7492 | 0.4 | 10 | 11.0204 | 19.4409 | 2.4205 | 6 | 0.4 | 12.5 | 0.4 | 5 | 27.5
| 7493 | 0.8 | 5 | 10.1887 | 17.9613 | 3.6875 | 4.0851 | 1 | 5 | 0.1 | 20 | 30
| 7494 | 1.8 | 2.2222 | 9.8182 | 16.6646 | 3.0064 | 3.84 | 1 | 5 | 0.4 | 5 | 12.2222
| 7495 | 0.6 | 6.6667 | 13.1707 | 19.3198 | 3.6875 | 2.4615 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 7496 | 0.6 | 6.6667 | 9.3103 | 16.3758 | 3.3007 | 3.7647 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 7497 | 0.8 | 5 | 18 | 24.4974 | 2.4974 | 4 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 7498 | 0.8 | 5 | 8.5714 | 15.5056 | 2.7602 | 4.1739 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 7499 | 0.8 | 5 | 12.5581 | 21.1925 | 2.9873 | 5.6471 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 7500 | 0.8 | 5 | 11.0204 | 19.9904 | 2.7765 | 6.1935 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 7501 | 1 | 4 | 12.2727 | 18.0775 | 2.8957 | 2.9091 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7502 | 0.8 | 5 | 15.4286 | 21.1279 | 2.6517 | 3.0476 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 7503 | 1.4 | 2.8571 | 12 | 18.6204 | 2.1553 | 4.4651 | 1 | 5 | 0.4 | 5 | 12.8571
| 7504 | 0.6 | 6.6667 | 10.3846 | 21.907 | 3.5224 | 8 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 7505 | 1.4 | 2.8571 | 11.0204 | 24.0393 | 2.9136 | 10.1053 | 0.6 | 8.3333 | 0.2 | 10 | 21.1905
| 7506 | 0.4 | 10 | 15.4286 | 23.826 | 2.5792 | 5.8182 | 1 | 5 | 0.2 | 10 | 25
| 7507 | 0.8 | 5 | 9.6429 | 16.1618 | 3.3714 | 3.1475 | 1.8 | 2.7778 | 0.6 | 3.3333 | 11.1111
| 7508 | 0.8 | 5 | 12 | 18.2649 | 3.0649 | 3.2 | 0.2 | 25 | 0.4 | 5 | 35
| 7509 | 0.6 | 6.6667 | 13.1707 | 18.9971 | 2.8263 | 3 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 7510 | 0.8 | 5 | 9.6429 | 17.4795 | 2.9136 | 4.9231 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 7511 | 0.6 | 6.6667 | 9.6429 | 19.8039 | 2.7765 | 7.3846 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 7512 | 1 | 4 | 11.4894 | 19.9563 | 3.2778 | 5.1892 | 1 | 5 | 0.1 | 20 | 29
| 7513 | 0.6 | 6.6667 | 14.2105 | 19.7022 | 2.9317 | 2.56 | 1 | 5 | 0.4 | 5 | 16.6667
| 7514 | 0.4 | 10 | 13.5 | 22.6165 | 3.6308 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 7515 | 1.4 | 2.8571 | 14.2105 | 22.0075 | 2.6077 | 5.1892 | 0.6 | 8.3333 | 0.4 | 5 | 16.1905
| 7516 | 0.2 | 20 | 11.7391 | 19.3169 | 3.0064 | 4.5714 | 1 | 5 | 0.2 | 10 | 35
| 7517 | 1.2 | 3.3333 | 18.6207 | 23.3277 | 2.3366 | 2.3704 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 7518 | 0.6 | 6.6667 | 13.1707 | 20.9251 | 2.5652 | 5.1892 | 1 | 5 | 0.4 | 5 | 16.6667
| 7519 | 0.6 | 6.6667 | 7.6056 | 14.8311 | 2.3024 | 4.9231 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 7520 | 0.4 | 10 | 13.5 | 21.1358 | 2.3024 | 5.3333 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 7521 | 0.6 | 6.6667 | 11.7391 | 18.5524 | 3.7165 | 3.0968 | 1 | 5 | 0.4 | 5 | 16.6667
| 7522 | 0.8 | 5 | 9.6429 | 18.6002 | 2.3366 | 6.6207 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 7523 | 0.4 | 10 | 13.8462 | 20.0171 | 2.8606 | 3.3103 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 7524 | 0.8 | 5 | 12 | 19.3719 | 3.1053 | 4.2667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 7525 | 1.2 | 3.3333 | 11.25 | 19.7732 | 3.4706 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 7526 | 1 | 4 | 14.2105 | 23.469 | 3.0649 | 6.1935 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 7527 | 1.2 | 3.3333 | 13.1707 | 21.9856 | 3.1678 | 5.6471 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 7528 | 1 | 4 | 9.4737 | 17.7404 | 4 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 7529 | 0.8 | 5 | 9.3103 | 16.4835 | 2.8095 | 4.3636 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 7530 | 1.6 | 2.5 | 17.4194 | 24.8801 | 2.5376 | 4.9231 | 1.2 | 4.1667 | 0.1 | 20 | 26.6667
| 7531 | 1.2 | 3.3333 | 15.8824 | 21.8195 | 3.2329 | 2.7042 | 1 | 5 | 1 | 2 | 10.3333
| 7532 | 0.8 | 5 | 11.0204 | 16.3682 | 3.0064 | 2.3415 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 7533 | 0.4 | 10 | 13.5 | 20.3856 | 2.4205 | 4.4651 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 7534 | 1.2 | 3.3333 | 12.8571 | 18.896 | 3.085 | 2.9538 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 7535 | 1 | 4 | 13.5 | 24.3276 | 3.7165 | 7.1111 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 7536 | 1.6 | 2.5 | 11.4894 | 20.8299 | 3.5224 | 5.8182 | 0.8 | 6.25 | 0.2 | 10 | 18.75
| 7537 | 0.6 | 6.6667 | 13.5 | 21.9183 | 3.085 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 7538 | 0.8 | 5 | 11.4894 | 19.1035 | 3.3475 | 4.2667 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 7539 | 1.2 | 3.3333 | 9.3103 | 17.1295 | 3.9008 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 7540 | 0.8 | 5 | 9.3103 | 17.1893 | 2.8263 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 7541 | 0.8 | 5 | 15.8824 | 23.7371 | 2.9317 | 4.9231 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 7542 | 0.4 | 10 | 12.5581 | 19.0512 | 2.2264 | 4.2667 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 7543 | 0.4 | 10 | 13.1707 | 21.8224 | 2.6517 | 6 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 7544 | 1.2 | 3.3333 | 13.5 | 20.5351 | 2.95 | 4.0851 | 1 | 5 | 0.1 | 20 | 28.3333
| 7545 | 1.2 | 3.3333 | 11.4894 | 18.2558 | 3.2109 | 3.5556 | 0.8 | 6.25 | 0.8 | 2.5 | 12.0833
| 7546 | 1.4 | 2.8571 | 11.7391 | 20.972 | 3.2329 | 6 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 7547 | 0.4 | 10 | 10.3846 | 16.3784 | 2.5652 | 3.4286 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 7548 | 1 | 4 | 8.5714 | 14.2532 | 2.6818 | 3 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 7549 | 0.6 | 6.6667 | 14.5946 | 21.6999 | 3.1053 | 4 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 7550 | 0.8 | 5 | 11.4894 | 19.8427 | 3.3007 | 5.0526 | 0.2 | 25 | 0.6 | 3.3333 | 33.3333
| 7551 | 1 | 4 | 11.0204 | 18.3852 | 2.6818 | 4.6829 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 7552 | 1 | 4 | 10.5882 | 16.3208 | 2.95 | 2.7826 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 7553 | 1 | 4 | 10.1887 | 19.2428 | 2.8606 | 6.1935 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 7554 | 0.4 | 10 | 13.5 | 20.7842 | 2.4842 | 4.8 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 7555 | 0.6 | 6.6667 | 13.8462 | 24.2028 | 4.5385 | 5.8182 | 0.4 | 12.5 | 0.8 | 2.5 | 21.6667
| 7556 | 0.4 | 10 | 11.25 | 20.242 | 4.069 | 4.9231 | 1 | 5 | 0.2 | 10 | 25
| 7557 | 1 | 4 | 10.1887 | 20.4124 | 3.6031 | 6.6207 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 7558 | 1 | 4 | 11.25 | 21.1025 | 3.6589 | 6.1935 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 7559 | 0.6 | 6.6667 | 13.1707 | 19.2839 | 2.6222 | 3.4909 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 7560 | 1 | 4 | 14.2105 | 20.3612 | 2.4583 | 3.6923 | 1 | 5 | 0.1 | 20 | 29
| 7561 | 0.8 | 5 | 12.8571 | 19.4227 | 3.2552 | 3.3103 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 7562 | 0.8 | 5 | 10.3846 | 18.3529 | 3.0452 | 4.9231 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 7563 | 0.8 | 5 | 12.8571 | 20.6129 | 3.8374 | 3.9184 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 7564 | 0.6 | 6.6667 | 12.2727 | 18.6668 | 3.0256 | 3.3684 | 1.8 | 2.7778 | 0.4 | 5 | 14.4444
| 7565 | 0.6 | 6.6667 | 12.8571 | 19.4573 | 2.6818 | 3.9184 | 1 | 5 | 0.1 | 20 | 31.6667
| 7566 | 0.8 | 5 | 10.1887 | 15.5846 | 2.3483 | 3.0476 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 7567 | 1.2 | 3.3333 | 13.8462 | 22.896 | 3.7165 | 5.3333 | 1 | 5 | 0.2 | 10 | 18.3333
| 7568 | 0.8 | 5 | 11.4894 | 19.3117 | 2.3366 | 5.4857 | 1 | 5 | 0.4 | 5 | 15
| 7569 | 1 | 4 | 13.1707 | 18.6265 | 2.4082 | 3.0476 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 7570 | 1 | 4 | 11.7391 | 18.9994 | 3.4203 | 3.84 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 7571 | 1 | 4 | 10.5882 | 17.5453 | 2.5934 | 4.3636 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 7572 | 0.8 | 5 | 21.6 | 28.2507 | 3.6031 | 3.0476 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 7573 | 0.8 | 5 | 15.8824 | 24.0402 | 3.1053 | 5.0526 | 1 | 5 | 0.1 | 20 | 30
| 7574 | 1.4 | 2.8571 | 11.0204 | 22.4161 | 3.3957 | 8 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 7575 | 0.4 | 10 | 13.5 | 20.3852 | 3.0452 | 3.84 | 1 | 5 | 0.4 | 5 | 20
| 7576 | 0.8 | 5 | 10.1887 | 16.6421 | 3.085 | 3.3684 | 1 | 5 | 0.4 | 5 | 15
| 7577 | 1.2 | 3.3333 | 7.6056 | 20.0037 | 3.2552 | 9.1429 | 1 | 5 | 0.2 | 10 | 18.3333
| 7578 | 0.6 | 6.6667 | 12.5581 | 19.7082 | 3.0649 | 4.0851 | 1 | 5 | 0.6 | 3.3333 | 15
| 7579 | 1.2 | 3.3333 | 13.8462 | 21.4432 | 3.0256 | 4.5714 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 7580 | 0.8 | 5 | 10.1887 | 16.622 | 3.0649 | 3.3684 | 1 | 5 | 0.1 | 20 | 30
| 7581 | 1.2 | 3.3333 | 10.3846 | 18.0741 | 2.6369 | 5.0526 | 1 | 5 | 0.2 | 10 | 18.3333
| 7582 | 0.6 | 6.6667 | 15 | 23.5428 | 2.8957 | 5.6471 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 7583 | 1.2 | 3.3333 | 10 | 17.8916 | 2.9686 | 4.9231 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 7584 | 0.6 | 6.6667 | 18.6207 | 26.0162 | 3.6308 | 3.7647 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 7585 | 0.4 | 10 | 12.8571 | 18.8273 | 3.1467 | 2.8235 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 7586 | 0.8 | 5 | 12 | 20.2009 | 3.2778 | 4.9231 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 7587 | 0.4 | 10 | 12.5581 | 17.9456 | 2.7929 | 2.5946 | 1 | 5 | 0.8 | 2.5 | 17.5
| 7588 | 1 | 4 | 12.5581 | 19.6501 | 2.7283 | 4.3636 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 7589 | 1 | 4 | 12 | 18.95 | 2.95 | 4 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 7590 | 0.4 | 10 | 11.7391 | 21.8822 | 3.5224 | 6.6207 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 7591 | 0.6 | 6.6667 | 15 | 23.7786 | 3.4453 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 7592 | 0.2 | 20 | 16.875 | 23.675 | 3.3714 | 3.4286 | 1 | 5 | 0.4 | 5 | 30
| 7593 | 0.8 | 5 | 10.1887 | 17.8998 | 3.3475 | 4.3636 | 1 | 5 | 0.4 | 5 | 15
| 7594 | 1 | 4 | 10.3846 | 16.2474 | 2.3719 | 3.4909 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 7595 | 1 | 4 | 9.8182 | 20.0222 | 2.5241 | 7.68 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 7596 | 0.6 | 6.6667 | 13.5 | 20.96 | 3.8374 | 3.6226 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 7597 | 0.6 | 6.6667 | 13.5 | 19.8724 | 2.6077 | 3.7647 | 1 | 5 | 0.4 | 5 | 16.6667
| 7598 | 0.8 | 5 | 13.8462 | 23.394 | 3.9008 | 5.6471 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 7599 | 0.6 | 6.6667 | 19.2857 | 26.4674 | 4.0342 | 3.1475 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 7600 | 0.8 | 5 | 10.8 | 18.1403 | 3.2552 | 4.0851 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 7601 | 1 | 4 | 18 | 27.2888 | 3.4706 | 5.8182 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 7602 | 1 | 4 | 12.8571 | 19.9451 | 3.3957 | 3.6923 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 7603 | 0.6 | 6.6667 | 11.0204 | 20.9024 | 2.4974 | 7.3846 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 7604 | 0.8 | 5 | 11.4894 | 22.1493 | 3.5489 | 7.1111 | 1 | 5 | 0.1 | 20 | 30
| 7605 | 1 | 4 | 11.0204 | 17.2268 | 3.0064 | 3.2 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 7606 | 1 | 4 | 7.5 | 18.7614 | 2.9136 | 8.3478 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 7607 | 0.8 | 5 | 13.1707 | 19.2369 | 2.5106 | 3.5556 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 7608 | 0.8 | 5 | 13.5 | 20.6996 | 3.0256 | 4.1739 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 7609 | 1.6 | 2.5 | 12.2727 | 20.93 | 3.3239 | 5.3333 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10
| 7610 | 0.6 | 6.6667 | 7.8261 | 15.3177 | 2.3024 | 5.1892 | 1 | 5 | 0.4 | 5 | 16.6667
| 7611 | 0.8 | 5 | 11.4894 | 18.1695 | 3.1892 | 3.4909 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 7612 | 0.4 | 10 | 15 | 21.0139 | 2.4583 | 3.5556 | 1.6 | 3.125 | 0.6 | 3.3333 | 16.4583
| 7613 | 1 | 4 | 12.5581 | 20.887 | 2.6818 | 5.6471 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7614 | 1 | 4 | 9.1525 | 16.1334 | 2.8957 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7615 | 1.4 | 2.8571 | 15.4286 | 24.0195 | 3.1053 | 5.4857 | 0.8 | 6.25 | 0.1 | 20 | 29.1071
| 7616 | 0.4 | 10 | 13.1707 | 22.1567 | 3.9333 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 7617 | 0.8 | 5 | 11.4894 | 18.7002 | 3.2109 | 4 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 7618 | 0.1 | 40 | 10.1887 | 18.7679 | 2.5792 | 6 | 1.2 | 4.1667 | 0.2 | 10 | 54.1667
| 7619 | 1 | 4 | 8.3077 | 16.1819 | 4.0342 | 3.84 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.8333
| 7620 | 0.6 | 6.6667 | 8.5714 | 17.1023 | 3.0452 | 5.4857 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 7621 | 1 | 4 | 10.8 | 18.7843 | 2.9317 | 5.0526 | 0.4 | 12.5 | 0.2 | 10 | 26.5
| 7622 | 0.8 | 5 | 10.5882 | 21.3657 | 5.1304 | 5.6471 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 7623 | 0.8 | 5 | 14.2105 | 21.9373 | 2.5376 | 5.1892 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 7624 | 1.4 | 2.8571 | 12.5581 | 20.2057 | 2.4583 | 5.1892 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 7625 | 0.6 | 6.6667 | 15 | 20.7442 | 2.7442 | 3 | 1 | 5 | 0.2 | 10 | 21.6667
| 7626 | 1 | 4 | 15 | 21.5529 | 2.8606 | 3.6923 | 1 | 5 | 0.4 | 5 | 14
| 7627 | 0.8 | 5 | 9 | 15.0976 | 2.8434 | 3.2542 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 7628 | 0.4 | 10 | 11.25 | 18.4609 | 3.2109 | 4 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 7629 | 1 | 4 | 8.8525 | 17.8937 | 2.4205 | 6.6207 | 0.4 | 12.5 | 0.2 | 10 | 26.5
| 7630 | 0.4 | 10 | 16.875 | 22.9451 | 2.5792 | 3.4909 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 7631 | 1 | 4 | 10.5882 | 17.4031 | 3.3239 | 3.4909 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 7632 | 1.2 | 3.3333 | 9.4737 | 16.8885 | 2.8434 | 4.5714 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 7633 | 0.6 | 6.6667 | 17.4194 | 26.28 | 2.8606 | 6 | 0.4 | 12.5 | 0.2 | 10 | 29.1667
| 7634 | 1.2 | 3.3333 | 11.25 | 18.5636 | 2.95 | 4.3636 | 1 | 5 | 0.2 | 10 | 18.3333
| 7635 | 0.6 | 6.6667 | 15.4286 | 23.8287 | 3.3475 | 5.0526 | 1 | 5 | 0.6 | 3.3333 | 15
| 7636 | 0.8 | 5 | 11.25 | 18.315 | 3.1467 | 3.9184 | 1.6 | 3.125 | 0.6 | 3.3333 | 11.4583
| 7637 | 0.6 | 6.6667 | 10 | 15.3892 | 2.8957 | 2.4935 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 7638 | 0.8 | 5 | 13.8462 | 21.1572 | 2.2584 | 5.0526 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 7639 | 0.6 | 6.6667 | 9.8182 | 17.4884 | 3.4963 | 4.1739 | 1.2 | 4.1667 | 1 | 2 | 12.8333
| 7640 | 1.2 | 3.3333 | 10.3846 | 17.89 | 3.4203 | 4.0851 | 1 | 5 | 0.4 | 5 | 13.3333
| 7641 | 1 | 4 | 12 | 17.816 | 2.3251 | 3.4909 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 7642 | 0.8 | 5 | 12.8571 | 19.6019 | 3.1892 | 3.5556 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 7643 | 1.2 | 3.3333 | 12.5581 | 19.6747 | 4.069 | 3.0476 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 7644 | 1.2 | 3.3333 | 10.8 | 18.8155 | 2.8263 | 5.1892 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 7645 | 0.6 | 6.6667 | 10.3846 | 17.3481 | 3.0452 | 3.9184 | 1 | 5 | 0.4 | 5 | 16.6667
| 7646 | 0.8 | 5 | 11.4894 | 17.9671 | 3.2778 | 3.2 | 0.4 | 12.5 | 0.6 | 3.3333 | 20.8333
| 7647 | 0.6 | 6.6667 | 8.5714 | 14.3978 | 2.8263 | 3 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 7648 | 0.4 | 10 | 14.5946 | 20.9202 | 3.6589 | 2.6667 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 7649 | 0.4 | 10 | 11.25 | 18.1966 | 3.3239 | 3.6226 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 7650 | 0.8 | 5 | 12.5581 | 19.3371 | 2.8606 | 3.9184 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 7651 | 0.8 | 5 | 11.0204 | 17.8477 | 2.9873 | 3.84 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 7652 | 0.2 | 20 | 11.0204 | 16.0846 | 2.36 | 2.7042 | 1.8 | 2.7778 | 0.2 | 10 | 32.7778
| 7653 | 0.6 | 6.6667 | 13.1707 | 21.8541 | 3.6308 | 5.0526 | 1 | 5 | 0.2 | 10 | 21.6667
| 7654 | 0.8 | 5 | 12 | 20.1355 | 3.8689 | 4.2667 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 7655 | 0.8 | 5 | 11.4894 | 21.1769 | 3.6875 | 6 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 7656 | 1 | 4 | 11.7391 | 16.4855 | 2.6818 | 2.0645 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 7657 | 0.8 | 5 | 13.1707 | 22.2872 | 3.6308 | 5.4857 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 7658 | 0.2 | 20 | 8.1818 | 18.1849 | 3.6031 | 6.4 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 7659 | 1.6 | 2.5 | 9.3103 | 15.8046 | 3.1258 | 3.3684 | 1.2 | 4.1667 | 0.8 | 2.5 | 9.1667
| 7660 | 0.8 | 5 | 12.2727 | 20.551 | 4.1043 | 4.1739 | 1 | 5 | 1 | 2 | 12
| 7661 | 1.4 | 2.8571 | 12.8571 | 23.29 | 3.5758 | 6.8571 | 1 | 5 | 0.2 | 10 | 17.8571
| 7662 | 0.6 | 6.6667 | 12.5581 | 23.8412 | 3.6031 | 7.68 | 1 | 5 | 0.4 | 5 | 16.6667
| 7663 | 1.2 | 3.3333 | 10.8 | 17.9904 | 3.1053 | 4.0851 | 1 | 5 | 0.4 | 5 | 13.3333
| 7664 | 1.4 | 2.8571 | 12 | 19.616 | 3.776 | 3.84 | 1.4 | 3.5714 | 0.4 | 5 | 11.4286
| 7665 | 0.8 | 5 | 17.4194 | 26.229 | 3.3239 | 5.4857 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 7666 | 0.4 | 10 | 10.1887 | 18.4428 | 3.0649 | 5.1892 | 1 | 5 | 0.4 | 5 | 20
| 7667 | 0.4 | 10 | 10.1887 | 17.3773 | 3.4963 | 3.6923 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 7668 | 1 | 4 | 10 | 17.844 | 2.5106 | 5.3333 | 1 | 5 | 0.2 | 10 | 19
| 7669 | 1 | 4 | 8.5714 | 16.5783 | 3.3239 | 4.6829 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 7670 | 1.2 | 3.3333 | 11.7391 | 18.7823 | 2.7765 | 4.2667 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 7671 | 0.4 | 10 | 10.5882 | 17.2122 | 2.9317 | 3.6923 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 7672 | 0.6 | 6.6667 | 15 | 24.3406 | 3.5224 | 5.8182 | 1.6 | 3.125 | 0.4 | 5 | 14.7917
| 7673 | 0.2 | 20 | 11.0204 | 19.1648 | 2.4974 | 5.6471 | 1 | 5 | 0.1 | 20 | 45
| 7674 | 0.8 | 5 | 8.8525 | 17.1999 | 3.776 | 4.5714 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 7675 | 0.8 | 5 | 10.8 | 17.2207 | 3.3239 | 3.0968 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 7676 | 0.6 | 6.6667 | 10.3846 | 17.7533 | 3.746 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 7677 | 0.6 | 6.6667 | 10.3846 | 19.7321 | 3.3475 | 6 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 7678 | 1 | 4 | 12 | 17.2524 | 2.6222 | 2.6301 | 1.4 | 3.5714 | 0.1 | 20 | 27.5714
| 7679 | 0.8 | 5 | 11.4894 | 18.7891 | 2.7283 | 4.5714 | 1.6 | 3.125 | 0.2 | 10 | 18.125
| 7680 | 1.2 | 3.3333 | 13.1707 | 24.0664 | 2.8957 | 8 | 1 | 5 | 0.2 | 10 | 18.3333
| 7681 | 1.2 | 3.3333 | 10 | 16.8133 | 3.7165 | 3.0968 | 1 | 5 | 0.4 | 5 | 13.3333
| 7682 | 1 | 4 | 7.3973 | 14.565 | 3.1678 | 4 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 7683 | 0.4 | 10 | 14.2105 | 22.6098 | 2.9136 | 5.4857 | 1.6 | 3.125 | 0.6 | 3.3333 | 16.4583
| 7684 | 1.4 | 2.8571 | 11.4894 | 20.8759 | 3.9008 | 5.4857 | 1 | 5 | 0.4 | 5 | 12.8571
| 7685 | 0.6 | 6.6667 | 10.5882 | 17.5395 | 3.3957 | 3.5556 | 1 | 5 | 0.6 | 3.3333 | 15
| 7686 | 1 | 4 | 14.2105 | 22.053 | 3.5758 | 4.2667 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7687 | 0.4 | 10 | 15.4286 | 21.9063 | 3.2778 | 3.2 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 7688 | 0.6 | 6.6667 | 18.6207 | 27.5999 | 2.5792 | 6.4 | 1 | 5 | 0.4 | 5 | 16.6667
| 7689 | 1.4 | 2.8571 | 11.7391 | 18.8116 | 2.9873 | 4.0851 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 7690 | 0.1 | 40 | 10.1887 | 16.1772 | 2.433 | 3.5556 | 0.8 | 6.25 | 0.6 | 3.3333 | 49.5833
| 7691 | 0.8 | 5 | 16.875 | 22.6134 | 2.4842 | 3.2542 | 1.8 | 2.7778 | 0.4 | 5 | 12.7778
| 7692 | 0.6 | 6.6667 | 12 | 20.0697 | 3.1467 | 4.9231 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 7693 | 1 | 4 | 10 | 19.3402 | 3.1467 | 6.1935 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 7694 | 0.4 | 10 | 10.5882 | 19.5621 | 4.2909 | 4.6829 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 7695 | 0.2 | 20 | 11.4894 | 18.4518 | 2.4974 | 4.4651 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 7696 | 0.4 | 10 | 11.25 | 18.9333 | 2.7602 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 7697 | 0.6 | 6.6667 | 11.4894 | 19.7212 | 3.5489 | 4.6829 | 0.6 | 8.3333 | 0.8 | 2.5 | 17.5
| 7698 | 0.8 | 5 | 10.3846 | 20.2089 | 3.6308 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 7699 | 1 | 4 | 12 | 17.974 | 3.0649 | 2.9091 | 1 | 5 | 0.2 | 10 | 19
| 7700 | 1.2 | 3.3333 | 10 | 18.4073 | 2.7602 | 5.6471 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 7701 | 0.6 | 6.6667 | 8.8525 | 15.5637 | 2.7929 | 3.9184 | 1 | 5 | 0.4 | 5 | 16.6667
| 7702 | 1 | 4 | 9.6429 | 16.5745 | 2.9317 | 4 | 1 | 5 | 0.8 | 2.5 | 11.5
| 7703 | 1 | 4 | 10 | 16.7293 | 3.3007 | 3.4286 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7704 | 0.6 | 6.6667 | 12.2727 | 20.5031 | 3.6589 | 4.5714 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 7705 | 1.4 | 2.8571 | 8.3077 | 17.2937 | 3.1678 | 5.8182 | 1 | 5 | 0.2 | 10 | 17.8571
| 7706 | 0.4 | 10 | 17.4194 | 24.3733 | 3.8065 | 3.1475 | 1.6 | 3.125 | 0.6 | 3.3333 | 16.4583
| 7707 | 0.8 | 5 | 10.8 | 16.2917 | 2.9317 | 2.56 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 7708 | 1.2 | 3.3333 | 10.5882 | 17.8835 | 2.9317 | 4.3636 | 1.4 | 3.5714 | 0.8 | 2.5 | 9.4048
| 7709 | 0.6 | 6.6667 | 11.0204 | 18.4475 | 2.7442 | 4.6829 | 1 | 5 | 0.4 | 5 | 16.6667
| 7710 | 1 | 4 | 7.6056 | 15.8078 | 3.6308 | 4.5714 | 0.2 | 25 | 0.4 | 5 | 34
| 7711 | 1.2 | 3.3333 | 12.8571 | 22.6528 | 3.3957 | 6.4 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 7712 | 1 | 4 | 9.3103 | 16.2561 | 2.8606 | 4.0851 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 7713 | 0.6 | 6.6667 | 13.5 | 18.8674 | 2.4583 | 2.9091 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 7714 | 0.4 | 10 | 12.2727 | 18.7496 | 2.6369 | 3.84 | 1 | 5 | 0.4 | 5 | 20
| 7715 | 0.8 | 5 | 14.2105 | 20.7658 | 2.6369 | 3.9184 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 7716 | 0.6 | 6.6667 | 13.1707 | 20.1211 | 2.7765 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 7717 | 0.4 | 10 | 12.2727 | 21.6112 | 4.5385 | 4.8 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 7718 | 0.8 | 5 | 12.5581 | 18.9066 | 2.7929 | 3.5556 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 7719 | 0.8 | 5 | 11.7391 | 19.7266 | 3.5224 | 4.4651 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 7720 | 0.8 | 5 | 14.2105 | 19.3997 | 3.1892 | 2 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 7721 | 0.4 | 10 | 13.1707 | 20.7853 | 2.9317 | 4.6829 | 1 | 5 | 1 | 2 | 17
| 7722 | 0.8 | 5 | 18.6207 | 25.1966 | 3.085 | 3.4909 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 7723 | 0.4 | 10 | 10.3846 | 15.2476 | 2.3366 | 2.5263 | 1.6 | 3.125 | 0.2 | 10 | 23.125
| 7724 | 0.6 | 6.6667 | 14.2105 | 22.0679 | 2.5241 | 5.3333 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 7725 | 1 | 4 | 10.5882 | 16.3602 | 3.1053 | 2.6667 | 1 | 5 | 0.4 | 5 | 14
| 7726 | 1 | 4 | 12.5581 | 23.8376 | 2.9317 | 8.3478 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 7727 | 1 | 4 | 8.0597 | 14.5968 | 2.6971 | 3.84 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 7728 | 0.4 | 10 | 13.1707 | 22.2834 | 2.7126 | 6.4 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 7729 | 1.4 | 2.8571 | 13.5 | 19.7566 | 3.3475 | 2.9091 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 7730 | 0.4 | 10 | 18.6207 | 24.2524 | 2.4842 | 3.1475 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 7731 | 0.6 | 6.6667 | 11.7391 | 18.4378 | 3.0064 | 3.6923 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 7732 | 1 | 4 | 11.0204 | 19.3508 | 3.2778 | 5.0526 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 7733 | 0.2 | 20 | 10.1887 | 18.267 | 3.0256 | 5.0526 | 0.8 | 6.25 | 0.1 | 20 | 46.25
| 7734 | 1.2 | 3.3333 | 10.8 | 17.5822 | 2.6971 | 4.0851 | 1 | 5 | 0.4 | 5 | 13.3333
| 7735 | 0.2 | 20 | 9 | 16.8817 | 4.6275 | 3.2542 | 0.6 | 8.3333 | 0.1 | 20 | 48.3333
| 7736 | 1.2 | 3.3333 | 12.8571 | 19.6475 | 3.0256 | 3.7647 | 1 | 5 | 0.2 | 10 | 18.3333
| 7737 | 0.6 | 6.6667 | 10.5882 | 19.1792 | 3.1053 | 5.4857 | 1 | 5 | 0.2 | 10 | 21.6667
| 7738 | 1 | 4 | 9 | 15.2753 | 2.5106 | 3.7647 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 7739 | 1 | 4 | 9.8182 | 15.5829 | 2 | 3.7647 | 1 | 5 | 0.2 | 10 | 19
| 7740 | 0.6 | 6.6667 | 12.8571 | 18.8509 | 2.5652 | 3.4286 | 1 | 5 | 0.6 | 3.3333 | 15
| 7741 | 1.6 | 2.5 | 11.0204 | 21.9556 | 3.2552 | 7.68 | 0.6 | 8.3333 | 0.4 | 5 | 15.8333
| 7742 | 0.8 | 5 | 9.1525 | 21.5732 | 3.2778 | 9.1429 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 7743 | 1.2 | 3.3333 | 15 | 22.0556 | 2.4842 | 4.5714 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 7744 | 1 | 4 | 13.8462 | 24.5325 | 3.0064 | 7.68 | 1 | 5 | 0.2 | 10 | 19
| 7745 | 0.8 | 5 | 9.1525 | 18.2706 | 2.4974 | 6.6207 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 7746 | 0.1 | 40 | 14.5946 | 22.2816 | 3.4203 | 4.2667 | 1.8 | 2.7778 | 0.1 | 20 | 62.7778
| 7747 | 0.4 | 10 | 8.8525 | 16.5292 | 3.1053 | 4.5714 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 7748 | 0.8 | 5 | 7.6056 | 14.7164 | 3.0256 | 4.0851 | 1 | 5 | 0.2 | 10 | 20
| 7749 | 1 | 4 | 16.875 | 24.7006 | 3.0256 | 4.8 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 7750 | 1 | 4 | 20 | 29.5642 | 3.746 | 5.8182 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 7751 | 0.6 | 6.6667 | 11.25 | 19.2726 | 3.6589 | 4.3636 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 7752 | 0.6 | 6.6667 | 12 | 19.8731 | 2.95 | 4.9231 | 1.4 | 3.5714 | 0.8 | 2.5 | 12.7381
| 7753 | 0.4 | 10 | 12 | 22.0309 | 3.8374 | 6.1935 | 1 | 5 | 0.4 | 5 | 20
| 7754 | 0.6 | 6.6667 | 10.1887 | 18.6455 | 4.5385 | 3.9184 | 0.4 | 12.5 | 0.1 | 20 | 39.1667
| 7755 | 0.6 | 6.6667 | 14.2105 | 20.5404 | 2.5652 | 3.7647 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 7756 | 0.2 | 20 | 18 | 26.2945 | 3.1053 | 5.1892 | 1 | 5 | 0.4 | 5 | 30
| 7757 | 0.8 | 5 | 8.1818 | 14.7293 | 3.3475 | 3.2 | 1 | 5 | 0.4 | 5 | 15
| 7758 | 1.4 | 2.8571 | 11.7391 | 21.4396 | 2.8434 | 6.8571 | 0.6 | 8.3333 | 0.8 | 2.5 | 13.6905
| 7759 | 1.2 | 3.3333 | 11.7391 | 21.1897 | 2.5934 | 6.8571 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 7760 | 0.4 | 10 | 12.2727 | 20.3662 | 2.6077 | 5.4857 | 0.6 | 8.3333 | 0.1 | 20 | 38.3333
| 7761 | 0.8 | 5 | 12.2727 | 21.106 | 3.3475 | 5.4857 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 7762 | 0.6 | 6.6667 | 11.4894 | 16.9273 | 2.8434 | 2.5946 | 1.4 | 3.5714 | 0.1 | 20 | 30.2381
| 7763 | 0.4 | 10 | 20.7692 | 29.1279 | 2.1651 | 6.1935 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 7764 | 0.6 | 6.6667 | 13.5 | 20.8629 | 3.2778 | 4.0851 | 1 | 5 | 0.2 | 10 | 21.6667
| 7765 | 0.8 | 5 | 13.8462 | 22.3951 | 3.4963 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 7766 | 0.6 | 6.6667 | 23.4783 | 31.7475 | 2.6222 | 5.6471 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 7767 | 1 | 4 | 10.5882 | 18.1383 | 3.085 | 4.4651 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 7768 | 1 | 4 | 12.8571 | 18.7543 | 2.6971 | 3.2 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 7769 | 0.6 | 6.6667 | 11.4894 | 21.6068 | 3.0064 | 7.1111 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 7770 | 0.6 | 6.6667 | 12.8571 | 17.7712 | 2.4205 | 2.4935 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 7771 | 0.6 | 6.6667 | 10.5882 | 19.9597 | 3.3714 | 6 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 7772 | 0.6 | 6.6667 | 16.875 | 24.5221 | 2.3137 | 5.3333 | 1 | 5 | 0.4 | 5 | 16.6667
| 7773 | 1.2 | 3.3333 | 10 | 21.2379 | 2.5106 | 8.7273 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 7774 | 0.6 | 6.6667 | 11.4894 | 17.44 | 3.085 | 2.8657 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 7775 | 0.8 | 5 | 13.5 | 20.0701 | 2.6517 | 3.9184 | 1 | 5 | 0.4 | 5 | 15
| 7776 | 0.4 | 10 | 9 | 18.5804 | 3.9333 | 5.6471 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 7777 | 0.6 | 6.6667 | 11.7391 | 20.0866 | 3.776 | 4.5714 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 7778 | 1.2 | 3.3333 | 18.6207 | 26.8993 | 2.7929 | 5.4857 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 7779 | 1 | 4 | 21.6 | 30.9333 | 4 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 7780 | 1 | 4 | 9.4737 | 15.6976 | 2.9136 | 3.3103 | 1.4 | 3.5714 | 0.1 | 20 | 27.5714
| 7781 | 0.1 | 40 | 15.8824 | 21.8753 | 2.7929 | 3.2 | 1 | 5 | 0.6 | 3.3333 | 48.3333
| 7782 | 0.8 | 5 | 7.8261 | 15.5759 | 2.6971 | 5.0526 | 1 | 5 | 0.4 | 5 | 15
| 7783 | 1.2 | 3.3333 | 16.3636 | 21.3441 | 2.4205 | 2.56 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 7784 | 1.2 | 3.3333 | 14.2105 | 23.1483 | 2.7442 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 7785 | 1.2 | 3.3333 | 16.3636 | 24.0722 | 3.0256 | 4.6829 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 7786 | 1.4 | 2.8571 | 18.6207 | 27.8302 | 2.8095 | 6.4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 7787 | 1 | 4 | 11.7391 | 20.664 | 3.2778 | 5.6471 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 7788 | 0.8 | 5 | 12.8571 | 21.3492 | 3.0064 | 5.4857 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 7789 | 0.8 | 5 | 9.3103 | 15.7726 | 2.6222 | 3.84 | 1 | 5 | 0.2 | 10 | 20
| 7790 | 0.4 | 10 | 15.8824 | 24.4486 | 3.2329 | 5.3333 | 1 | 5 | 0.2 | 10 | 25
| 7791 | 0.8 | 5 | 11.0204 | 18.1025 | 2.5106 | 4.5714 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 7792 | 1 | 4 | 15 | 21.6706 | 3.4706 | 3.2 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 7793 | 1.2 | 3.3333 | 15 | 21.8181 | 3.1258 | 3.6923 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 7794 | 0.4 | 10 | 15.4286 | 22.3243 | 2.8957 | 4 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 7795 | 1 | 4 | 10.8 | 16.7317 | 2.9317 | 3 | 1 | 5 | 0.4 | 5 | 14
| 7796 | 0.4 | 10 | 12.2727 | 17.4821 | 2.5792 | 2.6301 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 7797 | 0.8 | 5 | 12.2727 | 19.8692 | 2.9136 | 4.6829 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 7798 | 1.2 | 3.3333 | 9 | 17.042 | 3.4706 | 4.5714 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 7799 | 0.6 | 6.6667 | 12.5581 | 20.3646 | 3.8065 | 4 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 7800 | 0.6 | 6.6667 | 10.5882 | 20.5656 | 4.3303 | 5.6471 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 7801 | 0.6 | 6.6667 | 12 | 18.2222 | 2.6667 | 3.5556 | 1 | 5 | 0.2 | 10 | 21.6667
| 7802 | 0.8 | 5 | 16.875 | 23.7023 | 2.9873 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 7803 | 0.6 | 6.6667 | 13.1707 | 22.892 | 2.3366 | 7.3846 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 7804 | 1 | 4 | 12.2727 | 18.9528 | 3.1892 | 3.4909 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 7805 | 0.4 | 10 | 11.7391 | 19.6998 | 3.2778 | 4.6829 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 7806 | 1 | 4 | 12.5581 | 19.5219 | 2.6971 | 4.2667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 7807 | 0.8 | 5 | 10 | 18.7024 | 2.3024 | 6.4 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 7808 | 0.8 | 5 | 11.0204 | 16.9359 | 3.0064 | 2.9091 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 7809 | 0.6 | 6.6667 | 15.8824 | 22.2102 | 2.0611 | 4.2667 | 0.6 | 8.3333 | 0.1 | 20 | 35
| 7810 | 0.4 | 10 | 11.7391 | 19.3087 | 3.3957 | 4.1739 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 7811 | 0.8 | 5 | 14.5946 | 22.2092 | 2.9317 | 4.6829 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 7812 | 0.4 | 10 | 15.8824 | 22.418 | 2.8434 | 3.6923 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 7813 | 1 | 4 | 9.6429 | 17.4492 | 3.0064 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7814 | 1.2 | 3.3333 | 11.25 | 20.1242 | 2.0171 | 6.8571 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 7815 | 0.8 | 5 | 12 | 20.6236 | 4.5385 | 4.0851 | 1 | 5 | 0.4 | 5 | 15
| 7816 | 1 | 4 | 11.0204 | 20.8089 | 3.1678 | 6.6207 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 7817 | 1.6 | 2.5 | 9.6429 | 18.7162 | 3.2552 | 5.8182 | 1.2 | 4.1667 | 0.1 | 20 | 26.6667
| 7818 | 1.2 | 3.3333 | 13.8462 | 21.4653 | 3.4453 | 4.1739 | 1 | 5 | 0.4 | 5 | 13.3333
| 7819 | 1.4 | 2.8571 | 10.5882 | 15.7157 | 2.4974 | 2.6301 | 0.6 | 8.3333 | 0.6 | 3.3333 | 14.5238
| 7820 | 0.6 | 6.6667 | 11.4894 | 19.1096 | 2.6971 | 4.9231 | 1 | 5 | 0.1 | 20 | 31.6667
| 7821 | 0.8 | 5 | 12 | 19.1361 | 3.3714 | 3.7647 | 1.6 | 3.125 | 0.8 | 2.5 | 10.625
| 7822 | 0.2 | 20 | 11.25 | 17.4859 | 2.4712 | 3.7647 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 7823 | 1.2 | 3.3333 | 14.2105 | 21.0971 | 2.7126 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 7824 | 0.6 | 6.6667 | 10.3846 | 18.0389 | 3.1892 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 15
| 7825 | 0.6 | 6.6667 | 10.8 | 17.0134 | 3.4706 | 2.7429 | 1 | 5 | 0.2 | 10 | 21.6667
| 7826 | 0.8 | 5 | 12.5581 | 21.3868 | 3.776 | 5.0526 | 1 | 5 | 0.4 | 5 | 15
| 7827 | 0.4 | 10 | 12 | 19.716 | 2.7929 | 4.9231 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 7828 | 0.6 | 6.6667 | 12.2727 | 19.8802 | 3.5224 | 4.0851 | 1 | 5 | 0.6 | 3.3333 | 15
| 7829 | 1 | 4 | 15.4286 | 21.2952 | 2.6667 | 3.2 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 7830 | 0.8 | 5 | 10.3846 | 17.0049 | 3.4203 | 3.2 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 7831 | 1 | 4 | 10.5882 | 17.9392 | 2.9873 | 4.3636 | 1 | 5 | 0.4 | 5 | 14
| 7832 | 1.4 | 2.8571 | 12 | 20.1782 | 3.2552 | 4.9231 | 1 | 5 | 0.4 | 5 | 12.8571
| 7833 | 0.8 | 5 | 12.8571 | 20.6883 | 3.746 | 4.0851 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 7834 | 0.6 | 6.6667 | 12.2727 | 20.5561 | 2.95 | 5.3333 | 1 | 5 | 0.6 | 3.3333 | 15
| 7835 | 1 | 4 | 14.5946 | 23.0845 | 3.3007 | 5.1892 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 7836 | 0.8 | 5 | 16.3636 | 23.562 | 2.9317 | 4.2667 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 7837 | 1.2 | 3.3333 | 12 | 19.5185 | 2.1852 | 5.3333 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 7838 | 0.8 | 5 | 11.25 | 18.1975 | 3.2552 | 3.6923 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 7839 | 1 | 4 | 10.1887 | 19.4521 | 3.4453 | 5.8182 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 7840 | 0.4 | 10 | 10.3846 | 19.5035 | 3.3007 | 5.8182 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 7841 | 1.2 | 3.3333 | 12 | 17.5024 | 3.1892 | 2.3133 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 7842 | 1 | 4 | 11.25 | 19.374 | 3.6589 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 7843 | 0.6 | 6.6667 | 6.6667 | 21.925 | 2.4583 | 12.8 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 7844 | 0.4 | 10 | 12.5581 | 20.4192 | 3.776 | 4.0851 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 7845 | 0.6 | 6.6667 | 13.5 | 21.0304 | 3.4453 | 4.0851 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 7846 | 1.2 | 3.3333 | 10.3846 | 19.2327 | 3.6589 | 5.1892 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 7847 | 0.6 | 6.6667 | 13.5 | 22.3633 | 3.0452 | 5.8182 | 1 | 5 | 0.4 | 5 | 16.6667
| 7848 | 1 | 4 | 13.8462 | 23.2506 | 3.2109 | 6.1935 | 1 | 5 | 0.2 | 10 | 19
| 7849 | 0.6 | 6.6667 | 11.0204 | 18.0872 | 2.3838 | 4.6829 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 7850 | 0.6 | 6.6667 | 12 | 19.1719 | 2.3719 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 7851 | 0.6 | 6.6667 | 11.4894 | 17.9029 | 3.0452 | 3.3684 | 1.2 | 4.1667 | 1 | 2 | 12.8333
| 7852 | 0.2 | 20 | 11.25 | 18.0102 | 2.7602 | 4 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 7853 | 0.4 | 10 | 13.1707 | 18.8912 | 3.1258 | 2.5946 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 7854 | 1.6 | 2.5 | 12.8571 | 21.822 | 3.1467 | 5.8182 | 1.2 | 4.1667 | 0.2 | 10 | 16.6667
| 7855 | 1 | 4 | 10.1887 | 16.2697 | 2.7126 | 3.3684 | 1 | 5 | 0.4 | 5 | 14
| 7856 | 1 | 4 | 11.4894 | 17.9216 | 2.2584 | 4.1739 | 1 | 5 | 0.2 | 10 | 19
| 7857 | 1 | 4 | 10 | 16.5934 | 2.5934 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7858 | 1 | 4 | 13.8462 | 20.3873 | 2.7765 | 3.7647 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7859 | 0.8 | 5 | 15.8824 | 25.3275 | 3.0452 | 6.4 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 7860 | 0.8 | 5 | 15 | 24.7475 | 3.3475 | 6.4 | 1.6 | 3.125 | 0.2 | 10 | 18.125
| 7861 | 0.2 | 20 | 13.8462 | 26.8914 | 3.4453 | 9.6 | 0.8 | 6.25 | 0.2 | 10 | 36.25
| 7862 | 1.2 | 3.3333 | 12 | 19.0696 | 2.8957 | 4.1739 | 1.4 | 3.5714 | 0.8 | 2.5 | 9.4048
| 7863 | 0.8 | 5 | 12.8571 | 21.3114 | 2.9686 | 5.4857 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 7864 | 1 | 4 | 10.3846 | 18.2174 | 3.6589 | 4.1739 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 7865 | 0.6 | 6.6667 | 11.7391 | 20.3502 | 3.2778 | 5.3333 | 1 | 5 | 0.6 | 3.3333 | 15
| 7866 | 0.8 | 5 | 9.6429 | 19.7685 | 2.4456 | 7.68 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 7867 | 1.2 | 3.3333 | 10.3846 | 18.1737 | 3.5224 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 7868 | 1.2 | 3.3333 | 9.8182 | 19.694 | 3.2552 | 6.6207 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 7869 | 0.6 | 6.6667 | 10.5882 | 16.5964 | 2.8606 | 3.1475 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 7870 | 1 | 4 | 9.4737 | 19.0284 | 4.069 | 5.4857 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 7871 | 1 | 4 | 12 | 19.7968 | 2.7442 | 5.0526 | 1 | 5 | 0.2 | 10 | 19
| 7872 | 1 | 4 | 11.4894 | 19.0347 | 3.3714 | 4.1739 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 7873 | 1.2 | 3.3333 | 13.8462 | 19.933 | 2.7765 | 3.3103 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 7874 | 1 | 4 | 9.8182 | 15.8412 | 2.7126 | 3.3103 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7875 | 0.6 | 6.6667 | 11.7391 | 19.1464 | 2.4842 | 4.9231 | 1.6 | 3.125 | 0.4 | 5 | 14.7917
| 7876 | 1 | 4 | 13.1707 | 19.2868 | 2.9686 | 3.1475 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 7877 | 1.4 | 2.8571 | 15.8824 | 22.2775 | 3.3475 | 3.0476 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 7878 | 1 | 4 | 16.3636 | 24.1527 | 3.5224 | 4.2667 | 1 | 5 | 0.2 | 10 | 19
| 7879 | 0.6 | 6.6667 | 11.0204 | 17.4895 | 2.9136 | 3.5556 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 7880 | 0.6 | 6.6667 | 15.4286 | 23.8521 | 2.7765 | 5.6471 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 7881 | 1 | 4 | 14.2105 | 20.8556 | 2.4712 | 4.1739 | 1 | 5 | 0.8 | 2.5 | 11.5
| 7882 | 0.6 | 6.6667 | 15.4286 | 24.8498 | 3.6031 | 5.8182 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 7883 | 1.4 | 2.8571 | 15 | 26.4203 | 3.4203 | 8 | 1 | 5 | 0.2 | 10 | 17.8571
| 7884 | 1 | 4 | 13.5 | 19.4209 | 2.6667 | 3.2542 | 1 | 5 | 0.4 | 5 | 14
| 7885 | 1.2 | 3.3333 | 11.0204 | 17.6514 | 2.7126 | 3.9184 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 7886 | 1 | 4 | 11.25 | 19.73 | 3.1467 | 5.3333 | 1 | 5 | 0.8 | 2.5 | 11.5
| 7887 | 0.6 | 6.6667 | 10.3846 | 18.3846 | 2.6667 | 5.3333 | 1 | 5 | 0.4 | 5 | 16.6667
| 7888 | 1 | 4 | 11.0204 | 20.015 | 3.3475 | 5.6471 | 1.4 | 3.5714 | 0.1 | 20 | 27.5714
| 7889 | 1 | 4 | 14.5946 | 20.8036 | 3.2552 | 2.9538 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 7890 | 0.6 | 6.6667 | 15 | 21.3256 | 3.6589 | 2.6667 | 1.6 | 3.125 | 0.4 | 5 | 14.7917
| 7891 | 0.6 | 6.6667 | 13.1707 | 20.5685 | 2.8263 | 4.5714 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 7892 | 1 | 4 | 9.6429 | 14.6612 | 2.4583 | 2.56 | 1 | 5 | 0.2 | 10 | 19
| 7893 | 1.4 | 2.8571 | 11.4894 | 18.4579 | 2.9686 | 4 | 1 | 5 | 0.4 | 5 | 12.8571
| 7894 | 1 | 4 | 12.8571 | 19.2561 | 2.8434 | 3.5556 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 7895 | 0.6 | 6.6667 | 15.4286 | 23.9274 | 3.5758 | 4.9231 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 7896 | 0.8 | 5 | 8.7097 | 15.7161 | 3.8065 | 3.2 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 7897 | 0.8 | 5 | 9.4737 | 18.945 | 3.2778 | 6.1935 | 1.6 | 3.125 | 0.2 | 10 | 18.125
| 7898 | 0.8 | 5 | 17.4194 | 29.8965 | 2.3719 | 10.1053 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 7899 | 0.6 | 6.6667 | 12.5581 | 19.3154 | 3.0649 | 3.6923 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 7900 | 1.4 | 2.8571 | 10.1887 | 17.7644 | 3.5758 | 4 | 1.4 | 3.5714 | 0.2 | 10 | 16.4286
| 7901 | 0.4 | 10 | 12 | 20.7251 | 2.3251 | 6.4 | 1 | 5 | 0.4 | 5 | 20
| 7902 | 1 | 4 | 17.4194 | 27.9298 | 3.1258 | 7.3846 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 7903 | 1 | 4 | 11.7391 | 20.0225 | 2.95 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7904 | 1.2 | 3.3333 | 16.3636 | 25.9965 | 3.2329 | 6.4 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 7905 | 1.6 | 2.5 | 11.0204 | 19.3156 | 2.8095 | 5.4857 | 1 | 5 | 0.4 | 5 | 12.5
| 7906 | 0.1 | 40 | 11.7391 | 18.5642 | 2.36 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 51.25
| 7907 | 0.4 | 10 | 11.4894 | 17.9259 | 2.7442 | 3.6923 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 7908 | 1 | 4 | 14.5946 | 21.4239 | 2.7442 | 4.0851 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 7909 | 1.2 | 3.3333 | 9.4737 | 15.8426 | 2.878 | 3.4909 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 7910 | 0.4 | 10 | 15.4286 | 22.4291 | 2.6369 | 4.3636 | 0.4 | 12.5 | 0.6 | 3.3333 | 25.8333
| 7911 | 0.4 | 10 | 12.8571 | 20.2659 | 3.0452 | 4.3636 | 0.4 | 12.5 | 0.4 | 5 | 27.5
| 7912 | 1 | 4 | 13.8462 | 21.0779 | 3.1467 | 4.0851 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 7913 | 0.8 | 5 | 16.875 | 25.4909 | 4.2523 | 4.3636 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 7914 | 0.6 | 6.6667 | 12 | 23.4203 | 3.4203 | 8 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 7915 | 1 | 4 | 12.5581 | 19.3486 | 3.1678 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7916 | 0.4 | 10 | 15.8824 | 24.579 | 3.2109 | 5.4857 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 7917 | 0.8 | 5 | 18.6207 | 27.0127 | 5.2444 | 3.1475 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 7918 | 0.4 | 10 | 13.8462 | 23.9467 | 2.4205 | 7.68 | 1.6 | 3.125 | 0.4 | 5 | 18.125
| 7919 | 0.8 | 5 | 12.5581 | 21.8588 | 3.3007 | 6 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 7920 | 0.6 | 6.6667 | 12.2727 | 19.4519 | 3.8689 | 3.3103 | 1 | 5 | 0.4 | 5 | 16.6667
| 7921 | 0.8 | 5 | 12 | 18.5911 | 2.8263 | 3.7647 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 7922 | 1.4 | 2.8571 | 12.5581 | 19.9382 | 2.6971 | 4.6829 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 7923 | 0.8 | 5 | 11.7391 | 19.788 | 3.1258 | 4.9231 | 1 | 5 | 0.8 | 2.5 | 12.5
| 7924 | 0.4 | 10 | 10.5882 | 17.4017 | 2.7283 | 4.0851 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 7925 | 1 | 4 | 10 | 17.1735 | 3.2552 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 7926 | 0.6 | 6.6667 | 12.5581 | 18.2502 | 2.8263 | 2.8657 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 7927 | 0.4 | 10 | 15 | 20.616 | 2.2476 | 3.3684 | 1 | 5 | 0.4 | 5 | 20
| 7928 | 1 | 4 | 9.3103 | 16.0283 | 3.0256 | 3.6923 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 7929 | 0.8 | 5 | 15.8824 | 25.8322 | 2.5652 | 7.3846 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 7930 | 1 | 4 | 15 | 22.8188 | 2.8957 | 4.9231 | 1 | 5 | 0.4 | 5 | 14
| 7931 | 0.6 | 6.6667 | 8.1818 | 16.4763 | 3.3714 | 4.9231 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 7932 | 1.2 | 3.3333 | 15.8824 | 27.9402 | 4.6733 | 7.3846 | 1 | 5 | 0.2 | 10 | 18.3333
| 7933 | 0.6 | 6.6667 | 14.5946 | 20.9899 | 3.085 | 3.3103 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 7934 | 0.6 | 6.6667 | 14.5946 | 23.3241 | 3.8065 | 4.9231 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 7935 | 1.4 | 2.8571 | 14.2105 | 20.0515 | 3.2109 | 2.6301 | 1.4 | 3.5714 | 0.2 | 10 | 16.4286
| 7936 | 1 | 4 | 17.4194 | 23.8618 | 2.5241 | 3.9184 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 7937 | 1.4 | 2.8571 | 14.2105 | 23.2396 | 3.2109 | 5.8182 | 1 | 5 | 0.2 | 10 | 17.8571
| 7938 | 0.8 | 5 | 19.2857 | 25.4357 | 2.95 | 3.2 | 1 | 5 | 0.2 | 10 | 20
| 7939 | 0.4 | 10 | 11.7391 | 19.5265 | 2.9873 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 7940 | 0.8 | 5 | 10.1887 | 17.1068 | 2.7442 | 4.1739 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 7941 | 1.4 | 2.8571 | 9.3103 | 16.9979 | 3.3239 | 4.3636 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 7942 | 1 | 4 | 11.7391 | 18.3084 | 2.4842 | 4.0851 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 7943 | 0.8 | 5 | 12 | 19.8548 | 2.9317 | 4.9231 | 1 | 5 | 0.4 | 5 | 15
| 7944 | 0.8 | 5 | 9.1525 | 16.4366 | 2.7126 | 4.5714 | 1 | 5 | 0.1 | 20 | 30
| 7945 | 0.2 | 20 | 8.8525 | 18.9189 | 2.6818 | 7.3846 | 1.2 | 4.1667 | 0.8 | 2.5 | 26.6667
| 7946 | 1.2 | 3.3333 | 9.8182 | 19.782 | 2.5792 | 7.3846 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 7947 | 0.6 | 6.6667 | 12.8571 | 19.1638 | 2.878 | 3.4286 | 1 | 5 | 0.2 | 10 | 21.6667
| 7948 | 0.1 | 40 | 8.5714 | 17.1156 | 3.2109 | 5.3333 | 0.6 | 8.3333 | 0.4 | 5 | 53.3333
| 7949 | 0.4 | 10 | 20 | 25.9285 | 2.0885 | 3.84 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 7950 | 0.6 | 6.6667 | 9.6429 | 18.1148 | 3.5489 | 4.9231 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 7951 | 0.8 | 5 | 15.8824 | 22.9127 | 2.6667 | 4.3636 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 7952 | 1 | 4 | 9.3103 | 17.147 | 2.9136 | 4.9231 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 7953 | 0.8 | 5 | 16.3636 | 22.4914 | 2.6369 | 3.4909 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 7954 | 1 | 4 | 10.1887 | 16.4707 | 2.9136 | 3.3684 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 7955 | 0.8 | 5 | 10.1887 | 15.1152 | 2.433 | 2.4935 | 1.4 | 3.5714 | 0.8 | 2.5 | 11.0714
| 7956 | 0.6 | 6.6667 | 16.875 | 23.8375 | 2.4974 | 4.4651 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 7957 | 1 | 4 | 12.2727 | 18.4545 | 3.085 | 3.0968 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 7958 | 0.4 | 10 | 14.2105 | 20.2717 | 3.6308 | 2.4304 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 7959 | 0.8 | 5 | 9.3103 | 20.2438 | 3.5489 | 7.3846 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 7960 | 0.6 | 6.6667 | 9.6429 | 16.7359 | 2.8263 | 4.2667 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 7961 | 0.4 | 10 | 12.8571 | 20.6878 | 2.4974 | 5.3333 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 7962 | 0.6 | 6.6667 | 12.2727 | 22.8844 | 2.9317 | 7.68 | 1 | 5 | 0.4 | 5 | 16.6667
| 7963 | 0.4 | 10 | 10.8 | 19.2592 | 3.1258 | 5.3333 | 0.2 | 25 | 0.4 | 5 | 40
| 7964 | 0.6 | 6.6667 | 15 | 21.1884 | 2.878 | 3.3103 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 7965 | 0.6 | 6.6667 | 15 | 24.2429 | 2.6222 | 6.6207 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 7966 | 0.4 | 10 | 15 | 24.9498 | 2.5652 | 7.3846 | 1 | 5 | 0.4 | 5 | 20
| 7967 | 1.2 | 3.3333 | 8.8525 | 19.5962 | 2.3959 | 8.3478 | 1 | 5 | 0.4 | 5 | 13.3333
| 7968 | 1.2 | 3.3333 | 13.1707 | 21.7225 | 3.8689 | 4.6829 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 7969 | 1 | 4 | 13.1707 | 21.1263 | 2.6222 | 5.3333 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 7970 | 0.6 | 6.6667 | 14.5946 | 20.315 | 3.1258 | 2.5946 | 1 | 5 | 0.1 | 20 | 31.6667
| 7971 | 0.6 | 6.6667 | 14.5946 | 22.2489 | 3.1892 | 4.4651 | 1 | 5 | 0.2 | 10 | 21.6667
| 7972 | 1 | 4 | 9 | 15.7447 | 3.1892 | 3.5556 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 7973 | 1 | 4 | 15.4286 | 22.6875 | 3.085 | 4.1739 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 7974 | 0.6 | 6.6667 | 10.8 | 19.4284 | 3.5758 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 7975 | 0.6 | 6.6667 | 9.8182 | 19.2206 | 2.2913 | 7.1111 | 1.6 | 3.125 | 0.4 | 5 | 14.7917
| 7976 | 0.6 | 6.6667 | 16.3636 | 22.701 | 2.4974 | 3.84 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 7977 | 0.8 | 5 | 12.2727 | 21.3577 | 3.085 | 6 | 1 | 5 | 0.1 | 20 | 30
| 7978 | 0.8 | 5 | 9.6429 | 20.1015 | 3.3475 | 7.1111 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 7979 | 1.4 | 2.8571 | 12.5581 | 19.8738 | 2.7442 | 4.5714 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 7980 | 1 | 4 | 12 | 18.4697 | 2.5514 | 3.9184 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 7981 | 0.4 | 10 | 13.1707 | 20.7521 | 3.4963 | 4.0851 | 0.8 | 6.25 | 1 | 2 | 18.25
| 7982 | 0.6 | 6.6667 | 13.5 | 20.4252 | 3.2329 | 3.6923 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 7983 | 0.6 | 6.6667 | 11.4894 | 22.0208 | 3.4203 | 7.1111 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 7984 | 0.8 | 5 | 12.8571 | 21.2013 | 2.6971 | 5.6471 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 7985 | 1.4 | 2.8571 | 21.6 | 31.1543 | 2.6971 | 6.8571 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 7986 | 1 | 4 | 11.7391 | 20.858 | 3.3007 | 5.8182 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 7987 | 0.4 | 10 | 14.5946 | 20.3885 | 2.6971 | 3.0968 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 7988 | 0.8 | 5 | 14.2105 | 21.5508 | 3.2552 | 4.0851 | 1.4 | 3.5714 | 0.8 | 2.5 | 11.0714
| 7989 | 1 | 4 | 13.8462 | 21.1864 | 3.2552 | 4.0851 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 7990 | 0.2 | 20 | 11.4894 | 18.261 | 2.9317 | 3.84 | 1.4 | 3.5714 | 0.6 | 3.3333 | 26.9048
| 7991 | 0.8 | 5 | 12.5581 | 18.1581 | 2.8957 | 2.7042 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 7992 | 0.6 | 6.6667 | 19.2857 | 29.322 | 2.6517 | 7.3846 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 7993 | 1.6 | 2.5 | 8.0597 | 14.1403 | 2.8263 | 3.2542 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.0833
| 7994 | 0.8 | 5 | 14.2105 | 22.3041 | 2.7602 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 7995 | 0.6 | 6.6667 | 12.8571 | 19.6941 | 2.3719 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 7996 | 0.6 | 6.6667 | 19.2857 | 29.3446 | 3.6589 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 7997 | 0.6 | 6.6667 | 10 | 16.285 | 3.085 | 3.2 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 7998 | 0.8 | 5 | 10.1887 | 16.4602 | 2.5792 | 3.6923 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 7999 | 1 | 4 | 13.1707 | 18.9392 | 3.0256 | 2.7429 | 1 | 5 | 0.4 | 5 | 14
| 8000 | 0.4 | 10 | 13.5 | 19.6884 | 2.878 | 3.3103 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 8001 | 1 | 4 | 10.1887 | 17.4244 | 3.3957 | 3.84 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 8002 | 0.4 | 10 | 11.0204 | 17.7038 | 2.8434 | 3.84 | 1.6 | 3.125 | 0.2 | 10 | 23.125
| 8003 | 1 | 4 | 9.3103 | 17.0284 | 3.1467 | 4.5714 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 8004 | 1 | 4 | 12.8571 | 21.5263 | 3.746 | 4.9231 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 8005 | 0.4 | 10 | 13.8462 | 20.2139 | 3.1678 | 3.2 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 8006 | 1 | 4 | 12.2727 | 19.3548 | 2.5106 | 4.5714 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 8007 | 0.8 | 5 | 13.5 | 20.8496 | 2.6667 | 4.6829 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 8008 | 1.4 | 2.8571 | 14.5946 | 21.8636 | 4.069 | 3.2 | 1 | 5 | 0.2 | 10 | 17.8571
| 8009 | 0.2 | 20 | 9.4737 | 17.0666 | 2.7929 | 4.8 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 8010 | 1 | 4 | 15.4286 | 22.6709 | 3.3239 | 3.9184 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 8011 | 0.8 | 5 | 10.3846 | 17.8412 | 3.3714 | 4.0851 | 1.4 | 3.5714 | 0.8 | 2.5 | 11.0714
| 8012 | 1 | 4 | 10.5882 | 16.3768 | 2.36 | 3.4286 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 8013 | 0.8 | 5 | 10 | 16.4427 | 3.776 | 2.6667 | 1 | 5 | 0.2 | 10 | 20
| 8014 | 0.2 | 20 | 12.2727 | 18.0648 | 2.9686 | 2.8235 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 8015 | 0.8 | 5 | 14.2105 | 20.126 | 3.0064 | 2.9091 | 1 | 5 | 0.2 | 10 | 20
| 8016 | 1 | 4 | 18.6207 | 27.0496 | 3.746 | 4.6829 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 8017 | 0.8 | 5 | 11.0204 | 18.195 | 3.746 | 3.4286 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 8018 | 0.8 | 5 | 10.5882 | 17.7915 | 2.2802 | 4.9231 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 8019 | 0.4 | 10 | 10.3846 | 20.2276 | 2.4583 | 7.3846 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 8020 | 1 | 4 | 15.8824 | 22.1662 | 2.7283 | 3.5556 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 8021 | 0.8 | 5 | 7.9412 | 15.5318 | 3.3239 | 4.2667 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 8022 | 0.8 | 5 | 16.875 | 24.0534 | 3.6875 | 3.4909 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 8023 | 1 | 4 | 10 | 19.2434 | 2.8434 | 6.4 | 1 | 5 | 0.1 | 20 | 29
| 8024 | 1 | 4 | 21.6 | 28.7273 | 2.8606 | 4.2667 | 0.6 | 8.3333 | 1 | 2 | 14.3333
| 8025 | 0.8 | 5 | 13.8462 | 21.6055 | 3.3957 | 4.3636 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 8026 | 1 | 4 | 11.0204 | 18.793 | 3.6875 | 4.0851 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 8027 | 0.8 | 5 | 10.8 | 17.8236 | 3.1053 | 3.9184 | 1 | 5 | 0.4 | 5 | 15
| 8028 | 0.4 | 10 | 10.3846 | 16.6217 | 3.3714 | 2.8657 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 8029 | 0.8 | 5 | 13.5 | 20.4867 | 3.1467 | 3.84 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 8030 | 0.8 | 5 | 10 | 16.2893 | 2.6667 | 3.6226 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 8031 | 1.2 | 3.3333 | 13.1707 | 21.2643 | 2.7602 | 5.3333 | 1 | 5 | 0.2 | 10 | 18.3333
| 8032 | 1.2 | 3.3333 | 12.5581 | 29.9066 | 2.5792 | 14.7692 | 1 | 5 | 0.4 | 5 | 13.3333
| 8033 | 1.6 | 2.5 | 8.0597 | 17.3791 | 3.1258 | 6.1935 | 0.8 | 6.25 | 0.4 | 5 | 13.75
| 8034 | 0.6 | 6.6667 | 12.5581 | 18.7081 | 2.8957 | 3.2542 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 8035 | 1 | 4 | 11.4894 | 18.7263 | 3.746 | 3.4909 | 1.6 | 3.125 | 0.1 | 20 | 27.125
| 8036 | 1 | 4 | 9.8182 | 17.8552 | 2.5514 | 5.4857 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 8037 | 0.8 | 5 | 15.8824 | 20.9326 | 2.8434 | 2.2069 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 8038 | 0.8 | 5 | 11.4894 | 21.9389 | 3.0649 | 7.3846 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 8039 | 0.2 | 20 | 15 | 22.9256 | 3.6589 | 4.2667 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 8040 | 0.8 | 5 | 15 | 21.9132 | 3.6589 | 3.2542 | 0.4 | 12.5 | 0.2 | 10 | 27.5
| 8041 | 1.4 | 2.8571 | 12.5581 | 20.1395 | 3.4963 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 8042 | 0.8 | 5 | 16.875 | 23.9181 | 2.7765 | 4.2667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 8043 | 0.8 | 5 | 14.2105 | 21.1898 | 2.7126 | 4.2667 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 8044 | 1.4 | 2.8571 | 11.0204 | 17.9897 | 3.6589 | 3.3103 | 1 | 5 | 0.4 | 5 | 12.8571
| 8045 | 1.4 | 2.8571 | 10.5882 | 18.0597 | 3.0064 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 8046 | 1 | 4 | 7.2973 | 14.623 | 2.8606 | 4.4651 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 8047 | 0.8 | 5 | 11.4894 | 17.9454 | 2.5376 | 3.9184 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 8048 | 0.8 | 5 | 12.8571 | 19.379 | 2.6818 | 3.84 | 1 | 5 | 0.2 | 10 | 20
| 8049 | 1 | 4 | 17.4194 | 25.5638 | 2.4974 | 5.6471 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 8050 | 0.8 | 5 | 14.5946 | 21.3615 | 2.6818 | 4.0851 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 8051 | 0.4 | 10 | 9.6429 | 16.832 | 3.1892 | 4 | 1.4 | 3.5714 | 0.8 | 2.5 | 16.0714
| 8052 | 0.8 | 5 | 11.4894 | 18.2655 | 3.3475 | 3.4286 | 1 | 5 | 0.2 | 10 | 20
| 8053 | 1 | 4 | 11.7391 | 19.3955 | 3.085 | 4.5714 | 0.6 | 8.3333 | 0.1 | 20 | 32.3333
| 8054 | 0.6 | 6.6667 | 14.5946 | 20.8551 | 2.4205 | 3.84 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 8055 | 0.4 | 10 | 8.4375 | 13.6456 | 2.6818 | 2.5263 | 1 | 5 | 0.8 | 2.5 | 17.5
| 8056 | 0.6 | 6.6667 | 10.8 | 19.5409 | 3.2552 | 5.4857 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 8057 | 1.2 | 3.3333 | 17.4194 | 26.2883 | 4.069 | 4.8 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 8058 | 1 | 4 | 11.0204 | 17.2896 | 2.2692 | 4 | 1 | 5 | 0.4 | 5 | 14
| 8059 | 0.6 | 6.6667 | 12.5581 | 21.2553 | 2.6971 | 6 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 8060 | 1 | 4 | 13.1707 | 20.4064 | 3.3957 | 3.84 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 8061 | 1.2 | 3.3333 | 9.6429 | 17.0992 | 3.9008 | 3.5556 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.1667
| 8062 | 1 | 4 | 8.5714 | 15.4277 | 3.3007 | 3.5556 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 8063 | 0.8 | 5 | 15.8824 | 24.6879 | 2.9873 | 5.8182 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 8064 | 0.8 | 5 | 8.8525 | 17.2745 | 3.2329 | 5.1892 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 8065 | 1 | 4 | 16.875 | 24.0474 | 1.9832 | 5.1892 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 8066 | 0.6 | 6.6667 | 9.8182 | 14.3836 | 2.4082 | 2.1573 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 8067 | 1 | 4 | 11.4894 | 17.9822 | 3.4453 | 3.0476 | 1 | 5 | 0.4 | 5 | 14
| 8068 | 0.8 | 5 | 13.8462 | 20.3243 | 3.1678 | 3.3103 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 8069 | 1.2 | 3.3333 | 10.5882 | 18.1047 | 2.5934 | 4.9231 | 1 | 5 | 0.4 | 5 | 13.3333
| 8070 | 0.8 | 5 | 12 | 20.9377 | 2.7442 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 8071 | 1 | 4 | 11.4894 | 19.2883 | 4.0342 | 3.7647 | 0.2 | 25 | 0.6 | 3.3333 | 32.3333
| 8072 | 0.2 | 20 | 13.1707 | 20.593 | 2.6222 | 4.8 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 8073 | 1 | 4 | 9 | 17.6095 | 3.4203 | 5.1892 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 8074 | 1.2 | 3.3333 | 9.4737 | 18.3873 | 2.9136 | 6 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 8075 | 0.8 | 5 | 15.8824 | 20.2048 | 2.4583 | 1.8641 | 0.4 | 12.5 | 0.2 | 10 | 27.5
| 8076 | 0.4 | 10 | 15 | 24.0223 | 2.1651 | 6.8571 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 8077 | 0.4 | 10 | 10.3846 | 17.8299 | 3.4453 | 4 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 8078 | 0.8 | 5 | 10.5882 | 16.492 | 2.3483 | 3.5556 | 1 | 5 | 0.2 | 10 | 20
| 8079 | 0.8 | 5 | 16.3636 | 25.3893 | 3.0256 | 6 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 8080 | 0.4 | 10 | 12 | 19.586 | 3.746 | 3.84 | 1 | 5 | 0.2 | 10 | 25
| 8081 | 0.8 | 5 | 12.2727 | 24.425 | 4.7677 | 7.3846 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 8082 | 0.8 | 5 | 11.4894 | 19.8964 | 4.1404 | 4.2667 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 8083 | 0.8 | 5 | 11.4894 | 18.8557 | 2.3137 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 8084 | 0.8 | 5 | 14.5946 | 21.7024 | 2.7442 | 4.3636 | 1.4 | 3.5714 | 0.8 | 2.5 | 11.0714
| 8085 | 1 | 4 | 8.7097 | 15.8889 | 3.8689 | 3.3103 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 8086 | 0.8 | 5 | 15 | 22.6414 | 3.2778 | 4.3636 | 1.6 | 3.125 | 0.8 | 2.5 | 10.625
| 8087 | 1 | 4 | 10.1887 | 16.095 | 2.8095 | 3.0968 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 8088 | 0.4 | 10 | 9.3103 | 16.0876 | 2.5106 | 4.2667 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 8089 | 0.6 | 6.6667 | 12 | 17.9106 | 3.1678 | 2.7429 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 8090 | 1 | 4 | 10.8 | 17.0743 | 2.6517 | 3.6226 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 8091 | 0.2 | 20 | 11.4894 | 18.9706 | 3.7165 | 3.7647 | 0.8 | 6.25 | 0.2 | 10 | 36.25
| 8092 | 1 | 4 | 14.5946 | 20.66 | 2.6369 | 3.4286 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 8093 | 0.8 | 5 | 10.3846 | 18.4874 | 2.9136 | 5.1892 | 1 | 5 | 0.4 | 5 | 15
| 8094 | 0.6 | 6.6667 | 14.5946 | 22.1986 | 2.5514 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 8095 | 1 | 4 | 11.25 | 18.639 | 3.4706 | 3.9184 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 8096 | 0.8 | 5 | 16.875 | 24.86 | 2.6517 | 5.3333 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 8097 | 0.2 | 20 | 13.5 | 20.8198 | 2.6369 | 4.6829 | 1 | 5 | 0.1 | 20 | 45
| 8098 | 0.8 | 5 | 10.5882 | 16.6446 | 3.2329 | 2.8235 | 1 | 5 | 0.2 | 10 | 20
| 8099 | 0.8 | 5 | 14.5946 | 21.0138 | 2.5792 | 3.84 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 8100 | 1.2 | 3.3333 | 12.8571 | 19.0214 | 3.2552 | 2.9091 | 1.6 | 3.125 | 0.6 | 3.3333 | 9.7917
| 8101 | 1.2 | 3.3333 | 12.8571 | 20.0175 | 3.3957 | 3.7647 | 1 | 5 | 0.4 | 5 | 13.3333
| 8102 | 0.6 | 6.6667 | 11.4894 | 18.09 | 2.237 | 4.3636 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 8103 | 0.8 | 5 | 13.5 | 20.3434 | 2.8434 | 4 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 8104 | 1 | 4 | 9.8182 | 17.3635 | 3.3714 | 4.1739 | 1 | 5 | 0.4 | 5 | 14
| 8105 | 0.6 | 6.6667 | 12.2727 | 20.7527 | 3.1467 | 5.3333 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 8106 | 0.4 | 10 | 17.4194 | 24.0819 | 2.7442 | 3.9184 | 1.6 | 3.125 | 0.4 | 5 | 18.125
| 8107 | 0.8 | 5 | 9.8182 | 16.6792 | 2.4974 | 4.3636 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 8108 | 0.8 | 5 | 12 | 18.3988 | 2.3137 | 4.0851 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 8109 | 0.8 | 5 | 9.6429 | 18.0029 | 2.36 | 6 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 8110 | 1.2 | 3.3333 | 15 | 23.582 | 3.6589 | 4.9231 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 8111 | 0.8 | 5 | 14.2105 | 20.3536 | 3.1892 | 2.9538 | 1 | 5 | 0.2 | 10 | 20
| 8112 | 0.8 | 5 | 18.6207 | 25.9891 | 4 | 3.3684 | 1 | 5 | 0.4 | 5 | 15
| 8113 | 0.6 | 6.6667 | 13.1707 | 24.7294 | 3.2109 | 8.3478 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 8114 | 0.8 | 5 | 10.1887 | 15.686 | 2.4974 | 3 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 8115 | 0.6 | 6.6667 | 11.4894 | 18.8373 | 2.7765 | 4.5714 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 8116 | 1.2 | 3.3333 | 15.4286 | 26.9022 | 3.1258 | 8.3478 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 8117 | 1.4 | 2.8571 | 10 | 15.9621 | 2.4712 | 3.4909 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 8118 | 0.8 | 5 | 17.4194 | 25.1852 | 3.3007 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 8119 | 0.8 | 5 | 10 | 15.7106 | 2.5106 | 3.2 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 8120 | 1 | 4 | 17.4194 | 28.5246 | 3.1053 | 8 | 1 | 5 | 0.4 | 5 | 14
| 8121 | 1 | 4 | 9.4737 | 16.407 | 2.6667 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 8122 | 0.4 | 10 | 15.8824 | 25.2538 | 3.3714 | 6 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 8123 | 0.6 | 6.6667 | 11.25 | 18.4065 | 2.7929 | 4.3636 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 8124 | 0.8 | 5 | 8.4375 | 13.8307 | 2.9317 | 2.4615 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 8125 | 0.2 | 20 | 14.2105 | 20.8186 | 2.8434 | 3.7647 | 1 | 5 | 0.2 | 10 | 35
| 8126 | 0.2 | 20 | 9 | 17.5518 | 3.8689 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 8127 | 0.4 | 10 | 13.1707 | 20.3214 | 2.5792 | 4.5714 | 1 | 5 | 0.4 | 5 | 20
| 8128 | 1 | 4 | 10.1887 | 18.8614 | 3.0256 | 5.6471 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 8129 | 0.6 | 6.6667 | 9.8182 | 17.744 | 3.1258 | 4.8 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 8130 | 0.6 | 6.6667 | 15 | 21.3829 | 2.7602 | 3.6226 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 8131 | 0.4 | 10 | 13.8462 | 22.7276 | 3.3957 | 5.4857 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 8132 | 1.2 | 3.3333 | 12.8571 | 23.5238 | 2.6667 | 8 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 8133 | 0.8 | 5 | 16.875 | 26.369 | 2.6369 | 6.8571 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 8134 | 0.6 | 6.6667 | 15.4286 | 25.2529 | 3.6308 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 15
| 8135 | 1 | 4 | 12 | 19.5429 | 4.4952 | 3.0476 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 8136 | 0.8 | 5 | 12.2727 | 19.1784 | 2.9873 | 3.9184 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 8137 | 0.2 | 20 | 16.3636 | 24.344 | 3.8065 | 4.1739 | 0.6 | 8.3333 | 0.4 | 5 | 33.3333
| 8138 | 0.8 | 5 | 9.4737 | 15.7921 | 2.95 | 3.3684 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 8139 | 0.8 | 5 | 11.0204 | 18.6793 | 3.6589 | 4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 8140 | 1.4 | 2.8571 | 14.2105 | 19.5654 | 2.7602 | 2.5946 | 1.4 | 3.5714 | 0.4 | 5 | 11.4286
| 8141 | 0.8 | 5 | 15 | 21.1943 | 3.1467 | 3.0476 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 8142 | 0.4 | 10 | 11.7391 | 18.1881 | 2.8263 | 3.6226 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 8143 | 0.4 | 10 | 10.5882 | 24.3286 | 4.1404 | 9.6 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 8144 | 1.2 | 3.3333 | 18 | 24.7509 | 2.4842 | 4.2667 | 0.1 | 50 | 0.1 | 20 | 73.3333
| 8145 | 0.8 | 5 | 13.1707 | 21.569 | 3.0649 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 8146 | 1.2 | 3.3333 | 13.1707 | 22.1771 | 3.0064 | 6 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 8147 | 0.6 | 6.6667 | 11.0204 | 18.6719 | 2.9686 | 4.6829 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 8148 | 0.6 | 6.6667 | 12.5581 | 22.8744 | 2.9317 | 7.3846 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 8149 | 0.6 | 6.6667 | 14.5946 | 21.5017 | 2.1071 | 4.8 | 1 | 5 | 0.4 | 5 | 16.6667
| 8150 | 1 | 4 | 9.6429 | 16.34 | 2.6971 | 4 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 8151 | 0.8 | 5 | 13.5 | 19.6767 | 2.2584 | 3.9184 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 8152 | 1.4 | 2.8571 | 11.7391 | 19.7981 | 3.0064 | 5.0526 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 8153 | 1.2 | 3.3333 | 9.6429 | 16.9206 | 3.2778 | 4 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 8154 | 0.2 | 20 | 11.0204 | 17.153 | 3.085 | 3.0476 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 8155 | 0.8 | 5 | 18 | 26.1396 | 3.776 | 4.3636 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 8156 | 0.8 | 5 | 12.8571 | 21.2687 | 2.5934 | 5.8182 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 8157 | 0.4 | 10 | 10.3846 | 16.8208 | 3.1258 | 3.3103 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 8158 | 0.8 | 5 | 11.25 | 18.7935 | 2.8606 | 4.6829 | 1 | 5 | 0.2 | 10 | 20
| 8159 | 1 | 4 | 13.5 | 22.5077 | 2.6077 | 6.4 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 8160 | 0.8 | 5 | 9.1525 | 15.5875 | 3.0064 | 3.4286 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 8161 | 1.2 | 3.3333 | 12.8571 | 20.3384 | 3.7165 | 3.7647 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 8162 | 0.6 | 6.6667 | 10.8 | 17.3007 | 3.3007 | 3.2 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 8163 | 0.1 | 40 | 12.2727 | 19.6132 | 3.5758 | 3.7647 | 1 | 5 | 0.8 | 2.5 | 47.5
| 8164 | 0.6 | 6.6667 | 12.5581 | 20.5652 | 2.36 | 5.6471 | 1 | 5 | 0.4 | 5 | 16.6667
| 8165 | 0.8 | 5 | 12.2727 | 18.4654 | 3.0452 | 3.1475 | 0.6 | 8.3333 | 0.1 | 20 | 33.3333
| 8166 | 1 | 4 | 12.2727 | 21.6341 | 3.1678 | 6.1935 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 8167 | 0.4 | 10 | 12.2727 | 20.6324 | 2.7126 | 5.6471 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 8168 | 0.6 | 6.6667 | 9.8182 | 17.2897 | 3.0064 | 4.4651 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 8169 | 1 | 4 | 18 | 25.4708 | 3.6308 | 3.84 | 1 | 5 | 0.2 | 10 | 19
| 8170 | 0.4 | 10 | 10.3846 | 17.1367 | 2.9873 | 3.7647 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 8171 | 1 | 4 | 18 | 25.0351 | 2.95 | 4.0851 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 8172 | 1 | 4 | 11.4894 | 18.1321 | 2.878 | 3.7647 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 8173 | 0.6 | 6.6667 | 13.5 | 20.9573 | 3.9664 | 3.4909 | 1 | 5 | 0.6 | 3.3333 | 15
| 8174 | 0.4 | 10 | 7.5 | 14.5429 | 3.4203 | 3.6226 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 8175 | 1.6 | 2.5 | 10.3846 | 17.5916 | 2.8434 | 4.3636 | 0.8 | 6.25 | 0.2 | 10 | 18.75
| 8176 | 0.6 | 6.6667 | 9.3103 | 16.9439 | 3.8689 | 3.7647 | 1 | 5 | 0.6 | 3.3333 | 15
| 8177 | 0.6 | 6.6667 | 11.7391 | 18.9209 | 4.0342 | 3.1475 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 8178 | 1.2 | 3.3333 | 14.5946 | 26.2882 | 4.5825 | 7.1111 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 8179 | 0.6 | 6.6667 | 10.1887 | 18.8421 | 3.0064 | 5.6471 | 1 | 5 | 0.4 | 5 | 16.6667
| 8180 | 0.2 | 20 | 14.2105 | 21.5421 | 3.776 | 3.5556 | 0.6 | 8.3333 | 0.8 | 2.5 | 30.8333
| 8181 | 0.4 | 10 | 13.8462 | 20.1704 | 2.4842 | 3.84 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 8182 | 0.4 | 10 | 12.8571 | 18.5513 | 2.3838 | 3.3103 | 1 | 5 | 0.2 | 10 | 25
| 8183 | 0.4 | 10 | 9.8182 | 26.6524 | 4.0342 | 12.8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 8184 | 0.2 | 20 | 16.875 | 28.6872 | 3.085 | 8.7273 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 8185 | 0.6 | 6.6667 | 11.7391 | 19.3137 | 3.2109 | 4.3636 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 8186 | 0.8 | 5 | 10.1887 | 21.552 | 4.2523 | 7.1111 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 8187 | 1 | 4 | 16.875 | 24.6229 | 3.0649 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 8188 | 0.4 | 10 | 10.8 | 21.4143 | 4.2143 | 6.4 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 8189 | 0.2 | 20 | 12.8571 | 20.2219 | 2.6818 | 4.6829 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 8190 | 1.2 | 3.3333 | 12 | 19.746 | 3.746 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 8191 | 0.4 | 10 | 11.4894 | 17.8078 | 2.95 | 3.3684 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 8192 | 0.6 | 6.6667 | 16.3636 | 23.8739 | 3.0452 | 4.4651 | 0.6 | 8.3333 | 0.1 | 20 | 35
| 8193 | 1.2 | 3.3333 | 9.6429 | 18.8137 | 2.3137 | 6.8571 | 1.6 | 3.125 | 0.1 | 20 | 26.4583
| 8194 | 0.8 | 5 | 10.5882 | 18.397 | 3.1258 | 4.6829 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 8195 | 1 | 4 | 9.4737 | 16.0108 | 2.6971 | 3.84 | 1 | 5 | 0.2 | 10 | 19
| 8196 | 0.6 | 6.6667 | 12 | 18.0824 | 3.5224 | 2.56 | 1 | 5 | 0.6 | 3.3333 | 15
| 8197 | 0.6 | 6.6667 | 9.8182 | 16.5972 | 2.8606 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 8198 | 0.8 | 5 | 8.7097 | 18.5968 | 4.069 | 5.8182 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 8199 | 1 | 4 | 12.8571 | 18.7493 | 2.3366 | 3.5556 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 8200 | 0.6 | 6.6667 | 13.1707 | 20.1872 | 2.5514 | 4.4651 | 1 | 5 | 0.4 | 5 | 16.6667
| 8201 | 1 | 4 | 10.1887 | 16.4894 | 3.3007 | 3 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 8202 | 0.6 | 6.6667 | 10.5882 | 17.1069 | 2.8263 | 3.6923 | 1 | 5 | 0.6 | 3.3333 | 15
| 8203 | 0.4 | 10 | 10.8 | 18.0456 | 2.4456 | 4.8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 8204 | 0.2 | 20 | 11.0204 | 19.6315 | 3.2778 | 5.3333 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 8205 | 0.6 | 6.6667 | 15.4286 | 21.6162 | 2.2692 | 3.9184 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 8206 | 1.2 | 3.3333 | 10.1887 | 15.7449 | 3.1258 | 2.4304 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 8207 | 1 | 4 | 14.5946 | 24.1644 | 2.7126 | 6.8571 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 8208 | 1.4 | 2.8571 | 9.1525 | 15.6231 | 3.4706 | 3 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 8209 | 0.6 | 6.6667 | 14.5946 | 20.3638 | 3.0649 | 2.7042 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 8210 | 0.6 | 6.6667 | 12.2727 | 18.9907 | 3.0256 | 3.6923 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 8211 | 0.4 | 10 | 18 | 24.8031 | 3.6031 | 3.2 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 8212 | 1 | 4 | 12 | 19.0873 | 2.6222 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 8213 | 0.2 | 20 | 10 | 15.3751 | 2.9136 | 2.4615 | 0.6 | 8.3333 | 0.6 | 3.3333 | 31.6667
| 8214 | 0.8 | 5 | 9.3103 | 14.9103 | 2.7765 | 2.8235 | 1 | 5 | 0.4 | 5 | 15
| 8215 | 1 | 4 | 15 | 22.5491 | 3.6308 | 3.9184 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 8216 | 0.6 | 6.6667 | 11.4894 | 17.0166 | 2.8606 | 2.6667 | 1.4 | 3.5714 | 0.1 | 20 | 30.2381
| 8217 | 0.6 | 6.6667 | 9.1525 | 16.7136 | 2.3719 | 5.1892 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 8218 | 0.8 | 5 | 12.2727 | 18.578 | 3.1053 | 3.2 | 1 | 5 | 0.1 | 20 | 30
| 8219 | 0.8 | 5 | 12.2727 | 19.1908 | 2.7442 | 4.1739 | 1 | 5 | 0.2 | 10 | 20
| 8220 | 0.8 | 5 | 15.8824 | 26.0466 | 2.4842 | 7.68 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 8221 | 0.6 | 6.6667 | 9.8182 | 20.5078 | 4.069 | 6.6207 | 1 | 5 | 0.2 | 10 | 21.6667
| 8222 | 0.8 | 5 | 13.8462 | 24.1441 | 4.1043 | 6.1935 | 1 | 5 | 0.2 | 10 | 20
| 8223 | 0.6 | 6.6667 | 11.0204 | 17.646 | 3.7165 | 2.9091 | 1.6 | 3.125 | 0.6 | 3.3333 | 13.125
| 8224 | 1.2 | 3.3333 | 14.5946 | 23.8973 | 2.4456 | 6.8571 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 8225 | 0.4 | 10 | 10.1887 | 17.0667 | 2.878 | 4 | 1 | 5 | 0.4 | 5 | 20
| 8226 | 0.8 | 5 | 13.8462 | 21.8298 | 3.3007 | 4.6829 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 8227 | 0.8 | 5 | 20 | 27.8367 | 2.9136 | 4.9231 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 8228 | 0.6 | 6.6667 | 11.7391 | 20.3675 | 3.5758 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 8229 | 1.2 | 3.3333 | 12.5581 | 19.8191 | 3.4963 | 3.7647 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 8230 | 0.8 | 5 | 14.5946 | 22.4862 | 2.9686 | 4.9231 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 8231 | 0.8 | 5 | 16.3636 | 24.2092 | 2.7929 | 5.0526 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 8232 | 1 | 4 | 12.5581 | 19.5339 | 2.5106 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 8233 | 0.4 | 10 | 13.1707 | 21.0315 | 3.3957 | 4.4651 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 8234 | 0.6 | 6.6667 | 16.3636 | 22.9289 | 2.5652 | 4 | 1 | 5 | 0.2 | 10 | 21.6667
| 8235 | 1.2 | 3.3333 | 10.5882 | 15.319 | 2.2692 | 2.4615 | 1 | 5 | 0.2 | 10 | 18.3333
| 8236 | 0.6 | 6.6667 | 10.1887 | 16.5716 | 2.7602 | 3.6226 | 1 | 5 | 0.6 | 3.3333 | 15
| 8237 | 0.6 | 6.6667 | 12.2727 | 20.4009 | 3.4453 | 4.6829 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 8238 | 1 | 4 | 12.8571 | 18.871 | 2.4583 | 3.5556 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 8239 | 0.6 | 6.6667 | 13.8462 | 21.7111 | 3.0649 | 4.8 | 1 | 5 | 0.2 | 10 | 21.6667
| 8240 | 0.8 | 5 | 12.5581 | 19.0717 | 3.085 | 3.4286 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 8241 | 0.8 | 5 | 15.4286 | 27.2541 | 4.9684 | 6.8571 | 1 | 5 | 0.4 | 5 | 15
| 8242 | 1.2 | 3.3333 | 16.875 | 23.0428 | 3.1678 | 3 | 1 | 5 | 0.4 | 5 | 13.3333
| 8243 | 0.6 | 6.6667 | 11.25 | 21.426 | 3.776 | 6.4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 8244 | 1 | 4 | 10.1887 | 16.4192 | 2.1455 | 4.0851 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 8245 | 0.8 | 5 | 8.1818 | 17.8154 | 2.7765 | 6.8571 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 8246 | 0.6 | 6.6667 | 14.5946 | 22.054 | 2.7765 | 4.6829 | 1.6 | 3.125 | 0.2 | 10 | 19.7917
| 8247 | 0.8 | 5 | 8.5714 | 16.995 | 2.7765 | 5.6471 | 0.2 | 25 | 0.8 | 2.5 | 32.5
| 8248 | 0.8 | 5 | 13.8462 | 20.1011 | 2.8263 | 3.4286 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 8249 | 0.6 | 6.6667 | 7.9412 | 18.8729 | 2.9317 | 8 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 8250 | 1 | 4 | 13.1707 | 18.825 | 2.95 | 2.7042 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 8251 | 0.6 | 6.6667 | 13.8462 | 20.5588 | 2.7126 | 4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 8252 | 0.4 | 10 | 13.5 | 20.124 | 2.9317 | 3.6923 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 8253 | 0.4 | 10 | 10.5882 | 18.1169 | 2.1953 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 8254 | 0.8 | 5 | 14.5946 | 22.238 | 2.8434 | 4.8 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 8255 | 1.2 | 3.3333 | 12.5581 | 21.9666 | 2.5514 | 6.8571 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 8256 | 0.8 | 5 | 11.7391 | 18.6676 | 2.8434 | 4.0851 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 8257 | 0.8 | 5 | 13.5 | 19.6247 | 2.36 | 3.7647 | 0.4 | 12.5 | 0.6 | 3.3333 | 20.8333
| 8258 | 0.6 | 6.6667 | 12.8571 | 18.779 | 3.2552 | 2.6667 | 1 | 5 | 0.6 | 3.3333 | 15
| 8259 | 1.2 | 3.3333 | 18 | 25.5965 | 3.2329 | 4.3636 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 8260 | 0.6 | 6.6667 | 16.3636 | 23.2686 | 3.0649 | 3.84 | 1 | 5 | 0.4 | 5 | 16.6667
| 8261 | 1.6 | 2.5 | 12.8571 | 19.5235 | 2.8263 | 3.84 | 0.6 | 8.3333 | 0.1 | 20 | 30.8333
| 8262 | 1 | 4 | 12.2727 | 19.0444 | 2.9317 | 3.84 | 1 | 5 | 0.2 | 10 | 19
| 8263 | 0.8 | 5 | 13.8462 | 21.3134 | 3.5489 | 3.9184 | 1 | 5 | 0.2 | 10 | 20
| 8264 | 0.6 | 6.6667 | 13.8462 | 19.7317 | 2.9317 | 2.9538 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 8265 | 0.8 | 5 | 15.4286 | 24.1294 | 3.9008 | 4.8 | 1 | 5 | 0.1 | 20 | 30
| 8266 | 0.8 | 5 | 9.8182 | 22.6074 | 3.1892 | 9.6 | 1 | 5 | 0.1 | 20 | 30
| 8267 | 0.4 | 10 | 14.2105 | 20.4048 | 3.1467 | 3.0476 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 8268 | 1 | 4 | 11.4894 | 18.5239 | 2.8606 | 4.1739 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 8269 | 1 | 4 | 11.7391 | 17.7077 | 2.9686 | 3 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 8270 | 0.6 | 6.6667 | 12 | 21.8759 | 3.2552 | 6.6207 | 1 | 5 | 0.4 | 5 | 16.6667
| 8271 | 1.2 | 3.3333 | 9.4737 | 19.9636 | 3.1053 | 7.3846 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 8272 | 1.6 | 2.5 | 13.8462 | 19.8452 | 3.0452 | 2.9538 | 1.2 | 4.1667 | 0.8 | 2.5 | 9.1667
| 8273 | 0.4 | 10 | 15.4286 | 23.5358 | 3.9333 | 4.1739 | 0.2 | 25 | 0.1 | 20 | 55
| 8274 | 0.6 | 6.6667 | 16.875 | 22.6399 | 2.5106 | 3.2542 | 1 | 5 | 0.6 | 3.3333 | 15
| 8275 | 0.6 | 6.6667 | 11.0204 | 18.1679 | 4 | 3.1475 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 8276 | 0.2 | 20 | 12.2727 | 19.2535 | 2.8957 | 4.0851 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 8277 | 1.4 | 2.8571 | 12.2727 | 20.3755 | 2.9136 | 5.1892 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 8278 | 1.2 | 3.3333 | 8.3077 | 15.1815 | 3.4453 | 3.4286 | 1 | 5 | 0.2 | 10 | 18.3333
| 8279 | 1.2 | 3.3333 | 12 | 20.0959 | 3.6308 | 4.4651 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 8280 | 0.8 | 5 | 17.4194 | 25.7959 | 3.3239 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 8281 | 1.2 | 3.3333 | 11.0204 | 17.5918 | 3.3714 | 3.2 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 8282 | 0.4 | 10 | 13.8462 | 20.4204 | 2.8095 | 3.7647 | 1.6 | 3.125 | 0.6 | 3.3333 | 16.4583
| 8283 | 1 | 4 | 12 | 17.9361 | 2.6818 | 3.2542 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 8284 | 0.2 | 20 | 10.8 | 21.4486 | 2.9686 | 7.68 | 1 | 5 | 0.4 | 5 | 30
| 8285 | 0.6 | 6.6667 | 13.1707 | 20.9136 | 3.2778 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 8286 | 1 | 4 | 10 | 17.0163 | 3.3239 | 3.6923 | 1 | 5 | 0.4 | 5 | 14
| 8287 | 0.6 | 6.6667 | 16.3636 | 22.4469 | 3.3007 | 2.7826 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 8288 | 0.6 | 6.6667 | 19.2857 | 27.1296 | 2.0258 | 5.8182 | 1 | 5 | 0.2 | 10 | 21.6667
| 8289 | 0.8 | 5 | 13.8462 | 20.8698 | 3.1053 | 3.9184 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 8290 | 0.6 | 6.6667 | 13.1707 | 20.7203 | 4.4528 | 3.0968 | 1 | 5 | 0.4 | 5 | 16.6667
| 8291 | 1 | 4 | 10.5882 | 17.3756 | 2.216 | 4.5714 | 1 | 5 | 0.2 | 10 | 19
| 8292 | 0.4 | 10 | 11.0204 | 17.8431 | 3.8689 | 2.9538 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 8293 | 0.4 | 10 | 11.25 | 17.6414 | 2.5514 | 3.84 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 8294 | 1 | 4 | 9.6429 | 16.6509 | 2.3251 | 4.6829 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 8295 | 0.8 | 5 | 17.4194 | 26.8424 | 3.776 | 5.6471 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 8296 | 0.2 | 20 | 15.4286 | 22.1161 | 3.0649 | 3.6226 | 0.6 | 8.3333 | 0.2 | 10 | 38.3333
| 8297 | 0.8 | 5 | 10 | 18.8055 | 2.9873 | 5.8182 | 1 | 5 | 0.8 | 2.5 | 12.5
| 8298 | 1.6 | 2.5 | 15 | 22.581 | 2.2476 | 5.3333 | 0.4 | 12.5 | 0.4 | 5 | 20
| 8299 | 0.6 | 6.6667 | 12 | 18.7115 | 2.5376 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 8300 | 1.2 | 3.3333 | 15.8824 | 24.3223 | 2.7929 | 5.6471 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 8301 | 0.8 | 5 | 18 | 24.5704 | 2.878 | 3.6923 | 1 | 5 | 0.1 | 20 | 30
| 8302 | 0.8 | 5 | 24.5455 | 31.9086 | 3.1892 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 8303 | 1 | 4 | 17.4194 | 23.9751 | 4.2143 | 2.3415 | 1 | 5 | 0.2 | 10 | 19
| 8304 | 0.8 | 5 | 11.0204 | 20.016 | 3.8065 | 5.1892 | 1 | 5 | 0.2 | 10 | 20
| 8305 | 1 | 4 | 10 | 18.1392 | 2.95 | 5.1892 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 8306 | 0.8 | 5 | 11.25 | 19.2164 | 3.9664 | 4 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 8307 | 1 | 4 | 12.2727 | 20.3663 | 2.7602 | 5.3333 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 8308 | 0.6 | 6.6667 | 15.8824 | 24.5168 | 3.4453 | 5.1892 | 1.6 | 3.125 | 0.4 | 5 | 14.7917
| 8309 | 0.4 | 10 | 15.4286 | 22.0108 | 3.7165 | 2.8657 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 8310 | 1.2 | 3.3333 | 16.3636 | 22.4844 | 2.5652 | 3.5556 | 1.6 | 3.125 | 0.2 | 10 | 16.4583
| 8311 | 1 | 4 | 15.4286 | 25.3114 | 3.0256 | 6.8571 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 8312 | 1.2 | 3.3333 | 14.5946 | 22.7 | 2.4583 | 5.6471 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 8313 | 0.6 | 6.6667 | 17.4194 | 25.5226 | 3.4203 | 4.6829 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 8314 | 1 | 4 | 11.7391 | 18.078 | 2.4205 | 3.9184 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 8315 | 0.8 | 5 | 14.2105 | 33.3501 | 4.3704 | 14.7692 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 8316 | 0.8 | 5 | 17.4194 | 30.7654 | 3.746 | 9.6 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 8317 | 0.6 | 6.6667 | 21.6 | 29.7675 | 2.6818 | 5.4857 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 8318 | 0.4 | 10 | 11.0204 | 22.0081 | 3.6031 | 7.3846 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 8319 | 0.8 | 5 | 13.8462 | 19.8565 | 2.9136 | 3.0968 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 8320 | 0.6 | 6.6667 | 13.5 | 21.8137 | 3.6308 | 4.6829 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 8321 | 0.2 | 20 | 13.5 | 19.8895 | 2.6971 | 3.6923 | 0.6 | 8.3333 | 0.6 | 3.3333 | 31.6667
| 8322 | 0.6 | 6.6667 | 10.8 | 15.8381 | 2.6077 | 2.4304 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 8323 | 1 | 4 | 11.25 | 19.0543 | 3.2329 | 4.5714 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 8324 | 0.6 | 6.6667 | 13.1707 | 19.1055 | 3.0256 | 2.9091 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 8325 | 0.1 | 40 | 10 | 18.2387 | 2.4205 | 5.8182 | 0.8 | 6.25 | 0.8 | 2.5 | 48.75
| 8326 | 1.2 | 3.3333 | 15.8824 | 22.4735 | 2.9686 | 3.6226 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 8327 | 1.2 | 3.3333 | 10.8 | 21.3955 | 3.2109 | 7.3846 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 8328 | 1 | 4 | 9.6429 | 17.281 | 3.3714 | 4.2667 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 8329 | 0.6 | 6.6667 | 9.6429 | 21.3371 | 2.5514 | 9.1429 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 8330 | 1 | 4 | 10 | 17.9682 | 3.0452 | 4.9231 | 1 | 5 | 0.2 | 10 | 19
| 8331 | 1.4 | 2.8571 | 10.3846 | 20.1734 | 2.9317 | 6.8571 | 0.6 | 8.3333 | 0.6 | 3.3333 | 14.5238
| 8332 | 0.6 | 6.6667 | 10.8 | 17.6086 | 2.9686 | 3.84 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 8333 | 1.2 | 3.3333 | 15 | 22.188 | 4.1404 | 3.0476 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 8334 | 1.2 | 3.3333 | 10.8 | 18.111 | 2.2584 | 5.0526 | 0.2 | 25 | 0.2 | 10 | 38.3333
| 8335 | 1 | 4 | 15 | 20.7525 | 2.8434 | 2.9091 | 0.4 | 12.5 | 0.8 | 2.5 | 19
| 8336 | 0.6 | 6.6667 | 10.8 | 18.685 | 3.085 | 4.8 | 1 | 5 | 0.4 | 5 | 16.6667
| 8337 | 0.4 | 10 | 7.9412 | 16.1616 | 3.1678 | 5.0526 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 8338 | 0.8 | 5 | 10 | 18.4875 | 3.6875 | 4.8 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 8339 | 0.8 | 5 | 10.1887 | 17.0387 | 2.9317 | 3.9184 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 8340 | 0.6 | 6.6667 | 12.8571 | 22.864 | 2.8957 | 7.1111 | 1 | 5 | 0.6 | 3.3333 | 15
| 8341 | 0.6 | 6.6667 | 11.4894 | 17.4464 | 2.8095 | 3.1475 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 8342 | 0.4 | 10 | 8.7097 | 14.4407 | 2.3024 | 3.4286 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 8343 | 0.8 | 5 | 8.8525 | 17.3244 | 3.5489 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 8344 | 0.2 | 20 | 12.5581 | 22.4117 | 3.2329 | 6.6207 | 1 | 5 | 0.2 | 10 | 35
| 8345 | 0.6 | 6.6667 | 9.8182 | 19.5515 | 2.6222 | 7.1111 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 8346 | 0.8 | 5 | 12.8571 | 21.7162 | 3.8065 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 8347 | 0.8 | 5 | 11.0204 | 18.7762 | 3.8374 | 3.9184 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 8348 | 1 | 4 | 11.7391 | 22.4337 | 3.8374 | 6.8571 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 8349 | 0.6 | 6.6667 | 8.7097 | 16.0113 | 3.746 | 3.5556 | 1 | 5 | 0.4 | 5 | 16.6667
| 8350 | 0.8 | 5 | 12 | 20.3289 | 2.6818 | 5.6471 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 8351 | 0.8 | 5 | 16.3636 | 22.9872 | 3.2552 | 3.3684 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 8352 | 1.4 | 2.8571 | 13.8462 | 22.0931 | 2.9136 | 5.3333 | 1.4 | 3.5714 | 0.6 | 3.3333 | 9.7619
| 8353 | 0.6 | 6.6667 | 12.8571 | 18.5027 | 2.4456 | 3.2 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 8354 | 1 | 4 | 15.4286 | 21.6229 | 3.1467 | 3.0476 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 8355 | 0.4 | 10 | 11.4894 | 16.3046 | 2.7283 | 2.087 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 8356 | 0.4 | 10 | 10.5882 | 18.0087 | 2.4974 | 4.9231 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 8357 | 0.1 | 40 | 18.6207 | 25.1736 | 2.8606 | 3.6923 | 1 | 5 | 0.6 | 3.3333 | 48.3333
| 8358 | 0.6 | 6.6667 | 14.5946 | 22.4688 | 4.0342 | 3.84 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 8359 | 0.4 | 10 | 10.5882 | 17.2387 | 2.3838 | 4.2667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 8360 | 1 | 4 | 14.5946 | 23.4788 | 2.4842 | 6.4 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.8333
| 8361 | 1 | 4 | 11.4894 | 16.5805 | 2.3483 | 2.7429 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 8362 | 1.4 | 2.8571 | 10.5882 | 17.1915 | 2.3366 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 8363 | 1.4 | 2.8571 | 12.8571 | 26.569 | 3.0452 | 10.6667 | 0.6 | 8.3333 | 0.1 | 20 | 31.1905
| 8364 | 1 | 4 | 14.2105 | 22.5396 | 2.8434 | 5.4857 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 8365 | 1.2 | 3.3333 | 9.6429 | 15.5205 | 2.9686 | 2.9091 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 8366 | 0.8 | 5 | 12.8571 | 19.4947 | 3.1467 | 3.4909 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 8367 | 0.6 | 6.6667 | 14.2105 | 18.5392 | 2.1953 | 2.1333 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 8368 | 1.6 | 2.5 | 10 | 20.041 | 3.4203 | 6.6207 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10
| 8369 | 0.4 | 10 | 14.2105 | 18.8363 | 2.1953 | 2.4304 | 1 | 5 | 0.1 | 20 | 35
| 8370 | 0.8 | 5 | 10.5882 | 19.1506 | 2.7442 | 5.8182 | 1.4 | 3.5714 | 0.8 | 2.5 | 11.0714
| 8371 | 1 | 4 | 10.3846 | 17.443 | 2.2584 | 4.8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 8372 | 0.8 | 5 | 14.5946 | 20.8383 | 2.5514 | 3.6923 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 8373 | 0.6 | 6.6667 | 10.8 | 18.1631 | 3.1892 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 8374 | 0.4 | 10 | 13.1707 | 19.928 | 3.0649 | 3.6923 | 1 | 5 | 0.2 | 10 | 25
| 8375 | 0.6 | 6.6667 | 12.2727 | 18.6668 | 3.0256 | 3.3684 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 8376 | 1 | 4 | 9.8182 | 19.3234 | 3.1053 | 6.4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 8377 | 1 | 4 | 22.5 | 29.4833 | 3.0649 | 3.9184 | 1 | 5 | 0.2 | 10 | 19
| 8378 | 0.6 | 6.6667 | 13.8462 | 22.089 | 4.069 | 4.1739 | 1 | 5 | 0.2 | 10 | 21.6667
| 8379 | 0.6 | 6.6667 | 12.8571 | 19.1107 | 3.6589 | 2.5946 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 8380 | 1 | 4 | 11.25 | 18.5917 | 3.1678 | 4.1739 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 8381 | 1 | 4 | 9 | 18.7005 | 2.8434 | 6.8571 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 8382 | 1 | 4 | 11.4894 | 20.7469 | 2.6369 | 6.6207 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 8383 | 0.8 | 5 | 9.8182 | 17.8769 | 4.1404 | 3.9184 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 8384 | 0.6 | 6.6667 | 19.2857 | 30.2897 | 3.3239 | 7.68 | 1 | 5 | 0.2 | 10 | 21.6667
| 8385 | 1 | 4 | 12.2727 | 18.852 | 3.2109 | 3.3684 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 8386 | 0.8 | 5 | 11.4894 | 19.9129 | 2.7765 | 5.6471 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 8387 | 1 | 4 | 11.25 | 17.5028 | 3.1053 | 3.1475 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 8388 | 0.8 | 5 | 10.1887 | 18.8934 | 3.3714 | 5.3333 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 8389 | 0.6 | 6.6667 | 12.8571 | 21.0564 | 3.1467 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 8390 | 0.8 | 5 | 13.5 | 21.3256 | 3.0256 | 4.8 | 1 | 5 | 0.2 | 10 | 20
| 8391 | 0.4 | 10 | 11.7391 | 17.8188 | 3.1258 | 2.9538 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 8392 | 1 | 4 | 12.5581 | 20.2561 | 3.2329 | 4.4651 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 8393 | 1.2 | 3.3333 | 11.25 | 20.232 | 3.4963 | 5.4857 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 8394 | 0.4 | 10 | 12.8571 | 18.9528 | 2.8957 | 3.2 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 8395 | 0.6 | 6.6667 | 11.0204 | 17.2276 | 2.6517 | 3.5556 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 8396 | 1 | 4 | 10.8 | 20.913 | 2.433 | 7.68 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 8397 | 0.2 | 20 | 10 | 22.4434 | 2.8434 | 9.6 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 8398 | 1.2 | 3.3333 | 14.2105 | 21.0325 | 2.4583 | 4.3636 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 8399 | 0.2 | 20 | 16.3636 | 25.3277 | 3.6308 | 5.3333 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 8400 | 0.8 | 5 | 12.5581 | 19.995 | 2.6369 | 4.8 | 1 | 5 | 0.4 | 5 | 15
| 8401 | 1 | 4 | 12 | 20.3889 | 2.1953 | 6.1935 | 1.6 | 3.125 | 0.2 | 10 | 17.125
| 8402 | 1.2 | 3.3333 | 11.4894 | 20.2211 | 2.9136 | 5.8182 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 8403 | 1 | 4 | 15 | 23.89 | 3.8374 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 8404 | 0.8 | 5 | 9.8182 | 16.1734 | 1.9916 | 4.3636 | 1 | 5 | 0.8 | 2.5 | 12.5
| 8405 | 0.8 | 5 | 10.8 | 16.9686 | 2.9686 | 3.2 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 8406 | 1.4 | 2.8571 | 9.6429 | 16.8619 | 3.3007 | 3.9184 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 8407 | 1.2 | 3.3333 | 15.4286 | 23.1243 | 2.8957 | 4.8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 8408 | 0.6 | 6.6667 | 12.5581 | 22.6193 | 2.95 | 7.1111 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 8409 | 1 | 4 | 11.25 | 17.8502 | 2.7602 | 3.84 | 1 | 5 | 0.1 | 20 | 29
| 8410 | 1.2 | 3.3333 | 20.7692 | 30.9096 | 4.1404 | 6 | 1.8 | 2.7778 | 0.2 | 10 | 16.1111
| 8411 | 1.2 | 3.3333 | 11.25 | 19.8556 | 2.2056 | 6.4 | 1 | 5 | 0.4 | 5 | 13.3333
| 8412 | 1 | 4 | 14.2105 | 22.812 | 3.5489 | 5.0526 | 1 | 5 | 0.8 | 2.5 | 11.5
| 8413 | 0.8 | 5 | 15 | 22.9053 | 3.1053 | 4.8 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 8414 | 0.2 | 20 | 19.2857 | 29.4922 | 3.8065 | 6.4 | 1.6 | 3.125 | 0.1 | 20 | 43.125
| 8415 | 1 | 4 | 12.5581 | 19.631 | 2.6077 | 4.4651 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 8416 | 1 | 4 | 20 | 27.4035 | 2.0702 | 5.3333 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 8417 | 1.2 | 3.3333 | 14.2105 | 29.558 | 3.3475 | 12 | 1.6 | 3.125 | 0.4 | 5 | 11.4583
| 8418 | 1.6 | 2.5 | 20.7692 | 27.3272 | 2.2913 | 4.2667 | 0.8 | 6.25 | 0.2 | 10 | 18.75
| 8419 | 0.8 | 5 | 12.2727 | 19.0175 | 3.1892 | 3.5556 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 8420 | 0.6 | 6.6667 | 11.4894 | 18.1642 | 2.4082 | 4.2667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 8421 | 1.4 | 2.8571 | 11.4894 | 19.768 | 2.7929 | 5.4857 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 8422 | 1.4 | 2.8571 | 12 | 18.3343 | 2.8434 | 3.4909 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 8423 | 1.2 | 3.3333 | 16.875 | 24.2369 | 3.9333 | 3.4286 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 8424 | 1.2 | 3.3333 | 15.4286 | 21.5619 | 2.5106 | 3.6226 | 1 | 5 | 0.2 | 10 | 18.3333
| 8425 | 0.8 | 5 | 16.3636 | 22.9872 | 3.2552 | 3.3684 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 8426 | 0.8 | 5 | 16.875 | 26.4554 | 3.9333 | 5.6471 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 8427 | 0.4 | 10 | 9.1525 | 18.7223 | 2.7126 | 6.8571 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 8428 | 0.8 | 5 | 9.3103 | 18.2126 | 3.2552 | 5.6471 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 8429 | 0.8 | 5 | 14.2105 | 23.4369 | 2.8263 | 6.4 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 8430 | 0.8 | 5 | 15 | 33.2398 | 3.4706 | 14.7692 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 8431 | 1.2 | 3.3333 | 14.2105 | 20.6556 | 2.36 | 4.0851 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 8432 | 0.6 | 6.6667 | 8.4375 | 14.5574 | 2.8095 | 3.3103 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 8433 | 1.6 | 2.5 | 9.8182 | 16.9098 | 3.8374 | 3.2542 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.0833
| 8434 | 0.4 | 10 | 9.4737 | 16.1813 | 3.085 | 3.6226 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 8435 | 1 | 4 | 10.3846 | 18.4944 | 2.7765 | 5.3333 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 8436 | 0.4 | 10 | 13.5 | 20.8417 | 3.1678 | 4.1739 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 8437 | 1 | 4 | 22.5 | 30.8296 | 4.4112 | 3.9184 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 8438 | 0.6 | 6.6667 | 13.5 | 23.5068 | 2.8957 | 7.1111 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 8439 | 0.8 | 5 | 11.7391 | 20.4833 | 2.7442 | 6 | 1 | 5 | 0.2 | 10 | 20
| 8440 | 0.8 | 5 | 12.2727 | 19.8472 | 3.2109 | 4.3636 | 1 | 5 | 0.8 | 2.5 | 12.5
| 8441 | 0.8 | 5 | 14.5946 | 20.1466 | 2.0611 | 3.4909 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 8442 | 0.4 | 10 | 14.5946 | 28.0954 | 3.9008 | 9.6 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 8443 | 1.2 | 3.3333 | 13.5 | 19.0907 | 2.6369 | 2.9538 | 0.8 | 6.25 | 0.8 | 2.5 | 12.0833
| 8444 | 1.4 | 2.8571 | 11.7391 | 19.3836 | 3.4706 | 4.1739 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 8445 | 0.1 | 40 | 12.5581 | 20.0674 | 2.8263 | 4.6829 | 1.2 | 4.1667 | 0.2 | 10 | 54.1667
| 8446 | 1 | 4 | 9.1525 | 16.6133 | 2.5376 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 8447 | 1 | 4 | 12 | 21.7885 | 3.1678 | 6.6207 | 1 | 5 | 0.2 | 10 | 19
| 8448 | 1 | 4 | 11.0204 | 17.1704 | 2.95 | 3.2 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 8449 | 1 | 4 | 12.5581 | 19.8373 | 3.1053 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 8450 | 0.4 | 10 | 13.5 | 19.9136 | 3.0452 | 3.3684 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 8451 | 0.1 | 40 | 13.8462 | 23.5977 | 3.9333 | 5.8182 | 1 | 5 | 0.2 | 10 | 55
| 8452 | 0.6 | 6.6667 | 18.6207 | 27.9707 | 2.95 | 6.4 | 0.4 | 12.5 | 0.8 | 2.5 | 21.6667
| 8453 | 0.4 | 10 | 9 | 16.3403 | 3.2552 | 4.0851 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 8454 | 1 | 4 | 15 | 21.1148 | 2.8606 | 3.2542 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 8455 | 0.8 | 5 | 14.5946 | 28.8042 | 4.1043 | 10.1053 | 1 | 5 | 0.2 | 10 | 20
| 8456 | 1.6 | 2.5 | 11.0204 | 21.7456 | 3.0452 | 7.68 | 1 | 5 | 0.2 | 10 | 17.5
| 8457 | 0.6 | 6.6667 | 13.5 | 21.9734 | 2.8263 | 5.6471 | 0.4 | 12.5 | 0.2 | 10 | 29.1667
| 8458 | 0.2 | 20 | 15.8824 | 23.4324 | 3.085 | 4.4651 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 8459 | 1.4 | 2.8571 | 15.8824 | 27.2951 | 3.0649 | 8.3478 | 1 | 5 | 0.2 | 10 | 17.8571
| 8460 | 0.6 | 6.6667 | 11.4894 | 19.4838 | 3.6308 | 4.3636 | 1 | 5 | 0.2 | 10 | 21.6667
| 8461 | 1 | 4 | 11.4894 | 18.0254 | 3.0452 | 3.4909 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 8462 | 1 | 4 | 14.5946 | 23.6457 | 3.2329 | 5.8182 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 8463 | 1 | 4 | 17.4194 | 28.9781 | 3.2109 | 8.3478 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 8464 | 1 | 4 | 11.4894 | 17.6746 | 2.4205 | 3.7647 | 1 | 5 | 0.1 | 20 | 29
| 8465 | 0.8 | 5 | 17.4194 | 25.1063 | 3.4203 | 4.2667 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 8466 | 0.8 | 5 | 15 | 22.0637 | 3.3714 | 3.6923 | 1 | 5 | 0.1 | 20 | 30
| 8467 | 0.2 | 20 | 12 | 18.885 | 3.6308 | 3.2542 | 0.6 | 8.3333 | 0.2 | 10 | 38.3333
| 8468 | 0.8 | 5 | 9.6429 | 18.0066 | 2.878 | 5.4857 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 8469 | 1 | 4 | 10.8 | 18.685 | 3.085 | 4.8 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 8470 | 1.2 | 3.3333 | 15 | 20.7614 | 2.8957 | 2.8657 | 0.4 | 12.5 | 0.2 | 10 | 25.8333
| 8471 | 0.8 | 5 | 10.5882 | 18.9601 | 2.3719 | 6 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 8472 | 1.2 | 3.3333 | 23.4783 | 29.0411 | 2.6971 | 2.8657 | 1 | 5 | 0.1 | 20 | 28.3333
| 8473 | 1.2 | 3.3333 | 10.8 | 17.3261 | 2.6077 | 3.9184 | 1.4 | 3.5714 | 0.8 | 2.5 | 9.4048
| 8474 | 1 | 4 | 11.25 | 21.521 | 4.4528 | 5.8182 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 8475 | 0.6 | 6.6667 | 15 | 21.9457 | 2.8606 | 4.0851 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 8476 | 1 | 4 | 10.3846 | 21.3198 | 3.2552 | 7.68 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 8477 | 1.2 | 3.3333 | 12 | 21.7528 | 2.8957 | 6.8571 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 8478 | 0.8 | 5 | 9 | 19.4329 | 3.5758 | 6.8571 | 0.1 | 50 | 0.1 | 20 | 75
| 8479 | 0.4 | 10 | 15.4286 | 22.9959 | 3.3007 | 4.2667 | 1.6 | 3.125 | 0.2 | 10 | 23.125
| 8480 | 0.8 | 5 | 15.8824 | 25.1399 | 2.6369 | 6.6207 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 8481 | 0.6 | 6.6667 | 11.25 | 19.8469 | 4.3303 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 8482 | 1.2 | 3.3333 | 16.3636 | 23.5573 | 2.6222 | 4.5714 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 8483 | 0.6 | 6.6667 | 15.8824 | 25.1408 | 3.0649 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 15
| 8484 | 0.8 | 5 | 14.5946 | 23.3469 | 3.1053 | 5.6471 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 8485 | 0.6 | 6.6667 | 10.8 | 17.5961 | 2.6222 | 4.1739 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 8486 | 0.6 | 6.6667 | 12.5581 | 19.6138 | 2.4842 | 4.5714 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 8487 | 0.4 | 10 | 10.5882 | 18.8424 | 3.0649 | 5.1892 | 1 | 5 | 0.2 | 10 | 25
| 8488 | 1.2 | 3.3333 | 12 | 17.344 | 2.9136 | 2.4304 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 8489 | 1.2 | 3.3333 | 11.4894 | 19.104 | 2.9317 | 4.6829 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 8490 | 0.6 | 6.6667 | 13.8462 | 20.7786 | 3.1678 | 3.7647 | 1 | 5 | 0.4 | 5 | 16.6667
| 8491 | 1.8 | 2.2222 | 11.25 | 20.0981 | 3.6589 | 5.1892 | 0.6 | 8.3333 | 0.8 | 2.5 | 13.0556
| 8492 | 1.2 | 3.3333 | 15 | 23.986 | 3.1678 | 5.8182 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 8493 | 0.8 | 5 | 15.4286 | 27.0316 | 3.2552 | 8.3478 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 8494 | 0.8 | 5 | 9.4737 | 18.8801 | 3.0064 | 6.4 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 8495 | 0.4 | 10 | 9.6429 | 16.7597 | 3.8065 | 3.3103 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 8496 | 1 | 4 | 9.4737 | 15.763 | 2.6667 | 3.6226 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 8497 | 1 | 4 | 21.6 | 28.2507 | 3.6031 | 3.0476 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 8498 | 0.6 | 6.6667 | 13.5 | 18.3065 | 2.2802 | 2.5263 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 8499 | 0.6 | 6.6667 | 9.4737 | 14.7804 | 2.5241 | 2.7826 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 8500 | 0.4 | 10 | 17.4194 | 24.8342 | 2.8434 | 4.5714 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 8501 | 0.8 | 5 | 13.8462 | 21.7325 | 2.6971 | 5.1892 | 0.6 | 8.3333 | 0.1 | 20 | 33.3333
| 8502 | 0.4 | 10 | 16.3636 | 24.0829 | 2.6667 | 5.0526 | 1.6 | 3.125 | 0.6 | 3.3333 | 16.4583
| 8503 | 0.2 | 20 | 13.1707 | 19.9497 | 2.8606 | 3.9184 | 0.6 | 8.3333 | 0.6 | 3.3333 | 31.6667
| 8504 | 0.6 | 6.6667 | 18 | 26.3078 | 3.2552 | 5.0526 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 8505 | 0.6 | 6.6667 | 10.1887 | 19.5118 | 3.8374 | 5.4857 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 8506 | 1.2 | 3.3333 | 11.0204 | 17.4799 | 2.9686 | 3.4909 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 8507 | 0.6 | 6.6667 | 11.0204 | 16.5677 | 2.237 | 3.3103 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 8508 | 0.4 | 10 | 8.1818 | 18.7052 | 2.8434 | 7.68 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 8509 | 0.6 | 6.6667 | 10 | 17.5851 | 2.3959 | 5.1892 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 8510 | 0.8 | 5 | 12.2727 | 23.3046 | 4.4112 | 6.6207 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 8511 | 0.4 | 10 | 11.4894 | 18.3674 | 2.7929 | 4.0851 | 1 | 5 | 0.1 | 20 | 35
| 8512 | 0.6 | 6.6667 | 12.8571 | 20.7839 | 2.5934 | 5.3333 | 1 | 5 | 0.6 | 3.3333 | 15
| 8513 | 0.8 | 5 | 11.7391 | 17.7698 | 2.7765 | 3.2542 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 8514 | 1.4 | 2.8571 | 14.2105 | 22.4798 | 2.6222 | 5.6471 | 0.6 | 8.3333 | 0.2 | 10 | 21.1905
| 8515 | 1.2 | 3.3333 | 13.8462 | 20.528 | 2.6818 | 4 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 8516 | 1.2 | 3.3333 | 13.8462 | 20.483 | 2.6369 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 8517 | 0.4 | 10 | 12.8571 | 19.7621 | 3.0649 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 8518 | 0.8 | 5 | 15.8824 | 25.5375 | 3.2552 | 6.4 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 8519 | 0.6 | 6.6667 | 11.7391 | 20.5487 | 2.8095 | 6 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 8520 | 0.6 | 6.6667 | 16.3636 | 24.694 | 3.2778 | 5.0526 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 8521 | 1.4 | 2.8571 | 15.8824 | 25.0715 | 3.1892 | 6 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 8522 | 1.2 | 3.3333 | 15 | 21.8877 | 2.5241 | 4.3636 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 8523 | 0.6 | 6.6667 | 11.0204 | 17.2624 | 2.9317 | 3.3103 | 1 | 5 | 0.2 | 10 | 21.6667
| 8524 | 1 | 4 | 11.25 | 22.2952 | 3.0452 | 8 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 8525 | 0.6 | 6.6667 | 12 | 20.1745 | 3.6031 | 4.5714 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 8526 | 0.6 | 6.6667 | 14.2105 | 20.9928 | 2.6971 | 4.0851 | 1 | 5 | 0.6 | 3.3333 | 15
| 8527 | 0.4 | 10 | 10.8 | 19.896 | 3.2778 | 5.8182 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 8528 | 0.4 | 10 | 12.8571 | 20.8571 | 2.6667 | 5.3333 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 8529 | 1 | 4 | 12 | 18.9114 | 3.1467 | 3.7647 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 8530 | 0.4 | 10 | 10.1887 | 19.1251 | 3.6031 | 5.3333 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 8531 | 0.4 | 10 | 11.0204 | 19.5513 | 3.0452 | 5.4857 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 8532 | 0.2 | 20 | 11.4894 | 18.0687 | 3.2109 | 3.3684 | 1.2 | 4.1667 | 0.6 | 3.3333 | 27.5
| 8533 | 0.6 | 6.6667 | 12.2727 | 22.0799 | 2.95 | 6.8571 | 1 | 5 | 0.2 | 10 | 21.6667
| 8534 | 0.8 | 5 | 12.8571 | 22.2133 | 4.6733 | 4.6829 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 8535 | 1 | 4 | 13.8462 | 23.8492 | 3.6031 | 6.4 | 1 | 5 | 0.2 | 10 | 19
| 8536 | 1.2 | 3.3333 | 12.5581 | 18.6994 | 2.7126 | 3.4286 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 8537 | 0.6 | 6.6667 | 10 | 20.6032 | 3.746 | 6.8571 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 8538 | 0.8 | 5 | 12.5581 | 21.0555 | 2.4974 | 6 | 1 | 5 | 0.2 | 10 | 20
| 8539 | 0.4 | 10 | 11.25 | 20.3984 | 2.2913 | 6.8571 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 8540 | 0.6 | 6.6667 | 14.5946 | 21.3166 | 2.6369 | 4.0851 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 8541 | 1 | 4 | 13.8462 | 20.0139 | 3.1678 | 3 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 8542 | 1.2 | 3.3333 | 20 | 28.1785 | 3.1258 | 5.0526 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 8543 | 1.4 | 2.8571 | 13.1707 | 21.6839 | 3.3239 | 5.1892 | 1 | 5 | 0.2 | 10 | 17.8571
| 8544 | 0.2 | 20 | 12.2727 | 21.3892 | 3.6308 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 8545 | 0.8 | 5 | 12 | 21.2667 | 3.9333 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 8546 | 1.2 | 3.3333 | 11.25 | 19.4522 | 3.6308 | 4.5714 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 8547 | 0.6 | 6.6667 | 11.4894 | 19.1763 | 3.4203 | 4.2667 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 8548 | 1 | 4 | 16.3636 | 22.6212 | 2.5652 | 3.6923 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 8549 | 1.2 | 3.3333 | 11.7391 | 19.2137 | 3.3007 | 4.1739 | 1 | 5 | 0.4 | 5 | 13.3333
| 8550 | 0.4 | 10 | 14.5946 | 26.367 | 3.0452 | 8.7273 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 8551 | 1.4 | 2.8571 | 15.4286 | 21.2561 | 2.3366 | 3.4909 | 1.6 | 3.125 | 0.6 | 3.3333 | 9.3155
| 8552 | 1.2 | 3.3333 | 15.8824 | 23.7163 | 2.3483 | 5.4857 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 8553 | 0.6 | 6.6667 | 10.5882 | 17.4905 | 2.7283 | 4.1739 | 1 | 5 | 0.2 | 10 | 21.6667
| 8554 | 0.8 | 5 | 9.1525 | 15.2661 | 2.9136 | 3.2 | 1 | 5 | 0.4 | 5 | 15
| 8555 | 0.8 | 5 | 11.25 | 21.2749 | 3.1678 | 6.8571 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 8556 | 0.8 | 5 | 13.8462 | 22.8978 | 2.6517 | 6.4 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 8557 | 0.6 | 6.6667 | 9.8182 | 18.0121 | 2.8606 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 8558 | 0.4 | 10 | 9.3103 | 16.9617 | 2.7283 | 4.9231 | 1 | 5 | 0.4 | 5 | 20
| 8559 | 0.8 | 5 | 11.7391 | 18.818 | 2.3959 | 4.6829 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 8560 | 1 | 4 | 12.2727 | 19.4194 | 3.1467 | 4 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 8561 | 1.4 | 2.8571 | 9.1525 | 15.901 | 3.1258 | 3.6226 | 1 | 5 | 0.8 | 2.5 | 10.3571
| 8562 | 0.6 | 6.6667 | 18.6207 | 25.189 | 2.7283 | 3.84 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 8563 | 0.6 | 6.6667 | 10.1887 | 16.9371 | 3.1258 | 3.6226 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 8564 | 0.4 | 10 | 13.1707 | 21.077 | 2.4205 | 5.4857 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 8565 | 0.6 | 6.6667 | 15 | 21.0348 | 3.776 | 2.2588 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 8566 | 0.8 | 5 | 12 | 24.0209 | 2.878 | 9.1429 | 1 | 5 | 0.4 | 5 | 15
| 8567 | 1.2 | 3.3333 | 11.4894 | 17.2407 | 2.5514 | 3.2 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 8568 | 1.2 | 3.3333 | 7.2 | 13.5894 | 2.0258 | 4.3636 | 1 | 5 | 0.2 | 10 | 18.3333
| 8569 | 1.4 | 2.8571 | 11.0204 | 17.6711 | 2.0793 | 4.5714 | 1.4 | 3.5714 | 0.4 | 5 | 11.4286
| 8570 | 1.2 | 3.3333 | 9.4737 | 17.1517 | 2.878 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 8571 | 0.4 | 10 | 10.5882 | 18.163 | 2.6517 | 4.9231 | 1 | 5 | 0.4 | 5 | 20
| 8572 | 0.2 | 20 | 9.6429 | 15.7498 | 2.5514 | 3.5556 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 8573 | 0.6 | 6.6667 | 11.7391 | 18.0851 | 2.0793 | 4.2667 | 1 | 5 | 0.4 | 5 | 16.6667
| 8574 | 1.6 | 2.5 | 18.6207 | 27.6463 | 3.0256 | 6 | 1.6 | 3.125 | 0.8 | 2.5 | 8.125
| 8575 | 0.8 | 5 | 12.2727 | 18.6861 | 3.6308 | 2.7826 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 8576 | 0.8 | 5 | 14.5946 | 23.4977 | 3.085 | 5.8182 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 8577 | 1 | 4 | 12.5581 | 20.2026 | 3.4706 | 4.1739 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 8578 | 0.4 | 10 | 13.5 | 21.104 | 2.5514 | 5.0526 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 8579 | 1 | 4 | 13.8462 | 18.9446 | 2.6369 | 2.4615 | 1.4 | 3.5714 | 0.8 | 2.5 | 10.0714
| 8580 | 0.4 | 10 | 15.8824 | 25.1602 | 3.6308 | 5.6471 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 8581 | 1.2 | 3.3333 | 10.1887 | 16.9803 | 3.3007 | 3.4909 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 8582 | 0.4 | 10 | 20.7692 | 29.4227 | 3.1678 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 8583 | 0.2 | 20 | 15.8824 | 23.8523 | 2.4842 | 5.4857 | 0.6 | 8.3333 | 0.4 | 5 | 33.3333
| 8584 | 0.6 | 6.6667 | 9.6429 | 15.832 | 3.1892 | 3 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 8585 | 0.4 | 10 | 12.5581 | 20.4541 | 2.8434 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 8586 | 0.8 | 5 | 16.3636 | 21.1292 | 2.2056 | 2.56 | 1 | 5 | 0.4 | 5 | 15
| 8587 | 1.2 | 3.3333 | 15.8824 | 22.3634 | 2.3959 | 4.0851 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 8588 | 0.6 | 6.6667 | 12.2727 | 20.6701 | 2.5792 | 5.8182 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 8589 | 1.6 | 2.5 | 9.6429 | 16.5035 | 2.8606 | 4 | 1 | 5 | 0.8 | 2.5 | 10
| 8590 | 0.4 | 10 | 10.8 | 19.9996 | 2.0885 | 7.1111 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 8591 | 0.6 | 6.6667 | 7.6056 | 15.0657 | 3.8374 | 3.6226 | 1 | 5 | 0.4 | 5 | 16.6667
| 8592 | 0.8 | 5 | 10.8 | 19.858 | 3.8689 | 5.1892 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 8593 | 1.4 | 2.8571 | 10.5882 | 15.8292 | 2.4583 | 2.7826 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 8594 | 0.6 | 6.6667 | 8.7097 | 15.4277 | 2.878 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 8595 | 0.2 | 20 | 10.3846 | 17.4922 | 3.1892 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 8596 | 0.8 | 5 | 10 | 18.156 | 3.2329 | 4.9231 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 8597 | 1 | 4 | 18 | 25.3241 | 2.5241 | 4.8 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 8598 | 1 | 4 | 10.1887 | 17.3385 | 3.6589 | 3.4909 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 8599 | 0.8 | 5 | 12.8571 | 18.824 | 2.7126 | 3.2542 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 8600 | 0.8 | 5 | 12.8571 | 20.0671 | 3.4453 | 3.7647 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 8601 | 0.6 | 6.6667 | 9.6429 | 15.8406 | 2.433 | 3.7647 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 8602 | 0.8 | 5 | 8.3077 | 16.3244 | 3.4453 | 4.5714 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 8603 | 0.4 | 10 | 15.8824 | 24.3554 | 2.9873 | 5.4857 | 1.6 | 3.125 | 0.6 | 3.3333 | 16.4583
| 8604 | 0.4 | 10 | 15.8824 | 23.3931 | 3.746 | 3.7647 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 8605 | 0.6 | 6.6667 | 12.8571 | 23.3977 | 2.8606 | 7.68 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 8606 | 0.6 | 6.6667 | 12.5581 | 19.0204 | 2.6222 | 3.84 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 8607 | 0.4 | 10 | 11.25 | 18.5817 | 2.7602 | 4.5714 | 1 | 5 | 0.2 | 10 | 25
| 8608 | 0.2 | 20 | 10.1887 | 18.8485 | 3.4706 | 5.1892 | 1.6 | 3.125 | 0.6 | 3.3333 | 26.4583
| 8609 | 0.6 | 6.6667 | 19.2857 | 25.214 | 2.7283 | 3.2 | 1 | 5 | 0.6 | 3.3333 | 15
| 8610 | 1 | 4 | 14.5946 | 20.8362 | 2.9873 | 3.2542 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 8611 | 0.6 | 6.6667 | 13.1707 | 18.9852 | 2.8606 | 2.9538 | 1 | 5 | 0.2 | 10 | 21.6667
| 8612 | 1.4 | 2.8571 | 15.8824 | 21.9275 | 3.0452 | 3 | 0.8 | 6.25 | 0.8 | 2.5 | 11.6071
| 8613 | 0.6 | 6.6667 | 25.7143 | 32.4015 | 2.4205 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 8614 | 0.2 | 20 | 11.25 | 18.4278 | 2.7126 | 4.4651 | 1.2 | 4.1667 | 0.6 | 3.3333 | 27.5
| 8615 | 0.4 | 10 | 10.8 | 18.3314 | 3.1678 | 4.3636 | 1 | 5 | 0.2 | 10 | 25
| 8616 | 0.8 | 5 | 12 | 24.3745 | 2.2692 | 10.1053 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 8617 | 0.4 | 10 | 13.1707 | 20.2432 | 2.9873 | 4.0851 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 8618 | 0.4 | 10 | 11.0204 | 19.099 | 3.3957 | 4.6829 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 8619 | 0.4 | 10 | 14.2105 | 22.1516 | 2.6077 | 5.3333 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 8620 | 0.6 | 6.6667 | 12.2727 | 20.1902 | 2.7283 | 5.1892 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 8621 | 1 | 4 | 9.1525 | 13.9145 | 2.4205 | 2.3415 | 1 | 5 | 0.4 | 5 | 14
| 8622 | 1.2 | 3.3333 | 10.5882 | 19.0856 | 2.4974 | 6 | 1 | 5 | 0.2 | 10 | 18.3333
| 8623 | 1.4 | 2.8571 | 16.3636 | 23.3644 | 3.4453 | 3.5556 | 1 | 5 | 0.2 | 10 | 17.8571
| 8624 | 0.8 | 5 | 10 | 15.3296 | 2.4205 | 2.9091 | 1.4 | 3.5714 | 0.8 | 2.5 | 11.0714
| 8625 | 1.4 | 2.8571 | 12.5581 | 18.0606 | 2.5934 | 2.9091 | 1.4 | 3.5714 | 0.4 | 5 | 11.4286
| 8626 | 0.6 | 6.6667 | 10 | 17.0256 | 3.0256 | 4 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 8627 | 0.4 | 10 | 13.5 | 21.2891 | 3.3239 | 4.4651 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 8628 | 0.8 | 5 | 9.4737 | 18.1703 | 3.2109 | 5.4857 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 8629 | 1.4 | 2.8571 | 11.25 | 21.8835 | 3.5224 | 7.1111 | 1 | 5 | 0.4 | 5 | 12.8571
| 8630 | 0.8 | 5 | 12.2727 | 17.8407 | 2.4712 | 3.0968 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 8631 | 1.2 | 3.3333 | 10.1887 | 19.0701 | 3.3957 | 5.4857 | 0.4 | 12.5 | 0.1 | 20 | 35.8333
| 8632 | 1.2 | 3.3333 | 13.5 | 21.4053 | 3.1053 | 4.8 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 8633 | 1.4 | 2.8571 | 8.7097 | 16.3445 | 2.4456 | 5.1892 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 8634 | 0.2 | 20 | 13.1707 | 20.1657 | 2.7283 | 4.2667 | 0.8 | 6.25 | 0.8 | 2.5 | 28.75
| 8635 | 0.8 | 5 | 11.7391 | 17.439 | 2.4456 | 3.2542 | 1 | 5 | 0.1 | 20 | 30
| 8636 | 0.8 | 5 | 10.3846 | 16.3682 | 2.2913 | 3.6923 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 8637 | 1 | 4 | 11.25 | 17.7567 | 2.6667 | 3.84 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 8638 | 1 | 4 | 12 | 20.95 | 2.95 | 6 | 1 | 5 | 1 | 2 | 11
| 8639 | 0.6 | 6.6667 | 12 | 19.1239 | 2.95 | 4.1739 | 1 | 5 | 0.4 | 5 | 16.6667
| 8640 | 1.6 | 2.5 | 13.5 | 39.7913 | 2.2913 | 24 | 1.2 | 4.1667 | 0.4 | 5 | 11.6667
| 8641 | 0.6 | 6.6667 | 16.3636 | 21.7932 | 2.0611 | 3.3684 | 1 | 5 | 0.4 | 5 | 16.6667
| 8642 | 0.6 | 6.6667 | 11.0204 | 16.9011 | 2.3251 | 3.5556 | 1 | 5 | 0.6 | 3.3333 | 15
| 8643 | 1.2 | 3.3333 | 11.0204 | 17.6589 | 2.3719 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 8644 | 1 | 4 | 13.8462 | 20.6569 | 2.6369 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 8645 | 1.6 | 2.5 | 12.8571 | 19.5684 | 2.7929 | 3.9184 | 0.6 | 8.3333 | 0.4 | 5 | 15.8333
| 8646 | 0.8 | 5 | 12.8571 | 21.0764 | 2.0258 | 6.1935 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 8647 | 0.6 | 6.6667 | 16.875 | 24.9033 | 3.1053 | 4.9231 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 8648 | 1 | 4 | 12.2727 | 18.8162 | 2.4583 | 4.0851 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 8649 | 0.4 | 10 | 12.8571 | 20.5657 | 3.0256 | 4.6829 | 1 | 5 | 0.2 | 10 | 25
| 8650 | 0.4 | 10 | 11.25 | 18.5353 | 3.4453 | 3.84 | 1 | 5 | 0.4 | 5 | 20
| 8651 | 0.4 | 10 | 9.4737 | 16.3759 | 2.7283 | 4.1739 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 8652 | 1 | 4 | 15.4286 | 22.7246 | 3.2109 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 8653 | 0.6 | 6.6667 | 9.6429 | 19.951 | 3.6875 | 6.6207 | 1 | 5 | 0.4 | 5 | 16.6667
| 8654 | 0.8 | 5 | 15 | 22.2242 | 2.8606 | 4.3636 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 8655 | 1.2 | 3.3333 | 12 | 19.985 | 2.6517 | 5.3333 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 8656 | 1.2 | 3.3333 | 10 | 16.449 | 2.8263 | 3.6226 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.1667
| 8657 | 0.4 | 10 | 10.1887 | 16.496 | 3.6031 | 2.7042 | 1 | 5 | 0.1 | 20 | 35
| 8658 | 0.6 | 6.6667 | 10.5882 | 18.8575 | 2.6222 | 5.6471 | 1 | 5 | 0.2 | 10 | 21.6667
| 8659 | 1 | 4 | 12.5581 | 20.1026 | 3.2778 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 8660 | 1 | 4 | 13.1707 | 23.207 | 2.6517 | 7.3846 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 8661 | 1.2 | 3.3333 | 10.8 | 16.5652 | 2.5652 | 3.2 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 8662 | 1.2 | 3.3333 | 12.5581 | 19.191 | 2.7929 | 3.84 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 8663 | 0.6 | 6.6667 | 11.25 | 17.8895 | 3.2109 | 3.4286 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 8664 | 0.6 | 6.6667 | 15.4286 | 24.5752 | 3.1467 | 6 | 1 | 5 | 0.1 | 20 | 31.6667
| 8665 | 1 | 4 | 11.7391 | 19.8423 | 3.4203 | 4.6829 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 8666 | 1.4 | 2.8571 | 12.8571 | 21.0528 | 3.3957 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 8667 | 1.2 | 3.3333 | 13.5 | 19.7029 | 2.5106 | 3.6923 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 8668 | 1.4 | 2.8571 | 11.4894 | 19.5921 | 2.9136 | 5.1892 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 8669 | 0.6 | 6.6667 | 8.4375 | 14.3095 | 3.0064 | 2.8657 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 8670 | 1 | 4 | 10.1887 | 17.9696 | 2.7283 | 5.0526 | 1 | 5 | 0.2 | 10 | 19
| 8671 | 0.8 | 5 | 10.3846 | 19.3706 | 3.1678 | 5.8182 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 8672 | 1 | 4 | 10.5882 | 17.1441 | 3.0649 | 3.4909 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 8673 | 0.8 | 5 | 14.2105 | 21.5242 | 2.95 | 4.3636 | 1.2 | 4.1667 | 1 | 2 | 11.1667
| 8674 | 1.2 | 3.3333 | 12.2727 | 20.664 | 2.7442 | 5.6471 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 8675 | 1 | 4 | 8.0597 | 15.3186 | 3.085 | 4.1739 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 8676 | 1 | 4 | 7.8261 | 16.7103 | 2.4842 | 6.4 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 8677 | 1 | 4 | 14.2105 | 20.3644 | 3.0064 | 3.1475 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 8678 | 1 | 4 | 10.8 | 16.7084 | 3.1258 | 2.7826 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 8679 | 1.6 | 2.5 | 11.7391 | 17.33 | 2.6818 | 2.9091 | 1.4 | 3.5714 | 0.4 | 5 | 11.0714
| 8680 | 0.6 | 6.6667 | 16.875 | 25.9618 | 4.0342 | 5.0526 | 1 | 5 | 0.6 | 3.3333 | 15
| 8681 | 0.8 | 5 | 13.8462 | 23.8179 | 2.8606 | 7.1111 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 8682 | 0.8 | 5 | 12.2727 | 17.6798 | 2.9136 | 2.4935 | 1.4 | 3.5714 | 0.1 | 20 | 28.5714
| 8683 | 1 | 4 | 12 | 20.6557 | 3.6031 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 8684 | 0.8 | 5 | 16.3636 | 23.3471 | 2.8095 | 4.1739 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 8685 | 0.4 | 10 | 12.8571 | 21.4036 | 2.7283 | 5.8182 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 8686 | 1.2 | 3.3333 | 11.4894 | 19.273 | 2.8606 | 4.9231 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 8687 | 1.2 | 3.3333 | 15 | 24.0909 | 4.2909 | 4.8 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 8688 | 1.2 | 3.3333 | 13.5 | 20.4796 | 2.4082 | 4.5714 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 8689 | 0.6 | 6.6667 | 15.4286 | 22.3137 | 3.0452 | 3.84 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 8690 | 0.6 | 6.6667 | 8.0597 | 16.5576 | 3.4453 | 5.0526 | 1 | 5 | 0.2 | 10 | 21.6667
| 8691 | 0.8 | 5 | 10.1887 | 19.1135 | 3.2778 | 5.6471 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 8692 | 1 | 4 | 10 | 17.7917 | 2.4583 | 5.3333 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 8693 | 0.8 | 5 | 14.2105 | 21.5059 | 3.6031 | 3.6923 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 8694 | 0.8 | 5 | 11.7391 | 21.1348 | 3.3957 | 6 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 8695 | 0.6 | 6.6667 | 10.8 | 20.5177 | 2.8606 | 6.8571 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 8696 | 0.8 | 5 | 8.4375 | 16.1251 | 3.3239 | 4.3636 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 8697 | 0.6 | 6.6667 | 10.1887 | 20.4513 | 2.878 | 7.3846 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 8698 | 0.8 | 5 | 13.5 | 21.9221 | 3.2329 | 5.1892 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 8699 | 1.2 | 3.3333 | 10.1887 | 18.185 | 2.5106 | 5.4857 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 8700 | 1.2 | 3.3333 | 11.0204 | 20.471 | 2.5934 | 6.8571 | 1 | 5 | 0.2 | 10 | 18.3333
| 8701 | 0.4 | 10 | 16.875 | 24.6814 | 3.0064 | 4.8 | 1 | 5 | 0.4 | 5 | 20
| 8702 | 1.2 | 3.3333 | 16.3636 | 22.6073 | 2.5514 | 3.6923 | 1 | 5 | 0.4 | 5 | 13.3333
| 8703 | 0.8 | 5 | 12.8571 | 18.5287 | 2.5241 | 3.1475 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 8704 | 0.8 | 5 | 12 | 20.5825 | 4.5825 | 4 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 8705 | 0.2 | 20 | 12.5581 | 19.7431 | 3.4203 | 3.7647 | 1.2 | 4.1667 | 0.6 | 3.3333 | 27.5
| 8706 | 0.8 | 5 | 12.5581 | 19.5927 | 2.8606 | 4.1739 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 8707 | 0.8 | 5 | 12.2727 | 18.1692 | 2.9873 | 2.9091 | 1 | 5 | 0.1 | 20 | 30
| 8708 | 0.6 | 6.6667 | 11.25 | 19.2652 | 2.6818 | 5.3333 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 8709 | 0.8 | 5 | 13.8462 | 24.9183 | 3.6875 | 7.3846 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 8710 | 1 | 4 | 9 | 15.3952 | 3.8689 | 2.5263 | 1 | 5 | 0.4 | 5 | 14
| 8711 | 1 | 4 | 15 | 20.8079 | 2.7602 | 3.0476 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 8712 | 1 | 4 | 15.4286 | 25.014 | 2.7283 | 6.8571 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 8713 | 0.8 | 5 | 10.3846 | 17.3849 | 2.8263 | 4.1739 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 8714 | 1.4 | 2.8571 | 12.2727 | 21.7986 | 3.1258 | 6.4 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 8715 | 1.4 | 2.8571 | 12.8571 | 20.7221 | 3.0649 | 4.8 | 0.4 | 12.5 | 0.2 | 10 | 25.3571
| 8716 | 0.8 | 5 | 13.8462 | 20.9764 | 3.0452 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 8717 | 0.4 | 10 | 18 | 27.5411 | 3.3475 | 6.1935 | 1.8 | 2.7778 | 0.1 | 20 | 32.7778
| 8718 | 0.6 | 6.6667 | 13.5 | 21.5371 | 2.5514 | 5.4857 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 8719 | 1.2 | 3.3333 | 13.8462 | 21.3386 | 2.8095 | 4.6829 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 8720 | 0.8 | 5 | 13.5 | 19.624 | 2.2056 | 3.9184 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 8721 | 1 | 4 | 12.5581 | 19.4362 | 2.878 | 4 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 8722 | 0.4 | 10 | 11.4894 | 17.5081 | 3.0649 | 2.9538 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 8723 | 0.8 | 5 | 8.8525 | 17.3601 | 2.8606 | 5.6471 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 8724 | 1.2 | 3.3333 | 15 | 22.5965 | 2.9136 | 4.6829 | 1.6 | 3.125 | 0.2 | 10 | 16.4583
| 8725 | 0.6 | 6.6667 | 12.5581 | 19.5339 | 2.5106 | 4.4651 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 8726 | 1.2 | 3.3333 | 15 | 24.869 | 4.8163 | 5.0526 | 1 | 5 | 0.1 | 20 | 28.3333
| 8727 | 1.2 | 3.3333 | 9.4737 | 15.8612 | 2.3024 | 4.0851 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 8728 | 1 | 4 | 12.8571 | 21.5867 | 3.8065 | 4.9231 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 8729 | 1 | 4 | 11.4894 | 18.1502 | 2.9686 | 3.6923 | 0.2 | 25 | 0.4 | 5 | 34
| 8730 | 1 | 4 | 10.1887 | 16.5779 | 3.1892 | 3.2 | 1 | 5 | 0.2 | 10 | 19
| 8731 | 0.8 | 5 | 15 | 25.9975 | 4.1404 | 6.8571 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 8732 | 0.6 | 6.6667 | 15 | 20.4927 | 2.3959 | 3.0968 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 8733 | 0.6 | 6.6667 | 13.8462 | 21.8973 | 3.6875 | 4.3636 | 1 | 5 | 0.6 | 3.3333 | 15
| 8734 | 0.2 | 20 | 13.1707 | 18.9985 | 3.0452 | 2.7826 | 1.2 | 4.1667 | 1 | 2 | 26.1667
| 8735 | 0.4 | 10 | 12.2727 | 19.3394 | 3.5758 | 3.4909 | 1.4 | 3.5714 | 0.8 | 2.5 | 16.0714
| 8736 | 0.4 | 10 | 10.5882 | 17.3234 | 3.6875 | 3.0476 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 8737 | 0.6 | 6.6667 | 15.8824 | 23.157 | 2.8095 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 8738 | 1.4 | 2.8571 | 15 | 20.0312 | 2.4712 | 2.56 | 1.2 | 4.1667 | 0.8 | 2.5 | 9.5238
| 8739 | 0.2 | 20 | 14.5946 | 21.5388 | 3.5758 | 3.3684 | 1 | 5 | 0.2 | 10 | 35
| 8740 | 0.6 | 6.6667 | 11.7391 | 20.9733 | 3.9008 | 5.3333 | 1 | 5 | 0.6 | 3.3333 | 15
| 8741 | 0.6 | 6.6667 | 10.8 | 17.7049 | 3.0649 | 3.84 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 8742 | 1.2 | 3.3333 | 9.4737 | 16.3201 | 3.0064 | 3.84 | 1 | 5 | 0.2 | 10 | 18.3333
| 8743 | 1 | 4 | 12.2727 | 20.2825 | 2.5241 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 8744 | 1 | 4 | 9 | 14.6269 | 2.5792 | 3.0476 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 8745 | 1 | 4 | 22.5 | 31.5663 | 2.4456 | 6.6207 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 8746 | 1.2 | 3.3333 | 12.8571 | 18.8209 | 2.4082 | 3.5556 | 1 | 5 | 0.4 | 5 | 13.3333
| 8747 | 0.2 | 20 | 13.8462 | 24.2522 | 3.5489 | 6.8571 | 1.2 | 4.1667 | 0.6 | 3.3333 | 27.5
| 8748 | 1 | 4 | 10.5882 | 18.2748 | 2.4974 | 5.1892 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.8333
| 8749 | 0.8 | 5 | 13.8462 | 22.5034 | 3.3239 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 8750 | 1.4 | 2.8571 | 13.8462 | 20.2709 | 2.0611 | 4.3636 | 0.8 | 6.25 | 0.1 | 20 | 29.1071
| 8751 | 1 | 4 | 11.25 | 18.0072 | 3.0649 | 3.6923 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 8752 | 0.6 | 6.6667 | 18.6207 | 24.3561 | 2.8263 | 2.9091 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 8753 | 0.6 | 6.6667 | 12 | 17.7111 | 2.0885 | 3.6226 | 1 | 5 | 0.6 | 3.3333 | 15
| 8754 | 0.4 | 10 | 9 | 19.228 | 2.8434 | 7.3846 | 0.4 | 12.5 | 0.8 | 2.5 | 25
| 8755 | 0.6 | 6.6667 | 16.3636 | 24.6342 | 3.3475 | 4.9231 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 8756 | 0.8 | 5 | 12.8571 | 20.7079 | 3.1678 | 4.6829 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 8757 | 1.2 | 3.3333 | 11.7391 | 19.0276 | 4.0342 | 3.2542 | 1 | 5 | 0.4 | 5 | 13.3333
| 8758 | 0.4 | 10 | 8.7097 | 18.3235 | 3.4203 | 6.1935 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 8759 | 1.6 | 2.5 | 11.0204 | 17.0706 | 2.6818 | 3.3684 | 1 | 5 | 0.4 | 5 | 12.5
| 8760 | 0.8 | 5 | 8.5714 | 15.9117 | 3.2552 | 4.0851 | 1 | 5 | 0.8 | 2.5 | 12.5
| 8761 | 0.4 | 10 | 13.1707 | 18.4612 | 2.3366 | 2.9538 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 8762 | 1.4 | 2.8571 | 12.2727 | 19.2016 | 2.5652 | 4.3636 | 1 | 5 | 0.4 | 5 | 12.8571
| 8763 | 1 | 4 | 12.8571 | 24.0038 | 3.1467 | 8 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 8764 | 1.8 | 2.2222 | 13.5 | 22.1115 | 3.1258 | 5.4857 | 1.2 | 4.1667 | 0.1 | 20 | 26.3889
| 8765 | 0.6 | 6.6667 | 10.5882 | 17.1468 | 3.776 | 2.7826 | 1 | 5 | 0.4 | 5 | 16.6667
| 8766 | 0.4 | 10 | 9.8182 | 16.8701 | 2.878 | 4.1739 | 1.6 | 3.125 | 0.4 | 5 | 18.125
| 8767 | 0.8 | 5 | 12.2727 | 18.2098 | 3.2329 | 2.7042 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 8768 | 0.8 | 5 | 15.8824 | 25.2299 | 3.3475 | 6 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 8769 | 1 | 4 | 16.875 | 23.3622 | 2.9317 | 3.5556 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 8770 | 0.8 | 5 | 20 | 26.4433 | 3.3957 | 3.0476 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 8771 | 0.4 | 10 | 11.4894 | 16.6392 | 2.4456 | 2.7042 | 1 | 5 | 0.2 | 10 | 25
| 8772 | 1.2 | 3.3333 | 10.8 | 16.3025 | 2.5934 | 2.9091 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 8773 | 0.8 | 5 | 9.3103 | 17.0284 | 3.1467 | 4.5714 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 8774 | 1.2 | 3.3333 | 9.6429 | 16.8304 | 3.3475 | 3.84 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 8775 | 0.6 | 6.6667 | 11.4894 | 18.7854 | 3.2109 | 4.0851 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 8776 | 1.2 | 3.3333 | 11.0204 | 16.5517 | 2.6222 | 2.9091 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 8777 | 1.2 | 3.3333 | 7.1053 | 13.9868 | 3.1892 | 3.6923 | 1 | 5 | 0.2 | 10 | 18.3333
| 8778 | 0.4 | 10 | 11.0204 | 17.2154 | 3.3714 | 2.8235 | 1.6 | 3.125 | 0.2 | 10 | 23.125
| 8779 | 0.6 | 6.6667 | 11.25 | 19.6474 | 2.5792 | 5.8182 | 1 | 5 | 0.2 | 10 | 21.6667
| 8780 | 1 | 4 | 16.875 | 21.9602 | 2.8263 | 2.2588 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 8781 | 1 | 4 | 8.8525 | 16.9764 | 3.3239 | 4.8 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 8782 | 1 | 4 | 9.1525 | 15.6937 | 2.7765 | 3.7647 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 8783 | 0.8 | 5 | 14.5946 | 22.4411 | 4.2909 | 3.5556 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 8784 | 1 | 4 | 11.4894 | 20.2823 | 2.7929 | 6 | 1.4 | 3.5714 | 0.8 | 2.5 | 10.0714
| 8785 | 1.4 | 2.8571 | 11.4894 | 21.9223 | 3.5758 | 6.8571 | 1.4 | 3.5714 | 0.8 | 2.5 | 8.9286
| 8786 | 1 | 4 | 12.5581 | 20.9365 | 3.1892 | 5.1892 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 8787 | 1 | 4 | 12.2727 | 18.3377 | 3.0649 | 3 | 1 | 5 | 0.2 | 10 | 19
| 8788 | 0.6 | 6.6667 | 9.8182 | 16.8209 | 2.5376 | 4.4651 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 8789 | 1 | 4 | 17.4194 | 26.3094 | 3.8374 | 5.0526 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 8790 | 1 | 4 | 12.2727 | 19.0826 | 3.0452 | 3.7647 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 8791 | 0.6 | 6.6667 | 12.8571 | 21.355 | 3.4453 | 5.0526 | 0.4 | 12.5 | 0.2 | 10 | 29.1667
| 8792 | 1 | 4 | 12.2727 | 18.4984 | 3.0256 | 3.2 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 8793 | 0.6 | 6.6667 | 12.8571 | 19.9716 | 3.746 | 3.3684 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 8794 | 1.2 | 3.3333 | 11.0204 | 17.2533 | 3.2329 | 3 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 8795 | 0.8 | 5 | 10.3846 | 16.334 | 3.1258 | 2.8235 | 0.2 | 25 | 0.4 | 5 | 35
| 8796 | 0.2 | 20 | 15.8824 | 23.8667 | 2.9317 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 8797 | 1 | 4 | 13.5 | 21.0599 | 2.6369 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 8798 | 0.6 | 6.6667 | 11.4894 | 21.1535 | 3.4706 | 6.1935 | 1 | 5 | 0.1 | 20 | 31.6667
| 8799 | 0.8 | 5 | 12 | 18.7569 | 3.9333 | 2.8235 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 8800 | 0.8 | 5 | 15.8824 | 22.1996 | 2.8263 | 3.4909 | 1 | 5 | 0.1 | 20 | 30
| 8801 | 0.8 | 5 | 9.8182 | 21.7664 | 2.3483 | 9.6 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 8802 | 0.4 | 10 | 12.8571 | 20.8266 | 5.1868 | 2.7826 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 8803 | 0.8 | 5 | 12.2727 | 20.1094 | 2.9136 | 4.9231 | 1 | 5 | 0.1 | 20 | 30
| 8804 | 0.8 | 5 | 13.8462 | 20.3518 | 2.4205 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 8805 | 1.4 | 2.8571 | 11.0204 | 16.9242 | 2.3483 | 3.5556 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 8806 | 1.2 | 3.3333 | 12.2727 | 20.9071 | 2.9873 | 5.6471 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 8807 | 0.8 | 5 | 14.2105 | 23.4711 | 2.8606 | 6.4 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 8808 | 1.2 | 3.3333 | 9.6429 | 16.898 | 3.2552 | 4 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 8809 | 0.8 | 5 | 18.6207 | 23.8582 | 2.3719 | 2.8657 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 8810 | 0.4 | 10 | 11.7391 | 19.9157 | 2.9873 | 5.1892 | 1.4 | 3.5714 | 0.2 | 10 | 23.5714
| 8811 | 1.2 | 3.3333 | 10 | 18.6689 | 3.8689 | 4.8 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 8812 | 1 | 4 | 20.7692 | 26.3821 | 2.5652 | 3.0476 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 8813 | 1.2 | 3.3333 | 8.7097 | 16.5388 | 2.7765 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 8814 | 0.8 | 5 | 8.1818 | 15.1278 | 3.746 | 3.2 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 8815 | 1.2 | 3.3333 | 12.2727 | 18.2241 | 2.6971 | 3.2542 | 1.2 | 4.1667 | 0.1 | 20 | 27.5
| 8816 | 1 | 4 | 11.7391 | 17.852 | 2.4205 | 3.6923 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 8817 | 1.4 | 2.8571 | 18 | 27.8445 | 2.9873 | 6.8571 | 1 | 5 | 0.2 | 10 | 17.8571
| 8818 | 1 | 4 | 12 | 19.8365 | 3.3714 | 4.4651 | 1 | 5 | 0.2 | 10 | 19
| 8819 | 0.8 | 5 | 13.5 | 20.0812 | 3.0256 | 3.5556 | 1 | 5 | 0.8 | 2.5 | 12.5
| 8820 | 0.6 | 6.6667 | 11.7391 | 17.874 | 2.9873 | 3.1475 | 1 | 5 | 0.6 | 3.3333 | 15
| 8821 | 0.6 | 6.6667 | 13.5 | 19.4504 | 3.1678 | 2.7826 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 8822 | 0.6 | 6.6667 | 10.1887 | 16.565 | 2.2913 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 8823 | 1.2 | 3.3333 | 10.8 | 20.365 | 3.3714 | 6.1935 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 8824 | 0.6 | 6.6667 | 9.8182 | 18.7659 | 3.3007 | 5.6471 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 8825 | 1 | 4 | 7.9412 | 14.2755 | 2.8434 | 3.4909 | 1 | 5 | 0.2 | 10 | 19
| 8826 | 0.2 | 20 | 10.3846 | 19.5775 | 2.7929 | 6.4 | 1 | 5 | 0.4 | 5 | 30
| 8827 | 1.2 | 3.3333 | 15.4286 | 23.6585 | 2.7442 | 5.4857 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 8828 | 1.2 | 3.3333 | 10.8 | 19.8526 | 4 | 5.0526 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 8829 | 0.6 | 6.6667 | 13.5 | 19.4883 | 2.4974 | 3.4909 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 8830 | 0.8 | 5 | 12.2727 | 19.4205 | 3.8374 | 3.3103 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 8831 | 0.8 | 5 | 12.2727 | 20.0333 | 3.1892 | 4.5714 | 1 | 5 | 0.2 | 10 | 20
| 8832 | 0.2 | 20 | 8.7097 | 17.6233 | 2.9136 | 6 | 1.8 | 2.7778 | 0.6 | 3.3333 | 26.1111
| 8833 | 0.6 | 6.6667 | 12.5581 | 19.3689 | 2.6369 | 4.1739 | 1 | 5 | 0.4 | 5 | 16.6667
| 8834 | 0.4 | 10 | 9.3103 | 15.9608 | 2.3838 | 4.2667 | 1.4 | 3.5714 | 0.8 | 2.5 | 16.0714
| 8835 | 0.4 | 10 | 11.7391 | 21.2934 | 2.6971 | 6.8571 | 1 | 5 | 0.8 | 2.5 | 17.5
| 8836 | 0.6 | 6.6667 | 10.5882 | 16.3419 | 2.3251 | 3.4286 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 8837 | 1.2 | 3.3333 | 11.7391 | 18.5487 | 2.8095 | 4 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 8838 | 1 | 4 | 13.1707 | 19.5192 | 2.7929 | 3.5556 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 8839 | 0.4 | 10 | 12.5581 | 18.508 | 2.1852 | 3.7647 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 8840 | 1.4 | 2.8571 | 11.0204 | 19.0748 | 3.3714 | 4.6829 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 8841 | 0.8 | 5 | 15 | 22.0168 | 2.9317 | 4.0851 | 1 | 5 | 0.2 | 10 | 20
| 8842 | 1.4 | 2.8571 | 10.1887 | 19.4611 | 2.6517 | 6.6207 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 8843 | 1.2 | 3.3333 | 13.8462 | 22.2031 | 3.1678 | 5.1892 | 1.6 | 3.125 | 0.6 | 3.3333 | 9.7917
| 8844 | 1 | 4 | 9.8182 | 16.6838 | 3.0256 | 3.84 | 1 | 5 | 0.1 | 20 | 29
| 8845 | 0.8 | 5 | 10.1887 | 17.4256 | 3.746 | 3.4909 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 8846 | 0.4 | 10 | 11.4894 | 18.6523 | 3.4706 | 3.6923 | 1 | 5 | 1 | 2 | 17
| 8847 | 0.6 | 6.6667 | 10.1887 | 18.8809 | 3.0452 | 5.6471 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 8848 | 1.2 | 3.3333 | 19.2857 | 25.9691 | 2.8434 | 3.84 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 8849 | 1 | 4 | 16.3636 | 24.4796 | 4.9684 | 3.1475 | 1 | 5 | 0.4 | 5 | 14
| 8850 | 1.4 | 2.8571 | 11.0204 | 18.4657 | 3.4453 | 4 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 8851 | 1 | 4 | 11.4894 | 17.5737 | 2.5934 | 3.4909 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 8852 | 0.6 | 6.6667 | 15.8824 | 23.3114 | 3.2552 | 4.1739 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 8853 | 0.2 | 20 | 11.4894 | 17.5345 | 3.0452 | 3 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 8854 | 0.6 | 6.6667 | 13.1707 | 19.6022 | 3.5224 | 2.9091 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 8855 | 1.2 | 3.3333 | 16.3636 | 21.4526 | 2.9317 | 2.1573 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 8856 | 0.4 | 10 | 13.1707 | 20.2763 | 2.9317 | 4.1739 | 1.2 | 4.1667 | 0.1 | 20 | 34.1667
| 8857 | 0.6 | 6.6667 | 15 | 21.5752 | 3.1467 | 3.4286 | 1 | 5 | 0.6 | 3.3333 | 15
| 8858 | 0.8 | 5 | 14.5946 | 30.1229 | 2.7283 | 12.8 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 8859 | 1 | 4 | 7.7143 | 17.8313 | 3.4963 | 6.6207 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 8860 | 0.4 | 10 | 13.5 | 20.0569 | 3.6031 | 2.9538 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 8861 | 1.2 | 3.3333 | 14.2105 | 20.1844 | 2.8263 | 3.1475 | 0.4 | 12.5 | 0.4 | 5 | 20.8333
| 8862 | 0.8 | 5 | 11.25 | 21.9017 | 2.6517 | 8 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 8863 | 0.4 | 10 | 15.8824 | 21.9634 | 2.7126 | 3.3684 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 8864 | 0.8 | 5 | 11.7391 | 21.4866 | 3.3475 | 6.4 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 8865 | 1 | 4 | 11.7391 | 19.9514 | 2.5652 | 5.6471 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 8866 | 0.6 | 6.6667 | 7.6056 | 14.7696 | 3.3239 | 3.84 | 1 | 5 | 0.6 | 3.3333 | 15
| 8867 | 0.4 | 10 | 8.7097 | 14.9465 | 3.1892 | 3.0476 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 8868 | 0.6 | 6.6667 | 13.5 | 20.8516 | 3.085 | 4.2667 | 1 | 5 | 0.4 | 5 | 16.6667
| 8869 | 0.4 | 10 | 15 | 24.0517 | 2.6517 | 6.4 | 0.4 | 12.5 | 0.4 | 5 | 27.5
| 8870 | 0.8 | 5 | 9.8182 | 19.8645 | 3.1892 | 6.8571 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 8871 | 1.2 | 3.3333 | 10 | 15.7062 | 1.7879 | 3.9184 | 1.2 | 4.1667 | 0.1 | 20 | 27.5
| 8872 | 1.2 | 3.3333 | 15.4286 | 22.8078 | 2.5792 | 4.8 | 1 | 5 | 0.4 | 5 | 13.3333
| 8873 | 0.6 | 6.6667 | 12.5581 | 21.6979 | 3.8065 | 5.3333 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 8874 | 0.4 | 10 | 13.8462 | 20.1506 | 2.6818 | 3.6226 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 8875 | 1 | 4 | 10.1887 | 17.1695 | 2.8957 | 4.0851 | 1 | 5 | 0.8 | 2.5 | 11.5
| 8876 | 1.4 | 2.8571 | 11.25 | 17.6006 | 2.5106 | 3.84 | 0.8 | 6.25 | 0.1 | 20 | 29.1071
| 8877 | 0.1 | 40 | 15 | 24.2109 | 3.2109 | 6 | 0.6 | 8.3333 | 0.4 | 5 | 53.3333
| 8878 | 0.4 | 10 | 12.8571 | 19.1098 | 2.6971 | 3.5556 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 8879 | 0.8 | 5 | 8.3077 | 14.1304 | 2.9136 | 2.9091 | 1 | 5 | 0.4 | 5 | 15
| 8880 | 0.8 | 5 | 9.1525 | 17.3074 | 2.3366 | 5.8182 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 8881 | 0.4 | 10 | 11.7391 | 21.0044 | 2.4082 | 6.8571 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 8882 | 1.2 | 3.3333 | 11.25 | 18.6837 | 2.9686 | 4.4651 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 8883 | 1 | 4 | 10.3846 | 16.0453 | 2.878 | 2.7826 | 1 | 5 | 0.4 | 5 | 14
| 8884 | 0.8 | 5 | 14.5946 | 20.7826 | 2.6971 | 3.4909 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 8885 | 0.6 | 6.6667 | 12 | 21.4064 | 3.0064 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 8886 | 1 | 4 | 10.8 | 21.4335 | 3.5224 | 7.1111 | 1 | 5 | 0.2 | 10 | 19
| 8887 | 0.4 | 10 | 10 | 17.581 | 2.2476 | 5.3333 | 1 | 5 | 0.2 | 10 | 25
| 8888 | 0.6 | 6.6667 | 11.7391 | 18.1975 | 2.4583 | 4 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 8889 | 1 | 4 | 13.5 | 23.0053 | 3.1053 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 8890 | 0.6 | 6.6667 | 14.5946 | 24.1976 | 3.6031 | 6 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 8891 | 1.2 | 3.3333 | 12 | 20.2635 | 3.2109 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 8892 | 1 | 4 | 11.25 | 18.6301 | 2.6971 | 4.6829 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 8893 | 0.6 | 6.6667 | 13.8462 | 20.7102 | 3.7165 | 3.1475 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 8894 | 1 | 4 | 13.5 | 20.2119 | 2.3483 | 4.3636 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 8895 | 1 | 4 | 16.875 | 24.3456 | 3.4706 | 4 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 8896 | 0.1 | 40 | 12.5581 | 20.3228 | 4 | 3.7647 | 1 | 5 | 0.4 | 5 | 50
| 8897 | 0.6 | 6.6667 | 13.1707 | 21.2616 | 3.1678 | 4.9231 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 8898 | 0.8 | 5 | 13.5 | 20.7923 | 3.0256 | 4.2667 | 1.2 | 4.1667 | 0.8 | 2.5 | 11.6667
| 8899 | 0.8 | 5 | 11.4894 | 19.8679 | 3.0452 | 5.3333 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 8900 | 0.8 | 5 | 13.8462 | 18.7985 | 2.6667 | 2.2857 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 8901 | 0.4 | 10 | 9.1525 | 15.0005 | 2.5376 | 3.3103 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 8902 | 0.4 | 10 | 11.7391 | 20.1149 | 3.5758 | 4.8 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 8903 | 0.8 | 5 | 12.2727 | 19.2714 | 2.9136 | 4.0851 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 8904 | 1.2 | 3.3333 | 13.5 | 21.0492 | 2.36 | 5.1892 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 8905 | 1 | 4 | 13.8462 | 21.0264 | 3.0064 | 4.1739 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.8333
| 8906 | 1.2 | 3.3333 | 11.4894 | 18.3347 | 2.7602 | 4.0851 | 1.4 | 3.5714 | 0.1 | 20 | 26.9048
| 8907 | 0.4 | 10 | 10.3846 | 18.3179 | 3.9333 | 4 | 1 | 5 | 0.4 | 5 | 20
| 8908 | 0.6 | 6.6667 | 9.6429 | 19.0232 | 2.2692 | 7.1111 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 8909 | 1.2 | 3.3333 | 10.3846 | 19.211 | 2.8263 | 6 | 1 | 5 | 0.4 | 5 | 13.3333
| 8910 | 1 | 4 | 12.5581 | 18.1016 | 2.3959 | 3.1475 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 8911 | 0.4 | 10 | 12 | 18.8856 | 2.4205 | 4.4651 | 1 | 5 | 0.4 | 5 | 20
| 8912 | 0.6 | 6.6667 | 14.2105 | 19.6685 | 2.9317 | 2.5263 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 8913 | 1 | 4 | 10.8 | 17.2336 | 2.878 | 3.5556 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 8914 | 0.6 | 6.6667 | 13.8462 | 20.8402 | 3.3714 | 3.6226 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 8915 | 1 | 4 | 10 | 15.8357 | 2.2802 | 3.5556 | 1 | 5 | 0.2 | 10 | 19
| 8916 | 0.6 | 6.6667 | 12.5581 | 19.4617 | 2.6369 | 4.2667 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 8917 | 0.6 | 6.6667 | 10.8 | 21.3068 | 3.3957 | 7.1111 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 8918 | 0.2 | 20 | 14.2105 | 23.6918 | 2.8606 | 6.6207 | 1 | 5 | 0.4 | 5 | 30
| 8919 | 0.6 | 6.6667 | 10.8 | 22.7692 | 2.8263 | 9.1429 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 8920 | 0.8 | 5 | 14.2105 | 21.245 | 2.8606 | 4.1739 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 8921 | 1.4 | 2.8571 | 9.8182 | 18.1486 | 3.2778 | 5.0526 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 8922 | 1 | 4 | 8.8525 | 18.7745 | 3.0649 | 6.8571 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 8923 | 0.6 | 6.6667 | 10.8 | 17.3796 | 2.216 | 4.3636 | 0.6 | 8.3333 | 0.1 | 20 | 35
| 8924 | 0.8 | 5 | 10 | 17.5906 | 3.3239 | 4.2667 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 8925 | 1 | 4 | 8.7097 | 15.8595 | 3.6589 | 3.4909 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 8926 | 0.4 | 10 | 12.8571 | 22.806 | 3.5489 | 6.4 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 8927 | 1.4 | 2.8571 | 16.3636 | 24.1459 | 3.2109 | 4.5714 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 8928 | 1 | 4 | 13.8462 | 33.0266 | 4.4112 | 14.7692 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 8929 | 1.4 | 2.8571 | 15 | 21.5911 | 2.8263 | 3.7647 | 1.4 | 3.5714 | 0.1 | 20 | 26.4286
| 8930 | 1.2 | 3.3333 | 10.8 | 19.3662 | 3.2329 | 5.3333 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 8931 | 0.6 | 6.6667 | 11.0204 | 18.331 | 3.4706 | 3.84 | 1 | 5 | 0.2 | 10 | 21.6667
| 8932 | 1.4 | 2.8571 | 10.5882 | 16.709 | 2.5652 | 3.5556 | 1 | 5 | 0.2 | 10 | 17.8571
| 8933 | 0.8 | 5 | 13.5 | 21.5959 | 3.6308 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 8934 | 0.8 | 5 | 13.5 | 20.4872 | 3.4963 | 3.4909 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 8935 | 0.4 | 10 | 19.2857 | 30.008 | 5.0753 | 5.6471 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 8936 | 0.8 | 5 | 10.5882 | 17.6732 | 3.085 | 4 | 1 | 5 | 0.4 | 5 | 15
| 8937 | 1.4 | 2.8571 | 12.5581 | 19.0732 | 3.1467 | 3.3684 | 1 | 5 | 0.2 | 10 | 17.8571
| 8938 | 0.8 | 5 | 18 | 28.6369 | 2.6369 | 8 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 8939 | 0.1 | 40 | 11.4894 | 17.8039 | 2.6222 | 3.6923 | 1.2 | 4.1667 | 0.2 | 10 | 54.1667
| 8940 | 1 | 4 | 14.2105 | 21.7606 | 3.085 | 4.4651 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 8941 | 0.6 | 6.6667 | 10.3846 | 20.3528 | 3.3475 | 6.6207 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 8942 | 0.6 | 6.6667 | 12.5581 | 22.0295 | 3.2778 | 6.1935 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 8943 | 0.6 | 6.6667 | 7.7143 | 13.0936 | 2.7126 | 2.6667 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 8944 | 1.2 | 3.3333 | 10.8 | 17.7632 | 2.878 | 4.0851 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 8945 | 0.8 | 5 | 18 | 23.9401 | 2.8434 | 3.0968 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 8946 | 0.6 | 6.6667 | 9.1525 | 15.8778 | 2.5514 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 8947 | 1.2 | 3.3333 | 11.0204 | 17.3872 | 2.7442 | 3.6226 | 0.4 | 12.5 | 0.8 | 2.5 | 18.3333
| 8948 | 0.4 | 10 | 11.25 | 18.9473 | 3.1258 | 4.5714 | 1 | 5 | 0.1 | 20 | 35
| 8949 | 0.6 | 6.6667 | 15.4286 | 23.1444 | 3.6308 | 4.0851 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 8950 | 1 | 4 | 10.5882 | 17.7169 | 2.2056 | 4.9231 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 8951 | 1.4 | 2.8571 | 16.875 | 26.4888 | 3.4203 | 6.1935 | 0.6 | 8.3333 | 0.4 | 5 | 16.1905
| 8952 | 1 | 4 | 14.5946 | 20.1219 | 2.8606 | 2.6667 | 1 | 5 | 0.4 | 5 | 14
| 8953 | 0.4 | 10 | 14.5946 | 21.1504 | 3.0649 | 3.4909 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 8954 | 0.4 | 10 | 14.5946 | 21.7511 | 2.7929 | 4.3636 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 8955 | 0.4 | 10 | 14.2105 | 23.7572 | 3.1467 | 6.4 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 8956 | 0.6 | 6.6667 | 10.5882 | 22.9959 | 2.3024 | 10.1053 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 8957 | 0.6 | 6.6667 | 11.4894 | 18.4067 | 3.5489 | 3.3684 | 1 | 5 | 0.2 | 10 | 21.6667
| 8958 | 1.2 | 3.3333 | 12.8571 | 19.9694 | 3.3475 | 3.7647 | 2 | 2.5 | 0.2 | 10 | 15.8333
| 8959 | 1 | 4 | 12.2727 | 22.3052 | 4.2143 | 5.8182 | 1 | 5 | 0.2 | 10 | 19
| 8960 | 0.1 | 40 | 13.5 | 19.7304 | 2.6077 | 3.6226 | 0.4 | 12.5 | 0.4 | 5 | 57.5
| 8961 | 0.4 | 10 | 16.3636 | 21.7255 | 2.5792 | 2.7826 | 1.2 | 4.1667 | 0.1 | 20 | 34.1667
| 8962 | 0.8 | 5 | 14.2105 | 21.1062 | 2.8957 | 4 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 8963 | 0.6 | 6.6667 | 13.1707 | 23.5174 | 2.6667 | 7.68 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 8964 | 1 | 4 | 9 | 19.835 | 4.2143 | 6.6207 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 8965 | 0.8 | 5 | 10.1887 | 19.2428 | 2.8606 | 6.1935 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 8966 | 0.8 | 5 | 11.25 | 18.3717 | 3.6308 | 3.4909 | 0.4 | 12.5 | 0.2 | 10 | 27.5
| 8967 | 1 | 4 | 9.3103 | 17.818 | 2.8606 | 5.6471 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 8968 | 0.6 | 6.6667 | 11.0204 | 17.2224 | 3.1053 | 3.0968 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 8969 | 1.2 | 3.3333 | 16.3636 | 23.5276 | 3.3239 | 3.84 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 8970 | 1 | 4 | 15.8824 | 22.9685 | 3.1678 | 3.9184 | 1 | 5 | 0.4 | 5 | 14
| 8971 | 0.6 | 6.6667 | 12.5581 | 28.9889 | 3.6308 | 12.8 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 8972 | 0.8 | 5 | 15.4286 | 25.037 | 2.4974 | 7.1111 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 8973 | 1 | 4 | 10 | 18.9377 | 2.7442 | 6.1935 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 8974 | 1 | 4 | 14.5946 | 20.9667 | 2.0085 | 4.3636 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 8975 | 0.6 | 6.6667 | 16.875 | 24.4868 | 3.1467 | 4.4651 | 1 | 5 | 0.1 | 20 | 31.6667
| 8976 | 1.4 | 2.8571 | 9.4737 | 18.1335 | 3.4706 | 5.1892 | 1.4 | 3.5714 | 0.8 | 2.5 | 8.9286
| 8977 | 1 | 4 | 15.8824 | 23.2073 | 2.1357 | 5.1892 | 1 | 5 | 0.1 | 20 | 29
| 8978 | 0.1 | 40 | 11.4894 | 20.427 | 2.5376 | 6.4 | 1 | 5 | 0.2 | 10 | 55
| 8979 | 0.6 | 6.6667 | 11.25 | 21.7379 | 3.6308 | 6.8571 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 8980 | 0.8 | 5 | 13.8462 | 20.7634 | 3.5489 | 3.3684 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 8981 | 0.6 | 6.6667 | 14.5946 | 23.3132 | 3.2329 | 5.4857 | 1 | 5 | 0.6 | 3.3333 | 15
| 8982 | 0.6 | 6.6667 | 15 | 23.4154 | 4.3303 | 4.0851 | 1.4 | 3.5714 | 0.1 | 20 | 30.2381
| 8983 | 0.6 | 6.6667 | 15.8824 | 21.8588 | 2.7765 | 3.2 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 8984 | 0.6 | 6.6667 | 17.4194 | 26.1379 | 3.2329 | 5.4857 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 8985 | 0.6 | 6.6667 | 12.5581 | 20.716 | 3.1053 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 8986 | 1.2 | 3.3333 | 15 | 21.1881 | 2.6971 | 3.4909 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 8987 | 1.6 | 2.5 | 15.4286 | 22.0781 | 2.8095 | 3.84 | 0.4 | 12.5 | 0.1 | 20 | 35
| 8988 | 1.4 | 2.8571 | 14.5946 | 23.3675 | 3.1258 | 5.6471 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 8989 | 1 | 4 | 11.7391 | 17.7579 | 3.0649 | 2.9538 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 8990 | 0.8 | 5 | 10.5882 | 17.8113 | 2.6517 | 4.5714 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 8991 | 0.6 | 6.6667 | 14.2105 | 19.5791 | 2.9686 | 2.4 | 0.2 | 25 | 0.4 | 5 | 36.6667
| 8992 | 1.4 | 2.8571 | 10.5882 | 17.8027 | 3.6589 | 3.5556 | 0.4 | 12.5 | 0.8 | 2.5 | 17.8571
| 8993 | 1.4 | 2.8571 | 13.1707 | 22.3472 | 2.7765 | 6.4 | 1.6 | 3.125 | 0.6 | 3.3333 | 9.3155
| 8994 | 0.8 | 5 | 11.25 | 21.5663 | 2.9317 | 7.3846 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 8995 | 1 | 4 | 10.5882 | 18.2146 | 2.8263 | 4.8 | 1 | 5 | 0.1 | 20 | 29
| 8996 | 0.6 | 6.6667 | 14.2105 | 21.6923 | 2.6818 | 4.8 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 8997 | 1.2 | 3.3333 | 9.1525 | 14.0329 | 2.0978 | 2.7826 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 8998 | 0.6 | 6.6667 | 12.2727 | 19.1979 | 3.2329 | 3.6923 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 8999 | 1 | 4 | 16.3636 | 28.2036 | 2.6971 | 9.1429 | 1 | 5 | 0.2 | 10 | 19
| 9000 | 0.2 | 20 | 10 | 17.6973 | 3.1258 | 4.5714 | 0.8 | 6.25 | 0.2 | 10 | 36.25
| 9001 | 1.4 | 2.8571 | 11.25 | 19.1059 | 2.6667 | 5.1892 | 1 | 5 | 0.4 | 5 | 12.8571
| 9002 | 0.4 | 10 | 11.0204 | 18.5307 | 3.0452 | 4.4651 | 1.6 | 3.125 | 0.2 | 10 | 23.125
| 9003 | 0.2 | 20 | 11.4894 | 17.9215 | 2.8095 | 3.6226 | 1 | 5 | 0.4 | 5 | 30
| 9004 | 0.8 | 5 | 13.5 | 19.1374 | 2.7283 | 2.9091 | 1 | 5 | 0.4 | 5 | 15
| 9005 | 0.8 | 5 | 10.8 | 16.835 | 2.9873 | 3.0476 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 9006 | 0.8 | 5 | 10.3846 | 18.4621 | 2.7442 | 5.3333 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 9007 | 1 | 4 | 10.8 | 17.8875 | 2.9136 | 4.1739 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 9008 | 0.8 | 5 | 10.5882 | 16.4603 | 3.0064 | 2.8657 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 9009 | 0.6 | 6.6667 | 20 | 27.676 | 3.2109 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 9010 | 1 | 4 | 12 | 19.3714 | 3.3714 | 4 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 9011 | 0.4 | 10 | 15.8824 | 22.5275 | 2.4712 | 4.1739 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 9012 | 1 | 4 | 13.5 | 21.1673 | 2.7442 | 4.9231 | 1 | 5 | 0.4 | 5 | 14
| 9013 | 0.6 | 6.6667 | 10.3846 | 19.8934 | 2.6517 | 6.8571 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 9014 | 0.8 | 5 | 12.8571 | 20.8598 | 2.95 | 5.0526 | 1 | 5 | 0.2 | 10 | 20
| 9015 | 0.8 | 5 | 10.5882 | 18.3652 | 3.6031 | 4.1739 | 1 | 5 | 0.4 | 5 | 15
| 9016 | 0.8 | 5 | 10.8 | 18.9357 | 2.1357 | 6 | 1 | 5 | 0.8 | 2.5 | 12.5
| 9017 | 0.2 | 20 | 8.0597 | 14.538 | 2.9873 | 3.4909 | 1.2 | 4.1667 | 0.1 | 20 | 44.1667
| 9018 | 0.2 | 20 | 12.8571 | 20.2208 | 3.4453 | 3.9184 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 9019 | 1 | 4 | 12.2727 | 18.9791 | 3.2778 | 3.4286 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 9020 | 1.4 | 2.8571 | 18.6207 | 25.9313 | 2.5106 | 4.8 | 1.2 | 4.1667 | 0.8 | 2.5 | 9.5238
| 9021 | 0.2 | 20 | 12.2727 | 20.3663 | 2.7602 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 9022 | 0.6 | 6.6667 | 18.6207 | 25.892 | 2.3483 | 4.9231 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 9023 | 0.8 | 5 | 9.8182 | 16.6004 | 2.6971 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 9024 | 0.4 | 10 | 10.8 | 16.7947 | 2.3024 | 3.6923 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 9025 | 1.2 | 3.3333 | 11.4894 | 18.9638 | 2.5514 | 4.9231 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 9026 | 0.8 | 5 | 13.5 | 19.0049 | 2.4082 | 3.0968 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 9027 | 1.2 | 3.3333 | 10.1887 | 16.809 | 3.4203 | 3.2 | 1 | 5 | 0.1 | 20 | 28.3333
| 9028 | 1.2 | 3.3333 | 11.0204 | 23.5851 | 3.8374 | 8.7273 | 1 | 5 | 0.4 | 5 | 13.3333
| 9029 | 0.2 | 20 | 11.0204 | 20.0069 | 2.7929 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 9030 | 0.8 | 5 | 12.5581 | 20.4962 | 3.2552 | 4.6829 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 9031 | 1 | 4 | 11.4894 | 17.5599 | 2.7602 | 3.3103 | 1.8 | 2.7778 | 0.2 | 10 | 16.7778
| 9032 | 1 | 4 | 11.25 | 24.2617 | 3.8689 | 9.1429 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 9033 | 1 | 4 | 9.8182 | 20.1059 | 2.6077 | 7.68 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 9034 | 0.8 | 5 | 8.7097 | 21.9408 | 3.1258 | 10.1053 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9035 | 1.4 | 2.8571 | 12.2727 | 20.8805 | 2.6077 | 6 | 0.6 | 8.3333 | 0.6 | 3.3333 | 14.5238
| 9036 | 0.6 | 6.6667 | 11.0204 | 18.7376 | 2.3838 | 5.3333 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 9037 | 1 | 4 | 17.4194 | 24.7036 | 2.4842 | 4.8 | 1.6 | 3.125 | 0.6 | 3.3333 | 10.4583
| 9038 | 1.2 | 3.3333 | 13.8462 | 23.4769 | 3.6308 | 6 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 9039 | 0.8 | 5 | 14.5946 | 21.8605 | 3.3475 | 3.9184 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 9040 | 0.8 | 5 | 13.8462 | 20.8888 | 2.4712 | 4.5714 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 9041 | 1 | 4 | 12.8571 | 20.5453 | 3.6031 | 4.0851 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 9042 | 0.8 | 5 | 14.2105 | 22.5183 | 3.2552 | 5.0526 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 9043 | 1.2 | 3.3333 | 12 | 18.9333 | 2.6667 | 4.2667 | 1 | 5 | 0.2 | 10 | 18.3333
| 9044 | 1.2 | 3.3333 | 11.0204 | 16.5467 | 2.216 | 3.3103 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 9045 | 0.2 | 20 | 15 | 21.3253 | 3.3714 | 2.9538 | 0.6 | 8.3333 | 0.4 | 5 | 33.3333
| 9046 | 0.4 | 10 | 11.7391 | 19.0443 | 2.6222 | 4.6829 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 9047 | 1 | 4 | 12.8571 | 18.3413 | 2.3366 | 3.1475 | 1 | 5 | 0.4 | 5 | 14
| 9048 | 0.6 | 6.6667 | 16.3636 | 23.9994 | 2.7126 | 4.9231 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 9049 | 1.2 | 3.3333 | 16.875 | 23.2976 | 2.9317 | 3.4909 | 0.8 | 6.25 | 0.8 | 2.5 | 12.0833
| 9050 | 0.8 | 5 | 14.2105 | 20.8434 | 2.2692 | 4.3636 | 1 | 5 | 0.4 | 5 | 15
| 9051 | 0.2 | 20 | 10.8 | 17.893 | 2.8263 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 9052 | 0.8 | 5 | 12 | 18.9774 | 3.5489 | 3.4286 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 9053 | 1 | 4 | 13.8462 | 19.9099 | 2.8095 | 3.2542 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 9054 | 1 | 4 | 11.7391 | 20.9997 | 2.8606 | 6.4 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 9055 | 1.2 | 3.3333 | 11.0204 | 18.2807 | 3.4203 | 3.84 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 9056 | 1.2 | 3.3333 | 24.5455 | 32.7977 | 4.2523 | 4 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 9057 | 0.8 | 5 | 12.8571 | 19.3166 | 2.9686 | 3.4909 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9058 | 0.6 | 6.6667 | 12 | 21.4203 | 3.4203 | 6 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 9059 | 1 | 4 | 14.2105 | 20.7947 | 2.7442 | 3.84 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 9060 | 0.4 | 10 | 17.4194 | 24.5871 | 3.1678 | 4 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 9061 | 1 | 4 | 12.8571 | 19.3131 | 2.5376 | 3.9184 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 9062 | 0.4 | 10 | 12.8571 | 19.3097 | 2.7602 | 3.6923 | 0.6 | 8.3333 | 0.8 | 2.5 | 20.8333
| 9063 | 0.6 | 6.6667 | 13.5 | 22.4215 | 3.8689 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 9064 | 0.4 | 10 | 10 | 18.0489 | 3.1258 | 4.9231 | 1 | 5 | 0.8 | 2.5 | 17.5
| 9065 | 0.8 | 5 | 11.7391 | 21.0279 | 3.4706 | 5.8182 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 9066 | 1 | 4 | 13.1707 | 20.697 | 2.8434 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 9067 | 0.2 | 20 | 12.5581 | 20.1082 | 3.085 | 4.4651 | 0.4 | 12.5 | 0.6 | 3.3333 | 35.8333
| 9068 | 0.8 | 5 | 11.0204 | 22.1207 | 3.4203 | 7.68 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 9069 | 1 | 4 | 13.8462 | 18.9459 | 2.0522 | 3.0476 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 9070 | 1.2 | 3.3333 | 17.4194 | 26.7115 | 3.8065 | 5.4857 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 9071 | 1 | 4 | 9.1525 | 18.0116 | 3.8065 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 9072 | 1 | 4 | 15.8824 | 23.7011 | 2.8957 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 9073 | 1 | 4 | 8.7097 | 15.4699 | 2.7602 | 4 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 9074 | 0.6 | 6.6667 | 12.5581 | 24.0141 | 3.776 | 7.68 | 1.8 | 2.7778 | 0.4 | 5 | 14.4444
| 9075 | 1 | 4 | 8.0597 | 13.8674 | 2.6077 | 3.2 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 9076 | 0.2 | 20 | 10.3846 | 17.9215 | 2.4842 | 5.0526 | 0.6 | 8.3333 | 0.2 | 10 | 38.3333
| 9077 | 1.6 | 2.5 | 12 | 18.0307 | 2.7765 | 3.2542 | 1 | 5 | 0.8 | 2.5 | 10
| 9078 | 1.2 | 3.3333 | 10 | 16.6081 | 2.8434 | 3.7647 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 9079 | 0.4 | 10 | 12.8571 | 21.2792 | 3.2329 | 5.1892 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 9080 | 0.6 | 6.6667 | 13.1707 | 18.4033 | 3.0256 | 2.2069 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 9081 | 0.8 | 5 | 8.8525 | 16.0672 | 3.5224 | 3.6923 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9082 | 0.8 | 5 | 16.3636 | 23.5043 | 3.3007 | 3.84 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 9083 | 0.6 | 6.6667 | 10.3846 | 17.352 | 2.3959 | 4.5714 | 1.4 | 3.5714 | 0.8 | 2.5 | 12.7381
| 9084 | 0.6 | 6.6667 | 16.3636 | 23.297 | 2.6667 | 4.2667 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 9085 | 0.8 | 5 | 10.5882 | 20.1349 | 3.1467 | 6.4 | 1 | 5 | 0.4 | 5 | 15
| 9086 | 0.8 | 5 | 8.1818 | 19.3729 | 3.8065 | 7.3846 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 9087 | 0.6 | 6.6667 | 19.2857 | 25.2999 | 3.3475 | 2.6667 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 9088 | 0.6 | 6.6667 | 12.5581 | 19.5744 | 3.3239 | 3.6923 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 9089 | 1.2 | 3.3333 | 15.8824 | 22.2652 | 2.7602 | 3.6226 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 9090 | 0.4 | 10 | 14.5946 | 22.9305 | 3.1467 | 5.1892 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 9091 | 0.8 | 5 | 13.1707 | 21.2196 | 3.1258 | 4.9231 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 9092 | 0.6 | 6.6667 | 16.3636 | 23.2669 | 3.8065 | 3.0968 | 1 | 5 | 0.6 | 3.3333 | 15
| 9093 | 0.8 | 5 | 10 | 18.247 | 3.3239 | 4.9231 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 9094 | 0.4 | 10 | 12.2727 | 19.8423 | 3.3957 | 4.1739 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 9095 | 1 | 4 | 14.2105 | 23.439 | 2.6077 | 6.6207 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 9096 | 0.8 | 5 | 12 | 20.0552 | 3.2552 | 4.8 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 9097 | 0.8 | 5 | 10 | 20.5234 | 2.8434 | 7.68 | 1 | 5 | 0.2 | 10 | 20
| 9098 | 0.4 | 10 | 12.8571 | 18.3524 | 2.7126 | 2.7826 | 0.4 | 12.5 | 0.4 | 5 | 27.5
| 9099 | 1 | 4 | 13.1707 | 20.1246 | 4 | 2.9538 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 9100 | 0.4 | 10 | 12.5581 | 19.0942 | 3.0452 | 3.4909 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 9101 | 1 | 4 | 9.6429 | 19.0114 | 2.9686 | 6.4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 9102 | 0.8 | 5 | 12.2727 | 20.0695 | 2.7442 | 5.0526 | 1 | 5 | 0.2 | 10 | 20
| 9103 | 0.4 | 10 | 10.1887 | 15.8634 | 2.4205 | 3.2542 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 9104 | 0.8 | 5 | 10.1887 | 22.8143 | 3.0256 | 9.6 | 1 | 5 | 0.4 | 5 | 15
| 9105 | 0.4 | 10 | 13.1707 | 21.2483 | 2.7442 | 5.3333 | 1 | 5 | 0.2 | 10 | 25
| 9106 | 1 | 4 | 14.5946 | 22.5475 | 4.3303 | 3.6226 | 1.8 | 2.7778 | 0.2 | 10 | 16.7778
| 9107 | 1.4 | 2.8571 | 14.2105 | 21.1353 | 3.0064 | 3.9184 | 2 | 2.5 | 0.1 | 20 | 25.3571
| 9108 | 1.2 | 3.3333 | 10.5882 | 18.8504 | 2.7765 | 5.4857 | 1 | 5 | 0.4 | 5 | 13.3333
| 9109 | 1.2 | 3.3333 | 11.7391 | 18.5781 | 3.1467 | 3.6923 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 9110 | 0.2 | 20 | 11.7391 | 20.7211 | 3.4963 | 5.4857 | 1.4 | 3.5714 | 0.1 | 20 | 43.5714
| 9111 | 0.2 | 20 | 15.8824 | 24.9089 | 3.8374 | 5.1892 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 9112 | 0.4 | 10 | 16.875 | 25.4721 | 2.95 | 5.6471 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 9113 | 0.4 | 10 | 12.8571 | 19.2317 | 3.2778 | 3.0968 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 9114 | 0.2 | 20 | 13.5 | 21.3367 | 2.9136 | 4.9231 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 9115 | 0.6 | 6.6667 | 15 | 22.7891 | 3.3239 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 9116 | 0.4 | 10 | 12.2727 | 19.5057 | 2.433 | 4.8 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 9117 | 1 | 4 | 15 | 22.1107 | 3.0256 | 4.0851 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 9118 | 0.4 | 10 | 16.3636 | 24.0917 | 3.0452 | 4.6829 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 9119 | 0.6 | 6.6667 | 12.5581 | 19.9013 | 2.878 | 4.4651 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 9120 | 0.8 | 5 | 13.5 | 23.2806 | 2.3959 | 7.3846 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9121 | 0.8 | 5 | 14.5946 | 22.4054 | 2.3251 | 5.4857 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 9122 | 1.2 | 3.3333 | 13.8462 | 25.075 | 3.5489 | 7.68 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 9123 | 1.4 | 2.8571 | 12 | 20.7922 | 3.6031 | 5.1892 | 0.8 | 6.25 | 0.1 | 20 | 29.1071
| 9124 | 0.6 | 6.6667 | 8.5714 | 20.4084 | 2.237 | 9.6 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 9125 | 1.8 | 2.2222 | 25.7143 | 32.4816 | 2.5934 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 13.4722
| 9126 | 0.1 | 40 | 12.2727 | 20.0008 | 3.0452 | 4.6829 | 0.4 | 12.5 | 0.4 | 5 | 57.5
| 9127 | 1 | 4 | 16.3636 | 22.9747 | 3.3007 | 3.3103 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 9128 | 1.2 | 3.3333 | 8.5714 | 16.3841 | 3.3475 | 4.4651 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 9129 | 0.6 | 6.6667 | 13.5 | 20.5452 | 3.0452 | 4 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 9130 | 0.8 | 5 | 8.8525 | 14.5006 | 2.5514 | 3.0968 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9131 | 0.2 | 20 | 9.1525 | 16.7312 | 2.8957 | 4.6829 | 0.6 | 8.3333 | 0.4 | 5 | 33.3333
| 9132 | 0.6 | 6.6667 | 18 | 24.4109 | 2.237 | 4.1739 | 1 | 5 | 0.1 | 20 | 31.6667
| 9133 | 0.2 | 20 | 19.2857 | 27.7857 | 2.6818 | 5.8182 | 1 | 5 | 0.1 | 20 | 45
| 9134 | 1 | 4 | 10.1887 | 16.0334 | 2.6971 | 3.1475 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 9135 | 1.2 | 3.3333 | 12.5581 | 24.4321 | 3.1467 | 8.7273 | 1 | 5 | 0.2 | 10 | 18.3333
| 9136 | 0.8 | 5 | 14.5946 | 23.0538 | 3.1258 | 5.3333 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 9137 | 1.2 | 3.3333 | 14.5946 | 20.1429 | 2.3483 | 3.2 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 9138 | 1.2 | 3.3333 | 13.5 | 21.9731 | 2.9873 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 9139 | 0.6 | 6.6667 | 16.875 | 26.9873 | 3.2552 | 6.8571 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 9140 | 1 | 4 | 7.2973 | 14.5302 | 3.2329 | 4 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 9141 | 0.6 | 6.6667 | 12.5581 | 21.3146 | 2.1357 | 6.6207 | 1 | 5 | 0.4 | 5 | 16.6667
| 9142 | 1 | 4 | 15 | 25.068 | 3.2109 | 6.8571 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 9143 | 1 | 4 | 8.5714 | 15.3475 | 3.3475 | 3.4286 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 9144 | 0.8 | 5 | 10 | 18.0283 | 3.1053 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9145 | 0.2 | 20 | 10.8 | 17.2778 | 3.2778 | 3.2 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 9146 | 0.6 | 6.6667 | 10.3846 | 20.3559 | 2.2913 | 7.68 | 1 | 5 | 0.2 | 10 | 21.6667
| 9147 | 0.8 | 5 | 8.8525 | 20.3893 | 2.8095 | 8.7273 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 9148 | 1.4 | 2.8571 | 10 | 17.2974 | 2.4974 | 4.8 | 0.6 | 8.3333 | 0.4 | 5 | 16.1905
| 9149 | 1 | 4 | 10.8 | 18.7307 | 2.878 | 5.0526 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 9150 | 1 | 4 | 12.2727 | 18.7988 | 2.6077 | 3.9184 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 9151 | 1 | 4 | 14.5946 | 20.3871 | 3.1258 | 2.6667 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 9152 | 1 | 4 | 10.8 | 17.7504 | 2.7765 | 4.1739 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 9153 | 1.2 | 3.3333 | 15.4286 | 23.7683 | 3.0064 | 5.3333 | 1 | 5 | 0.2 | 10 | 18.3333
| 9154 | 1 | 4 | 10 | 16.4871 | 3.2329 | 3.2542 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 9155 | 0.8 | 5 | 12 | 18.3895 | 2.6971 | 3.6923 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 9156 | 0.6 | 6.6667 | 13.8462 | 21.6969 | 3.1678 | 4.6829 | 1 | 5 | 0.2 | 10 | 21.6667
| 9157 | 0.2 | 20 | 12.5581 | 18.2892 | 3.3007 | 2.4304 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 9158 | 1 | 4 | 9.8182 | 17.7045 | 2.6971 | 5.1892 | 0.4 | 12.5 | 0.6 | 3.3333 | 19.8333
| 9159 | 1.2 | 3.3333 | 12.2727 | 19.5833 | 3.4706 | 3.84 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 9160 | 0.6 | 6.6667 | 16.875 | 23.1465 | 2.5792 | 3.6923 | 1 | 5 | 0.1 | 20 | 31.6667
| 9161 | 0.6 | 6.6667 | 11.7391 | 21.1648 | 3.0256 | 6.4 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 9162 | 0.8 | 5 | 8.5714 | 14.8045 | 3.3239 | 2.9091 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9163 | 1 | 4 | 14.5946 | 21.2127 | 3.4706 | 3.1475 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 9164 | 1 | 4 | 13.8462 | 21.3861 | 2.9686 | 4.5714 | 1 | 5 | 0.8 | 2.5 | 11.5
| 9165 | 1 | 4 | 18.6207 | 25.5521 | 2.36 | 4.5714 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 9166 | 0.2 | 20 | 13.8462 | 23.7281 | 2.4974 | 7.3846 | 0.8 | 6.25 | 0.2 | 10 | 36.25
| 9167 | 0.8 | 5 | 11.25 | 19.7808 | 2.7126 | 5.8182 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9168 | 0.8 | 5 | 11.4894 | 21.1445 | 3.2552 | 6.4 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 9169 | 1 | 4 | 11.4894 | 17.6966 | 2.6517 | 3.5556 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 9170 | 1.2 | 3.3333 | 13.5 | 19.2442 | 2.7442 | 3 | 1.8 | 2.7778 | 0.6 | 3.3333 | 9.4444
| 9171 | 0.8 | 5 | 11.25 | 20.0219 | 2.3719 | 6.4 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9172 | 0.4 | 10 | 18 | 23.9078 | 2.7602 | 3.1475 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 9173 | 1.2 | 3.3333 | 11.0204 | 17.989 | 2.9686 | 4 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 9174 | 0.4 | 10 | 13.8462 | 20.7919 | 2.8606 | 4.0851 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 9175 | 0.4 | 10 | 10.3846 | 16.3862 | 2.5106 | 3.4909 | 0.8 | 6.25 | 0.8 | 2.5 | 18.75
| 9176 | 0.6 | 6.6667 | 15.8824 | 22.2082 | 3.1258 | 3.2 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 9177 | 1.2 | 3.3333 | 12.8571 | 20.4338 | 2.5241 | 5.0526 | 1.2 | 4.1667 | 0.1 | 20 | 27.5
| 9178 | 0.8 | 5 | 12 | 19.7133 | 2.5241 | 5.1892 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9179 | 1.2 | 3.3333 | 16.3636 | 23.7981 | 3.1678 | 4.2667 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 9180 | 0.4 | 10 | 15.8824 | 23.4038 | 2.95 | 4.5714 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 9181 | 1 | 4 | 11.7391 | 21.7801 | 3.4203 | 6.6207 | 1 | 5 | 1 | 2 | 11
| 9182 | 0.2 | 20 | 11.0204 | 18.1119 | 3.0064 | 4.0851 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 9183 | 0.4 | 10 | 13.8462 | 22.3366 | 2.8434 | 5.6471 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 9184 | 0.8 | 5 | 12.5581 | 20.4316 | 2.2264 | 5.6471 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 9185 | 1.4 | 2.8571 | 15 | 21.0123 | 3.1467 | 2.8657 | 0.6 | 8.3333 | 0.4 | 5 | 16.1905
| 9186 | 0.6 | 6.6667 | 15 | 22.9437 | 4.4528 | 3.4909 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 9187 | 0.4 | 10 | 12.8571 | 18.983 | 3.1258 | 3 | 0.6 | 8.3333 | 0.1 | 20 | 38.3333
| 9188 | 0.6 | 6.6667 | 11.4894 | 18.8541 | 2.6818 | 4.6829 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 9189 | 1 | 4 | 10.3846 | 16.428 | 2.8434 | 3.2 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 9190 | 1.2 | 3.3333 | 13.5 | 22.1015 | 3.5489 | 5.0526 | 1 | 5 | 0.2 | 10 | 18.3333
| 9191 | 0.4 | 10 | 12.8571 | 21.0418 | 2.5376 | 5.6471 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 9192 | 0.2 | 20 | 14.5946 | 24.2953 | 3.3007 | 6.4 | 1.2 | 4.1667 | 0.4 | 5 | 29.1667
| 9193 | 1.2 | 3.3333 | 10.1887 | 17.3779 | 3.1892 | 4 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 9194 | 0.2 | 20 | 15.4286 | 24.2381 | 2.8095 | 6 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 9195 | 0.6 | 6.6667 | 20 | 29.5258 | 3.1258 | 6.4 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 9196 | 0.8 | 5 | 10.3846 | 17.0864 | 3.2109 | 3.4909 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9197 | 0.6 | 6.6667 | 9.3103 | 18.3614 | 3.2329 | 5.8182 | 1 | 5 | 0.6 | 3.3333 | 15
| 9198 | 0.8 | 5 | 10.8 | 17.8444 | 2.5792 | 4.4651 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 9199 | 1 | 4 | 12.5581 | 20.716 | 3.1053 | 5.0526 | 1.4 | 3.5714 | 0.8 | 2.5 | 10.0714
| 9200 | 0.8 | 5 | 9 | 16.844 | 2.5106 | 5.3333 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 9201 | 0.8 | 5 | 10.8 | 19.5483 | 2.3483 | 6.4 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 9202 | 0.8 | 5 | 11.25 | 18.5453 | 2.9317 | 4.3636 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 9203 | 0.2 | 20 | 13.8462 | 22.5782 | 3.085 | 5.6471 | 1.2 | 4.1667 | 0.1 | 20 | 44.1667
| 9204 | 0.8 | 5 | 12.5581 | 20.7026 | 2.4974 | 5.6471 | 1 | 5 | 0.2 | 10 | 20
| 9205 | 0.4 | 10 | 15.4286 | 22.2542 | 2.6517 | 4.1739 | 1 | 5 | 0.2 | 10 | 25
| 9206 | 0.8 | 5 | 12.8571 | 20.1442 | 3.5224 | 3.7647 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 9207 | 0.8 | 5 | 11.7391 | 22.4952 | 3.3714 | 7.3846 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 9208 | 1 | 4 | 13.8462 | 19.4524 | 2.6971 | 2.9091 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 9209 | 0.6 | 6.6667 | 14.5946 | 22.1849 | 2.5376 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 9210 | 0.8 | 5 | 11.7391 | 19.0232 | 2.7126 | 4.5714 | 1 | 5 | 0.2 | 10 | 20
| 9211 | 1 | 4 | 10 | 16.2977 | 2.9873 | 3.3103 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 9212 | 0.8 | 5 | 11.7391 | 19.4371 | 3.2329 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9213 | 1 | 4 | 16.875 | 25.1974 | 3.5224 | 4.8 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 9214 | 1 | 4 | 13.1707 | 19.6386 | 3.4203 | 3.0476 | 0.6 | 8.3333 | 0.1 | 20 | 32.3333
| 9215 | 0.8 | 5 | 9 | 16.1678 | 3.1678 | 4 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 9216 | 0.4 | 10 | 22.5 | 31.8402 | 3.1467 | 6.1935 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 9217 | 0.8 | 5 | 15 | 21.0186 | 2.3959 | 3.6226 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9218 | 0.8 | 5 | 13.1707 | 19.6624 | 2.6517 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 9219 | 1.2 | 3.3333 | 13.5 | 21.6684 | 4.9684 | 3.2 | 1.4 | 3.5714 | 0.4 | 5 | 11.9048
| 9220 | 1 | 4 | 15.8824 | 22.4826 | 2.7602 | 3.84 | 0.2 | 25 | 0.2 | 10 | 39
| 9221 | 0.8 | 5 | 13.5 | 23.8532 | 2.9686 | 7.3846 | 1 | 5 | 0.2 | 10 | 20
| 9222 | 0.1 | 40 | 16.3636 | 23.7526 | 3.4706 | 3.9184 | 1.2 | 4.1667 | 0.2 | 10 | 54.1667
| 9223 | 1 | 4 | 10.1887 | 17.015 | 2.8263 | 4 | 1 | 5 | 0.4 | 5 | 14
| 9224 | 0.6 | 6.6667 | 13.5 | 21.146 | 2.5934 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 9225 | 0.2 | 20 | 13.1707 | 21.7823 | 3.1258 | 5.4857 | 0.8 | 6.25 | 0.1 | 20 | 46.25
| 9226 | 0.8 | 5 | 13.5 | 24.1523 | 4.2523 | 6.4 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 9227 | 1 | 4 | 14.2105 | 22.5675 | 3.1678 | 5.1892 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 9228 | 0.8 | 5 | 11.7391 | 18.5964 | 3.6031 | 3.2542 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 9229 | 0.8 | 5 | 15 | 21.5957 | 2.5106 | 4.0851 | 1 | 5 | 0.1 | 20 | 30
| 9230 | 0.8 | 5 | 13.8462 | 20.4784 | 2.4583 | 4.1739 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 9231 | 0.8 | 5 | 13.5 | 20.1608 | 3.1053 | 3.5556 | 1 | 5 | 0.4 | 5 | 15
| 9232 | 0.2 | 20 | 15.4286 | 21.9281 | 3.1892 | 3.3103 | 1.4 | 3.5714 | 0.4 | 5 | 28.5714
| 9233 | 0.4 | 10 | 11.7391 | 18.2927 | 2.0885 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 9234 | 1 | 4 | 10 | 17.258 | 2.7929 | 4.4651 | 1.4 | 3.5714 | 0.1 | 20 | 27.5714
| 9235 | 0.8 | 5 | 11.0204 | 20.3398 | 3.1258 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9236 | 0.4 | 10 | 12.5581 | 18.6033 | 3.0452 | 3 | 1 | 5 | 0.8 | 2.5 | 17.5
| 9237 | 0.8 | 5 | 13.5 | 20.0704 | 2.878 | 3.6923 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 9238 | 0.8 | 5 | 15 | 21.5964 | 3.1678 | 3.4286 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 9239 | 0.6 | 6.6667 | 11.4894 | 19.0641 | 2.6517 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 15
| 9240 | 1 | 4 | 10.5882 | 17.7597 | 3.5489 | 3.6226 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 9241 | 0.6 | 6.6667 | 19.2857 | 25.5641 | 2.36 | 3.9184 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 9242 | 1.4 | 2.8571 | 18.6207 | 28.1366 | 3.8689 | 5.6471 | 1 | 5 | 0.2 | 10 | 17.8571
| 9243 | 0.6 | 6.6667 | 18.6207 | 28.8371 | 3.1053 | 7.1111 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 9244 | 1.2 | 3.3333 | 10.5882 | 16.3647 | 2.7765 | 3 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 9245 | 0.8 | 5 | 10.1887 | 16.8438 | 3.746 | 2.9091 | 1 | 5 | 0.2 | 10 | 20
| 9246 | 0.6 | 6.6667 | 9 | 13.9143 | 2.2476 | 2.6667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 9247 | 0.8 | 5 | 13.5 | 23.2885 | 3.1678 | 6.6207 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 9248 | 0.6 | 6.6667 | 11.7391 | 18.4912 | 2.9873 | 3.7647 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 9249 | 0.4 | 10 | 12.8571 | 20.5916 | 2.6818 | 5.0526 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 9250 | 1.2 | 3.3333 | 7.8261 | 20.1564 | 3.6031 | 8.7273 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 9251 | 0.6 | 6.6667 | 12.8571 | 22.2242 | 3.5489 | 5.8182 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 9252 | 1.4 | 2.8571 | 12.8571 | 20.0019 | 2.878 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 9253 | 0.8 | 5 | 11.4894 | 19.599 | 3.746 | 4.3636 | 1 | 5 | 0.2 | 10 | 20
| 9254 | 0.2 | 20 | 9.3103 | 16.743 | 3.3475 | 4.0851 | 0.8 | 6.25 | 0.2 | 10 | 36.25
| 9255 | 0.8 | 5 | 13.1707 | 19.3986 | 3.4453 | 2.7826 | 1 | 5 | 0.4 | 5 | 15
| 9256 | 0.4 | 10 | 15.8824 | 26.4136 | 3.1467 | 7.3846 | 1 | 5 | 0.4 | 5 | 20
| 9257 | 0.2 | 20 | 10.3846 | 19.0068 | 2.6222 | 6 | 1.4 | 3.5714 | 0.1 | 20 | 43.5714
| 9258 | 0.6 | 6.6667 | 13.8462 | 23.4159 | 2.7126 | 6.8571 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 9259 | 0.2 | 20 | 14.2105 | 22.9797 | 3.7165 | 5.0526 | 1.2 | 4.1667 | 0.6 | 3.3333 | 27.5
| 9260 | 1 | 4 | 11.4894 | 18.6031 | 2.3137 | 4.8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 9261 | 0.6 | 6.6667 | 8.5714 | 20.4454 | 3.1467 | 8.7273 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 9262 | 1.2 | 3.3333 | 12.5581 | 17.9609 | 2.5792 | 2.8235 | 1 | 5 | 0.1 | 20 | 28.3333
| 9263 | 1 | 4 | 9.6429 | 17.9073 | 3.9008 | 4.3636 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 9264 | 0.2 | 20 | 15.8824 | 25.6497 | 3.1467 | 6.6207 | 0.4 | 12.5 | 0.4 | 5 | 37.5
| 9265 | 0.6 | 6.6667 | 12.5581 | 19.7123 | 2.4712 | 4.6829 | 1 | 5 | 0.6 | 3.3333 | 15
| 9266 | 1 | 4 | 11.7391 | 18.0368 | 2.9873 | 3.3103 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 9267 | 0.6 | 6.6667 | 10 | 20.0973 | 2.7126 | 7.3846 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 9268 | 0.6 | 6.6667 | 10.1887 | 16.707 | 2.8957 | 3.6226 | 1 | 5 | 0.6 | 3.3333 | 15
| 9269 | 0.8 | 5 | 9.3103 | 16.8091 | 3.8065 | 3.6923 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9270 | 0.8 | 5 | 14.5946 | 22.8785 | 2.6369 | 5.6471 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9271 | 1 | 4 | 15.4286 | 23.1938 | 2.7126 | 5.0526 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 9272 | 1.2 | 3.3333 | 15.4286 | 21.5486 | 2.4974 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 9273 | 0.8 | 5 | 10 | 17.573 | 2.3838 | 5.1892 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 9274 | 0.6 | 6.6667 | 9.6429 | 16.7804 | 3.4453 | 3.6923 | 1.8 | 2.7778 | 0.4 | 5 | 14.4444
| 9275 | 1 | 4 | 18 | 25.8455 | 2.7929 | 5.0526 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 9276 | 0.4 | 10 | 9.4737 | 15.9003 | 3.6031 | 2.8235 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 9277 | 0.8 | 5 | 10.5882 | 19.5946 | 3.0064 | 6 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 9278 | 1 | 4 | 9.8182 | 18.7695 | 2.5514 | 6.4 | 0.6 | 8.3333 | 0.1 | 20 | 32.3333
| 9279 | 0.8 | 5 | 16.875 | 24.5356 | 2.8606 | 4.8 | 1 | 5 | 0.2 | 10 | 20
| 9280 | 1 | 4 | 12 | 19.092 | 2.7283 | 4.3636 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 9281 | 0.8 | 5 | 14.2105 | 22.9221 | 3.5224 | 5.1892 | 1 | 5 | 0.4 | 5 | 15
| 9282 | 0.4 | 10 | 13.5 | 22.2692 | 3.7165 | 5.0526 | 1 | 5 | 0.2 | 10 | 25
| 9283 | 0.4 | 10 | 12 | 21.7424 | 3.5489 | 6.1935 | 1 | 5 | 0.8 | 2.5 | 17.5
| 9284 | 1.4 | 2.8571 | 12.2727 | 19.6442 | 3.3714 | 4 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 9285 | 0.6 | 6.6667 | 18.6207 | 25.8595 | 3.0649 | 4.1739 | 1.6 | 3.125 | 0.2 | 10 | 19.7917
| 9286 | 1 | 4 | 9 | 16.2109 | 3.2109 | 4 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 9287 | 0.6 | 6.6667 | 10.3846 | 18.4781 | 2.6077 | 5.4857 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 9288 | 0.6 | 6.6667 | 20 | 26.2942 | 3.1467 | 3.1475 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 9289 | 0.6 | 6.6667 | 12.2727 | 23.2283 | 2.6077 | 8.3478 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 9290 | 0.8 | 5 | 12.5581 | 21.0025 | 3.2552 | 5.1892 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 9291 | 1.2 | 3.3333 | 16.875 | 25.3975 | 3.1892 | 5.3333 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 9292 | 1 | 4 | 10.8 | 16.6491 | 2.4205 | 3.4286 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 9293 | 0.6 | 6.6667 | 10.1887 | 17.3338 | 3.7165 | 3.4286 | 0.8 | 6.25 | 1 | 2 | 14.9167
| 9294 | 0.8 | 5 | 15.4286 | 22.2467 | 3.1258 | 3.6923 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 9295 | 0.4 | 10 | 10.8 | 19.3624 | 2.7442 | 5.8182 | 1.4 | 3.5714 | 0.1 | 20 | 33.5714
| 9296 | 1 | 4 | 10 | 17.5748 | 2.6517 | 4.9231 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 9297 | 0.4 | 10 | 12.2727 | 19.3377 | 3.0649 | 4 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 9298 | 0.4 | 10 | 11.4894 | 17.787 | 2.9873 | 3.3103 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 9299 | 0.8 | 5 | 11.0204 | 17.4395 | 3.3714 | 3.0476 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9300 | 0.6 | 6.6667 | 11.0204 | 17.6819 | 3.2329 | 3.4286 | 1 | 5 | 0.6 | 3.3333 | 15
| 9301 | 0.8 | 5 | 10.8 | 17.6134 | 2.3483 | 4.4651 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 9302 | 1.4 | 2.8571 | 11.0204 | 17.7373 | 2.1455 | 4.5714 | 0.6 | 8.3333 | 0.8 | 2.5 | 13.6905
| 9303 | 0.6 | 6.6667 | 11.7391 | 17.8423 | 3.0064 | 3.0968 | 0.6 | 8.3333 | 0.8 | 2.5 | 17.5
| 9304 | 0.2 | 20 | 13.5 | 18.866 | 2.2692 | 3.0968 | 1 | 5 | 0.2 | 10 | 35
| 9305 | 0.1 | 40 | 9.6429 | 22.3346 | 3.5489 | 9.1429 | 0.2 | 25 | 0.4 | 5 | 70
| 9306 | 0.6 | 6.6667 | 12.2727 | 21.1818 | 3.5758 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 9307 | 0.8 | 5 | 13.5 | 21.3126 | 3.3475 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9308 | 0.8 | 5 | 11.25 | 17.699 | 2.8263 | 3.6226 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9309 | 1.2 | 3.3333 | 10 | 16.4433 | 3.3957 | 3.0476 | 1 | 5 | 0.4 | 5 | 13.3333
| 9310 | 0.8 | 5 | 12.5581 | 19.2914 | 2.9686 | 3.7647 | 1 | 5 | 0.8 | 2.5 | 12.5
| 9311 | 0.8 | 5 | 20 | 26.4701 | 3.6875 | 2.7826 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 9312 | 1.4 | 2.8571 | 11.4894 | 18.9006 | 2.7283 | 4.6829 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.3571
| 9313 | 1 | 4 | 10.8 | 17.9447 | 2.878 | 4.2667 | 0.6 | 8.3333 | 0.1 | 20 | 32.3333
| 9314 | 1 | 4 | 16.875 | 23.6654 | 3.1678 | 3.6226 | 1 | 5 | 0.4 | 5 | 14
| 9315 | 1.2 | 3.3333 | 12.5581 | 20.9347 | 3.3239 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 9316 | 1 | 4 | 11.7391 | 19.1078 | 2.4456 | 4.9231 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 9317 | 0.6 | 6.6667 | 11.7391 | 19.0365 | 2.4974 | 4.8 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 9318 | 1 | 4 | 12.8571 | 19.0614 | 2.95 | 3.2542 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 9319 | 0.8 | 5 | 10.8 | 19.0963 | 3.4963 | 4.8 | 1 | 5 | 0.1 | 20 | 30
| 9320 | 0.2 | 20 | 13.8462 | 21.7843 | 3.2552 | 4.6829 | 0.8 | 6.25 | 0.2 | 10 | 36.25
| 9321 | 0.8 | 5 | 13.8462 | 19.7754 | 2.237 | 3.6923 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9322 | 0.8 | 5 | 16.875 | 24.4938 | 3.2552 | 4.3636 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 9323 | 1.6 | 2.5 | 12 | 17.7063 | 2.3959 | 3.3103 | 0.4 | 12.5 | 0.4 | 5 | 20
| 9324 | 1 | 4 | 13.1707 | 20.1467 | 3.776 | 3.2 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 9325 | 0.1 | 40 | 12.2727 | 20.3933 | 2.3024 | 5.8182 | 1 | 5 | 0.4 | 5 | 50
| 9326 | 1.2 | 3.3333 | 14.5946 | 23.3595 | 3.5758 | 5.1892 | 1.2 | 4.1667 | 0.1 | 20 | 27.5
| 9327 | 0.6 | 6.6667 | 9.8182 | 17.43 | 3.1467 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 9328 | 1 | 4 | 15.8824 | 24.4672 | 3.3957 | 5.1892 | 1 | 5 | 0.2 | 10 | 19
| 9329 | 0.4 | 10 | 10.8 | 19.1019 | 2.9686 | 5.3333 | 1 | 5 | 0.8 | 2.5 | 17.5
| 9330 | 0.8 | 5 | 9.1525 | 16.6521 | 3.2329 | 4.2667 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 9331 | 0.6 | 6.6667 | 10.1887 | 22.1396 | 3.6031 | 8.3478 | 1 | 5 | 0.6 | 3.3333 | 15
| 9332 | 0.1 | 40 | 11.0204 | 21.561 | 2.8606 | 7.68 | 1.4 | 3.5714 | 0.4 | 5 | 48.5714
| 9333 | 0.8 | 5 | 12.2727 | 18.8089 | 2.9136 | 3.6226 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 9334 | 0.6 | 6.6667 | 15.4286 | 21.4575 | 2.3366 | 3.6923 | 1 | 5 | 0.4 | 5 | 16.6667
| 9335 | 1.4 | 2.8571 | 10.1887 | 19.8943 | 3.085 | 6.6207 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 9336 | 0.8 | 5 | 8.5714 | 14.5597 | 2.4974 | 3.4909 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9337 | 1 | 4 | 11.25 | 18.977 | 4.1043 | 3.6226 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 9338 | 1.2 | 3.3333 | 12.5581 | 22.5205 | 3.1053 | 6.8571 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 9339 | 0.4 | 10 | 9.8182 | 14.9372 | 2.1651 | 2.9538 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 9340 | 1.6 | 2.5 | 13.1707 | 20.7825 | 3.1467 | 4.4651 | 0.6 | 8.3333 | 0.2 | 10 | 20.8333
| 9341 | 1 | 4 | 10.3846 | 17.9346 | 2.4974 | 5.0526 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 9342 | 1 | 4 | 20 | 26.7113 | 2.7929 | 3.9184 | 0.8 | 6.25 | 1 | 2 | 12.25
| 9343 | 0.8 | 5 | 14.5946 | 22.3375 | 3.2778 | 4.4651 | 1 | 5 | 0.2 | 10 | 20
| 9344 | 0.6 | 6.6667 | 12 | 19.7317 | 2.9317 | 4.8 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 9345 | 0.8 | 5 | 14.2105 | 23.819 | 2.4974 | 7.1111 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 9346 | 1.2 | 3.3333 | 11.4894 | 18.2146 | 2.5514 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 9347 | 1.2 | 3.3333 | 16.3636 | 24.2286 | 3.0649 | 4.8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 9348 | 1 | 4 | 12.2727 | 18.6886 | 2.9873 | 3.4286 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 9349 | 1.4 | 2.8571 | 11.4894 | 17.0224 | 2.5792 | 2.9538 | 0.6 | 8.3333 | 0.8 | 2.5 | 13.6905
| 9350 | 0.6 | 6.6667 | 10.5882 | 17.0018 | 3.0452 | 3.3684 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 9351 | 0.6 | 6.6667 | 15.4286 | 24.2885 | 4.177 | 4.6829 | 1.4 | 3.5714 | 0.1 | 20 | 30.2381
| 9352 | 0.4 | 10 | 12 | 17.4621 | 3.2552 | 2.2069 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 9353 | 0.1 | 40 | 11.0204 | 18.6938 | 2.4842 | 5.1892 | 1.6 | 3.125 | 0.1 | 20 | 63.125
| 9354 | 1.2 | 3.3333 | 13.1707 | 18.9985 | 3.0452 | 2.7826 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 9355 | 0.6 | 6.6667 | 7.3973 | 15.358 | 3.2778 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 9356 | 0.6 | 6.6667 | 7.5 | 13.5502 | 2.6818 | 3.3684 | 1 | 5 | 0.4 | 5 | 16.6667
| 9357 | 1 | 4 | 16.3636 | 23.6176 | 2.9873 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 9358 | 1 | 4 | 10.1887 | 17.8476 | 3.6589 | 4 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 9359 | 0.8 | 5 | 12.8571 | 21.1911 | 3.8689 | 4.4651 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 9360 | 1 | 4 | 18 | 24.6614 | 3.2329 | 3.4286 | 1 | 5 | 0.4 | 5 | 14
| 9361 | 0.8 | 5 | 10.1887 | 15.8599 | 2.4712 | 3.2 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9362 | 1 | 4 | 13.1707 | 21.867 | 2.878 | 5.8182 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 9363 | 1.4 | 2.8571 | 11.4894 | 19.5625 | 3.8065 | 4.2667 | 1.2 | 4.1667 | 0.4 | 5 | 12.0238
| 9364 | 0.4 | 10 | 12.2727 | 18.847 | 2.8095 | 3.7647 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 9365 | 0.4 | 10 | 20.7692 | 29.6599 | 2.6971 | 6.1935 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 9366 | 0.6 | 6.6667 | 9.1525 | 17.6117 | 3.1258 | 5.3333 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 9367 | 0.6 | 6.6667 | 11.7391 | 21.057 | 2.6971 | 6.6207 | 0.4 | 12.5 | 0.2 | 10 | 29.1667
| 9368 | 1.2 | 3.3333 | 11.25 | 17.306 | 2.2913 | 3.7647 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 9369 | 0.4 | 10 | 13.1707 | 21.5738 | 3.6031 | 4.8 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 9370 | 1.2 | 3.3333 | 9.8182 | 17.3396 | 3.6031 | 3.9184 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 9371 | 0.6 | 6.6667 | 15 | 20.3903 | 2.6077 | 2.7826 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 9372 | 0.6 | 6.6667 | 15.8824 | 21.4442 | 2.9317 | 2.6301 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 9373 | 1 | 4 | 12 | 18.7673 | 2.5934 | 4.1739 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 9374 | 0.8 | 5 | 8.7097 | 13.5982 | 2.2584 | 2.6301 | 1 | 5 | 0.2 | 10 | 20
| 9375 | 0.8 | 5 | 12.5581 | 21.0807 | 3.1892 | 5.3333 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 9376 | 0.8 | 5 | 14.5946 | 22.7472 | 3.6875 | 4.4651 | 0.8 | 6.25 | 1 | 2 | 13.25
| 9377 | 0.6 | 6.6667 | 14.2105 | 21.8749 | 3.3007 | 4.3636 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 9378 | 0.6 | 6.6667 | 11.7391 | 20.237 | 3.4453 | 5.0526 | 1.6 | 3.125 | 0.6 | 3.3333 | 13.125
| 9379 | 0.6 | 6.6667 | 13.8462 | 22.4858 | 3.7165 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 9380 | 0.8 | 5 | 14.5946 | 23.4384 | 3.0256 | 5.8182 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 9381 | 0.8 | 5 | 14.5946 | 20.5881 | 3.2109 | 2.7826 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 9382 | 1.4 | 2.8571 | 7.5 | 13.3077 | 2.6077 | 3.2 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 9383 | 1 | 4 | 15.8824 | 23.1676 | 3.4453 | 3.84 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 9384 | 1.2 | 3.3333 | 12.2727 | 18.5394 | 2.3483 | 3.9184 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 9385 | 1 | 4 | 15 | 22.0559 | 3.6875 | 3.3684 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 9386 | 0.6 | 6.6667 | 12.8571 | 23.0867 | 4.5825 | 5.6471 | 1 | 5 | 0.4 | 5 | 16.6667
| 9387 | 1 | 4 | 19.2857 | 25.5339 | 2.4082 | 3.84 | 0.4 | 12.5 | 0.2 | 10 | 26.5
| 9388 | 1.6 | 2.5 | 12.2727 | 20.5377 | 2.9317 | 5.3333 | 0.6 | 8.3333 | 0.4 | 5 | 15.8333
| 9389 | 0.4 | 10 | 13.5 | 20.7381 | 2.6667 | 4.5714 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 9390 | 0.8 | 5 | 23.4783 | 29.9969 | 2.8263 | 3.6923 | 1.4 | 3.5714 | 0.8 | 2.5 | 11.0714
| 9391 | 1 | 4 | 11.4894 | 19.5314 | 3.4706 | 4.5714 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 9392 | 1 | 4 | 12.2727 | 17.82 | 2.5934 | 2.9538 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 9393 | 1.4 | 2.8571 | 18.6207 | 28.1964 | 3.5758 | 6 | 1 | 5 | 0.2 | 10 | 17.8571
| 9394 | 0.8 | 5 | 12.5581 | 20.6844 | 2.7929 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 9395 | 1.4 | 2.8571 | 11.7391 | 18.6857 | 3.3239 | 3.6226 | 1 | 5 | 0.2 | 10 | 17.8571
| 9396 | 0.8 | 5 | 9.1525 | 15.8759 | 3.1678 | 3.5556 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9397 | 1 | 4 | 10.1887 | 18.1494 | 3.2778 | 4.6829 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 9398 | 0.2 | 20 | 11.7391 | 21.3283 | 3.1892 | 6.4 | 1 | 5 | 0.2 | 10 | 35
| 9399 | 0.6 | 6.6667 | 12 | 19.5897 | 2.6667 | 4.9231 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 9400 | 1 | 4 | 17.4194 | 25.01 | 3.3239 | 4.2667 | 1 | 5 | 0.2 | 10 | 19
| 9401 | 0.8 | 5 | 9.3103 | 16.4726 | 2.6971 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9402 | 1 | 4 | 9.1525 | 15.4768 | 2.4842 | 3.84 | 1 | 5 | 0.4 | 5 | 14
| 9403 | 1 | 4 | 9.8182 | 19.1672 | 2.7283 | 6.6207 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 9404 | 0.8 | 5 | 11.7391 | 22.3508 | 2.9317 | 7.68 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9405 | 0.4 | 10 | 12.2727 | 19.2996 | 2.7602 | 4.2667 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 9406 | 0.6 | 6.6667 | 13.1707 | 18.9646 | 2.6971 | 3.0968 | 1 | 5 | 0.6 | 3.3333 | 15
| 9407 | 0.2 | 20 | 11.7391 | 17.7313 | 2.6818 | 3.3103 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 9408 | 0.8 | 5 | 16.3636 | 26.7934 | 3.0452 | 7.3846 | 1 | 5 | 1 | 2 | 12
| 9409 | 0.8 | 5 | 10.5882 | 16.3675 | 2.5792 | 3.2 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 9410 | 0.6 | 6.6667 | 9.4737 | 18.2502 | 2.7765 | 6 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 9411 | 0.6 | 6.6667 | 13.5 | 23.617 | 3.4963 | 6.6207 | 1 | 5 | 0.4 | 5 | 16.6667
| 9412 | 1.4 | 2.8571 | 11.0204 | 16.9099 | 3.1467 | 2.7429 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 9413 | 0.4 | 10 | 10.1887 | 17.8763 | 3.3239 | 4.3636 | 1.6 | 3.125 | 0.6 | 3.3333 | 16.4583
| 9414 | 0.6 | 6.6667 | 11.25 | 20.969 | 3.9008 | 5.8182 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 9415 | 0.4 | 10 | 14.2105 | 21.3418 | 3.5758 | 3.5556 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 9416 | 0.8 | 5 | 10 | 15.8869 | 2.4583 | 3.4286 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 9417 | 1.2 | 3.3333 | 15.8824 | 22.3029 | 2.4205 | 4 | 1.4 | 3.5714 | 0.8 | 2.5 | 9.4048
| 9418 | 0.4 | 10 | 12.2727 | 18.5209 | 2.4082 | 3.84 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 9419 | 1 | 4 | 14.5946 | 24.4581 | 3.0064 | 6.8571 | 1 | 5 | 0.2 | 10 | 19
| 9420 | 1 | 4 | 11.7391 | 21.8376 | 2.9873 | 7.1111 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 9421 | 0.4 | 10 | 12.5581 | 18.7245 | 3.3007 | 2.8657 | 1.6 | 3.125 | 0.8 | 2.5 | 15.625
| 9422 | 0.4 | 10 | 12.2727 | 19.6414 | 2.4456 | 4.9231 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 9423 | 0.6 | 6.6667 | 11.0204 | 18.0656 | 3.0452 | 4 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 9424 | 1 | 4 | 10.5882 | 16.4217 | 2.5792 | 3.2542 | 1 | 5 | 0.4 | 5 | 14
| 9425 | 1 | 4 | 13.5 | 22.7329 | 3.2329 | 6 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 9426 | 0.8 | 5 | 13.1707 | 21.2804 | 3.746 | 4.3636 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9427 | 0.6 | 6.6667 | 13.5 | 20.218 | 2.878 | 3.84 | 1 | 5 | 0.2 | 10 | 21.6667
| 9428 | 1 | 4 | 10 | 15.731 | 2.3024 | 3.4286 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 9429 | 0.6 | 6.6667 | 9 | 16.2841 | 2.7126 | 4.5714 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 9430 | 0.6 | 6.6667 | 9.1525 | 15.5746 | 3.1678 | 3.2542 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 9431 | 0.2 | 20 | 13.5 | 19.7994 | 3.0452 | 3.2542 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 9432 | 0.8 | 5 | 9.4737 | 17.7809 | 4.8163 | 3.4909 | 1 | 5 | 0.8 | 2.5 | 12.5
| 9433 | 1.6 | 2.5 | 10.5882 | 17.8087 | 2.4205 | 4.8 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.0833
| 9434 | 0.6 | 6.6667 | 14.5946 | 21.2764 | 3.3714 | 3.3103 | 0.4 | 12.5 | 0.6 | 3.3333 | 22.5
| 9435 | 1.2 | 3.3333 | 12.8571 | 22.5996 | 3.5489 | 6.1935 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 9436 | 1 | 4 | 12.2727 | 19.6358 | 3.1892 | 4.1739 | 0.8 | 6.25 | 0.1 | 20 | 30.25
| 9437 | 0.8 | 5 | 8.7097 | 15.1609 | 2.8957 | 3.5556 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 9438 | 1 | 4 | 13.1707 | 20.7895 | 3.2552 | 4.3636 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 9439 | 0.4 | 10 | 9.6429 | 18.9532 | 4.6275 | 4.6829 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 9440 | 1.2 | 3.3333 | 13.1707 | 21.7016 | 3.0452 | 5.4857 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 9441 | 0.4 | 10 | 20 | 26.8092 | 2.4456 | 4.3636 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 9442 | 0.6 | 6.6667 | 9 | 14.9702 | 3.1467 | 2.8235 | 0.4 | 12.5 | 0.2 | 10 | 29.1667
| 9443 | 0.2 | 20 | 15.4286 | 22.5517 | 3.8689 | 3.2542 | 1.2 | 4.1667 | 0.6 | 3.3333 | 27.5
| 9444 | 0.6 | 6.6667 | 14.5946 | 21.9839 | 3.0256 | 4.3636 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 9445 | 1.4 | 2.8571 | 8.1818 | 13.7631 | 3.2109 | 2.3704 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 9446 | 1 | 4 | 10.5882 | 17.0416 | 3.085 | 3.3684 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 9447 | 1 | 4 | 12.5581 | 20.047 | 3.9333 | 3.5556 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 9448 | 1 | 4 | 11.0204 | 19.2407 | 3.4203 | 4.8 | 0.6 | 8.3333 | 0.8 | 2.5 | 14.8333
| 9449 | 0.8 | 5 | 11.25 | 19.8351 | 4.4112 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9450 | 0.8 | 5 | 11.4894 | 19.8651 | 3.5758 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 9451 | 1.2 | 3.3333 | 18 | 25.5283 | 2.7283 | 4.8 | 1 | 5 | 0.4 | 5 | 13.3333
| 9452 | 0.8 | 5 | 13.5 | 22.5476 | 4.5825 | 4.4651 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 9453 | 0.8 | 5 | 13.1707 | 20.9836 | 2.7602 | 5.0526 | 1.6 | 3.125 | 0.6 | 3.3333 | 11.4583
| 9454 | 0.8 | 5 | 11.0204 | 16.3901 | 2.8434 | 2.5263 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9455 | 0.6 | 6.6667 | 11.7391 | 20.704 | 3.1467 | 5.8182 | 1 | 5 | 0.2 | 10 | 21.6667
| 9456 | 0.8 | 5 | 15 | 22.9702 | 2.6369 | 5.3333 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9457 | 1.2 | 3.3333 | 15 | 20.8268 | 2.4583 | 3.3684 | 1 | 5 | 0.4 | 5 | 13.3333
| 9458 | 1.2 | 3.3333 | 12 | 20.9234 | 3.1053 | 5.8182 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 9459 | 0.6 | 6.6667 | 11.0204 | 19.0756 | 3.2552 | 4.8 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 9460 | 0.8 | 5 | 19.2857 | 39.0317 | 3.746 | 16 | 0.6 | 8.3333 | 0.1 | 20 | 33.3333
| 9461 | 0.6 | 6.6667 | 10 | 17.3858 | 3.3007 | 4.0851 | 1 | 5 | 0.4 | 5 | 16.6667
| 9462 | 1.4 | 2.8571 | 13.1707 | 23.2877 | 3.4963 | 6.6207 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 9463 | 0.8 | 5 | 11.7391 | 17.0758 | 2.3366 | 3 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 9464 | 0.2 | 20 | 12.5581 | 20.8041 | 2.7602 | 5.4857 | 1 | 5 | 0.1 | 20 | 45
| 9465 | 1.6 | 2.5 | 14.2105 | 22.9978 | 4.1043 | 4.6829 | 1.2 | 4.1667 | 0.4 | 5 | 11.6667
| 9466 | 1 | 4 | 12.5581 | 20.5244 | 2.9136 | 5.0526 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 9467 | 1 | 4 | 11.7391 | 17.7825 | 2.8434 | 3.2 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 9468 | 1 | 4 | 12.2727 | 18.4596 | 3.2778 | 2.9091 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 9469 | 0.8 | 5 | 11.4894 | 18.4359 | 3.3239 | 3.6226 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 9470 | 1 | 4 | 9.6429 | 21.5168 | 3.1467 | 8.7273 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 9471 | 1.2 | 3.3333 | 11.25 | 17.8201 | 2.6517 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 9472 | 1.4 | 2.8571 | 11.0204 | 21.0667 | 3.1892 | 6.8571 | 1 | 5 | 0.4 | 5 | 12.8571
| 9473 | 0.6 | 6.6667 | 12.8571 | 21.5298 | 3.0256 | 5.6471 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 9474 | 0.2 | 20 | 12.2727 | 20.077 | 3.2329 | 4.5714 | 1 | 5 | 0.1 | 20 | 45
| 9475 | 0.8 | 5 | 10.3846 | 18.611 | 2.2264 | 6 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 9476 | 1.2 | 3.3333 | 11.4894 | 18.9997 | 3.1467 | 4.3636 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 9477 | 1 | 4 | 9.4737 | 20.8694 | 3.3957 | 8 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 9478 | 0.6 | 6.6667 | 15.4286 | 22.3925 | 4.1404 | 2.8235 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 9479 | 0.4 | 10 | 16.3636 | 23.6092 | 2.4456 | 4.8 | 1 | 5 | 0.4 | 5 | 20
| 9480 | 1 | 4 | 9.1525 | 17.7894 | 2.6369 | 6 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 9481 | 1.2 | 3.3333 | 11.7391 | 19.8926 | 3.4706 | 4.6829 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 9482 | 1.2 | 3.3333 | 10.3846 | 17.9121 | 3.6875 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 9483 | 1.2 | 3.3333 | 12.2727 | 19.68 | 2.4842 | 4.9231 | 1 | 5 | 0.4 | 5 | 13.3333
| 9484 | 0.8 | 5 | 10.5882 | 18.7222 | 3.2109 | 4.9231 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 9485 | 1 | 4 | 11.4894 | 18.1739 | 2.5106 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 9486 | 0.8 | 5 | 13.8462 | 21.5337 | 3.6875 | 4 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 9487 | 0.2 | 20 | 11.25 | 18.0796 | 3.0649 | 3.7647 | 0.6 | 8.3333 | 0.1 | 20 | 48.3333
| 9488 | 0.8 | 5 | 14.2105 | 21.302 | 3.0064 | 4.0851 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 9489 | 0.6 | 6.6667 | 11.4894 | 17.0804 | 3.2778 | 2.3133 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 9490 | 1.2 | 3.3333 | 12.5581 | 20.3472 | 3.5224 | 4.2667 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 9491 | 0.8 | 5 | 10.1887 | 17.1157 | 3.3714 | 3.5556 | 1.6 | 3.125 | 0.6 | 3.3333 | 11.4583
| 9492 | 0.4 | 10 | 8.8525 | 17.2519 | 3.7165 | 4.6829 | 1 | 5 | 0.1 | 20 | 35
| 9493 | 1.2 | 3.3333 | 15.4286 | 22.0441 | 2.6971 | 3.9184 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15
| 9494 | 0.2 | 20 | 11.7391 | 20.1791 | 2.7929 | 5.6471 | 1.4 | 3.5714 | 0.2 | 10 | 33.5714
| 9495 | 0.4 | 10 | 10.1887 | 19.3696 | 2.9873 | 6.1935 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 9496 | 0.4 | 10 | 14.5946 | 21.1358 | 2.7765 | 3.7647 | 1 | 5 | 0.8 | 2.5 | 17.5
| 9497 | 1.4 | 2.8571 | 11.0204 | 16.825 | 2.3137 | 3.4909 | 1.6 | 3.125 | 0.4 | 5 | 10.9821
| 9498 | 0.8 | 5 | 9.8182 | 16.8479 | 2.4583 | 4.5714 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 9499 | 1 | 4 | 12 | 19.8291 | 2.7765 | 5.0526 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 9500 | 0.8 | 5 | 13.5 | 19.077 | 3.1467 | 2.4304 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 9501 | 1.2 | 3.3333 | 13.1707 | 20.731 | 2.7602 | 4.8 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 9502 | 0.8 | 5 | 10.3846 | 17.3048 | 3.9664 | 2.9538 | 0.4 | 12.5 | 0.2 | 10 | 27.5
| 9503 | 0.8 | 5 | 9.1525 | 16.364 | 3.3714 | 3.84 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9504 | 0.8 | 5 | 11.0204 | 20.3704 | 2.95 | 6.4 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 9505 | 1 | 4 | 13.5 | 19.4231 | 2.8263 | 3.0968 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 9506 | 0.8 | 5 | 11.4894 | 19.8732 | 2.3838 | 6 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 9507 | 0.6 | 6.6667 | 11.0204 | 16.9487 | 2.7283 | 3.2 | 1 | 5 | 0.2 | 10 | 21.6667
| 9508 | 0.8 | 5 | 8.1818 | 15.0153 | 3.2109 | 3.6226 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 9509 | 0.8 | 5 | 17.4194 | 23.727 | 3.2109 | 3.0968 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9510 | 1 | 4 | 11.7391 | 18.3573 | 3.4706 | 3.1475 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 9511 | 0.4 | 10 | 12.2727 | 19.1001 | 2.9873 | 3.84 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 9512 | 0.6 | 6.6667 | 12 | 22.3967 | 3.776 | 6.6207 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 9513 | 0.4 | 10 | 10.1887 | 15.9403 | 3.085 | 2.6667 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 9514 | 1.2 | 3.3333 | 13.5 | 20.8479 | 2.7765 | 4.5714 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 9515 | 0.4 | 10 | 18.6207 | 26.1425 | 3.2552 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 9516 | 0.6 | 6.6667 | 12 | 23.7724 | 3.0452 | 8.7273 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 9517 | 1 | 4 | 14.2105 | 26.501 | 2.1852 | 10.1053 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 9518 | 0.2 | 20 | 10.1887 | 17.6602 | 3.0064 | 4.4651 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 9519 | 1 | 4 | 13.8462 | 23.7289 | 3.0256 | 6.8571 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 9520 | 1.4 | 2.8571 | 10.8 | 17.2192 | 2.5792 | 3.84 | 1 | 5 | 0.2 | 10 | 17.8571
| 9521 | 0.6 | 6.6667 | 10.8 | 16.5919 | 2.5376 | 3.2542 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 9522 | 0.6 | 6.6667 | 18.6207 | 27.3497 | 3.3957 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 9523 | 0.6 | 6.6667 | 10 | 17.6767 | 3.1053 | 4.5714 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 9524 | 1.4 | 2.8571 | 15.4286 | 23.884 | 4.3704 | 4.0851 | 0.4 | 12.5 | 0.6 | 3.3333 | 18.6905
| 9525 | 0.2 | 20 | 7.9412 | 14.6335 | 3.3239 | 3.3684 | 0.6 | 8.3333 | 0.4 | 5 | 33.3333
| 9526 | 0.8 | 5 | 15.4286 | 23.9086 | 3.1467 | 5.3333 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 9527 | 0.6 | 6.6667 | 20 | 27.8311 | 3.746 | 4.0851 | 1 | 5 | 0.4 | 5 | 16.6667
| 9528 | 1 | 4 | 9.1525 | 17.64 | 3.6875 | 4.8 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 9529 | 0.4 | 10 | 13.1707 | 19.8316 | 2.9686 | 3.6923 | 1 | 5 | 0.4 | 5 | 20
| 9530 | 1 | 4 | 12.5581 | 19.6177 | 2.7929 | 4.2667 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 9531 | 0.8 | 5 | 15.4286 | 23.649 | 3.1678 | 5.0526 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 9532 | 0.6 | 6.6667 | 7.7143 | 17.6128 | 3.2778 | 6.6207 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 9533 | 0.4 | 10 | 10.5882 | 17.8049 | 2.95 | 4.2667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 9534 | 0.8 | 5 | 16.875 | 23.2235 | 2.7929 | 3.5556 | 1.8 | 2.7778 | 0.4 | 5 | 12.7778
| 9535 | 0.4 | 10 | 11.7391 | 17.5471 | 2.0433 | 3.7647 | 1 | 5 | 0.4 | 5 | 20
| 9536 | 0.6 | 6.6667 | 14.2105 | 20.0974 | 2.4583 | 3.4286 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 9537 | 0.6 | 6.6667 | 17.4194 | 24.8669 | 2.2584 | 5.1892 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 9538 | 1.4 | 2.8571 | 12.5581 | 19.3257 | 2.3024 | 4.4651 | 1 | 5 | 0.1 | 20 | 27.8571
| 9539 | 0.1 | 40 | 8.1818 | 17.7516 | 2.7126 | 6.8571 | 1.2 | 4.1667 | 0.1 | 20 | 64.1667
| 9540 | 0.6 | 6.6667 | 7.9412 | 14.2921 | 2.7283 | 3.6226 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 9541 | 0.6 | 6.6667 | 12 | 18.023 | 2.7126 | 3.3103 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 9542 | 0.4 | 10 | 16.875 | 23.9552 | 2.2802 | 4.8 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 9543 | 0.8 | 5 | 12.8571 | 20.6224 | 2.7126 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 9544 | 0.6 | 6.6667 | 14.5946 | 21.9593 | 2.6818 | 4.6829 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 9545 | 0.6 | 6.6667 | 10.8 | 19.0742 | 3.085 | 5.1892 | 1 | 5 | 0.2 | 10 | 21.6667
| 9546 | 1 | 4 | 18 | 25.5442 | 2.7442 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 9547 | 1.2 | 3.3333 | 12.8571 | 19.3123 | 3.2552 | 3.2 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 9548 | 1 | 4 | 13.5 | 20.7997 | 3.1258 | 4.1739 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 9549 | 0.6 | 6.6667 | 13.1707 | 22.073 | 3.2552 | 5.6471 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 9550 | 0.4 | 10 | 15 | 21.4477 | 2.6077 | 3.84 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 9551 | 1.4 | 2.8571 | 11.4894 | 19.0347 | 3.3714 | 4.1739 | 0.8 | 6.25 | 0.1 | 20 | 29.1071
| 9552 | 0.8 | 5 | 11.25 | 16.8628 | 2.5652 | 3.0476 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 9553 | 0.8 | 5 | 11.4894 | 19.5321 | 3.8689 | 4.1739 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 9554 | 1 | 4 | 11.4894 | 19.2937 | 3.2329 | 4.5714 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 9555 | 1.4 | 2.8571 | 11.7391 | 19.2626 | 3.9008 | 3.6226 | 0.6 | 8.3333 | 0.6 | 3.3333 | 14.5238
| 9556 | 0.6 | 6.6667 | 17.4194 | 23.8967 | 2.7126 | 3.7647 | 1 | 5 | 0.2 | 10 | 21.6667
| 9557 | 1 | 4 | 12.5581 | 20.2456 | 3.6875 | 4 | 1 | 5 | 0.4 | 5 | 14
| 9558 | 0.8 | 5 | 9.6429 | 20.2363 | 2.5934 | 8 | 1 | 5 | 0.2 | 10 | 20
| 9559 | 0.4 | 10 | 11.7391 | 18.6857 | 3.3239 | 3.6226 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 9560 | 0.4 | 10 | 18.6207 | 27.1186 | 3.4453 | 5.0526 | 1.4 | 3.5714 | 0.1 | 20 | 33.5714
| 9561 | 0.8 | 5 | 11.25 | 20.4194 | 3.5224 | 5.6471 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 9562 | 1 | 4 | 12.2727 | 18.323 | 2.6818 | 3.3684 | 1 | 5 | 0.4 | 5 | 14
| 9563 | 0.6 | 6.6667 | 14.5946 | 22.7523 | 2.9686 | 5.1892 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 9564 | 1 | 4 | 10.8 | 16.5309 | 2.4205 | 3.3103 | 1 | 5 | 0.4 | 5 | 14
| 9565 | 1.2 | 3.3333 | 9.8182 | 19.0291 | 3.2109 | 6 | 1.2 | 4.1667 | 0.4 | 5 | 12.5
| 9566 | 0.6 | 6.6667 | 12 | 22.6945 | 3.8374 | 6.8571 | 1 | 5 | 0.2 | 10 | 21.6667
| 9567 | 0.8 | 5 | 14.5946 | 25.9736 | 2.6517 | 8.7273 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 9568 | 0.8 | 5 | 18 | 27.8257 | 2.9686 | 6.8571 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 9569 | 0.6 | 6.6667 | 11.7391 | 20.9086 | 3.5224 | 5.6471 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 9570 | 0.6 | 6.6667 | 9.1525 | 16.8068 | 3.1892 | 4.4651 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 9571 | 1.2 | 3.3333 | 9.3103 | 15.8028 | 3.3957 | 3.0968 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 9572 | 0.4 | 10 | 11.0204 | 18.0578 | 3.8374 | 3.2 | 1 | 5 | 0.2 | 10 | 25
| 9573 | 0.8 | 5 | 12 | 23.045 | 2.6971 | 8.3478 | 0.4 | 12.5 | 0.4 | 5 | 22.5
| 9574 | 0.4 | 10 | 13.5 | 20.3869 | 2.9686 | 3.9184 | 1.4 | 3.5714 | 0.8 | 2.5 | 16.0714
| 9575 | 1 | 4 | 16.3636 | 27.2208 | 3.746 | 7.1111 | 1.4 | 3.5714 | 0.4 | 5 | 12.5714
| 9576 | 1.6 | 2.5 | 10.8 | 17.1741 | 3.4203 | 2.9538 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.0833
| 9577 | 0.8 | 5 | 9.4737 | 15.3142 | 2.7929 | 3.0476 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 9578 | 0.6 | 6.6667 | 13.8462 | 22.1884 | 2.5241 | 5.8182 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 9579 | 1.2 | 3.3333 | 12 | 21.3827 | 3.1892 | 6.1935 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 9580 | 1 | 4 | 7.7143 | 15.8857 | 3.3714 | 4.8 | 1 | 5 | 0.2 | 10 | 19
| 9581 | 0.6 | 6.6667 | 14.5946 | 24.9223 | 3.4706 | 6.8571 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 9582 | 0.6 | 6.6667 | 11.0204 | 21.0512 | 3.6308 | 6.4 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 9583 | 0.8 | 5 | 11.0204 | 17.1639 | 3.2778 | 2.8657 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9584 | 0.2 | 20 | 11.25 | 18.4278 | 2.7126 | 4.4651 | 0.6 | 8.3333 | 0.6 | 3.3333 | 31.6667
| 9585 | 0.4 | 10 | 12.8571 | 20.007 | 3.6589 | 3.4909 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 9586 | 0.4 | 10 | 15.4286 | 25.6738 | 2.8606 | 7.3846 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 9587 | 0.6 | 6.6667 | 10.1887 | 19.1535 | 3.1467 | 5.8182 | 1 | 5 | 0.6 | 3.3333 | 15
| 9588 | 1.2 | 3.3333 | 20.7692 | 27.8421 | 2.6077 | 4.4651 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 9589 | 0.2 | 20 | 10.8 | 19.229 | 3.746 | 4.6829 | 0.8 | 6.25 | 0.2 | 10 | 36.25
| 9590 | 0.6 | 6.6667 | 13.5 | 20.707 | 2.8434 | 4.3636 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 9591 | 0.4 | 10 | 16.3636 | 23.5012 | 3.4453 | 3.6923 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 9592 | 0.6 | 6.6667 | 8.0597 | 15.1477 | 3.3957 | 3.6923 | 0.8 | 6.25 | 0.8 | 2.5 | 15.4167
| 9593 | 1.2 | 3.3333 | 16.875 | 24.5215 | 3.8065 | 3.84 | 1 | 5 | 0.4 | 5 | 13.3333
| 9594 | 0.8 | 5 | 8.3077 | 15.5918 | 2.7126 | 4.5714 | 1 | 5 | 0.4 | 5 | 15
| 9595 | 0.6 | 6.6667 | 12.2727 | 18.8827 | 2.9873 | 3.6226 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 9596 | 1.2 | 3.3333 | 10 | 17.5491 | 3.6308 | 3.9184 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 9597 | 0.4 | 10 | 19.2857 | 30.6097 | 3.3239 | 8 | 0.8 | 6.25 | 0.2 | 10 | 26.25
| 9598 | 1 | 4 | 9.8182 | 19.7962 | 2.5934 | 7.3846 | 1 | 5 | 0.8 | 2.5 | 11.5
| 9599 | 0.6 | 6.6667 | 8.5714 | 15.6402 | 2.4974 | 4.5714 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 9600 | 1.4 | 2.8571 | 15.8824 | 24.6473 | 3.5758 | 5.1892 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 9601 | 0.6 | 6.6667 | 8.5714 | 17.1488 | 2.3838 | 6.1935 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 9602 | 0.6 | 6.6667 | 15.8824 | 25.0932 | 3.2109 | 6 | 1 | 5 | 0.4 | 5 | 16.6667
| 9603 | 1.2 | 3.3333 | 20 | 27.4476 | 2.2584 | 5.1892 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 9604 | 0.2 | 20 | 12.2727 | 16.9786 | 2.5241 | 2.1818 | 1 | 5 | 0.2 | 10 | 35
| 9605 | 1.2 | 3.3333 | 13.1707 | 19.7403 | 3.746 | 2.8235 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 9606 | 1 | 4 | 16.875 | 22.5954 | 3.1258 | 2.5946 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 9607 | 0.6 | 6.6667 | 12 | 20.2584 | 2.2584 | 6 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 9608 | 1 | 4 | 9.4737 | 15.8603 | 2.8957 | 3.4909 | 1.2 | 4.1667 | 0.8 | 2.5 | 10.6667
| 9609 | 0.8 | 5 | 13.1707 | 19.0603 | 3.1467 | 2.7429 | 1 | 5 | 0.4 | 5 | 15
| 9610 | 0.4 | 10 | 20 | 28.0747 | 3.9008 | 4.1739 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 9611 | 1 | 4 | 10.3846 | 16.6868 | 2.3838 | 3.9184 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 9612 | 0.4 | 10 | 12 | 20.1007 | 3.3007 | 4.8 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 9613 | 0.6 | 6.6667 | 13.8462 | 24.0235 | 2.4974 | 7.68 | 1 | 5 | 0.4 | 5 | 16.6667
| 9614 | 0.8 | 5 | 12.5581 | 22.3509 | 2.4082 | 7.3846 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 9615 | 1.4 | 2.8571 | 16.875 | 24.4715 | 3.2329 | 4.3636 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 9616 | 0.2 | 20 | 12.2727 | 19.3667 | 3.6031 | 3.4909 | 1.2 | 4.1667 | 1 | 2 | 26.1667
| 9617 | 1 | 4 | 10.3846 | 18.3799 | 2.3483 | 5.6471 | 1 | 5 | 0.4 | 5 | 14
| 9618 | 1 | 4 | 14.2105 | 21.6194 | 3.7165 | 3.6923 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 9619 | 1 | 4 | 18 | 25.5942 | 3.4203 | 4.1739 | 1.4 | 3.5714 | 0.1 | 20 | 27.5714
| 9620 | 1 | 4 | 13.5 | 19.9852 | 2.7929 | 3.6923 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 9621 | 0.8 | 5 | 16.875 | 24.3558 | 3.3957 | 4.0851 | 0.4 | 12.5 | 0.2 | 10 | 27.5
| 9622 | 1.4 | 2.8571 | 8.8525 | 15.5966 | 2.7442 | 4 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 9623 | 1.4 | 2.8571 | 15.8824 | 22.4538 | 3.3714 | 3.2 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 9624 | 1 | 4 | 10 | 16.5842 | 2.7442 | 3.84 | 1.2 | 4.1667 | 0.2 | 10 | 18.1667
| 9625 | 0.8 | 5 | 15 | 20.3327 | 3.1258 | 2.2069 | 1.4 | 3.5714 | 0.8 | 2.5 | 11.0714
| 9626 | 0.8 | 5 | 12.2727 | 20.3405 | 3.4963 | 4.5714 | 1 | 5 | 0.4 | 5 | 15
| 9627 | 1 | 4 | 11.4894 | 22.8833 | 2.6667 | 8.7273 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 9628 | 1.4 | 2.8571 | 13.8462 | 21.2595 | 3.1467 | 4.2667 | 0.8 | 6.25 | 0.2 | 10 | 19.1071
| 9629 | 0.6 | 6.6667 | 12.5581 | 16.9482 | 2.2802 | 2.1099 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 9630 | 1.2 | 3.3333 | 10.5882 | 17.1641 | 3.085 | 3.4909 | 1 | 5 | 0.4 | 5 | 13.3333
| 9631 | 0.4 | 10 | 8.8525 | 15.7125 | 2.5934 | 4.2667 | 0.8 | 6.25 | 0.6 | 3.3333 | 19.5833
| 9632 | 0.6 | 6.6667 | 15.8824 | 26.9259 | 3.6589 | 7.3846 | 1 | 5 | 0.4 | 5 | 16.6667
| 9633 | 1.2 | 3.3333 | 10.8 | 21.1277 | 3.4706 | 6.8571 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 9634 | 1.2 | 3.3333 | 11.25 | 16.4219 | 3.085 | 2.087 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 9635 | 0.8 | 5 | 15 | 21.0423 | 2.5514 | 3.4909 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 9636 | 0.8 | 5 | 18 | 24.779 | 2.8606 | 3.9184 | 1.6 | 3.125 | 0.2 | 10 | 18.125
| 9637 | 0.4 | 10 | 12.2727 | 20.2808 | 3.085 | 4.9231 | 1 | 5 | 0.8 | 2.5 | 17.5
| 9638 | 1 | 4 | 12 | 24.358 | 3.6308 | 8.7273 | 0.4 | 12.5 | 0.4 | 5 | 21.5
| 9639 | 0.4 | 10 | 14.5946 | 28.2487 | 3.5489 | 10.1053 | 1 | 5 | 0.4 | 5 | 20
| 9640 | 0.8 | 5 | 10.1887 | 17.4303 | 2.7765 | 4.4651 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 9641 | 1 | 4 | 10 | 15.2546 | 2.7283 | 2.5263 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 9642 | 0.8 | 5 | 9.1525 | 15.1888 | 2.6077 | 3.4286 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 9643 | 1 | 4 | 11.4894 | 19.9703 | 4.2143 | 4.2667 | 1.4 | 3.5714 | 0.8 | 2.5 | 10.0714
| 9644 | 0.8 | 5 | 12.2727 | 18.323 | 2.6818 | 3.3684 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 9645 | 0.8 | 5 | 12.8571 | 19.1668 | 2.1357 | 4.1739 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9646 | 0.6 | 6.6667 | 11.4894 | 19.1642 | 2.6222 | 5.0526 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 9647 | 0.6 | 6.6667 | 7.7143 | 16.5239 | 3.3239 | 5.4857 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 9648 | 1 | 4 | 12 | 20.95 | 2.95 | 6 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 9649 | 1 | 4 | 15.8824 | 22.1054 | 2.4583 | 3.7647 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 9650 | 0.4 | 10 | 13.5 | 21.6392 | 2.95 | 5.1892 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 9651 | 1 | 4 | 20.7692 | 29.7552 | 3.1678 | 5.8182 | 1 | 5 | 0.2 | 10 | 19
| 9652 | 0.6 | 6.6667 | 12.5581 | 21.1804 | 2.6222 | 6 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 9653 | 0.8 | 5 | 11.0204 | 17.8104 | 2.95 | 3.84 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9654 | 0.6 | 6.6667 | 12.2727 | 19.0826 | 3.9008 | 2.9091 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 9655 | 1.2 | 3.3333 | 9.4737 | 17.0172 | 2.8606 | 4.6829 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 9656 | 1.2 | 3.3333 | 6.8354 | 14.9751 | 3.776 | 4.3636 | 1 | 5 | 0.4 | 5 | 13.3333
| 9657 | 1 | 4 | 8.7097 | 20.8143 | 4.72 | 7.3846 | 1 | 5 | 1 | 2 | 11
| 9658 | 0.4 | 10 | 14.2105 | 20.6019 | 2.5514 | 3.84 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 9659 | 0.8 | 5 | 12.2727 | 19.8431 | 3.1053 | 4.4651 | 1 | 5 | 0.2 | 10 | 20
| 9660 | 1.4 | 2.8571 | 18 | 25.1639 | 3.3239 | 3.84 | 1.4 | 3.5714 | 0.4 | 5 | 11.4286
| 9661 | 0.4 | 10 | 9.8182 | 17.6176 | 2.3137 | 5.4857 | 1.8 | 2.7778 | 1 | 2 | 14.7778
| 9662 | 1 | 4 | 14.5946 | 21.1495 | 3.3007 | 3.2542 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 9663 | 1 | 4 | 9.4737 | 21.8215 | 4 | 8.3478 | 1.6 | 3.125 | 0.1 | 20 | 27.125
| 9664 | 0.8 | 5 | 9.8182 | 16.5361 | 3.0256 | 3.6923 | 1 | 5 | 0.2 | 10 | 20
| 9665 | 1 | 4 | 14.2105 | 20.7355 | 2.7602 | 3.7647 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 9666 | 1 | 4 | 16.875 | 25.0012 | 2.7929 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 9667 | 1.2 | 3.3333 | 17.4194 | 27.3615 | 3.085 | 6.8571 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 9668 | 1 | 4 | 12.8571 | 20.7624 | 3.1053 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 9669 | 0.6 | 6.6667 | 15.4286 | 21.4939 | 2.9686 | 3.0968 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 9670 | 1 | 4 | 13.5 | 21.9215 | 4.866 | 3.5556 | 1 | 5 | 0.4 | 5 | 14
| 9671 | 0.8 | 5 | 12.2727 | 20.2796 | 3.3239 | 4.6829 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 9672 | 1 | 4 | 12.5581 | 22.0394 | 2.8606 | 6.6207 | 1 | 5 | 0.4 | 5 | 14
| 9673 | 1.2 | 3.3333 | 10.5882 | 17.3844 | 2.6222 | 4.1739 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 9674 | 0.8 | 5 | 13.1707 | 21.0164 | 2.36 | 5.4857 | 1 | 5 | 0.2 | 10 | 20
| 9675 | 1.2 | 3.3333 | 13.8462 | 19.2325 | 2.8263 | 2.56 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 9676 | 1.4 | 2.8571 | 16.875 | 23.0811 | 2.8957 | 3.3103 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 9677 | 0.8 | 5 | 13.1707 | 20.9973 | 3.2552 | 4.5714 | 1 | 5 | 0.2 | 10 | 20
| 9678 | 1 | 4 | 15.8824 | 22.7252 | 3.746 | 3.0968 | 1 | 5 | 0.4 | 5 | 14
| 9679 | 1.2 | 3.3333 | 8.4375 | 17.6184 | 2.9873 | 6.1935 | 1.4 | 3.5714 | 0.2 | 10 | 16.9048
| 9680 | 0.8 | 5 | 12.2727 | 18.8922 | 2.4456 | 4.1739 | 1 | 5 | 0.4 | 5 | 15
| 9681 | 1 | 4 | 13.5 | 19.957 | 3.1467 | 3.3103 | 1 | 5 | 0.2 | 10 | 19
| 9682 | 0.2 | 20 | 15.4286 | 21.9221 | 3.0649 | 3.4286 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 9683 | 1.2 | 3.3333 | 9.3103 | 18.3953 | 3.085 | 6 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 9684 | 1.4 | 2.8571 | 11.7391 | 19.7696 | 2.6971 | 5.3333 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.4405
| 9685 | 0.8 | 5 | 11.4894 | 17.7898 | 2.8095 | 3.4909 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 9686 | 0.4 | 10 | 18 | 26.4899 | 3.3007 | 5.1892 | 1.4 | 3.5714 | 1 | 2 | 15.5714
| 9687 | 1 | 4 | 15.8824 | 20.9194 | 2.6667 | 2.3704 | 1.4 | 3.5714 | 0.1 | 20 | 27.5714
| 9688 | 0.8 | 5 | 10.8 | 16.9506 | 2.4583 | 3.6923 | 1 | 5 | 0.4 | 5 | 15
| 9689 | 0.4 | 10 | 12.8571 | 21.5187 | 2.8434 | 5.8182 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 9690 | 0.8 | 5 | 9 | 15.7447 | 3.1892 | 3.5556 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 9691 | 1.4 | 2.8571 | 11.25 | 15.9799 | 2.4974 | 2.2326 | 1 | 5 | 0.6 | 3.3333 | 11.1905
| 9692 | 1.2 | 3.3333 | 12.2727 | 25.8061 | 3.9333 | 9.6 | 1 | 5 | 0.2 | 10 | 18.3333
| 9693 | 1 | 4 | 9.8182 | 16.4435 | 2.8606 | 3.7647 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 9694 | 1.2 | 3.3333 | 9.6429 | 18.1582 | 2.6971 | 5.8182 | 1.2 | 4.1667 | 0.1 | 20 | 27.5
| 9695 | 0.4 | 10 | 15.4286 | 21.8965 | 3.4203 | 3.0476 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 9696 | 0.4 | 10 | 10.8 | 19.5115 | 3.6589 | 5.0526 | 1 | 5 | 0.4 | 5 | 20
| 9697 | 1 | 4 | 11.25 | 17.532 | 2.9136 | 3.3684 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 9698 | 0.8 | 5 | 9.4737 | 15.5856 | 3.4453 | 2.6667 | 1 | 5 | 0.4 | 5 | 15
| 9699 | 1.2 | 3.3333 | 9 | 15.1664 | 3.3007 | 2.8657 | 1.4 | 3.5714 | 0.1 | 20 | 26.9048
| 9700 | 0.6 | 6.6667 | 11.25 | 22.1835 | 3.5489 | 7.3846 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 9701 | 0.4 | 10 | 20 | 27.744 | 3.6589 | 4.0851 | 1.2 | 4.1667 | 0.1 | 20 | 34.1667
| 9702 | 0.8 | 5 | 11.7391 | 20.0833 | 2.6971 | 5.6471 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 9703 | 0.8 | 5 | 11.7391 | 18.7378 | 2.9136 | 4.0851 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 9704 | 1.4 | 2.8571 | 12.8571 | 21.8431 | 3.1678 | 5.8182 | 0.1 | 50 | 0.4 | 5 | 57.8571
| 9705 | 0.8 | 5 | 20 | 27.5778 | 3.0064 | 4.5714 | 0.6 | 8.3333 | 0.4 | 5 | 18.3333
| 9706 | 0.8 | 5 | 16.875 | 23.8039 | 2.5652 | 4.3636 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 9707 | 0.8 | 5 | 10.3846 | 17.966 | 3.4963 | 4.0851 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9708 | 0.6 | 6.6667 | 15.4286 | 21.9157 | 3.2329 | 3.2542 | 1.2 | 4.1667 | 0.8 | 2.5 | 13.3333
| 9709 | 0.1 | 40 | 10.5882 | 20.6395 | 2.6667 | 7.3846 | 1 | 5 | 0.6 | 3.3333 | 48.3333
| 9710 | 0.8 | 5 | 15.4286 | 24.2223 | 3.1467 | 5.6471 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 9711 | 1 | 4 | 17.4194 | 24.0885 | 3.3007 | 3.3684 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 9712 | 0.8 | 5 | 11.7391 | 19.4586 | 4.2909 | 3.4286 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 9713 | 1 | 4 | 9 | 18.2957 | 2.8957 | 6.4 | 0.8 | 6.25 | 0.8 | 2.5 | 12.75
| 9714 | 0.4 | 10 | 15 | 22.1447 | 2.878 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 9715 | 1.4 | 2.8571 | 13.8462 | 21.3906 | 3.2778 | 4.2667 | 1.4 | 3.5714 | 0.2 | 10 | 16.4286
| 9716 | 0.8 | 5 | 10 | 18.0212 | 2.9686 | 5.0526 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 9717 | 0.8 | 5 | 14.5946 | 20.8766 | 2.9136 | 3.3684 | 1 | 5 | 0.4 | 5 | 15
| 9718 | 0.8 | 5 | 11.4894 | 21.0292 | 2.1553 | 7.3846 | 1.4 | 3.5714 | 0.6 | 3.3333 | 11.9048
| 9719 | 1.6 | 2.5 | 13.8462 | 30.2423 | 2.6818 | 13.7143 | 1.2 | 4.1667 | 0.8 | 2.5 | 9.1667
| 9720 | 1.2 | 3.3333 | 12.2727 | 19.9076 | 3.7165 | 3.9184 | 0.8 | 6.25 | 0.1 | 20 | 29.5833
| 9721 | 0.6 | 6.6667 | 15 | 25.3618 | 2.6818 | 7.68 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 9722 | 0.8 | 5 | 13.1707 | 19.2531 | 3.5224 | 2.56 | 1.6 | 3.125 | 0.6 | 3.3333 | 11.4583
| 9723 | 0.4 | 10 | 10.8 | 16.5918 | 2.7442 | 3.0476 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 9724 | 1 | 4 | 18 | 23.0433 | 2.0433 | 3 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 9725 | 0.8 | 5 | 14.2105 | 21.0021 | 3.3007 | 3.4909 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 9726 | 1 | 4 | 16.875 | 25.6623 | 4.1043 | 4.6829 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 9727 | 1.2 | 3.3333 | 13.1707 | 20.9998 | 2.7765 | 5.0526 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 9728 | 0.6 | 6.6667 | 12.8571 | 23.5171 | 3.5489 | 7.1111 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 9729 | 0.2 | 20 | 13.1707 | 21.2251 | 3.3714 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 9730 | 0.6 | 6.6667 | 15 | 24.7628 | 2.6517 | 7.1111 | 0.6 | 8.3333 | 0.1 | 20 | 35
| 9731 | 0.6 | 6.6667 | 9 | 16.2907 | 2.6077 | 4.6829 | 0.6 | 8.3333 | 0.2 | 10 | 25
| 9732 | 1.2 | 3.3333 | 13.5 | 20.1609 | 2.9686 | 3.6923 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 9733 | 0.8 | 5 | 9.4737 | 16.6408 | 2.4842 | 4.6829 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9734 | 0.8 | 5 | 17.4194 | 26.9672 | 3.9008 | 5.6471 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9735 | 0.2 | 20 | 14.2105 | 21.5028 | 3.0256 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 9736 | 0.4 | 10 | 10.8 | 18.0205 | 2.4205 | 4.8 | 0.6 | 8.3333 | 0.2 | 10 | 28.3333
| 9737 | 1 | 4 | 11.7391 | 18.6708 | 2.9317 | 4 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 9738 | 1 | 4 | 11.25 | 18.8471 | 3.0256 | 4.5714 | 1 | 5 | 0.4 | 5 | 14
| 9739 | 0.6 | 6.6667 | 13.5 | 21.7541 | 3.0649 | 5.1892 | 1 | 5 | 0.4 | 5 | 16.6667
| 9740 | 0.8 | 5 | 15 | 23.4205 | 2.4205 | 6 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9741 | 0.8 | 5 | 11.0204 | 18.753 | 2.8095 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9742 | 0.8 | 5 | 17.4194 | 25.0289 | 2.8095 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 9743 | 0.8 | 5 | 9.8182 | 17.8099 | 3.4203 | 4.5714 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 9744 | 0.8 | 5 | 9 | 14.814 | 2.4456 | 3.3684 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 9745 | 0.8 | 5 | 13.1707 | 19.5182 | 3.3475 | 3 | 0.6 | 8.3333 | 0.6 | 3.3333 | 16.6667
| 9746 | 0.4 | 10 | 7.8261 | 15.9195 | 2.6077 | 5.4857 | 1 | 5 | 0.4 | 5 | 20
| 9747 | 1.2 | 3.3333 | 10.1887 | 18.0042 | 3.5489 | 4.2667 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 9748 | 1 | 4 | 10.3846 | 17.7163 | 2.7602 | 4.5714 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 9749 | 1 | 4 | 7.7143 | 16.2586 | 4.3704 | 4.1739 | 1 | 5 | 0.2 | 10 | 19
| 9750 | 0.8 | 5 | 8.5714 | 17.0303 | 3.6589 | 4.8 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9751 | 1 | 4 | 12 | 18.7602 | 2.7602 | 4 | 1 | 5 | 0.2 | 10 | 19
| 9752 | 1 | 4 | 12 | 18.3243 | 2.8957 | 3.4286 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 9753 | 1 | 4 | 16.3636 | 25.1565 | 2.7929 | 6 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 9754 | 0.4 | 10 | 10.8 | 18.476 | 3.2109 | 4.4651 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 9755 | 0.8 | 5 | 9.1525 | 16.7158 | 2.5106 | 5.0526 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 9756 | 0.6 | 6.6667 | 16.875 | 23.6857 | 3.2552 | 3.5556 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 9757 | 0.6 | 6.6667 | 8.5714 | 16.0321 | 2.5376 | 4.9231 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 9758 | 1.4 | 2.8571 | 12 | 18.2528 | 3.1053 | 3.1475 | 1.4 | 3.5714 | 0.2 | 10 | 16.4286
| 9759 | 1 | 4 | 11.4894 | 17.602 | 2.7442 | 3.3684 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 9760 | 0.8 | 5 | 9 | 15.5376 | 2.5376 | 4 | 1 | 5 | 1 | 2 | 12
| 9761 | 1.2 | 3.3333 | 14.5946 | 21.8535 | 3.085 | 4.1739 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 9762 | 1 | 4 | 19.2857 | 28.2297 | 3.1258 | 5.8182 | 1 | 5 | 0.4 | 5 | 14
| 9763 | 0.8 | 5 | 9.4737 | 16.1743 | 2.8606 | 3.84 | 1 | 5 | 0.4 | 5 | 15
| 9764 | 0.8 | 5 | 13.5 | 20.6892 | 3.1892 | 4 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 9765 | 0.8 | 5 | 14.5946 | 21.9924 | 2.8263 | 4.5714 | 1.4 | 3.5714 | 0.1 | 20 | 28.5714
| 9766 | 0.4 | 10 | 15.8824 | 21.7315 | 3.0256 | 2.8235 | 1.2 | 4.1667 | 0.8 | 2.5 | 16.6667
| 9767 | 1.4 | 2.8571 | 7.8261 | 16.3109 | 2.6667 | 5.8182 | 0.4 | 12.5 | 0.4 | 5 | 20.3571
| 9768 | 0.8 | 5 | 16.3636 | 25.6558 | 3.8065 | 5.4857 | 1 | 5 | 0.4 | 5 | 15
| 9769 | 0.8 | 5 | 9.8182 | 18.9347 | 3.6308 | 5.4857 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 9770 | 1 | 4 | 10.3846 | 19.8934 | 2.6517 | 6.8571 | 1.4 | 3.5714 | 0.2 | 10 | 17.5714
| 9771 | 1 | 4 | 12 | 17.8617 | 2.5514 | 3.3103 | 1.4 | 3.5714 | 0.1 | 20 | 27.5714
| 9772 | 0.8 | 5 | 10 | 17.2342 | 4.0342 | 3.2 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 9773 | 1 | 4 | 13.5 | 21.4569 | 2.4712 | 5.4857 | 1 | 5 | 0.4 | 5 | 14
| 9774 | 0.6 | 6.6667 | 10.8 | 18.8489 | 3.1258 | 4.9231 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 9775 | 0.8 | 5 | 9 | 17.042 | 3.4706 | 4.5714 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9776 | 0.6 | 6.6667 | 10.1887 | 16.8251 | 2.5514 | 4.0851 | 1 | 5 | 0.4 | 5 | 16.6667
| 9777 | 1 | 4 | 7.2973 | 13.3757 | 2.3137 | 3.7647 | 1 | 5 | 0.4 | 5 | 14
| 9778 | 1.2 | 3.3333 | 12.2727 | 18.8263 | 2.0885 | 4.4651 | 1 | 5 | 0.4 | 5 | 13.3333
| 9779 | 0.6 | 6.6667 | 13.5 | 23.3953 | 2.5106 | 7.3846 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 9780 | 0.8 | 5 | 14.5946 | 22.7525 | 3.1053 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 9781 | 0.8 | 5 | 15.8824 | 25.6584 | 3.776 | 6 | 1 | 5 | 0.2 | 10 | 20
| 9782 | 0.4 | 10 | 10.1887 | 17.2238 | 2.95 | 4.0851 | 1 | 5 | 0.1 | 20 | 35
| 9783 | 1.4 | 2.8571 | 9.3103 | 15.9509 | 3.085 | 3.5556 | 1.2 | 4.1667 | 0.2 | 10 | 17.0238
| 9784 | 0.6 | 6.6667 | 13.1707 | 20.9702 | 2.3137 | 5.4857 | 0.4 | 12.5 | 0.4 | 5 | 24.1667
| 9785 | 0.8 | 5 | 9.1525 | 16.8966 | 3.6589 | 4.0851 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 9786 | 1 | 4 | 15.4286 | 22.3024 | 3.4453 | 3.4286 | 1 | 5 | 0.2 | 10 | 19
| 9787 | 1 | 4 | 15.8824 | 25.4047 | 3.5224 | 6 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 9788 | 0.4 | 10 | 10.1887 | 21.6443 | 2.7283 | 8.7273 | 1 | 5 | 0.6 | 3.3333 | 18.3333
| 9789 | 0.6 | 6.6667 | 8.7097 | 18.3488 | 6.2105 | 3.4286 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 9790 | 0.2 | 20 | 16.3636 | 24.0417 | 2.878 | 4.8 | 1 | 5 | 0.2 | 10 | 35
| 9791 | 0.6 | 6.6667 | 12.5581 | 20.1552 | 3.0256 | 4.5714 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 9792 | 1 | 4 | 13.5 | 19.9832 | 2.8606 | 3.6226 | 1 | 5 | 0.2 | 10 | 19
| 9793 | 1.2 | 3.3333 | 10.3846 | 20.7378 | 2.9686 | 7.3846 | 0.6 | 8.3333 | 0.4 | 5 | 16.6667
| 9794 | 0.8 | 5 | 10.5882 | 20.0184 | 2.8095 | 6.6207 | 0.2 | 25 | 0.4 | 5 | 35
| 9795 | 1 | 4 | 12.5581 | 22.0685 | 4.177 | 5.3333 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 9796 | 0.8 | 5 | 10.8 | 19.0716 | 3.8065 | 4.4651 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 9797 | 1 | 4 | 10.3846 | 19.4045 | 2.8263 | 6.1935 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 9798 | 0.6 | 6.6667 | 10.5882 | 19.6415 | 4.3704 | 4.6829 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 9799 | 0.8 | 5 | 12.5581 | 19.7593 | 4.1043 | 3.0968 | 1 | 5 | 0.2 | 10 | 20
| 9800 | 0.4 | 10 | 12.5581 | 20.2185 | 2.4712 | 5.1892 | 0.8 | 6.25 | 0.1 | 20 | 36.25
| 9801 | 0.8 | 5 | 11.25 | 20.5906 | 3.5224 | 5.8182 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9802 | 0.8 | 5 | 10.8 | 16.4667 | 2.6667 | 3 | 1 | 5 | 0.1 | 20 | 30
| 9803 | 0.8 | 5 | 15.8824 | 25.0501 | 3.1678 | 6 | 1 | 5 | 0.2 | 10 | 20
| 9804 | 0.2 | 20 | 14.5946 | 24.0202 | 3.0256 | 6.4 | 1.4 | 3.5714 | 0.6 | 3.3333 | 26.9048
| 9805 | 1.2 | 3.3333 | 11.4894 | 18.6207 | 3.5758 | 3.5556 | 0.4 | 12.5 | 0.1 | 20 | 35.8333
| 9806 | 0.8 | 5 | 11.4894 | 21.0601 | 2.95 | 6.6207 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 9807 | 1.2 | 3.3333 | 9.3103 | 15.7637 | 3.085 | 3.3684 | 0.8 | 6.25 | 0.4 | 5 | 14.5833
| 9808 | 0.8 | 5 | 19.2857 | 24.8424 | 2.3024 | 3.2542 | 1.4 | 3.5714 | 0.1 | 20 | 28.5714
| 9809 | 0.6 | 6.6667 | 13.1707 | 21.2135 | 3.8689 | 4.1739 | 1.2 | 4.1667 | 0.6 | 3.3333 | 14.1667
| 9810 | 1 | 4 | 10.5882 | 20.2143 | 4.1404 | 5.4857 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 9811 | 0.6 | 6.6667 | 11.7391 | 19.641 | 2.7126 | 5.1892 | 1 | 5 | 0.2 | 10 | 21.6667
| 9812 | 0.4 | 10 | 10.8 | 16.7761 | 2.4205 | 3.5556 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 9813 | 0.8 | 5 | 11.4894 | 18.086 | 3.6875 | 2.9091 | 1.6 | 3.125 | 0.2 | 10 | 18.125
| 9814 | 1 | 4 | 11.7391 | 19.0077 | 2.6971 | 4.5714 | 1.4 | 3.5714 | 0.8 | 2.5 | 10.0714
| 9815 | 1.2 | 3.3333 | 10.5882 | 16.5425 | 3.0452 | 2.9091 | 1 | 5 | 0.2 | 10 | 18.3333
| 9816 | 0.8 | 5 | 12.2727 | 18.827 | 2.9317 | 3.6226 | 1 | 5 | 1 | 2 | 12
| 9817 | 0.6 | 6.6667 | 10 | 19.2141 | 2.5934 | 6.6207 | 0.4 | 12.5 | 0.6 | 3.3333 | 22.5
| 9818 | 1 | 4 | 18 | 24.8684 | 2.95 | 3.9184 | 1 | 5 | 0.8 | 2.5 | 11.5
| 9819 | 0.4 | 10 | 12 | 18.9342 | 3.8374 | 3.0968 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 9820 | 1 | 4 | 10.5882 | 19.4462 | 3.2109 | 5.6471 | 0.6 | 8.3333 | 0.6 | 3.3333 | 15.6667
| 9821 | 0.8 | 5 | 9.8182 | 17.9261 | 2.6222 | 5.4857 | 1 | 5 | 0.2 | 10 | 20
| 9822 | 0.8 | 5 | 8.7097 | 15.4628 | 2.5792 | 4.1739 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9823 | 0.8 | 5 | 16.875 | 23.9179 | 2.36 | 4.6829 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 9824 | 1.2 | 3.3333 | 10.8 | 16.9216 | 3.1678 | 2.9538 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 9825 | 1 | 4 | 9.8182 | 17.8772 | 3.0064 | 5.0526 | 1 | 5 | 0.2 | 10 | 19
| 9826 | 1.2 | 3.3333 | 15.4286 | 25.6912 | 2.878 | 7.3846 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 9827 | 0.4 | 10 | 18.6207 | 28.7638 | 3.5224 | 6.6207 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 9828 | 0.8 | 5 | 12.5581 | 20.6279 | 3.1467 | 4.9231 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 9829 | 0.8 | 5 | 10.5882 | 16.5122 | 2.7765 | 3.1475 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9830 | 0.8 | 5 | 10.8 | 17.9293 | 3.2109 | 3.9184 | 1.6 | 3.125 | 0.4 | 5 | 13.125
| 9831 | 0.2 | 20 | 10.8 | 17.2778 | 3.2778 | 3.2 | 1 | 5 | 0.4 | 5 | 30
| 9832 | 1.4 | 2.8571 | 16.875 | 22.9392 | 2.3719 | 3.6923 | 0.8 | 6.25 | 0.4 | 5 | 14.1071
| 9833 | 0.6 | 6.6667 | 11.4894 | 17.0834 | 2.7283 | 2.8657 | 1 | 5 | 0.4 | 5 | 16.6667
| 9834 | 0.8 | 5 | 9.8182 | 19.5238 | 3.085 | 6.6207 | 1 | 5 | 0.4 | 5 | 15
| 9835 | 0.6 | 6.6667 | 12.8571 | 19.4739 | 3.1258 | 3.4909 | 1.6 | 3.125 | 0.4 | 5 | 14.7917
| 9836 | 0.8 | 5 | 15.8824 | 23.0447 | 2.8957 | 4.2667 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 9837 | 1 | 4 | 13.1707 | 21.4449 | 3.085 | 5.1892 | 0.8 | 6.25 | 0.6 | 3.3333 | 13.5833
| 9838 | 0.2 | 20 | 9.8182 | 19.6498 | 3.2109 | 6.6207 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 9839 | 1 | 4 | 7.9412 | 14.4812 | 3.7165 | 2.8235 | 1.2 | 4.1667 | 0.1 | 20 | 28.1667
| 9840 | 0.8 | 5 | 12.8571 | 18.9637 | 3.3239 | 2.7826 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 9841 | 0.4 | 10 | 11.25 | 19.5989 | 3.5489 | 4.8 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 9842 | 1.8 | 2.2222 | 10.1887 | 19.6374 | 3.2552 | 6.1935 | 1.4 | 3.5714 | 0.6 | 3.3333 | 9.127
| 9843 | 1.2 | 3.3333 | 10.8 | 18.2594 | 2.7765 | 4.6829 | 1.2 | 4.1667 | 0.8 | 2.5 | 10
| 9844 | 0.4 | 10 | 9.1525 | 15.5477 | 3.3475 | 3.0476 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 9845 | 1.2 | 3.3333 | 16.875 | 24.4201 | 4.2909 | 3.2542 | 0.8 | 6.25 | 0.2 | 10 | 19.5833
| 9846 | 1 | 4 | 14.2105 | 21.6426 | 2.8606 | 4.5714 | 1 | 5 | 0.2 | 10 | 19
| 9847 | 0.6 | 6.6667 | 12.2727 | 18.2167 | 3.6308 | 2.3133 | 1.4 | 3.5714 | 0.2 | 10 | 20.2381
| 9848 | 0.8 | 5 | 12.2727 | 20.6423 | 2.5514 | 5.8182 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 9849 | 0.6 | 6.6667 | 12 | 18.4329 | 3.2329 | 3.2 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 9850 | 0.8 | 5 | 8.8525 | 14.5009 | 2.0258 | 3.6226 | 0.6 | 8.3333 | 0.2 | 10 | 23.3333
| 9851 | 1 | 4 | 15 | 21.0161 | 2.0978 | 3.9184 | 1 | 5 | 0.8 | 2.5 | 11.5
| 9852 | 1.2 | 3.3333 | 7.8261 | 14.6031 | 2.2056 | 4.5714 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 9853 | 1 | 4 | 15 | 21.7602 | 2.7602 | 4 | 1 | 5 | 0.8 | 2.5 | 11.5
| 9854 | 0.6 | 6.6667 | 11.7391 | 19.4354 | 3.5224 | 4.1739 | 1.4 | 3.5714 | 0.6 | 3.3333 | 13.5714
| 9855 | 0.4 | 10 | 9.3103 | 15.2874 | 2.6667 | 3.3103 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 9856 | 0.8 | 5 | 8.0597 | 15.826 | 2.433 | 5.3333 | 1 | 5 | 0.2 | 10 | 20
| 9857 | 0.8 | 5 | 11.4894 | 17.4958 | 2.3838 | 3.6226 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 9858 | 0.8 | 5 | 14.5946 | 21.8299 | 3.4706 | 3.7647 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 9859 | 0.8 | 5 | 13.1707 | 22.276 | 3.1053 | 6 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 9860 | 0.8 | 5 | 14.2105 | 24.3875 | 4.177 | 6 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 9861 | 0.2 | 20 | 15.4286 | 22.6491 | 2.5376 | 4.6829 | 0.8 | 6.25 | 0.4 | 5 | 31.25
| 9862 | 1 | 4 | 9.4737 | 15.9397 | 2.8434 | 3.6226 | 1.6 | 3.125 | 0.4 | 5 | 12.125
| 9863 | 1 | 4 | 11.4894 | 18.5946 | 3.1053 | 4 | 1 | 5 | 0.4 | 5 | 14
| 9864 | 1 | 4 | 10.5882 | 18.698 | 2.7765 | 5.3333 | 0.6 | 8.3333 | 0.2 | 10 | 22.3333
| 9865 | 1 | 4 | 10.1887 | 15.2567 | 2.3251 | 2.7429 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 9866 | 1 | 4 | 11.7391 | 18.5499 | 2.6369 | 4.1739 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 9867 | 1.2 | 3.3333 | 15 | 23.9563 | 3.4706 | 5.4857 | 1 | 5 | 0.4 | 5 | 13.3333
| 9868 | 0.8 | 5 | 9.4737 | 14.9423 | 2.3719 | 3.0968 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 9869 | 0.4 | 10 | 15.4286 | 26.7828 | 3.0064 | 8.3478 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 9870 | 1 | 4 | 12.5581 | 18.142 | 2.3838 | 3.2 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 9871 | 0.2 | 20 | 8.4375 | 14.4078 | 2.2056 | 3.7647 | 1.4 | 3.5714 | 0.6 | 3.3333 | 26.9048
| 9872 | 1 | 4 | 12.2727 | 19.7222 | 2.878 | 4.5714 | 1 | 5 | 0.2 | 10 | 19
| 9873 | 1.2 | 3.3333 | 20 | 26.6786 | 2.7602 | 3.9184 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 9874 | 0.4 | 10 | 13.8462 | 22.0173 | 2.5241 | 5.6471 | 1 | 5 | 0.4 | 5 | 20
| 9875 | 0.6 | 6.6667 | 11.25 | 18.6014 | 2.5514 | 4.8 | 0.6 | 8.3333 | 0.1 | 20 | 35
| 9876 | 1 | 4 | 14.5946 | 21.9554 | 2.8957 | 4.4651 | 1 | 5 | 0.1 | 20 | 29
| 9877 | 0.4 | 10 | 15.4286 | 22.8598 | 4.177 | 3.2542 | 1 | 5 | 0.4 | 5 | 20
| 9878 | 0.8 | 5 | 11.7391 | 19.7005 | 3.4963 | 4.4651 | 1 | 5 | 0.2 | 10 | 20
| 9879 | 1 | 4 | 11.25 | 17.9464 | 2.9317 | 3.7647 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.9048
| 9880 | 0.8 | 5 | 13.8462 | 21.1641 | 3.2329 | 4.0851 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9881 | 1 | 4 | 15.4286 | 22.5558 | 2.8606 | 4.2667 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 9882 | 1.2 | 3.3333 | 12.8571 | 21.6095 | 3.1053 | 5.6471 | 0.6 | 8.3333 | 0.2 | 10 | 21.6667
| 9883 | 1 | 4 | 12.8571 | 20.4302 | 2.3838 | 5.1892 | 1 | 5 | 0.4 | 5 | 14
| 9884 | 0.2 | 20 | 15.4286 | 23.8065 | 3.8065 | 4.5714 | 0.8 | 6.25 | 0.6 | 3.3333 | 29.5833
| 9885 | 0.6 | 6.6667 | 11.4894 | 17.2196 | 2.9873 | 2.7429 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 9886 | 0.8 | 5 | 12.2727 | 21.5601 | 2.6667 | 6.6207 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9887 | 1.2 | 3.3333 | 11.0204 | 16.8963 | 2.7283 | 3.1475 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 9888 | 0.6 | 6.6667 | 15.4286 | 22.6866 | 2.7929 | 4.4651 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 9889 | 0.8 | 5 | 12 | 18.6608 | 3.1053 | 3.5556 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9890 | 0.6 | 6.6667 | 12 | 19.4595 | 2.1261 | 5.3333 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 9891 | 1 | 4 | 15.4286 | 23.3619 | 2.7442 | 5.1892 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 9892 | 0.2 | 20 | 16.3636 | 27.3849 | 5.0213 | 6 | 0.8 | 6.25 | 0.8 | 2.5 | 28.75
| 9893 | 0.8 | 5 | 11.4894 | 17.5959 | 3.3239 | 2.7826 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 9894 | 0.6 | 6.6667 | 11.4894 | 20.0828 | 2.5934 | 6 | 0.6 | 8.3333 | 0.4 | 5 | 20
| 9895 | 0.6 | 6.6667 | 10 | 16.0434 | 2.8434 | 3.2 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 9896 | 1.2 | 3.3333 | 9.1525 | 16.3024 | 3.6589 | 3.4909 | 1 | 5 | 0.2 | 10 | 18.3333
| 9897 | 0.6 | 6.6667 | 12.5581 | 19.5884 | 2.6667 | 4.3636 | 0.8 | 6.25 | 0.4 | 5 | 17.9167
| 9898 | 0.8 | 5 | 9.4737 | 17.3691 | 3.3239 | 4.5714 | 1.2 | 4.1667 | 0.1 | 20 | 29.1667
| 9899 | 0.4 | 10 | 12.2727 | 18.9335 | 3.1053 | 3.5556 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 9900 | 1 | 4 | 12 | 19.0596 | 2.7929 | 4.2667 | 0.4 | 12.5 | 0.2 | 10 | 26.5
| 9901 | 1 | 4 | 10.3846 | 18.5802 | 3.0064 | 5.1892 | 1 | 5 | 0.4 | 5 | 14
| 9902 | 0.8 | 5 | 9.4737 | 15.5159 | 2.5514 | 3.4909 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 9903 | 0.8 | 5 | 10.1887 | 18.4593 | 3.4706 | 4.8 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9904 | 1 | 4 | 13.1707 | 23.199 | 2.3483 | 7.68 | 1 | 5 | 0.2 | 10 | 19
| 9905 | 0.8 | 5 | 12.2727 | 20.8792 | 3.8065 | 4.8 | 1 | 5 | 0.8 | 2.5 | 12.5
| 9906 | 0.8 | 5 | 12.8571 | 19.3933 | 3.1678 | 3.3684 | 1 | 5 | 0.2 | 10 | 20
| 9907 | 0.8 | 5 | 13.1707 | 19.495 | 2.8957 | 3.4286 | 1.4 | 3.5714 | 0.1 | 20 | 28.5714
| 9908 | 0.6 | 6.6667 | 12 | 19.8188 | 2.8957 | 4.9231 | 1.2 | 4.1667 | 0.1 | 20 | 30.8333
| 9909 | 0.6 | 6.6667 | 12.8571 | 20.4668 | 2.4205 | 5.1892 | 0.8 | 6.25 | 0.1 | 20 | 32.9167
| 9910 | 1.6 | 2.5 | 13.5 | 25.7236 | 3.4963 | 8.7273 | 1.6 | 3.125 | 0.8 | 2.5 | 8.125
| 9911 | 0.6 | 6.6667 | 13.1707 | 24.0516 | 3.4963 | 7.3846 | 1.4 | 3.5714 | 0.1 | 20 | 30.2381
| 9912 | 1.2 | 3.3333 | 10.5882 | 17.1566 | 2.7283 | 3.84 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 9913 | 0.6 | 6.6667 | 11.25 | 18.5181 | 3.5758 | 3.6923 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 9914 | 0.8 | 5 | 13.1707 | 20.7381 | 3.3007 | 4.2667 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 9915 | 0.1 | 40 | 9.8182 | 17.3815 | 2.5106 | 5.0526 | 0.8 | 6.25 | 0.4 | 5 | 51.25
| 9916 | 0.8 | 5 | 10.3846 | 18.049 | 3.746 | 3.9184 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 9917 | 1.2 | 3.3333 | 7.8261 | 13.637 | 2.9873 | 2.8235 | 1.2 | 4.1667 | 0.6 | 3.3333 | 10.8333
| 9918 | 0.2 | 20 | 15 | 22.886 | 3.5224 | 4.3636 | 1 | 5 | 0.2 | 10 | 35
| 9919 | 1.2 | 3.3333 | 13.5 | 22.4934 | 2.5934 | 6.4 | 1 | 5 | 0.6 | 3.3333 | 11.6667
| 9920 | 0.4 | 10 | 15.4286 | 21.5698 | 2.7126 | 3.4286 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 9921 | 0.8 | 5 | 16.875 | 22.9678 | 3.0452 | 3.0476 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 9922 | 0.6 | 6.6667 | 13.1707 | 25.2351 | 3.7165 | 8.3478 | 0.8 | 6.25 | 0.6 | 3.3333 | 16.25
| 9923 | 0.4 | 10 | 14.2105 | 22.1634 | 4.3303 | 3.6226 | 1.2 | 4.1667 | 0.4 | 5 | 19.1667
| 9924 | 0.8 | 5 | 9.6429 | 16.6262 | 3.0649 | 3.9184 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 9925 | 1 | 4 | 22.5 | 28.3408 | 2.9317 | 2.9091 | 1 | 5 | 0.4 | 5 | 14
| 9926 | 0.4 | 10 | 12 | 20.6535 | 3.1678 | 5.4857 | 1 | 5 | 0.8 | 2.5 | 17.5
| 9927 | 0.6 | 6.6667 | 7.9412 | 15.1765 | 3.4706 | 3.7647 | 1.6 | 3.125 | 0.6 | 3.3333 | 13.125
| 9928 | 0.6 | 6.6667 | 15 | 28.5008 | 3.9008 | 9.6 | 0.6 | 8.3333 | 0.8 | 2.5 | 17.5
| 9929 | 0.2 | 20 | 15 | 26.0444 | 3.9333 | 7.1111 | 1.2 | 4.1667 | 0.2 | 10 | 34.1667
| 9930 | 0.8 | 5 | 11.0204 | 19.5693 | 3.4963 | 5.0526 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 9931 | 0.8 | 5 | 12.5581 | 19.6771 | 3.4963 | 3.6226 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 9932 | 1 | 4 | 10.5882 | 18.0568 | 4.2143 | 3.2542 | 1 | 5 | 0.2 | 10 | 19
| 9933 | 1.2 | 3.3333 | 8.7097 | 14.5763 | 2.6667 | 3.2 | 1.2 | 4.1667 | 0.2 | 10 | 17.5
| 9934 | 0.4 | 10 | 8.8525 | 16.7683 | 3.2329 | 4.6829 | 1 | 5 | 0.2 | 10 | 25
| 9935 | 0.4 | 10 | 12.2727 | 21.7441 | 3.2778 | 6.1935 | 0.6 | 8.3333 | 0.4 | 5 | 23.3333
| 9936 | 1.2 | 3.3333 | 11.25 | 23.6936 | 3.3007 | 9.1429 | 1.4 | 3.5714 | 0.6 | 3.3333 | 10.2381
| 9937 | 0.6 | 6.6667 | 11.0204 | 21.5334 | 2.1651 | 8.3478 | 1.2 | 4.1667 | 0.4 | 5 | 15.8333
| 9938 | 1 | 4 | 15 | 21.8273 | 2.9873 | 3.84 | 1.2 | 4.1667 | 0.6 | 3.3333 | 11.5
| 9939 | 0.4 | 10 | 12 | 19.0724 | 2.9873 | 4.0851 | 0.2 | 25 | 0.6 | 3.3333 | 38.3333
| 9940 | 1 | 4 | 12 | 18.2029 | 3.4203 | 2.7826 | 0.6 | 8.3333 | 0.4 | 5 | 17.3333
| 9941 | 0.8 | 5 | 12 | 19.9542 | 3.6875 | 4.2667 | 0.8 | 6.25 | 0.4 | 5 | 16.25
| 9942 | 0.8 | 5 | 10.1887 | 19.4216 | 3.2329 | 6 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9943 | 0.2 | 20 | 12.5581 | 18.8735 | 3.1678 | 3.1475 | 0.8 | 6.25 | 0.2 | 10 | 36.25
| 9944 | 1 | 4 | 11.0204 | 18.4876 | 3.5489 | 3.9184 | 1 | 5 | 0.2 | 10 | 19
| 9945 | 1 | 4 | 9.3103 | 17.0027 | 4 | 3.6923 | 1 | 5 | 0.1 | 20 | 29
| 9946 | 0.8 | 5 | 15.8824 | 21.4403 | 2.2476 | 3.3103 | 1.4 | 3.5714 | 0.2 | 10 | 18.5714
| 9947 | 0.6 | 6.6667 | 12.8571 | 19.2441 | 2.6222 | 3.7647 | 1 | 5 | 0.6 | 3.3333 | 15
| 9948 | 1.4 | 2.8571 | 8.7097 | 16.0576 | 2.7765 | 4.5714 | 1 | 5 | 0.8 | 2.5 | 10.3571
| 9949 | 0.8 | 5 | 10.5882 | 29.4839 | 2.8957 | 16 | 0.4 | 12.5 | 0.6 | 3.3333 | 20.8333
| 9950 | 0.8 | 5 | 15 | 21.8273 | 2.9873 | 3.84 | 1.2 | 4.1667 | 0.2 | 10 | 19.1667
| 9951 | 0.4 | 10 | 9.4737 | 16.0496 | 3.085 | 3.4909 | 1.4 | 3.5714 | 0.4 | 5 | 18.5714
| 9952 | 0.6 | 6.6667 | 12.2727 | 21.5258 | 2.3959 | 6.8571 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 9953 | 1 | 4 | 9 | 17.3137 | 3.6308 | 4.6829 | 1.2 | 4.1667 | 0.4 | 5 | 13.1667
| 9954 | 0.8 | 5 | 15 | 20.8756 | 2.5652 | 3.3103 | 0.6 | 8.3333 | 0.8 | 2.5 | 15.8333
| 9955 | 0.4 | 10 | 11.7391 | 17.6679 | 3.1053 | 2.8235 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 9956 | 0.8 | 5 | 11.7391 | 21.1862 | 2.8263 | 6.6207 | 1.4 | 3.5714 | 0.4 | 5 | 13.5714
| 9957 | 0.4 | 10 | 15.4286 | 21.3779 | 3.1258 | 2.8235 | 1.2 | 4.1667 | 0.6 | 3.3333 | 17.5
| 9958 | 0.6 | 6.6667 | 11.4894 | 20.7235 | 3.9008 | 5.3333 | 0.6 | 8.3333 | 0.8 | 2.5 | 17.5
| 9959 | 0.6 | 6.6667 | 16.3636 | 24.6226 | 3.6875 | 4.5714 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 9960 | 1 | 4 | 12 | 17.6344 | 2.5376 | 3.0968 | 1.4 | 3.5714 | 0.1 | 20 | 27.5714
| 9961 | 0.6 | 6.6667 | 16.3636 | 24.694 | 3.2778 | 5.0526 | 0.6 | 8.3333 | 0.6 | 3.3333 | 18.3333
| 9962 | 0.8 | 5 | 14.5946 | 21.3711 | 2.7765 | 4 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 9963 | 0.4 | 10 | 13.1707 | 20.9883 | 2.4842 | 5.3333 | 0.8 | 6.25 | 0.4 | 5 | 21.25
| 9964 | 0.8 | 5 | 15.8824 | 23.7928 | 2.9873 | 4.9231 | 1 | 5 | 0.6 | 3.3333 | 13.3333
| 9965 | 1 | 4 | 12 | 21.7277 | 4.5385 | 5.1892 | 1 | 5 | 0.6 | 3.3333 | 12.3333
| 9966 | 0.8 | 5 | 8.8525 | 15.3887 | 2.9136 | 3.6226 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 9967 | 0.8 | 5 | 8.1818 | 16.6717 | 3.3007 | 5.1892 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 9968 | 0.4 | 10 | 10.1887 | 19.5081 | 3.1258 | 6.1935 | 1 | 5 | 0.2 | 10 | 25
| 9969 | 0.6 | 6.6667 | 13.8462 | 22.2532 | 4.1404 | 4.2667 | 1.2 | 4.1667 | 0.2 | 10 | 20.8333
| 9970 | 0.4 | 10 | 11.7391 | 18.4849 | 4.2523 | 2.4935 | 1 | 5 | 0.2 | 10 | 25
| 9971 | 1 | 4 | 15.8824 | 21.9473 | 3.0649 | 3 | 1 | 5 | 0.1 | 20 | 29
| 9972 | 0.8 | 5 | 20 | 27.1863 | 3.6308 | 3.5556 | 0.8 | 6.25 | 0.2 | 10 | 21.25
| 9973 | 0.8 | 5 | 11.25 | 17.9679 | 3.0256 | 3.6923 | 0.8 | 6.25 | 0.1 | 20 | 31.25
| 9974 | 1.2 | 3.3333 | 12.8571 | 20.7729 | 3.2329 | 4.6829 | 1 | 5 | 0.4 | 5 | 13.3333
| 9975 | 0.8 | 5 | 11.25 | 16.1445 | 2.7126 | 2.1818 | 1 | 5 | 0.4 | 5 | 15
| 9976 | 0.8 | 5 | 9.1525 | 16.6042 | 2.6517 | 4.8 | 1.2 | 4.1667 | 0.6 | 3.3333 | 12.5
| 9977 | 0.4 | 10 | 12 | 19.0875 | 2.9136 | 4.1739 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 9978 | 0.4 | 10 | 21.6 | 28.617 | 2.4456 | 4.5714 | 1.2 | 4.1667 | 0.2 | 10 | 24.1667
| 9979 | 0.8 | 5 | 11.7391 | 19.8069 | 3.4963 | 4.5714 | 0.8 | 6.25 | 0.8 | 2.5 | 13.75
| 9980 | 0.2 | 20 | 11.25 | 19.6437 | 3.4706 | 4.9231 | 1.2 | 4.1667 | 0.8 | 2.5 | 26.6667
| 9981 | 1 | 4 | 14.5946 | 19.812 | 2.9317 | 2.2857 | 0.8 | 6.25 | 0.2 | 10 | 20.25
| 9982 | 0.6 | 6.6667 | 21.6 | 28.6078 | 3.1678 | 3.84 | 1.4 | 3.5714 | 0.4 | 5 | 15.2381
| 9983 | 1.2 | 3.3333 | 10.5882 | 16.8213 | 3.3239 | 2.9091 | 0.8 | 6.25 | 0.6 | 3.3333 | 12.9167
| 9984 | 0.4 | 10 | 13.5 | 21.9386 | 3.1053 | 5.3333 | 0.6 | 8.3333 | 0.6 | 3.3333 | 21.6667
| 9985 | 0.6 | 6.6667 | 12.5581 | 19.7651 | 2.5241 | 4.6829 | 1 | 5 | 0.4 | 5 | 16.6667
| 9986 | 0.8 | 5 | 15.8824 | 22.1174 | 2.7442 | 3.4909 | 0.8 | 6.25 | 0.6 | 3.3333 | 14.5833
| 9987 | 0.8 | 5 | 10.5882 | 17.3655 | 2.5106 | 4.2667 | 1.2 | 4.1667 | 0.4 | 5 | 14.1667
| 9988 | 0.8 | 5 | 13.8462 | 26.074 | 3.085 | 9.1429 | 1 | 5 | 0.4 | 5 | 15
| 9989 | 0.6 | 6.6667 | 6.8354 | 14.1314 | 3.2109 | 4.0851 | 1 | 5 | 0.8 | 2.5 | 14.1667
| 9990 | 0.4 | 10 | 13.1707 | 21.1877 | 4.2523 | 3.7647 | 1.4 | 3.5714 | 0.6 | 3.3333 | 16.9048
| 9991 | 1.2 | 3.3333 | 9.8182 | 18.5229 | 3.3714 | 5.3333 | 1 | 5 | 0.8 | 2.5 | 10.8333
| 9992 | 0.2 | 20 | 10.8 | 16.6818 | 2.6818 | 3.2 | 1 | 5 | 0.6 | 3.3333 | 28.3333
| 9993 | 1.4 | 2.8571 | 12.8571 | 19.3707 | 3.085 | 3.4286 | 1.2 | 4.1667 | 0.8 | 2.5 | 9.5238
| 9994 | 1.6 | 2.5 | 12.2727 | 18.2656 | 2.7929 | 3.2 | 1 | 5 | 0.2 | 10 | 17.5
| 9995 | 1.4 | 2.8571 | 13.8462 | 21.1436 | 3.8689 | 3.4286 | 1 | 5 | 0.2 | 10 | 17.8571
| 9996 | 0.6 | 6.6667 | 11.4894 | 21.2958 | 3.8065 | 6 | 0.8 | 6.25 | 0.2 | 10 | 22.9167
| 9997 | 1 | 4 | 14.5946 | 21.3225 | 2.8095 | 3.9184 | 0.8 | 6.25 | 0.4 | 5 | 15.25
| 9998 | 1.4 | 2.8571 | 10.3846 | 16.1162 | 3.0649 | 2.6667 | 0.6 | 8.3333 | 0.4 | 5 | 16.1905
| 9999 | 1.2 | 3.3333 | 11.25 | 19.5963 | 2.8606 | 5.4857 | 1 | 5 | 0.2 | 10 | 18.3333
| 10000 | 1.2 | 3.3333 | 12.2727 | 21.1481 | 2.6818 | 6.1935 | 0.8 | 6.25 | 0.4 | 5 | 14.5833

## SIPmath Chart Data
| Avg_TH_Leg_2 | Avg_TH_Leg_1 | Avg_TH_Leg_3 | Resampled_TH_C | Delivery_time_C | Delivery_time_L1 | Project_Delivery_time_PLAN | Delivery_time_L2 | Delivery_time_L3 | Resampled_TH_A | Delivery_time_A | Resampled_TH_O | Delivery_time_O | Project_Delivery_time_ACTUAL
Expected Value | 2.7 | 0.42 | 1.41 | 0.8 | 7 | 13 | 20 | 3.1 | 4.7 | 1 | 6 | 0.41 | 6.8 | 19
Series Name | Avg_TH_Leg_2 Avg 2,7 | Avg_TH_Leg_1 Avg 0,42 | Avg_TH_Leg_3 Avg 1,41 | Resampled_TH_C Avg 0,8 | Delivery_time_C Avg 7 | Delivery_time_L1 Avg 13 | Project_Delivery_time_PLAN Avg 20 | Delivery_time_L2 Avg 3,1 | Delivery_time_L3 Avg 4,7 | Resampled_TH_A Avg 1 | Delivery_time_A Avg 6 | Resampled_TH_O Avg 0,41 | Delivery_time_O Avg 6,8 | Project_Delivery_time_ACTUAL Avg 19
Integer chart? | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Loss Exceedance | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Number of Bins | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Label position | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Bin Width | 0.4 | 0.08 | 0.31 | 0.19 | 4 | 4 | 4 | 0.5 | 2.3 | 0.19 | 5 | 0.09 | 1.8 | 7
Decimals | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 2 | 1 | 0
Scale | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Use Axis Title? | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Axis Title | Axis Title | Axis Title | Axis Title | Axis Title | Axis Title | Axis Title | Axis Title | Axis Title | Axis Title | Axis Title | Axis Title | Axis Title | Axis Title | Axis Title
Min | 1.3 | 0.13 | 0.25 | 0.1 | 2 | 6 | 12 | 1.8 | 1.8 | 0.1 | 3 | 0.1 | 2 | 8
Bin Range | 1.7 | 0.21 | 0.56 | 0.29 | 6 | 10 | 16 | 2.3 | 4.1 | 0.29 | 8 | 0.19 | 3.8 | 15
Frequency | 2.1 | 0.29 | 0.87 | 0.48 | 10 | 14 | 20 | 2.8 | 6.4 | 0.48 | 13 | 0.28 | 5.6 | 22
Labels | 2.5 | 0.37 | 1.18 | 0.67 | 14 | 18 | 24 | 3.3 | 8.7 | 0.67 | 18 | 0.37 | 7.4 | 29
Cumulative | 2.9 | 0.45 | 1.49 | 0.86 | 18 | 22 | 28 | 3.8 | 11 | 0.86 | 23 | 0.46 | 9.2 | 36
| 3.3 | 0.53 | 1.8 | 1.05 | 22 | 26 | 32 | 4.3 | 13.3 | 1.05 | 28 | 0.55 | 11 | 43
| 3.7 | 0.61 | 2.11 | 1.24 | 26 | 30 | 36 | 4.8 | 15.6 | 1.24 | 33 | 0.64 | 12.8 | 50
| 4.1 | 0.69 | 2.42 | 1.43 | 30 | 34 | 40 | 5.3 | 17.9 | 1.43 | 38 | 0.73 | 14.6 | 57
| 4.5 | 0.77 | 2.73 | 1.62 | 34 | 38 | 44 | 5.8 | 20.2 | 1.62 | 43 | 0.82 | 16.4 | 64
| 4.9 | 0.85 | 3.04 | 1.81 | 38 | 42 | 48 | 6.3 | 22.5 | 1.81 | 48 | 0.91 | 18.2 | 71
| 5.3 | 0.93 | 3.35 | 2 | 42 | 46 | 52 | 6.8 | 24.8 | 2 | 53 | 1 | 20 | 78
| 5.7 | 1.01 | 3.66 | 2.19 | 46 | 50 | 56 | 7.3 | 27.1 | 2.19 | 58 | 1.09 | 21.8 | 85
| 6.1 | 1.09 | 3.97 | 2.38 | 50 | 54 | 60 | 7.8 | 29.4 | 2.38 | 63 | 1.18 | 23.6 | 92
| 6.5 | 1.17 | 4.28 | 2.57 | 54 | 58 | 64 | 8.3 | 31.7 | 2.57 | 68 | 1.27 | 25.4 | 99
| 6.9 | 1.25 | 4.59 | 2.76 | 58 | 62 | 68 | 8.8 | 34 | 2.76 | 73 | 1.36 | 27.2 | 106
| 7.3 | 1.33 | 4.9 | 2.95 | 62 | 66 | 72 | 9.3 | 36.3 | 2.95 | 78 | 1.45 | 29 | 113
| 7.7 | 1.41 | 5.21 | 3.14 | 66 | 70 | 76 | 9.8 | 38.6 | 3.14 | 83 | 1.54 | 30.8 | 120
| 8.1 | 1.49 | 5.52 | 3.33 | 70 | 74 | 80 | 10.3 | 40.9 | 3.33 | 88 | 1.63 | 32.6 | 127
| 8.5 | 1.57 | 5.83 | 3.52 | 74 | 78 | 84 | 10.8 | 43.2 | 3.52 | 93 | 1.72 | 34.4 | 134
| 8.9 | 1.65 | 6.14 | 3.71 | 78 | 82 | 88 | 11.3 | 45.5 | 3.71 | 98 | 1.81 | 36.2 | 141
| 9.3 | 1.73 | 6.45 | 3.9 | 82 | 86 | 92 | 11.8 | 47.8 | 3.9 | 103 | 1.9 | 38 | 148
| 9.7 | 1.81 | 6.76 | 4.09 | 86 | 90 | 96 | 12.3 | 50.1 | 4.09 | 108 | 1.99 | 39.8 | 155
| 10.1 | 1.89 | 7.07 | 4.28 | 90 | 94 | 100 | 12.8 | 52.4 | 4.28 | 113 | 2.08 | 41.6 | 162
| 10.5 | 1.97 | 7.38 | 4.47 | 94 | 98 | 104 | 13.3 | 54.7 | 4.47 | 118 | 2.17 | 43.4 | 169
| 10.9 | 2.05 | 7.69 | 4.66 | 98 | 102 | 108 | 13.8 | 57 | 4.66 | 123 | 2.26 | 45.2 | 176
| 11.3 | 2.13 | 8 | 4.85 | 102 | 106 | 112 | 14.3 | 59.3 | 4.85 | 128 | 2.35 | 47 | 183
| 11.7 | 2.21 | 8.31 | 5.04 | 106 | 110 | 116 | 14.8 | 61.6 | 5.04 | 133 | 2.44 | 48.8 | 190
| 12.1 | 2.29 | 8.62 | 5.23 | 110 | 114 | 120 | 15.3 | 63.9 | 5.23 | 138 | 2.53 | 50.6 | 197
| 12.5 | 2.37 | 8.93 | 5.42 | 114 | 118 | 124 | 15.8 | 66.2 | 5.42 | 143 | 2.62 | 52.4 | 204
| 12.9 | 2.45 | 9.24 | 5.61 | 118 | 122 | 128 | 16.3 | 68.5 | 5.61 | 148 | 2.71 | 54.2 | 211
| 13.3 | 2.53 | 9.55 | 5.8 | 122 | 126 | 132 | 16.8 | 70.8 | 5.8 | 153 | 2.8 | 56 | 218
| 13.7 | 2.61 | 9.86 | 5.99 | 126 | 130 | 136 | 17.3 | 73.1 | 5.99 | 158 | 2.89 | 57.8 | 225
| 14.1 | 2.69 | 10.17 | 6.18 | 130 | 134 | 140 | 17.8 | 75.4 | 6.18 | 163 | 2.98 | 59.6 | 232
| 14.5 | 2.77 | 10.48 | 6.37 | 134 | 138 | 144 | 18.3 | 77.7 | 6.37 | 168 | 3.07 | 61.4 | 239
| 14.9 | 2.85 | 10.79 | 6.56 | 138 | 142 | 148 | 18.8 | 80 | 6.56 | 173 | 3.16 | 63.2 | 246
| 15.3 | 2.93 | 11.1 | 6.75 | 142 | 146 | 152 | 19.3 | 82.3 | 6.75 | 178 | 3.25 | 65 | 253
| 15.7 | 3.01 | 11.41 | 6.94 | 146 | 150 | 156 | 19.8 | 84.6 | 6.94 | 183 | 3.34 | 66.8 | 260
| 16.1 | 3.09 | 11.72 | 7.13 | 150 | 154 | 160 | 20.3 | 86.9 | 7.13 | 188 | 3.43 | 68.6 | 267
| 16.5 | 3.17 | 12.03 | 7.32 | 154 | 158 | 164 | 20.8 | 89.2 | 7.32 | 193 | 3.52 | 70.4 | 274
| 16.9 | 3.25 | 12.34 | 7.51 | 158 | 162 | 168 | 21.3 | 91.5 | 7.51 | 198 | 3.61 | 72.2 | 281
| 17.3 | 3.33 | 12.65 | 7.7 | 162 | 166 | 172 | 21.8 | 93.8 | 7.7 | 203 | 3.7 | 74 | 288
| 17.7 | 3.41 | 12.96 | 7.89 | 166 | 170 | 176 | 22.3 | 96.1 | 7.89 | 208 | 3.79 | 75.8 | 295
| 18.1 | 3.49 | 13.27 | 8.08 | 170 | 174 | 180 | 22.8 | 98.4 | 8.08 | 213 | 3.88 | 77.6 | 302
| 18.5 | 3.57 | 13.58 | 8.27 | 174 | 178 | 184 | 23.3 | 100.7 | 8.27 | 218 | 3.97 | 79.4 | 309
| 18.9 | 3.65 | 13.89 | 8.46 | 178 | 182 | 188 | 23.8 | 103 | 8.46 | 223 | 4.06 | 81.2 | 316
| 19.3 | 3.73 | 14.2 | 8.65 | 182 | 186 | 192 | 24.3 | 105.3 | 8.65 | 228 | 4.15 | 83 | 323
| 19.7 | 3.81 | 14.51 | 8.84 | 186 | 190 | 196 | 24.8 | 107.6 | 8.84 | 233 | 4.24 | 84.8 | 330
| 20.1 | 3.89 | 14.82 | 9.03 | 190 | 194 | 200 | 25.3 | 109.9 | 9.03 | 238 | 4.33 | 86.6 | 337
| 20.5 | 3.97 | 15.13 | 9.22 | 194 | 198 | 204 | 25.8 | 112.2 | 9.22 | 243 | 4.42 | 88.4 | 344
| 20.9 | 4.05 | 15.44 | 9.41 | 198 | 202 | 208 | 26.3 | 114.5 | 9.41 | 248 | 4.51 | 90.2 | 351
| 21.3 | 4.13 | 15.75 | 9.6 | 202 | 206 | 212 | 26.8 | 116.8 | 9.6 | 253 | 4.6 | 92 | 358
| 21.7 | 4.21 | 16.06 | 9.79 | 206 | 210 | 216 | 27.3 | 119.1 | 9.79 | 258 | 4.69 | 93.8 | 365
| 22.1 | 4.29 | 16.37 | 9.98 | 210 | 214 | 220 | 27.8 | 121.4 | 9.98 | 263 | 4.78 | 95.6 | 372
| 22.5 | 4.37 | 16.68 | 10.17 | 214 | 218 | 224 | 28.3 | 123.7 | 10.17 | 268 | 4.87 | 97.4 | 379
| 22.9 | 4.45 | 16.99 | 10.36 | 218 | 222 | 228 | 28.8 | 126 | 10.36 | 273 | 4.96 | 99.2 | 386
| 23.3 | 4.53 | 17.3 | 10.55 | 222 | 226 | 232 | 29.3 | 128.3 | 10.55 | 278 | 5.05 | 101 | 393
| 23.7 | 4.61 | 17.61 | 10.74 | 226 | 230 | 236 | 29.8 | 130.6 | 10.74 | 283 | 5.14 | 102.8 | 400
| 24.1 | 4.69 | 17.92 | 10.93 | 230 | 234 | 240 | 30.3 | 132.9 | 10.93 | 288 | 5.23 | 104.6 | 407
| 24.5 | 4.77 | 18.23 | 11.12 | 234 | 238 | 244 | 30.8 | 135.2 | 11.12 | 293 | 5.32 | 106.4 | 414
| 24.9 | 4.85 | 18.54 | 11.31 | 238 | 242 | 248 | 31.3 | 137.5 | 11.31 | 298 | 5.41 | 108.2 | 421
| 25.3 | 4.93 | 18.85 | 11.5 | 242 | 246 | 252 | 31.8 | 139.8 | 11.5 | 303 | 5.5 | 110 | 428
| 25.7 | 5.01 | 19.16 | 11.69 | 246 | 250 | 256 | 32.3 | 142.1 | 11.69 | 308 | 5.59 | 111.8 | 435
| 26.1 | 5.09 | 19.47 | 11.88 | 250 | 254 | 260 | 32.8 | 144.4 | 11.88 | 313 | 5.68 | 113.6 | 442
| 26.5 | 5.17 | 19.78 | 12.07 | 254 | 258 | 264 | 33.3 | 146.7 | 12.07 | 318 | 5.77 | 115.4 | 449
| 26.9 | 5.25 | 20.09 | 12.26 | 258 | 262 | 268 | 33.8 | 149 | 12.26 | 323 | 5.86 | 117.2 | 456
| 27.3 | 5.33 | 20.4 | 12.45 | 262 | 266 | 272 | 34.3 | 151.3 | 12.45 | 328 | 5.95 | 119 | 463
| 27.7 | 5.41 | 20.71 | 12.64 | 266 | 270 | 276 | 34.8 | 153.6 | 12.64 | 333 | 6.04 | 120.8 | 470
| 28.1 | 5.49 | 21.02 | 12.83 | 270 | 274 | 280 | 35.3 | 155.9 | 12.83 | 338 | 6.13 | 122.6 | 477
| 28.5 | 5.57 | 21.33 | 13.02 | 274 | 278 | 284 | 35.8 | 158.2 | 13.02 | 343 | 6.22 | 124.4 | 484
| 28.9 | 5.65 | 21.64 | 13.21 | 278 | 282 | 288 | 36.3 | 160.5 | 13.21 | 348 | 6.31 | 126.2 | 491
| 29.3 | 5.73 | 21.95 | 13.4 | 282 | 286 | 292 | 36.8 | 162.8 | 13.4 | 353 | 6.4 | 128 | 498
| 29.7 | 5.81 | 22.26 | 13.59 | 286 | 290 | 296 | 37.3 | 165.1 | 13.59 | 358 | 6.49 | 129.8 | 505
| 30.1 | 5.89 | 22.57 | 13.78 | 290 | 294 | 300 | 37.8 | 167.4 | 13.78 | 363 | 6.58 | 131.6 | 512
| 30.5 | 5.97 | 22.88 | 13.97 | 294 | 298 | 304 | 38.3 | 169.7 | 13.97 | 368 | 6.67 | 133.4 | 519
| 30.9 | 6.05 | 23.19 | 14.16 | 298 | 302 | 308 | 38.8 | 172 | 14.16 | 373 | 6.76 | 135.2 | 526
| 31.3 | 6.13 | 23.5 | 14.35 | 302 | 306 | 312 | 39.3 | 174.3 | 14.35 | 378 | 6.85 | 137 | 533
| 31.7 | 6.21 | 23.81 | 14.54 | 306 | 310 | 316 | 39.8 | 176.6 | 14.54 | 383 | 6.94 | 138.8 | 540
| 32.1 | 6.29 | 24.12 | 14.73 | 310 | 314 | 320 | 40.3 | 178.9 | 14.73 | 388 | 7.03 | 140.6 | 547
| 32.5 | 6.37 | 24.43 | 14.92 | 314 | 318 | 324 | 40.8 | 181.2 | 14.92 | 393 | 7.12 | 142.4 | 554
| 32.9 | 6.45 | 24.74 | 15.11 | 318 | 322 | 328 | 41.3 | 183.5 | 15.11 | 398 | 7.21 | 144.2 | 561
| 33.3 | 6.53 | 25.05 | 15.3 | 322 | 326 | 332 | 41.8 | 185.8 | 15.3 | 403 | 7.3 | 146 | 568
| 33.7 | 6.61 | 25.36 | 15.49 | 326 | 330 | 336 | 42.3 | 188.1 | 15.49 | 408 | 7.39 | 147.8 | 575
| 34.1 | 6.69 | 25.67 | 15.68 | 330 | 334 | 340 | 42.8 | 190.4 | 15.68 | 413 | 7.48 | 149.6 | 582
| 34.5 | 6.77 | 25.98 | 15.87 | 334 | 338 | 344 | 43.3 | 192.7 | 15.87 | 418 | 7.57 | 151.4 | 589
| 34.9 | 6.85 | 26.29 | 16.06 | 338 | 342 | 348 | 43.8 | 195 | 16.06 | 423 | 7.66 | 153.2 | 596
| 35.3 | 6.93 | 26.6 | 16.25 | 342 | 346 | 352 | 44.3 | 197.3 | 16.25 | 428 | 7.75 | 155 | 603
| 35.7 | 7.01 | 26.91 | 16.44 | 346 | 350 | 356 | 44.8 | 199.6 | 16.44 | 433 | 7.84 | 156.8 | 610
| 36.1 | 7.09 | 27.22 | 16.63 | 350 | 354 | 360 | 45.3 | 201.9 | 16.63 | 438 | 7.93 | 158.6 | 617
| 36.5 | 7.17 | 27.53 | 16.82 | 354 | 358 | 364 | 45.8 | 204.2 | 16.82 | 443 | 8.02 | 160.4 | 624
| 36.9 | 7.25 | 27.84 | 17.01 | 358 | 362 | 368 | 46.3 | 206.5 | 17.01 | 448 | 8.11 | 162.2 | 631
| 37.3 | 7.33 | 28.15 | 17.2 | 362 | 366 | 372 | 46.8 | 208.8 | 17.2 | 453 | 8.2 | 164 | 638
| 37.7 | 7.41 | 28.46 | 17.39 | 366 | 370 | 376 | 47.3 | 211.1 | 17.39 | 458 | 8.29 | 165.8 | 645
| 38.1 | 7.49 | 28.77 | 17.58 | 370 | 374 | 380 | 47.8 | 213.4 | 17.58 | 463 | 8.38 | 167.6 | 652
| 38.5 | 7.57 | 29.08 | 17.77 | 374 | 378 | 384 | 48.3 | 215.7 | 17.77 | 468 | 8.47 | 169.4 | 659
| 38.9 | 7.65 | 29.39 | 17.96 | 378 | 382 | 388 | 48.8 | 218 | 17.96 | 473 | 8.56 | 171.2 | 666
| 39.3 | 7.73 | 29.7 | 18.15 | 382 | 386 | 392 | 49.3 | 220.3 | 18.15 | 478 | 8.65 | 173 | 673
| 39.7 | 7.81 | 30.01 | 18.34 | 386 | 390 | 396 | 49.8 | 222.6 | 18.34 | 483 | 8.74 | 174.8 | 680
| 40.1 | 7.89 | 30.32 | 18.53 | 390 | 394 | 400 | 50.3 | 224.9 | 18.53 | 488 | 8.83 | 176.6 | 687
| 40.5 | 7.97 | 30.63 | 18.72 | 394 | 398 | 404 | 50.8 | 227.2 | 18.72 | 493 | 8.92 | 178.4 | 694
| 40.9 | 8.05 | 30.94 | 18.91 | 398 | 402 | 408 | 51.3 | 229.5 | 18.91 | 498 | 9.01 | 180.2 | 701
| 41.3 | 8.13 | 31.25 | 19.1 | 402 | 406 | 412 | 51.8 | 231.8 | 19.1 | 503 | 9.1 | 182 | 708
| 41.7 | 8.21 | 31.56 | 19.29 | 406 | 410 | 416 | 52.3 | 234.1 | 19.29 | 508 | 9.19 | 183.8 | 715
| 42.1 | 8.29 | 31.87 | 19.48 | 410 | 414 | 420 | 52.8 | 236.4 | 19.48 | 513 | 9.28 | 185.6 | 722
| 0.0063 | 0.0029 | 0.0047 | 0.0621 | 0.6046 | 0.1765 | 0.0617 | 0.0342 | 0.4322 | 0.0043 | 0.8563 | 0.0786 | 0.3187 | 0.3508
| 0.0658 | 0.0568 | 0.0729 | 0.1278 | 0.3333 | 0.5764 | 0.4591 | 0.2949 | 0.4558 | 0.0315 | 0.1394 | 0.2541 | 0.3486 | 0.4271
| 0.2763 | 0.2238 | 0.2266 | 0.2055 | 0 | 0.2116 | 0.3606 | 0.3851 | 0.0874 | 0.1079 | 0 | 0 | 0 | 0.1169
| 0.3598 | 0.3833 | 0.2914 | 0.2292 | 0 | 0.0293 | 0.0969 | 0.2057 | 0.0199 | 0.2144 | 0 | 0.3486 | 0 | 0.0774
| 0.2137 | 0.2388 | 0.2262 | 0.1884 | 0.0516 | 0.0053 | 0.0179 | 0.0619 | 0.0028 | 0.2808 | 0.0039 | 0 | 0.2541 | 0.0112
| 0.0665 | 0.072 | 0.1171 | 0.1189 | 0 | 0.0008 | 0.0029 | 0.0135 | 0.0013 | 0.2247 | 0 | 0.2323 | 0 | 0.01
| 0.0108 | 0.0201 | 0.0424 | 0.0505 | 0 | 0 | 0.0007 | 0.0037 | 0.0005 | 0.1016 | 0 | 0 | 0 | 0.0044
| 0.0008 | 0.0022 | 0.014 | 0.0149 | 0 | 0 | 0.0001 | 0.0007 | 0 | 0.0288 | 0 | 0.0757 | 0 | 0.0011
| 0 | 0 | 0.004 | 0.0025 | 0 | 0.0001 | 0.0001 | 0.0003 | 0 | 0.0056 | 0 | 0 | 0 | 0.0009
| 0 | 0.0001 | 0.0007 | 0.0002 | 0.0105 | 0 | 0 | 0 | 0.0001 | 0.0004 | 0.0004 | 0.0107 | 0.0786 | 0.0002
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1,3 | 0,13 | 0,25 | 0,1 | 2 | 6 | 12 | 1,8 | 1,8 | 0,1 | 3 | 0,1 | 2 | 8
| 1,7 | 0,21 | 0,56 | 0,29 | 6 | 10 | 16 | 2,3 | 4,1 | 0,29 | 8 | 0,19 | 3,8 | 15
| 2,1 | 0,29 | 0,87 | 0,48 | 10 | 14 | 20 | 2,8 | 6,4 | 0,48 | 13 | 0,28 | 5,6 | 22
| 2,5 | 0,37 | 1,18 | 0,67 | 14 | 18 | 24 | 3,3 | 8,7 | 0,67 | 18 | 0,37 | 7,4 | 29
| 2,9 | 0,45 | 1,49 | 0,86 | 18 | 22 | 28 | 3,8 | 11 | 0,86 | 23 | 0,46 | 9,2 | 36
| 3,3 | 0,53 | 1,8 | 1,05 | 22 | 26 | 32 | 4,3 | 13,3 | 1,05 | 28 | 0,55 | 11 | 43
| 3,7 | 0,61 | 2,11 | 1,24 | 26 | 30 | 36 | 4,8 | 15,6 | 1,24 | 33 | 0,64 | 12,8 | 50
| 4,1 | 0,69 | 2,42 | 1,43 | 30 | 34 | 40 | 5,3 | 17,9 | 1,43 | 38 | 0,73 | 14,6 | 57
| 4,5 | 0,77 | 2,73 | 1,62 | 34 | 38 | 44 | 5,8 | 20,2 | 1,62 | 43 | 0,82 | 16,4 | 64
| 4,9 | 0,85 | 3,04 | 1,81 | 38 | 42 | 48 | 6,3 | 22,5 | 1,81 | 48 | 0,91 | 18,2 | 71
| 5,3 | 0,93 | 3,35 | 2 | 42 | 46 | 52 | 6,8 | 24,8 | 2 | 53 | 1 | 20 | 78
| 5,7 | 1,01 | 3,66 | 2,19 | 46 | 50 | 56 | 7,3 | 27,1 | 2,19 | 58 | 1,09 | 21,8 | 85
| 6,1 | 1,09 | 3,97 | 2,38 | 50 | 54 | 60 | 7,8 | 29,4 | 2,38 | 63 | 1,18 | 23,6 | 92
| 6,5 | 1,17 | 4,28 | 2,57 | 54 | 58 | 64 | 8,3 | 31,7 | 2,57 | 68 | 1,27 | 25,4 | 99
| 6,9 | 1,25 | 4,59 | 2,76 | 58 | 62 | 68 | 8,8 | 34 | 2,76 | 73 | 1,36 | 27,2 | 106
| 7,3 | 1,33 | 4,9 | 2,95 | 62 | 66 | 72 | 9,3 | 36,3 | 2,95 | 78 | 1,45 | 29 | 113
| 7,7 | 1,41 | 5,21 | 3,14 | 66 | 70 | 76 | 9,8 | 38,6 | 3,14 | 83 | 1,54 | 30,8 | 120
| 8,1 | 1,49 | 5,52 | 3,33 | 70 | 74 | 80 | 10,3 | 40,9 | 3,33 | 88 | 1,63 | 32,6 | 127
| 8,5 | 1,57 | 5,83 | 3,52 | 74 | 78 | 84 | 10,8 | 43,2 | 3,52 | 93 | 1,72 | 34,4 | 134
| 8,9 | 1,65 | 6,14 | 3,71 | 78 | 82 | 88 | 11,3 | 45,5 | 3,71 | 98 | 1,81 | 36,2 | 141
| 9,3 | 1,73 | 6,45 | 3,9 | 82 | 86 | 92 | 11,8 | 47,8 | 3,9 | 103 | 1,9 | 38 | 148
| 9,7 | 1,81 | 6,76 | 4,09 | 86 | 90 | 96 | 12,3 | 50,1 | 4,09 | 108 | 1,99 | 39,8 | 155
| 10,1 | 1,89 | 7,07 | 4,28 | 90 | 94 | 100 | 12,8 | 52,4 | 4,28 | 113 | 2,08 | 41,6 | 162
| 10,5 | 1,97 | 7,38 | 4,47 | 94 | 98 | 104 | 13,3 | 54,7 | 4,47 | 118 | 2,17 | 43,4 | 169
| 10,9 | 2,05 | 7,69 | 4,66 | 98 | 102 | 108 | 13,8 | 57 | 4,66 | 123 | 2,26 | 45,2 | 176
| 11,3 | 2,13 | 8 | 4,85 | 102 | 106 | 112 | 14,3 | 59,3 | 4,85 | 128 | 2,35 | 47 | 183
| 11,7 | 2,21 | 8,31 | 5,04 | 106 | 110 | 116 | 14,8 | 61,6 | 5,04 | 133 | 2,44 | 48,8 | 190
| 12,1 | 2,29 | 8,62 | 5,23 | 110 | 114 | 120 | 15,3 | 63,9 | 5,23 | 138 | 2,53 | 50,6 | 197
| 12,5 | 2,37 | 8,93 | 5,42 | 114 | 118 | 124 | 15,8 | 66,2 | 5,42 | 143 | 2,62 | 52,4 | 204
| 12,9 | 2,45 | 9,24 | 5,61 | 118 | 122 | 128 | 16,3 | 68,5 | 5,61 | 148 | 2,71 | 54,2 | 211
| 13,3 | 2,53 | 9,55 | 5,8 | 122 | 126 | 132 | 16,8 | 70,8 | 5,8 | 153 | 2,8 | 56 | 218
| 13,7 | 2,61 | 9,86 | 5,99 | 126 | 130 | 136 | 17,3 | 73,1 | 5,99 | 158 | 2,89 | 57,8 | 225
| 14,1 | 2,69 | 10,17 | 6,18 | 130 | 134 | 140 | 17,8 | 75,4 | 6,18 | 163 | 2,98 | 59,6 | 232
| 14,5 | 2,77 | 10,48 | 6,37 | 134 | 138 | 144 | 18,3 | 77,7 | 6,37 | 168 | 3,07 | 61,4 | 239
| 14,9 | 2,85 | 10,79 | 6,56 | 138 | 142 | 148 | 18,8 | 80 | 6,56 | 173 | 3,16 | 63,2 | 246
| 15,3 | 2,93 | 11,1 | 6,75 | 142 | 146 | 152 | 19,3 | 82,3 | 6,75 | 178 | 3,25 | 65 | 253
| 15,7 | 3,01 | 11,41 | 6,94 | 146 | 150 | 156 | 19,8 | 84,6 | 6,94 | 183 | 3,34 | 66,8 | 260
| 16,1 | 3,09 | 11,72 | 7,13 | 150 | 154 | 160 | 20,3 | 86,9 | 7,13 | 188 | 3,43 | 68,6 | 267
| 16,5 | 3,17 | 12,03 | 7,32 | 154 | 158 | 164 | 20,8 | 89,2 | 7,32 | 193 | 3,52 | 70,4 | 274
| 16,9 | 3,25 | 12,34 | 7,51 | 158 | 162 | 168 | 21,3 | 91,5 | 7,51 | 198 | 3,61 | 72,2 | 281
| 17,3 | 3,33 | 12,65 | 7,7 | 162 | 166 | 172 | 21,8 | 93,8 | 7,7 | 203 | 3,7 | 74 | 288
| 17,7 | 3,41 | 12,96 | 7,89 | 166 | 170 | 176 | 22,3 | 96,1 | 7,89 | 208 | 3,79 | 75,8 | 295
| 18,1 | 3,49 | 13,27 | 8,08 | 170 | 174 | 180 | 22,8 | 98,4 | 8,08 | 213 | 3,88 | 77,6 | 302
| 18,5 | 3,57 | 13,58 | 8,27 | 174 | 178 | 184 | 23,3 | 100,7 | 8,27 | 218 | 3,97 | 79,4 | 309
| 18,9 | 3,65 | 13,89 | 8,46 | 178 | 182 | 188 | 23,8 | 103 | 8,46 | 223 | 4,06 | 81,2 | 316
| 19,3 | 3,73 | 14,2 | 8,65 | 182 | 186 | 192 | 24,3 | 105,3 | 8,65 | 228 | 4,15 | 83 | 323
| 19,7 | 3,81 | 14,51 | 8,84 | 186 | 190 | 196 | 24,8 | 107,6 | 8,84 | 233 | 4,24 | 84,8 | 330
| 20,1 | 3,89 | 14,82 | 9,03 | 190 | 194 | 200 | 25,3 | 109,9 | 9,03 | 238 | 4,33 | 86,6 | 337
| 20,5 | 3,97 | 15,13 | 9,22 | 194 | 198 | 204 | 25,8 | 112,2 | 9,22 | 243 | 4,42 | 88,4 | 344
| 20,9 | 4,05 | 15,44 | 9,41 | 198 | 202 | 208 | 26,3 | 114,5 | 9,41 | 248 | 4,51 | 90,2 | 351
| 21,3 | 4,13 | 15,75 | 9,6 | 202 | 206 | 212 | 26,8 | 116,8 | 9,6 | 253 | 4,6 | 92 | 358
| 21,7 | 4,21 | 16,06 | 9,79 | 206 | 210 | 216 | 27,3 | 119,1 | 9,79 | 258 | 4,69 | 93,8 | 365
| 22,1 | 4,29 | 16,37 | 9,98 | 210 | 214 | 220 | 27,8 | 121,4 | 9,98 | 263 | 4,78 | 95,6 | 372
| 22,5 | 4,37 | 16,68 | 10,17 | 214 | 218 | 224 | 28,3 | 123,7 | 10,17 | 268 | 4,87 | 97,4 | 379
| 22,9 | 4,45 | 16,99 | 10,36 | 218 | 222 | 228 | 28,8 | 126 | 10,36 | 273 | 4,96 | 99,2 | 386
| 23,3 | 4,53 | 17,3 | 10,55 | 222 | 226 | 232 | 29,3 | 128,3 | 10,55 | 278 | 5,05 | 101 | 393
| 23,7 | 4,61 | 17,61 | 10,74 | 226 | 230 | 236 | 29,8 | 130,6 | 10,74 | 283 | 5,14 | 102,8 | 400
| 24,1 | 4,69 | 17,92 | 10,93 | 230 | 234 | 240 | 30,3 | 132,9 | 10,93 | 288 | 5,23 | 104,6 | 407
| 24,5 | 4,77 | 18,23 | 11,12 | 234 | 238 | 244 | 30,8 | 135,2 | 11,12 | 293 | 5,32 | 106,4 | 414
| 24,9 | 4,85 | 18,54 | 11,31 | 238 | 242 | 248 | 31,3 | 137,5 | 11,31 | 298 | 5,41 | 108,2 | 421
| 25,3 | 4,93 | 18,85 | 11,5 | 242 | 246 | 252 | 31,8 | 139,8 | 11,5 | 303 | 5,5 | 110 | 428
| 25,7 | 5,01 | 19,16 | 11,69 | 246 | 250 | 256 | 32,3 | 142,1 | 11,69 | 308 | 5,59 | 111,8 | 435
| 26,1 | 5,09 | 19,47 | 11,88 | 250 | 254 | 260 | 32,8 | 144,4 | 11,88 | 313 | 5,68 | 113,6 | 442
| 26,5 | 5,17 | 19,78 | 12,07 | 254 | 258 | 264 | 33,3 | 146,7 | 12,07 | 318 | 5,77 | 115,4 | 449
| 26,9 | 5,25 | 20,09 | 12,26 | 258 | 262 | 268 | 33,8 | 149 | 12,26 | 323 | 5,86 | 117,2 | 456
| 27,3 | 5,33 | 20,4 | 12,45 | 262 | 266 | 272 | 34,3 | 151,3 | 12,45 | 328 | 5,95 | 119 | 463
| 27,7 | 5,41 | 20,71 | 12,64 | 266 | 270 | 276 | 34,8 | 153,6 | 12,64 | 333 | 6,04 | 120,8 | 470
| 28,1 | 5,49 | 21,02 | 12,83 | 270 | 274 | 280 | 35,3 | 155,9 | 12,83 | 338 | 6,13 | 122,6 | 477
| 28,5 | 5,57 | 21,33 | 13,02 | 274 | 278 | 284 | 35,8 | 158,2 | 13,02 | 343 | 6,22 | 124,4 | 484
| 28,9 | 5,65 | 21,64 | 13,21 | 278 | 282 | 288 | 36,3 | 160,5 | 13,21 | 348 | 6,31 | 126,2 | 491
| 29,3 | 5,73 | 21,95 | 13,4 | 282 | 286 | 292 | 36,8 | 162,8 | 13,4 | 353 | 6,4 | 128 | 498
| 29,7 | 5,81 | 22,26 | 13,59 | 286 | 290 | 296 | 37,3 | 165,1 | 13,59 | 358 | 6,49 | 129,8 | 505
| 30,1 | 5,89 | 22,57 | 13,78 | 290 | 294 | 300 | 37,8 | 167,4 | 13,78 | 363 | 6,58 | 131,6 | 512
| 30,5 | 5,97 | 22,88 | 13,97 | 294 | 298 | 304 | 38,3 | 169,7 | 13,97 | 368 | 6,67 | 133,4 | 519
| 30,9 | 6,05 | 23,19 | 14,16 | 298 | 302 | 308 | 38,8 | 172 | 14,16 | 373 | 6,76 | 135,2 | 526
| 31,3 | 6,13 | 23,5 | 14,35 | 302 | 306 | 312 | 39,3 | 174,3 | 14,35 | 378 | 6,85 | 137 | 533
| 31,7 | 6,21 | 23,81 | 14,54 | 306 | 310 | 316 | 39,8 | 176,6 | 14,54 | 383 | 6,94 | 138,8 | 540
| 32,1 | 6,29 | 24,12 | 14,73 | 310 | 314 | 320 | 40,3 | 178,9 | 14,73 | 388 | 7,03 | 140,6 | 547
| 32,5 | 6,37 | 24,43 | 14,92 | 314 | 318 | 324 | 40,8 | 181,2 | 14,92 | 393 | 7,12 | 142,4 | 554
| 32,9 | 6,45 | 24,74 | 15,11 | 318 | 322 | 328 | 41,3 | 183,5 | 15,11 | 398 | 7,21 | 144,2 | 561
| 33,3 | 6,53 | 25,05 | 15,3 | 322 | 326 | 332 | 41,8 | 185,8 | 15,3 | 403 | 7,3 | 146 | 568
| 33,7 | 6,61 | 25,36 | 15,49 | 326 | 330 | 336 | 42,3 | 188,1 | 15,49 | 408 | 7,39 | 147,8 | 575
| 34,1 | 6,69 | 25,67 | 15,68 | 330 | 334 | 340 | 42,8 | 190,4 | 15,68 | 413 | 7,48 | 149,6 | 582
| 34,5 | 6,77 | 25,98 | 15,87 | 334 | 338 | 344 | 43,3 | 192,7 | 15,87 | 418 | 7,57 | 151,4 | 589
| 34,9 | 6,85 | 26,29 | 16,06 | 338 | 342 | 348 | 43,8 | 195 | 16,06 | 423 | 7,66 | 153,2 | 596
| 35,3 | 6,93 | 26,6 | 16,25 | 342 | 346 | 352 | 44,3 | 197,3 | 16,25 | 428 | 7,75 | 155 | 603
| 35,7 | 7,01 | 26,91 | 16,44 | 346 | 350 | 356 | 44,8 | 199,6 | 16,44 | 433 | 7,84 | 156,8 | 610
| 36,1 | 7,09 | 27,22 | 16,63 | 350 | 354 | 360 | 45,3 | 201,9 | 16,63 | 438 | 7,93 | 158,6 | 617
| 36,5 | 7,17 | 27,53 | 16,82 | 354 | 358 | 364 | 45,8 | 204,2 | 16,82 | 443 | 8,02 | 160,4 | 624
| 36,9 | 7,25 | 27,84 | 17,01 | 358 | 362 | 368 | 46,3 | 206,5 | 17,01 | 448 | 8,11 | 162,2 | 631
| 37,3 | 7,33 | 28,15 | 17,2 | 362 | 366 | 372 | 46,8 | 208,8 | 17,2 | 453 | 8,2 | 164 | 638
| 37,7 | 7,41 | 28,46 | 17,39 | 366 | 370 | 376 | 47,3 | 211,1 | 17,39 | 458 | 8,29 | 165,8 | 645
| 38,1 | 7,49 | 28,77 | 17,58 | 370 | 374 | 380 | 47,8 | 213,4 | 17,58 | 463 | 8,38 | 167,6 | 652
| 38,5 | 7,57 | 29,08 | 17,77 | 374 | 378 | 384 | 48,3 | 215,7 | 17,77 | 468 | 8,47 | 169,4 | 659
| 38,9 | 7,65 | 29,39 | 17,96 | 378 | 382 | 388 | 48,8 | 218 | 17,96 | 473 | 8,56 | 171,2 | 666
| 39,3 | 7,73 | 29,7 | 18,15 | 382 | 386 | 392 | 49,3 | 220,3 | 18,15 | 478 | 8,65 | 173 | 673
| 39,7 | 7,81 | 30,01 | 18,34 | 386 | 390 | 396 | 49,8 | 222,6 | 18,34 | 483 | 8,74 | 174,8 | 680
| 40,1 | 7,89 | 30,32 | 18,53 | 390 | 394 | 400 | 50,3 | 224,9 | 18,53 | 488 | 8,83 | 176,6 | 687
| 40,5 | 7,97 | 30,63 | 18,72 | 394 | 398 | 404 | 50,8 | 227,2 | 18,72 | 493 | 8,92 | 178,4 | 694
| 40,9 | 8,05 | 30,94 | 18,91 | 398 | 402 | 408 | 51,3 | 229,5 | 18,91 | 498 | 9,01 | 180,2 | 701
| 41,3 | 8,13 | 31,25 | 19,1 | 402 | 406 | 412 | 51,8 | 231,8 | 19,1 | 503 | 9,1 | 182 | 708
| 41,7 | 8,21 | 31,56 | 19,29 | 406 | 410 | 416 | 52,3 | 234,1 | 19,29 | 508 | 9,19 | 183,8 | 715
0.001 | [6 empty] | 13.4222 | [6 empty] | 8.9286
0.004 | [6 empty] | 13.9004 | [6 empty] | 9.4048
0.007 | [6 empty] | 14.3095 | [6 empty] | 9.7917
0.01 | [6 empty] | 14.5289 | [6 empty] | 10
0.02 | [6 empty] | 15.0164 | [6 empty] | 10.3571
0.03 | [6 empty] | 15.3232 | [6 empty] | 10.8333
0.04 | [6 empty] | 15.5959 | [6 empty] | 10.9048
0.05 | [6 empty] | 15.8199 | [6 empty] | 11.4286
0.06 | [6 empty] | 15.969 | [6 empty] | 11.5
0.07 | [6 empty] | 16.1599 | [6 empty] | 11.6667
0.08 | [6 empty] | 16.3262 | [6 empty] | 11.7778
0.09 | [6 empty] | 16.449 | [6 empty] | 11.9048
0.1 | [6 empty] | 16.5733 | [6 empty] | 12.125
0.11 | [6 empty] | 16.6941 | [6 empty] | 12.3333
0.12 | [6 empty] | 16.8318 | [6 empty] | 12.5
0.13 | [6 empty] | 16.9361 | [6 empty] | 12.5
0.14 | [6 empty] | 17.0493 | [6 empty] | 12.5
0.15 | [6 empty] | 17.1562 | [6 empty] | 12.75
0.16 | [6 empty] | 17.2384 | [6 empty] | 12.9167
0.17 | [6 empty] | 17.3336 | [6 empty] | 13.1667
0.18 | [6 empty] | 17.4272 | [6 empty] | 13.1667
0.19 | [6 empty] | 17.5027 | [6 empty] | 13.3333
0.2 | [6 empty] | 17.598 | [6 empty] | 13.3333
0.21 | [6 empty] | 17.6795 | [6 empty] | 13.3333
0.22 | [6 empty] | 17.7659 | [6 empty] | 13.5714
0.23 | [6 empty] | 17.8467 | [6 empty] | 13.5833
0.24 | [6 empty] | 17.9277 | [6 empty] | 13.5833
0.25 | [6 empty] | 18.0184 | [6 empty] | 14
0.26 | [6 empty] | 18.0899 | [6 empty] | 14
0.27 | [6 empty] | 18.1625 | [6 empty] | 14.1667
0.28 | [6 empty] | 18.2484 | [6 empty] | 14.1667
0.29 | [6 empty] | 18.3194 | [6 empty] | 14.1667
0.3 | [6 empty] | 18.4014 | [6 empty] | 14.1667
0.31 | [6 empty] | 18.469 | [6 empty] | 14.5833
0.32 | [6 empty] | 18.5523 | [6 empty] | 14.5833
0.33 | [6 empty] | 18.6308 | [6 empty] | 14.8196
0.34 | [6 empty] | 18.7111 | [6 empty] | 15
0.35 | [6 empty] | 18.779 | [6 empty] | 15
0.36 | [6 empty] | 18.8528 | [6 empty] | 15
0.37 | [6 empty] | 18.9169 | [6 empty] | 15.2381
0.38 | [6 empty] | 18.9872 | [6 empty] | 15.25
0.39 | [6 empty] | 19.0506 | [6 empty] | 15.25
0.4 | [6 empty] | 19.1097 | [6 empty] | 15.8333
0.41 | [6 empty] | 19.1901 | [6 empty] | 15.8333
0.42 | [6 empty] | 19.2649 | [6 empty] | 16.0714
0.43 | [6 empty] | 19.3403 | [6 empty] | 16.25
0.44 | [6 empty] | 19.4105 | [6 empty] | 16.25
0.45 | [6 empty] | 19.479 | [6 empty] | 16.25
0.46 | [6 empty] | 19.5507 | [6 empty] | 16.6667
0.47 | [6 empty] | 19.631 | [6 empty] | 16.6667
0.48 | [6 empty] | 19.6954 | [6 empty] | 16.6667
0.49 | [6 empty] | 19.7732 | [6 empty] | 16.9048
0.5 | [6 empty] | 19.8498 | [6 empty] | 17.3333
0.51 | [6 empty] | 19.9167 | [6 empty] | 17.5
0.52 | [6 empty] | 19.9959 | [6 empty] | 17.5
0.53 | [6 empty] | 20.0681 | [6 empty] | 17.8571
0.54 | [6 empty] | 20.1446 | [6 empty] | 17.9167
0.55 | [6 empty] | 20.2185 | [6 empty] | 18.1667
0.56 | [6 empty] | 20.2993 | [6 empty] | 18.1667
0.57 | [6 empty] | 20.3675 | [6 empty] | 18.3333
0.58 | [6 empty] | 20.449 | [6 empty] | 18.3333
0.59 | [6 empty] | 20.5297 | [6 empty] | 18.3333
0.6 | [6 empty] | 20.6259 | [6 empty] | 18.5714
0.61 | [6 empty] | 20.7164 | [6 empty] | 19
0.62 | [6 empty] | 20.7997 | [6 empty] | 19.1071
0.63 | [6 empty] | 20.8766 | [6 empty] | 19.1667
0.64 | [6 empty] | 20.9751 | [6 empty] | 19.1667
0.65 | [6 empty] | 21.0557 | [6 empty] | 19.5833
0.66 | [6 empty] | 21.146 | [6 empty] | 19.7917
0.67 | [6 empty] | 21.2406 | [6 empty] | 20
0.68 | [6 empty] | 21.3272 | [6 empty] | 20
0.69 | [6 empty] | 21.4213 | [6 empty] | 20
0.7 | [6 empty] | 21.5235 | [6 empty] | 20.2381
0.71 | [6 empty] | 21.5982 | [6 empty] | 20.25
0.72 | [6 empty] | 21.6999 | [6 empty] | 20.8333
0.73 | [6 empty] | 21.8139 | [6 empty] | 20.8333
0.74 | [6 empty] | 21.908 | [6 empty] | 21.25
0.75 | [6 empty] | 22.0103 | [6 empty] | 21.25
0.76 | [6 empty] | 22.1443 | [6 empty] | 21.6667
0.77 | [6 empty] | 22.2673 | [6 empty] | 21.6667
0.78 | [6 empty] | 22.3769 | [6 empty] | 22.3333
0.79 | [6 empty] | 22.495 | [6 empty] | 22.9167
0.8 | [6 empty] | 22.6366 | [6 empty] | 23.3333
0.81 | [6 empty] | 22.7994 | [6 empty] | 23.3333
0.82 | [6 empty] | 22.944 | [6 empty] | 24.1667
0.83 | [6 empty] | 23.0917 | [6 empty] | 25
0.84 | [6 empty] | 23.2676 | [6 empty] | 25
0.85 | [6 empty] | 23.4201 | [6 empty] | 26.25
0.86 | [6 empty] | 23.6222 | [6 empty] | 27
0.87 | [6 empty] | 23.8039 | [6 empty] | 27.5714
0.88 | [6 empty] | 23.9772 | [6 empty] | 28.3333
0.89 | [6 empty] | 24.1915 | [6 empty] | 28.7775
0.9 | [6 empty] | 24.4209 | [6 empty] | 29.1667
0.91 | [6 empty] | 24.6517 | [6 empty] | 29.5833
0.92 | [6 empty] | 24.963 | [6 empty] | 30
0.93 | [6 empty] | 25.3195 | [6 empty] | 31.1946
0.94 | [6 empty] | 25.6739 | [6 empty] | 31.6667
0.95 | [6 empty] | 26.1188 | [6 empty] | 32.9167
0.96 | [6 empty] | 26.5702 | [6 empty] | 34.1667
0.97 | [6 empty] | 27.2372 | [6 empty] | 35
0.98 | [6 empty] | 28.1885 | [6 empty] | 38.3333
0.99 | [6 empty] | 29.7553 | [6 empty] | 48.3333
0.993 | [6 empty] | 30.7655 | [6 empty] | 50
0.996 | [6 empty] | 31.8404 | [6 empty] | 54.1667
0.999 | [6 empty] | 35.0935 | [6 empty] | 64.1667